## Data
Project Attributes | [13 empty] | Dates
Project Name | Applicant(s) | Application No. | Filed Under | Federal Involvement | Permit Type | Applicant's Environmental Filing Type | CEQA Document Type | NEPA Document Type | Voltage(s) | Miles or Acreage | Competively Bid or Non-Competitively Bid | CAISO Approval Year | Expected In-Service Date | CAISO Award Date | 12-Month Notice Date | Date MOU Executed | Date Contractor Selected | Date Contract Executed | Pre-Filing Date | File Date | Deficiency Letter 1 Date | Deficiency Letter 1 Response Date | Deficiency Letter 1 Topic(s) | Deficiency Letter 2 Date | Deficiency Letter 2 Response Date | Deficiency Letter 2 Topic(s) | Deficiency Letter 3 Date | Deficiency Letter 3 Response Date | Deficiency Letter 3 Topic(s) | Date Deemed Complete | Amendment 1 File Date(s) | Amendment 2 File Date | Amendment 3 File Date | Data Request 1 Date | Data Request 1 Response Date | Data Request 1 Topic(s) | Data Request 2 Date | Data Request 2 Response Date | Data Request 2 Topic(s) | Data Request 3 Date | Data Request 3 Response Date | Data Request 3 Topic(s) | Data Request 4 Date | Data Request 4 Response Date | Data Request 4 Topic(s) | Data Request 5 Date | Data Request 5 Response Date | Data Request 5 Topic(s) | Data Request 6 Date | Data Request 6 Response Date | Data Request 6 Topic(s) | Data Request 7 Date | Data Request 7 Response Date | Data Request 7 Topic(s) | Data Request 8 Date | Data Request 8 Response Date | Data Request 8 Topic(s) | Public Draft CEQA Document Date | Final CEQA Document Date | Prehearing Conference Date | Proposed Decision Date | Final Decision Date | Construction Start Date | NEPA - Lead Agency | NEPA - Lead Agency File Date | NEPA - NOI Date (if EIS) | NEPA - Public Draft NEPA Document Date | NEPA - NHPA Section 106 Completion Date | NEPA - ESA Consultation Completion Date | NEPA - FONSI Date (if EA) | NEPA - Record of Decision Date (if EIS)
Gorman-Kern River TLRR Project | Southern California Edison (SCE) | A.22-02-014 | GO 131-D | Yes | PTC | PEA | IS/MND | N/A | 66 kV | 65.3 miles | Non-Competitively Bid | N/A | Q3 2029 | N/A | 2017-05-04 | 2020-06-28 | 2019-10-14 | 2019-12-06 | 2021-07-16 | 2022-02-28 | 2022-03-29 | 2022-09-20 | Details on project description needed, gaps in cultural inventory survey areas & findings | 2022-04-29 | 2022-08-02 | Continued comments on cultural analysis | 2022-10-31 | 2022-12-01 | Continued comment on response to Deficiency Letter #1 | 2023-09-20 |  |  |  | 2023-02-13 | 2023-03-22 | Environmental information | 2023-04-10 | 2023-07-19 | Environmental information, Environmental analysis methodology | 2023-06-08 | 2023-06-22 | Project description information, environmental information | 2023-07-05 | 2023-08-09 | Environmental analysis methodology | 2023-09-15 | 2024-04-15 | Environmental information | 2023-12-21 | 2024-01-19 | Project description information, environmental information | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2025-03-27 | 2025-05-20 | 2025-09-19 | 2025-10-30 |  | USFS | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Manning 500/230 kV Substation Project | LS Power Grid California (LSPGC) | A.24-06-017 | GO 131-D | No | CPCN | PEA | IS/MND | N/A | 230 kV, 500 kV | 11.5 miles | Competitively Bid | 2022 | 2028-06-01 | 2023-01-23 | 2023-02-14 | 2023-05-15 | 2023-03-27 | 2023-06-27 | 2024-01-31 | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | N/A | N/A | N/A | 2024-07-24 | 2024-09-20 | Project description information, Environmental information, Environmental analysis methodology | 2025-02-27 | 2025-03-03 | Environmental information | 2025-05-17 | 2025-05-23 | Environmental information | 2025-05-30 | 2025-06-05 | Environmental information | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-06-21 | 2025-05-14 | 2025-09-08 | 2025-09-18 | 2026-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Plainfield Substation Upgrade Project | Pacific Gas & Electric (PG&E) | A.24-06-008 | GO 131-D | No | PTC | PEA | IS/MND | N/A | 60 kV | 6.1 acres | Non-Competitively Bid | 2011 | 2027-07-01 | 2011-05-11 | 2023-02-03 | 2023-04-07 | 2023-02-05 | 2023-06-12 | 2023-12-01 | 2024-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | N/A | N/A | N/A | 2024-07-17 | 2024-08-02 | Project description information, Environmental information, Environmental analysis methodology, Data | 2024-12-04 | 2024-12-12 | Project description information | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-07-08 | 2025-06-12 | 2025-11-10 | 2025-11-20 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Power the South Bay Project | LS Power Grid California (LSPGC) | A.24-05-014 | GO 131-D | No | CPCN | PEA | EIR | N/A | 230 kV | 12 miles | Competitively Bid | 2022 | 2028-06-01 | 2023-03-27 | 2023-03-28 | 2023-09-14 | 2023-05-26 | 2023-09-18 | 2024-02-21 | 2024-05-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2025-02-28 | N/A | N/A | 2024-06-13 | 2024-07-10 | Project description information, Environmental information, Environmental analysis methodology, Data | 2024-12-12 | 2024-12-20 | Project description information, environmental information | 2025-01-01 | 2025-01-15 | Project description information, environmental information | 2025-03-26 | 2025-04-21 | APSA | 2025-05-02 | 2025-05-23 | Environmental information | 2025-07-31 | 2025-08-19 | Project description information | 2025-08-28 | 2025-09-18 | Project description information, Consultation | 2025-10-10 | 2025-10-13 | Project description information, environmental information, Consultation | 2025-06-09 | 2025-12-12 | 2025-12-22 | 2025-03-09 | 2026-03-19 | 2026-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ironwood Transmission Line Project | Horizon West Transmission (HWT) | A.25-09-008 | GO 131-E | Yes | CPCN | PEA | EIR | EIS | 500 kV | 86 miles | Competitively Bid | 2023 | 2032-06-01 | 2024-04-11 | 2024-07-29 | 2025-01-14 | 2024-09-06 | 2025-01-03 | 2025-02-14 | 2025-09-22 | 2025-10-22 | 2026-01-21 | Project description information, Environmental information, Environmental analysis methodology, Data | [6 empty] | 2026-03-10 | [33 empty] | BLM | 2025-03-14 |  |  |  |  | N/A
Orange Regional Transmission Project | Southern California Edison (SCE) | TBD | GO 131-E | No | CPCN | Admin Draft | EIR (expected) | N/A | 500 kV | 30 miles | Competitively Bid | 2023 | 2034-06-01 | 2024-05-31 | 2025-06-17 | 2025-11-21 | 2025-06-17 | 2025-11-07 | 2026-05-12 |  | N/A | [42 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Suncrest 230 kV Loop-in Project | San Diego Gas & Electric (SDG&E) | A.26-05-005 | GO 131-E | Yes | PTC | Admin Draft | EIR | TBD | 230 kV | 16 miles | Non-Competitively Bid | 2023 | 2032 | 2023-05-22 | 2025-01-31 | 2025-07-02 | 2025-03-03 | 2025-06-26 | 2025-06-18 | 2026-05-08 | N/A | [8 empty] | 2026-06-04 | [33 empty] | USFS | 2025-10-02 | N/A |  |  |  |  | N/A
Timepiece 115/33 kV Substation Project | Southern California Edison (SCE) | TBD | GO 131-E | No | PTC | Admin Draft | IS/MND (expected) | N/A | 115 kV, 33 kV | TBD | Non-Competitively Bid | N/A | Q2 2030 | N/A | 2025-06-16 |  | 2025-12-08 | 2026-04-29 |  |  | N/A | [42 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Metrics (Detailed)
Performance Metrics (Detailed)
Project Name | Time from CAISO Award to 12-Month Notice (days) | Time from 12-Month Notice to Pre-Filing Date (days) | Pre-Filing Time to Date (days) | Contract Execution Time (days) | Number of Deficiency Letters | Deficiency Letter Response Time (Average) | Deficiency Letter Response Time (Total) (days) | Number of Data Requests | Data Request Response Time (Average) (days) | Data Request Response Time (Total) (days) | Time to Release Public Draft (days) | Number of Public Comments | Time from Draft CEQA to PHC | Time from Final CEQA to Final Decision | Time from PHC to Final Decision | Time from NEPA Filing to NHPA Completion | Time from NEPA Filing to ESA Completion | Time from NEPA Filing to FONSI or Record of Decision
Gorman-Kern River TLRR Project | N/A | 1534 | 227 | 53 | 3 | 175 | 301 | 6 | 71.3333 | 428 | 429 | 18 | 179 | 217 | 163 | N/A | N/A | N/A
Manning 500/230 kV Substation Project | 22 | 351 | 149 | 92 | 0 | N/A | N/A | 4 | 18.5 | 74 | 238 | 5 | 56 | 89 | 127 | N/A | N/A | N/A
Plainfield Substation Project | 4286 | 301 | 200 | 127 | 0 | N/A | N/A | 2 | 12 | 24 | 266 | 4 | 64 | 135 | 161 | N/A | N/A | N/A
Power the South Bay Project | 1 | 330 | 86 | 115 | 0 | N/A | N/A | 8 | 17.375 | 139 | 361 | 12 | 196 | 97 | 87 | N/A | N/A | N/A
Ironwood Transmission Line Project | 109 | 200 | 220 | 119 | 1 | 91 | 91 | 0 | N/A | N/A | In progress | TBD | In progress | In progress | In progress | In progress | In progress | In progress
Orange Regional Transmission Project | 382 | 329 | 140 | 143 | 0 | N/A | N/A | 0 | N/A | N/A | In progress | TBD | In progress | In progress | In progress | N/A | N/A | N/A
Suncrest 230 kV Loop-in Project | 620 | 138 | 324 | 115 | 0 | N/A | N/A | 0 | N/A | N/A | In progress | TBD | In progress | In progress | In progress | In progress | In progress | In progress
Timepiece 115/33 kV Substation Project | N/A | TBD | TBD | 142 | 0 | N/A | N/A | 0 | N/A | N/A | In progress | TBD | In progress | In progress | In progress | N/A | N/A | N/A

## Metrics (High-Level)
Performance Metrics (High-Level)
Project Name | Applicant(s) | Application No. | Permit Type | CEQA Document Type | Filed Under | Federal Involvement | Clock: Pre-Filing Time to Date | Clock: Total Time to Deem Application Complete | Clock: Total CEQA Time | Clock: Total CPUC Permit Time | Clock: Total NEPA Time | Number of Deficiency Letters | Number of Data Requests | Number of Amendments | Status
Gorman-Kern River TLRR Project | Southern California Edison (SCE) | A.22-02-014 | PTC | IS/MND | GO 131-D | Yes | 227 | 569 | 554 | 771 | TBD | 3 | 6 | 0 | Approved
Manning 500/230 kV Substation Project | LS Power Grid California (LSPGC) | A.24-06-017 | CPCN | IS/MND | GO 131-D | No | 149 | 26 | 332 | 421 | N/A | 0 | 4 | 0 | Approved
Plainfield Substation Project | Pacific Gas & Electric (PG&E) | A.24-06-008 | PTC | IS/MND | GO 131-D | No | 200 | 29 | 356 | 491 | N/A | 0 | 2 | 0 | Approved
Power the South Bay Project | LS Power Grid California (LSPGC) | A.24-05-014 | CPCN | EIR | GO 131-D | No | 86 | 27 | 547 | 644 | N/A | 0 | 8 | 1 | Approved
Ironwood Transmission Line Project | Horizon West Transmission (HWT) | A.25-09-008 | CPCN | EIR | GO 131-E | Yes | 220 | 169 | 203 | 203 | 564 | 1 | 0 | 0 | Draft Document Preparation
Orange Regional Transmission Project | Southern California Edison (SCE) | TBD | CPCN | EIR (expected) | GO 131-E | No | 140 | TBD | TBD | TBD | N/A | 0 | 0 | 0 | Pending
Suncrest 230 kV Loop-in Project | San Diego Gas & Electric (SDG&E) | A.26-05-005 | PTC | EIR | GO 131-E | Yes | 324 | 27 | 117 | 117 | 362 | 0 | 0 | 0 | Draft Document Preparation
Timepiece 115/33 kV Substation Project | Southern California Edison (SCE) | TBD | PTC | IS/MND (expected) | GO 131-E | No | TBD | TBD | TBD | TBD | N/A | 0 | 0 | 0 | Pending