| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 914.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 238.1 | 238.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2025-01-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2474.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-26 | 14 | 10 | 2024-11-26 | 2024-11-26 | 1 | 1 | 2024-11-26 | Unknown | Unknown | Unknown | 2024-11-26 | 2025-01-07 | 43 | 31 | 2024-11-26 | 2025-01-03 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 21750 | 21750 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-04 | 2023-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 120241 | 50684.29 | Unknown | Unknown | Yes | N/A | N/A | 2021-08-04 | 2023-01-31 | 546 | 390 | 2023-01-31 | 2023-12-13 | 317 | 227 | 2023-06-22 | 2023-12-12 | 138 | 98 | 2023-07-16 | 2023-07-21 | 6 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 655.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 343.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2024-07-11 | 301 | 215 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 728.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-19 | 3 | 3 | 2024-09-19 | 2025-01-03 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | 216 | 216 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1290 | 492.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | 2023-11-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13352 | 683.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-10-25 | 43 | 31 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 904.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-17 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-17 | 9 | 7 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2025-08-04 | 566 | 404 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1146.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-08-27 | 64 | 46 | 2024-08-27 | 2024-09-05 | 10 | 8 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1766.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2025-01-03 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-18 | 24 | 18 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | 2025-06-10 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6408.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-10 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | COUNTY OF SAN DIEGO-SOUTH of 56 | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 536.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-03-28 | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 148.05 | 148.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2825.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-01 | 2023-02-27 | 27 | 19 | 2023-02-27 | 2024-11-11 | 624 | 446 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-09-05 | 299 | 215 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2024-10-22 | IOU Designed & Installed | N/A | No | Unknown | 1351.55 | 377.04 | Unknown | 26.62 | 51.61 | 896.28 | 0 | 1541.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1519.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-11-04 | 27 | 19 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36350 | 1046.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-12-02 | 26 | 18 | 2024-12-02 | 2024-12-11 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1517.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-08-06 | 36 | 26 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4895.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | 2024-07-11 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2025-02-24 | 229 | 163 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1320.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2023-09-15 | 151 | 109 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4063.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-03-05 | 30 | 22 | 2025-03-05 | 2025-04-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 6122.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-11-05 | 8 | 6 | 2024-11-05 | 2024-11-07 | 3 | 3 | 2024-11-07 | 2025-03-21 | 135 | 97 | 2024-11-11 | 2024-11-19 | 9 | 7 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3594.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-05-01 | 22 | 16 | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-02 | 2025-06-03 | 33 | 23 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1301.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-10 | 5 | 3 | 2025-02-10 | 2025-03-03 | 22 | 16 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 319.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-02-05 | 10 | 8 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 72.2 | 72.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1348.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-07-23 | 22 | 16 | 2024-07-23 | 2024-07-26 | 4 | 4 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2025-07-03 | 343 | 245 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11.5 | 11.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1521.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-08-26 | 47 | 33 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2025-07-30 | 339 | 243 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 150 | 150 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47640.6 | 6478.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-17 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 132753 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2024-09-04 | 433 | 309 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 52.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-04-10 | 43 | 31 | 2025-04-10 | 2025-04-22 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-27 | 25 | 19 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-15 | 2023-10-16 | 2024-08-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 955 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-15 | 2023-03-24 | Unknown | Unknown | 2023-03-24 | 2023-10-16 | 207 | 147 | 2023-10-16 | 2023-11-14 | 30 | 22 | 2023-10-30 | 2023-11-16 | 18 | 14 | 2023-11-14 | 2024-08-12 | 273 | 195 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2238.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2025-01-02 | 22 | 16 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1435.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | PINE VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2025-03-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2112 | 935.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-26 | 35 | 25 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-03-02 | 97 | 69 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3043.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-03-04 | 9 | 7 | 2025-03-04 | 2025-03-31 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-08-21 | 144 | 104 | Unknown | 2025-08-22 | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19807.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-10-09 | 23 | 17 | 2024-10-09 | 2025-05-05 | 209 | 149 | 2024-11-15 | 2024-12-12 | 28 | 20 | 2025-04-10 | 2025-04-23 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4360.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-31 | 2024-08-05 | 6 | 4 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 187 | 187 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1055.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-12-19 | 31 | 23 | 2024-12-19 | 2024-12-26 | 8 | 6 | 2024-12-26 | 2025-04-07 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 773265.02 | 31094.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-06 | 2024-02-06 | 124 | 88 | 2024-02-06 | 2024-06-07 | 123 | 89 | 2024-02-12 | 2024-02-16 | 5 | 5 | 2024-02-16 | 2024-06-18 | 31 | 23 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-31 | 19 | 15 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-07-18 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1454.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2025-01-08 | 23 | 17 | 2025-01-08 | 2025-01-28 | 21 | 15 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 664.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-03-28 | 1 | 1 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-18 | 4 | 4 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7995 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 806.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-02-29 | 38 | 28 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1085.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2024-05-24 | 46 | 34 | 2024-05-24 | 2024-06-03 | 11 | 7 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | 2025-04-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2018.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-03-28 | 1 | 1 | 2025-03-28 | 2025-03-28 | 1 | 1 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-22 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | POWAY | POWAY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 311.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | 2023-11-13 | 287 | 205 | 2023-02-14 | 2024-03-05 | 386 | 276 | 2023-02-06 | 2024-03-12 | 17 | 13 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 7500 | 7500 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1850.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-06-11 | 24 | 18 | 2025-06-11 | 2025-06-12 | 2 | 2 | 2025-06-11 | 2025-06-12 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-01 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13.25 | 13.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1541.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-04-24 | 24 | 18 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 901.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2023-03-16 | 10 | 8 | 2023-03-16 | 2023-08-28 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 821.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-09 | 2 | 2 | 2025-04-09 | 2025-04-22 | 14 | 10 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 36.8 | 36.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2025-01-10 | 22 | 16 | 2025-01-10 | 2025-01-27 | 18 | 12 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | Applicant Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-12-11 | 45 | 33 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-21 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 440 | 440 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 303877 | 11367.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-02 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2025-05-15 | 527 | 377 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1608.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-27 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-27 | 16 | 12 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 89 | 89 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 2092.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-02-08 | 113 | 81 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3679.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | 2025-05-29 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-19 | 34 | 24 | 2025-05-29 | 2025-08-01 | 65 | 47 | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 17.7 | 17.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1107.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-08-11 | 56 | 40 | 2025-08-11 | 2025-08-12 | 2 | 2 | 2025-06-25 | 2025-06-27 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1642.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2025-01-06 | 70 | 50 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1225.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-15 | 15 | 11 | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1078.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-13 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-02-13 | 21 | 15 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-10-02 | 42 | 30 | 2024-10-02 | 2024-10-09 | 8 | 6 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | Unknown | Unknown | No | 2024-04-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | Yes | 42 | 1455.86 | 204.81 | Unknown | Unknown | 15.46 | 1235.59 | 3981 | 1530.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-06-05 | 52 | 38 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-04 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 271793 | 14133.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2023-08-15 | 2 | 2 | 2023-08-15 | 2023-11-02 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5960 | 680.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2024-02-07 | 100 | 72 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1538.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-16 | 10 | 8 | 2025-05-16 | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-26 | 39 | 29 | 2025-05-16 | 2025-07-01 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-12 | 2024-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 332759.92 | 93290.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-12 | 2024-10-17 | 6 | 4 | 2024-10-17 | 2025-05-28 | 224 | 160 | 2024-12-18 | 2025-03-27 | 20 | 18 | 2025-01-24 | 2025-06-04 | 89 | 63 | 2025-05-28 | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 82364.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-15 | 2 | 2 | 2024-08-15 | 2025-06-19 | 309 | 221 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-06 | 21 | 15 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 2029.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-06-07 | 4 | 4 | 2024-06-07 | 2024-10-22 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2025-06-04 | 23 | 17 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26761 | 3667.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-02-19 | 49 | 35 | 2025-02-19 | 2025-04-02 | 43 | 31 | 2025-05-02 | 2025-05-05 | 4 | 2 | 2025-02-19 | 2025-05-06 | 75 | 55 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1471.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-10-03 | 8 | 6 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | San Diego | 2898 | 2898 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 86038.26 | 83807.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-07-31 | 154 | 110 | 2024-07-31 | Unknown | Unknown | Unknown | 2024-08-16 | 2024-10-15 | 61 | 43 | 2024-09-04 | 2025-03-21 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1395.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-06-24 | 35 | 25 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56, POWAY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-28 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 78490 | 222372.82 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-28 | 2023-02-28 | 124 | 88 | 2023-02-28 | 2025-04-15 | 778 | 556 | 2023-05-03 | 2025-04-03 | 261 | 189 | 2023-06-08 | 2025-04-28 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1536.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-05-23 | 137 | 99 | 2024-05-23 | 2024-09-30 | 131 | 93 | 2024-09-09 | 2024-09-16 | 8 | 6 | 2024-08-28 | 2024-09-20 | 18 | 14 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 2732.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | 2025-02-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-05-08 | 2024-09-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 14551.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-03-20 | 35 | 25 | 2024-03-20 | 2024-07-05 | 108 | 78 | 2024-04-15 | 2024-05-06 | 22 | 16 | 2024-07-09 | 2024-07-16 | 8 | 6 | 2024-09-03 | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-26 | 24 | 18 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 1996 | 1996 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1142.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-30 | 23 | 17 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 332.14 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2023-03-01 | 325 | 233 | 2023-03-01 | 2023-03-15 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 546.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-05-31 | 1 | 1 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 62.35 | 62.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1651.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-05 | 16 | 12 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 411.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | 2023-10-23 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-10-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1563.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-09-05 | 94 | 68 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-04 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | Unknown | Unknown | No | 2024-12-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | Yes | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2819.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2025-01-13 | 41 | 29 | 2025-01-13 | 2025-02-18 | 37 | 27 | 2025-02-18 | 2025-04-14 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-07-01 | 72 | 52 | Unknown | 2025-06-25 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5950.01 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-23 | 2023-03-21 | 272 | 194 | 2023-03-21 | 2023-04-24 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-03-13 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1247.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-23 | 1 | 1 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6903.12 | 1419.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2025-02-06 | 84 | 60 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1030.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2772.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-14 | 8 | 6 | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 975.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-05 | Unknown | Unknown | 2025-06-05 | 2025-06-11 | 7 | 5 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-07-03 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 689.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-10-04 | 8 | 6 | 2024-10-04 | 2024-11-13 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1826.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2025-03-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1415.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-08-30 | Unknown | Unknown | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2025-03-03 | 165 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2025-04-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 305286.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2024-04-03 | 140 | 100 | 2024-04-03 | 2025-01-24 | 297 | 213 | 2024-04-29 | 2025-05-22 | 131 | 93 | 2024-07-29 | 2024-08-02 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | 2025-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 2416.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-04-23 | 78 | 56 | 2025-04-23 | 2025-06-02 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-21 | 19 | 13 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5581.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2024-03-07 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-30 | 8 | 6 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 529.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-20 | 2023-03-24 | 5 | 5 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 856.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-06-09 | 11 | 7 | 2025-06-09 | 2025-06-17 | 9 | 7 | 2025-06-17 | 2025-07-14 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-14 | 22 | 16 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1991.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-27 | 28 | 20 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2047.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-16 | 8 | 6 | 2025-05-16 | 2025-05-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1071.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-27 | 2025-06-25 | Unknown | Unknown | 2025-06-25 | 2025-06-27 | 3 | 3 | 2025-06-27 | Unknown | Unknown | Unknown | 2025-06-27 | 2025-07-11 | 15 | 11 | 2025-06-27 | 2025-07-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20.7 | 20.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1636.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-25 | 8 | 6 | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1531.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-03 | 2023-11-28 | 57 | 41 | 2023-11-28 | 2023-11-29 | 2 | 2 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-03-04 | 13 | 9 | 2025-03-04 | 2025-03-24 | 21 | 15 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1454.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-26 | 2025-02-14 | 600 | 430 | 2025-02-14 | 2025-02-18 | 5 | 3 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-08-27 | 191 | 137 | Unknown | 2025-08-25 | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 397.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-30 | 16 | 12 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | SAN YSIDRO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 96114.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-09-18 | 293 | 209 | 2024-09-18 | 2024-10-10 | 23 | 17 | 2024-07-01 | 2025-06-18 | 80 | 58 | 2024-06-26 | 2025-07-10 | 287 | 205 | 2024-10-10 | Unknown | Unknown | Unknown | 2024-10-17 | 2025-08-11 | 299 | 213 | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1249.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-10-31 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-10-28 | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2025-01-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1497.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-09-26 | 94 | 68 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-01-14 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1203.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-10-14 | 26 | 18 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1509.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-12-02 | 28 | 20 | 2024-12-02 | 2024-12-11 | 10 | 8 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2025-04-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1143.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-08-26 | 333 | 237 | 2024-08-26 | 2024-09-18 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2025-04-03 | 198 | 142 | Unknown | 2025-08-20 | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1225.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-30 | 18 | 14 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-08-22 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DULZURA | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1367.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-11 | 2023-05-11 | 1 | 1 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 969.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-08-26 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 631.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-05-13 | 12 | 8 | 2024-05-13 | 2024-07-17 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1357.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-12 | 2 | 2 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 138928 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2023-10-23 | Unknown | Unknown | 2023-10-23 | 2024-05-06 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-22 | 1 | 1 | 2024-05-06 | 2025-09-09 | 492 | 352 | Unknown | 2025-08-28 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 91.05 | 91.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | 2024-08-29 | IOU Designed & Installed | N/A | No | Unknown | 449.73 | 0 | Unknown | Unknown | 90.4 | 359.33 | 3981 | 284.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-07-11 | 78 | 56 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-29 | 50 | 36 | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | Unknown | Unknown | No | 2024-06-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | Yes | 279 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2046.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2025-03-27 | 280 | 200 | 2025-03-27 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 846.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE, MISSION VIEJO | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23540.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2025-01-13 | 300 | 214 | 2025-01-13 | Unknown | Unknown | Unknown | 2025-01-23 | 2025-01-28 | 6 | 4 | 2025-03-21 | 2025-04-18 | 20 | 14 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | 980 | 980 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1763.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-12 | 14 | 10 | 2025-03-12 | 2025-03-25 | 14 | 10 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1604.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2025-08-13 | 427 | 305 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2238.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | 2025-08-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2551.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-04-03 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4004.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-04-18 | 1 | 1 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1962.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-02-10 | 8 | 6 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | 2022-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13817 | 313.83 | Unknown | Unknown | Yes | N/A | N/A | 2022-03-21 | 2023-02-06 | 323 | 231 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-08-15 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-08-05 | 40 | 28 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 100.35 | 100.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1202.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-28 | 5 | 3 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-06-16 | 131 | 93 | Unknown | 2025-06-05 | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | PAUMA VALLEY | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 844.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-19 | 15 | 11 | 2025-03-19 | 2025-06-16 | 90 | 64 | 2025-03-19 | 2025-05-01 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-23 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11279.42 | 3815.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-08-07 | 212 | 152 | 2025-02-25 | 2025-06-17 | 2 | 2 | 2025-03-14 | 2025-06-20 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 28.1 | 28.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1132.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-09-13 | 115 | 83 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 92.4 | 92.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1502.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 110000 | 80390.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-08-01 | 63 | 45 | 2023-08-01 | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-04-19 | 2024-05-13 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1014.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-26 | 2025-06-27 | 2 | 2 | 2025-06-27 | 2025-06-27 | 1 | 1 | 2025-06-27 | 2025-08-05 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-08-05 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 57.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-25 | 16 | 12 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 162183 | 9485.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-04-03 | 44 | 32 | 2025-04-03 | 2025-05-20 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2025-05-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 37742.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2024-02-07 | 135 | 97 | 2024-02-07 | 2024-09-05 | 212 | 152 | 2024-02-23 | 2024-09-04 | 24 | 16 | 2024-02-29 | 2024-09-17 | 42 | 28 | 2025-02-18 | Unknown | Unknown | Unknown | 2025-02-18 | 2025-05-09 | 81 | 59 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 777.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-04-02 | 84 | 60 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 218 | 218 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 752.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 736.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-26 | 2024-01-30 | 5 | 3 | 2024-01-30 | 2024-02-02 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | 449.35 | 0 | Unknown | Unknown | 18.08 | 431.27 | 3981 | 1536.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-10-24 | 28 | 20 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-06-19 | 239 | 171 | Unknown | 2025-06-13 | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3660 | 1050.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-21 | 11 | 9 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-22 | 2023-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5292.78 | 10210.75 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-22 | 2023-03-09 | 200 | 144 | 2023-03-09 | 2024-01-12 | 310 | 222 | 2023-07-27 | 2024-01-11 | 112 | 80 | 2023-08-25 | 2023-08-30 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | Unknown | Unknown | No | 2023-06-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | Yes | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-26 | 6 | 4 | 2023-06-26 | 2023-06-26 | 1 | 1 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-03-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1566.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-21 | 2 | 2 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-03-04 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4742.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | 2025-03-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 81.12 | 81.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23815 | 31242.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2024-06-18 | 197 | 141 | 2024-06-18 | 2025-05-15 | 332 | 238 | 2024-10-08 | 2024-10-09 | 2 | 2 | 2024-08-05 | 2025-02-25 | 81 | 57 | 2025-05-15 | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1004.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2023-12-01 | 36 | 26 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | 2024-07-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | Yes | 244 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1016.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2025-03-31 | 245 | 175 | 2025-03-31 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2913.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-14 | 15 | 11 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | SAN JUAN CAPISTRANO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 700.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-02-25 | 49 | 35 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-04-17 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56, ESCONDIDO | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1085.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-13 | 10 | 8 | 2025-06-13 | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-02 | 20 | 14 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 154445 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2024-09-24 | 453 | 323 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1581.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-30 | 15 | 11 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-07-14 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-30 | 2025-05-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1816.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-06-25 | IOU Designed & Installed | N/A | No | Unknown | 1933.01 | 245.68 | Unknown | Unknown | 79.64 | 1607.69 | 3981 | 674.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-03-21 | 52 | 38 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-06-25 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1889.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-28 | 6 | 4 | 2025-05-28 | 2025-06-11 | 15 | 11 | 2025-05-28 | 2025-07-09 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-09 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2034.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-22 | 2023-09-12 | 175 | 125 | 2023-09-12 | 2023-10-03 | 22 | 16 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1627.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-09-24 | 58 | 42 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 1719.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-11 | 5 | 3 | 2025-03-11 | 2025-03-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-24 | 14 | 10 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-10 | Unknown | Unknown | No | 2023-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | Yes | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 557.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2024-03-05 | 141 | 101 | 2024-03-05 | 2023-11-10 | Unknown | Unknown | 2023-11-10 | 2024-02-13 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 134445 | 9491.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2024-01-03 | 15 | 11 | 2024-01-03 | 2024-10-10 | 282 | 202 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-11 | 2023-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 440.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-06-02 | 4 | 2 | 2024-06-02 | 2024-06-14 | 13 | 10 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2869.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-03-11 | 37 | 27 | 2025-03-11 | 2025-04-03 | 24 | 18 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-09-08 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1280.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | 2025-06-26 | 2 | 2 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-15 | 20 | 14 | 2025-06-25 | 2025-08-05 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 3733 | 3733 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 53597.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2025-01-09 | 330 | 236 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2025-01-13 | 24 | 18 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 483.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-08 | 2023-09-21 | Unknown | Unknown | 2023-09-21 | 2023-12-29 | 100 | 72 | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 1970.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | 2024-09-04 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-10-30 | 72 | 52 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | 120.2 | 120.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2273.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2024-01-12 | 25 | 19 | 2024-01-12 | 2025-04-28 | 473 | 337 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 547.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | 2023-10-04 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-11 | 7 | 5 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-05 | Unknown | Unknown | No | 2022-06-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | Yes | 344 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 24581.78 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-22 | 2023-05-11 | 324 | 232 | 2023-05-11 | 2025-02-28 | 660 | 472 | 2023-05-23 | 2024-06-14 | 175 | 125 | 2023-07-20 | 2024-07-05 | 172 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-09-04 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1675.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-12 | 10 | 8 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1270.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-03-28 | 11 | 9 | 2025-03-28 | 2025-03-31 | 4 | 2 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-06-18 | 85 | 61 | 2025-06-18 | 2025-06-23 | 6 | 4 | 2025-06-18 | 2025-06-23 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 330.05 | 330.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 853.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-19 | 5 | 3 | 2025-05-19 | 2025-05-29 | 11 | 9 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 832.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-06 | 9 | 7 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | 2025-06-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3409 | 1292.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-25 | 20 | 14 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-08-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 169737.11 | 84150.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-27 | 2023-06-30 | 4 | 4 | 2023-06-30 | 2024-12-18 | 538 | 384 | 2023-09-07 | 2024-12-10 | 10 | 8 | 2023-11-28 | 2025-01-06 | 24 | 18 | 2024-12-18 | 2025-06-06 | 171 | 123 | 2025-03-27 | 2025-06-30 | 96 | 68 | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 827.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-23 | 8 | 6 | 2025-05-23 | 2025-06-11 | 20 | 14 | 2025-05-22 | 2025-06-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-11 | 29 | 21 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 125804 | 3465.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-04-17 | 77 | 55 | 2023-04-17 | 2024-01-16 | 275 | 197 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | POWAY | 1800 | 1800 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 677813 | 73567.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-27 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-03-30 | 8 | 6 | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-27 | 2023-05-01 | 23 | 15 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 143.1 | 143.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1037.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-03-24 | 8 | 6 | 2025-03-24 | 2025-03-28 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 382785 | 149993.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2024-03-12 | 173 | 123 | 2024-03-12 | 2025-01-08 | 303 | 217 | 2024-05-10 | 2024-11-11 | 30 | 19 | 2024-07-30 | 2024-12-09 | 112 | 80 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1198.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-12-03 | 68 | 48 | 2024-12-03 | 2024-12-04 | 2 | 2 | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-07-16 | 225 | 161 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-01-02 | Unknown | Unknown | 2024-01-02 | 2024-03-15 | 74 | 54 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2728.25 | 2728.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2069.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-23 | 8 | 6 | 2024-07-23 | 2025-02-27 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4888.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-19 | 23 | 17 | 2025-02-19 | 2025-04-03 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-14 | 23 | 17 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 81.35 | 81.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-04-04 | 2025-04-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2001.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-04-02 | 13 | 9 | 2025-04-02 | 2025-04-04 | 3 | 3 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-15 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 264.15 | 264.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1272.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-06-02 | 20 | 14 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 107396 | 7388.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2023-08-31 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1100.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-11-12 | 42 | 30 | 2024-11-12 | 2024-11-22 | 11 | 9 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-07-30 | 251 | 179 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 683.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-09-27 | 189 | 135 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 101171 | 38197.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2024-01-22 | 125 | 89 | 2024-01-22 | 2024-06-27 | 158 | 114 | 2024-01-23 | 2024-04-30 | 16 | 12 | 2024-04-03 | 2024-08-09 | 81 | 52 | 2024-06-27 | Unknown | Unknown | Unknown | 2024-11-12 | 2025-08-25 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1439.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-07-14 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | 2025-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3840 | 510.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2025-07-24 | 368 | 264 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2985 | 693.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-12-20 | 46 | 34 | 2024-12-20 | 2025-02-06 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-20 | 22 | 16 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 123.05 | 123.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1497.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2348.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-09-09 | 49 | 35 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 88129.76 | 22448.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2024-01-23 | 126 | 90 | 2024-01-23 | 2024-06-20 | 150 | 108 | 2024-01-22 | 2025-03-21 | 18 | 14 | 2024-04-03 | 2025-03-31 | 17 | 5 | 2024-06-20 | Unknown | Unknown | Unknown | 2024-08-01 | 2025-06-23 | 327 | 233 | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 168.05 | 168.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1542.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-24 | 5 | 3 | 2025-03-24 | 2025-04-17 | 25 | 19 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-08-14 | 120 | 86 | Unknown | 2025-08-14 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 246.2 | 246.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 11823.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-09-11 | 286 | 204 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 447.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | 2025-01-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | Yes | 105 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1850.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2025-05-12 | 106 | 76 | 2025-05-12 | 2025-01-29 | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1412.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-29 | 35 | 25 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.4 | 14.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-08 | Unknown | Unknown | 2024-07-08 | 2024-07-25 | 18 | 14 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1625.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1080.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-22 | 17 | 13 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1226.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-10-16 | 24 | 18 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-11-07 | 181 | 129 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | 2025-05-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1649.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-04-09 | 15 | 11 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-05-09 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | LAKESIDE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1217.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | 2025-06-06 | 316 | 226 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | CALTRANS-NORTH of 56 | 1056 | 1056 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 313.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2024-01-17 | 51 | 37 | 2024-01-17 | 2024-04-08 | 83 | 59 | 2024-02-28 | 2024-03-04 | 6 | 4 | 2024-01-19 | 2024-03-28 | 66 | 48 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 803.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-19 | 4 | 2 | 2025-05-19 | 2025-06-05 | 18 | 14 | 2025-06-05 | 2025-06-23 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-29 | 37 | 27 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 699.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2023-10-25 | 97 | 69 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 1699.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-07-09 | 118 | 84 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1038.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-05-15 | 79 | 57 | 2025-05-15 | 2025-05-16 | 2 | 2 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | 2024-04-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | Yes | 437 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 192.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2025-06-12 | 437 | 313 | 2025-06-12 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2025-07-16 | 409 | 293 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1078.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-06-04 | 72 | 52 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1456.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-30 | 2 | 2 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 183.05 | 183.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1099.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-06-16 | 29 | 21 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4433.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-19 | 8 | 6 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 831.15 | 831.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2869.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-24 | 2024-01-05 | 166 | 120 | 2024-01-05 | 2024-05-29 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 2634.65 | 602.05 | Unknown | Unknown | 158.87 | 1873.73 | 2875.23 | 3058.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2024-07-09 | 85 | 61 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1381.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-12 | 10 | 8 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1660.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-31 | 24 | 18 | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1978.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-20 | 14 | 10 | 2025-03-20 | 2025-03-21 | 2 | 2 | 2025-03-07 | 2025-03-20 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1559.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2024-01-04 | 136 | 98 | 2024-01-04 | 2024-01-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | San Marcos | SAN MARCOS | 8994 | 8994 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 58327 | 115381.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2025-02-28 | 255 | 183 | 2024-11-22 | 2025-01-02 | 8 | 6 | 2024-09-25 | 2025-06-26 | 82 | 60 | 2025-02-28 | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 963.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-11 | 8 | 6 | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-06 | 2025-06-11 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-08-14 | 65 | 47 | Unknown | 2025-08-12 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1369.07 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-07-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 153.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-07-22 | 38 | 27 | 2023-07-22 | 2023-07-22 | 1 | 0 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1638.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-09-26 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | 2022-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13817 | 326.72 | Unknown | Unknown | Yes | N/A | N/A | 2022-03-21 | 2023-02-06 | 323 | 231 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 71.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2025-01-08 | 309 | 221 | 2025-01-08 | 2025-06-05 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2025-01-09 | 108 | 78 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-23 | 2025-06-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1159.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-23 | 5 | 5 | 2025-05-23 | 2025-05-23 | 1 | 1 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-06-12 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1354.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-06-09 | 147 | 105 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 469.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-01-22 | 2 | 2 | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-09-02 | 224 | 160 | Unknown | 2025-06-17 | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1753.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1143.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-06 | Unknown | Unknown | 2025-06-06 | 2025-06-27 | 22 | 16 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-23 | 2024-12-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 4693.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | 2024-05-29 | 413 | 295 | 2023-10-13 | 2024-02-23 | 2 | 2 | 2023-10-02 | 2024-11-27 | 88 | 64 | 2024-05-29 | 2024-10-02 | 127 | 91 | 2024-06-04 | 2024-11-08 | 158 | 114 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-09-05 | 486 | 348 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-10-26 | 2025-03-25 | IOU Designed & Installed | N/A | No | Unknown | 251494.58 | 8838.56 | Unknown | Unknown | 2984.93 | 239671.09 | 0 | 179396.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2024-02-13 | 229 | 163 | 2024-02-13 | 2025-03-18 | 400 | 286 | 2024-05-24 | 2025-03-07 | 42 | 30 | 2024-08-15 | 2025-04-09 | 33 | 23 | 2025-03-18 | 2025-05-21 | 65 | 47 | 2025-04-04 | 2025-05-21 | 48 | 34 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2096.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | 2025-07-01 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-02 | 10 | 8 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | VS 1087-H5 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 31530.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-17 | 2024-07-09 | 175 | 125 | 2024-07-09 | 2025-01-03 | 179 | 129 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-01-08 | 10 | 8 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1210.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-25 | 12 | 8 | 2025-03-25 | 2025-04-07 | 14 | 10 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-07-16 | 101 | 73 | Unknown | 2025-07-10 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 528.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-08-21 | 2 | 2 | 2024-08-21 | 2025-02-24 | 188 | 134 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65076 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-10-16 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-10-20 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 572.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-04-13 | 3 | 3 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 559.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-06-11 | 6 | 4 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-15 | 35 | 25 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 922.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-05-08 | 11 | 9 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-08-11 | 96 | 68 | Unknown | 2025-07-25 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 29002.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2025-07-02 | 483 | 345 | 2025-03-12 | 2025-04-01 | 21 | 15 | 2025-04-01 | 2025-08-11 | 68 | 48 | 2025-08-12 | Unknown | Unknown | Unknown | 2025-08-12 | 2025-08-12 | 1 | 1 | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1160.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-06-09 | 32 | 22 | 2025-06-09 | 2025-06-19 | 11 | 9 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-08-04 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 57259.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-08 | 2023-09-13 | 6 | 4 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1753.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-11 | 3 | 3 | 2024-09-11 | 2025-06-19 | 282 | 202 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-24 | 44 | 32 | 2025-06-19 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 985.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-09-06 | 37 | 27 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1066.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-12 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-09 | 99 | 71 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 90902 | 37402.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-10-15 | 196 | 140 | 2024-10-15 | 2025-01-16 | 94 | 68 | 2024-09-11 | 2024-11-04 | 20 | 16 | 2024-07-23 | 2025-01-22 | 89 | 63 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1932.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-06 | 2024-11-18 | 13 | 9 | 2024-11-18 | 2024-12-11 | 24 | 18 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 22043 | 22043 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1480.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-09-10 | 35 | 25 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 252 | 252 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98430.5 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-14 | 2023-10-04 | 325 | 233 | 2023-10-04 | 2025-03-17 | 531 | 379 | 2023-11-28 | 2025-03-14 | 99 | 73 | 2024-01-15 | 2025-08-01 | 143 | 105 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 106.2 | 106.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 48918.96 | 25091.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-23 | 2024-11-08 | 260 | 186 | 2024-11-08 | 2025-05-12 | 186 | 132 | 2024-12-03 | 2025-03-27 | 94 | 68 | 2025-03-20 | 2025-05-21 | 26 | 18 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 383.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-07-08 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 657.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-02-05 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-08-01 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | Unknown | Unknown | No | 2024-07-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | Yes | 93 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1170.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-10-09 | 94 | 68 | 2024-10-09 | 2024-11-25 | 48 | 34 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | 2022-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1244.1 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-15 | 2023-04-19 | 248 | 178 | 2023-04-19 | 2023-04-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-04-06 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Mission Viejo | COUNTY OF ORANGE, MISSION VIEJO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 97364.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-11-20 | 177 | 127 | 2024-11-20 | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-19 | 10 | 8 | 2025-01-08 | 2025-05-30 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3217.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-08 | 2 | 2 | 2025-04-08 | 2025-05-08 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 807.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-06-13 | 38 | 28 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-08-01 | 50 | 36 | Unknown | 2025-08-01 | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2020.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 7.19 | 0 | Unknown | Unknown | Unknown | 7.19 | 0 | 499.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-17 | 2023-03-17 | 1 | 1 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 2892.37 | 0 | Unknown | Unknown | 79.33 | 2813.04 | 3981 | 922.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-23 | 18 | 14 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-07-02 | 161 | 115 | Unknown | 2025-05-28 | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1324.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-10-10 | 85 | 61 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | SD 1169-D3 del sur housing (E) | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2025-06-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1384744 | 140925.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2023-09-26 | 112 | 80 | 2023-09-26 | 2024-11-18 | 420 | 300 | 2023-10-19 | 2024-11-19 | 300 | 214 | 2024-10-16 | 2025-08-13 | -234 | -174 | 2024-11-18 | Unknown | Unknown | Unknown | 2024-12-03 | 2025-06-20 | 200 | 144 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1680.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 120.1 | 120.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 985.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-06-20 | 50 | 36 | 2025-06-10 | 2025-06-11 | 2 | 2 | 2025-05-30 | 2025-06-17 | 19 | 13 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1032.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-06-03 | 126 | 90 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-07-21 | 47 | 33 | Unknown | 2025-07-18 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-26 | 21 | 15 | 2025-03-26 | 2025-04-08 | 14 | 10 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-07-07 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1421.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-03-28 | 50 | 36 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1385.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-25 | 2025-01-09 | 504 | 360 | 2025-01-09 | 2025-04-03 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-12 | 21 | 15 | 2025-04-03 | 2025-04-17 | 15 | 11 | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8683810 | 303328.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-14 | 2023-05-23 | 191 | 137 | 2023-05-23 | 2023-12-26 | 218 | 156 | 2023-06-08 | 2023-12-21 | 130 | 94 | 2023-07-19 | 2023-07-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1087 | 1087 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-07-19 | Unknown | Unknown | No | 2023-10-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | Yes | 329 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1311.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2024-09-20 | 330 | 236 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | DULZURA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5816 | 1535.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | 2023-09-18 | 214 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Santa Fe | COUNTY OF SAN DIEGO-NORTH of 56 | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3246.96 | 13037.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-06-13 | 120 | 86 | 2025-03-31 | 2025-06-11 | 21 | 15 | 2025-04-25 | 2025-07-14 | 40 | 28 | 2025-07-15 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-06-12 | 42 | 30 | 2025-06-12 | 2025-06-16 | 5 | 3 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 797.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-28 | 38 | 28 | 2025-02-28 | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-19 | 21 | 15 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-04-25 | 79 | 57 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2025-07-24 | 456 | 326 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2955.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-14 | 2 | 2 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14855 | 3833.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-10-17 | 11 | 9 | 2024-10-17 | 2024-10-29 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-07-22 | 44 | 32 | 2024-10-29 | 2025-06-02 | 217 | 155 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 2853.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | 2025-06-10 | 301 | 215 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3178.49 | 3381.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-06-12 | 149 | 107 | 2025-06-09 | 2025-06-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-23 | 42 | 30 | Unknown | 2025-07-21 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2023-10-31 | 23 | 17 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5270.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-10 | 2023-03-20 | 39 | 27 | 2023-03-20 | 2023-06-27 | 100 | 72 | 2023-04-20 | 2023-06-06 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1072.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2024-04-23 | 218 | 156 | 2024-04-23 | 2024-05-24 | 32 | 24 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2072.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-07-02 | 20 | 14 | 2024-07-02 | 2024-07-24 | 23 | 17 | 2024-07-02 | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-05 | 35 | 25 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1244.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-03-13 | 21 | 15 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1335.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-06 | 15 | 11 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 272.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 837.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-05-30 | 3 | 3 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 805.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7842 | 1390.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-19 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-19 | 3 | 3 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1483.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-08-01 | 60 | 44 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-26 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-11-26 | 148 | 106 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3670.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-03-17 | 4 | 2 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 389.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-02-24 | 12 | 10 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | 2025-03-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1789.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-26 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-11-27 | 3 | 3 | 2024-11-27 | Unknown | Unknown | Unknown | 2024-11-30 | 2025-01-07 | 39 | 27 | 2024-11-26 | 2025-03-03 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1320.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-10-04 | 22 | 16 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2025-07-30 | 300 | 214 | Unknown | 2025-07-14 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 4.7 | 4.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-22 | 20 | 14 | 2025-04-22 | 2025-04-25 | 4 | 4 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-07-23 | 90 | 64 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-20 | 4 | 4 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2024-02-16 | 2025-01-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11175.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-23 | 2024-09-23 | 337 | 241 | 2024-09-23 | 2025-01-15 | 115 | 83 | 2024-11-11 | 2024-11-12 | 2 | 2 | 2024-10-15 | 2025-01-13 | 35 | 27 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | 2024-11-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | Yes | 176 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2887.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2025-02-05 | 73 | 53 | 2025-02-05 | 2025-06-06 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-09 | 17 | 13 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2063 | 2257.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-06 | 2024-11-06 | 1 | 1 | 2024-11-06 | 2025-04-28 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | 3254 | 3254 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 105173.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-07-01 | 5 | 3 | 2024-07-01 | 2025-03-20 | 263 | 189 | 2024-08-27 | 2025-07-15 | 72 | 52 | 2025-01-28 | 2025-05-13 | 5 | 5 | 2025-05-21 | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-19 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-03-01 | 2024-03-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 501.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2023-12-26 | Unknown | Unknown | 2023-12-26 | 2024-03-01 | 67 | 49 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-11 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Escondido | Escondido | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 121200.31 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2023-06-12 | 428 | 306 | 2023-06-12 | 2025-05-29 | 718 | 514 | 2023-06-21 | 2025-08-26 | 755 | 539 | 2025-04-02 | 2025-06-12 | 27 | 21 | 2025-06-18 | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 62.35 | 62.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1064.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-19 | 21 | 15 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1179.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-13 | 9 | 7 | 2024-09-13 | 2024-09-13 | 1 | 1 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1947.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | 2024-05-22 | 3 | 3 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1000.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-06-19 | 93 | 67 | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-24 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 415.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-11-15 | 127 | 91 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-15 | Unknown | Unknown | No | 2022-06-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-13 | 2022-07-18 | 2024-01-11 | IOU Designed & Installed | N/A | Yes | 412 | 1801.94 | 502.13 | Unknown | 83.08 | 217.61 | 999.12 | 3885 | 1540.46 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-13 | 2023-07-31 | 414 | 296 | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | 2023-10-05 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2024-01-11 | 99 | 71 | Unknown | 2024-01-08 | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1329.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-04-16 | 70 | 50 | 2025-04-16 | 2025-04-18 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1894168.72 | 224997.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2025-01-10 | 186 | 134 | 2025-01-10 | 2025-05-01 | 112 | 80 | 2025-01-10 | 2025-05-28 | 64 | 44 | 2025-01-15 | 2025-05-13 | 38 | 28 | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-23 | 48 | 34 | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | 237 | 237 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-26 | Unknown | Unknown | No | 2022-06-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-10 | 2022-06-10 | Unknown | IOU Designed & Installed | N/A | Yes | 606 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10156 | 33486.83 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-10 | 2024-01-11 | 581 | 415 | 2024-01-11 | 2023-05-31 | Unknown | Unknown | 2022-09-20 | 2023-05-30 | 17 | 13 | 2023-03-13 | 2023-06-06 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | Both | IOU Design | Commercial | Underserved Community | CARLSBAD | CARLSBAD | 188 | 188 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 108689 | 114950.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-20 | 2023-10-11 | 206 | 148 | 2023-10-11 | 2025-01-08 | 456 | 326 | 2024-04-05 | 2024-08-28 | 59 | 41 | 2024-05-17 | 2025-01-25 | 102 | 75 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 1906.05 | 1906.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 942.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-27 | 11 | 9 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5196.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2024-04-11 | 154 | 110 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 168.2 | 168.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1051.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-27 | 5 | 3 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2902.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-22 | 2 | 2 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-15 | 2025-06-20 | IOU Designed & Installed | N/A | No | Unknown | 3096.22 | 0 | Unknown | Unknown | 35.37 | 3060.85 | 3981 | 1003.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2025-04-16 | 185 | 133 | 2025-04-16 | 2025-04-28 | 13 | 9 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-06-20 | 54 | 40 | Unknown | 2025-06-09 | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 102.1 | 102.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 22147.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-12-24 | 37 | 27 | 2024-12-24 | 2025-04-28 | 126 | 90 | 2025-03-05 | 2025-03-21 | 17 | 13 | 2025-04-28 | 2025-05-12 | 15 | 11 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 617 | 617 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 30829.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-19 | 7 | 5 | 2025-02-19 | 2025-04-30 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-08 | 21 | 15 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | Pauma Valley | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 165701 | 31023.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2025-03-06 | 367 | 263 | 2025-03-06 | 2025-05-13 | 69 | 49 | 2025-02-13 | 2025-05-08 | 17 | 13 | 2025-02-07 | 2025-05-15 | 19 | 13 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 376 | 376 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7770 | 763.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-10-10 | 121 | 87 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 242 | 242 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16177.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-28 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-07-19 | IOU Designed & Installed | N/A | No | Unknown | 5278.95 | 1410.08 | Unknown | 228.27 | 223.06 | 3417.54 | 3981 | 1034.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-05-10 | 17 | 13 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-07-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | 2020-07-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-06 | 2020-07-06 | Unknown | IOU Designed & Installed | N/A | Yes | 1400 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1141.58 | Unknown | Unknown | Yes | N/A | N/A | 2020-07-06 | 2024-05-06 | 1401 | 1001 | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2020-07-06 | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1521.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-07 | 6 | 4 | 2025-01-07 | 2025-02-14 | 39 | 29 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1608.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2025-03-06 | 122 | 88 | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-07-02 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 744.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-13 | 2023-07-14 | 2 | 2 | 2023-07-14 | 2023-10-24 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 663.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-12-03 | 79 | 57 | 2024-12-03 | 2025-07-02 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | 2025-04-23 | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1112.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-21 | 4 | 4 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2054.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2024-02-02 | 101 | 73 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-08-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14151028 | 394700.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-29 | 2024-12-23 | 270 | 192 | 2024-12-23 | 2025-05-29 | 158 | 114 | 2025-02-03 | 2025-05-27 | 33 | 25 | 2025-05-29 | 2025-09-05 | 22 | 16 | 2025-05-29 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1121.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-23 | 47 | 33 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1265.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-27 | 13 | 9 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 798.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 4181.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2025-04-22 | 243 | 173 | 2025-04-22 | 2025-04-30 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-09 | 17 | 11 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4712.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-09-09 | 34 | 24 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2702.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-06-06 | 85 | 61 | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27867 | 686.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-08-15 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 18.75 | 18.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3136.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-12 | Unknown | Unknown | 2024-10-12 | 2024-10-22 | 11 | 7 | 2024-10-22 | 2025-01-20 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-07-17 | 87 | 63 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 451.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-11-06 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2024-04-15 | 2025-04-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 639220 | 163991.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-06 | 2024-04-15 | 223 | 159 | 2024-04-15 | 2025-04-18 | 369 | 265 | 2024-05-28 | 2025-04-15 | 110 | 80 | 2024-09-17 | 2025-04-24 | 26 | 20 | 2025-04-18 | 2025-07-14 | 88 | 62 | 2025-05-22 | 2025-07-18 | 58 | 42 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 534.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | 2024-02-05 | 202 | 144 | 2025-05-30 | Unknown | Unknown | Unknown | 2025-04-03 | 2025-05-30 | 58 | 42 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | FB 1027-G2 | COUNTY OF SAN DIEGO-NORTH of 56 | 1045 | 1045 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 920919 | 96706.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2024-01-18 | 233 | 167 | 2024-01-18 | 2024-10-17 | 274 | 196 | 2024-03-14 | 2024-11-14 | 87 | 63 | 2024-09-16 | 2025-06-05 | 28 | 22 | 2024-10-17 | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1242.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-05-10 | 53 | 39 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3599 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 41940.2 | 11334.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-07-29 | 75 | 53 | 2024-07-29 | 2025-04-14 | 260 | 186 | 2024-08-06 | 2025-03-27 | 214 | 154 | 2025-03-07 | 2025-03-26 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1778.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-04-09 | 13 | 9 | 2025-04-08 | 2025-04-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | 2025-05-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2022.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-11 | 1 | 1 | 2025-03-11 | 2025-03-11 | 1 | 1 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-05-12 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 477.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-12-02 | 55 | 39 | 2024-12-02 | 2025-07-24 | 235 | 169 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-11 | 33 | 23 | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2505.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-27 | 27 | 19 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | SAN DIEGO | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3111 | 2402.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-10-04 | 5 | 5 | 2024-10-04 | 2024-12-12 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-05-28 | 168 | 120 | Unknown | 2025-08-05 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | Unknown | Unknown | No | 2025-03-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | Yes | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2150.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-07-02 | 121 | 87 | 2025-07-02 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-08-05 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2255.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-10-04 | 15 | 11 | 2024-10-04 | 2024-10-17 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | 2025-06-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26651.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2024-09-27 | 415 | 297 | 2024-09-27 | 2025-05-19 | 235 | 167 | 2024-09-27 | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-12 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 334441 | 129569.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2025-01-09 | 135 | 97 | 2025-01-09 | 2025-05-21 | 133 | 95 | 2025-02-01 | 2025-04-09 | 22 | 16 | 2025-04-09 | 2025-04-14 | 6 | 4 | 2025-05-21 | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 4760.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-06-27 | 94 | 68 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2025-08-22 | 422 | 302 | Unknown | Unknown | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | 2024-06-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1204.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-22 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2023-06-22 | 39 | 29 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2024-06-02 | 347 | 247 | Unknown | 2023-10-17 | Unknown | Unknown | 2024-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | 2024-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | Yes | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1202.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-11-08 | 23 | 17 | 2024-11-08 | 2024-11-14 | 7 | 5 | 2024-11-14 | 2025-02-07 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-07-31 | 252 | 180 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1197.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2024-12-23 | 7 | 5 | 2024-12-23 | 2025-01-21 | 30 | 22 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4770 | 1894.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1300.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-04-24 | 44 | 32 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1650.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-03-06 | 21 | 15 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2633.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-04-25 | 67 | 49 | 2025-04-25 | 2025-04-29 | 5 | 3 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3061.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-14 | 10 | 8 | 2025-02-14 | 2025-02-19 | 6 | 4 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2025-02-18 | 2025-05-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 17923.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2025-04-23 | 324 | 232 | 2025-04-23 | 2025-05-02 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-08 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 498.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2025-04-29 | 215 | 153 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-05-08 | 58 | 42 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-14 | 40 | 28 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 1823 | 1823 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2024-05-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 746.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-19 | 2024-01-31 | 227 | 163 | 2024-01-31 | 2025-07-09 | 526 | 376 | 2025-04-03 | 2025-05-28 | 56 | 40 | 2024-10-22 | 2025-08-07 | 94 | 70 | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1072.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-12-19 | 42 | 30 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1119.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2024-01-03 | 15 | 11 | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Santee | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2024-06-10 | 1 | 1 | 2024-06-10 | 2025-02-19 | 255 | 183 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1107.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-19 | 17 | 13 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1254.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-24 | 16 | 12 | 2024-10-24 | 2024-11-26 | 34 | 24 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-22 | 2023-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46962 | 555.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-22 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-21 | 12 | 10 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1070 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-12-11 | 92 | 66 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 506 | 506 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1117.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-06-11 | 21 | 15 | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-07-22 | 42 | 30 | Unknown | 2025-07-17 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 148.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-25 | 2023-04-27 | 3 | 3 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1150.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-10-14 | 5 | 3 | 2024-10-14 | 2024-11-19 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-13 | 30 | 22 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2650 | 2650 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 3036.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2024-03-19 | 204 | 146 | 2024-03-19 | 2024-04-18 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-04 | 15 | 11 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1437.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-08-29 | 9 | 7 | 2024-08-29 | 2024-09-05 | 8 | 6 | 2024-09-05 | 2024-09-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 316 | 316 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1364.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-11-01 | 82 | 60 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-30 | 2022-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1985.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-30 | 2023-02-27 | 60 | 42 | 2023-02-27 | 2023-03-15 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-03-04 | 6 | 5 | 2023-03-15 | 2023-06-21 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 331 | 331 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-15 | 2023-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 420303 | 76128.93 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-15 | 2023-08-02 | 475 | 339 | 2023-08-02 | 2024-03-21 | 233 | 167 | 2024-03-05 | 2024-03-20 | 15 | 11 | 2023-12-04 | 2024-03-28 | 15 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 242 | 242 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1254.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-12 | 9 | 7 | 2025-02-12 | 2025-05-07 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-27 | 52 | 38 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2022-11-17 | 2025-03-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | 37045.84 | 12515.08 | Unknown | Unknown | -17727.86 | 42258.62 | 0 | 31304.12 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-17 | 2023-02-01 | 77 | 55 | 2023-02-01 | 2023-10-25 | 267 | 191 | 2023-02-14 | 2024-12-28 | 76 | 55 | 2023-03-22 | 2025-03-04 | 127 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-03-21 | 67 | 49 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 103006.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2024-02-01 | 128 | 92 | 2024-02-01 | 2025-01-27 | 362 | 258 | 2024-12-26 | 2025-01-27 | 32 | 22 | 2024-01-31 | 2025-07-16 | 188 | 134 | 2025-03-06 | Unknown | Unknown | Unknown | 2025-03-06 | 2025-08-19 | 167 | 119 | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1844.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-12-09 | 19 | 13 | 2024-12-09 | 2024-12-23 | 15 | 11 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 996 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 699.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-02 | 2023-02-03 | 2 | 2 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | 239 | 239 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1954.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-07-29 | 22 | 16 | 2024-07-29 | 2024-08-29 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2025-03-04 | 88 | 64 | 2024-08-29 | 2025-08-15 | 352 | 252 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | ES 1129-H3 (E) | ES 1129-H3 (E) | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 201779.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-11 | 2024-08-21 | 469 | 335 | 2024-08-21 | 2025-05-06 | 259 | 185 | 2024-08-29 | 2025-03-11 | 125 | 89 | 2024-11-26 | 2025-05-19 | 38 | 28 | 2025-05-06 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 799.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-05-02 | 9 | 7 | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-03-05 | 41 | 29 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | JULIAN | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1621.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | 2025-01-02 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 971.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-08-29 | 9 | 7 | 2024-08-29 | 2024-09-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 95452.63 | 3809.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-15 | 2 | 2 | 2024-05-15 | 2024-07-10 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-14 | 20 | 13 | 2024-07-10 | 2025-07-01 | 357 | 255 | Unknown | 2025-06-23 | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 326863 | 326863 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13730 | 1337.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2025-06-26 | 325 | 233 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-07-08 | 21 | 15 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 897 | 897 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2316.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-12-28 | 25 | 19 | 2023-12-28 | 2024-01-19 | 23 | 17 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2025-07-15 | 566 | 404 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1817.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-19 | 8 | 6 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4606 | 555.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-30 | 2023-08-15 | 78 | 56 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.33 | 662.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-04-15 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-02 | 23 | 17 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 684.05 | 684.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | 2024-11-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | Yes | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1433 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2025-01-15 | 135 | 97 | 2025-01-15 | 2025-03-05 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-25 | 21 | 15 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-24 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1109.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-18 | 10 | 8 | 2025-04-18 | 2025-04-24 | 7 | 5 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-06-17 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1303.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-12 | 7 | 5 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 195.2 | 195.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 125698 | 4536.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2025-02-12 | 547 | 391 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-24 | 18 | 12 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SM 1128-H1 N. CITY PA3 MSO (E) | SM 1128-H1 N. CITY PA3 MSO (E) | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 139579 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2025-02-06 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-07-03 | 23 | 17 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1478.1 | 1478.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 834.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-04-18 | 29 | 21 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-07-25 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 200007 | 200007 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11851.63 | 5111.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-10-10 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-08-04 | 299 | 213 | Unknown | 2025-08-04 | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 695.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | 2025-05-29 | 225 | 161 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-14 | 30 | 22 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 26.05 | 26.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2239.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-04-09 | 92 | 66 | 2025-04-09 | 2025-04-18 | 10 | 8 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-05-23 | Unknown | Unknown | 2023-05-23 | 2023-08-01 | 71 | 51 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1436.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-08-17 | 2 | 1 | 2024-08-17 | 2024-08-17 | 1 | 0 | 2024-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-17 | 2025-08-08 | 357 | 255 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 699.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-23 | 2023-02-03 | 12 | 10 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 569283 | 43641.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-05 | 14 | 10 | 2023-10-05 | 2023-10-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2025-07-15 | 638 | 456 | Unknown | 2025-08-14 | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-01 | 2021-10-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 411379.62 | Unknown | Unknown | Yes | N/A | N/A | 2021-10-01 | 2023-04-06 | 553 | 395 | 2023-04-06 | 2023-05-17 | 42 | 30 | 2023-04-28 | 2023-05-01 | 4 | 2 | 2023-05-17 | 2023-06-16 | 31 | 23 | 2023-05-25 | Unknown | Unknown | Unknown | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 77.75 | 77.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | 2024-11-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | Yes | 81 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1615.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2025-01-06 | 64 | 46 | 2025-01-06 | 2025-01-24 | 19 | 15 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-07-30 | 248 | 178 | Unknown | 2025-05-29 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 894.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-10-02 | 21 | 15 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1537.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4172.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-18 | 14 | 10 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1476.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 231.07 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-27 | 2023-02-28 | 2 | 2 | 2023-02-28 | 2023-11-21 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2922.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1568.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | 2024-11-20 | 22 | 16 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4511.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-11-21 | 37 | 27 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2024-01-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1297.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2024-04-15 | 286 | 204 | 2024-04-15 | 2024-04-24 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-15 | 17 | 13 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1743.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-02-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-02-27 | IOU Designed & Installed | N/A | No | Unknown | 11270.75 | 2309.73 | Unknown | 608.64 | 134.13 | 8218.25 | 3981 | 1790.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-27 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1860.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-31 | 8 | 6 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-13 | Unknown | Customer elected Applicant Install | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 423503 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-06-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 996.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-08-30 | 86 | 62 | 2024-08-30 | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-17 | 19 | 13 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3020.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2024-12-16 | 12 | 8 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-08-06 | 234 | 168 | Unknown | 2025-07-31 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | Unknown | Unknown | No | 2025-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | Unknown | IOU Designed & Installed | N/A | Yes | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2025-04-02 | 120 | 86 | 2025-04-02 | 2025-06-06 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-25 | 18 | 14 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 2725.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1733.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-10-18 | 45 | 33 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 352.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-31 | 2023-04-03 | 4 | 2 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | Applicant Design | Commercial | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 375998 | 65262.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2025-01-02 | 171 | 123 | 2025-01-02 | 2025-06-26 | 176 | 126 | 2025-01-13 | 2025-02-13 | 32 | 24 | 2025-01-24 | 2025-07-15 | 106 | 72 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1223.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-13 | 11 | 9 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 139 | 139 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1135.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-10-18 | 53 | 39 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | 2025-03-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 656.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-02-03 | 56 | 40 | 2025-02-03 | 2025-02-19 | 17 | 13 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-19 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1149.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-09-11 | 35 | 25 | 2024-09-11 | 2024-09-16 | 6 | 4 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 558.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-28 | 2 | 2 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-15 | 34 | 24 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-09-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1386.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-06-19 | 2 | 2 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-09-04 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54614 | 47957.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | 2025-01-23 | 232 | 166 | 2024-08-23 | 2025-01-22 | 10 | 8 | 2024-12-31 | 2025-02-04 | 28 | 20 | 2025-01-23 | 2025-06-10 | 139 | 99 | 2025-02-05 | 2025-06-04 | 120 | 86 | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 778.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-17 | 20 | 14 | 2025-06-17 | 2025-06-26 | 10 | 8 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-14 | 19 | 13 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-12 | 2022-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2291.46 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-12 | 2023-12-05 | 420 | 300 | 2023-12-05 | 2023-12-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 3722.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-03-03 | 7 | 5 | 2025-03-03 | 2025-03-04 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-12 | 16 | 12 | 2025-03-04 | 2025-07-02 | 121 | 87 | Unknown | 2025-07-02 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Santee | CALTRANS-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 133138.18 | 34924.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-08-07 | 70 | 50 | 2024-08-07 | 2025-09-03 | 393 | 281 | 2024-12-06 | 2024-12-13 | 8 | 6 | 2025-01-11 | 2025-03-18 | -11 | -15 | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 501.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-06-11 | 41 | 29 | 2025-06-11 | 2025-06-23 | 13 | 9 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 582.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-12-20 | 64 | 46 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1839.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1065774 | 162593.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2025-01-09 | 56 | 40 | 2025-01-09 | 2025-05-27 | 139 | 99 | 2025-02-01 | 2025-05-23 | 26 | 20 | 2025-04-09 | 2025-04-15 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 819.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-02-15 | 16 | 12 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 572.83 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-19 | 2023-03-07 | 232 | 166 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-11-14 | IOU Designed & Installed | N/A | No | Unknown | 12823.78 | 2402.08 | Unknown | 134.83 | 700.68 | 9586.19 | 3981 | 2214.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-08-27 | 64 | 46 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-11-14 | 80 | 58 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SD 1128-H1 n. city PA3B (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 304216.27 | 56110.12 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-07 | 2024-06-12 | 554 | 396 | 2024-06-12 | 2024-12-30 | 202 | 144 | 2024-06-19 | 2025-02-19 | 84 | 60 | 2024-07-02 | 2025-06-26 | 67 | 51 | 2025-02-04 | Unknown | Unknown | Unknown | 2025-02-04 | 2025-08-01 | 179 | 129 | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 961.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-07 | 2023-06-15 | Unknown | Unknown | 2023-06-15 | 2023-09-28 | 106 | 76 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1191.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-07-24 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-03-17 | 2020-03-24 | 2024-11-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 248750 | 129146.5 | Unknown | Unknown | Yes | N/A | N/A | 2020-03-17 | 2024-02-15 | 1431 | 1023 | 2024-02-15 | 2024-05-17 | 93 | 67 | 2024-03-01 | 2025-07-21 | 21 | 15 | 2023-07-19 | 2024-05-10 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2025-08-11 | 448 | 320 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 232 | 232 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1460.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-23 | 9 | 7 | 2024-07-23 | 2024-08-01 | 10 | 8 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 477.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-09-30 | 8 | 6 | 2024-09-24 | 2024-09-25 | 2 | 2 | 2024-09-25 | 2024-10-04 | 10 | 8 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 237 | 237 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1423.6 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-19 | 2023-04-17 | 211 | 151 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 32181.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2025-03-03 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-06 | 25 | 19 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2572.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-09-02 | Unknown | Unknown | 2024-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-04 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3477.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-06-09 | 13 | 9 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2853.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-12 | 2 | 2 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 946.05 | 946.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2025-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 2242.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2025-01-13 | 392 | 280 | 2025-01-13 | 2025-04-04 | 82 | 60 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-08-11 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 1238.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-10-11 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-19 | 2022-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 327.46 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-19 | 2023-03-13 | 329 | 235 | 2023-03-13 | 2023-03-14 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 2504.05 | 2504.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-06-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-03-29 | 93 | 67 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-06-06 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1718.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-05-02 | 197 | 141 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | NCTD-Trolly South of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-25 | 2025-03-02 | IOU Designed & Installed | N/A | No | Unknown | 44742.97 | 8920.98 | Unknown | 605.84 | 2303.32 | 32912.83 | 5621 | 7000.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-08-15 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-10-30 | 163 | 117 | 2024-08-15 | Unknown | Unknown | Unknown | 2024-09-19 | 2025-01-17 | 121 | 87 | 2025-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 602 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2025-07-25 | 2 | 2 | 2024-08-05 | 2025-08-06 | 141 | 101 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | IMPERIAL BEACH, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 104250 | 30606.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-06 | 2023-06-07 | 2 | 2 | 2023-06-07 | Unknown | Unknown | Unknown | 2023-02-20 | 2024-03-11 | 386 | 276 | 2024-03-21 | 2024-07-12 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1314.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-07-28 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 50.75 | 50.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1570.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | 2025-03-20 | 4 | 4 | 2025-03-20 | 2025-04-18 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 883.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-25 | 16 | 12 | 2025-04-25 | 2025-05-19 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-27 | 2025-05-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1718.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-02-28 | 16 | 12 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-05-12 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1443.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-05-21 | 42 | 30 | 2025-05-21 | 2025-05-21 | 1 | 1 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 475.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-10-26 | 16 | 12 | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | 2024-02-14 | 7 | 5 | 2023-10-26 | 2024-10-04 | 342 | 245 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 347915 | 63050.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-03-27 | 65 | 47 | 2025-03-27 | 2025-04-15 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | 220 | 220 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 114507 | 37132.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-09-23 | 39 | 27 | 2025-07-10 | 2025-07-17 | 8 | 6 | 2024-09-24 | 2025-07-30 | 125 | 91 | 2024-09-23 | 2025-08-28 | 340 | 244 | 2025-06-13 | 2025-06-25 | 13 | 9 | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1316.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | 2025-07-02 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-09 | 8 | 6 | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1008.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-05-12 | 88 | 62 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-08-08 | 89 | 65 | Unknown | 2025-07-30 | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | 2025-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1864.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-03-29 | Unknown | Unknown | 2025-03-29 | 2025-04-14 | 17 | 11 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-06-05 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-08-06 | 42 | 30 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 456.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-07 | 2023-02-07 | 1 | 1 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | PALA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | 2023-05-26 | 2025-03-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 53643 | 159566.26 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-27 | 2023-05-26 | 212 | 152 | 2023-05-26 | 2025-03-11 | 656 | 468 | 2023-07-14 | 2025-02-11 | 96 | 68 | 2023-08-15 | 2025-07-28 | 472 | 337 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | COUNTY OF SAN DIEGO-SOUTH of 56, NATIONAL CITY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 3252.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-04-11 | 44 | 32 | 2025-04-11 | 2025-05-09 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-04-09 | 37 | 27 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2024-09-20 | 138 | 100 | 2024-09-20 | 2024-10-15 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-10-10 | 55 | 41 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 621.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-09-24 | 104 | 74 | 2024-09-24 | 2024-11-08 | 46 | 34 | 2024-10-02 | 2024-11-11 | 32 | 22 | 2024-10-01 | 2024-11-13 | 16 | 14 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 161 | 161 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1343.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-05-01 | 14 | 10 | 2025-05-01 | 2025-05-23 | 23 | 17 | 2025-04-24 | 2025-05-23 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-07-22 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1904.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-04-09 | 66 | 48 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 142.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2023-08-30 | 57 | 41 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | ALPINE | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 892.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-27 | 9 | 7 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-03-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 778.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-09-12 | 372 | 266 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2025-02-25 | 5 | 3 | 2025-02-25 | 2025-02-26 | 2 | 2 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-08-01 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1452.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | 2025-05-30 | 2 | 2 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 144.1 | 144.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2025-06-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1960.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-02-23 | 18 | 14 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2025-06-12 | 476 | 340 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1642.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-03-17 | 26 | 18 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | Lakeside | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1583.57 | 27584.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-16 | 2 | 2 | 2024-02-16 | 2025-05-29 | 469 | 335 | 2024-12-05 | 2025-05-27 | 170 | 120 | 2025-05-28 | 2025-09-08 | 104 | 74 | 2025-05-29 | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 826.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2023-08-01 | 2 | 2 | 2023-08-01 | 2023-10-25 | 86 | 62 | 2023-08-02 | 2023-08-23 | 15 | 11 | 2023-08-14 | 2023-08-30 | 17 | 13 | 2023-10-25 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4964.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2024-03-05 | 56 | 40 | 2024-03-05 | 2024-03-29 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1770.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-04-30 | 82 | 58 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2025-07-03 | 430 | 308 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1171.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | 2024-09-16 | 60 | 42 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | Unknown | Unknown | No | 2024-10-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2025-02-10 | IOU Designed & Installed | N/A | Yes | 118 | 256.65 | -4.5 | Unknown | Unknown | 17.4 | 243.75 | 3981 | 1056.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2025-02-10 | 119 | 85 | 2025-02-10 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-02-10 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | 2025-05-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1339.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-06-06 | 16 | 12 | 2025-06-06 | 2025-05-30 | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-08-12 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3264.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-22 | 2023-08-02 | 42 | 30 | 2023-08-02 | 2024-06-19 | 323 | 231 | 2024-03-26 | 2024-03-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2025-08-04 | 412 | 294 | Unknown | 2025-07-02 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1188.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-19 | 2024-03-29 | 11 | 9 | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 646.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2024-01-31 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Commercial | Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | 772 | 772 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12515.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2025-01-23 | 310 | 222 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2024-06-25 | 2025-04-09 | 108 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 611 | 611 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2053.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-18 | 2023-08-21 | 4 | 2 | 2023-08-21 | 2023-08-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 11.35 | 11.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1539.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-06-16 | 53 | 37 | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-14 | 2025-08-04 | 52 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 125.1 | 125.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-10-18 | 2025-07-01 | IOU Designed & Installed | N/A | No | Unknown | 110 | 0 | Unknown | Unknown | 53.32 | 56.68 | 3981 | 1160.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-10-15 | 23 | 17 | 2024-10-15 | 2024-10-18 | 4 | 4 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-07-01 | 257 | 183 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 347 | 347 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 882.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 1562.05 | 1562.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1992.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 118374.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2025-05-06 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-23 | 15 | 11 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 33.35 | 33.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 495.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-05-05 | 38 | 28 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | GUATAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 817.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-04-24 | 42 | 30 | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2251.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-04 | 2023-05-12 | 9 | 7 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 220741 | 18234.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | 2024-09-04 | 374 | 268 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1692.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-17 | 13 | 9 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-08-06 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1037.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-04-04 | 39 | 29 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 191730.77 | 82034.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-25 | 6 | 4 | 2024-11-25 | 2025-04-16 | 143 | 103 | 2025-01-29 | 2025-03-18 | 3 | 3 | 2025-04-15 | 2025-04-21 | 7 | 5 | 2025-04-16 | 2025-07-10 | 86 | 62 | 2025-04-24 | 2025-07-15 | 83 | 59 | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1182.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-14 | 14 | 10 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-10-14 | 105 | 75 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1622.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-09-20 | 78 | 56 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2025-09-03 | 349 | 249 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1561.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-12-03 | 201 | 143 | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 92.05 | 92.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1233.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-26 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-28 | 7 | 5 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1165.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1020.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1990.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-02-18 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-15 | 24 | 17 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19955.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2025-06-19 | 207 | 149 | Unknown | Unknown | Unknown | Unknown | 2024-12-14 | 2025-06-06 | 175 | 125 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2025-05-20 | 215 | 153 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6000 | 6000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2025-05-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1847.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2025-05-22 | 613 | 439 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 |  | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1522.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2025-06-25 | 303 | 217 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1583.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-11-19 | 21 | 15 | 2024-11-19 | 2024-12-09 | 21 | 15 | 2024-12-09 | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-17 | 9 | 7 | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1384.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-02-11 | Unknown | Unknown | 2024-02-11 | 2025-05-19 | 464 | 331 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-07-16 | 143 | 103 | Unknown | 2025-07-10 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3324.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-06 | 28 | 20 | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 3733 | 3733 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 18086.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2025-02-24 | 376 | 268 | 2024-08-07 | 2025-02-18 | 21 | 13 | 2024-09-10 | 2025-01-13 | 43 | 31 | 2025-02-24 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 871.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-17 | 2023-04-06 | 21 | 15 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2025-08-08 | 856 | 612 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 33438.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-27 | 3 | 3 | 2024-11-27 | 2025-06-13 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | Unknown | Unknown | No | 2024-11-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | Yes | 114 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1253.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2025-03-19 | 139 | 99 | 2025-03-19 | 2024-12-13 | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 403867.6 | 42909 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2024-06-10 | 1 | 1 | 2024-06-10 | 2024-06-21 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2025-09-02 | 439 | 313 | Unknown | 2025-07-31 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2210.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-29 | 14 | 10 | 2025-04-29 | 2025-05-20 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-07-30 | 69 | 49 | Unknown | 2025-07-30 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1303.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-02-28 | 72 | 52 | 2025-02-28 | 2025-03-04 | 5 | 3 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-08-07 | 157 | 113 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 507.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-09-25 | 51 | 37 | 2024-09-25 | 2024-12-26 | 93 | 67 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1045.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-09 | Unknown | Unknown | 2025-06-09 | 2025-06-18 | 10 | 8 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 90.05 | 90.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3514.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-09-20 | 142 | 102 | 2024-09-20 | 2025-06-16 | 270 | 192 | 2025-06-02 | 2025-06-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | 6169 | 6169 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1950.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2023-12-14 | 9 | 7 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-16 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1464.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-12-09 | 40 | 28 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 933.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-15 | 49 | 35 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1558.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-09-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 55.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2023-05-01 | Unknown | Unknown | 2023-05-01 | 2023-09-19 | 142 | 102 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 877.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2025-01-10 | 23 | 17 | 2025-01-10 | 2025-01-28 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-28 | 2025-05-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1906.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-25 | 6 | 4 | 2025-02-25 | 2025-02-28 | 4 | 4 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-05-22 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1906.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 6300 | 6300 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2154 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2025-01-08 | 463 | 331 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2025-06-12 | 30 | 22 | 2025-01-08 | 2025-09-02 | 238 | 170 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 126.05 | 126.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 38964.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-01-09 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1672.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-13 | 11 | 9 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-05-01 | 71 | 51 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2025-08-28 | 485 | 347 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1954.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-20 | 3 | 3 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1070.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-07-08 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1154.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-08-08 | 46 | 34 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1434.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-27 | 17 | 13 | 2025-06-11 | 2025-07-31 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 263.12 | 263.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 58895.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2025-01-30 | 49 | 35 | 2025-01-30 | 2025-04-18 | 79 | 57 | 2025-04-09 | 2025-04-16 | 8 | 6 | 2025-01-31 | 2025-04-24 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-11 | 2023-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 311.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-11 | 2023-03-11 | 1 | 0 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | N/A | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6648 | 708.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-19 | 2024-05-22 | 125 | 89 | 2024-05-22 | 2024-09-27 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2025-06-13 | 260 | 186 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 138.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1178.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-07-06 | 20 | 15 | 2024-07-06 | 2024-07-11 | 6 | 4 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 206 | 206 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3293.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2025-05-14 | 672 | 480 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-12 | 30 | 22 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1455.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-10-21 | 82 | 58 | 2024-10-21 | 2024-10-24 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-20 | 29 | 21 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1045.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-04 | Unknown | Unknown | 2025-06-04 | 2025-06-23 | 20 | 14 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 129179 | 11699.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | 2024-12-03 | 327 | 233 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-12-12 | 36 | 26 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 500.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-01 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1570.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-01 | 2024-12-17 | 17 | 12 | 2024-12-17 | 2025-01-07 | 22 | 16 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-08-15 | 221 | 159 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 355.1 | 355.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 876.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2025-01-22 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-11 | 21 | 15 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | SANTA YSABEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 178241.38 | 16421.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2025-04-03 | 316 | 226 | 2025-01-16 | 2025-02-11 | 27 | 19 | 2025-02-28 | 2025-03-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2779.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-31 | 2023-09-12 | 13 | 9 | 2023-09-12 | 2024-01-23 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2025-05-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1177.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2025-05-21 | 420 | 300 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 126475 | 28709.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-03-18 | 68 | 48 | 2024-03-18 | 2025-05-05 | 414 | 296 | 2024-05-02 | 2024-06-05 | 35 | 25 | 2025-03-05 | 2025-05-09 | 22 | 16 | 2025-05-05 | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 70.1 | 70.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1065.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2025-06-06 | 180 | 130 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1318.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-26 | 3 | 3 | 2025-03-26 | 2025-04-08 | 14 | 10 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1737.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-06-11 | 44 | 32 | 2025-06-11 | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-08 | 27 | 19 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1150.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 642.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-17 | 2023-04-18 | 33 | 23 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 511.05 | 511.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1190.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-26 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-26 | 11 | 9 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-12-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 332.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-12-04 | 20 | 14 | 2023-12-04 | 2023-12-07 | 4 | 4 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 55734 | 2625.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | 2023-04-17 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-07-12 | 86 | 62 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 128772 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-03-25 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3571.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 7004 | 7004 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-16 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2368.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-05-16 | 26 | 20 | 2025-05-16 | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-02 | 15 | 11 | 2025-05-16 | 2025-06-24 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23513.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-03-27 | 52 | 38 | 2024-03-27 | 2025-02-20 | 331 | 237 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2025-01-29 | 2025-03-06 | 31 | 23 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 27.05 | 27.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2024-08-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1676.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-09-26 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2806.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-12-13 | 37 | 27 | 2024-12-13 | 2025-01-13 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-06-17 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1190.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-06-05 | 16 | 12 | 2025-06-05 | 2025-06-17 | 13 | 9 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-19 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 447.15 | 447.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | Unknown | Unknown | No | 2025-01-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | Yes | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1259.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-04-11 | 100 | 72 | 2025-04-11 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 983.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-02-12 | 5 | 3 | 2024-02-12 | 2024-02-23 | 12 | 10 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27641 | 29617.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2024-01-09 | 103 | 73 | 2024-01-09 | 2024-08-15 | 220 | 158 | 2024-01-23 | 2024-09-04 | 51 | 37 | 2024-08-02 | 2024-09-05 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 926.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2024-02-01 | 11 | 9 | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1679.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-02-11 | 41 | 29 | 2025-02-11 | 2025-07-02 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-13 | 23 | 17 | 2025-07-02 | 2025-07-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1345.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2024-04-04 | 45 | 33 | 2024-04-04 | 2024-04-18 | 15 | 11 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1024.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-21 | 15 | 11 | 2025-05-21 | 2025-05-23 | 3 | 3 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-08-11 | 81 | 57 | Unknown | 2025-08-01 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-24 | 2025-05-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1663.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-24 | 5 | 3 | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-05-12 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 159.05 | 159.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 14222.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-08-09 | 243 | 175 | 2024-04-02 | 2024-08-06 | 127 | 91 | 2024-06-19 | 2024-06-27 | 9 | 7 | 2024-08-09 | 2025-07-23 | 349 | 249 | 2024-08-20 | 2025-08-06 | 352 | 252 | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-11-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-11-21 | 48 | 34 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1683.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-02-05 | 2 | 2 | 2025-02-05 | 2025-02-10 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-06 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | 570.47 | 0 | Unknown | Unknown | Unknown | 570.47 | 0 | 515.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-12-13 | 101 | 73 | 2025-04-17 | 2025-05-15 | 29 | 21 | 2025-05-15 | 2025-06-06 | 23 | 17 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1913.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 474380 | 15981.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-05-15 | 29 | 21 | 2025-05-15 | 2025-05-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-08-05 | 83 | 59 | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1784.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-26 | 23 | 17 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 2456.05 | 2456.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1026.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2025-01-06 | 365 | 261 | 2025-01-06 | 2025-01-10 | 5 | 5 | 2025-01-10 | 2025-06-09 | 151 | 107 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-08-28 | 80 | 58 | Unknown | 2025-08-13 | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | 2023-08-01 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-07-26 | 8 | 6 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 377.2 | 377.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47772 | 43604.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-07-09 | 63 | 45 | 2024-07-09 | 2025-02-24 | 231 | 165 | 2024-10-23 | 2025-02-21 | 82 | 60 | 2024-10-25 | 2025-02-12 | 107 | 77 | 2025-02-24 | 2025-04-01 | 37 | 27 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 193.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1412.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-14 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-06-14 | 45 | 33 | 2024-06-14 | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-28 | 15 | 11 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2500.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-17 | 2024-08-29 | 44 | 32 | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2023-09-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 564 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 484.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-03-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 77.1 | 77.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 478.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-16 | 2023-07-17 | 32 | 22 | 2023-07-17 | 2024-10-03 | 445 | 319 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2024-03-03 | IOU Designed & Installed | N/A | No | Unknown | 453.54 | 256.62 | Unknown | 8.51 | Unknown | 188.41 | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2024-02-16 | 152 | 110 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-03 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 697.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-05-02 | 23 | 17 | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-05-02 | 2025-05-07 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-08-04 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-16 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 851.47 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-16 | 2023-08-31 | 289 | 207 | 2023-08-31 | 2024-06-11 | 286 | 204 | 2025-07-11 | 2025-07-21 | 11 | 7 | 2024-05-31 | 2025-07-30 | 49 | 35 | 2024-06-11 | 2025-09-05 | 452 | 324 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 245 | 245 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 1447.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-07-10 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-07-05 | 31 | 23 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-05 | 2025-06-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2322.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-10 | 7 | 5 | 2025-03-10 | 2025-04-01 | 23 | 17 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-06-06 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 589.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-04-18 | 64 | 46 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-08-08 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2024-10-18 | 130 | 94 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-07-08 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1248.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-14 | 9 | 7 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1520.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-10 | 8 | 6 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 553.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-06-20 | 2 | 2 | 2024-06-20 | 2024-11-06 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47982 | 2232.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | 2025-07-31 | 724 | 518 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2025-08-14 | 296 | 212 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 670.05 | 670.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1437.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2025-08-04 | 707 | 505 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 166 | 166 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3198.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-03-06 | 24 | 18 | 2024-03-06 | 2024-03-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-03-14 | 8 | 6 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 936.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2025-04-08 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-22 | 22 | 16 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 255 | 255 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-05-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1812.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-14 | 15 | 11 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1336.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-08-14 | 29 | 21 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | 2022-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 339.19 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-25 | 2023-05-23 | 303 | 217 | 2023-05-23 | 2023-07-03 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-05-18 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-02-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1780673 | 47901.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-02-14 | 23 | 17 | 2025-02-14 | 2025-05-21 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2265.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-01-03 | 26 | 20 | 2025-01-03 | 2025-05-06 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-07-21 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | Valley Center | COUNTY OF SAN DIEGO-NORTH of 56 | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 100376 | 17652.75 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-29 | 2023-07-18 | 202 | 144 | 2023-07-18 | 2023-10-10 | 85 | 61 | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-09-20 | 2023-10-19 | 27 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-03 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1611.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-04-03 | 11 | 9 | 2025-04-03 | 2025-05-20 | 5 | 3 | 2025-05-02 | 2025-05-16 | 15 | 11 | 2025-04-03 | 2025-06-18 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-03 | 2024-12-05 | IOU Designed & Installed | N/A | No | Unknown | 58.78 | 0 | Unknown | Unknown | 24.88 | 33.9 | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-05-03 | 22 | 16 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-12-05 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 140 | 140 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1128.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-12-19 | 97 | 69 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-12-10 | 2025-01-10 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1324.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-10 | 6 | 4 | 2024-09-10 | 2025-01-09 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-01-09 | 2025-01-09 | 1 | 1 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1720.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-03-14 | 43 | 31 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1441.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-19 | 16 | 12 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-08-12 | 147 | 105 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 51916.2 | 51916.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1921.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-01-24 | 9 | 7 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-06-11 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1633.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-02-26 | 13 | 9 | 2024-02-26 | 2024-03-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-12 | 15 | 11 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2782.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 452.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-06-02 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1224.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-13 | 1 | 1 | 2025-05-13 | 2025-05-13 | 1 | 1 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-03-29 | 116 | 84 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7853 | 692.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-06-16 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 17710.6 | 1616.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-12 | 2024-02-14 | 34 | 24 | 2024-02-14 | 2024-08-15 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 637.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-05-04 | 24 | 18 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1374.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-27 | 2024-06-25 | 212 | 152 | 2024-06-25 | 2024-07-25 | 31 | 23 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1433.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2025-01-09 | 23 | 17 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-05-28 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 445.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2024-01-26 | 45 | 33 | 2024-01-26 | 2024-02-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-16 | 5 | 3 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 713.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-17 | 2023-04-17 | 1 | 1 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1012.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-10 | 15 | 11 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-25 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1654.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-06-24 | 25 | 17 | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-30 | 2024-05-13 | IOU Designed & Installed | N/A | No | Unknown | 1298.14 | -35.92 | Unknown | Unknown | 260.37 | 1073.69 | 2841 | 578.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-24 | 2023-04-30 | 7 | 5 | 2023-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-13 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | LA MESA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2009.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-03 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-07-07 | 89 | 65 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | santee | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-06-13 | 86 | 62 | 2024-06-13 | 2024-06-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-14 | 19 | 13 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 504 | 504 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 67000.85 | 64351.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2024-07-05 | 15 | 11 | 2024-07-05 | 2025-01-16 | 196 | 140 | 2024-10-15 | 2024-11-01 | 18 | 14 | 2024-12-19 | 2025-02-07 | 30 | 21 | 2025-01-16 | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 120.05 | 120.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3891 | 3283.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-03-03 | 19 | 13 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 128 | 128 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | 2024-02-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-02 | 2024-07-29 | IOU Designed & Installed | N/A | Yes | 58 | 753.7 | -15.39 | Unknown | Unknown | Unknown | 769.09 | 3981 | 981.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-04-16 | 56 | 40 | 2024-04-16 | 2024-04-19 | 4 | 4 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-07-29 | 150 | 106 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-03 | 2025-03-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4756.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-29 | Unknown | Unknown | 2025-01-29 | 2025-03-13 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 781.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2024-02-07 | 106 | 76 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3222.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | 2024-07-17 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-24 | 27 | 19 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 881.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-15 | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2024-01-22 | 109 | 77 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 529628 | 39266.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-06-19 | 5 | 3 | 2023-06-19 | 2023-07-21 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-12 | 7 | 5 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 489.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-03-03 | 54 | 38 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-06-17 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1619.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-29 | 8 | 6 | 2024-10-29 | 2024-11-01 | 4 | 4 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 762.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-15 | 2023-05-26 | 12 | 10 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | 4127 | 4127 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-13 | 2024-01-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 71955.32 | Unknown | Unknown | Yes | N/A | N/A | 2021-07-13 | 2024-08-02 | 1117 | 799 | 2024-08-02 | 2025-05-02 | 274 | 196 | 2024-08-14 | 2025-04-24 | 100 | 72 | 2024-12-21 | 2025-01-24 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1742.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-05-08 | 8 | 6 | 2024-05-08 | 2024-05-31 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-05-30 | 15 | 11 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | Unknown | Unknown | No | 2023-04-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | Yes | 490 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 264533 | 40399.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-10 | 2024-07-16 | 464 | 332 | 2024-07-16 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | 400.05 | 400.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | Unknown | Unknown | No | 2024-08-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | Yes | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1852.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2025-03-05 | 206 | 148 | 2025-03-05 | 2025-03-27 | 23 | 17 | 2025-01-13 | 2025-01-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-07-24 | 120 | 86 | Unknown | 2025-07-10 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 221.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2023-10-25 | 17 | 13 | 2023-10-25 | 2023-11-20 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | 2023-12-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | Yes | 137 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 197328.79 | 84686.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2024-04-11 | 247 | 177 | 2024-04-11 | 2025-01-22 | 287 | 205 | 2024-07-25 | 2025-07-07 | 38 | 28 | 2024-08-02 | 2025-01-30 | 29 | 17 | 2025-03-24 | Unknown | Unknown | Unknown | 2025-03-24 | 2025-08-25 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 949.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 397.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-30 | 15 | 11 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 13.4 | 13.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1214.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-07 | 1 | 1 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 18676 | 18676 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2024-10-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 270.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | 2023-09-07 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42.4 | 42.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1846.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-19 | 23 | 17 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-07-17 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.4 | 58.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-03-13 | 2024-06-12 | IOU Designed & Installed | N/A | No | Unknown | 2020.1 | 614.03 | Unknown | Unknown | 69.69 | 1336.38 | 15764 | 1005.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2024-04-18 | 221 | 159 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1595.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | 2025-05-29 | 2 | 2 | 2025-05-29 | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-23 | 20 | 14 | 2025-05-29 | 2025-08-20 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 211390.62 | 129540.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-05 | 2024-07-23 | 201 | 143 | 2024-07-23 | 2025-04-17 | 269 | 193 | 2024-08-19 | 2025-03-26 | 6 | 6 | 2024-10-07 | 2025-05-08 | 28 | 22 | 2025-09-09 | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1620.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-07-16 | 106 | 76 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4196.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2024-06-25 | 5 | 3 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16952.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2024-10-17 | 549 | 393 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-18 | Unknown | Unknown | No | 2022-05-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-08-31 | Unknown | IOU Designed & Installed | N/A | Yes | 936 | 22078.53 | 0 | Unknown | Unknown | 4670.33 | 17408.2 | 0 | 25575.49 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-12 | 2024-12-03 | 937 | 669 | 2024-12-03 | Unknown | Unknown | Unknown | 2022-11-18 | 2025-03-04 | 36 | 26 | 2025-02-18 | 2025-02-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 512810 | 16068.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-05-07 | 159 | 113 | 2024-05-07 | 2024-08-20 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-05-31 | 3 | 3 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | N/A | San Diego | San Diego | 38528 | 38528 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-12 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2078706 | 48119.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-12 | 2024-02-21 | 255 | 183 | 2024-02-21 | 2025-03-05 | 379 | 271 | 2024-02-28 | 2025-02-04 | 88 | 59 | 2024-04-15 | 2025-03-05 | 105 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2025-02-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3630.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3762.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2024-12-16 | 47 | 33 | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 680.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-02-13 | 1 | 1 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | santee | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24275.9 | 58758.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-09-21 | 44 | 32 | 2023-09-21 | 2024-06-20 | 274 | 196 | 2024-01-26 | 2024-06-13 | 39 | 29 | 2024-04-26 | 2024-07-08 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1390.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-22 | 13 | 9 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 1056 | 1056 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 2374.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2024-01-18 | 52 | 38 | 2024-01-18 | 2024-02-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-31 | 13 | 9 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2234.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-07 | 2023-12-12 | 6 | 4 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1768.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-04-09 | 17 | 13 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3264.48 | 17286.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2025-07-02 | 213 | 153 | 2025-06-09 | 2025-06-20 | 12 | 10 | 2025-03-28 | 2025-07-02 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1482.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-27 | 5 | 5 | 2025-06-20 | 2025-08-12 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | N/A | POWAY | POWAY | 2915 | 2915 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-04-29 | 2025-03-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 120953 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-06-12 | 118 | 84 | 2024-06-12 | 2025-03-17 | 279 | 199 | 2024-07-30 | 2025-05-09 | 18 | 14 | 2024-09-08 | 2025-05-14 | 227 | 160 | 2025-03-17 | 2025-06-19 | 95 | 69 | 2025-04-18 | 2025-06-23 | 67 | 47 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-11-13 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 2390.61 | Unknown | Unknown | Yes | N/A | N/A | 2020-11-13 | 2023-05-30 | 929 | 663 | 2023-05-30 | 2023-06-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | GUATAY | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14876 | 3034.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-04-11 | 20 | 14 | 2023-04-11 | 2023-06-28 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2945.91 | 32870 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-01 | 2023-09-07 | 99 | 71 | 2023-09-07 | 2024-10-17 | 407 | 291 | 2024-01-16 | 2025-06-04 | 116 | 84 | 2024-03-05 | 2024-09-20 | 32 | 24 | 2024-10-17 | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 132931 | 4742.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-04-08 | 49 | 35 | 2025-04-08 | 2025-06-06 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-04-30 | 10 | 8 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 88734.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-18 | 2023-04-18 | 152 | 108 | 2023-04-18 | 2024-10-17 | 549 | 393 | 2023-09-25 | 2024-10-15 | 32 | 24 | 2024-06-21 | 2024-11-05 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 86173.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-11-20 | 289 | 207 | 2024-11-20 | 2025-06-17 | 210 | 150 | 2024-12-06 | 2025-05-30 | 90 | 66 | 2025-01-30 | 2025-06-04 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 700.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-02 | 2023-07-06 | 66 | 48 | 2023-07-06 | 2023-07-06 | 1 | 1 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-03-19 | 2025-05-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3872.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-03-28 | 32 | 24 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1013.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-26 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-08-14 | 142 | 102 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1270.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2024-04-18 | 161 | 115 | 2024-04-18 | 2024-04-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-12-22 | 2024-04-16 | 117 | 83 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56, ESCONDIDO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1987.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2025-04-02 | 329 | 235 | 2025-04-02 | 2025-04-03 | 2 | 2 | 2025-04-03 | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-15 | 13 | 9 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1150.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-04-19 | 26 | 20 | 2024-04-19 | 2024-04-19 | 1 | 1 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6016.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1166.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-30 | 11 | 9 | 2025-05-30 | 2025-05-29 | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | Unknown | Unknown | No | 2025-04-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-06-11 | IOU Designed & Installed | N/A | Yes | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1654.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-10 | 3 | 3 | 2025-04-10 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-06-11 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-22 | 2024-03-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 644.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-22 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-04-03 | 139 | 99 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 119.1 | 119.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3050.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-01-30 | 4 | 4 | 2025-01-30 | 2025-06-03 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Rancho Mission Viejo | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-06-16 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | 430 | 430 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 607.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-05-07 | 22 | 16 | 2025-05-07 | 2025-05-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-12 | 12 | 8 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 732 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-10-18 | 30 | 22 | 2023-10-18 | 2024-08-20 | 308 | 220 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RSF 1188-G1 (E) | N/A | 160.05 | 160.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 227 | 10455.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2025-02-05 | 149 | 107 | 2024-11-18 | 2024-11-18 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 164.05 | 164.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1076.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-06-08 | 94 | 67 | 2024-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-08 | 2025-09-04 | 454 | 324 | Unknown | 2025-08-28 | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | 2024-03-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | Yes | 225 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1105.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-10-16 | 226 | 162 | 2024-10-16 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2025-09-04 | 549 | 393 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 972.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-03-15 | 40 | 30 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 959421 | 55265.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-02 | 2023-02-03 | 2 | 2 | 2023-02-03 | 2024-09-19 | 595 | 425 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21691.6 | 1793.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-05-16 | 66 | 48 | 2025-05-16 | 2025-06-18 | 34 | 24 | 2025-03-28 | 2025-05-16 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 73.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2023-12-06 | 6 | 4 | 2023-12-06 | 2023-12-11 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 2249.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-14 | 6 | 4 | 2025-01-14 | 2025-08-19 | 218 | 156 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 807.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-21 | 2023-04-24 | 4 | 2 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 30.5 | 30.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 574.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-04-28 | 60 | 42 | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2225 | 646.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | 2025-09-08 | 355 | 253 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2679.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | 2023-09-20 | 8 | 6 | 2023-09-20 | 2024-09-12 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1473.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-05-01 | 25 | 19 | 2025-05-01 | 2025-05-02 | 2 | 2 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-07-14 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 56391 | 25791.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2024-01-09 | 103 | 73 | 2024-01-09 | 2024-08-15 | 220 | 158 | 2024-01-23 | 2024-07-02 | 21 | 15 | 2024-08-01 | 2024-09-03 | 20 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | Unknown | Unknown | No | 2024-01-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | Yes | 232 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 837.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-07-30 | 188 | 134 | 2024-07-30 | 2024-09-13 | 46 | 34 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-15 | Unknown | Unknown | No | 2021-03-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-31 | 2021-03-31 | Unknown | IOU Designed & Installed | N/A | Yes | 728 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 341.75 | Unknown | Unknown | Yes | N/A | N/A | 2021-03-31 | 2023-03-29 | 729 | 521 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3150.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-15 | 2024-04-30 | 321 | 229 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-10-30 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1002.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-06-10 | 83 | 59 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2077.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-01-16 | 2 | 2 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 3656.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | 2025-06-27 | 53 | 39 | 2025-06-27 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-07-01 | 49 | 35 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 1139.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 168.15 | 168.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-31 | 2024-05-06 | IOU Designed & Installed | N/A | No | Unknown | 2233.83 | -8.51 | Unknown | Unknown | 228.55 | 2013.79 | 3981 | 1316.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2024-02-27 | 153 | 109 | 2024-02-27 | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-07 | 1 | 1 | 2024-02-27 | 2024-05-06 | 70 | 50 | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1969.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-19 | 2023-03-21 | 62 | 44 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3637.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 286632 | 26002.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-04 | 13 | 9 | 2023-10-04 | 2023-10-17 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | 2025-08-05 | 1 | 1 | 2023-10-17 | 2025-08-22 | 676 | 484 | Unknown | 2025-08-07 | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 834.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2024-02-07 | 1 | 1 | 2024-02-07 | 2024-02-07 | 1 | 1 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10.35 | 10.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1614.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-10-01 | 91 | 65 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 744.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-06 | 2023-07-10 | 5 | 3 | 2023-07-10 | 2023-07-21 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 876.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-05-23 | 116 | 84 | 2025-05-23 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-05-29 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1651.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-10-15 | 152 | 108 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-25 | 2022-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 141645 | 39150.53 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-25 | 2023-02-16 | 357 | 255 | 2023-02-16 | 2023-09-08 | 205 | 147 | 2021-08-26 | 2023-08-29 | 33 | 23 | 2023-08-31 | 2023-09-25 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2811.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-04-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4813 | 4005.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-21 | 3 | 3 | 2024-08-21 | 2024-10-08 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2025-03-26 | 170 | 122 | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4993.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-22 | 2 | 1 | 2025-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-13 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 178.05 | 178.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1395.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2025-01-10 | 23 | 17 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 109513.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-12-19 | 206 | 148 | 2024-12-19 | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-24 | 17 | 13 | 2025-05-09 | 2025-05-30 | 22 | 16 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2023-10-10 | 82 | 58 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 832.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-12 | 16 | 12 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-25 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 52.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-10-22 | 27 | 19 | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 947.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2024-03-07 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-30 | 8 | 6 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1166641.66 | 63260.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2025-03-07 | 382 | 274 | 2025-01-21 | Unknown | Unknown | Unknown | 2025-01-08 | 2025-03-19 | 44 | 32 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27867 | 673.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-10-29 | 49 | 35 | 2024-10-29 | 2025-01-08 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | 2022-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1659.9 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-03 | 2023-05-01 | 211 | 151 | 2023-05-01 | 2023-05-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1486 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | 2024-09-03 | 6 | 4 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2025-08-14 | 346 | 248 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 54.1 | 54.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1545.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-01-08 | Unknown | Unknown | 2024-01-08 | 2024-05-02 | 116 | 84 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 165 | 165 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2086.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 446.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2023-12-12 | 43 | 31 | 2023-12-12 | 2024-02-08 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1161.45 | 1161.45 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-03-21 | 2024-06-06 | IOU Designed & Installed | N/A | No | Unknown | 4.22 | -3.27 | Unknown | Unknown | Unknown | 7.49 | 7962 | 1188.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2024-03-22 | 178 | 128 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-06-06 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1388 | 1388 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 815.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-04-03 | 31 | 23 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-10 | 3 | 3 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1344.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-19 | Unknown | Unknown | No | 2023-03-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | Yes | 322 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 402346 | 5763.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-14 | 2023-12-18 | 280 | 200 | 2023-12-18 | 2024-07-16 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | JAMUL | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2722.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2025-01-06 | 628 | 448 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 383.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-03 | 2025-01-08 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-08-04 | 63 | 45 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 20946.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-07-02 | 7 | 5 | 2024-07-02 | 2025-03-27 | 269 | 193 | 2024-08-01 | 2025-03-18 | 169 | 121 | 2024-10-01 | 2025-05-27 | 41 | 29 | 2025-07-30 | Unknown | Unknown | Unknown | 2025-07-30 | 2025-08-18 | 20 | 14 | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1274.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-12 | 3 | 3 | 2025-03-12 | 2025-03-28 | 17 | 13 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-08-19 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2023-12-19 | 36 | 26 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-29 | 25 | 19 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 390.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-06-03 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-01-11 | 2025-02-24 | 45 | 31 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 1066.05 | 1066.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2761.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2025-02-04 | 63 | 45 | 2025-02-04 | 2025-02-06 | 3 | 3 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1466.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-09-16 | 119 | 85 | 2024-09-16 | 2024-09-17 | 2 | 2 | 2024-09-17 | 2025-09-03 | 352 | 252 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1037.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-08-05 | 12 | 8 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 280825.58 | 73716.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-05-07 | 112 | 80 | 2025-02-04 | 2025-04-14 | 11 | 9 | 2025-04-30 | 2025-05-27 | 28 | 20 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1103.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 877.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-03-25 | 97 | 69 | 2025-03-25 | 2025-04-25 | 32 | 24 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6825.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-02-02 | Unknown | Unknown | 2025-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 340.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-27 | 2023-06-14 | 49 | 35 | 2023-06-14 | 2023-06-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 792.45 | 792.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 948.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-08-26 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-02-13 | 29 | 21 | 2024-02-13 | 2024-02-13 | 1 | 1 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2025-08-29 | 564 | 404 | Unknown | 2025-08-25 | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1093.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-05-06 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-26 | 10 | 8 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1562.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-01-17 | 5 | 5 | 2025-01-17 | 2025-01-17 | 1 | 1 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | 2022-10-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 639700.7 | 44732.76 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-26 | 2023-02-08 | 106 | 76 | 2023-02-08 | 2023-08-07 | 181 | 129 | 2023-02-14 | 2023-08-01 | 110 | 80 | 2023-02-08 | 2023-08-16 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | 1280 | 1280 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 16953 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2025-03-20 | 176 | 126 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1621.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-12-12 | 81 | 59 | 2024-12-12 | 2024-12-12 | 1 | 1 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1236.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-11 | 6 | 4 | 2025-02-11 | 2025-03-07 | 25 | 19 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | Unknown | Unknown | No | 2023-12-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | Yes | 267 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 782.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-07 | 2024-08-30 | 268 | 192 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-09 | 20 | 14 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-09 | 7 | 5 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POTRERO | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3058.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-08-26 | 126 | 90 | 2024-08-26 | 2025-05-27 | 275 | 197 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 42.1 | 42.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1158.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-07-01 | 20 | 14 | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2549.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-04-22 | 91 | 65 | 2025-04-22 | 2025-07-08 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-07-07 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 764.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-07-17 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 789.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-07-16 | 22 | 16 | 2024-07-16 | 2025-08-06 | 387 | 277 | 2025-07-01 | 2025-07-07 | 7 | 5 | 2025-06-24 | 2025-07-08 | 10 | 8 | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1113.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-09 | Unknown | Unknown | 2025-06-09 | 2025-06-20 | 12 | 10 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-07-28 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-03 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-07 | 38 | 28 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 772 | 772 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1401460 | 15129.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-18 | 2 | 2 | 2024-09-18 | 2024-12-13 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 168.4 | 168.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1085.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-23 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2023-11-01 | 14 | 10 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 206.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-01-10 | 8 | 6 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 726.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-03-13 | 1 | 1 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-15 | 2024-11-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1735.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-15 | 3 | 3 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 487.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-09-15 | 26 | 20 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3891 | 1732.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-04-04 | 11 | 9 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | 2025-04-07 | 4 | 2 | 2025-04-07 | 2025-04-18 | 12 | 10 | 2025-05-19 | 2025-07-01 | 44 | 32 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | SAN DIEGO | 681 | 681 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2724.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-06-29 | Unknown | Unknown | 2024-06-29 | 2025-02-28 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-07 | 31 | 23 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9568 | 1346.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-11-26 | 279 | 199 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-08-27 | 218 | 156 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47772 | 3278.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 102.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-08-01 | 37 | 27 | 2024-08-01 | 2024-11-08 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-19 | 33 | 23 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | 2023-11-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | Yes | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 14403.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2024-01-16 | 50 | 36 | 2024-01-16 | Unknown | Unknown | Unknown | 2024-02-13 | 2024-11-15 | 38 | 28 | 2024-11-21 | 2024-12-10 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 105292.6 | 2476.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-21 | 2023-12-23 | 3 | 2 | 2023-12-23 | 2024-05-29 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | Unknown | Unknown | No | 2024-12-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | Unknown | IOU Designed & Installed | N/A | Yes | 125 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1654.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2025-05-01 | 126 | 90 | 2025-05-01 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-07-01 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-26 | 16 | 12 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 72.1 | 72.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1304.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-05-06 | 23 | 17 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-08 | 2025-08-29 | 631 | 451 | 2025-08-29 | 2025-08-29 | 1 | 1 | 2025-08-22 | 2025-08-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-11 | 43 | 31 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 569.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-06-20 | 2 | 2 | 2024-06-20 | 2024-11-06 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1873.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46962 | 555.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-07-21 | 5 | 5 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 10.4 | 10.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-06-05 | 23 | 17 | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 432 | 432 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 187270 | 46526.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-20 | 2023-06-28 | 9 | 7 | 2023-06-28 | 2024-08-09 | 409 | 293 | 2024-03-04 | 2024-08-06 | 40 | 26 | 2024-08-06 | 2024-09-09 | 31 | 21 | 2024-08-09 | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1425.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2025-02-17 | 102 | 72 | 2025-02-17 | 2025-02-18 | 2 | 2 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2143.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-08-09 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1086-G3 Summerwill WO1 (E) | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | 2025-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 49315 | 42015.7 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-23 | 2023-03-02 | 161 | 115 | 2023-03-02 | 2024-06-21 | 478 | 342 | 2023-03-06 | 2024-11-07 | 440 | 314 | 2023-03-27 | 2025-04-16 | -97 | -73 | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-03 | 2025-06-03 | 183 | 131 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 102.1 | 102.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1125.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-01-11 | Unknown | Unknown | 2025-01-11 | 2025-04-28 | 108 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-07 | 18 | 14 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1557.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-10-08 | 2 | 2 | 2024-10-08 | 2024-10-16 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-30 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2109.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-06-13 | 71 | 51 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 59 | 59 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1466.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-19 | 11 | 9 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1651.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-09-26 | 23 | 17 | 2024-09-26 | 2024-09-27 | 2 | 2 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 144 | 144 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1474.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-13 | 2023-04-03 | Unknown | Unknown | 2023-04-03 | 2024-09-04 | 521 | 373 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 775.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-05-08 | 29 | 21 | 2025-05-08 | 2025-06-23 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-06-06 | 29 | 21 | 2025-06-23 | 2024-12-26 | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 419.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2024-02-01 | 79 | 57 | 2024-02-01 | 2024-02-22 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 691 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-05-31 | 1 | 1 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 858.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2025-08-05 | 678 | 484 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12.7 | 12.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-07-09 | 20 | 14 | 2024-07-09 | 2024-07-12 | 4 | 4 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-02-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9278 | 4869.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-02-10 | 21 | 15 | 2025-02-10 | 2025-05-09 | 89 | 65 | 2025-03-20 | 2025-04-23 | 27 | 19 | 2025-02-20 | 2025-05-07 | 54 | 40 | 2025-05-09 | 2025-04-29 | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 91.05 | 91.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2585.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-10-18 | 60 | 44 | 2024-10-18 | 2024-10-21 | 4 | 2 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2969.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-04-10 | 17 | 13 | 2024-04-10 | 2024-05-03 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | Spring Valley | N/A | 3052 | 3052 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-04-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10790.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2024-04-24 | 127 | 91 | 2024-04-24 | 2024-08-29 | 128 | 92 | 2024-05-03 | 2024-06-03 | 32 | 22 | 2024-07-23 | 2024-07-26 | 4 | 4 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 143316 | 8841.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | 2024-07-01 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-22 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-11-22 | 41 | 29 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1907.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-04-11 | 22 | 16 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-07-25 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1597.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-12-12 | 16 | 12 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | Unknown | Unknown | No | 2023-08-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 206 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 38432.78 | 15245.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2024-03-08 | 200 | 144 | 2024-03-08 | 2024-09-04 | 181 | 129 | 2024-03-15 | 2024-08-09 | 89 | 60 | 2024-03-25 | 2025-09-07 | 21 | 15 | 2025-02-11 | Unknown | Unknown | Unknown | 2025-02-11 | 2025-08-19 | 190 | 136 | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1042.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-02-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-06-18 | 135 | 97 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-14 | 2022-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1003.11 | Unknown | Unknown | Yes | N/A | N/A | 2021-05-14 | 2024-08-21 | 1196 | 854 | 2024-08-21 | 2024-10-10 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28746 | 8394.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2024-05-01 | 239 | 171 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2025-06-03 | 42 | 30 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 559.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-25 | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-07-25 | 20 | 14 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 767.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-27 | 2024-03-11 | 76 | 54 | 2024-03-11 | 2024-04-15 | 36 | 26 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 160 | 160 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 687.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1319.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-09-30 | 34 | 24 | 2024-09-30 | 2024-10-17 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-28 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-21 | 2022-12-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 262655 | 44576.79 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-21 | 2023-03-21 | 91 | 65 | 2023-03-21 | 2023-03-23 | 3 | 3 | 2023-03-06 | 2023-03-21 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2108.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2024-09-07 | 145 | 104 | 2024-09-07 | 2025-02-26 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-17 | 2024-12-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2627.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-11-07 | 23 | 17 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-03 | 2021-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1054.06 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-03 | 2023-05-30 | 544 | 388 | 2023-05-30 | 2023-03-18 | Unknown | Unknown | 2023-05-10 | 2023-05-30 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1497.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2024-11-25 | 25 | 17 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-08-05 | 254 | 182 | Unknown | 2025-08-04 | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 278.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2025-04-08 | 608 | 434 | 2025-04-08 | 2025-04-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-21 | 14 | 10 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-09-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4549.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | 2024-09-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4425.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2024-05-13 | 390 | 278 | 2024-05-13 | 2024-05-30 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 751.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-01-19 | 93 | 67 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 148.7 | 148.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-27 | Unknown | Unknown | No | 2024-01-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | Yes | 405 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2025-01-14 | 365 | 261 | 2025-01-14 | 2025-02-24 | 42 | 30 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 268.5 | 268.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1669 | 2561.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-18 | 4 | 4 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | 2024-08-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | Unknown | Unknown | No | 2022-01-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-31 | 2022-04-26 | Unknown | IOU Designed & Installed | N/A | Yes | 870 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 150871 | 5474.97 | Unknown | Unknown | Yes | N/A | N/A | 2022-01-31 | 2024-06-19 | 871 | 623 | 2024-06-19 | 2022-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-22 | 2023-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 148.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-22 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2023-07-22 | 69 | 50 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-04-16 | IOU Designed & Installed | N/A | No | Unknown | 40.66 | -9.62 | Unknown | Unknown | 28.14 | 22.14 | 0 | 1482.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-04-16 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RAMONA | N/A | 871 | 871 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2764 | 311.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | 2023-05-15 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1725.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-10-07 | 43 | 31 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2726.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-05-02 | 12 | 10 | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1928.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-02-13 | 7 | 5 | 2025-02-13 | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-06 | 22 | 16 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | Underserved Community | Alpine | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 88213.98 | 55317.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-25 | 2023-09-18 | 117 | 83 | 2023-09-18 | 2024-08-15 | 333 | 239 | 2023-12-26 | Unknown | Unknown | Unknown | 2024-04-19 | 2024-08-14 | 18 | 14 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-06-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1177.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-12 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-03-12 | 34 | 24 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-06-13 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1150.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-27 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-04-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 89.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | 2025-03-17 | 13 | 9 | 2025-03-17 | 2025-04-03 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-11 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 25.15 | 25.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-11 | 2 | 2 | 2024-12-11 | 2024-12-13 | 3 | 3 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 173.05 | 173.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-11-05 | 43 | 31 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-07-29 | 267 | 191 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-08 | 63 | 45 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-14 | 464 | 332 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9041.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-07-15 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7128 | 13092.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-04-21 | 105 | 75 | 2025-04-21 | 2025-05-19 | 29 | 21 | 2025-05-19 | 2025-06-05 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | POWAY | POWAY | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 31143.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2025-01-23 | 7 | 5 | 2025-01-23 | 2025-04-15 | 83 | 59 | 2025-01-24 | 2025-01-27 | 4 | 2 | 2025-01-27 | 2025-04-29 | 33 | 25 | 2025-04-15 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1994.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-11 | 3 | 3 | 2025-04-11 | 2025-05-02 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4448.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1329.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-07-18 | 121 | 87 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1213.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-12-20 | 52 | 38 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2198.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-06-23 | 50 | 36 | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1301.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-18 | 2 | 2 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-07-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1145.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-07-07 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 192 | 192 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4198 | 3227.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2024-01-10 | 2 | 2 | 2024-01-10 | 2024-02-05 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 2322 | 2322 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2556555 | 173509.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-28 | 2024-07-15 | 292 | 208 | 2024-07-15 | 2025-05-14 | 304 | 218 | 2024-09-12 | 2025-05-08 | 62 | 45 | 2023-12-07 | 2025-08-27 | 196 | 136 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 144 | 144 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 10498.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-18 | 2024-02-22 | 67 | 49 | 2024-02-22 | 2024-06-20 | 120 | 86 | 2024-03-13 | 2024-03-18 | 6 | 4 | 2024-05-09 | 2024-06-06 | 24 | 18 | 2024-06-20 | 2025-07-08 | 384 | 274 | 2024-07-17 | 2025-07-29 | 378 | 270 | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 17084.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2025-01-29 | 69 | 49 | 2025-01-29 | 2025-05-01 | 93 | 67 | 2025-03-14 | 2025-03-19 | 6 | 4 | 2025-03-27 | 2025-05-29 | 45 | 33 | 2025-05-01 | 2025-08-25 | 117 | 83 | 2025-05-21 | 2025-08-25 | 97 | 69 | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1151.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-03-27 | 7 | 5 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 703.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-29 | 22 | 16 | 2025-05-29 | 2025-06-06 | 9 | 7 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2289 | 493.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-20 | 8 | 6 | 2024-11-20 | 2024-12-06 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 260.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-10-24 | 77 | 55 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-07-23 | 2024-08-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2797.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-06-18 | 106 | 76 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1291.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-10-13 | 17 | 13 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8521 | 1283.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-12 | 6 | 4 | 2025-02-12 | 2025-07-01 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-04 | 8 | 6 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1511.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-09-01 | Unknown | Unknown | 2023-09-01 | 2025-06-11 | 650 | 464 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-05-12 | 112 | 80 | 2025-06-11 | 2025-06-24 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 2700 | 2700 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 110628.77 | 38046.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-11-26 | 35 | 25 | 2024-11-26 | 2025-06-26 | 213 | 153 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-05-07 | 2025-07-16 | 60 | 42 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | 2024-10-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | Yes | 24 | 41.95 | 0 | Unknown | Unknown | Unknown | 41.95 | 3961 | 1397.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-04 | 2024-10-25 | 22 | 16 | 2024-10-25 | 2024-10-28 | 4 | 2 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65076 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-04-21 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1220.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-13 | Unknown | Unknown | 2025-06-13 | 2025-06-25 | 13 | 9 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2179 | 2179 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 985.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-09-04 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-28 | 30 | 22 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | 1109-H2 ES North AVE PH3 | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-08-21 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1012.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-07-16 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10980 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-05-10 | 19 | 15 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2875.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-07 | 8 | 6 | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-09-03 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11895 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-09-05 | 486 | 348 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO |  | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16016.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2024-12-31 | 387 | 277 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-28 | 20 | 14 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2025-01-27 | 75 | 53 | 2025-01-27 | 2025-01-31 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-05-10 | 2024-08-07 | IOU Designed & Installed | N/A | No | Unknown | 5689.62 | 1781.92 | Unknown | Unknown | 43.45 | 3864.25 | 3981 | 959.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-04-18 | 58 | 42 | 2024-04-18 | 2024-05-10 | 23 | 17 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-08-07 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1870.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-08-13 | 27 | 19 | 2024-08-13 | 2024-08-27 | 15 | 11 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1272.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-09 | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-16 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN YSIDRO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 893.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2024-01-11 | 65 | 47 | 2024-01-11 | 2024-11-18 | 313 | 223 | Unknown | Unknown | Unknown | Unknown | 2023-12-22 | 2024-01-02 | 12 | 8 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2197.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2024-01-26 | 44 | 32 | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1745.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-28 | 3 | 3 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1166.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-10 | 8 | 6 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-14 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 119375.8 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-14 | 2024-03-29 | 533 | 381 | 2024-03-29 | Unknown | Unknown | Unknown | 2024-04-09 | 2025-08-29 | 375 | 269 | 2025-05-12 | 2025-07-22 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-28 | 2025-06-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 980.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-28 | 2025-06-25 | Unknown | Unknown | 2025-06-25 | 2025-06-28 | 4 | 3 | 2025-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-28 | 2025-07-07 | 10 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2025-06-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 14203.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2025-02-12 | 177 | 127 | 2025-02-12 | 2025-06-03 | 112 | 80 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-05-12 | 2025-06-12 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 83451 | 2511.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-04-19 | 89 | 65 | 2024-04-04 | 2024-04-05 | 2 | 2 | 2024-04-05 | 2024-04-23 | 19 | 13 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 18.4 | 18.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 48689 | 1136.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-21 | 3 | 3 | 2025-02-21 | 2025-02-27 | 7 | 5 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 696658 | 58691.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2024-03-04 | 209 | 149 | 2024-03-04 | 2024-06-05 | 94 | 68 | 2024-04-02 | 2025-05-05 | 43 | 31 | 2024-04-09 | 2025-05-08 | 81 | 61 | 2024-06-05 | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1203.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-08-20 | 28 | 20 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2093.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 377.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2023-10-02 | 8 | 6 | 2023-10-02 | 2024-02-13 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 25368.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-08-13 | 154 | 110 | 2024-08-13 | 2025-05-01 | 262 | 188 | 2024-08-21 | 2025-01-16 | 39 | 29 | 2025-05-08 | 2025-05-21 | 14 | 10 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | 2025-09-08 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 308 | 308 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 55782 | 75788.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-22 | 2023-02-22 | 1 | 1 | 2023-02-22 | 2024-12-23 | 671 | 479 | 2023-02-22 | 2024-08-12 | 463 | 331 | 2023-08-07 | 2025-09-09 | 334 | 238 | 2024-12-23 | 2025-08-28 | 249 | 179 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 198.05 | 198.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2176.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2024-02-20 | 100 | 72 | 2024-02-20 | 2025-03-14 | 389 | 279 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-04-10 | 35 | 25 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11187.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 951.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-04 | 2023-05-04 | 1 | 1 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2255.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-30 | 2024-04-25 | 332 | 238 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1603.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | 2024-04-18 | 2 | 2 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | Fallbrook | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14775 | 15444.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-28 | 8 | 6 | 2023-06-28 | 2024-10-11 | 472 | 338 | 2023-11-06 | 2024-10-03 | 94 | 68 | 2023-10-17 | 2024-10-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 22633.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2024-12-11 | 401 | 287 | 2024-12-11 | 2025-05-05 | 146 | 104 | 2024-06-19 | 2025-03-06 | 214 | 154 | 2025-03-27 | 2025-04-03 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 308.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-03-15 | 94 | 68 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2647.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-16 | 2023-04-12 | Unknown | Unknown | 2023-04-12 | 2023-08-11 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3566.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-13 | 3 | 3 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2411.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-09-04 | 50 | 36 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-10-10 | 32 | 24 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2024-11-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 840.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-10-01 | Unknown | Unknown | 2023-10-01 | 2023-10-20 | 20 | 15 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-11-12 | 390 | 278 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 385.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-09-19 | 28 | 20 | 2023-09-19 | 2024-07-11 | 297 | 213 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2025-08-19 | 405 | 289 | Unknown | 2025-08-20 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 1275 | 1275 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 62860.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-09-06 | 278 | 200 | 2024-02-28 | 2024-07-01 | 125 | 89 | 2024-07-01 | 2025-06-05 | 28 | 22 | 2024-09-06 | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1328.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-07-05 | 74 | 54 | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 310.2 | 310.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65482 | 42602.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2024-01-26 | 45 | 33 | 2024-01-26 | 2024-06-10 | 137 | 97 | 2024-02-13 | Unknown | Unknown | Unknown | 2024-05-29 | 2025-07-29 | 39 | 29 | 2024-06-10 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 31.05 | 31.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3186.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2025-04-04 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 371.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | Unknown | Unknown | Unknown | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1276.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-09-06 | 113 | 81 | 2024-09-06 | 2024-09-09 | 4 | 2 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 823.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-26 | 2023-05-16 | 21 | 15 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-06-07 | 23 | 17 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1247.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-02-04 | 27 | 19 | 2025-02-04 | 2025-02-25 | 22 | 16 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1377.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2025-01-15 | 55 | 39 | 2025-01-15 | 2025-02-07 | 24 | 18 | 2025-02-07 | 2025-06-20 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-08-18 | 60 | 42 | Unknown | 2025-08-01 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1714.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-07-30 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 37.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-05-28 | 22 | 16 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-07 | Unknown | Unknown | No | 2022-04-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | Unknown | IOU Designed & Installed | N/A | Yes | 623 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117.86 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2024-01-11 | 641 | 459 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2024-07-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1194.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-24 | 2023-12-08 | 46 | 34 | 2023-12-08 | 2024-01-11 | 35 | 25 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-07-02 | 174 | 124 | Unknown | 2025-05-01 | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 709.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2025-02-07 | 208 | 150 | 2025-02-07 | 2025-03-19 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-17 | 21 | 15 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 227.2 | 227.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 20276 | 7175.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-12-05 | 34 | 24 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12650 | 516.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-26 | 15 | 11 | 2024-11-26 | 2025-06-09 | 196 | 140 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1767.05 | 1767.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1119.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2024-11-18 | 18 | 12 | 2024-11-18 | 2024-12-11 | 24 | 18 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-08-14 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-10-18 | 100 | 72 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | OC 1086-g1 | OC 1086-g1 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-06-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 97438.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-04 | 2023-04-23 | Unknown | Unknown | 2023-04-23 | 2024-08-23 | 489 | 350 | 2023-07-03 | 2024-10-03 | 82 | 58 | 2023-06-29 | 2024-08-21 | 78 | 56 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 8.7 | 8.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1668.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-09 | 42 | 30 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-07 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | 510.63 | 0 | Unknown | Unknown | Unknown | 510.63 | 0 | 2024.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-01 | 2024-06-28 | 514 | 368 | 2024-06-28 | 2025-01-21 | 208 | 148 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2157.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-11-11 | 34 | 24 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-09-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 970708 | 37991.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-18 | 2023-04-18 | 91 | 65 | 2023-04-18 | 2024-06-27 | 437 | 313 | 2024-01-30 | 2024-01-31 | 2 | 2 | 2024-01-31 | 2024-02-23 | 24 | 18 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19202 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-03-05 | 6 | 4 | 2024-03-05 | 2024-04-24 | 51 | 37 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 34040.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-03-10 | Unknown | Unknown | 2023-03-10 | 2024-11-06 | 608 | 434 | 2023-10-02 | 2024-10-30 | 395 | 283 | 2024-10-31 | 2025-09-09 | 314 | 222 | 2024-11-06 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36349.88 | 678.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2023-11-09 | 2 | 2 | 2023-11-09 | 2023-11-27 | 19 | 13 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1383.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | 2025-03-24 | 19 | 13 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-07-29 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1202.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-02-14 | 68 | 50 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1282.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-30 | Unknown | Unknown | 2025-05-30 | 2025-06-02 | 4 | 2 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | Unknown | Unknown | No | 2025-06-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | Yes | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1043.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-07-31 | 59 | 43 | 2025-07-31 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 39242 | 1428.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2023-08-23 | 2 | 2 | 2023-08-23 | 2023-08-28 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1153.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-07-02 | 47 | 33 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Valley Center | COUNTY OF SAN DIEGO-NORTH of 56 | 258.15 | 258.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2291.19 | 16618.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-03-04 | 13 | 9 | 2025-03-04 | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-18 | 2 | 2 | 2025-04-08 | 2025-04-17 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1329.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-03-08 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-02-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11139.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 435.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-05-29 | 72 | 52 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-11-13 | IOU Designed & Installed | N/A | No | Unknown | 10.03 | 0 | Unknown | Unknown | 4.56 | 5.47 | 0 | 987.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-01 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-02-01 | 23 | 17 | 2024-02-01 | 2024-10-15 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-11-13 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1067.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-09-19 | 57 | 41 | 2024-09-19 | 2024-10-03 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-22 | -25 | -27 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 775.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-25 | 19 | 15 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | Unknown | Unknown | No | 2024-03-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | Yes | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1316.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-06-11 | 91 | 65 | 2024-06-11 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19202 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-03-12 | 13 | 9 | 2024-03-12 | 2024-04-24 | 44 | 32 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 797.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-11-25 | 61 | 43 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-07-22 | 239 | 171 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | N/A | 25.4 | 25.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1504.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2025-02-21 | 267 | 191 | 2025-02-21 | 2025-04-10 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 59624 | 3850.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2023-08-31 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1829.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4078.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-09-18 | 20 | 14 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-19 | 2024-03-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 859.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-03-19 | 61 | 43 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10.8 | 10.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1551.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-08-06 | 15 | 11 | 2024-08-06 | 2024-08-16 | 11 | 9 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-04-15 | 55 | 39 | 2024-04-15 | 2024-04-19 | 5 | 5 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1763.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1519.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1123.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-24 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 848.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | 2024-12-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | Yes | 228 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 797.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-07-23 | 227 | 163 | 2025-07-23 | 2025-07-26 | 4 | 3 | 2025-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3158.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 6000 | 6000 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2208.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-10-30 | 97 | 69 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-07-25 | 269 | 193 | Unknown | 2025-07-31 | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.37 | 3.37 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 805.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-06-12 | 28 | 20 | 2025-06-12 | 2025-06-19 | 8 | 6 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-16 | 28 | 20 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1462.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-02-15 | 7 | 5 | 2023-02-15 | 2023-04-19 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2024-11-01 | 151 | 109 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2024-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 1005.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2024-01-31 | 175 | 125 | 2024-01-31 | 2024-02-12 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-05-08 | 23 | 17 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2024-11-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1573.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-04 | 13 | 9 | 2024-11-15 | 2024-11-18 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 973.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-08-05 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 264.05 | 264.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-04-26 | 36 | 26 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | 2025-02-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4448.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 153.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-06-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 63536 | 4595.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-05-13 | 2 | 2 | 2025-05-13 | 2025-05-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-20 | 39 | 29 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Dulzura | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2024-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31296.15 | 36858.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2024-05-24 | 339 | 243 | 2024-05-24 | 2025-03-11 | 292 | 208 | 2024-06-03 | 2025-02-20 | 84 | 62 | 2025-02-28 | 2025-03-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 20.2 | 20.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1805.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | 2025-04-11 | 12 | 10 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14103 | 745.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-08-02 | 11 | 9 | 2024-08-02 | 2025-01-27 | 179 | 127 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1169.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-18 | 19 | 15 | 2025-04-18 | 2025-05-09 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-07-14 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2117.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-01-24 | 2 | 2 | 2024-01-24 | 2025-04-07 | 440 | 314 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-15 | 23 | 17 | 2025-04-07 | 2025-08-21 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2025-01-10 | 79 | 57 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 141 | 141 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1823.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-09-20 | 57 | 41 | 2023-09-20 | 2023-09-28 | 9 | 7 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 495 | 495 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 972.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-07-29 | 5 | 3 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | 2022-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1208.41 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-07 | 2023-03-23 | 351 | 251 | 2023-03-23 | 2023-04-17 | 26 | 18 | 2023-11-03 | 2024-08-28 | 132 | 94 | 2023-01-30 | 2024-04-23 | 198 | 144 | 2023-04-17 | 2023-06-08 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4657.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2023-12-15 | 128 | 92 | 2023-12-15 | 2024-03-26 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 281.36 | 281.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2029.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-04-07 | 75 | 53 | 2025-04-07 | 2025-04-09 | 3 | 3 | 2025-03-29 | 2025-06-10 | 73 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1372.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 667.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4172.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1599.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-26 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-23 | 20 | 14 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19202 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-03-05 | 6 | 4 | 2024-03-05 | 2024-04-24 | 51 | 37 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-28 | IOU Designed & Installed | N/A | No | Unknown | 1735.67 | -32.8 | Unknown | Unknown | 62.64 | 1705.83 | 3981 | 1663.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2268 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-02-22 | 29 | 21 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2025-08-21 | 547 | 391 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3007.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-12-12 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65214 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-09-17 | 2 | 2 | 2024-09-17 | 2024-09-18 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 611.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-09-06 | 33 | 25 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-07-07 | 305 | 217 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2333.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-17 | 16 | 12 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-08-26 | 253 | 181 | Unknown | 2025-08-25 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-12 | Unknown | Unknown | No | 2025-03-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | Yes | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1335.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-04-18 | 39 | 29 | 2025-04-18 | 2025-06-04 | 48 | 34 | 2025-03-11 | 2025-03-14 | 4 | 4 | 2025-04-28 | 2025-05-01 | 4 | 4 | 2025-06-04 | 2025-07-08 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 720.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2024-03-22 | 177 | 127 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1861.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-01-24 | 2 | 2 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 157.22 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-03 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2101.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 354.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-08 | 2024-06-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1466.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-08 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-06-08 | 30 | 21 | 2024-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | LAGUNA BEACH | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-09 | 2023-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 973.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-09 | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-09-09 | 41 | 30 | 2023-09-09 | Unknown | Unknown | Unknown | 2023-09-09 | 2023-09-15 | 7 | 5 | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | 2024-07-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2025-06-06 | IOU Designed & Installed | N/A | Yes | 312 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1075.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2025-05-30 | 324 | 232 | 2025-05-30 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2025-06-06 | 234 | 168 | Unknown | 2025-05-28 | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1612.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-10-08 | 13 | 9 | 2024-10-08 | 2024-11-18 | 42 | 30 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2024-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2475.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2024-01-31 | 175 | 125 | 2024-01-31 | 2024-04-17 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7260.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8944 | 871.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-12-20 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-12-16 | 2024-01-02 | 18 | 12 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 51.36 | 51.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1431.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-18 | 9 | 7 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3431.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-12-03 | 76 | 54 | 2024-12-03 | 2025-01-10 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-20 | 13 | 9 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2819.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2025-01-15 | 171 | 123 | 2025-01-15 | 2025-01-29 | 15 | 11 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 4500 | 4500 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1069.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-06 | Unknown | Unknown | 2025-06-06 | 2025-06-25 | 20 | 14 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1763.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-20 | 10 | 8 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 103.35 | 103.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1379.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2025-01-07 | 145 | 103 | 2025-01-07 | 2025-01-14 | 8 | 6 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-03 | 2 | 2 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 215.05 | 215.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 579.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-08-25 | 203 | 145 | 2024-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 748.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2025-05-20 | 196 | 140 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-07-31 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32793.08 | 28404.73 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-21 | 2023-12-11 | 447 | 319 | 2023-12-11 | Unknown | Unknown | Unknown | 2025-01-09 | 2025-03-24 | 19 | 13 | 2024-10-15 | 2025-04-03 | 29 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 2.35 | 2.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-11-11 | 26 | 18 | 2024-11-11 | 2024-11-25 | 15 | 11 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-08-05 | 254 | 182 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 1569 | 1569 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 469667 | 13601.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | 2024-01-09 | 257 | 183 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2025-04-08 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | 33526.42 | 15159.1 | Unknown | Unknown | 61.25 | 18306.07 | 14655 | 24308.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-23 | 2025-02-07 | 47 | 35 | 2025-02-07 | 2025-04-08 | 61 | 43 | 2025-04-08 | 2025-04-25 | 18 | 14 | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-04-25 | 2025-06-16 | 53 | 37 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1082.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-06-15 | 12 | 9 | 2024-06-15 | 2024-06-15 | 1 | 0 | 2024-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1400.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-09-24 | 44 | 32 | 2024-09-24 | 2024-10-11 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-22 | 19 | 13 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 2790 | 2790 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2024-11-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-11-01 | 19 | 15 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-06 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | N/A | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1538766 | 166344.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-28 | 2024-01-25 | 304 | 218 | 2024-01-25 | 2024-07-23 | 181 | 129 | 2024-04-10 | 2024-09-11 | 32 | 20 | 2024-02-15 | 2025-06-27 | 147 | 107 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 133.4 | 133.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7964 | 1819.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-11-04 | 196 | 140 | 2024-11-04 | 2025-06-13 | 222 | 160 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-07 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 224 | 224 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1055.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-12-12 | 8 | 6 | 2023-12-12 | 2023-12-15 | 4 | 4 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2036.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-09 | 2023-08-04 | 57 | 41 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 25420.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-18 | 2023-10-05 | 49 | 35 | 2023-10-05 | 2024-04-25 | 204 | 146 | 2023-10-12 | 2024-04-01 | 173 | 123 | 2024-03-07 | 2024-04-23 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4047 | 351.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-05-27 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-06 | 9 | 7 | 2025-05-27 | 2025-08-06 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 330.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-24 | 26 | 18 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 9000 | 9000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5118.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-26 | 2024-10-23 | 272 | 194 | 2024-10-23 | 2025-02-06 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-02-13 | 36 | 26 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-23 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1026.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-23 | 2 | 2 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-18 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1713.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 516.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-05-15 | 100 | 72 | 2025-05-15 | 2025-05-29 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-12 | 13 | 9 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1122.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-13 | 5 | 5 | 2025-06-06 | 2025-06-17 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12930.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | 2025-08-07 | 386 | 276 | 2024-12-06 | 2024-12-09 | 4 | 2 | 2024-10-31 | 2025-08-05 | 90 | 66 | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1180.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-02-26 | 33 | 23 | 2024-02-26 | 2024-02-26 | 1 | 1 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 515.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-15 | 2025-02-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2881.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-15 | 10 | 8 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 120.05 | 120.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3113.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | 2025-03-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-08-13 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE, MISSION VIEJO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 66236.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2025-01-22 | 259 | 185 | 2025-01-22 | 2025-06-18 | 148 | 106 | 2025-02-06 | 2025-05-19 | 15 | 11 | 2025-03-21 | 2025-05-29 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 743.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2025-03-06 | 94 | 68 | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | 2024-04-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-07-08 | 2025-06-24 | IOU Designed & Installed | N/A | Yes | 432 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1141.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2025-06-27 | 429 | 307 | 2025-06-27 | 2024-07-08 | Unknown | Unknown | 2024-07-08 | 2025-06-06 | 334 | 240 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-24 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 112.4 | 112.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 5014.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-27 | 10 | 8 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 134.05 | 134.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1202.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-08-14 | 43 | 31 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3735.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-08-28 | 111 | 79 | 2024-08-28 | 2025-08-05 | 343 | 245 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1972.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-05-01 | 15 | 11 | 2024-05-01 | 2024-06-05 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-24 | 23 | 17 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1087.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-10 | 2 | 2 | 2024-10-10 | 2024-10-30 | 21 | 15 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | 2022-04-04 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15106924 | 552673.04 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-04 | 2023-07-20 | 473 | 339 | 2023-07-20 | 2024-01-12 | 177 | 127 | 2023-08-07 | 2025-03-05 | 153 | 107 | 2023-06-30 | 2024-10-16 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2025-08-14 | 340 | 244 | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | RA 1152-E7 CREEKSIDE XING WO2 (E) | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 43157 | 39501.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-08-20 | 167 | 119 | 2024-08-20 | 2025-02-06 | 171 | 123 | 2024-09-05 | 2025-01-10 | 45 | 33 | 2024-09-30 | 2025-02-27 | 37 | 27 | 2025-03-24 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2012.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-02-17 | 61 | 43 | 2025-02-17 | 2025-02-20 | 4 | 4 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-07-21 | 152 | 108 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1353.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-02 | 7 | 5 | 2025-06-02 | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-20 | 19 | 15 | 2025-06-02 | 2025-06-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 195.05 | 195.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 95.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-23 | 2023-03-01 | 38 | 28 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 437 | 437 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1824.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2024-12-26 | 14 | 10 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1392.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | 2023-08-29 | 6 | 4 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2257.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-10 | 3 | 3 | 2025-04-10 | 2025-04-21 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3158.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 13028.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | 2025-06-02 | 649 | 463 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-06-10 | 28 | 20 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | 2023-07-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2023-07-20 | 67 | 49 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 1357.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-04 | 2023-11-30 | 58 | 42 | 2023-11-30 | 2023-12-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-04 | 5 | 3 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-18 | 14 | 10 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5000 | 2793.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2024-02-02 | 51 | 37 | 2024-02-02 | 2024-03-26 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1686.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-10-29 | 127 | 91 | 2024-10-29 | 2024-11-04 | 7 | 5 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 401.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-19 | 2024-01-09 | 175 | 125 | 2024-01-09 | 2024-01-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2025-06-23 | 531 | 379 | Unknown | 2025-06-18 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | PAUMA VALLEY | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 595.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-04-11 | 16 | 12 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 186.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-06-19 | 8 | 6 | 2024-06-19 | 2024-06-19 | 1 | 1 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1308.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2025-05-01 | 133 | 95 | 2025-05-01 | 2025-05-02 | 2 | 2 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-07-16 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 96.1 | 96.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1108.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-03-01 | 10 | 8 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 214.45 | 214.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 33437.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-12-05 | 112 | 80 | 2024-12-05 | 2025-01-28 | 55 | 39 | 2024-12-20 | 2025-02-04 | 47 | 33 | 2025-01-21 | 2025-01-28 | 8 | 6 | 2025-01-28 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1173.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-10-10 | 60 | 44 | 2024-10-10 | 2024-10-23 | 14 | 10 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2025-07-18 | 269 | 193 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 438.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2023-11-15 | Unknown | Unknown | 2023-11-15 | 2024-02-23 | 101 | 73 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1480.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-10-01 | 204 | 146 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1945.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 472.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-04-08 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-05-29 | 17 | 13 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 116059 | 90079.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-03 | 2023-10-10 | 69 | 49 | 2023-10-10 | 2024-11-12 | 400 | 286 | 2023-12-28 | 2025-09-09 | 155 | 105 | 2023-08-31 | 2024-10-24 | 171 | 124 | 2024-11-12 | 2025-07-28 | 259 | 185 | 2024-11-20 | 2025-07-02 | 225 | 161 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 793.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-26 | 13 | 10 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | 2023-10-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2025-06-06 | IOU Designed & Installed | N/A | Yes | 445 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1517.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2025-01-14 | 471 | 337 | 2025-01-14 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2025-06-06 | 589 | 421 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1544.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-12-09 | 28 | 20 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-08-11 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 78.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-24 | 6 | 4 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-08-22 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 907.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1006.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-04-25 | 147 | 105 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-27 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3228.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-27 | 7 | 5 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-06-24 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 853.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-18 | 4 | 4 | 2025-04-18 | 2025-06-09 | 53 | 37 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 160.05 | 160.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2003.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-09-10 | 35 | 25 | 2024-09-10 | 2025-02-05 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3477.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-06-19 | 45 | 33 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1175.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-01-10 | 3 | 3 | 2024-01-10 | 2024-01-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-20 | 11 | 8 | 2024-01-17 | 2025-07-25 | 556 | 398 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 826.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-06 | 3 | 3 | 2025-06-06 | 2025-06-10 | 5 | 3 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1174.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-10-10 | 23 | 17 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1106.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-24 | 22 | 16 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-01 | 8 | 6 | 2025-06-24 | 2025-07-17 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 48.1 | 48.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 975.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-30 | 21 | 15 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 351 | 351 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1185.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-10-17 | 11 | 9 | 2024-10-17 | 2024-11-01 | 16 | 12 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-08-06 | 279 | 199 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1070.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-10-12 | 105 | 75 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2866.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-06-23 | 15 | 11 | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-11 | 2025-06-23 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 885.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-27 | 23 | 17 | 2025-02-27 | 2025-03-18 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10980 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-05-10 | 19 | 15 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2025-08-28 | 476 | 340 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-27 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1143.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-27 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-27 | 11 | 9 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-06-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 366252 | 23097.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-05 | 14 | 10 | 2023-10-05 | 2023-10-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 733.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-04-10 | 118 | 84 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | PW 1190-C5 Harmon rch WO3 (E) | N/A | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 32173.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-10-02 | 266 | 190 | 2024-10-02 | 2025-05-05 | 216 | 154 | 2024-10-17 | 2025-07-14 | 167 | 119 | 2025-04-16 | 2025-04-24 | 9 | 7 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-05-14 | 2025-08-19 | 98 | 70 | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 4504.05 | 4504.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-10 | 2024-05-14 | IOU Designed & Installed | N/A | No | Unknown | 2666.25 | 773.64 | Unknown | 28.59 | 122.34 | 1741.68 | 0 | 852.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-05-10 | 37 | 27 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-14 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 36258.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-07-01 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-07-11 | 32 | 24 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Viejo | Rancho Viejo | 106.1 | 106.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 45881.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-01 | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-07-11 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 239328.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-25 | 2023-10-16 | 175 | 125 | 2023-10-16 | 2025-05-27 | 590 | 422 | 2023-05-30 | 2025-05-13 | 47 | 37 | 2023-05-16 | 2025-06-16 | 125 | 89 | 2025-05-27 | 2025-07-22 | 57 | 41 | 2025-06-24 | 2025-07-31 | 38 | 28 | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | San Diego | 315 | 315 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47488.35 | 30173.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-02-21 | 40 | 30 | 2025-02-21 | 2025-05-21 | 90 | 64 | 2025-04-02 | 2025-04-03 | 2 | 2 | 2025-05-08 | 2025-06-02 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2247.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-10 | 15 | 11 | 2025-04-10 | 2025-06-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 218 | 218 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 30581 | 10105.07 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2024-04-15 | 159 | 113 | 2024-04-15 | 2025-06-19 | 431 | 309 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-10-30 | 7 | 5 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1214931 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-21 | 2025-05-28 | 342 | 244 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA HILLS | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1202.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-02-03 | 14 | 10 | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 25.7 | 25.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3701.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-04-02 | 23 | 17 | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-07-01 | 90 | 64 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 14561.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-06-27 | 151 | 109 | 2025-04-16 | Unknown | Unknown | Unknown | 2025-07-02 | 2025-07-16 | 15 | 11 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-22 | 2024-12-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1807.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-09-22 | 2 | 2 | 2023-09-22 | 2023-10-04 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | Valley Center | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2867.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-31 | 17 | 13 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1250.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-15 | 24 | 18 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-09-10 | 8 | 6 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8628 | 107426.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2024-06-13 | 211 | 151 | 2024-06-13 | 2024-10-17 | 127 | 91 | 2024-06-28 | 2025-05-07 | 246 | 174 | 2024-09-02 | 2025-05-12 | 253 | 181 | 2024-10-17 | 2025-03-12 | 147 | 105 | 2025-04-08 | 2025-04-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 137930 | 76479.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-09-08 | 57 | 41 | 2023-09-08 | 2025-02-05 | 517 | 369 | 2024-07-18 | 2024-07-25 | 8 | 6 | 2024-10-18 | 2025-02-11 | 44 | 30 | 2025-02-05 | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 605 | 605 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65482 | 9463.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | 2023-04-06 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-17 | 1 | 1 | 2023-04-06 | 2025-02-05 | 672 | 480 | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1431.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-06-05 | Unknown | Unknown | 2025-06-05 | 2025-06-09 | 5 | 3 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-07-28 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4868.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-17 | 15 | 11 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-03-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1034.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-03 | 2023-03-09 | 35 | 25 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5110 | 982.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-02 | 2024-09-20 | 50 | 36 | 2024-09-20 | 2024-10-29 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-12-04 | 41 | 29 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 228194 | 18399.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-28 | 2023-03-01 | Unknown | Unknown | 2023-03-01 | 2023-11-21 | 266 | 190 | 2023-08-29 | 2023-08-30 | 2 | 2 | 2023-09-18 | 2023-11-16 | 13 | 11 | 2023-11-21 | Unknown | Unknown | Unknown | 2025-04-18 | 2025-08-01 | 106 | 76 | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 652.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-21 | 2023-04-10 | 21 | 15 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1056711 | 6460.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-03-24 | 28 | 20 | 2025-03-24 | 2025-06-16 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-16 | 17 | 13 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 848.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | 2024-02-20 | 5 | 3 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 14670 | 14670 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47073 | 10491 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-12-18 | 204 | 146 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 5101.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-25 | 9 | 7 | 2024-10-25 | 2024-11-01 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2025-03-06 | 35 | 25 | 2024-11-01 | 2025-07-23 | 265 | 189 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 70880 | 70880 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 158104 | 17933.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2025-02-20 | 541 | 387 | 2025-02-20 | 2025-05-19 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-16 | 16 | 12 | 2025-05-19 | 2025-07-10 | 53 | 39 | Unknown | 2025-06-19 | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 569.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2023-10-24 | 65 | 47 | 2023-10-24 | 2023-10-27 | 4 | 4 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 610.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-28 | 2023-05-24 | Unknown | Unknown | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 488.7 | 0 | Unknown | Unknown | 5.11 | 483.59 | 3981 | 863.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-05-01 | 38 | 28 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2023-04-24 | Unknown | Unknown | 2023-04-24 | 2023-08-16 | 115 | 83 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | CB 1126-J7 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8964.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-12-12 | 1 | 1 | 2024-12-12 | 2024-12-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1939.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | 2025-06-20 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-22 | 23 | 17 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13588.59 | 15510.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2025-04-08 | 146 | 104 | 2025-03-13 | 2025-06-02 | 8 | 4 | 2025-03-17 | 2025-04-21 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 124 | 124 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-02-27 | 16 | 12 | 2024-02-27 | 2024-03-08 | 11 | 9 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1972.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-10-23 | 42 | 30 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-25 | Unknown | Unknown | No | 2024-12-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | Yes | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 2106.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2025-01-09 | 29 | 21 | 2025-01-09 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1700.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-10-18 | 58 | 42 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 620.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2023-08-14 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 496.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-06 | 61 | 43 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3495.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-13 | 11 | 9 | 2024-12-13 | 2024-12-16 | 4 | 2 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 850.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-26 | 14 | 10 | 2025-06-26 | 2025-06-26 | 1 | 1 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 712.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-08-28 | 238 | 170 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 860.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-12-17 | 62 | 44 | 2023-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-10-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 656.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | 2023-12-13 | 58 | 42 | 2023-12-11 | 2024-04-12 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-10-15 | 308 | 220 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 693.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-05-01 | 29 | 21 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2025-03-18 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11655.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2025-03-20 | 116 | 84 | 2025-03-20 | 2025-06-19 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 50.05 | 50.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2465.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-22 | 7 | 5 | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 267717 | 40763.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-02 | 2025-01-30 | 548 | 392 | 2025-01-30 | 2025-06-23 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1634.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-03-05 | 21 | 15 | 2025-03-05 | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-09 | 35 | 25 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2912.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-28 | 9 | 7 | 2025-03-28 | 2025-04-01 | 5 | 3 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 600.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-11-02 | 66 | 48 | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | el cajon | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25843.95 | 16926.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2024-12-06 | 29 | 21 | 2024-12-06 | 2025-06-16 | 193 | 137 | 2025-03-28 | 2025-07-10 | 78 | 54 | 2025-05-05 | 2025-07-10 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | National City | National City | 640 | 640 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19751.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-21 | 2023-07-24 | 4 | 2 | 2023-07-24 | Unknown | Unknown | Unknown | 2024-02-12 | 2025-04-28 | 442 | 316 | 2024-02-06 | 2024-05-15 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | TECATE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-02-15 | 3 | 3 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 809.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2025-09-05 | 291 | 209 | 2025-09-05 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-08-13 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1086.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-05-17 | 54 | 40 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2025-07-14 | 420 | 300 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1422.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-29 | 28 | 20 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1407.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-27 | 14 | 10 | 2024-08-27 | 2024-09-16 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 831.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2025-05-23 | 348 | 250 | 2025-05-23 | 2025-05-23 | 1 | 1 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 589.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-04-18 | 63 | 45 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-08-08 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-01-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1803.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-01-31 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | 20700 | 20700 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 96924 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2024-12-26 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1054.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-05-07 | 41 | 29 | 2024-05-07 | 2024-06-27 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-20 | 24 | 18 | 2024-06-27 | 2024-07-19 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | Unknown | Unknown | No | 2024-06-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-20 | 2024-07-25 | IOU Designed & Installed | N/A | Yes | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1523.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-08-13 | 71 | 51 | 2024-08-13 | 2024-06-20 | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-25 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1910.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-21 | 8 | 6 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1245.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-04-07 | 33 | 23 | 2025-04-07 | 2025-04-28 | 22 | 16 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | RANCHO MISSION VIEJO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 63732.59 | 39872.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-06-18 | 197 | 141 | 2024-04-16 | 2025-04-30 | 346 | 248 | 2024-05-01 | 2025-07-17 | 151 | 105 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 59 | 59 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1677.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-17 | 11 | 9 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-04-24 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1044.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-09-04 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 651.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-15 | 11 | 9 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2749.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-08-18 | 121 | 87 | 2023-08-18 | 2023-08-23 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 638.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1258.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | 2025-01-28 | 7 | 5 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 419.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-06-16 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | La Jolla | La Jolla | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 39055 | 54354.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2025-05-07 | 570 | 408 | 2025-02-24 | 2025-03-06 | 11 | 9 | 2025-03-17 | 2025-05-13 | 28 | 20 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1650.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-10-21 | 127 | 91 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 899.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 828.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-01-24 | 20 | 14 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2024-03-27 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | 61201.97 | 21148.23 | Unknown | Unknown | 2082.45 | 37971.29 | 0 | 50167.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-09-25 | 238 | 170 | 2023-09-25 | 2025-01-22 | 486 | 348 | 2024-07-22 | 2025-01-21 | 53 | 39 | 2024-08-09 | 2025-05-27 | 160 | 114 | 2025-01-22 | Unknown | Unknown | Unknown | 2025-02-05 | 2025-07-02 | 148 | 106 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 81.15 | 81.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-26 | 2025-05-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-03-26 | 10 | 8 | 2025-03-26 | 2025-04-24 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-02 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 961.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-11 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-06-28 | 1 | 1 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1129-B1 TOWN HM PH2 | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 336211.13 | 60798.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-18 | 2024-02-29 | 43 | 31 | 2024-02-29 | 2024-08-21 | 175 | 125 | 2024-04-09 | 2025-06-05 | 78 | 56 | 2024-08-13 | 2025-02-04 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1001.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-13 | 2 | 2 | 2023-12-13 | 2023-12-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 2377.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2024-10-24 | 382 | 274 | 2024-10-24 | 2024-11-06 | 14 | 10 | 2025-05-13 | 2025-05-15 | 3 | 3 | 2024-08-15 | 2025-06-09 | 89 | 63 | 2024-11-06 | 2025-08-15 | 283 | 203 | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 178.1 | 178.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1353.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-10-18 | 23 | 17 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2025-08-26 | 308 | 220 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2211.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-23 | 9 | 7 | 2024-07-23 | 2024-07-24 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-19 | 2024-10-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3576.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 766.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2023-10-12 | 37 | 27 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9530.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2025-03-17 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-21 | 27 | 21 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-26 | 2024-06-11 | IOU Designed & Installed | N/A | No | Unknown | 1.89 | -4.55 | Unknown | Unknown | Unknown | 6.44 | 3961 | 192.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-04-23 | 48 | 34 | 2024-04-23 | 2024-06-11 | 50 | 36 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-09-26 | 2 | 2 | 2024-09-26 | 2024-11-04 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 744.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-04-04 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-07-30 | 118 | 84 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-18 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-08-18 | 50 | 36 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1600.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-18 | 4 | 4 | 2024-10-18 | 2025-05-23 | 218 | 156 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-07 | 12 | 8 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-09-09 | 28 | 20 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 717.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | 2025-04-03 | 744 | 532 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2391.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-02 | 7 | 5 | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-11 | 2023-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 870.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-11 | 2023-03-11 | 1 | 0 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN MARCOS | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1038.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-05-19 | 41 | 29 | 2025-05-19 | 2025-05-29 | 11 | 9 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Residential | N/A | EN 1147-B5 (E) | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 37989.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-11-18 | 301 | 215 | 2024-04-08 | 2025-03-19 | 9 | 7 | 2024-11-04 | 2025-02-12 | 92 | 64 | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-03 | 2025-07-29 | 239 | 171 | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 381.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | 2024-03-04 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Fallbrook | N/A | 230 | 230 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3000.19 | 10498.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-01 | 2024-04-11 | 11 | 9 | 2024-04-11 | 2024-12-09 | 243 | 173 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-06 | 3 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | national city | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8441.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-07-25 | 35 | 25 | 2023-07-25 | 2024-01-23 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-02-27 | 70 | 52 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1127.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-04-17 | 25 | 19 | 2025-04-17 | 2025-06-13 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-08-04 | 54 | 38 | Unknown | 2025-07-30 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1650.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-11-08 | 18 | 14 | 2024-11-08 | 2024-11-21 | 14 | 10 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 4000 | 4000 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1158.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-07-29 | 286 | 204 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1302.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-04-18 | 15 | 11 | 2025-04-18 | 2025-04-21 | 4 | 2 | 2025-04-07 | 2025-04-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 694.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-08-06 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 133.4 | 133.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | 15134.95 | 6726.88 | Unknown | Unknown | Unknown | 8408.07 | 0 | 19724.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | 2025-06-13 | 271 | 195 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-30 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1289.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-05-19 | 102 | 72 | 2025-05-19 | 2025-05-22 | 4 | 4 | 2025-02-07 | 2025-06-06 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-07-22 | 47 | 33 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1305.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-01 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1042.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-05-23 | 53 | 39 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 912.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-02-22 | 101 | 73 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-04-14 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-10 | 17 | 13 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1386.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-06-28 | 40 | 30 | 2024-06-28 | 2024-07-03 | 6 | 4 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4297 | 1841.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2025-03-03 | 267 | 191 | 2025-03-03 | 2025-06-16 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 351.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-03 | 3 | 3 | 2023-03-03 | 2023-06-12 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 33.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | 2024-05-24 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-02-16 | 80 | 58 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 678.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2025-05-06 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-08 | 13 | 9 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2632.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2025-01-09 | 98 | 70 | 2025-01-08 | 2025-04-18 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-08-29 | 128 | 92 | Unknown | 2025-07-24 | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-04-29 | IOU Designed & Installed | N/A | No | Unknown | 863.86 | -17.24 | Unknown | Unknown | 6.06 | 875.04 | 3981 | 1837.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-04-29 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | 42.2 | 42.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18434 | 6584.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-09 | 2024-05-13 | 95 | 67 | 2024-05-13 | 2024-05-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-07 | 36 | 26 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 389329.19 | 97120.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2025-01-09 | 135 | 97 | 2025-01-09 | 2025-05-16 | 128 | 92 | 2025-02-01 | 2025-04-09 | 22 | 16 | 2025-04-09 | 2025-04-14 | 6 | 4 | 2025-05-16 | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | Unknown | Unknown | No | 2023-07-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2024-12-26 | IOU Designed & Installed | N/A | Yes | 352 | 1133.58 | 0 | Unknown | Unknown | 187.93 | 945.65 | 3981 | 1521.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-17 | 2024-07-03 | 353 | 253 | 2024-07-03 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-26 | 8 | 6 | Unknown | 2024-07-15 | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3671.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | 2025-02-12 | 304 | 218 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | 2023-07-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-11 | 2023-07-27 | IOU Designed & Installed | N/A | Yes | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13818 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2023-07-12 | 3 | 3 | 2023-07-12 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-07-27 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | Unknown | Unknown | No | 2024-07-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | Yes | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1174.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-10-31 | 114 | 82 | 2024-10-31 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-10-31 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-30 | 2025-03-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 455.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-30 | 2025-05-08 | 40 | 29 | 2025-05-08 | 2025-05-21 | 14 | 10 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41967.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | 2025-06-02 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-06-11 | 64 | 46 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 97330 | 10644.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-10-19 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-10-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2101.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-09-27 | 122 | 88 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4511.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-09-27 | 10 | 8 | 2024-09-27 | 2024-10-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4993.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-04-10 | 38 | 28 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5447.8 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-22 | 2024-03-07 | 625 | 447 | 2024-03-07 | 2024-07-11 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-10-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1122.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-10-30 | 185 | 133 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2326.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2025-04-10 | 240 | 172 | 2025-04-10 | 2025-04-11 | 2 | 2 | 2025-03-05 | 2025-04-11 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 49550.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-12 | 2024-07-31 | 477 | 341 | 2024-07-31 | 2024-10-17 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1295.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-06-19 | 2 | 2 | 2024-06-19 | 2024-06-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-19 | 31 | 23 | 2024-06-20 | 2025-06-20 | 366 | 262 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-12-10 | 16 | 12 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27365 | 332.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2023-12-06 | 1 | 1 | 2023-12-06 | 2023-12-06 | 1 | 1 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 232 | 232 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 219226 | 34136.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-30 | 2024-02-01 | 64 | 46 | 2024-02-01 | Unknown | Unknown | Unknown | 2024-08-10 | 2024-08-11 | 2 | 0 | 2024-08-27 | 2024-10-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12.15 | 12.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2025-01-27 | 2025-05-09 | IOU Designed & Installed | N/A | No | Unknown | 422.9 | -8.43 | Unknown | Unknown | 3.43 | 427.9 | 7962 | 2007.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-01-14 | Unknown | Unknown | 2024-01-14 | 2025-01-27 | 380 | 271 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-05-09 | 103 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-07 | Unknown | Unknown | No | 2025-01-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | Yes | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3327.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-02-10 | 35 | 25 | 2025-02-10 | 2025-02-12 | 3 | 3 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 666.23 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-08 | 2023-04-24 | 138 | 98 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 222.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-06-28 | 88 | 64 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 904.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | 2024-03-06 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-23 | 25 | 19 | 2024-03-06 | 2024-08-23 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 636.05 | 636.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1122.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-07-17 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-17 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 429.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-05-30 | 114 | 82 | 2025-05-30 | 2025-06-05 | 7 | 5 | 2025-02-13 | 2025-06-04 | 112 | 80 | 2025-06-05 | 2025-07-15 | 39 | 26 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 |  | 2024-07-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1512.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-07-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 282.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-12 | 3 | 3 | 2025-02-12 | 2025-04-25 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-21 | 12 | 10 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 598.96 | -10.38 | Unknown | Unknown | 55.45 | 553.89 | 0 | 2027.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-04-30 | 7 | 5 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-24 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 129.25 | 129.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2025-01-10 | 25 | 19 | 2025-01-10 | 2025-02-23 | 45 | 31 | 2025-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2207.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-18 | 2023-12-14 | 58 | 42 | 2023-12-14 | 2023-12-18 | 5 | 3 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | 2025-01-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | Yes | 189 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1683.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-06-27 | 166 | 120 | 2025-06-27 | 2025-01-13 | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-08-08 | 208 | 150 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2025-03-12 | IOU Designed & Installed | N/A | No | Unknown | 2178.6 | 390.76 | Unknown | 39.01 | 48.36 | 1700.47 | 0 | 1467.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2025-01-31 | 178 | 128 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-03-12 | 41 | 29 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 40.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2060.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-20 | 16 | 12 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 343.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-20 | 10 | 8 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-08-06 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 98150 | 6721.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2025-01-16 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1283.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-04-08 | 37 | 27 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | VS 1108-C4 | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | 2022-09-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1087279 | 47082.85 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-09 | 2024-04-12 | 582 | 416 | 2024-04-12 | 2024-08-09 | 120 | 86 | 2024-06-10 | 2024-10-10 | 38 | 28 | 2024-08-08 | 2024-10-11 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2025-08-25 | 371 | 265 | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-30 | 2025-05-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1345.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-30 | 16 | 12 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 1245.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-12-18 | 10 | 8 | 2024-12-18 | 2025-01-09 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1699.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 226 | 226 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-30 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 51013 | 21421.23 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-30 | 2023-09-11 | 621 | 443 | 2023-09-11 | 2023-10-04 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 1218.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2024-01-31 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-28 | Unknown | Unknown | No | 2024-11-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | Yes | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1602.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2025-02-28 | 129 | 93 | 2025-02-28 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 2128.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-04-18 | 1 | 1 | 2024-04-18 | 2025-04-08 | 356 | 254 | Unknown | Unknown | Unknown | Unknown | 2024-10-19 | 2024-10-28 | 10 | 6 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 1548 | 1548 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-08-22 | 2025-03-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 90717.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2023-08-22 | 169 | 121 | 2023-08-22 | 2024-05-14 | 267 | 191 | 2023-10-06 | 2025-03-24 | 138 | 98 | 2024-03-05 | 2024-06-18 | 18 | 12 | 2024-05-14 | 2025-06-06 | 389 | 279 | 2025-04-22 | 2025-06-19 | 59 | 43 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 661428 | 56576.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-26 | 2023-06-02 | 8 | 6 | 2023-06-02 | 2024-03-07 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-26 | 14 | 10 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 897 | 897 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2319.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-05-23 | 121 | 87 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2138.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2025-01-27 | 300 | 214 | 2025-01-27 | 2025-02-12 | 17 | 13 | 2025-02-12 | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-14 | 30 | 22 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1142.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-29 | 2 | 2 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2177.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-08-01 | 4 | 4 | 2024-08-01 | 2025-04-04 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9149 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-29 | 13 | 9 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 413.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-05-06 | 90 | 64 | 2025-05-06 | 2025-05-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-05-05 | 21 | 15 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 48.45 | 48.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1448.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-27 | 22 | 16 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-08-13 | 168 | 120 | Unknown | 2025-08-07 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 21.2 | 21.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2528.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-12-20 | 25 | 19 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2025-02-12 | 267 | 191 | 2025-02-12 | 2025-02-13 | 2 | 2 | 2025-02-12 | 2025-02-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 1116 | 1116 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-05-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1704.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-06 | 2023-06-13 | 128 | 92 | 2023-06-13 | 2023-11-13 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-17 | 1 | 1 | 2023-11-13 | 2025-08-14 | 641 | 459 | Unknown | 2025-07-04 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1431.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1564.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-30 | 21 | 15 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3172.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2025-03-13 | 120 | 86 | 2025-03-13 | 2025-04-02 | 21 | 15 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1175.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-10-15 | 97 | 69 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1059.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-17 | 72 | 52 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1003.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2024-12-19 | 35 | 25 | 2024-12-19 | 2025-01-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3459.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-30 | 7 | 5 | 2024-09-30 | 2024-11-01 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1759.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-05-28 | Unknown | Unknown | 2024-05-28 | 2024-06-06 | 10 | 8 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1590.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-02-01 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 383.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-05-01 | 14 | 10 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-14 | 2025-06-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 17410.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-14 | 9 | 7 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-22 | 19 | 11 | 2025-05-01 | 2025-06-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3633.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-08-02 | 58 | 42 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8835.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2024-04-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 454134.04 | 131967.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-28 | 2024-10-22 | 422 | 302 | 2024-10-22 | 2025-02-28 | 130 | 94 | 2024-10-29 | 2025-03-04 | 7 | 3 | 2024-08-19 | 2025-08-20 | 264 | 190 | 2025-02-28 | Unknown | Unknown | Unknown | 2025-06-16 | 2025-08-05 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 960.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-03-24 | 29 | 21 | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-04-01 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1210.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2025-04-17 | 150 | 108 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-05-07 | 3 | 3 | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-06-04 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-07-11 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 287.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-09-27 | 44 | 32 | 2023-09-27 | 2023-09-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2025-06-02 | 614 | 438 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1156.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-03-06 | 63 | 45 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | CALTRANS-NORTH of 56, SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 390312 | 128250.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-07-23 | 161 | 115 | 2024-07-23 | Unknown | Unknown | Unknown | 2024-11-21 | 2025-04-09 | 50 | 36 | 2024-09-09 | 2025-04-30 | -114 | -84 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 813.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-16 | 58 | 42 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | 2024-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | Yes | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 589.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-04-18 | 1 | 1 | 2024-04-18 | 2024-04-19 | 2 | 2 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-07-31 | 470 | 336 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1165.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-12 | 7 | 5 | 2025-02-12 | 2025-02-14 | 3 | 3 | 2025-02-11 | 2025-02-14 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-08-28 | 196 | 140 | Unknown | 2025-08-15 | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 2700 | 2700 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 134836.49 | 152361.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-26 | 2024-11-26 | 1 | 1 | 2024-11-26 | 2025-09-05 | 284 | 204 | 2025-05-20 | 2025-06-20 | 32 | 24 | 2025-02-06 | 2025-08-07 | 61 | 45 | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 229236.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2024-02-21 | 98 | 70 | 2024-02-21 | 2024-08-14 | 176 | 126 | 2024-04-19 | 2025-06-02 | 155 | 109 | 2024-07-18 | 2025-06-10 | 141 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1609.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-08-12 | 33 | 23 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ES 1109-H5 ASH ST MSO WO1 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-08-29 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 479.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2709.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-04-05 | 2 | 2 | 2024-04-05 | 2024-04-25 | 21 | 15 | 2024-04-17 | 2024-05-14 | 28 | 20 | 2024-04-16 | 2024-06-12 | 58 | 42 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ES 1129-G6 amanda estates (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2025-01-28 | 363 | 259 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1336.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-18 | 5 | 3 | 2025-03-18 | 2025-04-23 | 37 | 27 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-08-12 | 112 | 80 | Unknown | 2025-08-01 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 879.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-10 | 2023-12-18 | 70 | 50 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2231.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-09-27 | 37 | 27 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-16 | 12 | 10 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 993.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-26 | 2023-08-24 | 211 | 151 | 2023-08-24 | 2023-10-24 | 62 | 44 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2232.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-14 | 2023-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1864.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-14 | 2023-10-15 | 2 | 0 | 2023-10-15 | 2023-10-15 | 1 | 0 | 2023-10-15 | 2023-11-02 | 19 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 440.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-11-06 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1095.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-21 | 22 | 16 | 2025-05-21 | 2025-05-23 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-23 | 17 | 13 | 2025-05-23 | 2025-07-21 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2579.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-10-14 | 14 | 10 | 2024-10-14 | 2024-10-18 | 5 | 5 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27867 | 3090.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-12-09 | 334 | 238 | 2024-12-09 | 2025-05-01 | 144 | 104 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | 75.25 | 75.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-07 | 2025-06-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15698 | 1709.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-02 | 2023-02-07 | 6 | 4 | 2023-02-07 | 2023-07-13 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-27 | 1 | 1 | 2023-07-13 | 2025-07-17 | 736 | 526 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 717.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2024-01-04 | 32 | 24 | 2024-01-04 | 2024-01-04 | 1 | 1 | 2024-01-04 | 2024-01-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 534.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-29 | 2024-04-17 | 20 | 14 | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN YSIDRO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1326.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2024-01-04 | 101 | 73 | 2024-01-04 | 2024-01-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-11 | 6 | 4 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | 2025-06-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1618.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-06-12 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 282 | 282 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2024-03-21 | 2025-06-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 463635 | 106701.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2024-10-22 | 615 | 439 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-11-06 | 70 | 50 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 84.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-10-08 | 217 | 155 | 2024-10-08 | 2024-11-12 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-09-20 | 60 | 44 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 2141.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-03-23 | Unknown | Unknown | 2025-03-23 | 2025-04-24 | 33 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-01 | 15 | 11 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1412.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-10-31 | 21 | 15 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1726.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-03-13 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-12 | 16 | 12 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 2934.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | 2025-05-06 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-11 | 11 | 9 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1223.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-30 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2433.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-02-06 | 23 | 17 | 2025-02-06 | 2025-02-26 | 21 | 15 | 2025-02-26 | 2025-03-10 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-07-23 | 135 | 97 | Unknown | 2025-07-02 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1571.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-10-31 | 21 | 15 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3171.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8880.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-07-20 | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-08 | 4 | 3 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | Unknown | Unknown | No | 2023-11-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | Yes | 601 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1516.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2025-07-14 | 602 | 430 | 2025-07-14 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2024-12-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2176.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-01 | 2024-10-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1540.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-01 | 34 | 24 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1674.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | 2025-03-20 | 16 | 12 | 2025-03-20 | 2025-06-03 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 203.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-16 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-10-16 | 14 | 10 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 426000 | 60425.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2024-01-10 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 216 | 216 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1976.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-29 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-04-05 | 109 | 79 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1022.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2023-04-20 | Unknown | Unknown | 2023-04-20 | 2023-08-11 | 114 | 82 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1861.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2037.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-09-28 | 150 | 108 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 263.12 | 263.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3978.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2025-04-18 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-07-16 | 15 | 11 | 2025-04-18 | 2025-07-01 | 75 | 53 | Unknown | 2025-07-24 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 930.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-07-31 | 22 | 16 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 968.92 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-14 | 2024-02-23 | 467 | 335 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 990.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-01 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 435.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2024-05-23 | 2 | 2 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-12 | 16 | 12 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 102993 | 30755.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2024-04-16 | 205 | 147 | 2024-04-16 | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-27 | 58 | 42 | 2024-08-19 | 2024-09-04 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6121.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-06-18 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-08-27 | 71 | 51 | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | RSF 1148-F6 (E) | COUNTY OF SAN DIEGO-NORTH of 56 | 31.05 | 31.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4631 | 21069.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2025-04-04 | 149 | 107 | 2024-11-22 | 2025-03-26 | 3 | 3 | 2025-01-21 | 2025-04-04 | 21 | 17 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 213323 | 31553.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-03-26 | 64 | 46 | 2025-03-26 | 2025-04-15 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 426074 | 30389.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-04-03 | 44 | 32 | 2025-04-03 | 2025-05-15 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1085.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-18 | 9 | 7 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 48.15 | 48.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1981.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-03-18 | 28 | 20 | 2025-03-18 | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-08 | 20 | 14 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 282 | 282 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 179320 | 15714.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2024-10-22 | 615 | 439 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ES 1129-F3 (E) | ESCONDIDO | 227.2 | 227.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12588 | 27870.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-12-05 | 34 | 24 | 2023-12-05 | Unknown | Unknown | Unknown | 2024-04-17 | 2024-06-17 | 62 | 44 | 2025-01-27 | 2025-02-19 | 21 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 77.75 | 77.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1571.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-10-01 | 19 | 13 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 44.4 | 44.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1264.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-03-18 | 41 | 29 | 2025-03-18 | 2025-03-21 | 4 | 4 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2025-03-11 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-08-28 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 645098.76 | 121651.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-03 | 2023-08-21 | 111 | 79 | 2023-08-21 | 2024-05-29 | 283 | 203 | 2024-01-31 | 2025-09-02 | 501 | 359 | 2023-10-06 | 2024-05-30 | 39 | 29 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1167.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-11 | 2 | 2 | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-04-14 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2836.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2025-06-03 | 377 | 269 | 2025-06-03 | 2025-06-04 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-06 | 17 | 13 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1716.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-18 | 15 | 11 | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | 2025-01-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 827.05 | 827.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 554.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 84.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-13 | 161 | 115 | 2024-08-13 | 2024-11-12 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-09-13 | 55 | 41 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | Poway | POWAY | 1823 | 1823 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26414.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-19 | 2024-01-31 | 227 | 163 | 2024-01-31 | 2025-07-09 | 526 | 376 | 2024-04-29 | 2025-06-17 | 11 | 9 | 2024-05-30 | 2025-07-08 | 41 | 29 | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | COUNTY OF ORANGE | 3096 | 3096 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2106980 | 288460.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-04 | 2024-09-26 | 359 | 257 | 2024-09-26 | Unknown | Unknown | Unknown | 2024-12-09 | 2025-05-21 | 42 | 32 | 2024-09-18 | 2025-06-13 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 398 | 398 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2133.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-07 | 4 | 4 | 2025-03-07 | Unknown | Unknown | Unknown | 2025-03-07 | 2025-05-28 | 83 | 59 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | POWAY | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 13919.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2025-02-04 | 176 | 126 | 2025-02-04 | 2025-07-31 | 178 | 128 | 2025-03-31 | 2025-04-01 | 2 | 2 | 2025-04-14 | 2025-06-27 | 24 | 18 | 2025-07-31 | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-29 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-06-29 | 58 | 42 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 821.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-09 | 18 | 14 | 2025-05-09 | 2025-06-04 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 847.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-04-25 | 67 | 49 | 2025-04-25 | 2025-04-28 | 4 | 2 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 576.4 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2023-12-18 | 33 | 23 | 2023-12-18 | 2023-12-27 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-27 | 16 | 12 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 1883.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2025-02-19 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-13 | 21 | 15 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 396.84 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-23 | 2023-01-31 | 223 | 159 | 2023-01-31 | 2023-02-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | PW 1170-E2 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7781.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-10-18 | 2025-02-06 | 112 | 80 | 2024-10-25 | 2025-01-31 | 9 | 6 | 2025-02-05 | 2025-02-26 | 12 | 10 | 2025-03-04 | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3136.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2023-03-20 | Unknown | Unknown | 2023-03-20 | 2025-03-20 | 732 | 524 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1303.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-11-04 | 13 | 9 | 2024-11-04 | 2025-01-29 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-01-28 | 71 | 51 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DULZURA | N/A | 1100 | 1100 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2071.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-08-22 | 31 | 23 | 2024-08-22 | 2024-09-27 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-04-22 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 649.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-03-13 | 16 | 12 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-07-15 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-09-09 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | 2024-05-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | Yes | 292 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1641.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2025-03-03 | 293 | 209 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | 2025-03-14 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 468.05 | 468.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4646.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-10-07 | 46 | 32 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 885 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-02-05 | 5 | 3 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 327 | 327 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2168.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-12-10 | 22 | 16 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 955.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-03-13 | 1 | 1 | 2024-03-13 | 2024-09-17 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 771.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-07-12 | 112 | 80 | 2023-07-12 | 2023-07-14 | 3 | 3 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 379.41 | 0 | Unknown | Unknown | 15.66 | 363.75 | 4658285 | 105451.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-04-22 | 90 | 64 | 2024-04-22 | 2025-03-10 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | 2024-12-21 | 2025-07-22 | 97 | 71 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 110774.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | 2025-04-04 | 187 | 135 | 2025-02-14 | 2025-03-25 | 40 | 28 | 2025-01-04 | 2025-04-16 | 71 | 51 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-16 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 22813 | 6188.7 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-16 | 2023-08-31 | 289 | 207 | 2023-08-31 | 2024-06-10 | 285 | 203 | 2024-04-26 | 2024-06-06 | 42 | 30 | 2024-04-29 | 2025-03-26 | 50 | 36 | 2024-06-10 | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 3927.15 | 3927.15 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3049.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-01-27 | 40 | 28 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 541089 | 541089 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-06-27 | 2023-07-12 | 16 | 12 | 2023-07-12 | 2023-07-12 | 1 | 1 | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 150 | 150 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1105.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-05-20 | 18 | 12 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 867.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-02-20 | 7 | 5 | 2025-02-20 | 2025-05-08 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1484.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1352.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-04-23 | 76 | 54 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2024-09-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1372.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-16 | 3 | 3 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-16 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1512.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2025-01-24 | 95 | 69 | 2025-01-24 | 2025-03-12 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 270 | 270 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1023.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-04 | 2024-05-14 | 407 | 291 | 2024-05-14 | 2025-06-26 | 409 | 293 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-09 | 21 | 15 | 2025-06-26 | 2025-07-16 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | BONITA | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 937.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-28 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | 2024-02-28 | 120 | 86 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2025-08-14 | 534 | 382 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3631.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | 2025-06-27 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-05-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1690.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-27 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | 2025-02-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | Yes | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1306.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-27 | 18 | 14 | 2025-02-27 | 2025-04-25 | 58 | 42 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 399.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-13 | 2023-03-13 | 1 | 1 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3544.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-03-08 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 708.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2057 | 2057 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 810.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1120.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-04-11 | 19 | 15 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-08-25 | 137 | 97 | Unknown | 2025-08-14 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 142845.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2024-04-18 | 122 | 88 | 2024-04-18 | 2024-10-24 | 190 | 136 | 2024-04-18 | 2025-04-29 | 123 | 89 | 2024-08-06 | 2024-08-28 | 23 | 17 | 2025-07-01 | Unknown | Unknown | Unknown | 2025-07-01 | 2025-07-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-05 | 2023-11-05 | 2025-01-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 152.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-05 | 2023-08-17 | Unknown | Unknown | 2023-08-17 | 2023-11-22 | 98 | 70 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2025-01-23 | 429 | 307 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 573.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-02-27 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-20 | 24 | 18 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1780.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-31 | 26 | 18 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | IMPERIAL BEACH | N/A | 42.1 | 42.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1328.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-04-15 | 98 | 70 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4760.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-11-15 | 18 | 14 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-07-15 | 243 | 173 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.28 | 48.28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2135.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-04-03 | 59 | 43 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-14 | 2023-03-01 | 16 | 12 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1454.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-20 | 24 | 18 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-08-06 | 140 | 100 | Unknown | 2025-08-05 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Bonita | COUNTY OF SAN DIEGO-SOUTH of 56 | 149.1 | 149.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2024-07-10 | 2025-06-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2286.66 | 54100.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-27 | 2024-01-24 | 485 | 347 | 2024-01-24 | 2025-05-01 | 464 | 332 | 2023-02-22 | 2023-05-10 | 78 | 56 | 2024-12-03 | 2025-05-12 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 346.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-06-14 | 2 | 2 | 2023-06-14 | 2023-07-19 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1153.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-30 | 2 | 2 | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1493.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-14 | 15 | 11 | 2025-03-14 | 2025-05-06 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 930.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-06 | 2023-04-28 | 23 | 17 | 2023-04-28 | 2024-07-03 | 433 | 309 | 2023-10-23 | 2024-04-25 | 34 | 26 | 2023-09-13 | 2025-05-19 | 84 | 60 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2023-01-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 609.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-13 | 2023-06-02 | 172 | 124 | 2023-06-02 | 2023-08-08 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2305 | 2541.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-09-06 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2505.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-06-02 | 50 | 36 | 2025-06-02 | 2025-06-09 | 8 | 6 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1604.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-18 | 19 | 13 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 372948 | 24108.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-04-03 | 44 | 32 | 2025-04-03 | 2025-05-15 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10575.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2025-02-19 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 845.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-25 | 8 | 6 | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 417.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-06 | 2023-09-15 | 10 | 8 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 44.8 | 44.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 965.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-04-10 | 14 | 10 | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2222.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2025-01-31 | 66 | 48 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-06-19 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | 2025-01-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | Yes | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1714.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-02-24 | 50 | 36 | 2025-02-24 | 2025-01-07 | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-02-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2023-02-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1448.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2025-01-05 | 48 | 34 | 2025-01-05 | 2025-01-07 | 3 | 2 | 2025-01-07 | 2025-07-08 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-08-08 | 214 | 154 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2336.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2025-04-10 | 171 | 123 | 2025-04-10 | 2025-04-14 | 5 | 3 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | 2025-06-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1442.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-08 | 8 | 6 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-06-11 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 51.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-08 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 581.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2024-01-02 | 110 | 78 | 2024-01-02 | 2024-01-04 | 3 | 3 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1277.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | 2024-10-10 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-01 | 33 | 25 | 2024-10-10 | 2025-07-15 | 279 | 199 | Unknown | 2025-07-23 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | 2728.25 | 2728.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19637.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-23 | 8 | 6 | 2024-07-23 | 2025-03-10 | 231 | 165 | 2025-01-06 | 2025-01-08 | 3 | 3 | 2025-02-21 | 2025-03-05 | 13 | 9 | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1464.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-07-25 | 8 | 6 | 2023-07-25 | 2025-02-13 | 570 | 408 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2025-03-08 | 20 | 15 | 2025-02-13 | 2025-05-06 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-11 | 2025-05-29 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2211.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-11 | 2 | 2 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-29 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 127.05 | 127.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7146 | 2400.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2025-05-15 | 584 | 418 | 2025-05-01 | 2025-05-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 663.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-01-27 | 54 | 38 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1098.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-06-24 | 48 | 34 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1080.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-04-08 | 22 | 16 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 108 | 108 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1770.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-06-11 | 148 | 106 | 2025-06-11 | 2025-06-16 | 6 | 4 | 2025-06-16 | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-08 | 23 | 17 | 2025-06-16 | 2025-07-09 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 635.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 236 | 236 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 805.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2339.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-14 | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2024-06-14 | 4 | 4 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15958.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-17 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2024-02-06 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-07 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 584.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-06-18 | 154 | 110 | 2025-06-18 | 2025-06-27 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-07-09 | 147 | 105 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | CAMPO | COUNTY OF SAN DIEGO-SOUTH of 56 | 2304 | 2304 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 379179.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2024-04-11 | 402 | 288 | 2024-04-11 | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-05 | 4 | 2 | 2024-08-06 | 2024-08-09 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1131 | 1149.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | 2024-04-24 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3950.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-06-16 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1842.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-12-17 | 26 | 18 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-08-05 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 867.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-06-25 | 44 | 32 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 506.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-11-20 | 177 | 127 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 282 | 282 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 576431.77 | 160205.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-27 | 2023-09-19 | 85 | 61 | 2023-09-19 | 2024-10-22 | 400 | 286 | 2024-04-10 | 2024-10-21 | 3 | 3 | 2024-05-04 | 2024-11-06 | 46 | 32 | 2024-10-22 | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1615.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-30 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2024-12-31 | 20 | 14 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 903 | 903 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | 2025-04-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | Yes | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2015.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-06-02 | 42 | 30 | 2025-06-02 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-06-06 | 29 | 21 | 2025-06-03 | 2025-06-09 | 7 | 5 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 56.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-20 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1158.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-11-15 | 39 | 29 | 2024-11-15 | 2024-11-18 | 4 | 2 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2223.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-26 | 17 | 13 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-16 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1293.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-20 | 8 | 6 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-07-10 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 407.05 | 407.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2025-01-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1152.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-06-06 | 77 | 55 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2025-01-22 | 231 | 165 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 786.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2023-10-24 | 29 | 21 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 1494.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-26 | 2023-06-20 | 26 | 18 | 2023-06-20 | 2023-09-25 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-07-11 | 13 | 9 | 2023-09-25 | 2023-10-12 | 18 | 14 | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2368.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-06-06 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-05-28 | 16 | 12 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 142.45 | 142.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28416 | 20971.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | 2024-10-09 | 2025-05-02 | 29 | 21 | 2025-03-28 | 2025-05-08 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1463.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-27 | 24 | 18 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1567.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-28 | 34 | 24 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 149.1 | 149.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1397.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-20 | 15 | 11 | 2025-02-20 | 2025-02-21 | 2 | 2 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-07-24 | 154 | 110 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 615940 | 33681.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-07-08 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2398 | 2398 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2024-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1378.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-07 | 2023-12-26 | 20 | 14 | 2023-12-26 | 2024-01-27 | 33 | 24 | 2024-01-27 | 2024-11-12 | 291 | 207 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4999.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | NCTD-Trolly South of 56, SAN DIEGO | 332 | 332 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35672 | 26668.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-07-24 | 100 | 72 | 2024-06-13 | 2024-06-18 | 6 | 4 | 2024-07-12 | 2024-08-14 | 1 | -3 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1247.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-05-13 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Carlsbad | CARLSBAD | 1109.7 | 1109.7 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2022-08-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32135.23 | 21165.96 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-19 | 2023-02-08 | 174 | 124 | 2023-02-08 | 2024-05-23 | 471 | 337 | 2023-02-27 | 2025-07-30 | 354 | 252 | 2024-04-12 | 2024-04-17 | 6 | 4 | 2024-06-04 | Unknown | Unknown | Unknown | 2024-06-04 | 2025-06-27 | 389 | 279 | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1123.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-18 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2023-12-27 | 29 | 21 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | 2024-11-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-05 | 2025-01-08 | IOU Designed & Installed | N/A | Yes | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 996.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2025-03-03 | 99 | 71 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-08 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SD 1189-H3 CMR Unit 5 (E) | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 430388.99 | 140182.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-07-26 | 60 | 44 | 2024-07-26 | 2025-04-02 | 251 | 179 | 2024-08-01 | 2025-01-21 | 15 | 9 | 2024-08-14 | 2025-04-21 | 70 | 50 | 2025-04-02 | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3099.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | 2024-04-10 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56, ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-04-17 | 2025-05-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1755.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-04-17 | 39 | 29 | 2025-04-17 | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-05 | 19 | 13 | 2025-04-17 | 2025-05-20 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | Unknown | Unknown | No | 2024-03-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | Yes | 229 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1589.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-11-12 | 230 | 164 | 2024-11-12 | 2025-01-24 | 74 | 54 | 2025-01-24 | 2025-03-04 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2291.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-13 | 2 | 2 | 2025-03-13 | 2025-03-28 | 16 | 12 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2539.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2025-01-16 | 79 | 57 | 2025-01-16 | 2025-01-17 | 2 | 2 | 2025-01-17 | 2025-06-04 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2272.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-09-22 | 60 | 44 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 461.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-26 | 2 | 2 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 513.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-08-11 | 68 | 50 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19837 | 14524.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-01 | 2023-11-14 | 106 | 76 | 2023-11-14 | 2024-11-06 | 359 | 257 | 2023-12-27 | 2024-01-03 | 8 | 6 | 2024-12-03 | 2024-12-30 | 28 | 20 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 36.36 | 36.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11006 | 2799.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-03-26 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | Unknown | Unknown | No | 2025-01-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | Yes | 88 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1792.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2025-01-20 | 18 | 12 | 2025-01-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-06-05 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1410.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | 2025-05-14 | 203 | 145 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-13 | 18 | 14 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1411.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-07-09 | 29 | 21 | 2024-07-09 | 2024-09-24 | 78 | 56 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 907.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-04-08 | 46 | 32 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 728.1 | 728.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1612.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-26 | 6 | 4 | 2024-11-26 | 2024-11-27 | 2 | 2 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 54995.8 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-09 | 2024-05-09 | 518 | 370 | 2024-05-09 | 2025-03-18 | 314 | 224 | 2024-09-24 | 2024-09-25 | 2 | 2 | 2024-10-22 | 2025-08-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-07-11 | 101 | 73 | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1823238.59 | 83216.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-10-23 | 171 | 123 | 2024-08-30 | 2024-09-03 | 5 | 3 | 2024-10-17 | 2024-10-22 | 6 | 4 | 2024-10-23 | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21215.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-01 | 2023-11-14 | 106 | 76 | 2023-11-14 | 2024-11-06 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-12-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1811.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-19 | 2 | 2 | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61.75 | 61.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1422.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-30 | 32 | 22 | 2025-03-30 | 2025-04-09 | 11 | 8 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 125.05 | 125.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2025-05-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1376.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2025-01-16 | 247 | 177 | 2025-01-16 | 2025-01-24 | 9 | 7 | 2025-01-24 | 2025-03-19 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-05-30 | 72 | 52 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 7275.4 | 7275.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1549.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-11-01 | 11 | 9 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 372.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-26 | 2023-07-14 | 19 | 15 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4356.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4280.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2024-01-04 | 2024-01-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 288.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-28 | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2024-01-04 | 18 | 14 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 778.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2024-01-05 | 31 | 23 | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 975.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | 2025-04-04 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-04-11 | 44 | 32 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 839.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-27 | 9 | 7 | 2025-06-27 | 2025-06-27 | 1 | 1 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown

## Tariff Cancelled-Rejected
Preliminary Project Information | [7 empty] | Site Capacity & Capacity Requested |  |  |  | Upstream Capacity |  |  |  | Customer Desired Energization Date vs Final Energization Date |  |  | Additional Capacity, Flexible Service Option, & Cancelled/Delayed Project Information | [10 empty] | Tariff Upgrade |  |  | Customer Elect and Customer Project Delay |  |  |  | Costing Components | [9 empty] | Step 1 - Intake (Customer) | [6 empty] | Step 2: Engineering and Design (IOU) |  |  |  | Step 3: Customer Dependencies (Customer) |  |  |  | Step 4: Utility Dependencies (IOU) |  |  |  | Step 5: Project Site Readiness (Customer) |  |  |  | Step 6: Project Site Readiness (IOU) |  |  |  | Step 7: Construction (IOU) |  |  |  | Step 8: Service Energization (IOU) |  |  |  | Customer Controlled Steps |  | IOU Controlled Steps |  | IOU & Customer Controlled Steps |  | Concurrent Steps |  |  | Meeting/Exceeding Energization Targets
Project Identifier # (project #) | Tariff (R15, R16, R29/R45, Combo) | OH (Overhead) or UG (Underground) | Applicant or IOU Design | Business Class (requested end-use) | Community type: Disadvantage Community (DAC) Underserved Community Tribal Community | City Project is Located in (City) | AHJ (Authority Having Jurisdiction) for permitting based off Project's location (AHJ) | Total Site Capacity at Time of Customer's Application for Service (kW) | Total Site Capacity Requested (kW) | Additional Capacity (kW) installed for future electric load deployment (as applicable) | Capacity Request Category: <1MW 1MW to 2M >2MW | Project triggered for upstream capacity project (Yes/No) | Date IOU identifies the need for an upstream capacity project and alerts customer of need for upstream capacity project (Date) | Date IOU completes the upstream capacity project (Date) | Time to complete upstream capacity project (Calendar Days) | Customer Desired Energization Date (Date) | Difference from Customer Desired Energization Date and Final Energization Date (Calendar Days) | Difference from Customer Desired Energization Date and Final Energization Date (Business Days) | Did customer install additional capacity to support future load growth? (Yes or No) | Identify when in the energization process the customer requested a change in design or scope (Date) | Identify when in energization process the customer requested a change in design or scope (Energization Step) | Customer cancelled/delayed project (as needed) (Yes or No) | Customer elected to install additional capacity to anticipate associated future load growth as indicated on customer's application (Yes or No) | Estimated timing for when customer anticipates additional capacity necessary as indicated on customer's application (Date) | Total additional kW capacity for the necessary future upgrade as listed on customer's application (kW) | If full energization of applicant site not feasible in a timely manner, explanation whether load management/flexible service options were installed/utilized to provide applicant with timely service | Amount of load (kW) provided to applicant using flexible service options (kW) | At the time energization provided, remaining (or total) unserved load requested by the applicant (kW) | Estimate when full service will be provided to the applicant for customers using flexible service and/or receiving tiered load schedules (Date) | Date when need for R15/16/29/45 upgrade identified (Date) | Date when Planning Work started R15/16/29/45 upgrade (Date) | Date when Construction Work started R15/16/29/45 upgrade (Date) | For R15/16 tariffs, did customer elect to take on typical IOU completed scope and vice versa. (i.e. Applicant Design or Applicant Install) (N/A, Customer elected Applicant Design/Install/Both) | For R15/16 tariffs, did customer elect to take on typical IOU completed scope and vice versa. Indicate Applicant Design or Applicant Install (N/A, Customer elected, IOU elected) Specify energization steps. (List Energization Steps) | For R15/R16 tariffs, project was delayed due to customer requested change in design or change in project scope (Yes, No) | For R15/R16 tariffs, the time the project was delayed due to customer requested change in design or change in project scope (Calendar Days) | Total Cost ($$$) to Complete All Energization Requests | Total Staffing, Labor, and Material Cost ($$$ Capital and Expense) | Total upstream capacity project cost ($$$) | Project Costs ($$$) for all IOU equipment for upstream capacity projects, Electric Rule 15, Electric Rule 16, and Electric Rule 29/45. | Project Costs ($$$) for anything else IOU covers | Total Construction/Overhead Costs ($$$) | Customer Allowance ($$$) | Estimated Costs ($$$) at Time of Design | Actual Costs ($$$) at Time of Energization | Difference of Estimated and Actual Costs at Time of Energization ($$$) | IOU assigned account/project manager for initial application (within 10 days) (Yes/No) | Date of IOU rejection of application (Date) | IOU reason for rejection of application (Reason) | Step 1 - Data Point Start 1) Intake Start Date (Date) | Step 1 - Data Point End 2) Intake End (Date) | Step 1: Intake (Calendar Days) | Step 1: Intake (Business Days) | Step 2 - Data Point Start 2) Engineering and Design Start (Date) | Step 2 - Data Point End 3) Engineering and Design End (Date) | Step 2: Engineering and Design (Calendar Days) | Step 2: Engineering and Design (Business Days) | Step 3 - Data Point Start 3) Customer Dependencies Start (Date) | Step 3 - Data Point End 4) Customer Dependencies End (Date) | Step 3: Customer Dependencies (Calendar Days) | Step 3: Customer Dependencies (Business Days) | Step 4 - Data Point Start 4) Utility Dependencies Start (Date) | Step 4 - Data Point End 5) Utility Dependencies End (Date) | Step 4: Utility Dependencies (Calendar Days) | Step 4: Utility Dependencies (Business Days) | Step 5 - Data Point Start 5) Customer Site Readiness Start (Date) | Step 5 - Data Point End 6) Customer Site Readiness End (Date) | Step 5: Site Readiness (Calendar Days) | Step 5: Site Readiness (Business Days) | Step 6 - Data Point Start 6) IOU Site Readiness Start (Date) | Step 6 - Data Point End 7) Site Readiness IOU End (Date) | Step 6: Site Readiness (Calendar Days) | Step 6: Site Readiness (Business Days) | Step 7 - Data Point Start 7) Construction Start (Date) | Step 7 - Data Point End 8) Construction End (Date) | Step 7: Construction (Calendar Days) | Step 7: Construction (Business Days) | Step 8 - Data Point Start 8) Service Energization Start (Date) | Step 8 - Data Point End 9) Service Energization End (Date) | Step 8: Service Energization (Calendar Days) | Step : Service Energization (Business Days) | Customer Controlled Steps: Step 1 - Intake, Step 3 - Customer Dependencies, & Step 5 - Site Readiness (Customer) (Calendar Days) | Customer Controlled Steps: Step 1 - Intake, Step 3 - Customer Dependencies, & Step 5 - Site Readiness (Customer) (Business Days) | IOU Controlled Steps: Step 2 - Engineering & Design, Step 4 - Utility Dependencies, Step 6 - Site Readiness (IOU), Step 7 - Construction, Step 8 - Service Energization (Calendar Days) | IOU Controlled Steps: Step 2 - Engineering & Design, Step 4 - Utility Dependencies, Step 6 - Site Readiness (IOU), Step 7 - Construction, Step 8 - Service Energization (Business Days) | End to End Cycle Time (1 to 8) (Calendar Days) | End to End Cycle Time (1 to 8) (Business Days) | Energization Steps Completed Concurrently (Energization Step(s) Listed) | Total time for Energization Steps Completed Concurrently (Calendar Days) | Total time for Energization Steps Completed Concurrently (Business Days) | R15/R16/R29/R45 Energization Average meeting/exceeding Average Energization Target (Meeting/Exceeding) | R15/R16/R29/R45 Energization Maximum meeting/exceeding Maximum Energization Target (Meeting/Exceeding) | R15/R16/R29/R45 Energization Reasoning as to why exceeded average/maximum Energization Target (Reasoning) | Location of project exceeding the maximum energization target: Location (circuit level)
| R15 | UG | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | DESCANSO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | WARNER SPRINGS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | BONSALL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | BOULEVARD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | WARNER SPRINGS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | Incorrect design. New job created. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | No work needed, internal FM | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | Cancelled per customer request. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | NATIONAL CITY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | Cancelled per customer request. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | Customer change of ownership. New owner cancelled request. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | Revised and included in another job | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15_16_Combo | OH | N/A | N/A | N/A | JAMUL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | Job created in error. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | Additional work required before work can be completed. Separate project created to address work required. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | Additional work required before work can be completed. Separate project created to address work required. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAGUNA NIGEL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | Revised order submitted once customer was ready to proceed. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | Per customer request | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | Outdated job. Replaced with new job. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | Duplicate | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | Per customer request | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | Incorrect. Was meant to be completed instead of cancelled. System update pending. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | Job not viable due to power source | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | Job not viable due to power source | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | Job written off | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-27 | Test Only | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-27 | Test Only | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-27 | Test Only | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | Duplicate | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | DESCANSO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | Work removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BORREGO SPRINGS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-06 | Job written off | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | Per customer request | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | Per customer request | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | Job already completed | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | Duplicative | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | Job not viable due to switch positions and cables already installed. | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOUTH LAGUNA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | New job created to replace and revise | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | Test only | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | N/A | N/A | 2023-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | OH | N/A | N/A | N/A | BONSALL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | N/A | N/A | 2023-06-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | N/A | N/A | 2023-10-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | N/A | N/A | 2023-05-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | N/A | N/A | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | N/A | N/A | 2023-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | N/A | N/A | 2023-06-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | N/A | N/A | 2023-09-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | N/A | 2023-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | JULIAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | N/A | N/A | 2023-05-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | JULIAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | N/A | N/A | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | N/A | N/A | 2023-06-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | N/A | N/A | 2023-07-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | N/A | N/A | 2024-07-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | N/A | N/A | 2023-05-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARDIFF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-16 | N/A | N/A | 2024-11-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | N/A | N/A | 2023-04-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | N/A | N/A | 2023-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | N/A | 2023-03-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | N/A | N/A | 2023-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | N/A | N/A | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | N/A | N/A | 2023-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | N/A | N/A | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | N/A | N/A | 2023-04-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | N/A | N/A | 2023-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | N/A | N/A | 2023-05-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | N/A | N/A | 2023-05-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | N/A | N/A | 2023-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | N/A | N/A | 2023-05-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | N/A | N/A | 2023-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | N/A | N/A | 2023-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | N/A | N/A | 2023-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | N/A | N/A | 2023-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CORONADO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | N/A | N/A | 2024-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | N/A | N/A | 2023-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | N/A | N/A | 2024-03-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | N/A | N/A | 2024-05-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | N/A | N/A | 2024-05-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15_16_Combo | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | N/A | N/A | 2023-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-12 | N/A | N/A | 2023-08-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | N/A | N/A | 2023-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | N/A | N/A | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | N/A | N/A | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | N/A | 2023-02-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | N/A | N/A | 2023-06-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | N/A | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | N/A | N/A | 2023-07-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | N/A | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | N/A | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | N/A | N/A | 2023-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | N/A | N/A | 2023-10-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | N/A | N/A | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | N/A | N/A | 2023-10-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | N/A | N/A | 2023-05-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | N/A | N/A | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | N/A | N/A | 2023-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | N/A | N/A | 2023-05-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | N/A | N/A | 2023-06-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | N/A | N/A | 2023-02-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | N/A | N/A | 2023-03-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | N/A | N/A | 2023-06-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | N/A | N/A | 2024-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | N/A | N/A | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | N/A | N/A | 2023-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | N/A | N/A | 2023-04-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | N/A | N/A | 2023-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | N/A | N/A | 2023-04-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO LA COSTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | N/A | N/A | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-05 | N/A | N/A | 2023-08-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | N/A | N/A | 2023-04-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | N/A | N/A | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | N/A | N/A | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | N/A | N/A | 2023-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | N/A | N/A | 2023-11-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | JAMUL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | N/A | N/A | 2023-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DESCANSO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | N/A | N/A | 2023-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | N/A | N/A | 2023-10-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | N/A | N/A | 2023-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN YSIDRO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | N/A | N/A | 2023-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | N/A | N/A | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | N/A | N/A | 2023-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | N/A | N/A | 2023-05-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | N/A | N/A | 2023-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | N/A | N/A | 2023-06-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | N/A | N/A | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | N/A | N/A | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | N/A | N/A | 2023-07-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | N/A | N/A | 2023-08-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | N/A | N/A | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | N/A | N/A | 2023-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | N/A | N/A | 2023-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | N/A | N/A | 2023-09-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-26 | N/A | N/A | 2024-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | N/A | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | N/A | N/A | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | N/A | N/A | 2024-07-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | N/A | N/A | 2024-12-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | N/A | N/A | 2023-10-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-30 | N/A | N/A | 2023-04-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | N/A | N/A | 2024-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | N/A | N/A | 2023-10-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | N/A | N/A | 2023-10-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | N/A | N/A | 2024-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | N/A | N/A | 2024-05-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | N/A | N/A | 2024-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | N/A | N/A | 2023-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | N/A | N/A | 2023-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | IMPERIAL BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-26 | N/A | N/A | 2024-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | N/A | N/A | 2024-07-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | N/A | N/A | 2023-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | N/A | 2023-03-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | N/A | N/A | 2023-07-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | N/A | N/A | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | N/A | N/A | 2023-03-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | N/A | N/A | 2023-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | N/A | N/A | 2023-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | N/A | N/A | 2024-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | N/A | N/A | 2023-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | N/A | N/A | 2023-07-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | N/A | N/A | 2024-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | N/A | N/A | 2024-01-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | N/A | N/A | 2024-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | N/A | N/A | 2024-08-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | N/A | 2023-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | N/A | N/A | 2023-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | N/A | N/A | 2023-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | N/A | N/A | 2023-08-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | N/A | N/A | 2023-02-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | N/A | N/A | 2023-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | IMPERIAL BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | N/A | N/A | 2023-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | N/A | N/A | 2024-11-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | N/A | N/A | 2023-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | N/A | N/A | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | MISSION VIEJO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | N/A | N/A | 2023-10-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOUTH LAGUNA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | N/A | N/A | 2024-01-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | N/A | N/A | 2023-11-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | N/A | N/A | 2024-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | N/A | N/A | 2024-04-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAS FLORES | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | N/A | N/A | 2024-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CAPISTRANO BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | N/A | N/A | 2024-10-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | N/A | N/A | 2024-09-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | N/A | N/A | 2023-04-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | N/A | N/A | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | N/A | N/A | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | N/A | N/A | 2023-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | N/A | 2024-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | N/A | N/A | 2024-04-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | N/A | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | N/A | N/A | 2023-05-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | N/A | N/A | 2023-05-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | N/A | N/A | 2023-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LEMON GROVE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | N/A | N/A | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | N/A | N/A | 2024-04-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | N/A | N/A | 2023-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARDIFF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | N/A | 2024-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | N/A | N/A | 2023-11-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | N/A | N/A | 2023-10-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | N/A | N/A | 2024-04-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | N/A | N/A | 2023-08-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | N/A | N/A | 2023-10-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | N/A | N/A | 2023-04-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOLANA BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | N/A | N/A | 2023-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | N/A | N/A | 2023-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | N/A | N/A | 2023-11-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | N/A | N/A | 2023-08-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | N/A | N/A | 2023-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | N/A | N/A | 2023-06-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CORONADO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-16 | N/A | N/A | 2023-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | N/A | N/A | 2023-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | N/A | N/A | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | N/A | N/A | 2023-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | NATIONAL CITY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | N/A | N/A | 2023-08-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | N/A | N/A | 2023-03-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | N/A | N/A | 2023-04-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | N/A | N/A | 2023-05-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | N/A | N/A | 2024-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | N/A | N/A | 2023-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | N/A | N/A | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | N/A | N/A | 2023-05-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-21 | N/A | N/A | 2022-12-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOLANA BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | N/A | N/A | 2023-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | N/A | N/A | 2023-11-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | N/A | N/A | 2023-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | N/A | N/A | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | N/A | N/A | 2023-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LEMON GROVE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | N/A | N/A | 2023-07-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | N/A | N/A | 2023-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | N/A | N/A | 2023-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | N/A | N/A | 2023-05-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | N/A | N/A | 2023-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | N/A | N/A | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | N/A | N/A | 2023-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | N/A | N/A | 2024-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | N/A | N/A | 2024-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | N/A | N/A | 2024-02-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | N/A | N/A | 2023-10-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A | N/A | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | N/A | N/A | 2023-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | N/A | N/A | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | N/A | N/A | 2023-05-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | N/A | 2023-04-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | N/A | N/A | 2023-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | N/A | N/A | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | N/A | N/A | 2023-06-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | N/A | 2023-05-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | N/A | 2023-05-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | N/A | N/A | 2023-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LEMON GROVE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | N/A | N/A | 2023-04-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | N/A | N/A | 2023-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | N/A | N/A | 2023-11-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | N/A | N/A | 2023-06-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | N/A | N/A | 2023-09-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-17 | N/A | N/A | 2023-06-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CORONADO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-11 | N/A | N/A | 2024-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CORONADO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | N/A | N/A | 2024-03-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | N/A | N/A | 2024-02-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | N/A | N/A | 2023-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | NATIONAL CITY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-10 | N/A | N/A | 2023-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | N/A | N/A | 2023-04-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LEMON GROVE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | N/A | N/A | 2023-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-30 | N/A | N/A | 2022-12-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | N/A | N/A | 2022-12-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | N/A | N/A | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | N/A | N/A | 2023-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | N/A | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | N/A | N/A | 2024-08-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | N/A | N/A | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | N/A | N/A | 2024-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | N/A | N/A | 2024-10-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | N/A | N/A | 2024-08-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | N/A | N/A | 2023-04-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | N/A | N/A | 2024-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | N/A | N/A | 2024-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | N/A | N/A | 2024-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | N/A | N/A | 2023-04-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | N/A | 2023-03-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | N/A | N/A | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | N/A | N/A | 2023-04-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-29 | N/A | N/A | 2023-04-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | N/A | N/A | 2023-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | N/A | 2023-03-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | N/A | N/A | 2023-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | N/A | N/A | 2023-02-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | N/A | N/A | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | N/A | N/A | 2023-03-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | N/A | N/A | 2023-03-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | N/A | N/A | 2024-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO LA COSTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | N/A | N/A | 2023-05-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | N/A | N/A | 2023-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | N/A | N/A | 2023-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | N/A | N/A | 2023-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | N/A | N/A | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | N/A | N/A | 2023-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | N/A | N/A | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | N/A | N/A | 2024-01-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | N/A | N/A | 2023-05-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | N/A | N/A | 2023-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | N/A | N/A | 2023-09-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | N/A | N/A | 2024-07-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | N/A | N/A | 2023-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BORREGO SPRINGS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | N/A | N/A | 2024-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | N/A | N/A | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | N/A | N/A | 2024-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | N/A | N/A | 2023-10-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | N/A | N/A | 2023-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | N/A | N/A | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | N/A | N/A | 2023-10-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | N/A | N/A | 2023-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CAPISTRANO BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | N/A | N/A | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | N/A | N/A | 2023-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | N/A | N/A | 2023-10-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LADERA RANCH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | N/A | N/A | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | N/A | N/A | 2024-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | N/A | N/A | 2023-08-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | N/A | N/A | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | N/A | N/A | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | N/A | N/A | 2024-03-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | N/A | N/A | 2023-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | NATIONAL CITY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | N/A | N/A | 2023-10-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | N/A | N/A | 2023-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | N/A | N/A | 2024-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | N/A | N/A | 2023-04-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | N/A | N/A | 2024-01-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | N/A | N/A | 2024-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | N/A | N/A | 2023-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | N/A | N/A | 2023-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | N/A | N/A | 2023-12-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | N/A | N/A | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | N/A | N/A | 2024-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | N/A | N/A | 2023-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | N/A | N/A | 2023-12-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | N/A | N/A | 2023-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | N/A | N/A | 2023-04-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | N/A | N/A | 2023-08-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | N/A | N/A | 2024-04-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | N/A | N/A | 2023-05-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | N/A | N/A | 2023-07-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | N/A | N/A | 2023-03-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | N/A | N/A | 2023-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | N/A | N/A | 2024-03-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | N/A | N/A | 2024-02-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | N/A | N/A | 2024-10-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | N/A | N/A | 2024-12-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | N/A | N/A | 2024-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-12 | N/A | N/A | 2023-08-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-12 | N/A | N/A | 2023-08-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | N/A | N/A | 2024-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | N/A | N/A | 2024-08-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | N/A | N/A | 2024-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | N/A | N/A | 2024-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | N/A | N/A | 2024-10-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | N/A | N/A | 2024-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | N/A | N/A | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | N/A | N/A | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | N/A | N/A | 2024-07-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | NATIONAL CITY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | N/A | N/A | 2023-08-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | N/A | N/A | 2023-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SOLANA BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | N/A | N/A | 2023-04-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | N/A | N/A | 2023-05-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | N/A | N/A | 2023-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | N/A | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | N/A | N/A | 2023-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | N/A | N/A | 2023-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | N/A | N/A | 2024-07-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | Job already completed | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | No customer response | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | Removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | Removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | Removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BORREGO SPRINGS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | No customer response | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | LADERA RANCH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | Job already completed | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | Duplicate job | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | Per customer request | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | No customer response | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | No customer response | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | Removed from scope of project | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | PALA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-01-31 | N/A | N/A | 2023-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | JACUMBA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-07 | N/A | N/A | 2023-04-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-06 | N/A | N/A | 2023-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | JULIAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-04 | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-02-25 | N/A | N/A | 2023-02-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-02-25 | N/A | N/A | 2023-02-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-02 | N/A | N/A | 2023-03-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-28 | N/A | N/A | 2023-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-21 | N/A | N/A | 2023-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-03-21 | N/A | N/A | 2024-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-19 | N/A | N/A | 2023-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-20 | N/A | N/A | 2023-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-02-22 | N/A | N/A | 2023-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-16 | N/A | N/A | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-24 | N/A | N/A | 2023-04-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-02 | N/A | N/A | 2023-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-09 | N/A | N/A | 2023-06-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-01 | N/A | N/A | 2023-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-04 | N/A | N/A | 2023-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-01 | N/A | N/A | 2023-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-18 | N/A | N/A | 2023-04-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-11 | N/A | N/A | 2023-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-10 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-21 | N/A | N/A | 2023-08-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-15 | N/A | N/A | 2023-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-29 | N/A | N/A | 2023-04-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R45 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-31 | N/A | N/A | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R45 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-22 | N/A | N/A | 2023-12-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-19 | N/A | N/A | 2023-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-06 | N/A | N/A | 2023-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-12 | N/A | N/A | 2023-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-28 | N/A | N/A | 2023-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-06 | N/A | N/A | 2023-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-19 | N/A | N/A | 2023-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-11 | N/A | N/A | 2023-04-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LADERA RANCH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-21 | N/A | N/A | 2023-04-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-25 | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-28 | N/A | N/A | 2023-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-24 | N/A | N/A | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | BONSALL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-07 | N/A | N/A | 2023-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-11 | N/A | N/A | 2023-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-15 | N/A | N/A | 2023-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-01 | N/A | N/A | 2023-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-13 | N/A | N/A | 2023-04-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-17 | N/A | N/A | 2023-07-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-17 | N/A | N/A | 2023-07-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-10 | N/A | N/A | 2023-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-01-09 | N/A | N/A | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-27 | N/A | N/A | 2023-07-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-11 | N/A | N/A | 2023-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-26 | N/A | N/A | 2023-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAGUNA HILLS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-09 | N/A | N/A | 2023-08-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-27 | N/A | N/A | 2023-07-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-03 | N/A | N/A | 2023-08-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-01 | N/A | N/A | 2023-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-11 | N/A | N/A | 2023-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-28 | N/A | N/A | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-23 | N/A | N/A | 2023-05-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-11 | N/A | N/A | 2023-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-16 | N/A | N/A | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-12 | N/A | N/A | 2023-10-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-17 | N/A | N/A | 2023-04-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-11 | N/A | N/A | 2023-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | IMPERIAL BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-08 | N/A | N/A | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-19 | N/A | N/A | 2023-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-12 | N/A | N/A | 2024-02-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-10 | N/A | N/A | 2023-11-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-16 | N/A | N/A | 2023-10-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-01-18 | N/A | N/A | 2024-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-01 | N/A | N/A | 2023-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-18 | N/A | N/A | 2023-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-03-27 | N/A | N/A | 2024-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-18 | N/A | N/A | 2023-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAGUNA HILLS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-25 | N/A | N/A | 2023-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-21 | N/A | N/A | 2023-11-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | POTRERO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-23 | N/A | N/A | 2023-10-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-18 | N/A | N/A | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-06 | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-01-02 | N/A | N/A | 2024-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-18 | N/A | N/A | 2023-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-13 | N/A | N/A | 2023-11-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | NATIONAL CITY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-17 | N/A | N/A | 2023-11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-01 | N/A | N/A | 2024-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-02-20 | N/A | N/A | 2025-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-19 | N/A | N/A | 2023-12-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-25 | N/A | N/A | 2023-09-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-04-24 | N/A | N/A | 2024-04-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LEMON GROVE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-01-29 | N/A | N/A | 2024-01-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOUTH LAGUNA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-27 | N/A | N/A | 2023-12-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-06 | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-15 | N/A | N/A | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | LAKESIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-03-15 | N/A | N/A | 2024-03-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-04-12 | N/A | N/A | 2024-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-15 | N/A | N/A | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAGUNA NIGEL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-21 | N/A | N/A | 2024-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LADERA RANCH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-22 | N/A | N/A | 2024-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-01-29 | N/A | N/A | 2024-01-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-21 | N/A | N/A | 2024-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-05-23 | N/A | N/A | 2024-05-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-04-16 | N/A | N/A | 2024-04-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R45 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-05-31 | N/A | N/A | 2024-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | MISSION VIEJO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-06-21 | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | COTO DE CAZA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-10-15 | N/A | N/A | 2024-10-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-07-05 | N/A | N/A | 2024-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LAGUNA HILLS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-08-05 | N/A | N/A | 2024-08-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-09-26 | N/A | N/A | 2024-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-09-06 | N/A | N/A | 2024-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-09-26 | N/A | N/A | 2024-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-10-21 | N/A | N/A | 2024-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-11-21 | N/A | N/A | 2024-11-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-16 | N/A | N/A | 2025-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-13 | N/A | N/A | 2025-01-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-07 | N/A | N/A | 2025-01-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-19 | N/A | N/A | 2025-01-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-22 | N/A | N/A | 2025-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CAMPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-27 | N/A | N/A | 2025-01-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-31 | N/A | N/A | 2025-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-02-04 | N/A | N/A | 2025-02-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-02-26 | N/A | N/A | 2025-02-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-02-14 | N/A | N/A | 2025-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-04-16 | N/A | N/A | 2025-04-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-04-16 | N/A | N/A | 2025-04-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOUTH LAGUNA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-03-10 | N/A | N/A | 2025-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | MISSION VIEJO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-07-29 | N/A | N/A | 2024-07-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SANTEE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-26 | N/A | N/A | 2023-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-04-24 | N/A | N/A | 2024-04-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-12-26 | N/A | N/A | 2024-12-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-02 | N/A | N/A | 2023-10-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-06 | N/A | N/A | 2023-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-03 | N/A | N/A | 2023-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-24 | N/A | N/A | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-01-16 | N/A | N/A | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-12-15 | N/A | N/A | 2023-12-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | JULIAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-05-06 | N/A | N/A | 2025-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-04 | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-24 | N/A | N/A | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-13 | N/A | N/A | 2023-11-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-07-18 | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-19 | N/A | N/A | 2023-08-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-25 | N/A | N/A | 2023-08-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-10-09 | N/A | N/A | 2024-10-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-03-27 | N/A | N/A | 2024-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-26 | N/A | N/A | 2023-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-06-06 | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-06-09 | N/A | N/A | 2025-06-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-26 | N/A | N/A | 2024-02-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | POWAY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-10 | N/A | N/A | 2023-04-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-13 | N/A | N/A | 2023-11-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-01 | N/A | N/A | 2023-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-14 | N/A | N/A | 2023-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-23 | N/A | N/A | 2023-08-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R15 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-14 | N/A | N/A | 2025-01-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-15 | N/A | N/A | 2023-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-21 | N/A | N/A | 2023-08-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SOLANA BEACH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-17 | N/A | N/A | 2023-11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-29 | N/A | N/A | 2024-02-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-30 | N/A | N/A | 2023-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-03-25 | N/A | N/A | 2025-03-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-05-21 | N/A | N/A | 2024-05-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-28 | N/A | N/A | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-08-08 | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-10 | N/A | N/A | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-18 | N/A | N/A | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-24 | N/A | N/A | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-10-20 | N/A | N/A | 2024-10-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-01-17 | N/A | N/A | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-02-02 | N/A | N/A | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-03-05 | N/A | N/A | 2025-03-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-29 | N/A | N/A | 2023-06-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-28 | N/A | N/A | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-05-07 | N/A | N/A | 2024-05-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-18 | N/A | N/A | 2023-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-25 | N/A | N/A | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-25 | N/A | N/A | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-03-30 | N/A | N/A | 2023-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | DULZURE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-02-10 | N/A | N/A | 2023-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-10 | N/A | N/A | 2025-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-15 | N/A | N/A | 2023-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-11-30 | N/A | N/A | 2023-11-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-25 | N/A | N/A | 2023-08-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | BOULEVARD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-05-03 | N/A | N/A | 2023-05-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-04-26 | N/A | N/A | 2024-04-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-19 | N/A | N/A | 2023-10-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN YSIDRO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-28 | N/A | N/A | 2023-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-03-28 | N/A | N/A | 2024-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-03 | N/A | N/A | 2023-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-28 | N/A | N/A | 2023-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-12-30 | N/A | N/A | 2024-12-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-04-12 | N/A | N/A | 2024-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-17 | N/A | N/A | 2023-08-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-30 | N/A | N/A | 2023-10-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-06-27 | N/A | N/A | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-21 | N/A | N/A | 2023-04-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-04 | N/A | N/A | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-01-14 | N/A | N/A | 2025-01-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-10-02 | N/A | N/A | 2023-10-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-05-21 | N/A | N/A | 2024-05-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-29 | N/A | N/A | 2023-08-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | RANCHO SANTA FE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-10-24 | N/A | N/A | 2024-10-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | BONITA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-03-24 | N/A | N/A | 2025-03-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-11-01 | N/A | N/A | 2024-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2024-07-12 | N/A | N/A | 2024-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-08-30 | N/A | N/A | 2023-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2025-03-19 | N/A | N/A | 2025-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | OH | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-04-07 | N/A | N/A | 2023-04-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | VISTA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-09-14 | N/A | N/A | 2023-09-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| R16 | UG | N/A | N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | 2023-07-21 | N/A | N/A | 2023-07-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## MPU Closed
Per Decision, Main Panel Upgrade (MPU) Data template to only include simple disconnect/reconnect work; All others would fall under Rule 16
MPU Project Identifier | Preliminary Project Data |  |  |  | MPU Specific End To End Data | [7 empty] | MPU Costing Components
Project Identifier # (project #) | Customer Desired Energization Date (Date) | Community type: Disadvantage Community (DAC) Underserved Community Tribal Community | City Project is Located in (City) | AHJ (Authority Having Jurisdiction) for permitting based off Project's location (AHJ) | Size of Installed Main Panel Upgrade (Amps) | Timing to Complete Main Panel Upgrade (Calendar Days) | Timing to Complete Main Panel Upgrade (Business Days) | Reason why upgrade was cancelled and/or rescheduled (Reason) | Main Panel Upgrade - Initial Schedule Date (Date) | Main Panel Upgrade - Rescheduled Date (as needed) (Date) | Additional Time from Initial Scheduled Date to Rescheduled Date (Calendar Days) | Additional Time from Initial Scheduled Date to Rescheduled Date (Business Days) | Total Staffing, Labor, and Material Cost ($$$ - Capital and Expense) | Project Costs ($$$) for anything else IOU covers | Total Construction/Overhead Costs ($$$) | Customer Allowance ($$$) | Estimated Costs ($$$) at Time of Design | Actual Costs ($$$) at Time of Energization | Difference of Estimated and Actual Costs at Time of Energization ($$$)
| 2025-04-10 | N/A | SAN DIEGO | N/A | Not Available | 141 | 101 | N/A | 2023-08-18 | Not Available | Not Available | Not Available | -11.03 | Unknown | -4.17 | 0 | 496.37 | -15.2 | 511.57
| 2026-08-28 | N/A | SAN DIEGO | N/A | Not Available | 322 | 230 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.46 | 0 | 158.79 | 4.46 | 154.33
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 265 | 189 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.43 | 0 | 463.93 | 12.43 | 451.5
| 2026-12-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2025-01-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.15 | 0 | 197.01 | 3.15 | 193.86
| 2026-01-17 | N/A | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2024-03-11 | Not Available | Not Available | Not Available | -10.3 | Unknown | -1.07 | 0 | 163.83 | -11.37 | 175.2
| 2026-03-20 | N/A | SAN DIEGO | N/A | Not Available | 81 | 57 | N/A | 2024-05-23 | Not Available | Not Available | Not Available | -7.66 | Unknown | -1.77 | 0 | 162.34 | -9.43 | 171.77
| 2025-11-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A | 2024-02-15 | Not Available | Not Available | Not Available | -8.47 | Unknown | -1.98 | 0 | 534.53 | -10.45 | 544.98
| 2025-03-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 224 | 160 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | -3 | Unknown | 161.16 | 0 | 158.37 | 158.16 | 0.21
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.16 | 0 | 197.01 | 9.16 | 187.85
| 2026-06-14 | N/A | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 5.72 | 0 | 192.95 | 5.72 | 187.23
| 2025-08-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 192 | 138 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.08 | 0 | 515.81 | -5.69 | 521.5
| 2026-12-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 130 | 92 | N/A | 2025-03-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.08 | 0 | 197.01 | 9.08 | 187.93
| 2025-03-31 | N/A | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2023-07-11 | Not Available | Not Available | Not Available | -6 | Unknown | -2.31 | 0 | 153.87 | -8.31 | 162.18
| 2026-01-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2024-04-11 | Not Available | Not Available | Not Available | -36.17 | Unknown | 949.16 | 0 | 501.18 | 912.99 | -411.81
| 2024-09-23 | N/A | SAN DIEGO | N/A | Not Available | 181 | 129 | N/A | 2024-03-05 | Not Available | Not Available | Not Available | -21.72 | Unknown | 724.01 | 0 | 513.31 | 702.29 | -188.98
| 2026-08-12 | N/A | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.75 | 0 | 197.01 | 5.75 | 191.26
| 2025-11-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 32 | 22 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 197.01 | 4.39 | 192.62
| 2026-05-13 | N/A | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.15 | 0 | 192.51 | 8.15 | 184.36
| 2025-04-27 | N/A | SAN DIEGO | N/A | Not Available | 162 | 116 | N/A | 2023-08-28 | Not Available | Not Available | Not Available | -13.23 | Unknown | -5 | 0 | 153.83 | -18.23 | 172.06
| 2025-10-02 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 260 | 186 | N/A |  | Not Available | Not Available | Not Available | 122.45 | Unknown | 84.25 | 0 | 534.53 | 206.7 | 327.83
| 2026-05-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 176 | 126 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.34 | 0 | 192.95 | 2.34 | 190.61
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.98 | 0 | 197.01 | 4.98 | 192.03
| 2026-11-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.63 | 0 | 1066.55 | 6.63 | 1059.92
| 2026-07-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 159 | 113 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.23 | 0 | 186.52 | 7.23 | 179.29
| 2027-01-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-02-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.69 | 0 | 554.38 | 8.69 | 545.69
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 289 | 207 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | -16.45 | Unknown | -8.94 | 0 | 554.38 | -25.39 | 579.77
| 2025-08-18 | N/A | SAN DIEGO | N/A | Not Available | 198 | 142 | N/A | 2024-02-29 | Not Available | Not Available | Not Available | -7.37 | Unknown | -0.53 | 0 | 158.79 | -7.9 | 166.69
| 2026-07-10 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2024-07-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.43 | 0 | 983.86 | 3.43 | 980.43
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.13 | 0 | 197.01 | 5.13 | 191.88
| 2026-11-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2024-12-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 33.69 | 0 | 1066.55 | 33.69 | 1032.86
| 2025-08-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 240 | 172 | N/A | 2024-02-29 | Not Available | Not Available | Not Available | -7.61 | Unknown | -1.75 | 0 | 534.53 | -9.36 | 543.89
| 2026-02-07 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-03-25 | Not Available | Not Available | Not Available | -7.29 | Unknown | -1.7 | 0 | 534.53 | -8.99 | 543.52
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 289 | 207 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | -20.92 | Unknown | -11.38 | 0 | 554.38 | -32.3 | 586.68
| 2026-11-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A |  | Not Available | Not Available | Not Available | 369.26 | Unknown | 619.83 | 0 | 1066.55 | 989.09 | 77.46
| 2026-07-29 | N/A | SAN DIEGO | N/A | Not Available | 173 | 125 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.93 | 0 | 197.01 | 13.93 | 183.08
| 2026-11-25 | N/A | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.48 | 0 | 197.01 | 9.48 | 187.53
| 2026-11-22 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.39 | 0 | 196.69 | 18.39 | 178.3
| 2026-03-28 | N/A | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2024-06-04 | Not Available | Not Available | Not Available | -7.49 | Unknown | 0.28 | 0 | 192.83 | -7.21 | 200.04
| 2025-07-07 | N/A | SAN DIEGO | N/A | Not Available | 236 | 168 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | -17.3 | Unknown | -3.01 | 0 | 158.79 | -20.31 | 179.1
| 2026-04-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 162 | 116 | N/A | 2024-09-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 31.76 | 0 | 192.83 | 31.76 | 161.07
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 147 | 105 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.78 | 0 | 554.38 | 6.78 | 547.6
| 2025-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 154 | 110 | N/A | 2024-02-23 | Not Available | Not Available | Not Available | -8.72 | Unknown | -2.04 | 0 | 534.53 | -10.76 | 545.29
| 2024-03-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 265 | 189 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.44 | 0 | 1049.43 | 16.44 | 1032.99
| 2025-08-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -4.26 | Unknown | -1.16 | 0 | 513.31 | -5.42 | 518.73
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.37 | 0 | 197.01 | 4.37 | 192.64
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 238 | 170 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.15 | 0 | 463.93 | 13.15 | 450.78
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.16 | 0 | 197.01 | 6.16 | 190.85
| 2025-07-20 | N/A | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | -5.83 | Unknown | -0.71 | 0 | 158.79 | -6.54 | 165.33
| 2027-01-30 | N/A | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | -15.28 | Unknown | -8.32 | 0 | 196.44 | -23.6 | 220.04
| 2026-08-30 | N/A | SAN DIEGO | N/A | Not Available | 26 | 18 | N/A | 2024-09-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.15 | 0 | 985.1 | 18.15 | 966.95
| 2025-06-22 | N/A | SAN DIEGO | N/A | Not Available | 174 | 124 | N/A | 2023-12-01 | Not Available | Not Available | Not Available | -6.51 | Unknown | -0.91 | 0 | 158.14 | -7.42 | 165.56
| 2026-12-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2024-12-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.27 | 0 | 197.01 | 5.27 | 191.74
| 2025-02-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 179 | 129 | N/A | 2023-08-28 | Not Available | Not Available | Not Available | -17.66 | Unknown | 637.22 | 0 | 496.45 | 619.56 | -123.11
| 2026-12-01 | N/A | MISSION VIEJO | N/A | Not Available | 35 | 25 | N/A | 2024-12-23 | Not Available | Not Available | Not Available | 10.24 | Unknown | 21.5 | 0 | 197.01 | 31.74 | 165.27
| 2025-09-13 | N/A | SAN CLEMENTE | N/A | Not Available | 8 | 6 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 26.72 | 0 | 1050.75 | 26.72 | 1024.03
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 1 | 1 | N/A | 2023-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 0.02 | 0 | 153.83 | 0.02 | 153.81
| 2026-08-16 | N/A | SAN CLEMENTE | N/A | Not Available | 60 | 42 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.59 | 0 | 192.95 | 9.59 | 183.36
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 701 | 501 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.41 | 0 | 153.83 | 3.41 | 150.42
| 2026-10-21 | N/A | LAGUNA HILLS | N/A | Not Available | 56 | 40 | N/A | 2024-12-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.6 | 0 | 184.29 | 8.6 | 175.69
| 2024-10-20 | N/A | MISSION VIEJO | N/A | Not Available | 129 | 93 | N/A | 2023-11-17 | Not Available | Not Available | Not Available | -8.9 | Unknown | -2.4 | 0 | 147.93 | -11.3 | 159.23
| 2025-11-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | -4.81 | Unknown | 1.31 | 0 | 162.34 | -3.5 | 165.84
| 2025-11-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 129 | 93 | N/A | 2024-02-28 | Not Available | Not Available | Not Available | -13.57 | Unknown | 89.79 | 0 | 534.53 | 76.22 | 458.31
| 2027-02-12 | N/A | CARLSBAD | N/A | Not Available | 18 | 12 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | -10.88 | Unknown | 552.6 | 0 | 196.69 | 541.72 | -345.03
| 2025-06-25 | N/A | SAN CLEMENTE | N/A | Not Available | 133 | 95 | N/A | 2024-10-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.87 | 0 | 192.95 | 6.87 | 186.08
| 2025-05-03 | N/A | SAN CLEMENTE | N/A | Not Available | 61 | 43 | N/A | 2024-06-11 | Not Available | Not Available | Not Available | -3.82 | Unknown | -0.65 | 0 | 180.38 | -4.47 | 184.85
| 2026-10-15 | Underserved Community | POWAY | N/A | Not Available | 50 | 36 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.57 | 0 | 197.01 | 4.57 | 192.44
| 2027-03-07 | N/A | LAS FLORES | N/A | Not Available | 38 | 28 | N/A | 2025-04-01 | Not Available | Not Available | Not Available | -18.72 | Unknown | 480.98 | 0 | 183.91 | 462.26 | -278.35
| 2025-06-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 147 | 105 | N/A | 2023-09-29 | Not Available | Not Available | Not Available | -12.58 | Unknown | -4.56 | 0 | 500.87 | -17.14 | 518.01
| 2024-10-23 | N/A | SAN CLEMENTE | N/A | Not Available | 134 | 96 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | -9.2 | Unknown | -2.15 | 0 | 515.81 | -11.35 | 527.16
| 2025-08-09 | N/A | EL CAJON | N/A | Not Available | 9 | 7 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 192.95 | 4.01 | 188.94
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 452 | 322 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.42 | 0 | 153.83 | 8.42 | 145.41
| 2024-05-03 | Underserved Community | LA MESA | N/A | Not Available | 127 | 91 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.83 | 0 | 496.45 | -6.61 | 503.06
| 2025-06-20 | N/A | SAN CLEMENTE | N/A | Not Available | 89 | 63 | N/A | 2024-09-06 | Not Available | Not Available | Not Available | 240.03 | Unknown | 153.8 | 0 | 192.51 | 393.83 | -201.32
| 2024-05-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 116 | 84 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -6.51 | Unknown | -1.53 | 0 | 153.83 | -8.04 | 161.87
| 2024-06-15 | Underserved Community | EL CAJON | N/A | Not Available | 28 | 20 | N/A | 2023-07-05 | Not Available | Not Available | Not Available | -9.68 | Unknown | -3.68 | 0 | 496.45 | -13.36 | 509.81
| 2026-08-12 | Underserved Community | SPRING VALLEY | N/A | Not Available | 15 | 11 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.21 | 0 | 1103.3 | 6.21 | 1097.09
| 2025-10-27 | Underserved Community | EL CAJON | N/A | Not Available | 93 | 67 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | -7.7 | 0 | 288.94 | -7.7 | 296.64
| 2025-08-16 | Underserved Community | ALPINE | N/A | Not Available | 4 | 4 | N/A | 2024-08-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.61 | 0 | 1050.75 | 7.61 | 1043.14
| 2025-04-25 | N/A | LAGUNA NIGUEL | N/A | Not Available | 80 | 58 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.7 | 0 | 192.51 | 4.7 | 187.81
| 2025-10-27 | Underserved Community | EL CAJON | N/A | Not Available | 102 | 74 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | 111.11 | Unknown | 741.8 | 0 | 288.94 | 852.91 | -563.97
| 2026-02-02 | Underserved Community | LA MESA | N/A | Not Available | 94 | 68 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | -9.24 | Unknown | -2.15 | 0 | 158.37 | -11.39 | 169.76
| 2024-03-30 | N/A | SAN DIEGO | N/A | Not Available | 126 | 90 | N/A | 2023-08-14 | Not Available | Not Available | Not Available | -8.92 | Unknown | -2.24 | 0 | 153.83 | -11.16 | 164.99
| 2025-10-02 | N/A | SAN DIEGO | N/A | Not Available | 124 | 90 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -10.54 | Unknown | -2.47 | 0 | 163.83 | -13.01 | 176.84
| 2024-12-18 | N/A | DANA POINT | N/A | Not Available | 60 | 44 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -6.66 | Unknown | -1.56 | 0 | 153.26 | -8.22 | 161.48
| 2026-03-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 32 | 22 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | -10.76 | Unknown | 552.72 | 0 | 196.44 | 541.96 | -345.52
| 2024-11-08 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 116 | 84 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -8.96 | Unknown | -2.38 | 0 | 98.28 | -11.34 | 109.62
| 2025-09-04 | N/A | SAN CLEMENTE | N/A | Not Available | 42 | 30 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 0 | 180.5 | 5.69 | 174.81
| 2025-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 180 | 130 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 241.96 | 0 | 288.94 | 241.96 | 46.98
| 2025-04-11 | N/A | MISSION VIEJO | N/A | Not Available | 94 | 68 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | 72.04 | Unknown | 55.4 | 0 | 192.83 | 127.44 | 65.39
| 2026-02-27 | Underserved Community | OCEANSIDE | N/A | Not Available | 285 | 203 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.52 | 0 | 163.83 | 6.52 | 157.31
| 2026-02-01 | N/A | SAN DIEGO | N/A | Not Available | 84 | 60 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.07 | 0 | 192.95 | 2.07 | 190.88
| 2026-05-01 | Underserved Community | LAKESIDE | N/A | Not Available | 9 | 7 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.71 | 0 | 118.25 | 2.71 | 115.54
| 2024-08-14 | N/A | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | -7.27 | Unknown | -2.36 | 0 | 514.57 | -9.63 | 524.2
| 2025-08-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 613 | 439 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | 44.75 | Unknown | 55.18 | 0 | 483.59 | 99.93 | 383.66
| 2025-12-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 123 | 87 | N/A |  | Not Available | Not Available | Not Available | 312.76 | Unknown | 215.9 | 0 | 163.83 | 528.66 | -364.83
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.26 | 0 | 463.93 | 5.26 | 458.67
| 2026-07-25 | N/A | SAN DIEGO | N/A | Not Available | 68 | 50 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.64 | 0 | 192.95 | 7.64 | 185.31
| 2026-12-18 | N/A | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2025-01-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.99 | 0 | 197.01 | 4.99 | 192.02
| 2026-03-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 102 | 74 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -4.73 | Unknown | -1.1 | 0 | 162.34 | -5.83 | 168.17
| 2026-08-21 | Underserved Community | LAKESIDE | N/A | Not Available | 72 | 52 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 180.5 | 4.29 | 176.21
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 59 | 43 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -7.88 | Unknown | -1.79 | 0 | 153.26 | -9.67 | 162.93
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 148 | 106 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.29 | 0 | 555.11 | 11.29 | 543.82
| 2025-12-04 | Underserved Community | VISTA | N/A | Not Available | 106 | 76 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | -42.81 | Unknown | -23.28 | 0 | 383.4 | -66.09 | 449.49
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 125 | 89 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -10.25 | Unknown | -1.62 | 0 | 374 | -11.87 | 385.87
| 2025-05-18 | Underserved Community | ESCONDIDO | N/A | Not Available | 76 | 54 | N/A | 2023-07-10 | Not Available | Not Available | Not Available | -11.28 | Unknown | -4.32 | 0 | 465.44 | -15.6 | 481.04
| 2025-08-29 | Underserved Community | ESCONDIDO | N/A | Not Available | 83 | 59 | N/A | 2023-11-10 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.61 | 0 | 481.24 | -6.57 | 487.81
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -3.07 | Unknown | -0.71 | 0 | 207.92 | -3.78 | 211.7
| 2026-08-12 | Underserved Community | VISTA | N/A | Not Available | 139 | 99 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.75 | 0 | 197.01 | 1.75 | 195.26
| 2027-04-30 | Underserved Community | LA MESA | N/A | Not Available | 26 | 20 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 338 | 242 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | -3.82 | Unknown | 7.62 | 0 | 374 | 3.8 | 370.2
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -7.2 | Unknown | -1.66 | 0 | 207.92 | -8.86 | 216.78
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 193 | 139 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -9.27 | Unknown | -2.15 | 0 | 158.14 | -11.42 | 169.56
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 193 | 139 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -12.5 | Unknown | -2.88 | 0 | 158.14 | -15.38 | 173.52
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 211 | 151 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.79 | -4.18 | 162.97
| 2026-10-30 | N/A | SANTEE | N/A | Not Available | 44 | 32 | N/A | 2024-12-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.86 | 0 | 197.01 | 6.86 | 190.15
| 2026-07-23 | N/A | CARLSBAD | N/A | Not Available | 76 | 54 | N/A | 2024-10-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.51 | 0 | 1050.75 | 2.51 | 1048.24
| 2026-07-29 | Underserved Community | LAKESIDE | N/A | Not Available | 37 | 27 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.57 | 0 | 180.5 | 8.57 | 171.93
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 171 | 123 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.78 | 0 | 158.51 | -4.19 | 162.7
| 2026-04-16 | N/A | POWAY | N/A | Not Available | 44 | 32 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -7.1 | Unknown | -1.65 | 0 | 192.83 | -8.75 | 201.58
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 252 | 180 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -7.67 | Unknown | -1.78 | 0 | 158.51 | -9.45 | 167.96
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 178 | 128 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2026-07-19 | Underserved Community | OCEANSIDE | N/A | Not Available | 28 | 20 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.13 | 0 | 1050.75 | 7.13 | 1043.62
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 210 | 150 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -6.17 | Unknown | -1.43 | 0 | 158.79 | -7.6 | 166.39
| 2026-02-09 | N/A | ENCINITAS | N/A | Not Available | 451 | 323 | N/A | 2024-04-17 | Not Available | Not Available | Not Available | -7.56 | Unknown | 75.8 | 0 | 163.83 | 68.24 | 95.59
| 2027-04-18 | Underserved Community | CORONADO | N/A | Not Available | 56 | 40 | N/A |  | Not Available | Not Available | Not Available | 307.88 | Unknown | 219.37 | 0 | 118.25 | 527.25 | -409
| 2026-08-12 | Underserved Community | LAKESIDE | N/A | Not Available | 103 | 73 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.19 | 0 | 180.5 | 7.19 | 173.31
| 2026-11-01 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 97 | 69 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.68 | 0 | 1066.55 | 7.68 | 1058.87
| 2025-07-08 | N/A | CARLSBAD | N/A | Not Available | 7 | 5 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | 506.8 | Unknown | 347.84 | 0 | 192.51 | 854.64 | -662.13
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 748 | 534 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.03 | 0 | 154.99 | -0.03 | 155.02
| 2027-03-25 | Underserved Community | CHULA VISTA | N/A | Not Available | 55 | 39 | N/A | 2025-06-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 118.25 | 3.05 | 115.2
| 2026-12-02 | Underserved Community | BOULEVARD | N/A | Not Available | 62 | 44 | N/A |  | Not Available | Not Available | Not Available | 502.72 | Unknown | 340.26 | 0 | 196.69 | 842.98 | -646.29
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -11.76 | Unknown | -2.72 | 0 | 158.14 | -14.48 | 172.62
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 204 | 146 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.45 | 0 | 374.14 | 12.45 | 361.69
| 2026-01-19 | Underserved Community | LA MESA | N/A | Not Available | 92 | 66 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.86 | 0 | 534.53 | -4.6 | 539.13
| 2026-10-09 | Underserved Community | LA JOLLA | N/A | Not Available | 37 | 27 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.64 | 0 | 197.01 | 4.64 | 192.37
| 2026-09-17 | Underserved Community | LAKESIDE | N/A | Not Available | 58 | 42 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.43 | 0 | 197.01 | 9.43 | 187.58
| 2024-04-26 | Underserved Community | LEMON GROVE | N/A | Not Available | 139 | 99 | N/A | 2023-08-15 | Not Available | Not Available | Not Available | -10.41 | Unknown | -3.97 | 0 | 496.37 | -14.38 | 510.75
| 2024-05-09 | N/A | SANTEE | N/A | Not Available | 208 | 150 | N/A | 2023-11-10 | Not Available | Not Available | Not Available | -15.95 | Unknown | -5.53 | 0 | 496.37 | -21.48 | 517.85
| 2024-07-03 | Underserved Community | SPRING VALLEY | N/A | Not Available | 370 | 264 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -6 | Unknown | -0.97 | 0 | 482.43 | -6.97 | 489.4
| 2026-04-09 | Underserved Community | SPRING VALLEY | N/A | Not Available | 128 | 92 | N/A | 2024-07-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.24 | 0 | 192.83 | 7.24 | 185.59
| 2026-09-11 | Underserved Community | SAN MARCOS | N/A | Not Available | 66 | 48 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.4 | 0 | 197.01 | 5.4 | 191.61
| 2026-03-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 232 | 166 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.24 | 0 | 192.83 | 5.24 | 187.59
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 244 | 174 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.17 | 0 | 554.38 | 13.17 | 541.21
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 272 | 194 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 463.93 | 4.71 | 459.22
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 265 | 189 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.49 | 0 | 463.93 | 10.49 | 453.44
| 2026-03-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.35 | 0 | 186.4 | 9.35 | 177.05
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 54 | 38 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.25 | 0 | 197.01 | 2.25 | 194.76
| 2026-11-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 32 | 22 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 197.01 | 4.39 | 192.62
| 2026-11-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.22 | 0 | 197.01 | 4.22 | 192.79
| 2026-10-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 18 | 14 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.18 | 0 | 197.01 | 8.18 | 188.83
| 2026-05-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.51 | 0 | 192.95 | 2.51 | 190.44
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.64 | 0 | 463.93 | 9.64 | 454.29
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 61 | 45 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.47 | 0 | 197.01 | 7.47 | 189.54
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.08 | 0 | 197.01 | 7.08 | 189.93
| 2025-08-23 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 171 | 123 | N/A | 2024-02-16 | Not Available | Not Available | Not Available | -13.3 | Unknown | -3.24 | 0 | 514.57 | -16.54 | 531.11
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 280 | 200 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.4 | 0 | 555.28 | 5.4 | 549.88
| 2025-04-01 | N/A | SAN DIEGO | N/A | Not Available | 262 | 188 | N/A | 2023-08-30 | Not Available | Not Available | Not Available | -23.8 | Unknown | 740.7 | 0 | 496.45 | 716.9 | -220.45
| 2026-09-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.16 | 0 | 1066.51 | -0.16 | 1066.67
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.26 | 0 | 463.93 | 10.26 | 453.67
| 2026-12-17 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.05 | 0 | 105.72 | 6.05 | 99.67
| 2027-03-03 | N/A | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.5 | 0 | 196.44 | 6.5 | 189.94
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.15 | 0 | 197.01 | 3.15 | 193.86
| 2025-02-20 | N/A | SAN DIEGO | N/A | Not Available | 350 | 250 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.91 | 0 | 529.2 | 8.91 | 520.29
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.53 | 0 | 197.01 | 4.53 | 192.48
| 2026-10-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | -36.84 | Unknown | 1831.48 | 0 | 1066.51 | 1794.64 | -728.13
| 2026-03-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -6 | Unknown | -1.38 | 0 | 529.2 | -7.38 | 536.58
| 2025-12-15 | N/A | SAN DIEGO | N/A | Not Available | 130 | 94 | N/A | 2024-04-22 | Not Available | Not Available | Not Available | -7.03 | Unknown | 0.44 | 0 | 163.83 | -6.59 | 170.42
| 2026-11-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.56 | 0 | 197.01 | 5.56 | 191.45
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.52 | 0 | 197.01 | 3.52 | 193.49
| 2025-12-26 | N/A | SAN DIEGO | N/A | Not Available | 13 | 9 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -5.64 | Unknown | -1.52 | 0 | 515.81 | -7.16 | 522.97
| 2026-07-09 | N/A | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2024-08-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.86 | 0 | 192.95 | 8.86 | 184.09
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.38 | 0 | 554.38 | 7.38 | 547
| 2026-09-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 67 | 49 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | -1.88 | Unknown | 91.87 | 0 | 999.88 | 89.99 | 909.89
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.46 | 0 | 197.01 | 3.46 | 193.55
| 2025-09-27 | N/A | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -19.56 | Unknown | -6.33 | 0 | 513.31 | -25.89 | 539.2
| 2026-11-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 25 | 17 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 0 | 197.01 | 5.69 | 191.32
| 2024-08-28 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2022-12-11 | Not Available | Not Available | Not Available | -17.08 | Unknown | -5.52 | 0 | 158.79 | -22.6 | 181.39
| 2025-06-21 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2023-07-13 | Not Available | Not Available | Not Available | -7.75 | Unknown | -2.96 | 0 | 496.45 | -10.71 | 507.16
| 2026-10-29 | N/A | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.51 | 0 | 197.01 | 4.51 | 192.5
| 2026-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 132 | 94 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.63 | 0 | 192.95 | 12.63 | 180.32
| 2026-06-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.22 | 0 | 1050.75 | 2.22 | 1048.53
| 2026-02-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 93 | 67 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -34.65 | Unknown | 1432.44 | 0 | 534.57 | 1397.79 | -863.22
| 2025-07-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2023-11-03 | Not Available | Not Available | Not Available | -7.57 | Unknown | -2.44 | 0 | 481.24 | -10.01 | 491.25
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 219 | 157 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.13 | 0 | 554.38 | 5.13 | 549.25
| 2025-06-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2024-10-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.49 | 0 | 1016.73 | 4.49 | 1012.24
| 2026-10-08 | N/A | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.27 | 0 | 197.01 | 5.27 | 191.74
| 2026-12-10 | N/A | POWAY | N/A | Not Available | 93 | 67 | N/A | 2025-03-24 | Not Available | Not Available | Not Available | -22.44 | Unknown | -12.2 | 0 | 105.72 | -34.64 | 140.36
| 2026-03-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 115 | 83 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.12 | 0 | 983.86 | -0.12 | 983.98
| 2024-01-26 | N/A | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -5.81 | Unknown | -2.13 | 0 | 496.37 | -7.94 | 504.31
| 2025-11-16 | N/A | RANCHO SANTA FE | N/A | Not Available | 339 | 243 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 163.83 | 5.81 | 158.02
| 2026-10-04 | N/A | SAN DIEGO | N/A | Not Available | 25 | 18 | N/A | 2024-11-06 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.29 | 0 | 197.01 | -0.29 | 197.3
| 2026-05-03 | Underserved Community | VISTA | N/A | Not Available | 87 | 63 | N/A | 2024-07-22 | Not Available | Not Available | Not Available | -14.92 | Unknown | 755.33 | 0 | 192.83 | 740.41 | -547.58
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 447 | 319 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.2 | 0 | 153.83 | 3.2 | 150.63
| 2025-03-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 469 | 335 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -14.6 | Unknown | -1.17 | 0 | 153.83 | -15.77 | 169.6
| 2026-07-18 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 58 | 42 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.35 | 0 | 192.95 | 18.35 | 174.6
| 2025-11-30 | Underserved Community | CHULA VISTA | N/A | Not Available | 140 | 100 | N/A | 2024-03-27 | Not Available | Not Available | Not Available | -8.37 | Unknown | -1.93 | 0 | 534.53 | -10.3 | 544.83
| 2026-07-31 | N/A | DANA POINT | N/A | Not Available | 183 | 131 | N/A | 2024-10-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.51 | 0 | 192.95 | 1.51 | 191.44
| 2025-01-22 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 55 | 39 | N/A | 2024-03-05 | Not Available | Not Available | Not Available | -13.62 | Unknown | -3.17 | 0 | 153.26 | -16.79 | 170.05
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 615 | 439 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.66 | 0 | 153.83 | 4.66 | 149.17
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 310 | 222 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.74 | 0 | 158.14 | 10.74 | 147.4
| 2026-08-28 | Underserved Community | LAKESIDE | N/A | Not Available | 54 | 38 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.59 | 0 | 197.01 | 7.59 | 189.42
| 2025-01-29 | Underserved Community | DANA POINT | N/A | Not Available | 51 | 37 | N/A | 2024-03-22 | Not Available | Not Available | Not Available | -3.92 | Unknown | -0.92 | 0 | 534.53 | -4.84 | 539.37
| 2024-04-04 | N/A | SAN CLEMENTE | N/A | Not Available | 334 | 240 | N/A | 2024-02-07 | Not Available | Not Available | Not Available | -55.95 | Unknown | 592.54 | 0 | 153.26 | 536.59 | -383.33
| 2026-09-25 | Underserved Community | LAKESIDE | N/A | Not Available | 44 | 32 | N/A | 2024-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.07 | 0 | 197.01 | 5.07 | 191.94
| 2024-05-12 | N/A | SAN DIEGO | N/A | Not Available | 123 | 89 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | 2869.57 | Unknown | 3893.95 | 0 | 469.58 | 6763.52 | -6293.94
| 2026-05-15 | Underserved Community | SAN MARCOS | N/A | Not Available | 105 | 75 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.4 | 0 | 192.51 | 5.4 | 187.11
| 2026-10-17 | Underserved Community | SAN MARCOS | N/A | Not Available | 94 | 68 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.83 | 0 | 184.29 | 15.83 | 168.46
| 2027-02-17 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 30 | 22 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.95 | 0 | 196.69 | 10.95 | 185.74
| 2025-10-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 224 | 160 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | -5.32 | Unknown | -1.26 | 0 | 158.79 | -6.58 | 165.37
| 2026-07-09 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 56 | 40 | N/A | 2024-08-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 192.95 | 4.01 | 188.94
| 2027-01-24 | Underserved Community | POWAY | N/A | Not Available | 56 | 40 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | -16.18 | Unknown | -8.8 | 0 | 196.69 | -24.98 | 221.67
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 447 | 319 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.83 | 0 | 153.83 | 7.83 | 146
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 524 | 374 | N/A | 2024-09-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.02 | 0 | 154.99 | 3.02 | 151.97
| 2026-12-17 | N/A | ENCINITAS | N/A | Not Available | 72 | 52 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | -2.19 | Unknown | 108.23 | 0 | 196.59 | 106.04 | 90.55
| 2024-05-30 | N/A | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -8.09 | Unknown | -2.94 | 0 | 469.58 | -11.03 | 480.61
| 2024-09-26 | Underserved Community | NATIONAL CITY | N/A | Not Available | 163 | 117 | N/A | 2024-01-19 | Not Available | Not Available | Not Available | -7.19 | Unknown | -1.67 | 0 | 515.81 | -8.86 | 524.67
| 2024-11-16 | Underserved Community | CAPISTRANO BEACH | N/A | Not Available | 106 | 76 | N/A | 2024-01-11 | Not Available | Not Available | Not Available | -4.1 | Unknown | -0.95 | 0 | 515.81 | -5.05 | 520.86
| 2025-07-01 | N/A | LAGUNA NIGUEL | N/A | Not Available | 59 | 43 | N/A | 2024-08-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.03 | 0 | 192.95 | 7.03 | 185.92
| 2025-08-14 | Underserved Community | LA MESA | N/A | Not Available | 7 | 5 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.4 | 0 | 1050.75 | 10.4 | 1040.35
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 579 | 413 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.71 | 0 | 154.99 | 5.71 | 149.28
| 2025-07-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 242 | 172 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | 1329.8 | Unknown | 681.75 | 0 | 481.24 | 2011.55 | -1530.31
| 2026-06-12 | N/A | SAN MARCOS | N/A | Not Available | 135 | 97 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.99 | 0 | 192.51 | 4.99 | 187.52
| 2026-04-25 | Underserved Community | LA JOLLA | N/A | Not Available | 71 | 51 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.17 | 0 | 1049.43 | 6.17 | 1043.26
| 2025-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 171 | 123 | N/A | 2025-04-01 | Not Available | Not Available | Not Available | -81.86 | Unknown | 2277.58 | 0 | 288.94 | 2195.72 | -1906.78
| 2025-06-11 | Underserved Community | BONSALL | N/A | Not Available | 72 | 52 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -7.02 | Unknown | -2.66 | 0 | 513.5 | -9.68 | 523.18
| 2025-03-17 | N/A | SOUTH LAGUNA | N/A | Not Available | 114 | 82 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | 99.3 | Unknown | 72.71 | 0 | 192.83 | 172.01 | 20.82
| 2027-03-05 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 54 | 38 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.53 | 0 | 1063.64 | 2.53 | 1061.11
| 2024-07-17 | Underserved Community | LA MESA | N/A | Not Available | 137 | 99 | N/A | 2023-10-26 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.33 | 0 | 1144.12 | -5.42 | 1149.54
| 2026-10-31 | Underserved Community | FALLBROOK | N/A | Not Available | 66 | 48 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.28 | 0 | 999.91 | 5.28 | 994.63
| 2024-06-08 | N/A | SANTEE | N/A | Not Available | 179 | 127 | N/A | 2023-11-03 | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.57 | 0 | 153.83 | -6.36 | 160.19
| 2026-07-29 | Underserved Community | OCEANSIDE | N/A | Not Available | 64 | 46 | N/A | 2024-10-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.55 | 0 | 192.95 | 4.55 | 188.4
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 701 | 501 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.25 | 0 | 154.99 | 5.25 | 149.74
| 2024-04-21 | N/A | MISSION VIEJO | N/A | Not Available | 306 | 218 | N/A | 2023-08-03 | Not Available | Not Available | Not Available | -4.45 | Unknown | -1.69 | 0 | 153.83 | -6.14 | 159.97
| 2025-09-29 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 404 | 288 | N/A |  | Not Available | Not Available | Not Available | 611 | Unknown | 267.66 | 0 | 515.81 | 878.66 | -362.85
| 2024-07-27 | Underserved Community | LA MESA | N/A | Not Available | 352 | 252 | N/A | 2024-07-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.98 | 0 | 500.87 | 6.98 | 493.89
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 324 | 232 | N/A | 2025-04-09 | Not Available | Not Available | Not Available | -8.57 | Unknown | -4.66 | 0 | 554.38 | -13.23 | 567.61
| 2025-06-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 298 | 212 | N/A | 2024-03-29 | Not Available | Not Available | Not Available | -8.47 | Unknown | -1.98 | 0 | 500.87 | -10.45 | 511.32
| 2024-08-21 | N/A | DANA POINT | N/A | Not Available | 172 | 124 | N/A | 2023-12-06 | Not Available | Not Available | Not Available | -6.31 | Unknown | -1.69 | 0 | 154.99 | -8 | 162.99
| 2027-01-08 | Underserved Community | POWAY | N/A | Not Available | 61 | 43 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.39 | 0 | 196.69 | 18.39 | 178.3
| 2027-03-11 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | 266.88 | Unknown | 181.45 | 0 | 196.59 | 448.33 | -251.74
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 326 | 232 | N/A | 2024-03-06 | Not Available | Not Available | Not Available | -10.01 | Unknown | -2.33 | 0 | 153.83 | -12.34 | 166.17
| 2025-10-31 | Underserved Community | SAN MARCOS | N/A | Not Available | 139 | 99 | N/A | 2024-03-11 | Not Available | Not Available | Not Available | -4.12 | Unknown | -0.96 | 0 | 213.91 | -5.08 | 218.99
| 2026-06-12 | Underserved Community | SAN MARCOS | N/A | Not Available | 126 | 90 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.82 | 0 | 192.51 | 5.82 | 186.69
| 2027-02-12 | N/A | COTO DE CAZA | N/A | Not Available | 63 | 45 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | -15.16 | Unknown | -8.25 | 0 | 196.69 | -23.41 | 220.1
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.42 | 0 | 1049.43 | 8.42 | 1041.01
| 2023-03-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 293 | 209 | N/A | 2023-12-20 | Not Available | Not Available | Not Available | -10.92 | Unknown | -2.93 | 0 | 1547.64 | -13.85 | 1561.49
| 2025-05-22 | N/A | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2023-08-24 | Not Available | Not Available | Not Available | -3.93 | Unknown | -1.49 | 0 | 153.83 | -5.42 | 159.25
| 2025-04-13 | N/A | SAN DIEGO | N/A | Not Available | 149 | 107 | N/A | 2023-08-18 | Not Available | Not Available | Not Available | -8.76 | Unknown | -3.31 | 0 | 153.83 | -12.07 | 165.9
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2024-11-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 197.01 | 5.81 | 191.2
| 2027-02-28 | N/A | SAN DIEGO | N/A | Not Available | 11 | 7 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.46 | 0 | 1063.08 | 6.46 | 1056.62
| 2025-09-11 | N/A | SAN DIEGO | N/A | Not Available | 154 | 110 | N/A | 2023-12-11 | Not Available | Not Available | Not Available | -9.52 | Unknown | -3.09 | 0 | 158.79 | -12.61 | 171.4
| 2027-01-29 | N/A | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.26 | 0 | 1101.15 | 7.26 | 1093.89
| 2026-04-23 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2024-07-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.08 | 0 | 192.51 | 6.08 | 186.43
| 2026-06-05 | N/A | SAN DIEGO | N/A | Not Available | 227 | 163 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1046.41 | 0 | 192.95 | 1046.41 | -853.46
| 2024-07-31 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1260.27 | 0 | 1260.27
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.58 | 0 | 197.01 | 2.58 | 194.43
| 2026-07-03 | N/A | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2024-09-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.59 | 0 | 192.95 | 3.59 | 189.36
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 253 | 181 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.76 | 0 | 554.38 | 13.76 | 540.62
| 2025-09-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 132 | 94 | N/A | 2024-01-12 | Not Available | Not Available | Not Available | 663.87 | Unknown | 410.29 | 0 | 515.81 | 1074.16 | -558.35
| 2026-11-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.52 | 0 | 197.01 | 3.52 | 193.49
| 2025-08-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 102 | N/A | 2023-12-26 | Not Available | Not Available | Not Available | -7.23 | Unknown | -1.68 | 0 | 515.81 | -8.91 | 524.72
| 2025-09-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 499 | 357 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.14 | 0 | 158.79 | 5.14 | 153.65
| 2025-08-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 219 | 157 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.11 | 0 | 197.01 | 8.11 | 188.9
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.74 | 0 | 197.01 | 5.74 | 191.27
| 2025-10-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 308 | 220 | N/A |  | Not Available | Not Available | Not Available | 190.31 | Unknown | 133.93 | 0 | 158.37 | 324.24 | -165.87
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 265 | 189 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 463.93 | 4.71 | 459.22
| 2025-08-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 262 | 188 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -8.68 | Unknown | -2.01 | 0 | 515.81 | -10.69 | 526.5
| 2025-05-17 | N/A | SAN DIEGO | N/A | Not Available | 272 | 194 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | -8.02 | Unknown | -2.6 | 0 | 496.37 | -10.62 | 506.99
| 2024-08-20 | N/A | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2023-11-08 | Not Available | Not Available | Not Available | 237.27 | Unknown | 177.41 | 0 | 158.51 | 414.68 | -256.17
| 2026-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 196.69 | 5.81 | 190.88
| 2026-03-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -9.08 | Unknown | -2.09 | 0 | 163.83 | -11.17 | 175
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 300 | 214 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | -15.64 | Unknown | -8.5 | 0 | 463.93 | -24.14 | 488.07
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.05 | 0 | 197.01 | 6.05 | 190.96
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 260 | 186 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.14 | 0 | 463.93 | 6.14 | 457.79
| 2026-06-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 102 | 72 | N/A | 2024-09-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.85 | 0 | 186.52 | 8.85 | 177.67
| 2025-09-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 52 | 38 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.58 | 0 | 180.5 | 9.58 | 170.92
| 2026-05-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 198 | 142 | N/A | 2024-11-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.52 | 0 | 1050.75 | 3.52 | 1047.23
| 2025-07-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 160 | 114 | N/A | 2023-11-07 | Not Available | Not Available | Not Available | 183.68 | Unknown | 131.68 | 0 | 152.86 | 315.36 | -162.5
| 2026-05-16 | N/A | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -7.85 | Unknown | -1.81 | 0 | 1050.61 | -9.66 | 1060.27
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.53 | 0 | 197.01 | 5.53 | 191.48
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 265 | 189 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.06 | 0 | 463.93 | 7.06 | 456.87
| 2026-11-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 68 | 50 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.15 | 0 | 197.01 | 7.15 | 189.86
| 2026-01-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 196 | 140 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.51 | 0 | 158.37 | 9.51 | 148.86
| 2025-06-15 | N/A | SAN DIEGO | N/A | Not Available | 123 | 89 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -7.05 | Unknown | -1.65 | 0 | 163.83 | -8.7 | 172.53
| 2026-11-04 | N/A | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.53 | 0 | 1032.15 | 4.53 | 1027.62
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 192 | 138 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.37 | 0 | 554.38 | 7.37 | 547.01
| 2026-07-30 | N/A | SAN DIEGO | N/A | Not Available | 94 | 68 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | 271.15 | Unknown | 190.96 | 0 | 197.01 | 462.11 | -265.1
| 2025-02-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-04-25 | Not Available | Not Available | Not Available | -14.05 | Unknown | -1.84 | 0 | 163.83 | -15.89 | 179.72
| 2026-06-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A |  | Not Available | Not Available | Not Available | 182.98 | Unknown | 496.67 | 0 | 186.52 | 679.65 | -493.13
| 2025-06-22 | N/A | SAN DIEGO | N/A | Not Available | 535 | 383 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.68 | 0 | 143.31 | 7.68 | 135.63
| 2025-04-10 | N/A | SAN DIEGO | N/A | Not Available | 176 | 126 | N/A | 2023-09-05 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.74 | 0 | 496.37 | -6.35 | 502.72
| 2025-10-09 | N/A | SAN DIEGO | N/A | Not Available | 132 | 94 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -6.34 | Unknown | -0.24 | 0 | 158.79 | -6.58 | 165.37
| 2026-08-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.2 | 0 | 999.88 | 9.2 | 990.68
| 2025-10-26 | N/A | SAN DIEGO | N/A | Not Available | 189 | 135 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -5.5 | Unknown | -1.29 | 0 | 534.53 | -6.79 | 541.32
| 2026-11-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 32 | 22 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.97 | 0 | 197.01 | 2.97 | 194.04
| 2026-12-13 | Underserved Community | OCEANSIDE | N/A | Not Available | 45 | 33 | N/A | 2025-02-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.53 | 0 | 197.01 | 6.53 | 190.48
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 296 | 212 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | -17.47 | Unknown | -9.49 | 0 | 463.93 | -26.96 | 490.89
| 2026-12-05 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 106 | 76 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.72 | 0 | 197.01 | 9.72 | 187.29
| 2024-06-30 | N/A | MISSION VIEJO | N/A | Not Available | 31 | 23 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.05 | 0 | 192.51 | 9.05 | 183.46
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 322 | 230 | N/A | 2024-03-06 | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.09 | 0 | 153.83 | -5.88 | 159.71
| 2026-11-05 | N/A | SAN CLEMENTE | N/A | Not Available | 64 | 46 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.34 | 0 | 197.01 | 9.34 | 187.67
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 397 | 283 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -5.65 | Unknown | -1.34 | 0 | 154.99 | -6.99 | 161.98
| 2025-06-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 190 | 136 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.57 | 0 | 153.83 | -9.97 | 163.8
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 432 | 308 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -4.12 | Unknown | -0.73 | 0 | 153.83 | -4.85 | 158.68
| 2025-10-11 | Underserved Community | SAN MARCOS | N/A | Not Available | 177 | 127 | N/A | 2024-03-29 | Not Available | Not Available | Not Available | -9.34 | Unknown | 361.12 | 0 | 591.53 | 351.78 | 239.75
| 2026-10-24 | Underserved Community | ESCONDIDO | N/A | Not Available | 31 | 23 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 184.29 | 3.85 | 180.44
| 2025-10-21 | N/A | ALISO VIEJO | N/A | Not Available | 37 | 27 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.26 | 0 | 184.29 | -0.26 | 184.55
| 2024-08-02 | N/A | LAGUNA HILLS | N/A | Not Available | 177 | 127 | N/A | 2023-09-28 | Not Available | Not Available | Not Available | -6.17 | Unknown | -2.01 | 0 | 154.99 | -8.18 | 163.17
| 2025-07-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 114 | 82 | N/A | 2023-09-14 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.61 | 0 | 496.37 | -6.57 | 502.94
| 2024-05-18 | N/A | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2023-08-11 | Not Available | Not Available | Not Available | -7.54 | Unknown | -2.87 | 0 | 496.37 | -10.41 | 506.78
| 2026-06-08 | N/A | LA JOLLA | N/A | Not Available | 65 | 47 | N/A | 2024-08-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 2361.29 | 3.05 | 2358.24
| 2024-08-22 | N/A | MISSION VIEJO | N/A | Not Available | 187 | 135 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | 783.32 | Unknown | 1017.61 | 0 | 163.83 | 1800.93 | -1637.1
| 2025-09-12 | Underserved Community | EL CAJON | N/A | Not Available | 12 | 8 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.96 | 0 | 192.95 | 14.96 | 177.99
| 2024-06-23 | N/A | SAN DIEGO | N/A | Not Available | 111 | 79 | N/A | 2023-09-05 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.54 | 0 | 496.37 | -5.63 | 502
| 2026-07-30 | N/A | SAN CLEMENTE | N/A | Not Available | 51 | 37 | N/A | 2024-09-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.71 | 0 | 192.95 | 7.71 | 185.24
| 2025-02-03 | Underserved Community | VISTA | N/A | Not Available | 194 | 140 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -3.79 | Unknown | 29.99 | 0 | 98.41 | 26.2 | 72.21
| 2026-07-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 51 | 37 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 999.88 | 3.85 | 996.03
| 2027-03-17 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 32 | 22 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.02 | 0 | 196.44 | 6.02 | 190.42
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 683 | 487 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.78 | 0 | 153.83 | 5.78 | 148.05
| 2025-06-23 | Underserved Community | ESCONDIDO | N/A | Not Available | 135 | 97 | N/A | 2023-11-07 | Not Available | Not Available | Not Available | -10.29 | Unknown | 5.68 | 0 | 591.49 | -4.61 | 596.1
| 2025-01-22 | N/A | SAN CLEMENTE | N/A | Not Available | 268 | 192 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.49 | 0 | 192.83 | 15.49 | 177.34
| 2024-05-05 | N/A | DANA POINT | N/A | Not Available | 254 | 182 | N/A | 2023-11-08 | Not Available | Not Available | Not Available | -12.19 | Unknown | -3.91 | 0 | 147.93 | -16.1 | 164.03
| 2026-06-13 | N/A | DANA POINT | N/A | Not Available | 76 | 54 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.58 | 0 | 192.95 | 5.58 | 187.37
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 488 | 348 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.42 | 0 | 153.83 | 9.42 | 144.41
| 2025-01-29 | N/A | DANA POINT | N/A | Not Available | 57 | 41 | N/A | 2024-03-01 | Not Available | Not Available | Not Available | -5.14 | Unknown | -1.19 | 0 | 153.26 | -6.33 | 159.59
| 2025-10-23 | Underserved Community | BONITA | N/A | Not Available | 532 | 380 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.76 | 0 | 534.53 | 7.76 | 526.77
| 2025-04-08 | N/A | LAGUNA HILLS | N/A | Not Available | 95 | 69 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | 72.04 | Unknown | 55.62 | 0 | 192.83 | 127.66 | 65.17
| 2025-12-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 153 | 109 | N/A | 2024-04-18 | Not Available | Not Available | Not Available | -6.35 | Unknown | 0.84 | 0 | 163.83 | -5.51 | 169.34
| 2026-03-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 119 | 85 | N/A | 2024-07-09 | Not Available | Not Available | Not Available | -13.8 | Unknown | -2.21 | 0 | 547.46 | -16.01 | 563.47
| 2026-11-14 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 105 | 75 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | 1287.73 | Unknown | 1633.23 | 0 | 184.29 | 2920.96 | -2736.67
| 2026-10-09 | N/A | POWAY | N/A | Not Available | 114 | 82 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.61 | 0 | 184.29 | 8.61 | 175.68
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 571 | 407 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.44 | 0 | 154.99 | 7.44 | 147.55
| 2026-09-09 | N/A | SAN CLEMENTE | N/A | Not Available | 51 | 37 | N/A | 2024-10-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.13 | 0 | 184.29 | 7.13 | 177.16
| 2025-05-28 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 176 | 126 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.87 | 0 | 1049.43 | 5.87 | 1043.56
| 2026-06-10 | N/A | DANA POINT | N/A | Not Available | 70 | 50 | N/A | 2024-07-31 | Not Available | Not Available | Not Available | 144.08 | Unknown | 105.9 | 0 | 192.51 | 249.98 | -57.47
| 2026-01-23 | N/A | SANTEE | N/A | Not Available | 108 | 78 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.34 | 0 | 1190.78 | -7.16 | 1197.94
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 578 | 412 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.28 | 0 | 153.83 | 5.28 | 148.55
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 664 | 474 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.18 | 0 | 153.83 | 5.18 | 148.65
| 2025-11-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 165 | 117 | N/A | 2024-05-03 | Not Available | Not Available | Not Available | -2.47 | Unknown | -0.59 | 0 | 534.57 | -3.06 | 537.63
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 438 | 312 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -5.1 | Unknown | -0.81 | 0 | 153.83 | -5.91 | 159.74
| 2025-05-06 | N/A | SAN CLEMENTE | N/A | Not Available | 66 | 48 | N/A | 2024-07-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.04 | 0 | 1049.43 | 5.04 | 1044.39
| 2024-08-28 | Underserved Community | LA MESA | N/A | Not Available | 170 | 122 | N/A | 2023-11-02 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.6 | 0 | 618.47 | -4.34 | 622.81
| 2026-08-23 | N/A | COTO DE CAZA | N/A | Not Available | 89 | 63 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.17 | 0 | 192.95 | 9.17 | 183.78
| 2025-03-18 | N/A | LAGUNA NIGUEL | N/A | Not Available | 85 | 61 | N/A | 2024-05-20 | Not Available | Not Available | Not Available | -6.02 | Unknown | -1.4 | 0 | 151.87 | -7.42 | 159.29
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 321 | 229 | N/A | 2024-03-06 | Not Available | Not Available | Not Available | -6.68 | Unknown | -1.5 | 0 | 153.83 | -8.18 | 162.01
| 2024-07-31 | N/A | DANA POINT | N/A | Not Available | 123 | 89 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.7 | 0 | 192.95 | 10.7 | 182.25
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 461 | 329 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.08 | 0 | 153.83 | 5.08 | 148.75
| 2027-04-28 | N/A | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-10-30 | Underserved Community | CHULA VISTA | N/A | Not Available | 66 | 48 | N/A | 2024-11-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.72 | 0 | 197.01 | 8.72 | 188.29
| 2025-10-11 | N/A | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -4.1 | Unknown | -0.95 | 0 | 158.79 | -5.05 | 163.84
| 2025-11-29 | Underserved Community | EL CAJON | N/A | Not Available | 130 | 94 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.24 | 0 | 1050.75 | -0.24 | 1050.99
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 268 | 192 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.91 | 0 | 463.93 | 6.91 | 457.02
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 268 | 192 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 463.93 | 8.02 | 455.91
| 2027-02-03 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.73 | 0 | 196.69 | 5.73 | 190.96
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 662 | 472 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.27 | 0 | 192.83 | 9.27 | 183.56
| 2027-02-24 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.13 | 0 | 196.44 | 16.13 | 180.31
| 2025-01-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 253 | 181 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | -6.33 | Unknown | -2.03 | 0 | 496.37 | -8.36 | 504.73
| 2024-05-12 | N/A | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | -6.58 | Unknown | -2.5 | 0 | 1117.07 | -9.08 | 1126.15
| 2026-05-06 | Underserved Community | LA JOLLA | N/A | Not Available | 133 | 95 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.62 | 0 | 322.96 | 7.62 | 315.34
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 171 | 123 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -16.7 | Unknown | -3.89 | 0 | 158.51 | -20.59 | 179.1
| 2024-04-20 | Underserved Community | LA MESA | N/A | Not Available | 253 | 181 | N/A | 2023-11-21 | Not Available | Not Available | Not Available | 5.5 | Unknown | 18.15 | 0 | 496.45 | 23.65 | 472.8
| 2026-09-12 | N/A | ENCINITAS | N/A | Not Available | 131 | 93 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.64 | 0 | 197.01 | 11.64 | 185.37
| 2025-03-24 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 204 | 146 | N/A | 2023-09-08 | Not Available | Not Available | Not Available | -7.09 | Unknown | -2.58 | 0 | 496.45 | -9.67 | 506.12
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 112 | 80 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -10.35 | Unknown | -1.65 | 0 | 374 | -12 | 386
| 2025-11-08 | N/A | CHULA VISTA | N/A | Not Available | 237 | 169 | N/A |  | Not Available | Not Available | Not Available | 573.84 | Unknown | 336.77 | 0 | 163.83 | 910.61 | -746.78
| 2026-09-24 | Underserved Community | SAN MARCOS | N/A | Not Available | 38 | 28 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 197.01 | 3.05 | 193.96
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 252 | 180 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -10.07 | Unknown | -2.33 | 0 | 158.14 | -12.4 | 170.54
| 2026-06-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 43 | 31 | N/A | 2024-08-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.4 | 0 | 1050.75 | 5.4 | 1045.35
| 2026-09-18 | Underserved Community | SAN MARCOS | N/A | Not Available | 66 | 48 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.21 | 0 | 197.01 | 5.21 | 191.8
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 78 | 56 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -11.02 | Unknown | -2.58 | 0 | 163.83 | -13.6 | 177.43
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 178 | 128 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -7.38 | Unknown | -1.71 | 0 | 158.14 | -9.09 | 167.23
| 2024-06-28 | N/A | EL CAJON | N/A | Not Available | 191 | 137 | N/A | 2023-10-20 | Not Available | Not Available | Not Available | -7.92 | Unknown | -2.69 | 0 | 496.37 | -10.61 | 506.98
| 2026-05-21 | N/A | CARLSBAD | N/A | Not Available | 51 | 37 | N/A | 2024-07-03 | Not Available | Not Available | Not Available | -9.14 | Unknown | 1.19 | 0 | 192.83 | -7.95 | 200.78
| 2026-08-26 | Underserved Community | CORONADO | N/A | Not Available | 146 | 104 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.9 | 0 | 190.04 | 9.9 | 180.14
| 2025-10-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 38 | 28 | N/A | 2024-11-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.31 | 0 | 197.01 | 13.31 | 183.7
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 177 | 127 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 211 | 151 | N/A | 2024-03-05 | Not Available | Not Available | Not Available | -12.62 | Unknown | -2.92 | 0 | 158.79 | -15.54 | 174.33
| 2026-03-08 | Underserved Community | VISTA | N/A | Not Available | 133 | 95 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.16 | 0 | 529.2 | 3.16 | 526.04
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 177 | 127 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 211 | 151 | N/A | 2024-03-05 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.79 | -4.18 | 162.97
| 2025-09-23 | Underserved Community | OCEANSIDE | N/A | Not Available | 323 | 231 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.7 | 0 | 493.45 | 4.7 | 488.75
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 171 | 123 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -10.64 | Unknown | -2.51 | 0 | 158.51 | -13.15 | 171.66
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 175 | 125 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | -12.51 | Unknown | -2.92 | 0 | 158.14 | -15.43 | 173.57
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 252 | 180 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -13.55 | Unknown | -3.14 | 0 | 158.51 | -16.69 | 175.2
| 2025-10-22 | N/A | VISTA | N/A | Not Available | 182 | 130 | N/A | 2024-03-27 | Not Available | Not Available | Not Available | -4.62 | Unknown | -1.08 | 0 | 158.79 | -5.7 | 164.49
| 2025-09-27 | N/A | CARLSBAD | N/A | Not Available | 134 | 96 | N/A | 2024-01-25 | Not Available | Not Available | Not Available | -8.99 | Unknown | -2.08 | 0 | 158.79 | -11.07 | 169.86
| 2027-03-23 | N/A | POWAY | N/A | Not Available | 65 | 47 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.92 | 0 | 118.25 | 2.92 | 115.33
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 69 | 49 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.78 | 0 | 192.83 | 2.78 | 190.05
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -7.72 | Unknown | -1.8 | 0 | 158.14 | -9.52 | 167.66
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 269 | 193 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -5.31 | Unknown | -1.23 | 0 | 158.79 | -6.54 | 165.33
| 2025-03-24 | Underserved Community | CHULA VISTA | N/A | Not Available | 162 | 116 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | 241.68 | Unknown | 154.96 | 0 | 111.56 | 396.64 | -285.08
| 2026-04-05 | Underserved Community | CHULA VISTA | N/A | Not Available | 113 | 81 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.74 | 0 | 186.09 | 12.74 | 173.35
| 2026-04-01 | N/A | LA JOLLA | N/A | Not Available | 175 | 125 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.21 | 0 | 192.83 | 5.21 | 187.62
| 2024-12-26 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 238 | 170 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | -32.38 | Unknown | 1359.45 | 0 | 496.45 | 1327.07 | -830.62
| 2025-04-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 81 | 59 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -5 | Unknown | -1.81 | 0 | 465.36 | -6.81 | 472.17
| 2026-08-05 | Underserved Community | SPRING VALLEY | N/A | Not Available | 84 | 60 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 197.01 | 4.29 | 192.72
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 354 | 254 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.97 | 0 | 158.14 | 5.97 | 152.17
| 2024-04-25 | N/A | ENCINITAS | N/A | Not Available | 785 | 561 | N/A | 2025-06-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 95.79 | 0 | 153.83 | 95.79 | 58.04
| 2026-03-15 | Underserved Community | VISTA | N/A | Not Available | 97 | 69 | N/A | 2024-06-05 | Not Available | Not Available | Not Available | -18.71 | Unknown | -1.02 | 0 | 162.34 | -19.73 | 182.07
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 127 | 91 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2025-10-03 | Underserved Community | ESCONDIDO | N/A | Not Available | 307 | 219 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.2 | 0 | 1050.61 | 7.2 | 1043.41
| 2025-07-11 | Underserved Community | LAKESIDE | N/A | Not Available | 95 | 69 | N/A | 2024-09-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.69 | 0 | 180.5 | 12.69 | 167.81
| 2027-03-19 | N/A | CHULA VISTA | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | 1132.9 | Unknown | 477.57 | 0 | 190.04 | 1610.47 | -1420.43
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 127 | 91 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2026-09-20 | Underserved Community | CHULA VISTA | N/A | Not Available | 50 | 36 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | -2.2 | Unknown | 115.11 | 0 | 190.44 | 112.91 | 77.53
| 2026-09-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 50 | 36 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 197.01 | 3.85 | 193.16
| 2026-02-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 187 | 133 | N/A | 2024-08-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.55 | 0 | 163.83 | 4.55 | 159.28
| 2025-07-22 | Underserved Community | LAKESIDE | N/A | Not Available | 108 | 78 | N/A | 2024-10-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 180.5 | 3.17 | 177.33
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 110 | 78 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -10.11 | Unknown | -2.33 | 0 | 374 | -12.44 | 386.44
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 118 | 84 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -15.59 | Unknown | -3.63 | 0 | 374 | -19.22 | 393.22
| 2026-08-22 | Underserved Community | SAN MARCOS | N/A | Not Available | 30 | 22 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.8 | 0 | 192.95 | 6.8 | 186.15
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 196 | 140 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -7.9 | Unknown | -1.81 | 0 | 158.51 | -9.71 | 168.22
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-23 | Not Available | Not Available | Not Available | -12.31 | Unknown | 133.55 | 0 | 207.92 | 121.24 | 86.68
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 395 | 283 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 158.14 | 4.29 | 153.85
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 175 | 125 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.08 | 0 | 158.51 | -5.69 | 164.2
| 2024-08-22 | Underserved Community | SANTEE | N/A | Not Available | 174 | 124 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | -6.16 | Unknown | -1.42 | 0 | 481.24 | -7.58 | 488.82
| 2025-09-15 | Underserved Community | LEMON GROVE | N/A | Not Available | 169 | 121 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -17.3 | Unknown | -4.15 | 0 | 515.81 | -21.45 | 537.26
| 2024-09-21 | Underserved Community | EL CAJON | N/A | Not Available | 113 | 81 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | -30.31 | Unknown | 1190.44 | 0 | 515.81 | 1160.13 | -644.32
| 2026-07-02 | Underserved Community | LAKESIDE | N/A | Not Available | 69 | 49 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.5 | 0 | 192.95 | 6.5 | 186.45
| 2026-03-27 | Underserved Community | FALLBROOK | N/A | Not Available | 112 | 80 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | -13.94 | Unknown | -2.22 | 0 | 1260.77 | -16.16 | 1276.93
| 2026-07-23 | N/A | VALLEY CENTER | N/A | Not Available | 70 | 50 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.43 | 0 | 1260.93 | 9.43 | 1251.5
| 2026-09-25 | Underserved Community | SAN MARCOS | N/A | Not Available | 60 | 42 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.55 | 0 | 197.01 | 4.55 | 192.46
| 2024-10-27 | Underserved Community | SPRING VALLEY | N/A | Not Available | 130 | 94 | N/A | 2024-02-20 | Not Available | Not Available | Not Available | -8.02 | Unknown | -1.86 | 0 | 515.81 | -9.88 | 525.69
| 2023-07-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 52 | 38 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.12 | 0 | 1523.44 | -1.12 | 1524.56
| 2025-12-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 131 | 93 | N/A | 2024-04-26 | Not Available | Not Available | Not Available | -4.98 | Unknown | -1.18 | 0 | 163.83 | -6.16 | 169.99
| 2025-04-24 | Underserved Community | SAN MARCOS | N/A | Not Available | 93 | 67 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.72 | 0 | 242.51 | 9.72 | 232.79
| 2026-07-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 102 | 72 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.34 | 0 | 631.94 | 2.34 | 629.6
| 2024-04-04 | N/A | SANTEE | N/A | Not Available | 206 | 148 | N/A | 2023-11-28 | Not Available | Not Available | Not Available | -6.17 | Unknown | -0.75 | 0 | 153.83 | -6.92 | 160.75
| 2026-01-03 | Underserved Community | VALLEY CENTER | N/A | Not Available | 115 | 83 | N/A | 2024-04-26 | Not Available | Not Available | Not Available | -14.5 | Unknown | -3.34 | 0 | 163.83 | -17.84 | 181.67
| 2027-01-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A |  | Not Available | Not Available | Not Available | 124.43 | Unknown | 487.11 | 0 | 1064.43 | 611.54 | 452.89
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.34 | 0 | 196.69 | 4.34 | 192.35
| 2026-07-19 | N/A | SAN DIEGO | N/A | Not Available | 326 | 234 | N/A | 2025-06-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.44 | 0 | 192.95 | 3.44 | 189.51
| 2026-01-04 | N/A | SAN DIEGO | N/A | Not Available | 231 | 165 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.88 | 0 | 163.83 | 7.88 | 155.95
| 2026-02-25 | N/A | SAN DIEGO | N/A | Not Available | 129 | 93 | N/A | 2024-07-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.41 | 0 | 162.34 | 11.41 | 150.93
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 197.01 | 5.81 | 191.2
| 2025-07-18 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 301 | 215 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -7.73 | Unknown | -1.5 | 0 | 515.81 | -9.23 | 525.04
| 2024-03-14 | N/A | SAN DIEGO | N/A | Not Available | 214 | 152 | N/A | 2023-10-18 | Not Available | Not Available | Not Available | -21.76 | Unknown | -6.73 | 0 | 153.87 | -28.49 | 182.36
| 2026-02-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 17 | 13 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 75.56 | 0 | 1063.08 | 75.56 | 987.52
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.27 | 0 | 197.01 | 10.27 | 186.74
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.65 | 0 | 197.01 | 6.65 | 190.36
| 2026-05-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | -0.94 | Unknown | 54.48 | 0 | 1050.75 | 53.54 | 997.21
| 2026-11-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.13 | 0 | 197.01 | 12.13 | 184.88
| 2025-06-22 | N/A | SAN DIEGO | N/A | Not Available | 207 | 149 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -15.97 | Unknown | -6.04 | 0 | 496.45 | -22.01 | 518.46
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 197.01 | 5.81 | 191.2
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.97 | 0 | 197.01 | 2.97 | 194.04
| 2026-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 248 | 178 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | -1.25 | Unknown | 80.56 | 0 | 1050.75 | 79.31 | 971.44
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.82 | 0 | 197.01 | 4.82 | 192.19
| 2026-11-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.94 | 0 | 197.01 | 3.94 | 193.07
| 2026-06-15 | N/A | SAN DIEGO | N/A | Not Available | 129 | 93 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.48 | 0 | 192.95 | 16.48 | 176.47
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | 108.58 | Unknown | 51.97 | 0 | 197.01 | 160.55 | 36.46
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 272 | 194 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.57 | 0 | 463.93 | 4.57 | 459.36
| 2026-12-10 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.08 | 0 | 197.01 | 9.08 | 187.93
| 2026-03-26 | N/A | SAN DIEGO | N/A | Not Available | 94 | 68 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.63 | 0 | 192.95 | 5.63 | 187.32
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 67 | 49 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.24 | 0 | 197.01 | 7.24 | 189.77
| 2026-05-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 208 | 148 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.01 | 0 | 192.95 | 12.01 | 180.94
| 2025-09-29 | N/A | SAN DIEGO | N/A | Not Available | 188 | 134 | N/A | 2024-02-20 | Not Available | Not Available | Not Available | -11.13 | Unknown | -1.35 | 0 | 158.79 | -12.48 | 171.27
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 302 | 216 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.15 | 0 | 555.28 | 13.15 | 542.13
| 2025-01-16 | N/A | SAN DIEGO | N/A | Not Available | 120 | 86 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -4.63 | Unknown | 1.35 | 0 | 117.7 | -3.28 | 120.98
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 191 | 137 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.35 | 0 | 464.73 | 6.35 | 458.38
| 2025-06-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 316 | 226 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -33.74 | Unknown | 1386.14 | 0 | 500.87 | 1352.4 | -851.53
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 265 | 189 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | 812.76 | Unknown | 1017.14 | 0 | 463.93 | 1829.9 | -1365.97
| 2027-02-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 74 | 54 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2026-10-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 180 | 128 | N/A | 2025-03-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.84 | 0 | 184.29 | 10.84 | 173.45
| 2024-07-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 247 | 177 | N/A | 2024-02-23 | Not Available | Not Available | Not Available | -4.53 | Unknown | 0.25 | 0 | 596.29 | -4.28 | 600.57
| 2026-05-31 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -10.78 | Unknown | -1.69 | 0 | 192.83 | -12.47 | 205.3
| 2026-08-14 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.92 | 0 | 192.95 | 8.92 | 184.03
| 2024-03-01 | N/A | SAN DIEGO | N/A | Not Available | 194 | 138 | N/A | 2023-08-16 | Not Available | Not Available | Not Available | -10.89 | Unknown | -4.13 | 0 | 496.37 | -15.02 | 511.39
| 2025-04-20 | N/A | SAN DIEGO | N/A | Not Available | 167 | 119 | N/A | 2023-08-18 | Not Available | Not Available | Not Available | -7.61 | Unknown | -2.9 | 0 | 496.37 | -10.51 | 506.88
| 2027-08-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A |  | Not Available | Not Available | Not Available | 535.84 | Unknown | 449.03 | 0 | 180.5 | 984.87 | -804.37
| 2027-01-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.28 | 0 | 196.44 | 5.28 | 191.16
| 2025-09-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 200 | 142 | N/A | 2024-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 127.41 | 0 | 158.37 | 127.41 | 30.96
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.42 | 0 | 197.01 | 5.42 | 191.59
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 463.93 | 0 | 463.93
| 2026-06-26 | N/A | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.64 | 0 | 192.95 | 6.64 | 186.31
| 2026-10-16 | N/A | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.62 | 0 | 288.94 | 2.62 | 286.32
| 2026-05-29 | N/A | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.79 | 0 | 192.95 | 5.79 | 187.16
| 2026-10-23 | N/A | SAN DIEGO | N/A | Not Available | 93 | 67 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.5 | 0 | 197.01 | 9.5 | 187.51
| 2025-02-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 357 | 255 | N/A | 2024-09-06 | Not Available | Not Available | Not Available | 186.4 | Unknown | 453.11 | 0 | 186.52 | 639.51 | -452.99
| 2026-02-19 | N/A | SAN MARCOS | N/A | Not Available | 56 | 40 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.87 | 0 | 235.63 | 1.87 | 233.76
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 588 | 420 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.23 | 0 | 153.83 | 5.23 | 148.6
| 2025-07-20 | Underserved Community | FALLBROOK | N/A | Not Available | 171 | 123 | N/A | 2023-10-31 | Not Available | Not Available | Not Available | -16.63 | Unknown | -5.37 | 0 | 513.31 | -22 | 535.31
| 2025-03-22 | N/A | SAN CLEMENTE | N/A | Not Available | 103 | 73 | N/A | 2024-05-17 | Not Available | Not Available | Not Available | -9.15 | Unknown | -2.11 | 0 | 162.34 | -11.26 | 173.6
| 2024-11-21 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 106 | 76 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | -4.62 | Unknown | -1.25 | 0 | 148.54 | -5.87 | 154.41
| 2026-08-29 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 78 | 56 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.67 | 0 | 184.29 | 8.67 | 175.62
| 2024-05-24 | N/A | SAN DIEGO | N/A | Not Available | 108 | 78 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -9.46 | Unknown | 120.65 | 0 | 496.37 | 111.19 | 385.18
| 2024-09-07 | N/A | LAGUNA NIGUEL | N/A | Not Available | 172 | 124 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | -10.35 | Unknown | -3.57 | 0 | 158.51 | -13.92 | 172.43
| 2026-06-12 | Underserved Community | SAN MARCOS | N/A | Not Available | 135 | 97 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.13 | 0 | 192.51 | 5.13 | 187.38
| 2027-03-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 67 | 47 | N/A |  | Not Available | Not Available | Not Available | 509.4 | Unknown | 336.23 | 0 | 450.11 | 845.63 | -395.52
| 2025-09-22 | Underserved Community | SAN MARCOS | N/A | Not Available | 306 | 220 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.95 | 0 | 163.83 | 13.95 | 149.88
| 2025-04-03 | N/A | LAGUNA HILLS | N/A | Not Available | 142 | 102 | N/A | 2024-08-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.88 | 0 | 180.5 | 8.88 | 171.62
| 2025-08-12 | Underserved Community | LAKESIDE | N/A | Not Available | 15 | 11 | N/A | 2024-08-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.12 | 0 | 1050.75 | 9.12 | 1041.63
| 2024-07-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 253 | 181 | N/A | 2024-03-01 | Not Available | Not Available | Not Available | -3.4 | Unknown | 0.19 | 0 | 596.29 | -3.21 | 599.5
| 2025-04-07 | N/A | SAN DIEGO | N/A | Not Available | 133 | 95 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -7.9 | Unknown | -1.52 | 0 | 153.83 | -9.42 | 163.25
| 2025-02-07 | Underserved Community | OCEANSIDE | N/A | Not Available | 175 | 125 | N/A | 2023-03-22 | Not Available | Not Available | Not Available | -7.1 | Unknown | -2.68 | 0 | 98.41 | -9.78 | 108.19
| 2027-01-02 | Underserved Community | RAMONA | N/A | Not Available | 58 | 42 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 3.6 | 0 | 196.69 | 3.6 | 193.09
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 574 | 410 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.84 | 0 | 153.83 | 3.84 | 149.99
| 2024-06-26 | Underserved Community | EL CAJON | N/A | Not Available | 264 | 190 | N/A | 2024-02-01 | Not Available | Not Available | Not Available | -4.09 | Unknown | -0.95 | 0 | 496.37 | -5.04 | 501.41
| 2025-05-24 | Underserved Community | CHULA VISTA | N/A | Not Available | 77 | 55 | N/A | 2024-03-06 | Not Available | Not Available | Not Available | -6.81 | Unknown | -1.6 | 0 | 1160.62 | -8.41 | 1169.03
| 2026-09-09 | N/A | SAN CLEMENTE | N/A | Not Available | 44 | 32 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.07 | 0 | 1066.51 | 4.07 | 1062.44
| 2025-04-10 | N/A | SAN CLEMENTE | N/A | Not Available | 58 | 42 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | -3.59 | Unknown | -0.83 | 0 | 162.34 | -4.42 | 166.76
| 2025-02-13 | Underserved Community | SANTEE | N/A | Not Available | 72 | 52 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | -13.1 | Unknown | -3.03 | 0 | 534.57 | -16.13 | 550.7
| 2025-02-16 | Underserved Community | DANA POINT | N/A | Not Available | 58 | 42 | N/A | 2024-04-12 | Not Available | Not Available | Not Available | -6.71 | Unknown | -6.71 | 0 | 534.57 | -13.42 | 547.99
| 2025-05-02 | N/A | SAN DIEGO | N/A | Not Available | 175 | 125 | N/A | 2023-09-20 | Not Available | Not Available | Not Available | -7.55 | Unknown | -1.58 | 0 | 153.83 | -9.13 | 162.96
| 2025-10-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 537 | 383 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.63 | 0 | 534.53 | 7.63 | 526.9
| 2026-02-03 | N/A | SANTEE | N/A | Not Available | 174 | 124 | N/A | 2024-07-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.94 | 0 | 534.53 | 6.94 | 527.59
| 2025-12-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2025-04-21 | Not Available | Not Available | Not Available | -4.21 | Unknown | 210.42 | 0 | 196.69 | 206.21 | -9.52
| 2024-10-30 | N/A | MISSION VIEJO | N/A | Not Available | 122 | 88 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | 240.54 | Unknown | 173.01 | 0 | 158.79 | 413.55 | -254.76
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 704 | 502 | N/A | 2025-03-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.48 | 0 | 154.99 | 6.48 | 148.51
| 2026-12-09 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 48 | 34 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.56 | 0 | 197.01 | 13.56 | 183.45
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 585 | 417 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.82 | 0 | 153.83 | 4.82 | 149.01
| 2026-03-29 | N/A | LA JOLLA | N/A | Not Available | 142 | 102 | N/A | 2024-08-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.75 | 0 | 529.2 | 3.75 | 525.45
| 2025-04-30 | N/A | POWAY | N/A | Not Available | 259 | 185 | N/A | 2024-02-23 | Not Available | Not Available | Not Available | -4.29 | Unknown | -1.02 | 0 | 153.83 | -5.31 | 159.14
| 2025-06-22 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 36 | 26 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.17 | 0 | 180.09 | 4.17 | 175.92
| 2025-10-27 | Underserved Community | EL CAJON | N/A | Not Available | 101 | 73 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | 62.97 | Unknown | 1081.94 | 0 | 288.94 | 1144.91 | -855.97
| 2026-06-07 | N/A | CARLSBAD | N/A | Not Available | 311 | 223 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.51 | 0 | 192.83 | 1.51 | 191.32
| 2025-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 173 | 125 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.68 | 0 | 288.94 | 6.68 | 282.26
| 2026-08-19 | Underserved Community | DANA POINT | N/A | Not Available | 49 | 35 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.91 | 0 | 180.5 | 2.91 | 177.59
| 2025-09-22 | N/A | COTO DE CAZA | N/A | Not Available | 42 | 30 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.99 | 0 | 197.01 | 7.99 | 189.02
| 2025-08-28 | Underserved Community | POWAY | N/A | Not Available | 174 | 124 | N/A | 2024-03-28 | Not Available | Not Available | Not Available | -12.09 | Unknown | -2.77 | 0 | 153.26 | -14.86 | 168.12
| 2025-08-17 | N/A | SAN DIEGO | N/A | Not Available | 151 | 109 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -2.38 | Unknown | -0.65 | 0 | 483.59 | -3.03 | 486.62
| 2026-05-13 | N/A | SANTEE | N/A | Not Available | 161 | 115 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.8 | 0 | 192.83 | 6.8 | 186.03
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2024-12-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.86 | 0 | 197.01 | 10.86 | 186.15
| 2026-03-11 | N/A | SAN CLEMENTE | N/A | Not Available | 112 | 80 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -6.37 | Unknown | -1.49 | 0 | 529.2 | -7.86 | 537.06
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 348 | 248 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -6.52 | Unknown | -1.56 | 0 | 154.99 | -8.08 | 163.07
| 2025-08-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 260 | 186 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -9.78 | Unknown | -2.28 | 0 | 163.83 | -12.06 | 175.89
| 2026-03-25 | N/A | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.78 | 0 | 192.51 | 3.78 | 188.73
| 2026-05-19 | N/A | SAN DIEGO | N/A | Not Available | 89 | 63 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.68 | 0 | 192.51 | 7.68 | 184.83
| 2026-12-17 | Underserved Community | SAN MARCOS | N/A | Not Available | 67 | 47 | N/A | 2025-02-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.2 | 0 | 209.48 | 6.2 | 203.28
| 2025-10-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 383 | 273 | N/A | 2024-10-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 3 | 0 | 534.53 | 3 | 531.53
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 136 | 98 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -8.04 | Unknown | -1.84 | 0 | 207.92 | -9.88 | 217.8
| 2025-10-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 134 | 96 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -6.34 | Unknown | -1.48 | 0 | 158.79 | -7.82 | 166.61
| 2026-02-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 82 | 58 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | 33.39 | Unknown | 493.17 | 0 | 1063.08 | 526.56 | 536.52
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.53 | 0 | 197.01 | 4.53 | 192.48
| 2025-12-10 | Underserved Community | EL CAJON | N/A | Not Available | 240 | 172 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.16 | 0 | 499.18 | 4.16 | 495.02
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 233 | 167 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.07 | 0 | 192.95 | 2.07 | 190.88
| 2026-10-14 | Underserved Community | CHULA VISTA | N/A | Not Available | 42 | 30 | N/A |  | Not Available | Not Available | Not Available | 264.94 | Unknown | 181.92 | 0 | 197.01 | 446.86 | -249.85
| 2025-08-18 | Underserved Community | OCEANSIDE | N/A | Not Available | 206 | 148 | N/A | 2024-02-07 | Not Available | Not Available | Not Available | -6.94 | Unknown | -1.63 | 0 | 158.79 | -8.57 | 167.36
| 2024-05-24 | Underserved Community | EL CAJON | N/A | Not Available | 118 | 84 | N/A | 2023-09-27 | Not Available | Not Available | Not Available | -5.31 | Unknown | -1.94 | 0 | 148.7 | -7.25 | 155.95
| 2025-07-30 | Underserved Community | VISTA | N/A | Not Available | 86 | 62 | N/A | 2023-10-18 | Not Available | Not Available | Not Available | -9.78 | Unknown | -2.4 | 0 | 153.83 | -12.18 | 166.01
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 406 | 290 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.75 | 0 | 158.14 | 3.75 | 154.39
| 2024-05-09 | N/A | CARLSBAD | N/A | Not Available | 206 | 148 | N/A | 2023-12-01 | Not Available | Not Available | Not Available | -5.48 | Unknown | -0.58 | 0 | 158.14 | -6.06 | 164.2
| 2025-04-07 | Underserved Community | CHULA VISTA | N/A | Not Available | 141 | 101 | N/A | 2023-11-09 | Not Available | Not Available | Not Available | 238.7 | Unknown | 620.15 | 0 | 152.86 | 858.85 | -705.99
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 142 | 102 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.25 | 0 | 645.75 | 10.25 | 635.5
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 139 | 99 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 207.92 | -4.06 | 211.98
| 2025-10-23 | Underserved Community | ESCONDIDO | N/A | Not Available | 389 | 277 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.35 | 0 | 163.83 | 15.35 | 148.48
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 231 | 165 | N/A | 2024-04-02 | Not Available | Not Available | Not Available | 2628.19 | Unknown | 3262.72 | 0 | 158.79 | 5890.91 | -5732.12
| 2025-11-09 | Underserved Community | CHULA VISTA | N/A | Not Available | 165 | 117 | N/A | 2024-03-04 | Not Available | Not Available | Not Available | -10.88 | Unknown | -2.52 | 0 | 163.83 | -13.4 | 177.23
| 2025-11-08 | Underserved Community | CHULA VISTA | N/A | Not Available | 236 | 168 | N/A |  | Not Available | Not Available | Not Available | 548.79 | Unknown | 376.68 | 0 | 163.83 | 925.47 | -761.64
| 2026-09-13 | Underserved Community | VISTA | N/A | Not Available | 30 | 22 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | 0 | 197.01
| 2025-11-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 273 | 195 | N/A | 2024-08-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 29.05 | 0 | 501.18 | 29.05 | 472.13
| 2026-01-07 | N/A | LA JOLLA | N/A | Not Available | 64 | 46 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.47 | 0 | 1050.75 | 6.47 | 1044.28
| 2025-06-24 | N/A | COTO DE CAZA | N/A | Not Available | 77 | 55 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | 109.72 | Unknown | 75.31 | 0 | 192.51 | 185.03 | 7.48
| 2026-01-12 | Underserved Community | POWAY | N/A | Not Available | 31 | 23 | N/A | 2024-03-01 | Not Available | Not Available | Not Available | -7.91 | Unknown | -1.84 | 0 | 163.83 | -9.75 | 173.58
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2025-06-16 | Underserved Community | VISTA | N/A | Not Available | 204 | 146 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -8.4 | Unknown | -2.27 | 0 | 515.81 | -10.67 | 526.48
| 2027-02-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 33 | 25 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | -9.89 | Unknown | -1.32 | 0 | 196.44 | -11.21 | 207.65
| 2026-09-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 46 | 32 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.8 | 0 | 1103.3 | 6.8 | 1096.5
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 175 | 125 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -11.86 | Unknown | -2.77 | 0 | 158.51 | -14.63 | 173.14
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 327 | 233 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | 504.66 | Unknown | 492.4 | 0 | 153.49 | 997.06 | -843.57
| 2026-11-21 | N/A | ENCINITAS | N/A | Not Available | 60 | 44 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.83 | 0 | 196.44 | 8.83 | 187.61
| 2025-05-16 | Underserved Community | ALPINE | N/A | Not Available | 36 | 26 | N/A | 2024-08-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.43 | 0 | 1050.75 | 5.43 | 1045.32
| 2026-09-26 | Underserved Community | VISTA | N/A | Not Available | 81 | 59 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 40.22 | 0 | 2212.77 | 40.22 | 2172.55
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 308 | 220 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -8.23 | Unknown | -1.97 | 0 | 154.99 | -10.2 | 165.19
| 2026-10-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 122 | 88 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.35 | 0 | 197.01 | 13.35 | 183.66
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -3.07 | Unknown | -0.71 | 0 | 207.92 | -3.78 | 211.7
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 142 | 102 | N/A | 2024-06-26 | Not Available | Not Available | Not Available | -4.54 | Unknown | -1.06 | 0 | 207.92 | -5.6 | 213.52
| 2026-11-06 | Underserved Community | CAMPO | N/A | Not Available | 151 | 109 | N/A |  | Not Available | Not Available | Not Available | 416.72 | Unknown | 172.68 | 0 | 105.72 | 589.4 | -483.68
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 210 | 150 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.11 | 0 | 158.79 | -5.9 | 164.69
| 2025-07-07 | N/A | LA JOLLA | N/A | Not Available | 117 | 83 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | -37.16 | Unknown | 1937.28 | 0 | 514.57 | 1900.12 | -1385.55
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 53 | 37 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 30.24 | 0 | 197.01 | 30.24 | 166.77
| 2024-11-29 | Underserved Community | EL CAJON | N/A | Not Available | 238 | 170 | N/A | 2024-07-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.46 | 0 | 499.18 | 8.46 | 490.72
| 2026-02-22 | N/A | POWAY | N/A | Not Available | 78 | 56 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 192.95 | 4.29 | 188.66
| 2026-07-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 98 | 70 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.91 | 0 | 197.01 | 7.91 | 189.1
| 2025-12-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 198 | 142 | N/A | 2024-05-16 | Not Available | Not Available | Not Available | -6.7 | Unknown | 60.45 | 0 | 534.53 | 53.75 | 480.78
| 2026-03-13 | Underserved Community | ESCONDIDO | N/A | Not Available | 170 | 122 | N/A | 2024-08-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 29.42 | 0 | 192.95 | 29.42 | 163.53
| 2024-07-20 | Underserved Community | EL CAJON | N/A | Not Available | 50 | 36 | N/A | 2023-08-10 | Not Available | Not Available | Not Available | -8.72 | Unknown | -1.81 | 0 | 143.91 | -10.53 | 154.44
| 2025-08-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 143 | 103 | N/A | 2024-01-18 | Not Available | Not Available | Not Available | -5.29 | Unknown | -1.41 | 0 | 515.81 | -6.7 | 522.51
| 2024-09-11 | Underserved Community | LA MESA | N/A | Not Available | 76 | 54 | N/A | 2023-11-13 | Not Available | Not Available | Not Available | -13.12 | Unknown | 119.84 | 0 | 513.31 | 106.72 | 406.59
| 2026-06-04 | N/A | RANCHO LA COSTA | N/A | Not Available | 61 | 43 | N/A | 2024-06-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.23 | 0 | 192.83 | 7.23 | 185.6
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 71 | 51 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.57 | 0 | 192.95 | 4.57 | 188.38
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 62 | 44 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 192.95 | 3.85 | 189.1
| 2024-06-19 | Underserved Community | SPRING VALLEY | N/A | Not Available | 116 | 84 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | -10.02 | Unknown | -3.81 | 0 | 496.37 | -13.83 | 510.2
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 141 | 101 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 207.92 | -4.06 | 211.98
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 196 | 140 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.34 | 0 | 158.51 | -7.16 | 165.67
| 2026-07-25 | Underserved Community | LAKESIDE | N/A | Not Available | 35 | 25 | N/A | 2024-08-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.89 | 0 | 180.5 | 7.89 | 172.61
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 193 | 139 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.34 | 0 | 158.14 | -7.16 | 165.3
| 2024-10-27 | Underserved Community | LEMON GROVE | N/A | Not Available | 116 | 84 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -10.65 | Unknown | -2.46 | 0 | 515.86 | -13.11 | 528.97
| 2024-09-27 | Underserved Community | LA MESA | N/A | Not Available | 113 | 81 | N/A | 2024-01-05 | Not Available | Not Available | Not Available | -9.33 | Unknown | -2.5 | 0 | 515.81 | -11.83 | 527.64
| 2025-01-10 | Underserved Community | EL CAJON | N/A | Not Available | 193 | 139 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | 302.41 | Unknown | 388.63 | 0 | 186.4 | 691.04 | -504.64
| 2024-03-21 | Underserved Community | LEMON GROVE | N/A | Not Available | 190 | 136 | N/A | 2023-07-12 | Not Available | Not Available | Not Available | -12.18 | Unknown | -4.66 | 0 | 496.45 | -16.84 | 513.29
| 2025-06-19 | Underserved Community | LA MESA | N/A | Not Available | 90 | 64 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | -22.3 | Unknown | 1108.45 | 0 | 1016.86 | 1086.15 | -69.29
| 2024-10-12 | Underserved Community | SPRING VALLEY | N/A | Not Available | 80 | 58 | N/A | 2023-12-21 | Not Available | Not Available | Not Available | -10.85 | Unknown | -2.89 | 0 | 515.81 | -13.74 | 529.55
| 2024-08-30 | Underserved Community | WARNER SPRINGS | N/A | Not Available | 64 | 46 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 983.28 | 0 | 985.13 | 983.28 | 1.85
| 2024-06-26 | N/A | SAN DIEGO | N/A | Not Available | 192 | 138 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | -14.02 | Unknown | -4.96 | 0 | 496.37 | -18.98 | 515.35
| 2025-10-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 168 | 120 | N/A |  | Not Available | Not Available | Not Available | 252.46 | Unknown | 173.15 | 0 | 534.53 | 425.61 | 108.92
| 2025-04-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 249 | 177 | N/A | 2023-12-15 | Not Available | Not Available | Not Available | -10.1 | Unknown | -2.74 | 0 | 153.87 | -12.84 | 166.71
| 2026-07-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2024-08-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.07 | 0 | 180.09 | 12.07 | 168.02
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.76 | 0 | 197.01 | 8.76 | 188.25
| 2025-04-17 | N/A | SAN DIEGO | N/A | Not Available | 112 | 80 | N/A | 2023-10-12 | Not Available | Not Available | Not Available | 808.88 | Unknown | 367.7 | 0 | 158.51 | 1176.58 | -1018.07
| 2026-01-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-02-14 | Not Available | Not Available | Not Available | -10.22 | Unknown | -5.55 | 0 | 196.69 | -15.77 | 212.46
| 2026-03-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2024-03-14 | Not Available | Not Available | Not Available | -6.23 | Unknown | -1.43 | 0 | 534.53 | -7.66 | 542.19
| 2026-06-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.97 | 0 | 1085.63 | 7.97 | 1077.66
| 2026-11-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.68 | 0 | 197.01 | 3.68 | 193.33
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.76 | 0 | 184.29 | 3.76 | 180.53
| 2027-03-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | -11.07 | Unknown | 547.92 | 0 | 1063.08 | 536.85 | 526.23
| 2025-10-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -12.68 | Unknown | -2.93 | 0 | 534.53 | -15.61 | 550.14
| 2025-08-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2023-12-21 | Not Available | Not Available | Not Available | -5.68 | Unknown | -1.86 | 0 | 515.81 | -7.54 | 523.35
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.98 | 0 | 197.01 | 4.98 | 192.03
| 2026-09-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 199 | 143 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.94 | 0 | 197.01 | 3.94 | 193.07
| 2026-12-11 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.18 | 0 | 197.01 | 5.18 | 191.83
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.97 | 0 | 197.01 | 2.97 | 194.04
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 279 | 199 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.34 | 0 | 463.93 | 5.34 | 458.59
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 279 | 199 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.12 | 0 | 463.93 | 7.12 | 456.81
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 296 | 212 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | -22.2 | Unknown | -12.06 | 0 | 464.73 | -34.26 | 498.99
| 2026-11-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 32 | 24 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.97 | 0 | 197.01 | 2.97 | 194.04
| 2025-03-30 | N/A | SAN DIEGO | N/A | Not Available | 169 | 121 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -12.72 | Unknown | -4.81 | 0 | 496.37 | -17.53 | 513.9
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 300 | 214 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | -18.13 | Unknown | -9.84 | 0 | 464.73 | -27.97 | 492.7
| 2026-08-30 | N/A | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.02 | 0 | 197.01 | 7.02 | 189.99
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 268 | 192 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.06 | 0 | 463.93 | 7.06 | 456.87
| 2026-10-24 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.13 | 0 | 197.01 | 4.13 | 192.88
| 2026-01-28 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | -7.84 | Unknown | 396.05 | 0 | 1064.43 | 388.21 | 676.22
| 2027-01-23 | N/A | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.68 | 0 | 196.69 | 7.68 | 189.01
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-02-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.71 | 0 | 463.93 | 8.71 | 455.22
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 286 | 204 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.89 | 0 | 555.28 | 6.89 | 548.39
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.87 | 0 | 197.01 | 10.87 | 186.14
| 2025-10-28 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -8.44 | Unknown | -2.27 | 0 | 534.53 | -10.71 | 545.24
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 219 | 157 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.68 | 0 | 644.91 | 7.68 | 637.23
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 280 | 200 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.98 | 0 | 463.93 | 7.98 | 455.95
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.04 | 0 | 197.01 | 7.04 | 189.97
| 2025-09-18 | N/A | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -12.3 | Unknown | -2.84 | 0 | 515.81 | -15.14 | 530.95
| 2026-05-09 | N/A | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.54 | 0 | 192.51 | 4.54 | 187.97
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 46 | 34 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.77 | 0 | 197.01 | 7.77 | 189.24
| 2026-02-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 168 | 120 | N/A | 2024-07-31 | Not Available | Not Available | Not Available | -7.55 | Unknown | 404.26 | 0 | 529.2 | 396.71 | 132.49
| 2025-12-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 201 | 143 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 20.83 | 0 | 1175.81 | 20.83 | 1154.98
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 286 | 204 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 11 | 0 | 464.73 | 11 | 453.73
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 302 | 216 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.81 | 0 | 554.38 | 4.81 | 549.57
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 218 | 156 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.96 | 0 | 463.93 | 8.96 | 454.97
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 307 | 219 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.62 | 0 | 464.73 | 6.62 | 458.11
| 2026-06-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 74 | 52 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | -29.37 | Unknown | 1455.15 | 0 | 1049.43 | 1425.78 | -376.35
| 2025-12-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A | 2024-03-29 | Not Available | Not Available | Not Available | -12.12 | Unknown | -2.8 | 0 | 534.53 | -14.92 | 549.45
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 307 | 219 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.37 | 0 | 464.73 | 4.37 | 460.36
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 25 | 19 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.76 | 0 | 196.69 | 4.76 | 191.93
| 2026-03-27 | N/A | SAN DIEGO | N/A | Not Available | 112 | 80 | N/A | 2024-07-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.06 | 0 | 192.51 | 7.06 | 185.45
| 2025-08-29 | N/A | SAN DIEGO | N/A | Not Available | 211 | 151 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -16.41 | Unknown | -3.8 | 0 | 483.59 | -20.21 | 503.8
| 2025-07-27 | N/A | SAN DIEGO | N/A | Not Available | 131 | 93 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -8.07 | Unknown | -1.43 | 0 | 158.14 | -9.5 | 167.64
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 192 | 138 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.5 | 0 | 554.38 | 7.5 | 546.88
| 2026-03-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 69 | 49 | N/A | 2024-05-20 | Not Available | Not Available | Not Available | -12 | Unknown | 121.24 | 0 | 529.2 | 109.24 | 419.96
| 2025-10-17 | N/A | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2024-05-07 | Not Available | Not Available | Not Available | -17.57 | Unknown | -4.06 | 0 | 162.34 | -21.63 | 183.97
| 2025-11-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 365 | 261 | N/A | 2024-11-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | 0 | 288.94
| 2025-10-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2023-12-28 | Not Available | Not Available | Not Available | -9.71 | Unknown | -2.61 | 0 | 515.81 | -12.32 | 528.13
| 2025-03-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 343 | 245 | N/A | 2025-02-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.06 | 0 | 105.72 | 15.06 | 90.66
| 2026-10-12 | N/A | SAN DIEGO | N/A | Not Available | 388 | 277 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.68 | 0 | 197.01 | 9.68 | 187.33
| 2025-02-08 | N/A | SAN DIEGO | N/A | Not Available | 5 | 3 | N/A | 2024-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.06 | 0 | 163.83 | 2.06 | 161.77
| 2026-11-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.07 | 0 | 197.01 | 4.07 | 192.94
| 2025-08-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 150 | 108 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1 | 0 | 513.31 | -4.74 | 518.05
| 2027-08-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 1016.86 | 3.05 | 1013.81
| 2025-05-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2024-07-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.15 | 0 | 1016.73 | 2.15 | 1014.58
| 2025-06-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 210 | 150 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | -7.71 | Unknown | -2.08 | 0 | 500.87 | -9.79 | 510.66
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 268 | 192 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.87 | 0 | 554.38 | 6.87 | 547.51
| 2026-03-19 | N/A | SAN DIEGO | N/A | Not Available | 61 | 43 | N/A | 2024-05-07 | Not Available | Not Available | Not Available | -12.37 | Unknown | -1.41 | 0 | 162.34 | -13.78 | 176.12
| 2026-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2025-06-24 | Not Available | Not Available | Not Available | 137.6 | Unknown | 187.36 | 0 | 428.69 | 324.96 | 103.73
| 2025-05-15 | N/A | SAN DIEGO | N/A | Not Available | 159 | 113 | N/A | 2023-09-25 | Not Available | Not Available | Not Available | -5.47 | Unknown | 511.89 | 0 | 500.87 | 506.42 | -5.55
| 2024-05-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 128 | 92 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | -16.7 | Unknown | -4 | 0 | 153.83 | -20.7 | 174.53
| 2025-05-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 68 | 48 | N/A | 2024-09-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 220.03 | 0 | 1576.13 | 220.03 | 1356.1
| 2025-04-10 | N/A | SAN DIEGO | N/A | Not Available | 183 | 131 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -9.91 | Unknown | -3.62 | 0 | 153.83 | -13.53 | 167.36
| 2025-05-08 | N/A | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -8.63 | Unknown | -3.15 | 0 | 496.37 | -11.78 | 508.15
| 2025-04-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2024-10-28 | Not Available | Not Available | Not Available | -15.15 | Unknown | 759.94 | 0 | 985.1 | 744.79 | 240.31
| 2025-04-19 | N/A | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2024-07-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.98 | 0 | 1050.61 | 6.98 | 1043.63
| 2026-04-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2024-06-05 | Not Available | Not Available | Not Available | -11.34 | Unknown | -2.62 | 0 | 1050.61 | -13.96 | 1064.57
| 2026-12-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 33.73 | 0 | 1560.05 | 33.73 | 1526.32
| 2025-08-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 104 | 74 | N/A | 2023-12-11 | Not Available | Not Available | Not Available | -39.66 | Unknown | 1495.84 | 0 | 515.81 | 1456.18 | -940.37
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-01-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.63 | 0 | 197.01 | 3.63 | 193.38
| 2026-03-30 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 121 | 87 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 34.47 | 0 | 1050.61 | 34.47 | 1016.14
| 2026-05-05 | N/A | POWAY | N/A | Not Available | 106 | 76 | N/A | 2024-08-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.18 | 0 | 192.83 | 8.18 | 184.65
| 2026-07-28 | Underserved Community | EL CAJON | N/A | Not Available | 101 | 73 | N/A | 2024-11-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.07 | 0 | 192.95 | 7.07 | 185.88
| 2024-04-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 35 | 25 | N/A | 2024-04-10 | Not Available | Not Available | Not Available | -20.94 | Unknown | -1.84 | 0 | 197.97 | -22.78 | 220.75
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -9.07 | Unknown | -2.09 | 0 | 158.14 | -11.16 | 169.3
| 2026-02-15 | Underserved Community | VISTA | N/A | Not Available | 155 | 111 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | 256.56 | Unknown | 181.08 | 0 | 534.57 | 437.64 | 96.93
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 354 | 254 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 158.14 | 3.17 | 154.97
| 2025-10-24 | Underserved Community | OCEANSIDE | N/A | Not Available | 202 | 144 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | 605.73 | Unknown | 447.03 | 0 | 534.53 | 1052.76 | -518.23
| 2026-02-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 80 | 58 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | -9.73 | Unknown | -2.27 | 0 | 162.34 | -12 | 174.34
| 2027-03-28 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 33 | 25 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | -0.94 | Unknown | 46.35 | 0 | 1029.34 | 45.41 | 983.93
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 391 | 279 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -10.41 | Unknown | -2.45 | 0 | 185.43 | -12.86 | 198.29
| 2025-01-04 | Underserved Community | SPRING VALLEY | N/A | Not Available | 62 | 44 | N/A | 2024-02-13 | Not Available | Not Available | Not Available | -10.9 | Unknown | -2.55 | 0 | 721.69 | -13.45 | 735.14
| 2026-10-18 | Underserved Community | CHULA VISTA | N/A | Not Available | 111 | 79 | N/A |  | Not Available | Not Available | Not Available | 1156.86 | Unknown | 482.92 | 0 | 190.44 | 1639.78 | -1449.34
| 2025-08-27 | N/A | LA JOLLA | N/A | Not Available | 94 | 68 | N/A | 2023-11-30 | Not Available | Not Available | Not Available | -5.12 | Unknown | -1.65 | 0 | 515.81 | -6.77 | 522.58
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 495 | 353 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.02 | 0 | 154.99 | 7.02 | 147.97
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 6 | 4 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.94 | 0 | 192.95 | 2.94 | 190.01
| 2026-02-06 | N/A | CARDIFF | N/A | Not Available | 135 | 97 | N/A | 2024-05-14 | Not Available | Not Available | Not Available | -13.98 | Unknown | -3.25 | 0 | 534.53 | -17.23 | 551.76
| 2026-06-26 | Underserved Community | FALLBROOK | N/A | Not Available | 44 | 32 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.82 | 0 | 192.51 | 4.82 | 187.69
| 2025-08-04 | N/A | RANCHO LA COSTA | N/A | Not Available | 158 | 114 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | -7.88 | Unknown | -2.12 | 0 | 158.79 | -10 | 168.79
| 2026-04-12 | Underserved Community | BONITA | N/A | Not Available | 200 | 142 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.73 | 0 | 186.52 | 10.73 | 175.79
| 2025-02-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -9.78 | Unknown | 3.95 | 0 | 154.79 | -5.83 | 160.62
| 2025-01-26 | Underserved Community | OCEANSIDE | N/A | Not Available | 167 | 119 | N/A | 2023-03-09 | Not Available | Not Available | Not Available | -5.65 | Unknown | -2.15 | 0 | 98.41 | -7.8 | 106.21
| 2024-10-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 366 | 262 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | -4.43 | Unknown | 0.23 | 0 | 94.08 | -4.2 | 98.28
| 2024-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 162 | 116 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | -9.35 | Unknown | -3.51 | 0 | 364.52 | -12.86 | 377.38
| 2024-12-09 | N/A | VISTA | N/A | Not Available | 128 | 92 | N/A | 2023-04-24 | Not Available | Not Available | Not Available | -5.55 | Unknown | -0.29 | 0 | 154.79 | -5.84 | 160.63
| 2025-10-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 172 | 122 | N/A | 2023-03-03 | Not Available | Not Available | Not Available | -7.9 | Unknown | -3.02 | 0 | 98.41 | -10.92 | 109.33
| 2024-02-10 | N/A | LAGUNA NIGUEL | N/A | Not Available | 128 | 92 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -15.73 | Unknown | -5.99 | 0 | 80.96 | -21.72 | 102.68
| 2023-12-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 161 | 115 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -15.9 | Unknown | -4.89 | 0 | 95.13 | -20.79 | 115.92
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | 124 | 90 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | -10.54 | Unknown | 528.8 | 0 | 197.01 | 518.26 | -321.25
| 2025-02-07 | Underserved Community | OCEANSIDE | N/A | Not Available | 141 | 101 | N/A | 2023-05-09 | Not Available | Not Available | Not Available | -4.1 | Unknown | -1.54 | 0 | 364.52 | -5.64 | 370.16
| 2024-12-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 124 | 88 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | -7.07 | Unknown | -2.67 | 0 | 499.96 | -9.74 | 509.7
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 216 | 154 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.44 | 0 | 163.83 | 2.44 | 161.39
| 2026-03-16 | N/A | CARDIFF | N/A | Not Available | 16 | 12 | N/A | 2024-05-24 | Not Available | Not Available | Not Available | -9.56 | Unknown | -0.74 | 0 | 192.51 | -10.3 | 202.81
| 2024-10-19 | N/A | ENCINITAS | N/A | Not Available | 200 | 144 | N/A | 2023-05-18 | Not Available | Not Available | Not Available | -3.03 | Unknown | 2.03 | 0 | 341 | -1 | 342
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 216 | 154 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.53 | 0 | 163.83 | 4.53 | 159.3
| 2025-03-17 | N/A | DEL MAR | N/A | Not Available | 125 | 89 | N/A | 2023-03-28 | Not Available | Not Available | Not Available | -3.94 | Unknown | -1.51 | 0 | 363.72 | -5.45 | 369.17
| 2026-08-28 | N/A | SAN CLEMENTE | N/A | Not Available | 91 | 65 | N/A | 2024-11-21 | Not Available | Not Available | Not Available | -37.58 | Unknown | 2347.8 | 0 | 105.08 | 2310.22 | -2205.14
| 2025-08-23 | Underserved Community | LAKESIDE | N/A | Not Available | 53 | 39 | N/A | 2024-12-30 | Not Available | Not Available | Not Available | 34.05 | Unknown | 385.58 | 0 | 197.01 | 419.63 | -222.62
| 2024-11-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 129 | 93 | N/A | 2023-03-24 | Not Available | Not Available | Not Available | -10.96 | Unknown | -11.11 | 0 | 341 | -22.07 | 363.07
| 2025-01-11 | Underserved Community | VISTA | N/A | Not Available | 162 | 116 | N/A | 2023-03-14 | Not Available | Not Available | Not Available | -10.46 | Unknown | -3.98 | 0 | 98.41 | -14.44 | 112.85
| 2023-12-27 | N/A | LAGUNA HILLS | N/A | Not Available | 237 | 169 | N/A | 2023-03-16 | Not Available | Not Available | Not Available | -6.84 | Unknown | -2.62 | 0 | 67.06 | -9.46 | 76.52
| 2024-04-17 | N/A | DEL MAR | N/A | Not Available | 133 | 95 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -10.02 | Unknown | -3.81 | 0 | 464.78 | -13.83 | 478.61
| 2024-02-23 | Underserved Community | VISTA | N/A | Not Available | 16 | 12 | N/A | 2023-05-26 | Not Available | Not Available | Not Available | -7.64 | Unknown | -2.92 | 0 | 464.78 | -10.56 | 475.34
| 2024-12-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2023-05-11 | Not Available | Not Available | Not Available | 255.6 | Unknown | 94.69 | 0 | 495.75 | 350.29 | 145.46
| 2024-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 164 | 118 | N/A | 2023-08-02 | Not Available | Not Available | Not Available | -10.54 | Unknown | -4 | 0 | 495.75 | -14.54 | 510.29
| 2025-12-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 126 | 90 | N/A | 2023-05-16 | Not Available | Not Available | Not Available | -4.11 | Unknown | -1.55 | 0 | 153.75 | -5.66 | 159.41
| 2025-04-12 | N/A | SAN CLEMENTE | N/A | Not Available | 38 | 28 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.57 | 0 | 192.83 | 6.57 | 186.26
| 2024-02-14 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 119 | 85 | N/A | 2023-05-17 | Not Available | Not Available | Not Available | -6 | Unknown | -2.26 | 0 | 110.98 | -8.26 | 119.24
| 2025-01-31 | N/A | ENCINITAS | N/A | Not Available | 79 | 57 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -5.14 | Unknown | 1.04 | 0 | 153.75 | -4.1 | 157.85
| 2024-11-27 | N/A | DANA POINT | N/A | Not Available | 63 | 45 | N/A | 2023-12-28 | Not Available | Not Available | Not Available | -11.84 | Unknown | -3.62 | 0 | 148.54 | -15.46 | 164
| 2024-03-06 | N/A | OCEANSIDE | N/A | Not Available | 127 | 91 | N/A | 2023-09-25 | Not Available | Not Available | Not Available | -5.83 | Unknown | -2.22 | 0 | 153.75 | -8.05 | 161.8
| 2024-04-19 | Underserved Community | OCEANSIDE | N/A | Not Available | 116 | 84 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -7.34 | Unknown | -2.78 | 0 | 143.83 | -10.12 | 153.95
| 2024-02-23 | Underserved Community | EL CAJON | N/A | Not Available | 149 | 107 | N/A | 2023-08-07 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.68 | 0 | 499.96 | -6.11 | 506.07
| 2024-10-26 | N/A | POWAY | N/A | Not Available | 197 | 141 | N/A | 2023-08-03 | Not Available | Not Available | Not Available | -10.21 | Unknown | -3.9 | 0 | 98.41 | -14.11 | 112.52
| 2024-06-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A | 2024-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.25 | 0 | 725.48 | -0.25 | 725.73
| 2025-01-01 | N/A | CARDIFF | N/A | Not Available | 202 | 144 | N/A | 2024-09-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 163.83 | 3.17 | 160.66
| 2026-03-20 | N/A | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2025-03-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.56 | 0 | 196.59 | 16.56 | 180.03
| 2024-06-30 | N/A | MISSION VIEJO | N/A | Not Available | 7 | 5 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.98 | 0 | 192.95 | 9.98 | 182.97
| 2025-12-09 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 34 | 24 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 22.76 | 0 | 104.94 | 22.76 | 82.18
| 2026-08-14 | Underserved Community | DANA POINT | N/A | Not Available | 61 | 45 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | 0 | 184.29
| 2025-02-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 102 | N/A | 2023-08-15 | Not Available | Not Available | Not Available | -31.7 | Unknown | 1152.94 | 0 | 495.75 | 1121.24 | -625.49
| 2025-09-03 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 101 | 73 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.1 | 0 | 105.08 | 7.1 | 97.98
| 2024-02-03 | Underserved Community | LA MESA | N/A | Not Available | 223 | 159 | N/A | 2023-08-08 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.87 | 0 | 376.27 | -6.82 | 383.09
| 2025-10-08 | N/A | ENCINITAS | N/A | Not Available | 391 | 279 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.66 | 0 | 203.23 | 15.66 | 187.57
| 2025-02-16 | Underserved Community | FALLBROOK | N/A | Not Available | 135 | 97 | N/A | 2023-06-27 | Not Available | Not Available | Not Available | -18.29 | Unknown | -6.95 | 0 | 594.91 | -25.24 | 620.15
| 2026-08-19 | Underserved Community | CAPISTRANO BEACH | N/A | Not Available | 54 | 40 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.77 | 0 | 1333.17 | 5.77 | 1327.4
| 2027-03-12 | N/A | SAN CLEMENTE | N/A | Not Available | 27 | 19 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.69 | 0 | 196.44 | 7.69 | 188.75
| 2025-04-04 | Underserved Community | SAN MARCOS | N/A | Not Available | 119 | 85 | N/A | 2023-08-15 | Not Available | Not Available | Not Available | -10.57 | Unknown | -4.01 | 0 | 153.75 | -14.58 | 168.33
| 2024-06-20 | N/A | SAN CLEMENTE | N/A | Not Available | 181 | 129 | N/A | 2024-02-27 | Not Available | Not Available | Not Available | -6.34 | Unknown | -1.5 | 0 | 111.81 | -7.84 | 119.65
| 2024-03-22 | N/A | LAGUNA NIGUEL | N/A | Not Available | 122 | 88 | N/A | 2023-07-05 | Not Available | Not Available | Not Available | 63.89 | Unknown | 40.14 | 0 | 110.98 | 104.03 | 6.95
| 2025-01-27 | N/A | SOLANA BEACH | N/A | Not Available | 51 | 37 | N/A | 2023-09-05 | Not Available | Not Available | Not Available | -5.14 | Unknown | 0.69 | 0 | 153.87 | -4.45 | 158.32
| 2026-02-06 | Underserved Community | DANA POINT | N/A | Not Available | 28 | 20 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.78 | 0 | 76.08 | 6.78 | 69.3
| 2025-11-24 | Underserved Community | OCEANSIDE | N/A | Not Available | 330 | 236 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.28 | 0 | 163.83 | 5.28 | 158.55
| 2026-07-10 | N/A | SAN CLEMENTE | N/A | Not Available | 39 | 29 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.82 | 0 | 102.37 | 5.82 | 96.55
| 2026-11-05 | N/A | DANA POINT | N/A | Not Available | 29 | 21 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | 208.36 | Unknown | 147.14 | 0 | 76.18 | 355.5 | -279.32
| 2024-01-16 | Underserved Community | LA MESA | N/A | Not Available | 189 | 135 | N/A | 2023-08-14 | Not Available | Not Available | Not Available | -8.91 | Unknown | -3.38 | 0 | 98.41 | -12.29 | 110.7
| 2024-10-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2023-12-27 | Not Available | Not Available | Not Available | -29.72 | Unknown | -31.34 | 0 | 483.59 | -61.06 | 544.65
| 2025-02-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2023-05-19 | Not Available | Not Available | Not Available | -7.88 | Unknown | -3 | 0 | 153.75 | -10.88 | 164.63
| 2025-03-31 | N/A | SAN CLEMENTE | N/A | Not Available | 5 | 5 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.22 | 0 | 1063.64 | 7.22 | 1056.42
| 2024-08-22 | N/A | SAN DIEGO | N/A | Not Available | 4 | 4 | N/A | 2023-08-24 | Not Available | Not Available | Not Available | -4.18 | Unknown | -1.6 | 0 | 148.7 | -5.78 | 154.48
| 2026-03-26 | N/A | DANA POINT | N/A | Not Available | 16 | 12 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | -24.15 | Unknown | 1204.83 | 0 | 196.59 | 1180.68 | -984.09
| 2025-02-06 | N/A | ENCINITAS | N/A | Not Available | 129 | 92 | N/A | 2023-04-21 | Not Available | Not Available | Not Available | -5.23 | Unknown | -1.99 | 0 | 144.8 | -7.22 | 152.02
| 2025-05-22 | N/A | SAN DIEGO | N/A | Not Available | 380 | 272 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.87 | 0 | 153.83 | 7.87 | 145.96
| 2026-03-19 | N/A | SAN DIEGO | N/A | Not Available | 19 | 13 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 196.59 | 3.85 | 192.74
| 2025-10-10 | Underserved Community | CHULA VISTA | N/A | Not Available | 155 | 111 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | -6.51 | Unknown | -2.47 | 0 | 363.72 | -8.98 | 372.7
| 2023-10-12 | N/A | SAN DIEGO | N/A | Not Available | 206 | 148 | N/A | 2023-05-08 | Not Available | Not Available | Not Available | -8.47 | Unknown | -3.22 | 0 | 98.41 | -11.69 | 110.1
| 2027-05-01 | N/A | CARLSBAD | N/A | Not Available | 8 | 6 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2025-01-15 | N/A | LAGUNA NIGUEL | N/A | Not Available | 98 | 70 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -17.53 | Unknown | -4.05 | 0 | 117.79 | -21.58 | 139.37
| 2025-03-04 | N/A | LAGUNA NIGUEL | N/A | Not Available | 87 | 63 | N/A | 2024-07-12 | Not Available | Not Available | Not Available | -21.18 | Unknown | -3.38 | 0 | 84.66 | -24.56 | 109.22
| 2025-03-28 | N/A | SAN MARCOS | N/A | Not Available | 162 | 116 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -11.26 | Unknown | -4.26 | 0 | 40.33 | -15.52 | 55.85
| 2025-11-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 46 | 34 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 233.02 | 0 | 196.44 | 233.02 | -36.58
| 2026-02-18 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 17 | 13 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.88 | 0 | 76.08 | 8.88 | 67.2
| 2025-02-20 | N/A | POWAY | N/A | Not Available | 89 | 64 | N/A | 2023-06-07 | Not Available | Not Available | Not Available | -15.37 | Unknown | -5.86 | 0 | 144.8 | -21.23 | 166.03
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 44 | 32 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 860.83 | 0 | 860.83
| 2025-07-05 | N/A | CARLSBAD | N/A | Not Available | 218 | 156 | N/A | 2024-06-05 | Not Available | Not Available | Not Available | -2.66 | Unknown | -0.6 | 0 | 202.37 | -3.26 | 205.63
| 2025-06-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2023-06-26 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.84 | 0 | 464.78 | -6.62 | 471.4
| 2027-02-12 | N/A | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 196.69 | 8.02 | 188.67
| 2027-02-13 | Underserved Community | LA MESA | N/A | Not Available | 17 | 13 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | -39.1 | Unknown | 1189.24 | 0 | 1063.08 | 1150.14 | -87.06
| 2027-01-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.73 | 0 | 196.69 | 8.73 | 187.96
| 2026-05-03 | N/A | DEL MAR | N/A | Not Available | 34 | 24 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | 506.8 | Unknown | 347.82 | 0 | 393.98 | 854.62 | -460.64
| 2026-11-26 | N/A | CARDIFF | N/A | Not Available | 25 | 19 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.8 | 0 | 279.3 | 6.8 | 272.5
| 2027-02-04 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.6 | 0 | 196.44 | 3.6 | 192.84
| 2026-09-30 | N/A | SAN DIEGO | N/A | Not Available | 23 | 17 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.16 | 0 | 1279.89 | 8.16 | 1271.73
| 2026-12-10 | Underserved Community | OCEANSIDE | N/A | Not Available | 50 | 36 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.63 | 0 | 197.01 | 5.63 | 191.38
| 2026-09-04 | Underserved Community | SAN MARCOS | N/A | Not Available | 16 | 12 | N/A | 2024-10-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.75 | 0 | 197.01 | 6.75 | 190.26
| 2025-09-19 | Underserved Community | LEMON GROVE | N/A | Not Available | 25 | 19 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.56 | 0 | 288.94 | 10.56 | 278.38
| 2026-12-18 | Underserved Community | FALLBROOK | N/A | Not Available | 28 | 20 | N/A | 2025-02-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.08 | 0 | 196.69 | 12.08 | 184.61
| 2027-02-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.46 | 0 | 196.69 | 5.46 | 191.23
| 2027-02-10 | N/A | SANTEE | N/A | Not Available | 20 | 14 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.89 | 0 | 196.69 | 9.89 | 186.8
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 34 | 24 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -7.05 | Unknown | -1.65 | 0 | 207.92 | -8.7 | 216.62
| 2026-11-18 | Underserved Community | PAUMA VALLEY | N/A | Not Available | 50 | 36 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 44.85 | 0 | 1103.34 | 44.85 | 1058.49
| 2026-10-31 | Underserved Community | VISTA | N/A | Not Available | 20 | 14 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.8 | 0 | 196.44 | 5.8 | 190.64
| 2026-01-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | -1.88 | Unknown | 96.82 | 0 | 1066.55 | 94.94 | 971.61
| 2026-04-28 | N/A | LA JOLLA | N/A | Not Available | 14 | 10 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -8.76 | Unknown | -2.04 | 0 | 1050.61 | -10.8 | 1061.41
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.15 | 0 | 197.01 | 3.15 | 193.86
| 2027-03-26 | Underserved Community | LAGUNA HILLS | N/A | Not Available | 36 | 26 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.94 | 0 | 79.48 | 1.94 | 77.54
| 2026-04-17 | Underserved Community | CHULA VISTA | N/A | Not Available | 38 | 28 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.83 | 0 | 1049.43 | 5.83 | 1043.6
| 2026-09-18 | N/A | SOLANA BEACH | N/A | Not Available | 21 | 15 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.42 | 0 | 288.94 | 4.42 | 284.52
| 2026-09-16 | N/A | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.65 | 0 | 197.01 | 13.65 | 183.36
| 2026-01-17 | N/A | CARDIFF | N/A | Not Available | 39 | 27 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | -6.85 | Unknown | 0.47 | 0 | 202.87 | -6.38 | 209.25
| 2027-04-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 30 | 22 | N/A |  | Not Available | Not Available | Not Available | 359.31 | Unknown | 230.56 | 0 | 118.25 | 589.87 | -471.62
| 2027-03-26 | N/A | ENCINITAS | N/A | Not Available | 35 | 25 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2025-06-14 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 50 | 36 | N/A | 2023-11-13 | Not Available | Not Available | Not Available | -12.69 | Unknown | -4.08 | 0 | 514.57 | -16.77 | 531.34
| 2024-06-08 | N/A | DEL MAR | N/A | Not Available | 56 | 40 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -6.38 | Unknown | -1.48 | 0 | 202.87 | -7.86 | 210.73
| 2026-01-29 | Underserved Community | VISTA | N/A | Not Available | 56 | 40 | N/A | 2024-10-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.54 | 0 | 274.07 | 14.54 | 259.53
| 2026-08-02 | N/A | MISSION VIEJO | N/A | Not Available | 37 | 27 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | 153.28 | Unknown | 105.1 | 0 | 102.37 | 258.38 | -156.01
| 2027-07-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | -6.31 | Unknown | -2.4 | 0 | 496.45 | -8.71 | 505.16
| 2027-05-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 16 | 12 | N/A | 2025-06-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.25 | 0 | 85.73 | 6.25 | 79.48
| 2025-12-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2024-03-13 | Not Available | Not Available | Not Available | -17.33 | Unknown | -3.99 | 0 | 163.83 | -21.32 | 185.15
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 44 | 32 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -5.04 | Unknown | -1.19 | 0 | 231.47 | -6.23 | 237.7
| 2026-06-18 | Underserved Community | VISTA | N/A | Not Available | 56 | 40 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.88 | 0 | 288.94 | 6.88 | 282.06
| 2026-03-09 | N/A | ENCINITAS | N/A | Not Available | 34 | 24 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2026-11-04 | Underserved Community | FALLBROOK | N/A | Not Available | 21 | 15 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 144.47 | 0 | 144.47
| 2027-02-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | -7.84 | Unknown | 407.29 | 0 | 196.44 | 399.45 | -203.01
| 2027-02-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A |  | Not Available | Not Available | Not Available | 1814.46 | Unknown | 2785.77 | 0 | 450.11 | 4600.23 | -4150.12
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 14 | 10 | N/A | 2024-05-22 | Not Available | Not Available | Not Available | -6.52 | Unknown | -1.5 | 0 | 207.92 | -8.02 | 215.94
| 2027-05-20 | N/A | SAN DIEGO | N/A | Not Available | 25 | 19 | N/A | 2025-06-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 118.25 | 2.02 | 116.23
| 2026-11-07 | N/A | SOLANA BEACH | N/A | Not Available | 22 | 16 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 38.54 | 0 | 278.69 | 38.54 | 240.15
| 2026-03-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2024-04-23 | Not Available | Not Available | Not Available | -9.36 | Unknown | 152.87 | 0 | 534.57 | 143.51 | 391.06
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 30 | 22 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -5.25 | Unknown | -1.24 | 0 | 162.34 | -6.49 | 168.83
| 2025-05-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 38 | 28 | N/A | 2023-08-25 | Not Available | Not Available | Not Available | -8.69 | Unknown | -3.26 | 0 | 143.91 | -11.95 | 155.86
| 2027-02-26 | N/A | SAN DIEGO | N/A | Not Available | 18 | 14 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.1 | 0 | 278.5 | 13.1 | 265.4
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 30 | 22 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -5.83 | Unknown | -1.33 | 0 | 162.34 | -7.16 | 169.5
| 2027-05-27 | Underserved Community | VISTA | N/A | Not Available | 10 | 8 | N/A | 2025-06-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 118.25 | 2.02 | 116.23
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 27 | 19 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | 273.28 | Unknown | 185.98 | 0 | 207.92 | 459.26 | -251.34
| 2026-11-21 | Underserved Community | SANTEE | N/A | Not Available | 34 | 24 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.67 | 0 | 105.72 | 7.67 | 98.05
| 2026-11-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.97 | 0 | 184.29 | 2.97 | 181.32
| 2026-01-28 | Underserved Community | OCEANSIDE | N/A | Not Available | 42 | 30 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | -5.65 | Unknown | 292.57 | 0 | 144.22 | 286.92 | -142.7
| 2027-01-28 | N/A | JAMUL | N/A | Not Available | 25 | 19 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | -12.86 | Unknown | -6.99 | 0 | 196.69 | -19.85 | 216.54
| 2025-12-07 | N/A | ENCINITAS | N/A | Not Available | 65 | 47 | N/A | 2024-03-28 | Not Available | Not Available | Not Available | -7.38 | Unknown | -0.4 | 0 | 163.83 | -7.78 | 171.61
| 2026-10-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 3 | 3 | N/A |  | Not Available | Not Available | Not Available | 643.21 | Unknown | 376.02 | 0 | 1066.51 | 1019.23 | 47.28
| 2024-10-03 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 2 | 2 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -5.14 | Unknown | 5 | 0 | 153.22 | -0.14 | 153.36
| 2025-06-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 157 | 113 | N/A | 2024-02-01 | Not Available | Not Available | Not Available | -5.31 | Unknown | -1.25 | 0 | 465.36 | -6.56 | 471.92
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.31 | 0 | 197.01 | 8.31 | 188.7
| 2027-08-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.61 | 0 | 496.37 | -6.04 | 502.41
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 280 | 200 | N/A | 2024-05-20 | Not Available | Not Available | Not Available | -4.37 | Unknown | -1.09 | 0 | 153.83 | -5.46 | 159.29
| 2025-07-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 108 | 78 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -3.93 | Unknown | 1.34 | 0 | 149.82 | -2.59 | 152.41
| 2026-05-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 328 | 234 | N/A | 2025-03-28 | Not Available | Not Available | Not Available | -17.13 | Unknown | -0.68 | 0 | 529.2 | -17.81 | 547.01
| 2026-05-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -8.74 | Unknown | -1.4 | 0 | 1050.61 | -10.14 | 1060.75
| 2026-06-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 3 | 3 | N/A |  | Not Available | Not Available | Not Available | 5830.09 | Unknown | 16960.32 | 0 | 868.23 | 22790.41 | -21922.18
| 2025-01-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2023-08-03 | Not Available | Not Available | Not Available | -4.46 | Unknown | -0.53 | 0 | 153.83 | -4.99 | 158.82
| 2026-10-21 | N/A | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.2 | 0 | 196.69 | 8.2 | 188.49
| 2027-03-31 | Underserved Community | LAKESIDE | N/A | Not Available | 8 | 6 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.43 | 0 | 196.59 | 8.43 | 188.16
| 2027-02-12 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 84 | 60 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 124 | 88 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | 1006.78 | Unknown | 1253.55 | 0 | 163.83 | 2260.33 | -2096.5
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.82 | 0 | 197.01 | 4.82 | 192.19
| 2026-03-18 | N/A | RANCHO SANTA FE | N/A | Not Available | 1 | 1 | N/A | 2024-05-22 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.17 | 0 | 186.4 | -6.13 | 192.53
| 2025-06-07 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2023-09-06 | Not Available | Not Available | Not Available | -30.36 | Unknown | 1153.55 | 0 | 496.37 | 1123.19 | -626.82
| 2025-04-22 | N/A | CORONADO | N/A | Not Available | 93 | 67 | N/A | 2023-10-27 | Not Available | Not Available | Not Available | 185.02 | Unknown | 116.77 | 0 | 620.49 | 301.79 | 318.7
| 2026-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 88 | 62 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -21.41 | Unknown | -11.61 | 0 | 197.01 | -33.02 | 230.03
| 2026-10-28 | Underserved Community | ESCONDIDO | N/A | Not Available | 65 | 47 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.69 | 0 | 1103.3 | 12.69 | 1090.61
| 2026-11-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 155 | 111 | N/A | 2025-04-28 | Not Available | Not Available | Not Available | 485.25 | Unknown | 1538.48 | 0 | 288.94 | 2023.73 | -1734.79
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 262 | 188 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -6.2 | Unknown | -1.47 | 0 | 154.99 | -7.67 | 162.66
| 2027-02-24 | N/A | CHULA VISTA | N/A | Not Available | 101 | 73 | N/A |  | Not Available | Not Available | Not Available | 1847.22 | Unknown | 1165.23 | 0 | 196.44 | 3012.45 | -2816.01
| 2026-06-26 | Underserved Community | OCEANSIDE | N/A | Not Available | 81 | 57 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.46 | 0 | 282.95 | 3.46 | 279.49
| 2026-08-27 | N/A | LA JOLLA | N/A | Not Available | 225 | 161 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | -9.41 | Unknown | 1190.69 | 0 | 1225.92 | 1181.28 | 44.64
| 2026-04-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 76 | 54 | N/A | 2024-06-04 | Not Available | Not Available | Not Available | -11.83 | Unknown | -1.89 | 0 | 207.92 | -13.72 | 221.64
| 2025-11-12 | N/A | SAN DIEGO | N/A | Not Available | 7 | 5 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.35 | 0 | 1103.3 | 6.35 | 1096.95
| 2026-10-15 | N/A | RANCHO SANTA FE | N/A | Not Available | 49 | 35 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.28 | 0 | 279.3 | 8.28 | 271.02
| 2026-03-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 5 | 3 | N/A | 2025-03-28 | Not Available | Not Available | Not Available | -11.21 | Unknown | -6.1 | 0 | 196.59 | -17.31 | 213.9
| 2023-09-26 | Underserved Community | LA MESA | N/A | Not Available | 102 | 72 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.1 | 0 | 529.2 | 6.1 | 523.1
| 2025-06-30 | N/A | CHULA VISTA | N/A | Not Available | 106 | 76 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -5.31 | Unknown | 6.11 | 0 | 153.49 | 0.8 | 152.69
| 2025-07-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 103 | 75 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | -5.98 | Unknown | -1.94 | 0 | 496.37 | -7.92 | 504.29
| 2025-09-29 | N/A | CARLSBAD | N/A | Not Available | 111 | 79 | N/A | 2024-04-18 | Not Available | Not Available | Not Available | -5.83 | Unknown | -0.02 | 0 | 163.83 | -5.85 | 169.68
| 2024-10-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 4 | 2 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | 244.9 | Unknown | 149.06 | 0 | 514.57 | 393.96 | 120.61
| 2024-12-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2024-01-05 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.1 | 0 | 515.81 | -5.19 | 521
| 2025-11-16 | N/A | RANCHO SANTA FE | N/A | Not Available | 191 | 137 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.5 | 0 | 162.34 | 6.5 | 155.84
| 2025-06-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A | 2023-12-21 | Not Available | Not Available | Not Available | -5.43 | Unknown | -1.47 | 0 | 514.57 | -6.9 | 521.47
| 2027-02-11 | N/A | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2025-05-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 229 | 163 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -19.3 | Unknown | -4.47 | 0 | 158.51 | -23.77 | 182.28
| 2026-01-14 | N/A | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2024-06-11 | Not Available | Not Available | Not Available | -7.12 | Unknown | 0.09 | 0 | 163.83 | -7.03 | 170.86
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 220 | 158 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.59 | 0 | 163.83 | 4.59 | 159.24
| 2026-04-05 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 114 | 82 | N/A |  | Not Available | Not Available | Not Available | 843.32 | Unknown | 411.97 | 0 | 787.09 | 1255.29 | -468.2
| 2023-11-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 196 | 140 | N/A | 2023-06-23 | Not Available | Not Available | Not Available | -9.21 | Unknown | -3.49 | 0 | 351.99 | -12.7 | 364.69
| 2026-11-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.66 | 0 | 184.29 | 4.66 | 179.63
| 2027-03-13 | N/A | SAN DIEGO | N/A | Not Available | 26 | 18 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2024-11-01 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 119 | 85 | N/A | 2023-06-08 | Not Available | Not Available | Not Available | 364.98 | Unknown | 192.7 | 0 | 363.72 | 557.68 | -193.96
| 2025-03-24 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | 291.18 | Unknown | 148.99 | 0 | 479.76 | 440.17 | 39.59
| 2024-02-21 | Underserved Community | EL CAJON | N/A | Not Available | 127 | 91 | N/A | 2023-04-21 | Not Available | Not Available | Not Available | -19.66 | Unknown | -7.46 | 0 | 499.96 | -27.12 | 527.08
| 2024-01-25 | Underserved Community | EL CAJON | N/A | Not Available | 65 | 47 | N/A | 2023-05-17 | Not Available | Not Available | Not Available | -13.06 | Unknown | 8.61 | 0 | 499.96 | -4.45 | 504.41
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.02 | 0 | 197.01 | 16.02 | 180.99
| 2025-09-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 110 | 78 | N/A |  | Not Available | Not Available | Not Available | 252.46 | Unknown | 173.15 | 0 | 515.81 | 425.61 | 90.2
| 2024-02-15 | Underserved Community | LA MESA | N/A | Not Available | 77 | 55 | N/A | 2023-05-24 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.49 | 0 | 499.96 | -5.41 | 505.37
| 2025-03-24 | N/A | SAN DIEGO | N/A | Not Available | 89 | 65 | N/A | 2023-07-10 | Not Available | Not Available | Not Available | -7.22 | Unknown | -1.56 | 0 | 148.74 | -8.78 | 157.52
| 2025-01-18 | Underserved Community | OCEANSIDE | N/A | Not Available | 62 | 44 | N/A | 2023-05-05 | Not Available | Not Available | Not Available | -4.45 | Unknown | -1.68 | 0 | 154.79 | -6.13 | 160.92
| 2024-09-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 204 | 146 | N/A | 2023-04-21 | Not Available | Not Available | Not Available | -5.81 | Unknown | 2.86 | 0 | 98.41 | -2.95 | 101.36
| 2023-09-30 | Underserved Community | EL CAJON | N/A | Not Available | 117 | 83 | N/A | 2023-03-14 | Not Available | Not Available | Not Available | -7.67 | Unknown | -2.93 | 0 | 363.72 | -10.6 | 374.32
| 2025-11-18 | N/A | LA JOLLA | N/A | Not Available | 38 | 28 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.84 | 0 | 197.01 | 5.84 | 191.17
| 2027-03-23 | N/A | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-06-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.97 | 0 | 196.59 | 1.97 | 194.62
| 2025-02-15 | N/A | SAN MARCOS | N/A | Not Available | 175 | 125 | N/A | 2023-10-10 | Not Available | Not Available | Not Available | 364.33 | Unknown | 229.92 | 0 | 495.75 | 594.25 | -98.5
| 2023-12-13 | N/A | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2023-04-27 | Not Available | Not Available | Not Available | -4.1 | Unknown | -1.54 | 0 | 499.96 | -5.64 | 505.6
| 2024-12-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2023-04-18 | Not Available | Not Available | Not Available | -8.23 | Unknown | 2.95 | 0 | 98.66 | -5.28 | 103.94
| 2025-07-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 188 | 134 | N/A |  | Not Available | Not Available | Not Available | 367.35 | Unknown | 218.66 | 0 | 515.81 | 586.01 | -70.2
| 2027-02-18 | N/A | ENCINITAS | N/A | Not Available | 34 | 24 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | -2.19 | Unknown | 114 | 0 | 196.59 | 111.81 | 84.78
| 2025-07-21 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -3.59 | Unknown | 5.13 | 0 | 153.49 | 1.54 | 151.95
| 2026-06-12 | N/A | SAN DIEGO | N/A | Not Available | 162 | 116 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.72 | 0 | 192.95 | 5.72 | 187.23
| 2026-08-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 43 | 31 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.32 | 0 | 197.01 | 6.32 | 190.69
| 2026-11-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2025-01-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.15 | 0 | 197.01 | 7.15 | 189.86
| 2025-11-18 | N/A | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2025-02-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.14 | 0 | 197.01 | 9.14 | 187.87
| 2026-03-08 | N/A | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -8.1 | Unknown | -1.3 | 0 | 984.98 | -9.4 | 994.38
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 104 | 74 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 192.95 | 8.02 | 184.93
| 2025-06-29 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 112 | 80 | N/A | 2024-03-07 | Not Available | Not Available | Not Available | -15.45 | Unknown | 8.51 | 0 | 153.49 | -6.94 | 160.43
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.93 | 0 | 380.88 | 3.93 | 376.95
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.55 | 0 | 380.88 | 9.55 | 371.33
| 2025-06-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 25 | 17 | N/A | 2024-03-01 | Not Available | Not Available | Not Available | -5.12 | Unknown | -1.2 | 0 | 534.53 | -6.32 | 540.85
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 57 | 41 | N/A | 2024-09-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 192.95 | 4.01 | 188.94
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 155 | 111 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -8.17 | Unknown | -1.88 | 0 | 163.83 | -10.05 | 173.88
| 2026-08-28 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.44 | 0 | 197.01 | 10.44 | 186.57
| 2025-02-06 | N/A | SAN DIEGO | N/A | Not Available | 582 | 416 | N/A | 2023-08-16 | Not Available | Not Available | Not Available | -16.07 | Unknown | -4.92 | 0 | 148.62 | -20.99 | 169.61
| 2027-02-11 | Underserved Community | JULIAN | N/A | Not Available | 70 | 50 | N/A |  | Not Available | Not Available | Not Available | 1279.36 | Unknown | 575.17 | 0 | 183.76 | 1854.53 | -1670.77
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 133 | 95 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -7.02 | Unknown | -1.63 | 0 | 163.83 | -8.65 | 172.48
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 232 | 166 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.51 | 0 | 197.1 | 5.51 | 191.59
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 204 | 146 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | 264.24 | Unknown | 329.97 | 0 | 163.83 | 594.21 | -430.38
| 2024-06-20 | Underserved Community | LEMON GROVE | N/A | Not Available | 86 | 62 | N/A | 2023-12-08 | Not Available | Not Available | Not Available | -12.83 | Unknown | -2.51 | 0 | 158.14 | -15.34 | 173.48
| 2026-05-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 88 | 64 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | -9.16 | Unknown | 502.07 | 0 | 1049.43 | 492.91 | 556.52
| 2026-09-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 7 | 5 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.19 | 0 | 1066.51 | 7.19 | 1059.32
| 2025-09-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -6.58 | Unknown | -1.52 | 0 | 515.81 | -8.1 | 523.91
| 2025-10-03 | N/A | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2024-06-28 | Not Available | Not Available | Not Available | -6.2 | Unknown | 0.43 | 0 | 163.83 | -5.77 | 169.6
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 111 | 79 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | -7.38 | Unknown | -1.71 | 0 | 163.83 | -9.09 | 172.92
| 2026-08-26 | Underserved Community | CHULA VISTA | N/A | Not Available | 66 | 48 | N/A |  | Not Available | Not Available | Not Available | 287 | Unknown | 572.88 | 0 | 1066.51 | 859.88 | 206.63
| 2026-12-17 | N/A | RANCHO LA COSTA | N/A | Not Available | 24 | 18 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.6 | 0 | 196.44 | 3.6 | 192.84
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 155 | 111 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -14.29 | Unknown | -3.29 | 0 | 163.83 | -17.58 | 181.41
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 241 | 173 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.55 | 0 | 163.83 | 9.55 | 154.28
| 2026-02-12 | N/A | SOLANA BEACH | N/A | Not Available | 176 | 126 | N/A | 2024-09-09 | Not Available | Not Available | Not Available | 502.72 | Unknown | 345.03 | 0 | 163.83 | 847.75 | -683.92
| 2027-03-21 | N/A | DANA POINT | N/A | Not Available | 62 | 44 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2025-05-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 179 | 129 | N/A | 2024-04-10 | Not Available | Not Available | Not Available | -5.64 | Unknown | -1.31 | 0 | 534.53 | -6.95 | 541.48
| 2026-08-19 | N/A | SAN DIEGO | N/A | Not Available | 32 | 22 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.99 | 0 | 999.88 | 4.99 | 994.89
| 2026-04-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 248 | 178 | N/A |  | Not Available | Not Available | Not Available | 307.88 | Unknown | 211.09 | 0 | 117.46 | 518.97 | -401.51
| 2027-03-31 | Underserved Community | DANA POINT | N/A | Not Available | 57 | 41 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 239 | 171 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.4 | 0 | 163.83 | 5.4 | 158.43
| 2026-06-06 | Underserved Community | CHULA VISTA | N/A | Not Available | 67 | 47 | N/A |  | Not Available | Not Available | Not Available | 380.61 | Unknown | 235.63 | 0 | 192.95 | 616.24 | -423.29
| 2026-07-27 | N/A | SANTEE | N/A | Not Available | 68 | 50 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | -1.5 | Unknown | 89.61 | 0 | 197.01 | 88.11 | 108.9
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 248 | 178 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.12 | 0 | 163.83 | 5.12 | 158.71
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 80 | 58 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.3 | 0 | 192.95 | 7.3 | 185.65
| 2026-01-31 | N/A | CARLSBAD | N/A | Not Available | 146 | 104 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.23 | 0 | 192.95 | 5.23 | 187.72
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 63 | 45 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.06 | 0 | 192.95 | 6.06 | 186.89
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2024-12-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.2 | 0 | 380.88 | 5.2 | 375.68
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 153 | 109 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.9 | 0 | 380.88 | 9.9 | 370.98
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 90 | 64 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.95 | 0 | 192.95 | 4.95 | 188
| 2026-09-30 | N/A | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-11-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.19 | 0 | 197.01 | 6.19 | 190.82
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 111 | 79 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 721 | 515 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 0.04 | 0 | 143.91 | 0.04 | 143.87
| 2026-09-24 | Underserved Community | LAKESIDE | N/A | Not Available | 73 | 53 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.17 | 0 | 1066.51 | 6.17 | 1060.34
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 71 | 51 | N/A | 2024-04-02 | Not Available | Not Available | Not Available | -5.65 | Unknown | -1.31 | 0 | 163.83 | -6.96 | 170.79
| 2025-11-27 | Underserved Community | OCEANSIDE | N/A | Not Available | 215 | 153 | N/A | 2024-05-22 | Not Available | Not Available | Not Available | -9.1 | Unknown | -2.1 | 0 | 163.83 | -11.2 | 175.03
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.94 | 0 | 207.92 | -10.34 | 218.26
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 395 | 283 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 158.14 | 3.17 | 154.97
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 196 | 140 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.34 | 0 | 158.14 | -7.16 | 165.3
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 139 | 99 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.23 | 0 | 192.83 | 6.23 | 186.6
| 2026-02-01 | Underserved Community | ESCONDIDO | N/A | Not Available | 30 | 22 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.98 | 0 | 997.93 | 13.98 | 983.95
| 2025-10-04 | Underserved Community | EL CAJON | N/A | Not Available | 45 | 33 | N/A | 2024-10-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.31 | 0 | 197.01 | 9.31 | 187.7
| 2026-02-12 | Underserved Community | BONITA | N/A | Not Available | 138 | 98 | N/A |  | Not Available | Not Available | Not Available | 241.68 | Unknown | 174.77 | 0 | 186.09 | 416.45 | -230.36
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 146 | 104 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.27 | 0 | 555.11 | 9.27 | 545.84
| 2026-05-15 | Underserved Community | VISTA | N/A | Not Available | 53 | 39 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -4.9 | Unknown | -0.79 | 0 | 1050.61 | -5.69 | 1056.3
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 193 | 139 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.07 | 0 | 158.14 | -5.68 | 163.82
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 120 | 86 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | 506.8 | Unknown | 69.54 | 0 | 374 | 576.34 | -202.34
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 171 | 123 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.78 | 0 | 158.51 | -4.19 | 162.7
| 2025-10-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 133 | 95 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -4.2 | Unknown | 1.34 | 0 | 163.83 | -2.86 | 166.69
| 2027-03-14 | Underserved Community | CHULA VISTA | N/A | Not Available | 21 | 15 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | -40.9 | Unknown | 932.51 | 0 | 1063.64 | 891.61 | 172.03
| 2027-02-24 | Underserved Community | OCEANSIDE | N/A | Not Available | 59 | 43 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.8 | 0 | 196.59 | 2.8 | 193.79
| 2027-09-24 | Underserved Community | BONITA | N/A | Not Available | 11 | 7 | N/A |  | Not Available | Not Available | Not Available | 253.74 | Unknown | 176.71 | 0 | 190.44 | 430.45 | -240.01
| 2026-08-07 | N/A | ENCINITAS | N/A | Not Available | 62 | 44 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.23 | 0 | 192.95 | 7.23 | 185.72
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 234 | 168 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.21 | 0 | 163.83 | 6.21 | 157.62
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2026-08-08 | N/A | ENCINITAS | N/A | Not Available | 62 | 44 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.65 | 0 | 192.95 | 6.65 | 186.3
| 2026-07-02 | N/A | EL CAJON | N/A | Not Available | 44 | 32 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 180.5 | 4.29 | 176.21
| 2026-03-24 | N/A | CARLSBAD | N/A | Not Available | 17 | 13 | N/A | 2025-03-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.3 | 0 | 196.44 | 6.3 | 190.14
| 2025-12-11 | Underserved Community | OCEANSIDE | N/A | Not Available | 137 | 97 | N/A | 2024-04-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.99 | 0 | 534.53 | 4.99 | 529.54
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -3.07 | Unknown | -0.71 | 0 | 207.92 | -3.78 | 211.7
| 2025-06-06 | N/A | RANCHO SANTA FE | N/A | Not Available | 29 | 21 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -6.63 | Unknown | -1.05 | 0 | 1050.61 | -7.68 | 1058.29
| 2025-08-16 | N/A | ENCINITAS | N/A | Not Available | 147 | 105 | N/A | 2024-12-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.74 | 0 | 192.95 | 13.74 | 179.21
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 178 | 128 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2026-08-07 | N/A | ENCINITAS | N/A | Not Available | 97 | 69 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.45 | 0 | 533.07 | 3.45 | 529.62
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 99 | 71 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.46 | 0 | 192.83 | 4.46 | 188.37
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 210 | 150 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -14.66 | Unknown | -3.39 | 0 | 158.79 | -18.05 | 176.84
| 2025-09-06 | N/A | CARLSBAD | N/A | Not Available | 129 | 93 | N/A | 2024-01-26 | Not Available | Not Available | Not Available | -8.56 | Unknown | -2 | 0 | 158.79 | -10.56 | 169.35
| 2026-07-29 | Underserved Community | LAKESIDE | N/A | Not Available | 37 | 27 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.63 | 0 | 180.5 | 2.63 | 177.87
| 2024-07-03 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 73 | 53 | N/A | 2024-09-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.9 | 0 | 344.22 | 9.9 | 334.32
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 175 | 125 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.78 | 0 | 158.14 | -4.19 | 162.33
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2025-05-26 | N/A | CHULA VISTA | N/A | Not Available | 285 | 205 | N/A | 2024-02-07 | Not Available | Not Available | Not Available | -9.91 | Unknown | 0.98 | 0 | 158.37 | -8.93 | 167.3
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 463 | 331 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | 172.09 | Unknown | 235.85 | 0 | 153.83 | 407.94 | -254.11
| 2026-04-17 | Underserved Community | VISTA | N/A | Not Available | 57 | 41 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -7.03 | Unknown | -1.11 | 0 | 1050.61 | -8.14 | 1058.75
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -10.29 | Unknown | -2.39 | 0 | 158.14 | -12.68 | 170.82
| 2025-09-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 168 | 120 | N/A | 2024-03-12 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.17 | 0 | 515.81 | -6.12 | 521.93
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 136 | 98 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -13.01 | Unknown | -3.05 | 0 | 207.92 | -16.06 | 223.98
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 119 | 85 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.38 | 0 | 207.92 | -7.2 | 215.12
| 2024-08-01 | Underserved Community | JAMUL | N/A | Not Available | 374 | 268 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.69 | 0 | 158.14 | 2.69 | 155.45
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 142 | 102 | N/A | 2024-06-26 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.38 | 0 | 283.36 | -7.2 | 290.56
| 2026-04-22 | N/A | POWAY | N/A | Not Available | 79 | 57 | N/A | 2024-07-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.42 | 0 | 192.83 | 12.42 | 180.41
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 49 | 35 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 197.01 | 4.01 | 193
| 2024-07-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 36 | 26 | N/A | 2023-09-20 | Not Available | Not Available | Not Available | -4.1 | Unknown | -0.37 | 0 | 153.83 | -4.47 | 158.3
| 2026-06-28 | Underserved Community | EL CAJON | N/A | Not Available | 49 | 35 | N/A | 2024-08-19 | Not Available | Not Available | Not Available | -12.7 | Unknown | 638.96 | 0 | 1050.75 | 626.26 | 424.49
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 136 | 98 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -8.04 | Unknown | -1.84 | 0 | 207.92 | -9.88 | 217.8
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 309 | 221 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.96 | 0 | 153.83 | -10.36 | 164.19
| 2027-03-04 | Underserved Community | SANTEE | N/A | Not Available | 61 | 43 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.88 | 0 | 196.59 | 1.88 | 194.71
| 2025-11-15 | N/A | ENCINITAS | N/A | Not Available | 226 | 162 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | -7.66 | Unknown | 0.7 | 0 | 163.83 | -6.96 | 170.79
| 2025-12-26 | N/A | CARLSBAD | N/A | Not Available | 96 | 68 | N/A | 2024-03-15 | Not Available | Not Available | Not Available | -11.28 | Unknown | -2.6 | 0 | 163.83 | -13.88 | 177.71
| 2026-02-13 | N/A | LA JOLLA | N/A | Not Available | 70 | 50 | N/A | 2024-04-11 | Not Available | Not Available | Not Available | -5.38 | Unknown | -1.25 | 0 | 163.83 | -6.63 | 170.46
| 2024-05-23 | Underserved Community | LA MESA | N/A | Not Available | 127 | 91 | N/A | 2023-09-25 | Not Available | Not Available | Not Available | -9.51 | Unknown | -3.45 | 0 | 698.08 | -12.96 | 711.04
| 2026-10-09 | Underserved Community | LA JOLLA | N/A | Not Available | 43 | 31 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.57 | 0 | 197.01 | 4.57 | 192.44
| 2024-07-05 | Underserved Community | SPRING VALLEY | N/A | Not Available | 544 | 388 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.25 | 0 | 482.43 | 6.25 | 476.18
| 2026-09-17 | Underserved Community | LAKESIDE | N/A | Not Available | 58 | 42 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.67 | 0 | 197.01 | 4.67 | 192.34
| 2026-05-13 | Underserved Community | LAKESIDE | N/A | Not Available | 104 | 74 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.74 | 0 | 192.51 | 15.74 | 176.77
| 2024-06-08 | Underserved Community | LA MESA | N/A | Not Available | 149 | 107 | N/A | 2023-11-13 | Not Available | Not Available | Not Available | -8.13 | Unknown | -2.63 | 0 | 482.43 | -10.76 | 493.19
| 2024-10-06 | Underserved Community | CAPISTRANO BEACH | N/A | Not Available | 149 | 107 | N/A | 2024-01-16 | Not Available | Not Available | Not Available | -4.79 | Unknown | 380.01 | 0 | 513.31 | 375.22 | 138.09
| 2025-02-04 | Underserved Community | OCEANSIDE | N/A | Not Available | 136 | 98 | N/A | 2023-06-12 | Not Available | Not Available | Not Available | -14.8 | Unknown | -5.63 | 0 | 98.41 | -20.43 | 118.84
| 2024-05-29 | Underserved Community | LA MESA | N/A | Not Available | 119 | 85 | N/A | 2024-01-16 | Not Available | Not Available | Not Available | -5.29 | Unknown | -1.23 | 0 | 483.59 | -6.52 | 490.11
| 2024-06-29 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 99 | 71 | N/A | 2023-08-31 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.87 | 0 | 480.37 | -6.82 | 487.19
| 2023-07-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 52 | 38 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.12 | 0 | 1269.55 | -1.12 | 1270.67
| 2025-10-03 | Underserved Community | FALLBROOK | N/A | Not Available | 175 | 125 | N/A | 2024-02-23 | Not Available | Not Available | Not Available | -11.33 | Unknown | 0.57 | 0 | 163.83 | -10.76 | 174.59
| 2026-07-02 | Underserved Community | LAKESIDE | N/A | Not Available | 84 | 60 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.61 | 0 | 192.95 | 7.61 | 185.34
| 2025-03-14 | Underserved Community | ESCONDIDO | N/A | Not Available | 80 | 58 | N/A | 2023-05-26 | Not Available | Not Available | Not Available | -6.14 | Unknown | -2.35 | 0 | 464.78 | -8.49 | 473.27
| 2025-01-26 | N/A | ENCINITAS | N/A | Not Available | 495 | 355 | N/A | 2024-07-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.39 | 0 | 499.96 | 6.39 | 493.57
| 2025-01-31 | Underserved Community | VISTA | N/A | Not Available | 150 | 108 | N/A | 2023-04-25 | Not Available | Not Available | Not Available | -11.04 | Unknown | -4.19 | 0 | 98.66 | -15.23 | 113.89
| 2024-03-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 264 | 190 | N/A | 2023-08-15 | Not Available | Not Available | Not Available | -44.15 | Unknown | -16.83 | 0 | 103.82 | -60.98 | 164.8
| 2027-01-29 | N/A | DANA POINT | N/A | Not Available | 26 | 18 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.03 | 0 | 196.69 | 9.03 | 187.66
| 2024-09-15 | Underserved Community | FALLBROOK | N/A | Not Available | 155 | 111 | N/A | 2023-03-23 | Not Available | Not Available | Not Available | -4.74 | Unknown | -1.8 | 0 | 376.27 | -6.54 | 382.81
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | 131 | 95 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 26.43 | 0 | 197.01 | 26.43 | 170.58
| 2027-01-16 | N/A | CAPISTRANO BEACH | N/A | Not Available | 26 | 18 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 39.84 | 0 | 196.69 | 39.84 | 156.85
| 2024-09-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A | 2023-03-23 | Not Available | Not Available | Not Available | -6.48 | Unknown | 0.35 | 0 | 98.41 | -6.13 | 104.54
| 2024-03-20 | N/A | CARLSBAD | N/A | Not Available | 165 | 119 | N/A | 2023-05-19 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.89 | 0 | 154.79 | -6.85 | 161.64
| 2026-11-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 47 | 35 | N/A | 2024-12-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.15 | 0 | 1066.55 | 6.15 | 1060.4
| 2023-12-20 | Underserved Community | VISTA | N/A | Not Available | 163 | 117 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -8.17 | Unknown | -3.11 | 0 | 363.72 | -11.28 | 375
| 2024-11-14 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A | 2023-03-31 | Not Available | Not Available | Not Available | -2.55 | Unknown | 685.51 | 0 | 532.88 | 682.96 | -150.08
| 2025-02-10 | Underserved Community | VISTA | N/A | Not Available | 143 | 103 | N/A | 2023-05-12 | Not Available | Not Available | Not Available | -3.3 | Unknown | -1.26 | 0 | 364.52 | -4.56 | 369.08
| 2025-01-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 159 | 113 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -12.87 | Unknown | -4.89 | 0 | 98.41 | -17.76 | 116.17
| 2023-11-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 83 | 59 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | -7.03 | Unknown | -0.1 | 0 | 98.41 | -7.13 | 105.54
| 2023-12-20 | N/A | LAGUNA HILLS | N/A | Not Available | 15 | 11 | N/A | 2023-02-28 | Not Available | Not Available | Not Available | -9.91 | Unknown | -3.76 | 0 | 98.41 | -13.67 | 112.08
| 2024-12-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2023-04-26 | Not Available | Not Available | Not Available | -5.89 | Unknown | -2.26 | 0 | 363.72 | -8.15 | 371.87
| 2025-01-10 | Underserved Community | CHULA VISTA | N/A | Not Available | 358 | 256 | N/A | 2024-03-22 | Not Available | Not Available | Not Available | -3.92 | Unknown | -0.92 | 0 | 495.75 | -4.84 | 500.59
| 2024-10-21 | Underserved Community | ESCONDIDO | N/A | Not Available | 117 | 83 | N/A | 2023-03-16 | Not Available | Not Available | Not Available | -6.68 | Unknown | -2.54 | 0 | 376.27 | -9.22 | 385.49
| 2024-10-18 | Underserved Community | VISTA | N/A | Not Available | 144 | 102 | N/A | 2023-02-06 | Not Available | Not Available | Not Available | -11.29 | Unknown | -4.3 | 0 | 363.72 | -15.59 | 379.31
| 2025-02-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 109 | 79 | N/A | 2023-05-04 | Not Available | Not Available | Not Available | -6.54 | Unknown | -2.48 | 0 | 153.75 | -9.02 | 162.77
| 2024-01-24 | N/A | LADERA RANCH | N/A | Not Available | 41 | 29 | N/A | 2023-02-28 | Not Available | Not Available | Not Available | -29.54 | Unknown | -11.24 | 0 | 67.06 | -40.78 | 107.84
| 2024-11-30 | N/A | MISSION VIEJO | N/A | Not Available | 10 | 8 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | 208.36 | Unknown | 148.4 | 0 | 76.18 | 356.76 | -280.58
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | 100 | 72 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | -26.98 | Unknown | -1390.28 | 0 | 197.01 | -1417.26 | 1614.27
| 2024-03-10 | Underserved Community | LAKESIDE | N/A | Not Available | 74 | 54 | N/A | 2023-08-01 | Not Available | Not Available | Not Available | -4.79 | Unknown | -0.65 | 0 | 153.75 | -5.44 | 159.19
| 2025-02-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 109 | 79 | N/A | 2023-03-06 | Not Available | Not Available | Not Available | -7.26 | Unknown | -2.75 | 0 | 98.41 | -10.01 | 108.42
| 2024-04-18 | N/A | LA JOLLA | N/A | Not Available | 117 | 83 | N/A | 2023-12-18 | Not Available | Not Available | Not Available | -14.97 | Unknown | -16.8 | 0 | 1447.41 | -31.77 | 1479.18
| 2025-02-05 | N/A | SAN CLEMENTE | N/A | Not Available | 113 | 81 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -8.68 | Unknown | -2.01 | 0 | 534.53 | -10.69 | 545.22
| 2025-01-31 | N/A | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2023-09-11 | Not Available | Not Available | Not Available | -7.72 | Unknown | -2.8 | 0 | 153.83 | -10.52 | 164.35
| 2024-10-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 150 | 108 | N/A | 2023-03-15 | Not Available | Not Available | Not Available | -5.71 | Unknown | 0.22 | 0 | 98.41 | -5.49 | 103.9
| 2027-03-14 | N/A | SAN CLEMENTE | N/A | Not Available | 17 | 13 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.1 | 0 | 76.04 | 6.1 | 69.94
| 2024-06-14 | Underserved Community | LEMON GROVE | N/A | Not Available | 45 | 33 | N/A | 2023-09-20 | Not Available | Not Available | Not Available | -9.89 | Unknown | -3.61 | 0 | 496.37 | -13.5 | 509.87
| 2026-08-29 | N/A | SAN CLEMENTE | N/A | Not Available | 17 | 13 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3152.39 | 0 | 197.01 | 3152.39 | -2955.38
| 2025-07-06 | N/A | LAGUNA HILLS | N/A | Not Available | 169 | 121 | N/A | 2023-09-05 | Not Available | Not Available | Not Available | -10.75 | Unknown | -3.53 | 0 | 143.91 | -14.28 | 158.19
| 2026-08-13 | N/A | COTO DE CAZA | N/A | Not Available | 49 | 35 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.76 | 0 | 74.22 | 7.76 | 66.46
| 2026-08-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 119 | 85 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | -10.15 | Unknown | 506.82 | 0 | 1066.51 | 496.67 | 569.84
| 2026-08-08 | N/A | LAGUNA NIGUEL | N/A | Not Available | 37 | 27 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.64 | 0 | 192.95 | 5.64 | 187.31
| 2025-05-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 82 | 58 | N/A | 2023-09-25 | Not Available | Not Available | Not Available | -5.12 | Unknown | -1.86 | 0 | 372.29 | -6.98 | 379.27
| 2027-04-20 | Underserved Community | SANTEE | N/A | Not Available | 14 | 10 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2027-02-11 | N/A | DANA POINT | N/A | Not Available | 53 | 37 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2025-04-10 | N/A | LAGUNA NIGUEL | N/A | Not Available | 39 | 29 | N/A | 2024-07-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 19.85 | 0 | 180.09 | 19.85 | 160.24
| 2026-08-13 | N/A | SAN CLEMENTE | N/A | Not Available | 51 | 37 | N/A | 2024-10-01 | Not Available | Not Available | Not Available | 3327.2 | Unknown | 2283.58 | 0 | 999.88 | 5610.78 | -4610.9
| 2027-03-26 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 23 | 17 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.92 | 0 | 196.38 | 2.92 | 193.46
| 2025-07-08 | Underserved Community | DANA POINT | N/A | Not Available | 63 | 45 | N/A | 2024-08-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.44 | 0 | 1050.75 | 4.44 | 1046.31
| 2024-12-27 | Underserved Community | DANA POINT | N/A | Not Available | 36 | 26 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -11.96 | Unknown | 191.69 | 0 | 534.53 | 179.73 | 354.8
| 2025-05-28 | N/A | LAGUNA NIGUEL | N/A | Not Available | 64 | 46 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.86 | 0 | 180.09 | 6.86 | 173.23
| 2027-03-04 | Underserved Community | LAGUNA HILLS | N/A | Not Available | 18 | 14 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | -16.48 | Unknown | -8.98 | 0 | 196.44 | -25.46 | 221.9
| 2027-04-20 | Underserved Community | SANTEE | N/A | Not Available | 14 | 10 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.94 | 0 | 118.25 | 3.94 | 114.31
| 2026-08-19 | N/A | SAN CLEMENTE | N/A | Not Available | 57 | 41 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.79 | 0 | 192.95 | 7.79 | 185.16
| 2025-09-03 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 133 | 95 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.06 | 0 | 105.08 | 11.06 | 94.02
| 2026-12-03 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 70 | 50 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.49 | 0 | 197.01 | 6.49 | 190.52
| 2025-05-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -11.69 | Unknown | -4.24 | 0 | 465.36 | -15.93 | 481.29
| 2024-11-16 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 224 | 160 | N/A |  | Not Available | Not Available | Not Available | -12.17 | Unknown | 1417.41 | 0 | 264.34 | 1405.24 | -1140.9
| 2023-12-30 | Underserved Community | VISTA | N/A | Not Available | 152 | 108 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | -6.83 | Unknown | -2.59 | 0 | 363.72 | -9.42 | 373.14
| 2026-09-11 | N/A | COTO DE CAZA | N/A | Not Available | 57 | 41 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.7 | 0 | 105.08 | 16.7 | 88.38
| 2025-04-04 | N/A | SAN DIEGO | N/A | Not Available | 149 | 107 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -5.15 | Unknown | -1.98 | 0 | 153.75 | -7.13 | 160.88
| 2025-04-07 | N/A | LA JOLLA | N/A | Not Available | 22 | 16 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | -9.94 | Unknown | -3.79 | 0 | 495.75 | -13.73 | 509.48
| 2027-03-27 | N/A | DEL MAR | N/A | Not Available | 50 | 36 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.92 | 0 | 178.33 | 1.92 | 176.41
| 2025-02-24 | N/A | DANA POINT | N/A | Not Available | 86 | 62 | N/A | 2024-08-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.14 | 0 | 180.38 | 4.14 | 176.24
| 2024-01-02 | N/A | MISSION VIEJO | N/A | Not Available | 179 | 129 | N/A | 2023-05-03 | Not Available | Not Available | Not Available | -13.25 | Unknown | -5.01 | 0 | 67.06 | -18.26 | 85.32
| 2024-09-19 | N/A | ENCINITAS | N/A | Not Available | 23 | 17 | N/A | 2023-10-16 | Not Available | Not Available | Not Available | -9.56 | Unknown | -1.98 | 0 | 198.18 | -11.54 | 209.72
| 2025-05-08 | N/A | MISSION VIEJO | N/A | Not Available | 49 | 35 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.23 | 0 | 180.5 | 13.23 | 167.27
| 2024-10-24 | Underserved Community | OCEANSIDE | N/A | Not Available | 143 | 101 | N/A | 2023-02-06 | Not Available | Not Available | Not Available | -4.42 | Unknown | -1.67 | 0 | 363.72 | -6.09 | 369.81
| 2026-08-12 | N/A | DANA POINT | N/A | Not Available | 58 | 42 | N/A | 2024-10-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.64 | 0 | 180.5 | 7.64 | 172.86
| 2025-02-06 | N/A | SAN DIEGO | N/A | Not Available | 346 | 248 | N/A | 2024-02-27 | Not Available | Not Available | Not Available | -10.22 | Unknown | -1.2 | 0 | 154.79 | -11.42 | 166.21
| 2025-01-25 | Underserved Community | CHULA VISTA | N/A | Not Available | 70 | 50 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | -5.65 | Unknown | 1.7 | 0 | 154.79 | -3.95 | 158.74
| 2025-01-27 | N/A | SOLANA BEACH | N/A | Not Available | 106 | 76 | N/A | 2023-09-19 | Not Available | Not Available | Not Available | -9.85 | Unknown | -3.72 | 0 | 479.76 | -13.57 | 493.33
| 2025-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A | 2023-08-23 | Not Available | Not Available | Not Available | -8.47 | Unknown | -3.21 | 0 | 465.44 | -11.68 | 477.12
| 2027-02-04 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | -17.11 | Unknown | -9.29 | 0 | 196.69 | -26.4 | 223.09
| 2024-06-05 | Underserved Community | VISTA | N/A | Not Available | 24 | 18 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -5.14 | Unknown | -1.38 | 0 | 203.23 | -6.52 | 209.75
| 2026-10-31 | N/A | ENCINITAS | N/A | Not Available | 30 | 22 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.12 | 0 | 279.3 | 9.12 | 270.18
| 2025-10-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 39 | 29 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | -21.84 | Unknown | 46.4 | 0 | 43.07 | 24.56 | 18.51
| 2026-01-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.43 | 0 | 196.69 | 5.43 | 191.26
| 2024-06-08 | N/A | DEL MAR | N/A | Not Available | 32 | 22 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -11.14 | Unknown | -3.6 | 0 | 202.37 | -14.74 | 217.11
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 29 | 21 | N/A | 2024-04-02 | Not Available | Not Available | Not Available | -5.48 | Unknown | -1.27 | 0 | 163.83 | -6.75 | 170.58
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 44 | 32 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -5.83 | Unknown | -1.37 | 0 | 150.74 | -7.2 | 157.94
| 2026-09-13 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-11-05 | Not Available | Not Available | Not Available | -1.5 | Unknown | 85.15 | 0 | 197.01 | 83.65 | 113.36
| 2025-09-29 | Underserved Community | ESCONDIDO | N/A | Not Available | 32 | 24 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.43 | 0 | 515.81 | -0.43 | 516.24
| 2025-04-03 | Underserved Community | CHULA VISTA | N/A | Not Available | 56 | 40 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -29.15 | Unknown | 1153.9 | 0 | 496.45 | 1124.75 | -628.3
| 2026-11-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.31 | 0 | 184.29 | 7.31 | 176.98
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 19 | 13 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.08 | 0 | 1066.55 | 15.08 | 1051.47
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 43 | 31 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -10.8 | Unknown | -2.48 | 0 | 207.92 | -13.28 | 221.2
| 2026-06-07 | N/A | CARLSBAD | N/A | Not Available | 28 | 20 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -7.82 | Unknown | -1.27 | 0 | 192.51 | -9.09 | 201.6
| 2027-04-03 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 44 | 32 | N/A |  | Not Available | Not Available | Not Available | -27.13 | Unknown | 1341.65 | 0 | 337.59 | 1314.52 | -976.93
| 2026-01-29 | N/A | CARLSBAD | N/A | Not Available | 19 | 13 | N/A | 2024-04-03 | Not Available | Not Available | Not Available | -9.91 | Unknown | -2.3 | 0 | 163.83 | -12.21 | 176.04
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 15 | 11 | N/A | 2024-05-22 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.94 | 0 | 207.92 | -10.34 | 218.26
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 47 | 33 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 150.74 | -4.06 | 154.8
| 2026-06-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 50 | 36 | N/A | 2024-07-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.48 | 0 | 282.95 | 4.48 | 278.47
| 2026-12-20 | Underserved Community | VISTA | N/A | Not Available | 38 | 28 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.78 | 0 | 196.69 | 6.78 | 189.91
| 2024-04-20 | N/A | OCEANSIDE | N/A | Not Available | 29 | 21 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -5.31 | Unknown | -2.05 | 0 | 153.87 | -7.36 | 161.23
| 2026-08-14 | Underserved Community | SAN MARCOS | N/A | Not Available | 22 | 16 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.63 | 0 | 192.95 | 7.63 | 185.32
| 2026-10-07 | N/A | ENCINITAS | N/A | Not Available | 23 | 17 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | -14.53 | Unknown | -7.92 | 0 | 196.44 | -22.45 | 218.89
| 2026-01-20 | N/A | SAN DIEGO | N/A | Not Available | 53 | 37 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.64 | 0 | 192.83 | 10.64 | 182.19
| 2026-05-07 | Underserved Community | VISTA | N/A | Not Available | 28 | 20 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -5.47 | Unknown | 0.63 | 0 | 192.83 | -4.84 | 197.67
| 2025-07-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1.36 | 0 | 496.37 | -5.1 | 501.47
| 2025-11-08 | N/A | CARDIFF | N/A | Not Available | 50 | 36 | N/A | 2023-12-27 | Not Available | Not Available | Not Available | -5.78 | Unknown | -1.9 | 0 | 496.75 | -7.68 | 504.43
| 2026-11-18 | N/A | SAN DIEGO | N/A | Not Available | 16 | 12 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.22 | 0 | 197.01 | 4.22 | 192.79
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 45 | 33 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 0 | 192.95 | 5.69 | 187.26
| 2027-05-19 | N/A | LAGUNA NIGUEL | N/A | Not Available | 18 | 12 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 79.48 | 2.02 | 77.46
| 2026-01-02 | N/A | SAN DIEGO | N/A | Not Available | 17 | 13 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.22 | 0 | 197.01 | 10.22 | 186.79
| 2025-07-11 | N/A | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2024-02-02 | Not Available | Not Available | Not Available | -6.92 | Unknown | -1.62 | 0 | 534.53 | -8.54 | 543.07
| 2026-01-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 196.69 | 4.39 | 192.3
| 2026-10-07 | N/A | ENCINITAS | N/A | Not Available | 50 | 36 | N/A | 2024-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.54 | 0 | 288.94 | 10.54 | 278.4
| 2026-01-14 | N/A | SAN DIEGO | N/A | Not Available | 10 | 8 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.97 | 0 | 196.69 | 8.97 | 187.72
| 2027-04-01 | N/A | DEL MAR | N/A | Not Available | 35 | 25 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | 1637.54 | Unknown | 1512.75 | 0 | 151.78 | 3150.29 | -2998.51
| 2024-07-11 | Underserved Community | EL CAJON | N/A | Not Available | 16 | 12 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -17.98 | Unknown | 19.19 | 0 | 816.58 | 1.21 | 815.37
| 2026-06-10 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2024-08-16 | Not Available | Not Available | Not Available | 375.47 | Unknown | 337.5 | 0 | 192.95 | 712.97 | -520.02
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 15 | 11 | N/A | 2024-05-23 | Not Available | Not Available | Not Available | -9.27 | Unknown | -2.13 | 0 | 207.92 | -11.4 | 219.32
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 34 | 24 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -9.68 | Unknown | -2.22 | 0 | 207.92 | -11.9 | 219.82
| 2026-12-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 31 | 23 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 23.2 | 0 | 196.69 | 23.2 | 173.49
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 43 | 31 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 207.92 | -4.06 | 211.98
| 2026-03-25 | N/A | ENCINITAS | N/A | Not Available | 42 | 30 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -8.5 | Unknown | -1.34 | 0 | 273.91 | -9.84 | 283.75
| 2025-04-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2023-08-25 | Not Available | Not Available | Not Available | 189.35 | Unknown | 120.26 | 0 | 153.83 | 309.61 | -155.78
| 2026-10-11 | Underserved Community | VISTA | N/A | Not Available | 48 | 34 | N/A | 2024-11-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.74 | 0 | 288.94 | 4.74 | 284.2
| 2026-10-14 | Underserved Community | CHULA VISTA | N/A | Not Available | 22 | 16 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.19 | 0 | 190.44 | -0.19 | 190.63
| 2026-12-11 | Underserved Community | EL CAJON | N/A | Not Available | 61 | 43 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.5 | 0 | 105.72 | 8.5 | 97.22
| 2024-07-13 | Underserved Community | VISTA | N/A | Not Available | 15 | 11 | N/A | 2023-07-17 | Not Available | Not Available | Not Available | -16.04 | Unknown | -6.11 | 0 | 143.95 | -22.15 | 166.1
| 2026-01-28 | N/A | RANCHO SANTA FE | N/A | Not Available | 2 | 2 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.34 | 0 | 196.69 | 9.34 | 187.35
| 2025-05-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2023-11-06 | Not Available | Not Available | Not Available | -6.23 | Unknown | -1.97 | 0 | 496.37 | -8.2 | 504.57
| 2026-04-21 | N/A | OCEANSIDE | N/A | Not Available | 70 | 50 | N/A | 2024-09-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.72 | 0 | 192.51 | 7.72 | 184.79
| 2025-10-28 | N/A | ENCINITAS | N/A | Not Available | 2 | 2 | N/A | 2024-10-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.88 | 0 | 301.34 | 10.88 | 290.46
| 2025-07-20 | Underserved Community | POWAY | N/A | Not Available | 192 | 138 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -14.91 | Unknown | -3.47 | 0 | 483.59 | -18.38 | 501.97
| 2026-03-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-04-08 | Not Available | Not Available | Not Available | -5.81 | Unknown | -1.33 | 0 | 534.53 | -7.14 | 541.67
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 49 | 35 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -8.94 | Unknown | 0.12 | 0 | 207.92 | -8.82 | 216.74
| 2025-01-14 | N/A | ENCINITAS | N/A | Not Available | 94 | 68 | N/A | 2023-06-06 | Not Available | Not Available | Not Available | -10.04 | Unknown | -3.82 | 0 | 98.66 | -13.86 | 112.52
| 2025-02-12 | N/A | SAN MARCOS | N/A | Not Available | 121 | 87 | N/A | 2023-02-16 | Not Available | Not Available | Not Available | -10.09 | Unknown | -3.85 | 0 | 92.06 | -13.94 | 106
| 2025-01-26 | N/A | ENCINITAS | N/A | Not Available | 28 | 20 | N/A | 2023-06-12 | Not Available | Not Available | Not Available | -9.37 | Unknown | -3.53 | 0 | 495.75 | -12.9 | 508.65
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 216 | 154 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.46 | 0 | 163.83 | 8.46 | 155.37
| 2026-12-04 | N/A | LAGUNA HILLS | N/A | Not Available | 21 | 15 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.57 | 0 | 197.01 | 7.57 | 189.44
| 2025-02-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 435 | 311 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -3.97 | Unknown | -0.94 | 0 | 625.02 | -4.91 | 629.93
| 2027-04-14 | N/A | SAN DIEGO | N/A | Not Available | 332 | 238 | N/A | 2023-04-19 | Not Available | Not Available | Not Available | -4.25 | Unknown | -0.12 | 0 | 154.79 | -4.37 | 159.16
| 2023-11-15 | N/A | CARLSBAD | N/A | Not Available | 161 | 115 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -6.13 | Unknown | -2.35 | 0 | 98.41 | -8.48 | 106.89
| 2026-01-29 | N/A | SAN DIEGO | N/A | Not Available | 26 | 20 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 24.22 | 0 | 196.69 | 24.22 | 172.47
| 2026-11-12 | Underserved Community | LAKESIDE | N/A | Not Available | 18 | 14 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.86 | 0 | 197.01 | 6.86 | 190.15
| 2024-12-09 | N/A | SAN DIEGO | N/A | Not Available | 138 | 98 | N/A | 2023-03-30 | Not Available | Not Available | Not Available | -7.58 | Unknown | -2.88 | 0 | 98.66 | -10.46 | 109.12
| 2024-01-03 | Underserved Community | VISTA | N/A | Not Available | 97 | 69 | N/A | 2023-06-06 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.49 | 0 | 363.72 | -5.41 | 369.13
| 2024-11-28 | Underserved Community | OCEANSIDE | N/A | Not Available | 160 | 114 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -8.29 | Unknown | -3.14 | 0 | 363.72 | -11.43 | 375.15
| 2024-02-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 142 | 102 | N/A | 2023-05-23 | Not Available | Not Available | Not Available | -6.85 | Unknown | -2.59 | 0 | 95.13 | -9.44 | 104.57
| 2025-08-23 | Underserved Community | LAKESIDE | N/A | Not Available | 59 | 43 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.02 | 0 | 197.01 | 18.02 | 178.99
| 2025-03-07 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | -14.48 | Unknown | -5.49 | 0 | 495.75 | -19.97 | 515.72
| 2026-01-06 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 8 | 6 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.34 | 0 | 104.94 | 6.34 | 98.6
| 2024-09-09 | Underserved Community | FALLBROOK | N/A | Not Available | 420 | 300 | N/A | 2024-03-20 | Not Available | Not Available | Not Available | -14 | Unknown | -3.26 | 0 | 376.27 | -17.26 | 393.53
| 2025-02-22 | N/A | RANCHO SANTA FE | N/A | Not Available | 110 | 78 | N/A | 2023-02-27 | Not Available | Not Available | Not Available | -8.57 | Unknown | -3.26 | 0 | 95.13 | -11.83 | 106.96
| 2024-12-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2023-04-18 | Not Available | Not Available | Not Available | -5.07 | Unknown | -1.93 | 0 | 364.52 | -7 | 371.52
| 2025-01-22 | N/A | ENCINITAS | N/A | Not Available | 70 | 50 | N/A | 2023-04-03 | Not Available | Not Available | Not Available | -9.05 | Unknown | -3.43 | 0 | 98.66 | -12.48 | 111.14
| 2026-09-19 | N/A | ENCINITAS | N/A | Not Available | 124 | 90 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.94 | 0 | 999.91 | 6.94 | 992.97
| 2026-10-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 115 | 83 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | -1.88 | Unknown | 188.28 | 0 | 1066.51 | 186.4 | 880.11
| 2025-01-19 | Underserved Community | OCEANSIDE | N/A | Not Available | 140 | 100 | N/A | 2023-03-31 | Not Available | Not Available | Not Available | -5.84 | Unknown | -2.23 | 0 | 98.66 | -8.07 | 106.73
| 2025-08-23 | Underserved Community | LAKESIDE | N/A | Not Available | 58 | 42 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | 82.69 | Unknown | 80.51 | 0 | 197.01 | 163.2 | 33.81
| 2025-04-05 | Underserved Community | VISTA | N/A | Not Available | 118 | 84 | N/A | 2023-04-25 | Not Available | Not Available | Not Available | -4.96 | Unknown | 3.26 | 0 | 871.59 | -1.7 | 873.29
| 2024-11-15 | N/A | CARLSBAD | N/A | Not Available | 162 | 116 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -6.45 | Unknown | -2.45 | 0 | 92.06 | -8.9 | 100.96
| 2024-02-21 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 326 | 232 | N/A | 2023-07-13 | Not Available | Not Available | Not Available | -9.44 | Unknown | -3.6 | 0 | 111.67 | -13.04 | 124.71
| 2025-01-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 139 | 99 | N/A | 2023-03-30 | Not Available | Not Available | Not Available | -9.9 | Unknown | -3.76 | 0 | 364.52 | -13.66 | 378.18
| 2024-02-10 | N/A | LAGUNA HILLS | N/A | Not Available | 119 | 85 | N/A | 2023-04-13 | Not Available | Not Available | Not Available | -9.43 | Unknown | -3.59 | 0 | 111.67 | -13.02 | 124.69
| 2025-02-14 | Underserved Community | VISTA | N/A | Not Available | 86 | 62 | N/A | 2023-02-17 | Not Available | Not Available | Not Available | -5.83 | Unknown | -2.22 | 0 | 242.5 | -8.05 | 250.55
| 2024-10-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 116 | 82 | N/A | 2023-04-24 | Not Available | Not Available | Not Available | -12.6 | Unknown | 256.43 | 0 | 464.78 | 243.83 | 220.95
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 46 | 34 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | -11.69 | Unknown | 597.11 | 0 | 860.83 | 585.42 | 275.41
| 2024-07-12 | Underserved Community | ALPINE | N/A | Not Available | 376 | 268 | N/A | 2024-12-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 40.16 | 0 | 1176.65 | 40.16 | 1136.49
| 2023-12-06 | N/A | SAN DIEGO | N/A | Not Available | 137 | 97 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -6.78 | Unknown | -2.59 | 0 | 98.41 | -9.37 | 107.78
| 2026-03-13 | N/A | SAN CLEMENTE | N/A | Not Available | 54 | 38 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -5.73 | Unknown | -1.37 | 0 | 84.66 | -7.1 | 91.76
| 2027-02-14 | Underserved Community | MISSION VIEJO | N/A | Not Available | 37 | 27 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.05 | 0 | 196.44 | 4.05 | 192.39
| 2024-01-05 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 385 | 275 | N/A | 2024-08-20 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.6 | 0 | Unknown | -0.6 | Unknown
| 2023-12-12 | Underserved Community | LA MESA | N/A | Not Available | 189 | 135 | N/A | 2023-07-31 | Not Available | Not Available | Not Available | -10.26 | Unknown | -3.9 | 0 | 363.72 | -14.16 | 377.88
| 2024-04-13 | Underserved Community | OCEANSIDE | N/A | Not Available | 23 | 17 | N/A | 2023-10-10 | Not Available | Not Available | Not Available | -7.03 | Unknown | -1.38 | 0 | 154.99 | -8.41 | 163.4
| 2024-03-10 | N/A | CARLSBAD | N/A | Not Available | 63 | 45 | N/A |  | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.83 | 0 | 143.83 | -6.62 | 150.45
| 2024-10-12 | N/A | SAN CLEMENTE | N/A | Not Available | 92 | 66 | N/A | 2023-11-17 | Not Available | Not Available | Not Available | -5.97 | Unknown | -1.95 | 0 | 147.93 | -7.92 | 155.85
| 2024-09-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 151 | 107 | N/A | 2023-04-24 | Not Available | Not Available | Not Available | -9.49 | Unknown | 3.42 | 0 | 98.41 | -6.07 | 104.48
| 2024-03-03 | N/A | CARLSBAD | N/A | Not Available | 548 | 392 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | 0 | 153.75
| 2024-11-30 | N/A | MISSION VIEJO | N/A | Not Available | 7 | 5 | N/A | 2024-12-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.1 | 0 | 184.29 | 13.1 | 171.19
| 2025-06-07 | N/A | SAN CLEMENTE | N/A | Not Available | 18 | 12 | N/A | 2024-07-30 | Not Available | Not Available | Not Available | 144.08 | Unknown | 101.76 | 0 | 74 | 245.84 | -171.84
| 2025-02-24 | Underserved Community | ESCONDIDO | N/A | Not Available | 256 | 182 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | -20.1 | Unknown | -5.4 | 0 | 40.01 | -25.5 | 65.51
| 2025-06-01 | Underserved Community | ESCONDIDO | N/A | Not Available | 35 | 25 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | -4.27 | Unknown | -1.6 | 0 | 40.04 | -5.87 | 45.91
| 2025-05-10 | Underserved Community | FALLBROOK | N/A | Not Available | 41 | 29 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -8.07 | Unknown | -3.05 | 0 | 595.76 | -11.12 | 606.88
| 2027-01-02 | N/A | SAN CLEMENTE | N/A | Not Available | 24 | 18 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 17.07 | 0 | 196.69 | 17.07 | 179.62
| 2025-02-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | -7.15 | Unknown | -2.72 | 0 | 153.75 | -9.87 | 163.62
| 2025-02-24 | N/A | POWAY | N/A | Not Available | 80 | 57 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | -4.63 | Unknown | -1.75 | 0 | 154.79 | -6.38 | 161.17
| 2025-04-05 | N/A | SAN CLEMENTE | N/A | Not Available | 49 | 35 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -5.83 | Unknown | -0.92 | 0 | 180.38 | -6.75 | 187.13
| 2024-12-31 | Underserved Community | LAGUNA HILLS | N/A | Not Available | 42 | 30 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.18 | 0 | 105.08 | 12.18 | 92.9
| 2027-04-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 118 | 84 | N/A | 2023-05-08 | Not Available | Not Available | Not Available | -5.29 | Unknown | 74.04 | 0 | 98.26 | 68.75 | 29.51
| 2026-04-04 | N/A | SAN DIEGO | N/A | Not Available | 161 | 115 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.86 | 0 | 207.92 | 5.86 | 202.06
| 2025-06-19 | N/A | SAN CLEMENTE | N/A | Not Available | 255 | 183 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | 312.69 | Unknown | 218.28 | 0 | 192.51 | 530.97 | -338.46
| 2025-01-11 | N/A | SAN DIEGO | N/A | Not Available | 145 | 105 | N/A | 2023-04-28 | Not Available | Not Available | Not Available | -10.94 | Unknown | -4.15 | 0 | 98.41 | -15.09 | 113.5
| 2025-05-02 | N/A | DANA POINT | N/A | Not Available | 33 | 23 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -6.57 | Unknown | -1.03 | 0 | 180.38 | -7.6 | 187.98
| 2025-02-27 | Underserved Community | DANA POINT | N/A | Not Available | 8 | 6 | N/A | 2024-04-25 | Not Available | Not Available | Not Available | -2.38 | Unknown | -0.55 | 0 | 396.91 | -2.93 | 399.84
| 2024-05-31 | N/A | SAN CLEMENTE | N/A | Not Available | 44 | 32 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | 136.64 | Unknown | 100.45 | 0 | 192.95 | 237.09 | -44.14
| 2025-06-19 | N/A | MISSION VIEJO | N/A | Not Available | 63 | 45 | N/A | 2024-08-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.04 | 0 | 74 | 4.04 | 69.96
| 2025-01-31 | N/A | SAN CLEMENTE | N/A | Not Available | 8 | 6 | N/A | 2025-01-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 25.2 | 0 | 383.43 | 25.2 | 358.23
| 2024-11-29 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 144 | 102 | N/A | 2023-03-28 | Not Available | Not Available | Not Available | -4.42 | Unknown | -1.67 | 0 | 272.8 | -6.09 | 278.89
| 2025-03-22 | N/A | MISSION VIEJO | N/A | Not Available | 15 | 11 | N/A | 2024-06-11 | Not Available | Not Available | Not Available | -8.04 | Unknown | -0.34 | 0 | 74.16 | -8.38 | 82.54
| 2024-05-10 | N/A | SAN CLEMENTE | N/A | Not Available | 461 | 329 | N/A | 2024-10-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 143.91 | 8.02 | 135.89
| 2026-12-28 | Underserved Community | MISSION VIEJO | N/A | Not Available | 35 | 25 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.54 | 0 | 197.01 | 6.54 | 190.47
| 2026-07-15 | N/A | LAGUNA HILLS | N/A | Not Available | 93 | 67 | N/A | 2024-08-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.04 | 0 | 102.37 | 7.04 | 95.33
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 7 | 5 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | 291.46 | Unknown | 198.36 | 0 | 207.92 | 489.82 | -281.9
| 2027-01-21 | Underserved Community | MISSION VIEJO | N/A | Not Available | 17 | 13 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 8 | 0 | 104.94 | 8 | 96.94
| 2023-12-20 | Underserved Community | OCEANSIDE | N/A | Not Available | 201 | 143 | N/A | 2023-09-19 | Not Available | Not Available | Not Available | -4.26 | Unknown | -1.62 | 0 | 363.72 | -5.88 | 369.6
| 2025-02-14 | N/A | CARLSBAD | N/A | Not Available | 72 | 52 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.82 | 0 | 153.75 | -6.61 | 160.36
| 2025-04-24 | Underserved Community | ESCONDIDO | N/A | Not Available | 25 | 19 | N/A | 2023-06-27 | Not Available | Not Available | Not Available | -9.19 | Unknown | -3.5 | 0 | 40.01 | -12.69 | 52.7
| 2025-04-10 | N/A | LAGUNA NIGUEL | N/A | Not Available | 39 | 27 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -14.04 | Unknown | -2.24 | 0 | 192.83 | -16.28 | 209.11
| 2025-03-05 | N/A | LAGUNA NIGUEL | N/A | Not Available | 31 | 23 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -6.69 | Unknown | -1.57 | 0 | 84.66 | -8.26 | 92.92
| 2025-04-25 | N/A | LAGUNA NIGUEL | N/A | Not Available | 76 | 54 | N/A | 2024-08-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.88 | 0 | 192.83 | 18.88 | 173.95
| 2025-03-31 | N/A | SAN CLEMENTE | N/A | Not Available | 12 | 8 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | -6.46 | Unknown | 319.45 | 0 | 450.11 | 312.99 | 137.12
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 43 | 31 | N/A | 2024-08-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 22.95 | 0 | 668.23 | 22.95 | 645.28
| 2025-03-21 | N/A | CORONADO | N/A | Not Available | 217 | 155 | N/A | 2024-01-14 | Not Available | Not Available | Not Available | -6.16 | Unknown | -1.42 | 0 | 496.45 | -7.58 | 504.03
| 2025-09-27 | N/A | CARLSBAD | N/A | Not Available | 75 | 53 | N/A | 2024-03-11 | Not Available | Not Available | Not Available | 582.92 | Unknown | 399.72 | 0 | 158.79 | 982.64 | -823.85
| 2024-06-27 | N/A | SAN CLEMENTE | N/A | Not Available | 206 | 148 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | -6.83 | Unknown | -1.83 | 0 | 143.91 | -8.66 | 152.57
| 2024-03-20 | Underserved Community | VISTA | N/A | Not Available | 93 | 67 | N/A | 2023-10-18 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.61 | 0 | 496.45 | -6.04 | 502.49
| 2026-04-17 | N/A | CARLSBAD | N/A | Not Available | 45 | 33 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | -1.88 | Unknown | 97.32 | 0 | 192.83 | 95.44 | 97.39
| 2025-03-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | 241.68 | Unknown | 153.28 | 0 | 153.83 | 394.96 | -241.13
| 2027-01-16 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.6 | 0 | 196.69 | 6.6 | 190.09
| 2026-02-26 | Underserved Community | OCEANSIDE | N/A | Not Available | 30 | 22 | N/A | 2024-05-03 | Not Available | Not Available | Not Available | -8.75 | Unknown | -2.04 | 0 | 163.83 | -10.79 | 174.62
| 2026-08-16 | Underserved Community | CAPISTRANO BEACH | N/A | Not Available | 61 | 43 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | 759.23 | Unknown | 554.5 | 0 | 180.5 | 1313.73 | -1133.23
| 2027-12-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.28 | 0 | 190.13 | 8.28 | 181.85
| 2026-04-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 36 | 26 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -5.83 | Unknown | -0.92 | 0 | 192.83 | -6.75 | 199.58
| 2025-12-18 | N/A | RANCHO LA COSTA | N/A | Not Available | 28 | 20 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.16 | 0 | 105.72 | 7.16 | 98.56
| 2025-07-24 | Underserved Community | CHULA VISTA | N/A | Not Available | 18 | 12 | N/A | 2023-08-15 | Not Available | Not Available | Not Available | -16.15 | Unknown | -4.37 | 0 | 496.37 | -20.52 | 516.89
| 2027-04-22 | N/A | DEL MAR | N/A | Not Available | 30 | 22 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | 854.01 | Unknown | 567 | 0 | 118.25 | 1421.01 | -1302.76
| 2027-01-22 | Underserved Community | SANTEE | N/A | Not Available | 42 | 30 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.34 | 0 | 196.69 | 5.34 | 191.35
| 2025-03-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2023-07-10 | Not Available | Not Available | Not Available | -6.86 | Unknown | 2.4 | 0 | 153.87 | -4.46 | 158.33
| 2025-11-22 | Underserved Community | FALLBROOK | N/A | Not Available | 10 | 8 | N/A | 2024-12-10 | Not Available | Not Available | Not Available | 606.24 | Unknown | 1169.29 | 0 | 695.23 | 1775.53 | -1080.3
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 52 | 38 | N/A |  | Not Available | Not Available | Not Available | 259.76 | Unknown | 594.45 | 0 | 189.89 | 854.21 | -664.32
| 2026-12-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 51 | 37 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.04 | 0 | 197.01 | 5.04 | 191.97
| 2026-05-09 | N/A | SAN DIEGO | N/A | Not Available | 25 | 19 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.62 | 0 | 192.51 | 4.62 | 187.89
| 2026-06-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 16 | 12 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.56 | 0 | 985.1 | 5.56 | 979.54
| 2026-07-31 | N/A | DEL MAR | N/A | Not Available | 15 | 11 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.88 | 0 | 197.01 | 5.88 | 191.13
| 2027-02-27 | N/A | OCEANSIDE | N/A | Not Available | 26 | 18 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.24 | 0 | 196.44 | 4.24 | 192.2
| 2026-11-13 | N/A | CHULA VISTA | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | 771.24 | Unknown | 318.53 | 0 | 197.01 | 1089.77 | -892.76
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 42 | 30 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -11.51 | Unknown | -2.61 | 0 | 207.92 | -14.12 | 222.04
| 2026-07-29 | N/A | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.34 | 0 | 192.95 | 2.34 | 190.61
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 50 | 36 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 207.92 | -4.06 | 211.98
| 2027-04-08 | N/A | ENCINITAS | N/A | Not Available | 21 | 15 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | 382.05 | Unknown | 256.93 | 0 | 196.59 | 638.98 | -442.39
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 19 | 15 | N/A | 2025-01-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.91 | 0 | 196.69 | 3.91 | 192.78
| 2026-06-13 | N/A | ENCINITAS | N/A | Not Available | 19 | 13 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.02 | 0 | 282.95 | 3.02 | 279.93
| 2024-04-01 | Underserved Community | ESCONDIDO | N/A | Not Available | 25 | 19 | N/A | 2023-07-18 | Not Available | Not Available | Not Available | -22.75 | Unknown | -8.67 | 0 | 153.87 | -31.42 | 185.29
| 2025-04-12 | N/A | SANTEE | N/A | Not Available | 40 | 28 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.53 | 0 | 192.83 | 8.53 | 184.3
| 2027-01-27 | Underserved Community | SANTEE | N/A | Not Available | 18 | 14 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.99 | 0 | 196.69 | 4.99 | 191.7
| 2026-05-07 | Underserved Community | FALLBROOK | N/A | Not Available | 35 | 25 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -16.92 | Unknown | -3.93 | 0 | 529.2 | -20.85 | 550.05
| 2027-03-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 19 | 15 | N/A |  | Not Available | Not Available | Not Available | 258.94 | Unknown | 105.83 | 0 | 190.04 | 364.77 | -174.73
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 28 | 20 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -4.84 | Unknown | -1.14 | 0 | 207.92 | -5.98 | 213.9
| 2027-02-20 | Underserved Community | CHULA VISTA | N/A | Not Available | 66 | 48 | N/A |  | Not Available | Not Available | Not Available | 440.42 | Unknown | 200.51 | 0 | 196.44 | 640.93 | -444.49
| 2026-04-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 36 | 26 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -4.92 | Unknown | -0.81 | 0 | 192.83 | -5.73 | 198.56
| 2027-03-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 196.59 | 3.05 | 193.54
| 2026-01-25 | N/A | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.04 | 0 | 1064.43 | 7.04 | 1057.39
| 2024-05-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 25 | 19 | N/A | 2023-07-11 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.84 | 0 | 465.44 | -6.62 | 472.06
| 2026-01-14 | N/A | SAN DIEGO | N/A | Not Available | 18 | 14 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.77 | 0 | 197.01 | 3.77 | 193.24
| 2026-01-21 | N/A | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.9 | 0 | 196.69 | 7.9 | 188.79
| 2023-06-15 | Underserved Community | CHULA VISTA | N/A | Not Available | 66 | 48 | N/A | 2024-01-16 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1.19 | 0 | 515.81 | -4.93 | 520.74
| 2026-01-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-02-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.51 | 0 | 196.69 | 5.51 | 191.18
| 2026-01-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | -7.5 | Unknown | 375.24 | 0 | 1064.43 | 367.74 | 696.69
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 44 | 32 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -5.83 | Unknown | -1.37 | 0 | 150.74 | -7.2 | 157.94
| 2026-09-22 | Underserved Community | LA MESA | N/A | Not Available | 168 | 120 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | -18.82 | Unknown | 149.91 | 0 | 197.01 | 131.09 | 65.92
| 2026-08-30 | N/A | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.25 | 0 | 999.88 | 4.25 | 995.63
| 2026-01-15 | N/A | SAN DIEGO | N/A | Not Available | 9 | 7 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.31 | 0 | 196.69 | 6.31 | 190.38
| 2027-04-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 133 | 95 | N/A | 2024-04-23 | Not Available | Not Available | Not Available | 26.76 | Unknown | 44.89 | 0 | 400.94 | 71.65 | 329.29
| 2026-05-08 | N/A | CARLSBAD | N/A | Not Available | 123 | 89 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.52 | 0 | 192.83 | 5.52 | 187.31
| 2025-04-17 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 19 | 13 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -2.38 | Unknown | 2.76 | 0 | 156.93 | 0.38 | 156.55
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 222 | 158 | N/A | 2023-02-08 | Not Available | Not Available | Not Available | -11.45 | Unknown | -2.64 | 0 | 158.14 | -14.09 | 172.23
| 2025-08-28 | Underserved Community | CHULA VISTA | N/A | Not Available | 74 | 52 | N/A |  | Not Available | Not Available | Not Available | 378.69 | Unknown | 232.23 | 0 | 158.37 | 610.92 | -452.55
| 2026-01-03 | Underserved Community | OCEANSIDE | N/A | Not Available | 20 | 14 | N/A | 2024-04-12 | Not Available | Not Available | Not Available | -6.17 | Unknown | 0.74 | 0 | 163.83 | -5.43 | 169.26
| 2026-04-12 | N/A | SAN MARCOS | N/A | Not Available | 75 | 53 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -12.09 | Unknown | -1.93 | 0 | 529.2 | -14.02 | 543.22
| 2026-12-02 | N/A | CARLSBAD | N/A | Not Available | 63 | 45 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.06 | 0 | 105.72 | 7.06 | 98.66
| 2025-05-26 | N/A | SAN MARCOS | N/A | Not Available | 153 | 109 | N/A | 2023-09-05 | Not Available | Not Available | Not Available | -12.11 | Unknown | -3.42 | 0 | 153.83 | -15.53 | 169.36
| 2026-07-05 | N/A | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.68 | 0 | 273.51 | 5.68 | 267.83
| 2026-12-05 | N/A | RANCHO SANTA FE | N/A | Not Available | 8 | 6 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | -17.47 | Unknown | -7.73 | 0 | 278.5 | -25.2 | 303.7
| 2026-12-02 | N/A | CARLSBAD | N/A | Not Available | 70 | 50 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.7 | 0 | 197.01 | 7.7 | 189.31
| 2025-05-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 166 | 120 | N/A | 2023-12-28 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.17 | 0 | 515.81 | -6.12 | 521.93
| 2026-11-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2024-12-23 | Not Available | Not Available | Not Available | 349.8 | Unknown | 630.21 | 0 | 190.44 | 980.01 | -789.57
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 525 | 375 | N/A | 2024-12-01 | Not Available | Not Available | Not Available | -6.92 | Unknown | -3.78 | 0 | 158.79 | -10.7 | 169.49
| 2026-04-22 | N/A | SAN DIEGO | N/A | Not Available | 101 | 72 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | -21.5 | Unknown | 1125.11 | 0 | 1049.43 | 1103.61 | -54.18
| 2024-02-03 | Underserved Community | LA MESA | N/A | Not Available | 91 | 65 | N/A | 2023-06-05 | Not Available | Not Available | Not Available | -8.16 | Unknown | -3.1 | 0 | 363.72 | -11.26 | 374.98
| 2026-09-27 | Underserved Community | LA JOLLA | N/A | Not Available | 9 | 7 | N/A | 2024-10-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 197.01 | 4.01 | 193
| 2025-11-02 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -5.28 | Unknown | 0.64 | 0 | 192.83 | -4.64 | 197.47
| 2024-02-24 | N/A | EL CAJON | N/A | Not Available | 61 | 43 | N/A | 2023-04-14 | Not Available | Not Available | Not Available | -10.29 | Unknown | -3.91 | 0 | 144.8 | -14.2 | 159
| 2026-02-15 | N/A | SOLANA BEACH | N/A | Not Available | 22 | 16 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | -10.3 | Unknown | -2.44 | 0 | 207.92 | -12.74 | 220.66
| 2025-02-21 | Underserved Community | POWAY | N/A | Not Available | 238 | 170 | N/A | 2023-10-30 | Not Available | Not Available | Not Available | -13.67 | Unknown | -2.57 | 0 | 154.79 | -16.24 | 171.03
| 2025-02-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 101 | 73 | N/A | 2023-07-05 | Not Available | Not Available | Not Available | 364.98 | Unknown | 188.72 | 0 | 153.75 | 553.7 | -399.95
| 2025-02-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 221 | 157 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -4.09 | Unknown | 10.66 | 0 | 495.75 | 6.57 | 489.18
| 2023-07-29 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 24 | 18 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1008.47 | 0 | 804.89 | 1008.47 | -203.58
| 2024-11-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 141 | 101 | N/A | 2023-04-05 | Not Available | Not Available | Not Available | -5.54 | Unknown | -2.11 | 0 | 364.52 | -7.65 | 372.17
| 2026-09-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 74 | 54 | N/A | 2025-01-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.22 | 0 | 197.01 | 11.22 | 185.79
| 2026-09-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 51 | 37 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.63 | 0 | 197.01 | 6.63 | 190.38
| 2025-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 235 | 167 | N/A |  | Not Available | Not Available | Not Available | 307.05 | Unknown | 154.86 | 0 | 158.37 | 461.91 | -303.54
| 2025-08-15 | Underserved Community | CHULA VISTA | N/A | Not Available | 65 | 47 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -12.62 | Unknown | 0.11 | 0 | 153.49 | -12.51 | 166
| 2025-10-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 168 | 120 | N/A | 2023-02-27 | Not Available | Not Available | Not Available | -8.68 | Unknown | -3.3 | 0 | 363.72 | -11.98 | 375.7
| 2027-03-14 | N/A | SAN DIEGO | N/A | Not Available | 31 | 23 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.84 | 0 | 196.59 | 5.84 | 190.75
| 2025-10-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 83 | 59 | N/A |  | Not Available | Not Available | Not Available | 236.04 | Unknown | 146.85 | 0 | 363.72 | 382.89 | -19.17
| 2024-02-14 | N/A | EL CAJON | N/A | Not Available | 56 | 40 | N/A | 2023-06-09 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.54 | 0 | 495.75 | -5.63 | 501.38
| 2026-09-06 | N/A | CARLSBAD | N/A | Not Available | 43 | 31 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.62 | 0 | 197.01 | 1.62 | 195.39
| 2023-11-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 208 | 148 | N/A | 2024-01-31 | Not Available | Not Available | Not Available | -7.36 | Unknown | 0.53 | 0 | 153.83 | -6.83 | 160.66
| 2025-06-09 | Underserved Community | ESCONDIDO | N/A | Not Available | 59 | 42 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -14.86 | Unknown | -4.97 | 0 | 153.83 | -19.83 | 173.66
| 2026-08-20 | Underserved Community | VISTA | N/A | Not Available | 21 | 15 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.81 | 0 | 197.01 | 7.81 | 189.2
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 37 | 27 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2025-02-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A |  | Not Available | Not Available | Not Available | 587.52 | Unknown | 403.29 | 0 | 787.09 | 990.81 | -203.72
| 2024-01-31 | N/A | SANTEE | N/A | Not Available | 118 | 84 | N/A | 2023-05-25 | Not Available | Not Available | Not Available | -8.38 | Unknown | -2.2 | 0 | 98.41 | -10.58 | 108.99
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 36 | 26 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2024-02-09 | N/A | SAN DIEGO | N/A | Not Available | 84 | 60 | N/A | 2023-03-28 | Not Available | Not Available | Not Available | -11.36 | Unknown | -4.32 | 0 | 818.45 | -15.68 | 834.13
| 2024-03-20 | Underserved Community | SPRING VALLEY | N/A | Not Available | 40 | 28 | N/A | 2023-07-12 | Not Available | Not Available | Not Available | -10.54 | Unknown | -4 | 0 | 495.75 | -14.54 | 510.29
| 2025-10-02 | N/A | SOLANA BEACH | N/A | Not Available | 92 | 66 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 13619.52 | 0 | 2220.19 | 13619.52 | -11399.33
| 2024-06-15 | N/A | ENCINITAS | N/A | Not Available | 36 | 26 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -19.14 | Unknown | 10.72 | 0 | 698.71 | -8.42 | 707.13
| 2025-08-15 | N/A | OCEANSIDE | N/A | Not Available | 58 | 42 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | 483.36 | Unknown | 67.8 | 0 | 162.34 | 551.16 | -388.82
| 2026-11-12 | Underserved Community | VISTA | N/A | Not Available | 43 | 31 | N/A | 2025-01-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.81 | 0 | 197.01 | 14.81 | 182.2
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 477 | 341 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.13 | 0 | 163.83 | 4.13 | 159.7
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 153 | 109 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.7 | 0 | 380.88 | 4.7 | 376.18
| 2026-03-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A |  | Not Available | Not Available | Not Available | 3243 | Unknown | 6520.29 | 0 | 192.83 | 9763.29 | -9570.46
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 111 | 79 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | -8.41 | Unknown | -1.95 | 0 | 163.83 | -10.36 | 174.19
| 2026-11-23 | Underserved Community | RAMONA | N/A | Not Available | 136 | 98 | N/A |  | Not Available | Not Available | Not Available | 1221.1 | Unknown | 575.55 | 0 | 196.44 | 1796.65 | -1600.21
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-12-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.15 | 0 | 380.88 | 5.15 | 375.73
| 2025-04-14 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2023-09-18 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.42 | 0 | 480.37 | -5.34 | 485.71
| 2025-09-18 | Underserved Community | VISTA | N/A | Not Available | 30 | 22 | N/A | 2024-03-19 | Not Available | Not Available | Not Available | -5.31 | Unknown | 0.06 | 0 | 163.83 | -5.25 | 169.08
| 2026-12-10 | N/A | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | -16.15 | Unknown | -7.13 | 0 | 196.69 | -23.28 | 219.97
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 155 | 111 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -12.71 | Unknown | -2.95 | 0 | 163.83 | -15.66 | 179.49
| 2027-02-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 28 | 20 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | -8.9 | Unknown | -4.82 | 0 | 196.44 | -13.72 | 210.16
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 133 | 95 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -9.78 | Unknown | -2.26 | 0 | 163.83 | -12.04 | 175.87
| 2026-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 103 | N/A |  | Not Available | Not Available | Not Available | 190.31 | Unknown | 130.57 | 0 | 1050.75 | 320.88 | 729.87
| 2025-03-09 | Underserved Community | VISTA | N/A | Not Available | 98 | 70 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 8 | 0 | 984.98 | 8 | 976.98
| 2025-11-07 | N/A | ENCINITAS | N/A | Not Available | 48 | 34 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -7.84 | Unknown | -0.39 | 0 | 163.83 | -8.23 | 172.06
| 2026-11-18 | N/A | SAN CLEMENTE | N/A | Not Available | 162 | 116 | N/A | 2025-05-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.75 | 0 | 197.01 | 1.75 | 195.26
| 2026-09-06 | N/A | POWAY | N/A | Not Available | 85 | 61 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.96 | 0 | 184.29 | 4.96 | 179.33
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 163 | 117 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -4.54 | Unknown | -1.06 | 0 | 163.83 | -5.6 | 169.43
| 2025-04-16 | Underserved Community | CHULA VISTA | N/A | Not Available | 63 | 45 | N/A | 2023-09-15 | Not Available | Not Available | Not Available | -9.92 | Unknown | -3.63 | 0 | 496.37 | -13.55 | 509.92
| 2026-11-09 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.03 | 0 | 197.01 | 5.03 | 191.98
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 239 | 171 | N/A | 2024-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.46 | 0 | 163.83 | 8.46 | 155.37
| 2025-04-17 | N/A | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2023-07-10 | Not Available | Not Available | Not Available | -7.39 | Unknown | -2.81 | 0 | 148.74 | -10.2 | 158.94
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 139 | 99 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 91 | 65 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.89 | 0 | 192.95 | 7.89 | 185.06
| 2027-01-31 | N/A | CARLSBAD | N/A | Not Available | 79 | 57 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | 854.01 | Unknown | 566.3 | 0 | 196.59 | 1420.31 | -1223.72
| 2025-10-30 | N/A |  | N/A | Not Available | 32 | 24 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | 476.51 | Unknown | 219.51 | 0 | 152.86 | 696.02 | -543.16
| 2026-01-01 | Underserved Community | ESCONDIDO | N/A | Not Available | 23 | 17 | N/A | 2024-04-26 | Not Available | Not Available | Not Available | -11.29 | Unknown | -0.18 | 0 | 198.42 | -11.47 | 209.89
| 2026-06-28 | Underserved Community | LAKESIDE | N/A | Not Available | 69 | 49 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.19 | 0 | 197.01 | 12.19 | 184.82
| 2026-09-19 | N/A | CARLSBAD | N/A | Not Available | 110 | 78 | N/A | 2025-04-28 | Not Available | Not Available | Not Available | 382.05 | Unknown | 191.94 | 0 | 1066.55 | 573.99 | 492.56
| 2026-07-25 | N/A | LA JOLLA | N/A | Not Available | 217 | 155 | N/A | 2025-04-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.06 | 0 | 197.01 | 2.06 | 194.95
| 2024-04-15 | Underserved Community | OCEANSIDE | N/A | Not Available | 37 | 27 | N/A | 2023-12-27 | Not Available | Not Available | Not Available | -11.76 | Unknown | -3.18 | 0 | 158.79 | -14.94 | 173.73
| 2026-08-02 | N/A | OCEANSIDE | N/A | Not Available | 14 | 10 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 192.95 | 4.29 | 188.66
| 2026-01-08 | Underserved Community | SAN MARCOS | N/A | Not Available | 66 | 48 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.35 | 0 | 142.83 | 6.35 | 136.48
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 70 | 50 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.11 | 0 | 192.95 | 6.11 | 186.84
| 2025-01-17 | N/A | CARLSBAD | N/A | Not Available | 55 | 39 | N/A | 2023-06-07 | Not Available | Not Available | Not Available | -13.05 | Unknown | -4.95 | 0 | 154.79 | -18 | 172.79
| 2024-12-02 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2023-05-23 | Not Available | Not Available | Not Available | -6.4 | Unknown | 186.63 | 0 | 98.41 | 180.23 | -81.82
| 2025-01-18 | Underserved Community | OCEANSIDE | N/A | Not Available | 140 | 100 | N/A | 2023-03-30 | Not Available | Not Available | Not Available | -7.07 | Unknown | -2.67 | 0 | 364.52 | -9.74 | 374.26
| 2024-03-03 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 62 | 44 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -11.16 | Unknown | -2.59 | 0 | 151.87 | -13.75 | 165.62
| 2023-12-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2023-06-22 | Not Available | Not Available | Not Available | -6.92 | Unknown | -2.63 | 0 | 495.75 | -9.55 | 505.3
| 2023-12-31 | N/A | SAN CLEMENTE | N/A | Not Available | 84 | 60 | N/A | 2024-01-10 | Not Available | Not Available | Not Available | -6.68 | Unknown | -1.78 | 0 | 483.59 | -8.46 | 492.05
| 2025-03-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 120 | 86 | N/A | 2021-04-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 0.03 | 0 | 499.96 | 0.03 | 499.93
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 176 | 126 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -6.19 | Unknown | -0.97 | 0 | 163.83 | -7.16 | 170.99
| 2026-12-11 | N/A | DANA POINT | N/A | Not Available | 45 | 33 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | -17.99 | Unknown | -8.02 | 0 | 196.69 | -26.01 | 222.7
| 2025-03-01 | Underserved Community | VISTA | N/A | Not Available | 152 | 108 | N/A | 2023-03-16 | Not Available | Not Available | Not Available | -5.89 | Unknown | 123.52 | 0 | 62.88 | 117.63 | -54.75
| 2024-10-10 | N/A | SAN MARCOS | N/A | Not Available | 121 | 87 | N/A | 2023-02-17 | Not Available | Not Available | Not Available | -14.43 | Unknown | 340.57 | 0 | 436.48 | 326.14 | 110.34
| 2025-02-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 186 | 134 | N/A | 2023-05-19 | Not Available | Not Available | Not Available | -8.18 | Unknown | -3.12 | 0 | 341.75 | -11.3 | 353.05
| 2025-01-31 | N/A | DANA POINT | N/A | Not Available | 29 | 21 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.04 | 0 | 105.08 | 6.04 | 99.04
| 2025-11-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 84 | 60 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.88 | 0 | 197.01 | 13.88 | 183.13
| 2024-02-23 | N/A | ENCINITAS | N/A | Not Available | 138 | 100 | N/A | 2023-05-17 | Not Available | Not Available | Not Available | -5.78 | Unknown | 13.32 | 0 | 479.76 | 7.54 | 472.22
| 2024-01-24 | N/A | CARLSBAD | N/A | Not Available | 167 | 119 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -4.42 | Unknown | -1.69 | 0 | 242.5 | -6.11 | 248.61
| 2024-08-29 | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | Not Available | 120 | 86 | N/A | 2023-02-09 | Not Available | Not Available | Not Available | -32.89 | Unknown | -12.52 | 0 | 363.72 | -45.41 | 409.13
| 2024-12-18 | Underserved Community | SAN MARCOS | N/A | Not Available | 165 | 119 | N/A | 2023-05-16 | Not Available | Not Available | Not Available | -7.16 | Unknown | -1.53 | 0 | 95.37 | -8.69 | 104.06
| 2025-11-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 79 | 57 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | -9.84 | Unknown | 516.57 | 0 | 197.01 | 506.73 | -309.72
| 2025-08-23 | Underserved Community | LAKESIDE | N/A | Not Available | 54 | 40 | N/A | 2025-01-02 | Not Available | Not Available | Not Available | 40.9 | Unknown | 58.2 | 0 | 197.01 | 99.1 | 97.91
| 2026-07-25 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 70 | 50 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.29 | 0 | 197.01 | 13.29 | 183.72
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 43 | 31 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 207.92 | -4.06 | 211.98
| 2024-01-12 | Underserved Community | EL CAJON | N/A | Not Available | 371 | 265 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.23 | 0 | 363.72 | -1.23 | 364.95
| 2027-02-04 | N/A | DANA POINT | N/A | Not Available | 16 | 12 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.24 | 0 | 196.69 | 10.24 | 186.45
| 2025-03-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 128 | 92 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -5.67 | Unknown | -0.99 | 0 | 40.01 | -6.66 | 46.67
| 2023-10-28 | Underserved Community | SPRING VALLEY | N/A | Not Available | 198 | 142 | N/A | 2023-09-19 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.87 | 0 | 364.52 | -6.82 | 371.34
| 2024-02-27 | Underserved Community | LAKESIDE | N/A | Not Available | 174 | 124 | N/A | 2023-08-11 | Not Available | Not Available | Not Available | -10.06 | Unknown | -3.84 | 0 | 499.96 | -13.9 | 513.86
| 2025-10-29 | Underserved Community | LAGUNA HILLS | N/A | Not Available | 22 | 16 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | 613.12 | Unknown | 464.98 | 0 | 184.29 | 1078.1 | -893.81
| 2024-04-18 | N/A | LA JOLLA | N/A | Not Available | 145 | 105 | N/A | 2023-12-21 | Not Available | Not Available | Not Available | -30.45 | Unknown | 685.2 | 0 | 1447.41 | 654.75 | 792.66
| 2025-09-06 | Underserved Community | OCEANSIDE | N/A | Not Available | 90 | 64 | N/A |  | Not Available | Not Available | Not Available | -8.73 | Unknown | -2.05 | 0 | 715.96 | -10.78 | 726.74
| 2025-04-25 | N/A | OCEANSIDE | N/A | Not Available | 22 | 16 | N/A | 2024-05-03 | Not Available | Not Available | Not Available | -13.37 | Unknown | -3.11 | 0 | 200.98 | -16.48 | 217.46
| 2024-12-27 | Underserved Community | DANA POINT | N/A | Not Available | 103 | 73 | N/A | 2024-05-07 | Not Available | Not Available | Not Available | -5.09 | Unknown | -1.2 | 0 | 787.98 | -6.29 | 794.27
| 2026-12-12 | N/A | MISSION VIEJO | N/A | Not Available | 67 | 49 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.75 | 0 | 197.01 | 6.75 | 190.26
| 2026-08-06 | N/A | POWAY | N/A | Not Available | 44 | 32 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 21.29 | 0 | 180.5 | 21.29 | 159.21
| 2024-03-14 | N/A | CARLSBAD | N/A | Not Available | 127 | 91 | N/A | 2023-10-30 | Not Available | Not Available | Not Available | -3.4 | Unknown | -1.25 | 0 | 495.75 | -4.65 | 500.4
| 2024-08-29 | N/A | ESCONDIDO | N/A | Not Available | 395 | 283 | N/A | 2023-03-10 | Not Available | Not Available | Not Available | -10.41 | Unknown | 0.72 | 0 | 29.33 | -9.69 | 39.02
| 2026-08-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.17 | 0 | 2115.64 | 8.17 | 2107.47
| 2025-04-12 | N/A | DANA POINT | N/A | Not Available | 71 | 51 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.42 | 0 | 74.16 | 4.42 | 69.74
| 2024-04-28 | Underserved Community | VISTA | N/A | Not Available | 364 | 260 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.76 | 0 | 158.51 | 5.76 | 152.75
| 2025-10-24 | Underserved Community | LEMON GROVE | N/A | Not Available | 14 | 10 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -11.99 | Unknown | -3.89 | 0 | 513.31 | -15.88 | 529.19
| 2024-02-28 | N/A | SAN DIEGO | N/A | Not Available | 141 | 101 | N/A | 2023-10-16 | Not Available | Not Available | Not Available | -7.88 | Unknown | -2.86 | 0 | 153.75 | -10.74 | 164.49
| 2025-03-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 134 | 96 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | -8.53 | Unknown | -3.24 | 0 | 242.5 | -11.77 | 254.27
| 2025-02-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 122 | 88 | N/A | 2023-05-04 | Not Available | Not Available | Not Available | -8.38 | Unknown | -3.19 | 0 | 153.75 | -11.57 | 165.32
| 2025-02-28 | N/A | RANCHO MISSION VIEJO | N/A | Not Available | 79 | 57 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | -14.18 | Unknown | -7.68 | 0 | 104.77 | -21.86 | 126.63
| 2025-11-16 | N/A | RANCHO SANTA FE | N/A | Not Available | 339 | 243 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 163.83 | 5.81 | 158.02
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 454 | 324 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.09 | 0 | 153.83 | 4.09 | 149.74
| 2025-04-22 | Underserved Community | EL CAJON | N/A | Not Available | 42 | 30 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.67 | 0 | 192.51 | 4.67 | 187.84
| 2026-09-11 | N/A | SAN CLEMENTE | N/A | Not Available | 57 | 41 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.4 | 0 | 184.29 | 4.4 | 179.89
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 470 | 336 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.06 | 0 | 153.83 | 2.06 | 151.77
| 2024-07-28 | Underserved Community | LAKESIDE | N/A | Not Available | 59 | 43 | N/A | 2023-09-22 | Not Available | Not Available | Not Available | -7.65 | Unknown | -2.89 | 0 | 320.25 | -10.54 | 330.79
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 470 | 336 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.16 | 0 | 153.83 | 3.16 | 150.67
| 2025-09-29 | Underserved Community | POWAY | N/A | Not Available | 208 | 150 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | -9.81 | Unknown | -2.29 | 0 | 163.83 | -12.1 | 175.93
| 2026-09-05 | N/A | COTO DE CAZA | N/A | Not Available | 73 | 53 | N/A | 2024-10-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.05 | 0 | 197.01 | 7.05 | 189.96
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 497 | 355 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.76 | 0 | 153.83 | 9.76 | 144.07
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 683 | 487 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.56 | 0 | 153.83 | 5.56 | 148.27
| 2026-06-10 | Underserved Community | LAKESIDE | N/A | Not Available | 42 | 30 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.2 | 0 | 192.51 | 7.2 | 185.31
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 491 | 351 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.63 | 0 | 153.83 | 2.63 | 151.2
| 2026-10-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | 84 | 60 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 35.96 | 0 | 1091.21 | 35.96 | 1055.25
| 2025-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 185 | 133 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.5 | 0 | 288.94 | 2.5 | 286.44
| 2027-01-03 | Underserved Community | LA MESA | N/A | Not Available | 52 | 38 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | -12.67 | Unknown | -6.89 | 0 | 196.69 | -19.56 | 216.25
| 2026-04-24 | Underserved Community | FALLBROOK | N/A | Not Available | 221 | 159 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 68.21 | 0 | 1050.61 | 68.21 | 982.4
| 2025-09-18 | Underserved Community | ESCONDIDO | N/A | Not Available | 335 | 239 | N/A | 2024-09-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.59 | 0 | 163.83 | 6.59 | 157.24
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 490 | 350 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.89 | 0 | 153.83 | 7.89 | 145.94
| 2025-05-08 | N/A | SOUTH LAGUNA | N/A | Not Available | 115 | 83 | N/A | 2024-07-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.88 | 0 | 192.51 | 13.88 | 178.63
| 2024-09-01 | Underserved Community | LA MESA | N/A | Not Available | 179 | 129 | N/A | 2024-01-11 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.16 | 0 | 513.31 | -6.11 | 519.42
| 2024-10-23 | Underserved Community | DANA POINT | N/A | Not Available | 98 | 70 | N/A | 2023-12-04 | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.57 | 0 | 515.81 | -6.36 | 522.17
| 2027-01-06 | N/A | SAN CLEMENTE | N/A | Not Available | 88 | 64 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.12 | 0 | 184 | 5.12 | 178.88
| 2026-02-21 | N/A | POWAY | N/A | Not Available | 92 | 66 | N/A | 2024-05-03 | Not Available | Not Available | Not Available | -13.66 | Unknown | -3.17 | 0 | 534.57 | -16.83 | 551.4
| 2024-06-14 | Underserved Community | EL CAJON | N/A | Not Available | 120 | 86 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | -29.91 | Unknown | 1002.31 | 0 | 513.5 | 972.4 | -458.9
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 124 | 88 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -13.91 | Unknown | -2.21 | 0 | 374 | -16.12 | 390.12
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 196 | 140 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -6.51 | Unknown | -1.52 | 0 | 158.51 | -8.03 | 166.54
| 2024-11-15 | Underserved Community | SPRING VALLEY | N/A | Not Available | 14 | 10 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | -30.38 | Unknown | 1204.17 | 0 | 152.86 | 1173.79 | -1020.93
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 136 | 98 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -5.83 | Unknown | -1.37 | 0 | 207.92 | -7.2 | 215.12
| 2027-01-13 | N/A | SOLANA BEACH | N/A | Not Available | 60 | 42 | N/A | 2025-03-24 | Not Available | Not Available | Not Available | -8.9 | Unknown | -3.07 | 0 | 196.69 | -11.97 | 208.66
| 2024-07-11 | N/A | SANTEE | N/A | Not Available | 128 | 92 | N/A | 2023-09-29 | Not Available | Not Available | Not Available | -4.79 | Unknown | -1.76 | 0 | 153.83 | -6.55 | 160.38
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 133 | 95 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.94 | 0 | 207.92 | -10.34 | 218.26
| 2027-03-12 | N/A | CARLSBAD | N/A | Not Available | 42 | 30 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 141 | 101 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -4.54 | Unknown | -1.06 | 0 | 207.92 | -5.6 | 213.52
| 2026-12-02 | Underserved Community | LAKESIDE | N/A | Not Available | 65 | 47 | N/A | 2025-01-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.55 | 0 | 197.01 | 12.55 | 184.46
| 2025-08-08 | Underserved Community | OCEANSIDE | N/A | Not Available | 211 | 151 | N/A | 2024-02-16 | Not Available | Not Available | Not Available | -4.96 | Unknown | 0.02 | 0 | 158.79 | -4.94 | 163.73
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 118 | 84 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | 506.8 | Unknown | 69.54 | 0 | 374 | 576.34 | -202.34
| 2026-04-19 | Underserved Community | SPRING VALLEY | N/A | Not Available | 57 | 41 | N/A | 2024-06-05 | Not Available | Not Available | Not Available | -7.1 | Unknown | -1.65 | 0 | 180.38 | -8.75 | 189.13
| 2028-01-20 | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Not Available | 23 | 17 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.29 | 0 | 190.13 | 8.29 | 181.84
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 350 | 250 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -7.72 | Unknown | -1.83 | 0 | 154.99 | -9.55 | 164.54
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 269 | 193 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -6.19 | Unknown | -1.43 | 0 | 158.79 | -7.62 | 166.41
| 2027-01-10 | Underserved Community | SANTEE | N/A | Not Available | 28 | 20 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.21 | 0 | 196.69 | 10.21 | 186.48
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 127 | 91 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -9.65 | Unknown | -1.53 | 0 | 374 | -11.18 | 385.18
| 2026-07-17 | Underserved Community | LAKESIDE | N/A | Not Available | 62 | 44 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.27 | 0 | 180.5 | 5.27 | 175.23
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 158.14 | -4.18 | 162.32
| 2026-02-15 | N/A | ENCINITAS | N/A | Not Available | 78 | 56 | N/A | 2024-04-11 | Not Available | Not Available | Not Available | -6.34 | Unknown | 0.6 | 0 | 163.83 | -5.74 | 169.57
| 2026-04-05 | Underserved Community | CHULA VISTA | N/A | Not Available | 108 | 78 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.75 | 0 | 180.38 | 6.75 | 173.63
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 363 | 259 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -17.72 | Unknown | -4.14 | 0 | 154.99 | -21.86 | 176.85
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 177 | 127 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | -11.76 | Unknown | -2.72 | 0 | 158.14 | -14.48 | 172.62
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -6.17 | Unknown | -1.43 | 0 | 158.14 | -7.6 | 165.74
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 231 | 165 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.8 | 0 | 163.83 | 6.8 | 157.03
| 2024-05-16 | N/A | ENCINITAS | N/A | Not Available | 195 | 139 | N/A | 2023-12-01 | Not Available | Not Available | Not Available | -8.5 | Unknown | -2.75 | 0 | 514.57 | -11.25 | 525.82
| 2025-10-17 | N/A | DEL MAR | N/A | Not Available | 588 | 420 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.31 | 0 | 163.83 | 1.31 | 162.52
| 2025-08-02 | N/A | CARLSBAD | N/A | Not Available | 141 | 101 | N/A | 2024-01-10 | Not Available | Not Available | Not Available | -3.57 | Unknown | -0.94 | 0 | 515.81 | -4.51 | 520.32
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 195 | 139 | N/A | 2024-06-02 | Not Available | Not Available | Not Available | -7.3 | Unknown | -1.17 | 0 | 163.83 | -8.47 | 172.3
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 203 | 145 | N/A | 2024-03-02 | Not Available | Not Available | Not Available | -6.86 | Unknown | -1.59 | 0 | 158.14 | -8.45 | 166.59
| 2024-05-03 | N/A | CARDIFF | N/A | Not Available | 190 | 136 | N/A | 2023-11-14 | Not Available | Not Available | Not Available | -9.79 | Unknown | -1.99 | 0 | 158.51 | -11.78 | 170.29
| 2027-01-28 | Underserved Community | SANTEE | N/A | Not Available | 95 | 67 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.69 | 1.76 | 194.93
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 139 | 99 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -7.29 | Unknown | -1.71 | 0 | 207.92 | -9 | 216.92
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 66 | 48 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.72 | 0 | 192.95 | 6.72 | 186.23
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 177 | 127 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -9.44 | Unknown | -66.26 | 0 | 158.14 | -75.7 | 233.84
| 2025-02-22 | N/A | ESCONDIDO | N/A | Not Available | 91 | 65 | N/A | 2024-05-22 | Not Available | Not Available | Not Available | -10.24 | Unknown | -2.37 | 0 | 501.14 | -12.61 | 513.75
| 2026-01-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 106 | 76 | N/A | 2024-04-22 | Not Available | Not Available | Not Available | -8.24 | Unknown | -1.92 | 0 | 501.18 | -10.16 | 511.34
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 171 | 123 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -6.19 | Unknown | -1.43 | 0 | 163.83 | -7.62 | 171.45
| 2025-06-28 | N/A | CARLSBAD | N/A | Not Available | 18 | 14 | N/A | 2024-07-09 | Not Available | Not Available | Not Available | -12.03 | Unknown | 60.03 | 0 | 192.51 | 48 | 144.51
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 354 | 254 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.97 | 0 | 134.89 | 5.97 | 128.92
| 2025-05-20 | N/A | DANA POINT | N/A | Not Available | 4 | 4 | N/A | 2024-05-22 | Not Available | Not Available | Not Available | 256.28 | Unknown | 178.79 | 0 | 192.83 | 435.07 | -242.24
| 2026-09-23 | Underserved Community | CHULA VISTA | N/A | Not Available | 62 | 44 | N/A |  | Not Available | Not Available | Not Available | 397.41 | Unknown | 245.01 | 0 | 197.01 | 642.42 | -445.41
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 72 | 52 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 192.95 | 3.85 | 189.1
| 2025-12-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 177 | 127 | N/A | 2024-05-03 | Not Available | Not Available | Not Available | -7.78 | Unknown | -1.79 | 0 | 553.02 | -9.57 | 562.59
| 2026-10-10 | Underserved Community | BONITA | N/A | Not Available | 30 | 22 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.09 | 0 | 142.83 | 15.09 | 127.74
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 390 | 278 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -6.9 | Unknown | 1.98 | 0 | 154.99 | -4.92 | 159.91
| 2025-12-08 | Underserved Community | SANTEE | N/A | Not Available | 95 | 69 | N/A | 2024-01-04 | Not Available | Not Available | Not Available | -7.27 | Unknown | -1.96 | 0 | 499.18 | -9.23 | 508.41
| 2026-05-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 62 | 44 | N/A | 2024-07-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.05 | 0 | 983.86 | 7.05 | 976.81
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 65 | 47 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.94 | 0 | 192.95 | 8.94 | 184.01
| 2026-03-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 91 | 65 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -7.75 | Unknown | -1.82 | 0 | 534.57 | -9.57 | 544.14
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 114 | 82 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -3.07 | Unknown | -0.71 | 0 | 207.92 | -3.78 | 211.7
| 2025-08-30 | N/A | CARLSBAD | N/A | Not Available | 186 | 134 | N/A | 2024-02-07 | Not Available | Not Available | Not Available | -7.09 | Unknown | -1.68 | 0 | 515.81 | -8.77 | 524.58
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 211 | 151 | N/A | 2024-03-05 | Not Available | Not Available | Not Available | -7.9 | Unknown | -1.81 | 0 | 158.79 | -9.71 | 168.5
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 126 | 90 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -7.3 | Unknown | -1.18 | 0 | 374 | -8.48 | 382.48
| 2026-05-28 | Underserved Community | ESCONDIDO | N/A | Not Available | 104 | 74 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.92 | 0 | 983.86 | 6.92 | 976.94
| 2026-07-03 | N/A | SAN MARCOS | N/A | Not Available | 52 | 38 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.48 | 0 | 192.95 | 14.48 | 178.47
| 2026-08-14 | Underserved Community | LAKESIDE | N/A | Not Available | 64 | 46 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.91 | 0 | 192.95 | 8.91 | 184.04
| 2024-04-11 | Underserved Community | LA MESA | N/A | Not Available | 115 | 83 | N/A | 2023-07-31 | Not Available | Not Available | Not Available | -12.09 | Unknown | -4.59 | 0 | 496.37 | -16.68 | 513.05
| 2024-05-02 | Underserved Community | LA MESA | N/A | Not Available | 146 | 104 | N/A | 2023-09-05 | Not Available | Not Available | Not Available | -7.68 | Unknown | -2.94 | 0 | 496.37 | -10.62 | 506.99
| 2024-06-14 | Underserved Community | SPRING VALLEY | N/A | Not Available | 16 | 12 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -5.29 | Unknown | -2.02 | 0 | 496.45 | -7.31 | 503.76
| 2024-09-04 | N/A | CARLSBAD | N/A | Not Available | 61 | 43 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.68 | 0 | 1490.43 | -0.68 | 1491.11
| 2025-10-10 | Underserved Community | JAMUL | N/A | Not Available | 177 | 127 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -23.97 | Unknown | -4.23 | 0 | 163.83 | -28.2 | 192.03
| 2024-05-02 | N/A | EL CAJON | N/A | Not Available | 122 | 88 | N/A | 2023-08-10 | Not Available | Not Available | Not Available | -10.41 | Unknown | -3.97 | 0 | 496.37 | -14.38 | 510.75
| 2024-05-22 | Underserved Community | EL CAJON | N/A | Not Available | 645 | 461 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | -11.64 | Unknown | -4.24 | 0 | 496.37 | -15.88 | 512.25
| 2024-04-17 | Underserved Community | LA MESA | N/A | Not Available | 120 | 86 | N/A | 2023-08-02 | Not Available | Not Available | Not Available | -10.21 | Unknown | -3.88 | 0 | 496.37 | -14.09 | 510.46
| 2025-12-08 | N/A | LA JOLLA | N/A | Not Available | 133 | 95 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.12 | 0 | 534.53 | -5.9 | 540.43
| 2025-12-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 171 | 123 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 2.7 | 0 | 196.69 | 2.7 | 193.99
| 2026-01-23 | Underserved Community | LA MESA | N/A | Not Available | 139 | 99 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -10.41 | Unknown | 0.16 | 0 | 163.83 | -10.25 | 174.08
| 2024-06-23 | N/A | SAN DIEGO | N/A | Not Available | 161 | 115 | N/A | 2023-10-20 | Not Available | Not Available | Not Available | -5.81 | Unknown | -1.9 | 0 | 496.37 | -7.71 | 504.08
| 2027-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 112.5 | 3.05 | 109.45
| 2027-01-06 | N/A | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.45 | 0 | 196.69 | 6.45 | 190.24
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 213 | 153 | N/A |  | Not Available | Not Available | Not Available | 317.94 | Unknown | 209.84 | 0 | 196.44 | 527.78 | -331.34
| 2025-04-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 373 | 267 | N/A | 2023-08-23 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.03 | 0 | 496.45 | -5.46 | 501.91
| 2025-06-05 | N/A | SAN DIEGO | N/A | Not Available | 226 | 162 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -5.19 | Unknown | -1.98 | 0 | 496.45 | -7.17 | 503.62
| 2022-02-26 | Underserved Community | CARLSBAD | N/A | Not Available |  |  | N/A | 2021-06-16 | Not Available | Not Available | Not Available | -4.83 | Unknown | -2.32 | 0 | 98.03 | -7.15 | 105.18
| 2024-12-23 | Underserved Community | SAN MARCOS | N/A | Not Available | 86 | 62 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | -7.89 | Unknown | -3.03 | 0 | 154.79 | -10.92 | 165.71
| 2024-10-30 | Underserved Community | FALLBROOK | N/A | Not Available | 142 | 102 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -9.92 | Unknown | -3.77 | 0 | 436.48 | -13.69 | 450.17
| 2023-06-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 219 | 157 | N/A | 2023-06-06 | Not Available | Not Available | Not Available | -9.33 | Unknown | -3.54 | 0 | 545.68 | -12.87 | 558.55
| 2026-12-16 | N/A | LAS FLORES | N/A | Not Available | 80 | 58 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.78 | 0 | 76.08 | 1.78 | 74.3
| 2023-10-19 | N/A | CARDIFF | N/A | Not Available | 170 | 122 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | -5.36 | Unknown | 3.6 | 0 | 363.72 | -1.76 | 365.48
| 2023-11-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 154 | 110 | N/A | 2023-05-24 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.67 | 0 | 98.41 | -6.1 | 104.51
| 2027-02-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 30 | 21 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.24 | 0 | 223.16 | 4.24 | 218.92
| 2027-08-07 | N/A | LA JOLLA | N/A | Not Available | 167 | 120 | N/A | 2023-09-06 | Not Available | Not Available | Not Available | -6.64 | Unknown | -2.52 | 0 | 496.37 | -9.16 | 505.53
| 2026-12-10 | N/A | ENCINITAS | N/A | Not Available | 46 | 34 | N/A | 2025-01-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.06 | 0 | 279.3 | 8.06 | 271.24
| 2024-12-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 17 | 13 | N/A | 2024-02-15 | Not Available | Not Available | Not Available | 189.35 | Unknown | 133.91 | 0 | 549.23 | 323.26 | 225.97
| 2024-09-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2023-09-14 | Not Available | Not Available | Not Available | -8.16 | Unknown | -3.08 | 0 | 496.37 | -11.24 | 507.61
| 2027-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | 31 | 23 | N/A | 2025-06-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-08-19 | Underserved Community | OCEANSIDE | N/A | Not Available | 29 | 21 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 36.5 | 0 | 197.01 | 36.5 | 160.51
| 2026-11-04 | N/A | DEL MAR | N/A | Not Available | 35 | 25 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.06 | 0 | 278.82 | 11.06 | 267.76
| 2025-08-28 | N/A | CARLSBAD | N/A | Not Available | 24 | 18 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -9.16 | Unknown | -2.44 | 0 | 515.81 | -11.6 | 527.41
| 2026-05-14 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 0 | 192.83 | 5.69 | 187.14
| 2026-03-11 | N/A | SAN DIEGO | N/A | Not Available | 76 | 54 | N/A | 2024-07-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.46 | 0 | 983.86 | 4.46 | 979.4
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 93 | 67 | N/A |  | Not Available | Not Available | Not Available | 617 | Unknown | 299.32 | 0 | 196.59 | 916.32 | -719.73
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 240 | 172 | N/A | 2025-05-13 | Not Available | Not Available | Not Available | -10.39 | Unknown | 527.38 | 0 | 3263.88 | 516.99 | 2746.89
| 2026-11-14 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.92 | 0 | 197.01 | 12.92 | 184.09
| 2026-05-29 | N/A | EL CAJON | N/A | Not Available | 107 | 77 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.64 | 0 | 139.89 | 7.64 | 132.25
| 2024-09-14 | N/A | DANA POINT | N/A | Not Available | 95 | 69 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | 249.15 | Unknown | 177.54 | 0 | 158.79 | 426.69 | -267.9
| 2024-04-20 | Underserved Community | FALLBROOK | N/A | Not Available |  |  | N/A | 2022-09-20 | Not Available | Not Available | Not Available | -2.65 | Unknown | -1.05 | 0 | 439.58 | -3.7 | 443.28
| 2024-10-12 | Underserved Community | SAN MARCOS | N/A | Not Available | 171 | 123 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | -3.3 | Unknown | -1.26 | 0 | 436.48 | -4.56 | 441.04
| 2023-06-23 | Underserved Community | LA JOLLA | N/A | Not Available | 162 | 116 | N/A | 2023-05-24 | Not Available | Not Available | Not Available | 73.34 | Unknown | 206.81 | 0 | 991.56 | 280.15 | 711.41
| 2023-08-29 | Underserved Community | OCEANSIDE | N/A | Not Available | 203 | 145 | N/A | 2023-08-17 | Not Available | Not Available | Not Available | -10.24 | Unknown | -2.04 | 0 | 104.98 | -12.28 | 117.26
| 2023-11-03 | Underserved Community | VISTA | N/A | Not Available | 157 | 113 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | -8.06 | Unknown | -1.85 | 0 | 98.41 | -9.91 | 108.32
| 2025-09-11 | Underserved Community | VISTA | N/A | Not Available | 161 | 115 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.21 | 0 | 197.01 | 3.21 | 193.8
| 2023-12-14 | N/A | SAN DIEGO | N/A | Not Available | 131 | 95 | N/A | 2023-04-11 | Not Available | Not Available | Not Available | -5.39 | Unknown | -2.06 | 0 | 154.79 | -7.45 | 162.24
| 2024-11-14 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 172 | 122 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -6.91 | Unknown | -2.64 | 0 | 602.74 | -9.55 | 612.29
| 2025-03-09 | Underserved Community | SAN MARCOS | N/A | Not Available | 597 | 427 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.54 | 0 | 153.75 | 5.54 | 148.21
| 2024-02-15 | N/A | SAN CLEMENTE | N/A | Not Available | 116 | 84 | N/A | 2023-05-01 | Not Available | Not Available | Not Available | -9.9 | Unknown | -3.74 | 0 | 111.67 | -13.64 | 125.31
| 2023-12-13 | Underserved Community | VISTA | N/A | Not Available | 93 | 67 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | -3.4 | Unknown | -1.3 | 0 | 363.72 | -4.7 | 368.42
| 2023-06-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 206 | 148 | N/A | 2023-06-05 | Not Available | Not Available | Not Available | -23.71 | Unknown | 22.04 | 0 | 71.35 | -1.67 | 73.02
| 2024-01-24 | Underserved Community | DANA POINT | N/A | Not Available | 192 | 138 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -9.26 | Unknown | -3.5 | 0 | 67.06 | -12.76 | 79.82
| 2025-01-12 | N/A | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2023-06-13 | Not Available | Not Available | Not Available | -6.52 | Unknown | -1.54 | 0 | 154.79 | -8.06 | 162.85
| 2024-01-05 | Underserved Community | OCEANSIDE | N/A | Not Available | 37 | 27 | N/A | 2023-10-12 | Not Available | Not Available | Not Available | -10.71 | Unknown | -4.06 | 0 | 480.37 | -14.77 | 495.14
| 2027-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 25 | 18 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.03 | 0 | 114.3 | 7.03 | 107.27
| 2027-01-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 51 | 36 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | -19.8 | Unknown | -10.76 | 0 | 196.44 | -30.56 | 227
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 87 | 63 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.75 | 0 | 163.83 | -4.02 | 167.85
| 2025-06-26 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 83 | 59 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | -10.99 | Unknown | -2.95 | 0 | 514.57 | -13.94 | 528.51
| 2025-08-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 7 | 5 | N/A | 2023-08-04 | Not Available | Not Available | Not Available | 257.99 | Unknown | 1502.96 | 0 | 851.13 | 1760.95 | -909.82
| 2025-08-17 | Underserved Community | VALLEY CENTER | N/A | Not Available | 82 | 60 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -3.59 | Unknown | -1.16 | 0 | 41.38 | -4.75 | 46.13
| 2024-06-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 656 | 470 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -4.76 | Unknown | -1.56 | 0 | 372.29 | -6.32 | 378.61
| 2025-08-15 | N/A | SAN DIEGO | N/A | Not Available | 6 | 4 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.49 | 0 | 192.95 | 8.49 | 184.46
| 2026-06-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 192.95 | 4.71 | 188.24
| 2025-05-25 | Underserved Community | CHULA VISTA | N/A | Not Available | 127 | 91 | N/A | 2023-12-18 | Not Available | Not Available | Not Available | 244.9 | Unknown | 175.01 | 0 | 148.7 | 419.91 | -271.21
| 2026-01-22 | Underserved Community | LAKESIDE | N/A | Not Available | 9 | 7 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.02 | 0 | 196.69 | 3.02 | 193.67
| 2026-03-15 | N/A | SAN DIEGO | N/A | Not Available | 13 | 9 | N/A | 2024-03-25 | Not Available | Not Available | Not Available | -16.23 | Unknown | 555.63 | 0 | 534.53 | 539.4 | -4.87
| 2027-01-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A |  | Not Available | Not Available | Not Available | 727.49 | Unknown | 679.01 | 0 | 1652.59 | 1406.5 | 246.09
| 2025-03-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | -12.71 | Unknown | 2.06 | 0 | 231.39 | -10.65 | 242.04
| 2027-01-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2025-04-11 | Not Available | Not Available | Not Available | -10.26 | Unknown | 507.62 | 0 | 797.33 | 497.36 | 299.97
| 2025-11-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 108 | 78 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | 1538.5 | Unknown | 720.14 | 0 | 515.81 | 2258.64 | -1742.83
| 2026-11-06 | N/A | EL CAJON | N/A | Not Available | 9 | 7 | N/A | 2024-12-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.19 | 0 | 197.01 | 8.19 | 188.82
| 2026-04-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 9 | 7 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | -28.8 | Unknown | 24.29 | 0 | 529.2 | -4.51 | 533.71
| 2026-05-31 | Underserved Community | LA MESA | N/A | Not Available | 91 | 65 | N/A | 2024-08-30 | Not Available | Not Available | Not Available | -3 | Unknown | 157.35 | 0 | 1050.61 | 154.35 | 896.26
| 2025-12-26 | N/A | RANCHO LA COSTA | N/A | Not Available | 87 | 63 | N/A | 2024-05-17 | Not Available | Not Available | Not Available | -6.75 | Unknown | -1.59 | 0 | 209.87 | -8.34 | 218.21
| 2026-12-05 | N/A | SAN DIEGO | N/A | Not Available | 89 | 63 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | -9.31 | Unknown | 23.55 | 0 | 197.01 | 14.24 | 182.77
| 2025-12-13 | N/A | RANCHO SANTA FE | N/A | Not Available | 89 | 63 | N/A | 2024-04-25 | Not Available | Not Available | Not Available | -5.31 | Unknown | 0.05 | 0 | 209.87 | -5.26 | 215.13
| 2026-03-01 | N/A | DEL MAR | N/A | Not Available | 99 | 71 | N/A | 2024-09-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.66 | 0 | 192.83 | 11.66 | 181.17
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 91 | 65 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -4.91 | Unknown | -0.8 | 0 | 163.83 | -5.71 | 169.54
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 3 | 3 | N/A |  | Not Available | Not Available | Not Available | 517.88 | Unknown | 211.68 | 0 | 450.11 | 729.56 | -279.45
| 2024-08-30 | Underserved Community | LAKESIDE | N/A | Not Available | 122 | 88 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -11.42 | Unknown | -1.48 | 0 | 158.14 | -12.9 | 171.04
| 2026-01-30 | N/A | ENCINITAS | N/A | Not Available | 8 | 6 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 196.69 | 4.39 | 192.3
| 2026-10-23 | N/A | SOLANA BEACH | N/A | Not Available | 140 | 100 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | -14.61 | Unknown | -7.95 | 0 | 288.94 | -22.56 | 311.5
| 2026-04-10 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 33 | 23 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | -46.95 | Unknown | 1674.01 | 0 | 400.94 | 1627.06 | -1226.12
| 2026-04-16 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -16.61 | Unknown | -2.65 | 0 | 787.98 | -19.26 | 807.24
| 2027-06-03 | N/A | ENCINITAS | N/A | Not Available | 14 | 10 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 118.25 | 2.02 | 116.23
| 2026-11-07 | Underserved Community | EL CAJON | N/A | Not Available | 28 | 20 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.16 | 0 | 197.01 | 9.16 | 187.85
| 2024-01-12 | Underserved Community | SPRING VALLEY | N/A | Not Available | 39 | 28 | N/A | 2023-02-27 | Not Available | Not Available | Not Available | -11.63 | Unknown | -4.42 | 0 | 363.72 | -16.05 | 379.77
| 2025-03-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 31 | 23 | N/A | 2023-06-26 | Not Available | Not Available | Not Available | -9.16 | Unknown | -3.48 | 0 | 495.75 | -12.64 | 508.39
| 2023-12-14 | Underserved Community | EL CAJON | N/A | Not Available | 69 | 49 | N/A | 2023-04-13 | Not Available | Not Available | Not Available | -7.82 | Unknown | -0.17 | 0 | 98.41 | -7.99 | 106.4
| 2026-09-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 46 | 34 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.16 | 0 | 142.83 | 14.16 | 128.67
| 2023-12-20 | Underserved Community | ALPINE | N/A | Not Available | 77 | 55 | N/A | 2023-03-02 | Not Available | Not Available | Not Available | -8.52 | Unknown | -3.25 | 0 | 363.72 | -11.77 | 375.49
| 2025-01-24 | Underserved Community | SAN MARCOS | N/A | Not Available | 197 | 141 | N/A | 2023-07-07 | Not Available | Not Available | Not Available | -13.25 | Unknown | -3.22 | 0 | 153.75 | -16.47 | 170.22
| 2022-09-26 | N/A | SANTEE | N/A | Not Available | 58 | 42 | N/A | 2023-04-20 | Not Available | Not Available | Not Available | -5.87 | Unknown | -1.21 | 0 | 154.79 | -7.08 | 161.87
| 2025-08-21 | Underserved Community | CHULA VISTA | N/A | Not Available | 184 | 132 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 4.94 | 0 | 95 | 4.94 | 90.06
| 2026-04-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 74 | 54 | N/A |  | Not Available | Not Available | Not Available | 190.31 | Unknown | 130.64 | 0 | 1050.61 | 320.95 | 729.66
| 2026-08-29 | N/A | DEL MAR | N/A | Not Available | 43 | 31 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.52 | 0 | 197.01 | 13.52 | 183.49
| 2023-12-29 | N/A | SANTEE | N/A | Not Available | 126 | 90 | N/A | 2023-05-03 | Not Available | Not Available | Not Available | -10.37 | Unknown | -3.95 | 0 | 363.72 | -14.32 | 378.04
| 2023-08-24 | Underserved Community | JAMUL | N/A | Not Available | 162 | 116 | N/A | 2023-07-25 | Not Available | Not Available | Not Available | -8.62 | Unknown | -2.16 | 0 | 98.66 | -10.78 | 109.44
| 2023-12-01 | N/A | DEL MAR | N/A | Not Available | 77 | 55 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | -5.65 | Unknown | 0.57 | 0 | 153.75 | -5.08 | 158.83
| 2026-02-13 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.78 | 0 | 118.25 | 1.78 | 116.47
| 2024-02-10 | Underserved Community | ALPINE | N/A | Not Available | 127 | 91 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | -9.24 | Unknown | -3.49 | 0 | 499.96 | -12.73 | 512.69
| 2024-11-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 133 | 95 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.48 | 0 | 495.75 | -5.4 | 501.15
| 2025-03-10 | N/A | ESCONDIDO | N/A | Not Available | 200 | 144 | N/A | 2023-10-30 | Not Available | Not Available | Not Available | -6.86 | Unknown | -2.21 | 0 | 512.85 | -9.07 | 521.92
| 2024-02-10 | Underserved Community | EL CAJON | N/A | Not Available | 78 | 56 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | -3.3 | Unknown | -1.26 | 0 | 363.72 | -4.56 | 368.28
| 2025-02-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 139 | 99 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -14.61 | Unknown | -5.55 | 0 | 153.75 | -20.16 | 173.91
| 2025-09-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 45 | 33 | N/A | 2023-12-27 | Not Available | Not Available | Not Available | -7.44 | Unknown | -1.73 | 0 | 515.81 | -9.17 | 524.98
| 2025-01-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 81 | 57 | N/A | 2023-08-03 | Not Available | Not Available | Not Available | -13.6 | Unknown | 6.59 | 0 | 495.75 | -7.01 | 502.76
| 2024-09-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 129 | 93 | N/A | 2023-05-18 | Not Available | Not Available | Not Available | -5.38 | Unknown | -1.35 | 0 | 599.5 | -6.73 | 606.23
| 2027-05-28 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 63 | 45 | N/A |  | Not Available | Not Available | Not Available | 181.27 | Unknown | 128.29 | 0 | 186.4 | 309.56 | -123.16
| 2025-06-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2023-11-30 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.24 | 0 | 513.31 | -5.85 | 519.16
| 2023-11-23 | Underserved Community | ALPINE | N/A | Not Available | 95 | 69 | N/A | 2023-06-09 | Not Available | Not Available | Not Available | -12.21 | Unknown | -4.63 | 0 | 98.41 | -16.84 | 115.25
| 2025-07-10 | N/A | SAN DIEGO | N/A | Not Available | 126 | 90 | N/A | 2024-01-10 | Not Available | Not Available | Not Available | -10.66 | Unknown | -2.85 | 0 | 154.99 | -13.51 | 168.5
| 2026-12-31 | Underserved Community | VISTA | N/A | Not Available | 58 | 42 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | 815.04 | Unknown | 541.2 | 0 | 196.59 | 1356.24 | -1159.65
| 2024-03-08 | N/A | SAN CLEMENTE | N/A | Not Available | 28 | 20 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1380.32 | 0 | 247.27 | 1380.32 | -1133.05
| 2026-10-08 | N/A | SAN DIEGO | N/A | Not Available | 17 | 13 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.89 | 0 | 197.01 | 3.89 | 193.12
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 85 | 61 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.63 | 0 | 192.95 | 2.63 | 190.32
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 241 | 173 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.69 | 0 | 163.83 | 2.69 | 161.14
| 2025-01-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2023-09-11 | Not Available | Not Available | Not Available | -6.34 | Unknown | -0.01 | 0 | 153.83 | -6.35 | 160.18
| 2027-01-17 | Underserved Community | EL CAJON | N/A | Not Available | 29 | 21 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | 165.95 | Unknown | 202.05 | 0 | 196.59 | 368 | -171.41
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 150 | 108 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -14.31 | Unknown | -3.33 | 0 | 163.83 | -17.64 | 181.47
| 2026-09-11 | N/A | SAN DIEGO | N/A | Not Available | 120 | 86 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.15 | 0 | 196.69 | 3.15 | 193.54
| 2026-04-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2024-07-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.13 | 0 | 192.51 | 8.13 | 184.38
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 164 | 118 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -16.75 | Unknown | -3.87 | 0 | 163.83 | -20.62 | 184.45
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 164 | 118 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -3.63 | Unknown | -0.85 | 0 | 163.83 | -4.48 | 168.31
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 150 | 108 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -25.05 | Unknown | 675.55 | 0 | 163.83 | 650.5 | -486.67
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 32 | 24 | N/A | 2024-10-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.83 | 0 | 197.01 | 3.83 | 193.18
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 157 | 113 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -19.93 | Unknown | -4.61 | 0 | 163.83 | -24.54 | 188.37
| 2024-05-03 | N/A | LAGUNA NIGUEL | N/A | Not Available | 78 | 56 | N/A | 2023-11-03 | Not Available | Not Available | Not Available | 417.36 | Unknown | 263.42 | 0 | 153.83 | 680.78 | -526.95
| 2027-03-27 | N/A | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 111 | 79 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2025-11-22 | N/A | SAN DIEGO | N/A | Not Available | 203 | 145 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.56 | 0 | 42.63 | 8.56 | 34.07
| 2025-08-09 | N/A | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.69 | 0 | 196.69 | 9.69 | 187
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 160 | 114 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.13 | 0 | 380.88 | 3.13 | 377.75
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 220 | 158 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.43 | 0 | 163.83 | 9.43 | 154.4
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 234 | 168 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.85 | 0 | 163.83 | 4.85 | 158.98
| 2027-03-25 | N/A | SAN CLEMENTE | N/A | Not Available | 35 | 25 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 164 | 118 | N/A | 2024-06-01 | Not Available | Not Available | Not Available | -10.97 | Unknown | -2.56 | 0 | 163.83 | -13.53 | 177.36
| 2026-11-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 67 | 47 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.87 | 0 | 197.01 | 3.87 | 193.14
| 2025-06-22 | N/A | ENCINITAS | N/A | Not Available | 86 | 62 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1919.66 | 0 | 483.59 | 1919.66 | -1436.07
| 2025-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 188 | 135 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | -4.58 | Unknown | 240.92 | 0 | 288.94 | 236.34 | 52.6
| 2023-10-11 | N/A | SAN DIEGO | N/A | Not Available | 40 | 29 | N/A | 2023-03-08 | Not Available | Not Available | Not Available | -7.39 | Unknown | -2.8 | 0 | 363.72 | -10.19 | 373.91
| 2024-08-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 117 | 85 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -20.57 | Unknown | -3.56 | 0 | 158.79 | -24.13 | 182.92
| 2025-08-29 | Underserved Community | BONITA | N/A | Not Available | 110 | 78 | N/A | 2024-03-11 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.86 | 0 | 515.81 | -4.6 | 520.41
| 2026-10-28 | N/A | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2025-04-21 | Not Available | Not Available | Not Available | 266.88 | Unknown | 179.51 | 0 | 196.59 | 446.39 | -249.8
| 2024-03-06 | Underserved Community | SPRING VALLEY | N/A | Not Available | 44 | 32 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -33.47 | Unknown | 921.45 | 0 | 495.75 | 887.98 | -392.23
| 2026-06-29 | Underserved Community | CHULA VISTA | N/A | Not Available | 201 | 143 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.83 | 0 | 190.44 | 10.83 | 179.61
| 2025-06-22 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 83 | 59 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | 273.61 | Unknown | 146.15 | 0 | 514.57 | 419.76 | 94.81
| 2024-12-18 | Underserved Community | CHULA VISTA | N/A | Not Available | 287 | 205 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 72.33 | 0 | 787.98 | 72.33 | 715.65
| 2026-03-14 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 59 | 43 | N/A | 2024-05-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.13 | 0 | 788.08 | 8.13 | 779.95
| 2025-05-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 67 | 49 | N/A | 2023-10-30 | Not Available | Not Available | Not Available | 183.68 | Unknown | 129.88 | 0 | 513.31 | 313.56 | 199.75
| 2024-12-07 | Underserved Community | VISTA | N/A | Not Available | 229 | 165 | N/A | 2023-12-11 | Not Available | Not Available | Not Available | 87.79 | Unknown | 122.72 | 0 | 153.75 | 210.51 | -56.76
| 2024-02-06 | Underserved Community | EL CAJON | N/A | Not Available | 352 | 252 | N/A | 2024-03-25 | Not Available | Not Available | Not Available | -27.77 | Unknown | -4.12 | 0 | 153.75 | -31.89 | 185.64
| 2023-03-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -4.59 | Unknown | -1.74 | 0 | 363.72 | -6.33 | 370.05
| 2025-09-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A | 2024-03-08 | Not Available | Not Available | Not Available | -8.22 | Unknown | 1.19 | 0 | 163.83 | -7.03 | 170.86
| 2026-01-02 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.19 | 0 | 196.69 | 6.19 | 190.5
| 2025-02-07 | Underserved Community | OCEANSIDE | N/A | Not Available | 116 | 84 | N/A | 2023-04-26 | Not Available | Not Available | Not Available | -5.55 | Unknown | -2.12 | 0 | 153.75 | -7.67 | 161.42
| 2023-12-29 | Underserved Community | LA MESA | N/A | Not Available | 75 | 54 | N/A | 2023-03-15 | Not Available | Not Available | Not Available | -11.38 | Unknown | -4.33 | 0 | 363.72 | -15.71 | 379.43
| 2025-03-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2023-07-05 | Not Available | Not Available | Not Available | -9.53 | Unknown | 255.47 | 0 | 495.75 | 245.94 | 249.81
| 2026-11-07 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.44 | 0 | 197.01 | 5.44 | 191.57
| 2026-04-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.25 | 0 | 192.95 | 5.25 | 187.7
| 2027-02-10 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.49 | 0 | 196.44 | 5.49 | 190.95
| 2025-04-13 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 153 | 109 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -9.16 | Unknown | -2.14 | 0 | 500.87 | -11.3 | 512.17
| 2025-07-10 | Underserved Community | OCEANSIDE | N/A | Not Available | 78 | 56 | N/A | 2024-01-31 | Not Available | Not Available | Not Available | -7.02 | Unknown | -1.64 | 0 | 158.79 | -8.66 | 167.45
| 2027-01-13 | N/A | LAGUNA NIGUEL | N/A | Not Available | 88 | 64 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2026-01-23 | Underserved Community | SAN MARCOS | N/A | Not Available | 47 | 33 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.17 | 0 | 196.69 | 8.17 | 188.52
| 2027-04-15 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 35 | 25 | N/A | 2025-06-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.98 | 0 | 118.25 | 1.98 | 116.27
| 2024-08-25 | Underserved Community | BONSALL | N/A | Not Available | 36 | 26 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -13.88 | Unknown | -1.35 | 0 | 158.79 | -15.23 | 174.02
| 2026-04-30 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | 416.09 | Unknown | 218.44 | 0 | 1049.43 | 634.53 | 414.9
| 2027-04-21 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 37 | 27 | N/A | 2025-05-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.98 | 0 | 118.25 | 1.98 | 116.27
| 2026-02-15 | N/A | ALPINE | N/A | Not Available | 36 | 26 | N/A | 2025-03-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.52 | 0 | 1063.08 | 12.52 | 1050.56
| 2025-03-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 153 | 109 | N/A | 2024-03-15 | Not Available | Not Available | Not Available | -5.11 | Unknown | -1.19 | 0 | 515.81 | -6.3 | 522.11
| 2027-04-03 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-05-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.92 | 0 | 118.25 | 2.92 | 115.33
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 709 | 506 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -14.95 | Unknown | -8.16 | 0 | 154.99 | -23.11 | 178.1
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 312 | 223 | N/A | 2025-03-20 | Not Available | Not Available | Not Available | -11.69 | Unknown | -6.37 | 0 | 464.73 | -18.06 | 482.79
| 2027-03-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 12 | 8 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 49.6 | 0 | 196.59 | 49.6 | 146.99
| 2026-03-29 | N/A | SANTEE | N/A | Not Available | 81 | 59 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.58 | 0 | 192.83 | 6.58 | 186.25
| 2023-12-05 | Underserved Community | VISTA | N/A | Not Available | 117 | 85 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | -38.68 | Unknown | -14.74 | 0 | 153.87 | -53.42 | 207.29
| 2024-06-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 92 | 66 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.89 | 0 | 153.75 | -6.85 | 160.6
| 2025-10-07 | N/A | SOUTH LAGUNA | N/A | Not Available | 12 | 10 | N/A | 2022-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.24 | 0 | 197.01 | 11.24 | 185.77
| 2025-02-20 | Underserved Community | SAN MARCOS | N/A | Not Available | 561 | 401 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.66 | 0 | 197.01 | 18.66 | 178.35
| 2025-01-25 | N/A | CARLSBAD | N/A | Not Available | 130 | 94 | N/A | 2023-04-19 | Not Available | Not Available | Not Available | -4.75 | Unknown | -1.81 | 0 | 154.79 | -6.56 | 161.35
| 2026-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 146 | 104 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | -7.38 | Unknown | 383.97 | 0 | 1066.51 | 376.59 | 689.92
| 2024-11-20 | N/A | LAGUNA NIGUEL | N/A | Not Available | 338 | 242 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.17 | 0 | 148.54 | 9.17 | 139.37
| 2025-06-22 | N/A | DANA POINT | N/A | Not Available | 17 | 13 | N/A | 2024-07-30 | Not Available | Not Available | Not Available | 120.84 | Unknown | 86.5 | 0 | 192.95 | 207.34 | -14.39
| 2024-02-24 | N/A | LAGUNA NIGUEL | N/A | Not Available | 128 | 92 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | 374.26 | Unknown | 497.37 | 0 | 111.67 | 871.63 | -759.96
| 2024-03-20 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 137 | 99 | N/A | 2023-07-10 | Not Available | Not Available | Not Available | -10.93 | Unknown | -4.17 | 0 | 110.98 | -15.1 | 126.08
| 2025-01-31 | N/A | SAN CLEMENTE | N/A | Not Available | 23 | 17 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.14 | 0 | 104.94 | 14.14 | 90.8
| 2026-10-06 | N/A | DANA POINT | N/A | Not Available | 23 | 17 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.28 | 0 | 196.44 | 12.28 | 184.16
| 2024-03-20 | N/A | SAN DIEGO | N/A | Not Available | 114 | 82 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -7.02 | Unknown | -2.66 | 0 | 495.75 | -9.68 | 505.43
| 2024-12-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 115 | 81 | N/A | 2023-02-27 | Not Available | Not Available | Not Available | -6.99 | Unknown | -2.65 | 0 | 92.06 | -9.64 | 101.7
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 60 | 44 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 25.66 | 0 | 860.83 | 25.66 | 835.17
| 2024-01-31 | Underserved Community | SANTEE | N/A | Not Available | 213 | 153 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | -6.86 | Unknown | -2.58 | 0 | 363.72 | -9.44 | 373.16
| 2024-03-22 | N/A | SOLANA BEACH | N/A | Not Available | 39 | 29 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | -7.09 | Unknown | -2.68 | 0 | 495.75 | -9.77 | 505.52
| 2025-02-20 | N/A | SAN DIEGO | N/A | Not Available | 158 | 114 | N/A | 2023-06-13 | Not Available | Not Available | Not Available | -7.39 | Unknown | -1.63 | 0 | 153.75 | -9.02 | 162.77
| 2025-02-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 152 | 108 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -9.83 | Unknown | 6.52 | 0 | 341 | -3.31 | 344.31
| 2025-02-14 | Underserved Community | ESCONDIDO | N/A | Not Available | 65 | 47 | N/A | 2023-08-14 | Not Available | Not Available | Not Available | -9.2 | Unknown | -3.47 | 0 | 595.76 | -12.67 | 608.43
| 2026-05-28 | N/A | CARLSBAD | N/A | Not Available | 21 | 15 | N/A | 2024-06-28 | Not Available | Not Available | Not Available | -4.73 | Unknown | 1.48 | 0 | 192.51 | -3.25 | 195.76
| 2026-11-10 | N/A | SOLANA BEACH | N/A | Not Available | 19 | 15 | N/A | 2024-11-25 | Not Available | Not Available | Not Available | 349.71 | Unknown | 426.89 | 0 | 288.94 | 776.6 | -487.66
| 2026-08-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A |  | Not Available | Not Available | Not Available | 382.05 | Unknown | 2.55 | 0 | 190.44 | 384.6 | -194.16
| 2025-11-14 | N/A | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2024-03-19 | Not Available | Not Available | Not Available | -19.5 | Unknown | -4.52 | 0 | 43.07 | -24.02 | 67.09
| 2026-09-30 | N/A | RANCHO SANTA FE | N/A | Not Available | 24 | 18 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.74 | 0 | 279.3 | 9.74 | 269.56
| 2027-02-01 | Underserved Community | BONITA | N/A | Not Available | 52 | 38 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | -11.73 | Unknown | -6.38 | 0 | 196.44 | -18.11 | 214.55
| 2026-09-14 | Underserved Community | OCEANSIDE | N/A | Not Available | 22 | 16 | N/A | 2024-10-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 197.01 | 3.05 | 193.96
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 28 | 20 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.38 | 0 | 207.92 | -7.2 | 215.12
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 30 | 22 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.75 | 0 | 162.34 | -4.02 | 166.36
| 2025-09-25 | Underserved Community | SAN MARCOS | N/A | Not Available | 19 | 13 | N/A | 2024-01-26 | Not Available | Not Available | Not Available | -12.09 | Unknown | 12.77 | 0 | 613.88 | 0.68 | 613.2
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 42 | 30 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.94 | 0 | 207.92 | -10.34 | 218.26
| 2027-04-15 | Underserved Community | MISSION VIEJO | N/A | Not Available | 22 | 16 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.92 | 0 | 57.62 | 2.92 | 54.7
| 2024-10-10 | Underserved Community | FALLBROOK | N/A | Not Available | 46 | 34 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -3.76 | Unknown | -1.23 | 0 | 615.98 | -4.99 | 620.97
| 2025-09-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2023-12-11 | Not Available | Not Available | Not Available | -11.54 | Unknown | 0.52 | 0 | 152.86 | -11.02 | 163.88
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 40 | 28 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -6.2 | Unknown | -1.44 | 0 | 207.92 | -7.64 | 215.56
| 2026-01-29 | N/A | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.57 | 0 | 196.69 | 11.57 | 185.12
| 2025-11-06 | Underserved Community | CHULA VISTA | N/A | Not Available | 35 | 25 | N/A | 2024-01-16 | Not Available | Not Available | Not Available | 252.46 | Unknown | 183.43 | 0 | 153.49 | 435.89 | -282.4
| 2026-05-21 | Underserved Community | CHULA VISTA | N/A | Not Available | 48 | 34 | N/A |  | Not Available | Not Available | Not Available | 259.49 | Unknown | 141.11 | 0 | 1050.61 | 400.6 | 650.01
| 2025-07-12 | N/A | CORONADO | N/A | Not Available | 46 | 34 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | 164.62 | Unknown | 1122.7 | 0 | 500.87 | 1287.32 | -786.45
| 2026-05-29 | Underserved Community | OCEANSIDE | N/A | Not Available | 38 | 28 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | 571.24 | Unknown | 309.97 | 0 | 1050.61 | 881.21 | 169.4
| 2025-07-10 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 36 | 26 | N/A | 2024-12-06 | Not Available | Not Available | Not Available | -0.31 | Unknown | 21.4 | 0 | 1066.51 | 21.09 | 1045.42
| 2025-01-25 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2024-02-06 | Not Available | Not Available | Not Available | 189.35 | Unknown | 137.17 | 0 | 158.37 | 326.52 | -168.15
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 29 | 21 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | 291.46 | Unknown | 198.41 | 0 | 162.34 | 489.87 | -327.53
| 2026-08-27 | Underserved Community | OCEANSIDE | N/A | Not Available | 34 | 24 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.08 | 0 | 288.94 | 4.08 | 284.86
| 2025-07-26 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -7.9 | Unknown | -2.88 | 0 | 144.99 | -10.78 | 155.77
| 2025-09-20 | N/A | POWAY | N/A | Not Available | 20 | 14 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -4.81 | Unknown | -1.84 | 0 | 143.91 | -6.65 | 150.56
| 2027-01-22 | N/A | POWAY | N/A | Not Available | 41 | 29 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.56 | 0 | 196.44 | 11.56 | 184.88
| 2027-01-15 | Underserved Community | CHULA VISTA | N/A | Not Available | 41 | 29 | N/A |  | Not Available | Not Available | Not Available | 383.51 | Unknown | 801.36 | 0 | 797.75 | 1184.87 | -387.12
| 2026-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.43 | 0 | 196.69 | 9.43 | 187.26
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 36 | 26 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2027-02-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 17 | 13 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.95 | 0 | 196.44 | 7.95 | 188.49
| 2025-06-18 | Underserved Community | LA MESA | N/A | Not Available | 42 | 30 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -4.86 | Unknown | -1.14 | 0 | 1016.73 | -6 | 1022.73
| 2025-05-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A |  | Not Available | Not Available | Not Available | 244.9 | Unknown | 166.68 | 0 | 534.57 | 411.58 | 122.99
| 2025-04-01 | Underserved Community | VISTA | N/A | Not Available | 25 | 19 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | -8.21 | Unknown | -1.91 | 0 | 104.94 | -10.12 | 115.06
| 2027-03-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | -7.69 | Unknown | 380.41 | 0 | 196.44 | 372.72 | -176.28
| 2024-06-28 | Underserved Community | SPRING VALLEY | N/A | Not Available | 31 | 23 | N/A | 2023-11-08 | Not Available | Not Available | Not Available | -10.41 | Unknown | -2.44 | 0 | 158.14 | -12.85 | 170.99
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 28 | 20 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | 273.28 | Unknown | 185.98 | 0 | 207.92 | 459.26 | -251.34
| 2026-09-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.27 | 0 | 190.44 | 10.27 | 180.17
| 2023-10-12 | Underserved Community | FALLBROOK | N/A | Not Available | 68 | 48 | N/A |  | Not Available | Not Available | Not Available | -2.66 | Unknown | 571.43 | 0 | 595.66 | 568.77 | 26.89
| 2025-08-09 | Underserved Community | ESCONDIDO | N/A | Not Available | 67 | 47 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | -12.12 | Unknown | 6.61 | 0 | 591.49 | -5.51 | 597
| 2025-12-05 | N/A | OCEANSIDE | N/A | Not Available | 8 | 6 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | -0.63 | Unknown | 59.14 | 0 | 279.3 | 58.51 | 220.79
| 2025-04-13 | Underserved Community | BONITA | N/A | Not Available | 155 | 111 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | 647.72 | Unknown | 382.93 | 0 | 149.82 | 1030.65 | -880.83
| 2025-05-03 | N/A | POWAY | N/A | Not Available | 559 | 399 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.53 | 0 | 465.36 | 4.53 | 460.83
| 2024-02-23 | Underserved Community | VISTA | N/A | Not Available | 11 | 9 | N/A | 2024-10-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.63 | 0 | 1777.54 | 3.63 | 1773.91
| 2025-08-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 504 | 360 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | -10.29 | Unknown | -3.91 | 0 | 143.91 | -14.2 | 158.11
| 2024-05-19 | N/A | SAN CLEMENTE | N/A | Not Available | 93 | 67 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 493.74 | 0 | 98.26 | 493.74 | -395.48
| 2026-04-22 | N/A | ENCINITAS | N/A | Not Available | 58 | 42 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.52 | 0 | 192.83 | -3.79 | 196.62
| 2025-11-27 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2024-03-13 | Not Available | Not Available | Not Available | -5.31 | Unknown | -1.25 | 0 | 163.83 | -6.56 | 170.39
| 2026-09-06 | N/A | CARLSBAD | N/A | Not Available | 107 | 77 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.61 | 0 | 197.01 | 8.61 | 188.4
| 2026-10-17 | Underserved Community | SAN MARCOS | N/A | Not Available | 82 | 58 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.24 | 0 | 142.83 | 7.24 | 135.59
| 2027-03-14 | N/A | POWAY | N/A | Not Available | 9 | 7 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.76 | 0 | 142.53 | 5.76 | 136.77
| 2026-05-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2024-06-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.43 | 0 | 529.2 | 3.43 | 525.77
| 2025-04-26 | N/A | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2023-11-16 | Not Available | Not Available | Not Available | -10.78 | Unknown | 11.58 | 0 | 465.36 | 0.8 | 464.56
| 2024-12-04 | N/A | CARLSBAD | N/A | Not Available | 13 | 9 | N/A | 2023-12-26 | Not Available | Not Available | Not Available | -5.31 | Unknown | -0.54 | 0 | 158.79 | -5.85 | 164.64
| 2025-05-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | 370.02 | Unknown | 206.51 | 0 | 148.7 | 576.53 | -427.83
| 2026-07-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 108 | 78 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.78 | 0 | 999.88 | 6.78 | 993.1
| 2026-06-10 | N/A | SAN DIEGO | N/A | Not Available | 5 | 3 | N/A | 2025-06-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.49 | 0 | 118.25 | 2.49 | 115.76
| 2027-02-11 | Underserved Community | VISTA | N/A | Not Available | 78 | 56 | N/A |  | Not Available | Not Available | Not Available | 764.1 | Unknown | 513.86 | 0 | 196.69 | 1277.96 | -1081.27
| 2024-04-04 | N/A | DANA POINT | N/A | Not Available | 323 | 231 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 999.27 | 0 | Unknown | 999.27 | Unknown
| 2025-06-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A |  | Not Available | Not Available | Not Available | 587.17 | Unknown | 297.85 | 0 | 799.93 | 885.02 | -85.09
| 2025-08-07 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | -8.06 | Unknown | 4.39 | 0 | 158.79 | -3.67 | 162.46
| 2027-01-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | -31.32 | Unknown | 285.96 | 0 | 196.69 | 254.64 | -57.95
| 2025-01-01 | N/A | CARDIFF | N/A | Not Available | 202 | 144 | N/A | 2024-09-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.5 | 0 | 163.83 | 5.5 | 158.33
| 2025-05-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A | 2023-09-28 | Not Available | Not Available | Not Available | 481.71 | Unknown | 282.73 | 0 | 496.45 | 764.44 | -267.99
| 2025-11-08 | N/A | CHULA VISTA | N/A | Not Available | 63 | 45 | N/A |  | Not Available | Not Available | Not Available | 385.5 | Unknown | 237.19 | 0 | 163.83 | 622.69 | -458.86
| 2025-02-27 | N/A | SAN DIEGO | N/A | Not Available | 76 | 54 | N/A | 2023-07-05 | Not Available | Not Available | Not Available | -8.49 | Unknown | -2.05 | 0 | 40.01 | -10.54 | 50.55
| 2026-09-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A | 2024-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.58 | 0 | 142.83 | 6.58 | 136.25
| 2026-09-20 | Underserved Community | SPRING VALLEY | N/A | Not Available | 19 | 13 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 22.14 | 0 | 288.94 | 22.14 | 266.8
| 2027-01-30 | N/A | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.18 | 0 | 196.44 | 8.18 | 188.26
| 2024-01-03 | Underserved Community | SANTEE | N/A | Not Available | 71 | 51 | N/A | 2023-02-08 | Not Available | Not Available | Not Available | -4.9 | Unknown | -1.86 | 0 | 363.72 | -6.76 | 370.48
| 2023-09-29 | Underserved Community | EL CAJON | N/A | Not Available | 67 | 48 | N/A | 2023-02-09 | Not Available | Not Available | Not Available | -6.04 | Unknown | -1.1 | 0 | 98.41 | -7.14 | 105.55
| 2026-07-02 | N/A | SAN DIEGO | N/A | Not Available | 13 | 9 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.88 | 0 | 196.59 | 1.88 | 194.71
| 2024-01-04 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 184 | 132 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | -8.82 | Unknown | -3.33 | 0 | 363.72 | -12.15 | 375.87
| 2023-11-15 | Underserved Community | EL CAJON | N/A | Not Available | 125 | 89 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | -6.03 | Unknown | -2.31 | 0 | 363.72 | -8.34 | 372.06
| 2024-09-19 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 122 | 88 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | 232.94 | Unknown | 401.19 | 0 | 951.66 | 634.13 | 317.53
| 2024-01-24 | Underserved Community | LA MESA | N/A | Not Available | 519 | 371 | N/A | 2023-02-09 | Not Available | Not Available | Not Available | -9.9 | Unknown | -3.76 | 0 | 363.72 | -13.66 | 377.38
| 2023-06-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 21 | 15 | N/A |  | Not Available | Not Available | Not Available | 27.3 | Unknown | 16953.64 | 0 | 4562.44 | 16980.94 | -12418.5
| 2025-04-17 | Underserved Community | NATIONAL CITY | N/A | Not Available | 110 | 78 | N/A | 2023-10-13 | Not Available | Not Available | Not Available | 257.62 | Unknown | 152.79 | 0 | 496.37 | 410.41 | 85.96
| 2024-02-13 | Underserved Community | LA MESA | N/A | Not Available | 82 | 58 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -9.51 | Unknown | -3.61 | 0 | 364.52 | -13.12 | 377.64
| 2023-12-29 | N/A | SAN DIEGO | N/A | Not Available | 159 | 115 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | -11.78 | Unknown | -4.47 | 0 | 363.72 | -16.25 | 379.97
| 2024-02-01 | Underserved Community | SANTEE | N/A | Not Available | 51 | 37 | N/A | 2023-03-03 | Not Available | Not Available | Not Available | -4.9 | Unknown | -1.86 | 0 | 363.72 | -6.76 | 370.48
| 2026-06-21 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2024-10-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.33 | 0 | 197.01 | 6.33 | 190.68
| 2025-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -6.33 | Unknown | -1.69 | 0 | 515.81 | -8.02 | 523.83
| 2026-03-22 | Underserved Community | VISTA | N/A | Not Available | 22 | 16 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.63 | 0 | 197.01 | 8.63 | 188.38
| 2025-08-28 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 49 | 35 | N/A |  | Not Available | Not Available | Not Available | 185.02 | Unknown | 132.94 | 0 | 186.4 | 317.96 | -131.56
| 2026-09-25 | N/A | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.06 | 0 | 197.01 | 8.06 | 188.95
| 2025-02-03 | Underserved Community | LEMON GROVE | N/A | Not Available | 70 | 50 | N/A | 2023-08-10 | Not Available | Not Available | Not Available | -4.27 | Unknown | 1.4 | 0 | 153.87 | -2.87 | 156.74
| 2025-08-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | 181.75 | Unknown | 97.1 | 0 | 500.87 | 278.85 | 222.02
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 13 | 9 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.67 | 0 | 192.95 | 2.67 | 190.28
| 2023-04-26 | N/A | ENCINITAS | N/A | Not Available | 148 | 106 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -2.9 | Unknown | 3.86 | 0 | 534.53 | 0.96 | 533.57
| 2025-02-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A | 2023-04-27 | Not Available | Not Available | Not Available | -5.7 | Unknown | -2.17 | 0 | 499.96 | -7.87 | 507.83
| 2024-01-25 | Underserved Community | SANTEE | N/A | Not Available | 106 | 76 | N/A | 2023-04-04 | Not Available | Not Available | Not Available | -8.13 | Unknown | -3.1 | 0 | 363.72 | -11.23 | 374.95
| 2023-12-06 | Underserved Community | LEMON GROVE | N/A | Not Available | 82 | 59 | N/A | 2023-03-13 | Not Available | Not Available | Not Available | -5.3 | Unknown | -2.03 | 0 | 363.72 | -7.33 | 371.05
| 2025-04-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2023-08-31 | Not Available | Not Available | Not Available | -7.91 | Unknown | -2.87 | 0 | 480.37 | -10.78 | 491.15
| 2024-05-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 118 | 84 | N/A | 2024-05-09 | Not Available | Not Available | Not Available | -6.75 | Unknown | 0.25 | 0 | 163.83 | -6.5 | 170.33
| 2023-12-15 | Underserved Community | EL CAJON | N/A | Not Available | 65 | 46 | N/A | 2023-02-08 | Not Available | Not Available | Not Available | -11.87 | Unknown | -4.51 | 0 | 363.72 | -16.38 | 380.1
| 2026-05-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 175 | 125 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | -0.62 | Unknown | 34.28 | 0 | 190.44 | 33.66 | 156.78
| 2026-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 150 | 107 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | 4148.37 | Unknown | 5031.04 | 0 | 1066.51 | 9179.41 | -8112.9
| 2025-03-07 | Underserved Community | CHULA VISTA | N/A | Not Available | 106 | 76 | N/A | 2023-08-16 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.68 | 0 | 495.75 | -6.11 | 501.86
| 2025-09-08 | Underserved Community | CHULA VISTA | N/A | Not Available | 42 | 30 | N/A | 2024-01-05 | Not Available | Not Available | Not Available | 435.54 | Unknown | 232.73 | 0 | 515.81 | 668.27 | -152.46
| 2024-02-27 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 78 | 56 | N/A | 2023-06-12 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.49 | 0 | 499.96 | -5.41 | 505.37
| 2024-01-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2023-03-31 | Not Available | Not Available | Not Available | -9.13 | Unknown | -3.46 | 0 | 98.41 | -12.59 | 111
| 2024-12-15 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 216 | 154 | N/A | 2023-09-11 | Not Available | Not Available | Not Available | -4.99 | Unknown | 49.94 | 0 | 363.72 | 44.95 | 318.77
| 2024-01-04 | Underserved Community | LA MESA | N/A | Not Available | 69 | 49 | N/A | 2023-02-21 | Not Available | Not Available | Not Available | -3.78 | Unknown | -1.43 | 0 | 1330.18 | -5.21 | 1335.39
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 41 | 29 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -6.2 | Unknown | -1.44 | 0 | 207.92 | -7.64 | 215.56
| 2024-02-14 | Underserved Community | LA MESA | N/A | Not Available | 73 | 53 | N/A | 2023-04-05 | Not Available | Not Available | Not Available | -14.21 | Unknown | -5.4 | 0 | 144.8 | -19.61 | 164.41
| 2026-10-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 136 | 98 | N/A | 2025-03-20 | Not Available | Not Available | Not Available | -10.55 | Unknown | -4.11 | 0 | 197.01 | -14.66 | 211.67
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 41 | 29 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -6.2 | Unknown | -1.44 | 0 | 207.92 | -7.64 | 215.56
| 2025-11-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 118 | 84 | N/A | 2023-05-11 | Not Available | Not Available | Not Available | -10.98 | Unknown | -1.8 | 0 | 98.41 | -12.78 | 111.19
| 2023-10-13 | Underserved Community | EL CAJON | N/A | Not Available | 2 | 2 | N/A | 2023-02-07 | Not Available | Not Available | Not Available | -8.85 | Unknown | -3.36 | 0 | 363.72 | -12.21 | 375.93
| 2025-03-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 82 | 58 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | 338.48 | Unknown | 389.2 | 0 | 480.44 | 727.68 | -247.24
| 2023-11-03 | Underserved Community | LA MESA | N/A | Not Available | 192 | 138 | N/A | 2023-04-11 | Not Available | Not Available | Not Available | -10.06 | Unknown | -2.6 | 0 | 95.13 | -12.66 | 107.79
| 2027-02-20 | N/A | SAN DIEGO | N/A | Not Available | 53 | 39 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.6 | 0 | 196.59 | 3.6 | 192.99
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 234 | 168 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.07 | 0 | 163.83 | 2.07 | 161.76
| 2025-05-22 | Underserved Community | BONITA | N/A | Not Available | 52 | 38 | N/A | 2023-08-08 | Not Available | Not Available | Not Available | -6.16 | Unknown | -2.36 | 0 | 496.37 | -8.52 | 504.89
| 2025-12-26 | N/A | SAN DIEGO | N/A | Not Available | 60 | 42 | N/A | 2024-05-20 | Not Available | Not Available | Not Available | -7.11 | Unknown | -0.2 | 0 | 162.34 | -7.31 | 169.65
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 99 | 71 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.75 | 0 | 192.95 | 3.75 | 189.2
| 2025-03-29 | N/A | SAN DIEGO | N/A | Not Available | 84 | 60 | N/A | 2023-10-02 | Not Available | Not Available | Not Available | -8 | Unknown | 43.94 | 0 | 480.37 | 35.94 | 444.43
| 2025-07-20 | N/A | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2023-12-14 | Not Available | Not Available | Not Available | -38.6 | Unknown | 1472.03 | 0 | 515.81 | 1433.43 | -917.62
| 2026-08-22 | N/A | SOLANA BEACH | N/A | Not Available | 47 | 35 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.53 | 0 | 197.01 | -0.53 | 197.54
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | 213 | 153 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 542.95 | 0 | 197.01 | 542.95 | -345.94
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 231 | 165 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 163.83 | 3.17 | 160.66
| 2026-03-24 | N/A | DANA POINT | N/A | Not Available | 67 | 47 | N/A | 2025-05-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.8 | 0 | 197.01 | 4.8 | 192.21
| 2026-11-26 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | -18.79 | Unknown | 36.66 | 0 | 1066.55 | 17.87 | 1048.68
| 2025-09-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 246 | 176 | N/A |  | Not Available | Not Available | Not Available | 587.3 | Unknown | 281.95 | 0 | 149.82 | 869.25 | -719.43
| 2026-01-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 136 | 97 | N/A | 2024-08-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.43 | 0 | 501.18 | 3.43 | 497.75
| 2026-05-30 | N/A | CARLSBAD | N/A | Not Available | 76 | 54 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | -10.09 | Unknown | 6.02 | 0 | 344.62 | -4.07 | 348.69
| 2026-07-09 | N/A | CARDIFF | N/A | Not Available | 91 | 65 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.63 | 0 | 1066.51 | 6.63 | 1059.88
| 2027-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 60 | 42 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -23.51 | Unknown | 625.64 | 0 | 163.83 | 602.13 | -438.3
| 2024-09-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | -5.29 | Unknown | -1.71 | 0 | 500.87 | -7 | 507.87
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 234 | 168 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.85 | 0 | 163.83 | 4.85 | 158.98
| 2026-01-07 | Underserved Community | EL CAJON | N/A | Not Available | 24 | 18 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.6 | 0 | 197.01 | 10.6 | 186.41
| 2025-06-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 109 | 79 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | 312.08 | Unknown | 220.69 | 0 | 469.58 | 532.77 | -63.19
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 254 | 182 | N/A | 2024-08-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 163.83 | 4.01 | 159.82
| 2026-12-03 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.93 | 0 | 197.01 | 7.93 | 189.08
| 2026-08-15 | Underserved Community | BONITA | N/A | Not Available | 77 | 55 | N/A |  | Not Available | Not Available | Not Available | 487.04 | Unknown | 247.26 | 0 | 197.01 | 734.3 | -537.29
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 181 | 129 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -6.19 | Unknown | -0.97 | 0 | 163.83 | -7.16 | 170.99
| 2025-09-20 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-04-12 | Not Available | Not Available | Not Available | -5.14 | Unknown | 0.22 | 0 | 163.83 | -4.92 | 168.75
| 2024-09-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 16 | 12 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.13 | 0 | 1050.75 | 4.13 | 1046.62
| 2027-02-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.84 | 0 | 190.04 | 3.84 | 186.2
| 2025-11-21 | N/A | CARLSBAD | N/A | Not Available | 109 | 77 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | -10.98 | Unknown | -1.25 | 0 | 163.83 | -12.23 | 176.06
| 2026-09-18 | Underserved Community | CHULA VISTA | N/A | Not Available | 17 | 13 | N/A |  | Not Available | Not Available | Not Available | 188.85 | Unknown | 534.99 | 0 | 1066.55 | 723.84 | 342.71
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 241 | 173 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.69 | 0 | 163.83 | 2.69 | 161.14
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 226 | 162 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.19 | 0 | 163.83 | 7.19 | 156.64
| 2025-04-05 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2023-09-19 | Not Available | Not Available | Not Available | -10.89 | Unknown | -3.95 | 0 | 480.37 | -14.84 | 495.21
| 2026-07-26 | Underserved Community | VISTA | N/A | Not Available | 67 | 49 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 27.4 | 0 | 1050.75 | 27.4 | 1023.35
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 77 | 55 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.61 | 0 | 192.95 | 7.61 | 185.34
| 2026-11-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.11 | 0 | 197.01 | 8.11 | 188.9
| 2026-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 46 | 32 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.13 | 0 | 197.01 | 6.13 | 190.88
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 69 | N/A |  | Not Available | Not Available | Not Available | 414.31 | Unknown | 273.45 | 0 | 196.59 | 687.76 | -491.17
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 176 | 126 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -4.91 | Unknown | -0.8 | 0 | 163.83 | -5.71 | 169.54
| 2026-04-15 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 19.44 | 0 | 192.95 | 19.44 | 173.51
| 2026-08-30 | N/A | SAN DIEGO | N/A | Not Available | 96 | 68 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.76 | 0 | 197.01 | 7.76 | 189.25
| 2025-11-29 | N/A | SAN DIEGO | N/A | Not Available | 54 | 38 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -4.45 | Unknown | -1.03 | 0 | 163.83 | -5.48 | 169.31
| 2026-02-06 | Underserved Community | VALLEY CENTER | N/A | Not Available | 41 | 29 | N/A |  | Not Available | Not Available | Not Available | 422.02 | Unknown | 282.93 | 0 | 118.25 | 704.95 | -586.7
| 2024-05-05 | N/A | OCEANSIDE | N/A | Not Available | 108 | 78 | N/A | 2023-12-14 | Not Available | Not Available | Not Available | -4.79 | Unknown | -0.1 | 0 | 158.14 | -4.89 | 163.03
| 2025-11-20 | Underserved Community | ESCONDIDO | N/A | Not Available | 47 | 33 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.76 | 0 | 197.01 | 11.76 | 185.25
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 231 | 165 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 163.83 | 3.17 | 160.66
| 2025-08-31 | N/A | CARLSBAD | N/A | Not Available | 163 | 117 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -4.73 | Unknown | 0.13 | 0 | 158.79 | -4.6 | 163.39
| 2027-03-11 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 34 | 24 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.88 | 0 | 196.59 | 1.88 | 194.71
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 469 | 335 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | Unknown | 3.05 | Unknown
| 2026-11-20 | N/A | SAN CLEMENTE | N/A | Not Available | 17 | 13 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.36 | 0 | 196.69 | 9.36 | 187.33
| 2024-02-14 | N/A | LAGUNA HILLS | N/A | Not Available | 169 | 121 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | -4.27 | Unknown | -1.61 | 0 | 111.67 | -5.88 | 117.55
| 2022-12-04 | Underserved Community | VISTA | N/A | Not Available | 282 | 202 | N/A | 2023-12-05 | Not Available | Not Available | Not Available | -5.14 | Unknown | -0.45 | 0 | 95.13 | -5.59 | 100.72
| 2023-06-30 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 77 | 55 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | -5.64 | Unknown | -2.14 | 0 | 499.96 | -7.78 | 507.74
| 2025-02-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 179 | 129 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.89 | 0 | 144.8 | -6.85 | 151.65
| 2027-03-25 | Underserved Community | MISSION VIEJO | N/A | Not Available | 12 | 8 | N/A | 2025-05-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.94 | 0 | 118.25 | 3.94 | 114.31
| 2024-01-27 | N/A | LAGUNA NIGUEL | N/A | Not Available | 21 | 15 | N/A | 2023-02-28 | Not Available | Not Available | Not Available | -4.59 | Unknown | -1.75 | 0 | 67.06 | -6.34 | 73.4
| 2023-12-27 | N/A | COTO DE CAZA | N/A | Not Available | 14 | 10 | N/A |  | Not Available | Not Available | Not Available | -22.91 | Unknown | -8.71 | 0 | 67.06 | -31.62 | 98.68
| 2026-11-21 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 45 | 33 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.28 | 0 | 197.01 | 11.28 | 185.73
| 2026-10-03 | N/A | SAN CLEMENTE | N/A | Not Available | 25 | 19 | N/A | 2025-01-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.28 | 0 | 197.01 | 10.28 | 186.73
| 2025-02-11 | Underserved Community | VISTA | N/A | Not Available | 217 | 155 | N/A | 2023-11-17 | Not Available | Not Available | Not Available | -6.85 | Unknown | -2.2 | 0 | 483.84 | -9.05 | 492.89
| 2025-11-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 83 | 59 | N/A | 2025-02-10 | Not Available | Not Available | Not Available | -13.77 | Unknown | 699.91 | 0 | 197.01 | 686.14 | -489.13
| 2025-01-23 | Underserved Community | OCEANSIDE | N/A | Not Available | 135 | 97 | N/A | 2023-04-20 | Not Available | Not Available | Not Available | -4.43 | Unknown | 1.76 | 0 | 154.79 | -2.67 | 157.46
| 2027-02-26 | Underserved Community | MISSION VIEJO | N/A | Not Available | 24 | 18 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.82 | 0 | 75.96 | 2.82 | 73.14
| 2025-03-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 500 | 358 | N/A | 2024-08-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.84 | 0 | 283.53 | 9.84 | 273.69
| 2026-12-02 | N/A | SAN CLEMENTE | N/A | Not Available | 23 | 17 | N/A | 2025-01-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.75 | 0 | 799.93 | 8.75 | 791.18
| 2026-11-20 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 30 | 22 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.06 | 0 | 197.01 | 18.06 | 178.95
| 2024-10-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 147 | 105 | N/A | 2023-03-09 | Not Available | Not Available | Not Available | -5.2 | Unknown | 0.74 | 0 | 98.41 | -4.46 | 102.87
| 2024-06-09 | Underserved Community | ESCONDIDO | N/A | Not Available | 131 | 95 | N/A | 2023-04-26 | Not Available | Not Available | Not Available | -9.11 | Unknown | 1.11 | 0 | 154.79 | -8 | 162.79
| 2024-01-12 | Underserved Community | EL CAJON | N/A | Not Available | 337 | 241 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.88 | 0 | 515.81 | -0.88 | 516.69
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 37 | 27 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 42 | 30 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | -8.4 | Unknown | -1.94 | 0 | 207.92 | -10.34 | 218.26
| 2024-11-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 159 | 113 | N/A | 2023-05-23 | Not Available | Not Available | Not Available | -3.76 | Unknown | 0.47 | 0 | 98.44 | -3.29 | 101.73
| 2024-01-24 | Underserved Community | EL CAJON | N/A | Not Available | 150 | 108 | N/A | 2023-04-25 | Not Available | Not Available | Not Available | -5.25 | Unknown | 3.23 | 0 | 273.56 | -2.02 | 275.58
| 2025-05-21 | N/A | SAN CLEMENTE | N/A | Not Available | 47 | 35 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.2 | 0 | 192.51 | 9.2 | 183.31
| 2025-02-25 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2023-06-08 | Not Available | Not Available | Not Available | -9.3 | Unknown | -3.53 | 0 | 495.75 | -12.83 | 508.58
| 2025-01-25 | Underserved Community | VISTA | N/A | Not Available | 140 | 100 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | -8.52 | Unknown | -3.25 | 0 | 364.52 | -11.77 | 376.29
| 2025-02-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | -6.34 | Unknown | 28.63 | 0 | 153.75 | 22.29 | 131.46
| 2025-02-06 | Underserved Community | NATIONAL CITY | N/A | Not Available | 277 | 197 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | 579.35 | Unknown | 259.13 | 0 | 499.96 | 838.48 | -338.52
| 2025-12-04 | N/A | ENCINITAS | N/A | Not Available | 2 | 2 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.5 | 0 | 288.94 | 5.5 | 283.44
| 2026-07-31 | N/A | LAGUNA HILLS | N/A | Not Available | 43 | 31 | N/A | 2024-10-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 20.7 | 0 | 192.95 | 20.7 | 172.25
| 2024-03-02 | Underserved Community | LA JOLLA | N/A | Not Available | 445 | 317 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.79 | 0 | 153.83 | 3.79 | 150.04
| 2025-01-11 | N/A | SAN DIEGO | N/A | Not Available | 145 | 105 | N/A | 2023-04-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 0.14 | 0 | 98.41 | 0.14 | 98.27
| 2025-12-13 | N/A | SAN CLEMENTE | N/A | Not Available | 32 | 24 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.12 | 0 | 184.29 | 8.12 | 176.17
| 2025-05-06 | N/A | MISSION VIEJO | N/A | Not Available | 29 | 21 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.81 | 0 | 192.51 | 9.81 | 182.7
| 2025-05-22 | N/A | SAN CLEMENTE | N/A | Not Available | 82 | 58 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | 234.61 | Unknown | 292.15 | 0 | 180.5 | 526.76 | -346.26
| 2026-03-22 | N/A | RANCHO LA COSTA | N/A | Not Available | 54 | 39 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.93 | 0 | 192.83 | 10.93 | 181.9
| 2024-11-15 | Underserved Community | VISTA | N/A | Not Available | 408 | 292 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.47 | 0 | 595.76 | 6.47 | 589.29
| 2025-01-17 | N/A | ESCONDIDO | N/A | Not Available | 47 | 35 | N/A | 2024-05-09 | Not Available | Not Available | Not Available | -17.32 | Unknown | -2.23 | 0 | 162.34 | -19.55 | 181.89
| 2024-03-28 | Underserved Community | VISTA | N/A | Not Available | 53 | 39 | N/A | 2023-06-05 | Not Available | Not Available | Not Available | -6.86 | Unknown | -2.59 | 0 | 153.75 | -9.45 | 163.2
| 2024-03-21 | N/A | DANA POINT | N/A | Not Available | 147 | 105 | N/A | 2023-06-14 | Not Available | Not Available | Not Available | -6.17 | Unknown | -2.31 | 0 | 110.98 | -8.48 | 119.46
| 2024-07-05 | N/A | LAGUNA NIGUEL | N/A | Not Available | 186 | 134 | N/A | 2024-04-11 | Not Available | Not Available | Not Available | -4.77 | Unknown | -1.12 | 0 | 158.79 | -5.89 | 164.68
| 2024-04-07 | Underserved Community | FALLBROOK | N/A | Not Available | 112 | 80 | N/A | 2023-05-23 | Not Available | Not Available | Not Available | -14.61 | Unknown | -5.54 | 0 | 40.01 | -20.15 | 60.16
| 2025-11-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 23 | 17 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 99 | 0 | 196.44 | 99 | 97.44
| 2024-09-24 | N/A | ENCINITAS | N/A | Not Available | 152 | 110 | N/A | 2023-02-21 | Not Available | Not Available | Not Available | -4.59 | Unknown | -0.52 | 0 | 98.41 | -5.11 | 103.52
| 2023-11-02 | Underserved Community | VISTA | N/A | Not Available | 222 | 158 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | -6.33 | Unknown | -2.4 | 0 | 363.72 | -8.73 | 372.45
| 2025-05-01 | Underserved Community | FALLBROOK | N/A | Not Available | 51 | 37 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -8.66 | Unknown | -3.28 | 0 | 595.76 | -11.94 | 607.7
| 2025-11-13 | Underserved Community | CHULA VISTA | N/A | Not Available | 51 | 37 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | -14.28 | Unknown | 712.88 | 0 | 196.44 | 698.6 | -502.16
| 2025-05-29 | N/A | SAN CLEMENTE | N/A | Not Available | 78 | 56 | N/A | 2024-09-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.37 | 0 | 983.92 | 6.37 | 977.55
| 2026-12-29 | Underserved Community | DANA POINT | N/A | Not Available | 39 | 27 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -12.2 | Unknown | -6.65 | 0 | 1064.43 | -18.85 | 1083.28
| 2024-04-20 | N/A | EL CAJON | N/A | Not Available | 42 | 30 | N/A | 2023-09-13 | Not Available | Not Available | Not Available | -8.99 | Unknown | -3.41 | 0 | 496.37 | -12.4 | 508.77
| 2026-03-14 | N/A | CARLSBAD | N/A | Not Available | 189 | 135 | N/A | 2024-11-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.64 | 0 | 192.83 | 6.64 | 186.19
| 2026-07-09 | N/A | SAN CLEMENTE | N/A | Not Available | 53 | 39 | N/A | 2024-12-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.94 | 0 | 105.08 | 12.94 | 92.14
| 2025-03-10 | N/A | SAN DIEGO | N/A | Not Available | 165 | 117 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -12.8 | Unknown | -4.66 | 0 | 153.75 | -17.46 | 171.21
| 2025-11-27 | N/A | SAN DIEGO | N/A | Not Available | 19 | 13 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.47 | 0 | 196.44 | 9.47 | 186.97
| 2026-08-30 | N/A | CARLSBAD | N/A | Not Available | 26 | 18 | N/A | 2024-10-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.44 | 0 | 197.01 | 3.44 | 193.57
| 2027-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 12 | 8 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.73 | 0 | 196.59 | 5.73 | 190.86
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 23 | 17 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -3.07 | Unknown | -0.71 | 0 | 207.92 | -3.78 | 211.7
| 2027-01-10 | Underserved Community | LA JOLLA | N/A | Not Available | 19 | 13 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | -13.85 | Unknown | -7.53 | 0 | 196.44 | -21.38 | 217.82
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 28 | 20 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | 291.46 | Unknown | 198.36 | 0 | 207.92 | 489.82 | -281.9
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 37 | 27 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2025-10-29 | N/A | CARLSBAD | N/A | Not Available | 21 | 15 | N/A | 2024-11-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.32 | 0 | 279.3 | 4.32 | 274.98
| 2025-05-31 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 19 | 13 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.05 | 0 | 118.25 | 3.05 | 115.2
| 2026-04-17 | Underserved Community | BONITA | N/A | Not Available | 52 | 38 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 274.42 | 0 | 186.09 | 729.1 | -543.01
| 2029-01-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | -8.03 | Unknown | 413.73 | 0 | 1064.43 | 405.7 | 658.73
| 2027-04-24 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 36 | 26 | N/A | 2025-05-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2027-01-30 | N/A | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.37 | 0 | 196.69 | 4.37 | 192.32
| 2024-04-17 | Underserved Community | LEMON GROVE | N/A | Not Available | 34 | 24 | N/A | 2023-07-07 | Not Available | Not Available | Not Available | -6.51 | Unknown | 28.96 | 0 | 143.95 | 22.45 | 121.5
| 2024-03-23 | N/A | ENCINITAS | N/A | Not Available | 36 | 26 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | -5.14 | Unknown | -0.82 | 0 | 153.87 | -5.96 | 159.83
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 28 | 20 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -5.82 | Unknown | -1.38 | 0 | 207.92 | -7.2 | 215.12
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.87 | 0 | 196.69 | 5.87 | 190.82
| 2026-05-03 | Underserved Community | OCEANSIDE | N/A | Not Available | 37 | 27 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | 606.36 | Unknown | 416.19 | 0 | 1016.73 | 1022.55 | -5.82
| 2026-07-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.27 | 0 | 197.01 | 11.27 | 185.74
| 2026-04-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2024-04-23 | Not Available | Not Available | Not Available | -11.6 | Unknown | -2.69 | 0 | 534.57 | -14.29 | 548.86
| 2027-03-14 | N/A | ENCINITAS | N/A | Not Available | 44 | 32 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | -8.05 | Unknown | 400.09 | 0 | 142.53 | 392.04 | -249.51
| 2026-01-29 | Underserved Community | LA MESA | N/A | Not Available | 56 | 40 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | -20.32 | Unknown | 1004.76 | 0 | 196.59 | 984.44 | -787.85
| 2026-11-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.98 | 0 | 197.01 | 4.98 | 192.03
| 2025-04-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 14 | 10 | N/A | 2024-04-08 | Not Available | Not Available | Not Available | -7.88 | Unknown | -1.81 | 0 | 202.87 | -9.69 | 212.56
| 2025-06-15 | N/A | LAGUNA HILLS | N/A | Not Available | 31 | 23 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.72 | 0 | 102.37 | 5.72 | 96.65
| 2027-01-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 46 | 32 | N/A |  | Not Available | Not Available | Not Available | 374.22 | Unknown | 194.02 | 0 | 196.69 | 568.24 | -371.55
| 2026-06-12 | N/A | DEL MAR | N/A | Not Available | 42 | 30 | N/A | 2024-09-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 25.91 | 0 | 192.95 | 25.91 | 167.04
| 2026-11-01 | N/A | CARLSBAD | N/A | Not Available | 19 | 15 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.64 | 0 | 288.94 | 8.64 | 280.3
| 2026-09-17 | Underserved Community | CHULA VISTA | N/A | Not Available | 22 | 16 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 0 | 197.01 | 5.69 | 191.32
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 15 | 11 | N/A | 2024-05-23 | Not Available | Not Available | Not Available | -14 | Unknown | -3.24 | 0 | 207.92 | -17.24 | 225.16
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 34 | 24 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -6.57 | Unknown | -1.5 | 0 | 162.34 | -8.07 | 170.41
| 2027-04-28 | N/A | DANA POINT | N/A | Not Available | 15 | 11 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.94 | 0 | 57.62 | 1.94 | 55.68
| 2027-04-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 23 | 17 | N/A |  | Not Available | Not Available | Not Available | 245.23 | Unknown | 1030.26 | 0 | 450.11 | 1275.49 | -825.38
| 2026-01-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 50 | 36 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.77 | 0 | 197.01 | 14.77 | 182.24
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 30 | 22 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.75 | 0 | 162.34 | -4.02 | 166.36
| 2027-02-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 12 | 8 | N/A | 2024-04-08 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.86 | 0 | 623.69 | -4.6 | 628.29
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 42 | 30 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 207.92 | -4.06 | 211.98
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 29 | 21 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | 291.46 | Unknown | 198.41 | 0 | 162.34 | 489.87 | -327.53
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 34 | 24 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -6.57 | Unknown | -1.5 | 0 | 162.34 | -8.07 | 170.41
| 2025-07-11 | Underserved Community | CHULA VISTA | N/A | Not Available | 66 | 48 | N/A | 2023-10-31 | Not Available | Not Available | Not Available | 763.68 | Unknown | 360.46 | 0 | 153.22 | 1124.14 | -970.92
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 47 | 33 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -3.27 | Unknown | -0.79 | 0 | 150.74 | -4.06 | 154.8
| 2025-11-14 | N/A | ENCINITAS | N/A | Not Available | 32 | 24 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | -10.71 | Unknown | -2.5 | 0 | 534.53 | -13.21 | 547.74
| 2026-04-08 | N/A | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.34 | 0 | 192.51 | 2.34 | 190.17
| 2027-04-23 | N/A | SAN DIEGO | N/A | Not Available | 23 | 17 | N/A | 2025-05-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 118.25 | 4.39 | 113.86
| 2025-11-27 | Underserved Community | OCEANSIDE | N/A | Not Available | 128 | 92 | N/A | 2024-06-05 | Not Available | Not Available | Not Available | -5.1 | Unknown | -1.21 | 0 | 163.83 | -6.31 | 170.14
| 2025-12-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2024-12-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.58 | 0 | 197.01 | 8.58 | 188.43
| 2025-11-25 | N/A | SAN DIEGO | N/A | Not Available | 74 | 54 | N/A | 2024-11-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.07 | 0 | 1032.15 | 2.07 | 1030.08
| 2026-05-29 | N/A | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.85 | 0 | 1086.86 | 5.85 | 1081.01
| 2025-03-05 | Underserved Community | EL CAJON | N/A | Not Available | 11 | 9 | N/A | 2024-03-06 | Not Available | Not Available | Not Available | -9.09 | Unknown | -2.11 | 0 | 163.83 | -11.2 | 175.03
| 2026-05-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 124 | 88 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.07 | 0 | 192.95 | 5.07 | 187.88
| 2026-02-27 | N/A | SOLANA BEACH | N/A | Not Available | 98 | 70 | N/A | 2024-07-03 | Not Available | Not Available | Not Available | -4.18 | Unknown | -0.66 | 0 | 534.57 | -4.84 | 539.41
| 2025-06-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A |  | Not Available | Not Available | Not Available | 189.35 | Unknown | 136.94 | 0 | 153.22 | 326.29 | -173.07
| 2026-07-31 | N/A | OCEANSIDE | N/A | Not Available | 49 | 35 | N/A | 2024-10-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.86 | 0 | 192.95 | 10.86 | 182.09
| 2025-08-17 | Underserved Community | VALLEY CENTER | N/A | Not Available | 82 | 60 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -5.79 | Unknown | -1.85 | 0 | 41.38 | -7.64 | 49.02
| 2025-06-30 | Underserved Community | CHULA VISTA | N/A | Not Available | 130 | 94 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -5.82 | Unknown | 2.29 | 0 | 153.49 | -3.53 | 157.02
| 2027-01-21 | Underserved Community | CHULA VISTA | N/A | Not Available | 85 | 61 | N/A |  | Not Available | Not Available | Not Available | 1639.49 | Unknown | 1344.94 | 0 | 190.13 | 2984.43 | -2794.3
| 2025-05-08 | N/A | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.49 | 0 | 192.83 | 4.49 | 188.34
| 2026-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 27.36 | 0 | 186.52 | 27.36 | 159.16
| 2024-05-01 | Underserved Community | SPRING VALLEY | N/A | Not Available | 8 | 6 | N/A | 2023-06-22 | Not Available | Not Available | Not Available | -9.8 | Unknown | -3.71 | 0 | 495.75 | -13.51 | 509.26
| 2026-05-29 | Underserved Community | RANCHITA | N/A | Not Available | 8 | 6 | N/A |  | Not Available | Not Available | Not Available | 1168.44 | Unknown | 614.55 | 0 | 465.64 | 1782.99 | -1317.35
| 2026-07-19 | N/A | ENCINITAS | N/A | Not Available | 62 | 44 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.68 | 0 | 1066.51 | 4.68 | 1061.83
| 2027-02-04 | Underserved Community | CHULA VISTA | N/A | Not Available | 84 | 60 | N/A |  | Not Available | Not Available | Not Available | 310.95 | Unknown | 147.58 | 0 | 196.69 | 458.53 | -261.84
| 2025-07-09 | Underserved Community | VALLEY CENTER | N/A | Not Available | 76 | 54 | N/A | 2023-11-07 | Not Available | Not Available | Not Available | -17.63 | Unknown | -4.73 | 0 | 482.43 | -22.36 | 504.79
| 2025-12-02 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.6 | 0 | 465.36 | -6.55 | 471.91
| 2026-06-10 | N/A | VISTA | N/A | Not Available | 162 | 116 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 192.51 | 4.39 | 188.12
| 2024-08-07 | Underserved Community | LA MESA | N/A | Not Available | 53 | 39 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | -8.05 | Unknown | -2.15 | 0 | 481.24 | -10.2 | 491.44
| 2024-07-26 | Underserved Community | VISTA | N/A | Not Available | 6 | 4 | N/A | 2023-07-31 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.5 | 0 | 496.37 | -5.42 | 501.79
| 2025-07-28 | N/A | CARLSBAD | N/A | Not Available | 62 | 44 | N/A | 2024-01-30 | Not Available | Not Available | Not Available | -6.52 | Unknown | -1.48 | 0 | 203.23 | -8 | 211.23
| 2026-09-17 | N/A | CARLSBAD | N/A | Not Available | 123 | 89 | N/A | 2025-02-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.06 | 0 | 288.94 | 8.06 | 280.88
| 2025-10-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 13 | 9 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.97 | 0 | 197.01 | 5.97 | 191.04
| 2025-06-07 | N/A | CHULA VISTA | N/A | Not Available | 53 | 37 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | 336.74 | Unknown | 210.85 | 0 | 152.86 | 547.59 | -394.73
| 2025-01-11 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 49 | 35 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | 237.76 | Unknown | 144.19 | 0 | 499.96 | 381.95 | 118.01
| 2024-02-10 | N/A | EL CAJON | N/A | Not Available | 72 | 52 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | -6.92 | Unknown | -2.63 | 0 | 495.75 | -9.55 | 505.3
| 2025-02-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 187 | 135 | N/A | 2023-09-22 | Not Available | Not Available | Not Available | -10.72 | Unknown | -3.91 | 0 | 464.78 | -14.63 | 479.41
| 2025-07-31 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2023-12-28 | Not Available | Not Available | Not Available | -8.64 | Unknown | -2.34 | 0 | 513.31 | -10.98 | 524.29
| 2025-09-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A |  | Not Available | Not Available | Not Available | 450.44 | Unknown | 238.94 | 0 | 156.93 | 689.38 | -532.45
| 2027-01-14 | Disadvantaged Community,Underserved Community,Tribal Community | PAUMA VALLEY | N/A | Not Available | 30 | 22 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1.38 | 0 | 1064.43 | 1.38 | 1063.05
| 2025-05-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 109 | 79 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | -10.61 | Unknown | 22.49 | 0 | 515.81 | 11.88 | 503.93
| 2024-03-20 | Underserved Community | SPRING VALLEY | N/A | Not Available | 88 | 64 | N/A | 2023-08-17 | Not Available | Not Available | Not Available | -9.02 | Unknown | -3.46 | 0 | 495.75 | -12.48 | 508.23
| 2024-07-05 | Underserved Community | LA MESA | N/A | Not Available | 23 | 17 | N/A | 2023-07-07 | Not Available | Not Available | Not Available | -7.27 | Unknown | -2.77 | 0 | 496.45 | -10.04 | 506.49
| 2025-08-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 7 | 5 | N/A | 2024-08-02 | Not Available | Not Available | Not Available | 181.27 | Unknown | 124.45 | 0 | 1016.86 | 305.72 | 711.14
| 2025-02-09 | N/A | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | -31.36 | Unknown | 1153.06 | 0 | 495.75 | 1121.7 | -625.95
| 2026-08-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 47 | N/A | 2024-11-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.76 | 0 | 1066.51 | 3.76 | 1062.75
| 2027-01-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2025-03-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.56 | 0 | 196.44 | 6.56 | 189.88
| 2025-03-09 | Underserved Community | VISTA | N/A | Not Available | 92 | 66 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 984.98 | 0 | 984.98
| 2025-05-08 | Underserved Community | CHULA VISTA | N/A | Not Available | 207 | 149 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -10.09 | Unknown | -1.17 | 0 | 148.7 | -11.26 | 159.96
| 2026-10-18 | Underserved Community | EL CAJON | N/A | Not Available | 9 | 7 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.36 | 0 | 197.01 | 6.36 | 190.65
| 2023-12-28 | Underserved Community | SANTEE | N/A | Not Available | 365 | 261 | N/A | 2024-01-19 | Not Available | Not Available | Not Available | -18.65 | Unknown | 575.4 | 0 | 363.72 | 556.75 | -193.03
| 2024-01-24 | N/A | ALPINE | N/A | Not Available | 57 | 41 | N/A | 2023-04-25 | Not Available | Not Available | Not Available | -7.22 | Unknown | 4.73 | 0 | 273.56 | -2.49 | 276.05
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 37 | 27 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 207.92 | -6.74 | 214.66
| 2026-03-22 | N/A | SOLANA BEACH | N/A | Not Available | 22 | 16 | N/A | 2024-05-02 | Not Available | Not Available | Not Available | -16.57 | Unknown | 624.71 | 0 | 529.2 | 608.14 | -78.94
| 2024-01-23 | Underserved Community | EL CAJON | N/A | Not Available | 144 | 104 | N/A | 2023-07-21 | Not Available | Not Available | Not Available | -14.86 | Unknown | -3.7 | 0 | 469.24 | -18.56 | 487.8
| 2025-04-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -6.85 | Unknown | -1.83 | 0 | 425.49 | -8.68 | 434.17
| 2024-02-14 | Underserved Community | SPRING VALLEY | N/A | Not Available | 129 | 93 | N/A | 2023-05-01 | Not Available | Not Available | Not Available | -3.95 | Unknown | 0.63 | 0 | 154.79 | -3.32 | 158.11
| 2024-02-21 | Underserved Community | SPRING VALLEY | N/A | Not Available | 69 | 49 | N/A | 2023-04-05 | Not Available | Not Available | Not Available | -4.74 | Unknown | -1.8 | 0 | 499.96 | -6.54 | 506.5
| 2024-02-07 | N/A | CAPISTRANO BEACH | N/A | Not Available | 107 | 77 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1347.91 | 0 | 455.72 | 1347.91 | -892.19
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | 45 | 33 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -8.04 | Unknown | -1.84 | 0 | 207.92 | -9.88 | 217.8
| 2027-03-07 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 28 | 20 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.94 | 0 | 118.25 | 3.94 | 114.31
| 2027-04-07 | N/A | SAN DIEGO | N/A | Not Available | 11 | 7 | N/A |  | Not Available | Not Available | Not Available | 254.7 | Unknown | 171.3 | 0 | 196.38 | 426 | -229.62
| 2027-03-12 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.38 | 1.99 | 194.39
| 2025-05-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 227 | 163 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.86 | 0 | 483.59 | -4.6 | 488.19
| 2026-02-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 188 | 134 | N/A | 2024-10-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 37.25 | 0 | 534.57 | 37.25 | 497.32
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 241 | 173 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.44 | 0 | 163.83 | 3.44 | 160.39
| 2027-02-17 | Underserved Community | VISTA | N/A | Not Available | 71 | 51 | N/A | 2025-06-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.97 | 0 | 196.59 | 1.97 | 194.62
| 2026-08-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 132 | 94 | N/A |  | Not Available | Not Available | Not Available | 307.25 | Unknown | 638.2 | 0 | 1066.55 | 945.45 | 121.1
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 85 | 61 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.07 | 0 | 192.95 | 2.07 | 190.88
| 2025-03-19 | N/A | SANTEE | N/A | Not Available | 85 | 61 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.7 | 0 | 192.95 | -0.7 | 193.65
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 246 | 176 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.03 | 0 | 163.83 | 12.03 | 151.8
| 2026-11-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 148 | 106 | N/A |  | Not Available | Not Available | Not Available | 575.75 | Unknown | 296.09 | 0 | 114.3 | 871.84 | -757.54
| 2026-04-08 | Underserved Community | SAN MARCOS | N/A | Not Available | 23 | 17 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.46 | 0 | 983.86 | 4.46 | 979.4
| 2025-06-09 | Underserved Community | LA MESA | N/A | Not Available | 18 | 14 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | 447.37 | Unknown | 551.07 | 0 | 196.44 | 998.44 | -802
| 2026-03-22 | N/A | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | -7.48 | Unknown | -1.7 | 0 | 529.2 | -9.18 | 538.38
| 2027-01-24 | N/A | POWAY | N/A | Not Available | 45 | 33 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.21 | 0 | 183.76 | 7.21 | 176.55
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 139 | 99 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 139 | 99 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2026-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2024-10-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.04 | 0 | 192.95 | 12.04 | 180.91
| 2026-03-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -6.46 | Unknown | 76.39 | 0 | 984.98 | 69.93 | 915.05
| 2024-06-12 | Underserved Community | LA MESA | N/A | Not Available | 195 | 139 | N/A | 2024-03-04 | Not Available | Not Available | Not Available | -9.47 | Unknown | -2.22 | 0 | 514.53 | -11.69 | 526.22
| 2026-07-09 | Underserved Community | ESCONDIDO | N/A | Not Available | 47 | 33 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 20.85 | 0 | 197.01 | 20.85 | 176.16
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 234 | 168 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.22 | 0 | 163.83 | 7.22 | 156.61
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 133 | 95 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -3.41 | Unknown | -0.77 | 0 | 163.83 | -4.18 | 168.01
| 2027-04-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2025-06-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.03 | 0 | 114.3 | 7.03 | 107.27
| 2026-06-05 | Underserved Community | POWAY | N/A | Not Available | 75 | 55 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 17.81 | 0 | 197.01 | 17.81 | 179.2
| 2025-04-10 | Underserved Community | CHULA VISTA | N/A | Not Available | 51 | 37 | N/A | 2023-07-25 | Not Available | Not Available | Not Available | -13.61 | Unknown | -5.17 | 0 | 480.44 | -18.78 | 499.22
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 77 | 55 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -3.63 | Unknown | -0.85 | 0 | 192.83 | -4.48 | 197.31
| 2026-08-19 | N/A | DANA POINT | N/A | Not Available | 108 | 78 | N/A | 2025-03-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 133 | 95 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -7.21 | Unknown | -1.67 | 0 | 163.83 | -8.88 | 172.71
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 157 | 113 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -9.87 | Unknown | -2.29 | 0 | 163.83 | -12.16 | 175.99
| 2024-03-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 34 | 24 | N/A | 2023-07-17 | Not Available | Not Available | Not Available | -5.48 | Unknown | -2.08 | 0 | 153.87 | -7.56 | 161.43
| 2027-03-29 | N/A | POWAY | N/A | Not Available | 22 | 16 | N/A |  | Not Available | Not Available | Not Available | 254.7 | Unknown | 171.3 | 0 | 997.19 | 426 | 571.19
| 2025-07-16 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -8.86 | Unknown | 5.9 | 0 | 513.31 | -2.96 | 516.27
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 139 | 99 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -8.41 | Unknown | -1.95 | 0 | 163.83 | -10.36 | 174.19
| 2024-04-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 204 | 146 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 1703.43 | 0 | 1332.16 | 1703.43 | -371.27
| 2025-11-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.98 | 0 | 197.01 | 4.98 | 192.03
| 2025-10-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.49 | 0 | 197.01 | 10.49 | 186.52
| 2026-03-26 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-05-14 | Not Available | Not Available | Not Available | -8.14 | Unknown | -1.87 | 0 | 529.2 | -10.01 | 539.21
| 2026-12-02 | N/A | SAN DIEGO | N/A | Not Available | 31 | 23 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.64 | 0 | 197.01 | 3.64 | 193.37
| 2027-02-14 | N/A | LAGUNA HILLS | N/A | Not Available | 90 | 64 | N/A | 2025-06-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.88 | 0 | 196.59 | 1.88 | 194.71
| 2026-06-20 | Underserved Community | ESCONDIDO | N/A | Not Available | 28 | 20 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.68 | 0 | 192.95 | 8.68 | 184.27
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 65 | 46 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 0 | 192.95 | 5.69 | 187.26
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 176 | 126 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -9.5 | Unknown | -1.53 | 0 | 163.83 | -11.03 | 174.86
| 2026-10-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 61 | 43 | N/A | 2024-11-27 | Not Available | Not Available | Not Available | -1.88 | Unknown | 103.34 | 0 | 1066.55 | 101.46 | 965.09
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 160 | 114 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.13 | 0 | 380.88 | 3.13 | 377.75
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 107 | 77 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.85 | 0 | 192.95 | 4.85 | 188.1
| 2027-02-03 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 106 | 76 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.43 | 0 | 1424.5 | 5.43 | 1419.07
| 2025-10-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -5.32 | Unknown | 1.06 | 0 | 163.83 | -4.26 | 168.09
| 2026-03-11 | N/A | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.7 | 0 | 197.01 | 5.7 | 191.31
| 2025-08-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 142 | 102 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.1 | 0 | 515.81 | -5.19 | 521
| 2025-07-10 | N/A | SAN DIEGO | N/A | Not Available | 484 | 346 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.49 | 0 | 158.14 | 10.49 | 147.65
| 2025-05-09 | N/A | SAN DIEGO | N/A | Not Available | 305 | 217 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -8.35 | Unknown | -1.92 | 0 | 496.37 | -10.27 | 506.64
| 2025-12-27 | N/A | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2024-03-08 | Not Available | Not Available | Not Available | -5.48 | Unknown | -1.27 | 0 | 163.83 | -6.75 | 170.58
| 2026-10-18 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.13 | 0 | 197.01 | 5.13 | 191.88
| 2026-10-16 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.47 | 0 | 197.01 | 6.47 | 190.54
| 2025-08-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 107 | 77 | N/A | 2023-12-14 | Not Available | Not Available | Not Available | -9.2 | Unknown | -2.96 | 0 | 515.81 | -12.16 | 527.97
| 2026-08-28 | N/A | SAN DIEGO | N/A | Not Available | 103 | 73 | N/A | 2024-11-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.72 | 0 | 197.01 | 7.72 | 189.29
| 2025-05-15 | N/A | SAN DIEGO | N/A | Not Available | 142 | 102 | N/A | 2023-12-14 | Not Available | Not Available | Not Available | -8.92 | Unknown | -2.41 | 0 | 158.14 | -11.33 | 169.47
| 2026-11-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2024-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.9 | 3981 | 999.91 | 5.9 | 994.01
| 2025-06-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 300 | 214 | N/A | 2024-04-16 | Not Available | Not Available | Not Available | -7.88 | Unknown | -1.79 | 0 | 500.87 | -9.67 | 510.54
| 2026-04-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 156 | 112 | N/A |  | Not Available | Not Available | Not Available | 317.18 | Unknown | 186.29 | 0 | 1049.43 | 503.47 | 545.96
| 2026-07-23 | N/A | SAN CLEMENTE | N/A | Not Available | 90 | 64 | N/A | 2024-09-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.32 | 0 | 192.95 | 7.32 | 185.63
| 2025-09-01 | N/A | SAN DIEGO | N/A | Not Available | 404 | 288 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 515.81 | 4.01 | 511.8
| 2025-03-27 | N/A | DANA POINT | N/A | Not Available | 114 | 82 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | 72.04 | Unknown | 54.62 | 0 | 192.51 | 126.66 | 65.85
| 2026-12-05 | N/A | COTO DE CAZA | N/A | Not Available | 35 | 25 | N/A | 2024-12-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.5 | 0 | 184.29 | 10.5 | 173.79
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | -13.23 | Unknown | -7.21 | 0 | 196.69 | -20.44 | 217.13
| 2026-07-31 | Underserved Community | LA MESA | N/A | Not Available | 32 | 24 | N/A | 2024-08-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.06 | 0 | 1067.34 | 5.06 | 1062.28
| 2027-02-11 | N/A | LAGUNA HILLS | N/A | Not Available | 31 | 23 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | -37.2 | Unknown | -16.19 | 0 | 196.44 | -53.39 | 249.83
| 2025-09-10 | Underserved Community | SAN MARCOS | N/A | Not Available | 127 | 91 | N/A | 2024-04-03 | Not Available | Not Available | Not Available | -10.23 | Unknown | 0.08 | 0 | 163.83 | -10.15 | 173.98
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | -20.44 | Unknown | -11.11 | 0 | 196.69 | -31.55 | 228.24
| 2026-03-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -15.13 | Unknown | -0.62 | 0 | 162.34 | -15.75 | 178.09
| 2025-12-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 295 | 211 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.12 | 0 | 163.83 | 12.12 | 151.71
| 2025-03-07 | N/A | LAGUNA HILLS | N/A | Not Available | 104 | 74 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | 60.25 | Unknown | 46.69 | 0 | 162.34 | 106.94 | 55.4
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | -9.09 | Unknown | -4.94 | 0 | 196.69 | -14.03 | 210.72
| 2026-02-22 | Underserved Community | SANTEE | N/A | Not Available | 266 | 190 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.02 | 0 | 648.92 | 10.02 | 638.9
| 2025-12-27 | Underserved Community | NATIONAL CITY | N/A | Not Available | 80 | 58 | N/A | 2024-03-08 | Not Available | Not Available | Not Available | -6.4 | Unknown | -1.5 | 0 | 534.53 | -7.9 | 542.43
| 2023-10-31 | Underserved Community | EL CAJON | N/A | Not Available | 100 | 72 | N/A | 2024-01-25 | Not Available | Not Available | Not Available | -18.44 | Unknown | -0.2 | 0 | 621.39 | -18.64 | 640.03
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 213 | 153 | N/A |  | Not Available | Not Available | Not Available | 211.95 | Unknown | 139.87 | 0 | 196.44 | 351.82 | -155.38
| 2026-07-09 | Underserved Community | SPRING VALLEY | N/A | Not Available | 57 | 41 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.9 | 0 | 1050.75 | 12.9 | 1037.85
| 2025-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 180 | 128 | N/A |  | Not Available | Not Available | Not Available | 551.03 | Unknown | 347.17 | 0 | 534.53 | 898.2 | -363.67
| 2027-12-31 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 197.01 | 8.02 | 188.99
| 2025-10-24 | N/A | SAN DIEGO | N/A | Not Available | 174 | 124 | N/A | 2024-03-20 | Not Available | Not Available | Not Available | -37.14 | Unknown | 1351.66 | 0 | 534.53 | 1314.52 | -779.99
| 2025-07-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 150 | 108 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.78 | 0 | 513.31 | -7.25 | 520.56
| 2026-03-13 | N/A | ENCINITAS | N/A | Not Available | 253 | 181 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 23.96 | 0 | 529.2 | 23.96 | 505.24
| 2025-01-03 | N/A | SANTEE | N/A | Not Available | 113 | 81 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | -38.33 | Unknown | 1380.37 | 0 | 552.98 | 1342.04 | -789.06
| 2026-03-20 | Underserved Community | CHULA VISTA | N/A | Not Available | 329 | 235 | N/A |  | Not Available | Not Available | Not Available | 245.04 | Unknown | 649.42 | 0 | 1050.61 | 894.46 | 156.15
| 2026-02-04 | Underserved Community | ESCONDIDO | N/A | Not Available | 161 | 115 | N/A | 2024-06-21 | Not Available | Not Available | Not Available | -4.92 | Unknown | -0.81 | 0 | 496.14 | -5.73 | 501.87
| 2026-07-22 | N/A | VISTA | N/A | Not Available | 73 | 53 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.11 | 0 | 1050.75 | 4.11 | 1046.64
| 2027-04-14 | Underserved Community | OCEANSIDE | N/A | Not Available | 31 | 23 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2027-02-11 | N/A | CARLSBAD | N/A | Not Available | 106 | 76 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | 253.1 | Unknown | 306.97 | 0 | 196.44 | 560.07 | -363.63
| 2025-08-23 | N/A | CARDIFF | N/A | Not Available | 69 | 49 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -6.85 | Unknown | -1.02 | 0 | 513.31 | -7.87 | 521.18
| 2026-05-09 | Underserved Community | OCEANSIDE | N/A | Not Available | 56 | 40 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -16.48 | Unknown | -1.09 | 0 | 192.83 | -17.57 | 210.4
| 2026-05-31 | N/A | OCEANSIDE | N/A | Not Available | 115 | 83 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | 128.28 | Unknown | 97.19 | 0 | 192.83 | 225.47 | -32.64
| 2024-08-02 | Underserved Community | LEMON GROVE | N/A | Not Available | 91 | 65 | N/A | 2023-10-18 | Not Available | Not Available | Not Available | -11.42 | Unknown | 219.36 | 0 | 518.15 | 207.94 | 310.21
| 2025-08-16 | N/A | DEL MAR | N/A | Not Available | 289 | 207 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | -7.95 | Unknown | 217.13 | 0 | 529.2 | 209.18 | 320.02
| 2026-03-14 | N/A | CARLSBAD | N/A | Not Available | 155 | 111 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | 37.61 | Unknown | 33.65 | 0 | 162.34 | 71.26 | 91.08
| 2026-04-08 | Underserved Community | VISTA | N/A | Not Available | 100 | 72 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -6 | Unknown | -0.97 | 0 | 1050.61 | -6.97 | 1057.58
| 2026-02-14 | N/A | VALLEY CENTER | N/A | Not Available | 113 | 81 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -11.27 | Unknown | -0.16 | 0 | 162.34 | -11.43 | 173.77
| 2024-01-09 | Underserved Community | LA MESA | N/A | Not Available | 190 | 136 | N/A | 2023-08-28 | Not Available | Not Available | Not Available | -4.26 | Unknown | -1.62 | 0 | 496.45 | -5.88 | 502.33
| 2025-09-20 | N/A | LA JOLLA | N/A | Not Available | 214 | 154 | N/A | 2024-03-20 | Not Available | Not Available | Not Available | -6.92 | Unknown | -1.62 | 0 | 515.81 | -8.54 | 524.35
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 727 | 519 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.61 | 3981 | 281.93 | 6.61 | 275.32
| 2025-02-11 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 94 | 66 | N/A | 2023-06-21 | Not Available | Not Available | Not Available | -8.14 | Unknown | 1.89 | 0 | 153.75 | -6.25 | 160
| 2026-10-17 | N/A | LAGUNA HILLS | N/A | Not Available | 152 | 110 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | -15.49 | Unknown | -5.14 | 0 | 197.01 | -20.63 | 217.64
| 2025-12-09 | N/A | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A | 2023-05-12 | Not Available | Not Available | Not Available | -9.81 | Unknown | -3.74 | 0 | 125.42 | -13.55 | 138.97
| 2024-11-27 | Underserved Community | VISTA | N/A | Not Available | 183 | 131 | N/A | 2023-03-31 | Not Available | Not Available | Not Available | -6.43 | Unknown | -2.43 | 0 | 363.72 | -8.86 | 372.58
| 2026-08-01 | N/A | LAGUNA HILLS | N/A | Not Available | 147 | 105 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.76 | 0 | 197.01 | 6.76 | 190.25
| 2023-12-20 | N/A | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2023-06-27 | Not Available | Not Available | Not Available | -3.93 | Unknown | -1.5 | 0 | 98.66 | -5.43 | 104.09
| 2020-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2024-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 773.84 | 0 | 773.84
| 2025-05-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 455 | 325 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 0 | 496.37 | 5.81 | 490.56
| 2025-05-28 | Underserved Community | DANA POINT | N/A | Not Available | 53 | 39 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | 144.08 | Unknown | 103.99 | 0 | 180.5 | 248.07 | -67.57
| 2023-02-01 | N/A | EL CAJON | N/A | Not Available | 192 | 138 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -6.33 | Unknown | -1.72 | 0 | 452.24 | -8.05 | 460.29
| 2025-03-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2023-08-28 | Not Available | Not Available | Not Available | -5.91 | Unknown | -2.26 | 0 | 496.37 | -8.17 | 504.54
| 2024-03-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 29 | 21 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.9 | 0 | 153.87 | -6.86 | 160.73
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2024-05-16 | Not Available | Not Available | Not Available | -26.65 | Unknown | 1124.37 | 0 | 801.94 | 1097.72 | -295.78
| 2025-07-31 | Underserved Community | BONSALL | N/A | Not Available | 99 | 71 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | -3.69 | Unknown | -1.41 | 0 | 397.18 | -5.1 | 402.28
| 2025-07-11 | Underserved Community | ESCONDIDO | N/A | Not Available | 279 | 199 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -10.35 | Unknown | -2.39 | 0 | 465.36 | -12.74 | 478.1
| 2025-05-26 | N/A | SAN DIEGO | N/A | Not Available | 431 | 309 | N/A | 2024-10-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.36 | 0 | 143.91 | 8.36 | 135.55
| 2025-04-11 | N/A | COTO DE CAZA | N/A | Not Available | 105 | 75 | N/A | 2024-09-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.94 | 0 | 74.16 | 7.94 | 66.22
| 2024-03-14 | N/A | SAN DIEGO | N/A | Not Available | 264 | 189 | N/A | 2023-08-28 | Not Available | Not Available | Not Available | -5.14 | Unknown | -0.71 | 0 | 153.75 | -5.85 | 159.6
| 2026-11-12 | Underserved Community | MISSION VIEJO | N/A | Not Available | 78 | 56 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 17 | 0 | 105.08 | 17 | 88.08
| 2027-03-11 | N/A | LAGUNA NIGUEL | N/A | Not Available | 23 | 17 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.81 | 0 | 196.59 | 2.81 | 193.78
| 2025-04-04 | N/A | MISSION VIEJO | N/A | Not Available | 36 | 26 | N/A | 2024-06-11 | Not Available | Not Available | Not Available | -8.19 | Unknown | 1.72 | 0 | 180.38 | -6.47 | 186.85
| 2025-01-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2023-04-11 | Not Available | Not Available | Not Available | -3.94 | Unknown | -1.51 | 0 | 374.98 | -5.45 | 380.43
| 2026-09-09 | N/A | DANA POINT | N/A | Not Available | 30 | 22 | N/A | 2024-10-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 17.75 | 0 | 184.29 | 17.75 | 166.54
| 2027-03-28 | Underserved Community | OCEANSIDE | N/A | Not Available | 22 | 16 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | 533.76 | Unknown | 362.26 | 0 | 151.78 | 896.02 | -744.24
| 2026-11-19 | N/A | CARDIFF | N/A | Not Available | 15 | 11 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.68 | 3981 | 197.01 | 3.68 | 193.33
| 2026-06-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 20 | 14 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.31 | 0 | 192.95 | 7.31 | 185.64
| 2027-01-06 | Underserved Community | VISTA | N/A | Not Available | 35 | 25 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.74 | 0 | 278.82 | 4.74 | 274.08
| 2026-06-21 | N/A | CARLSBAD | N/A | Not Available | 21 | 15 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.21 | 1000 | 192.51 | 6.21 | 186.3
| 2027-04-04 | Underserved Community | CHULA VISTA | N/A | Not Available | 52 | 38 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | -0.63 | Unknown | 46.66 | 0 | 1063.13 | 46.03 | 1017.1
| 2026-05-28 | Underserved Community | SPRING VALLEY | N/A | Not Available | 20 | 14 | N/A | 2024-07-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.36 | 3981 | 282.95 | 7.36 | 275.59
| 2026-06-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-07-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.44 | 3981 | 1049.43 | 4.44 | 1044.99
| 2026-08-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 35 | 25 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.6 | 0 | 288.94 | 4.6 | 284.34
| 2026-03-27 | N/A | CHULA VISTA | N/A | Not Available | 67 | 47 | N/A |  | Not Available | Not Available | Not Available | 362.52 | Unknown | 222.68 | 0 | 186.4 | 585.2 | -398.8
| 2026-04-29 | N/A | VALLEY CENTER | N/A | Not Available | 105 | 75 | N/A | 2025-01-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.07 | 0 | 197.01 | 18.07 | 178.94
| 2027-01-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | -1.26 | Unknown | 65.58 | 0 | 798.34 | 64.32 | 734.02
| 2026-11-04 | Underserved Community | OCEANSIDE | N/A | Not Available | 63 | 45 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.31 | 0 | 197.01 | 6.31 | 190.7
| 2026-12-04 | Underserved Community | CHULA VISTA | N/A | Not Available | 113 | 81 | N/A |  | Not Available | Not Available | Not Available | 385.62 | Unknown | 229.1 | 0 | 197.01 | 614.72 | -417.71
| 2025-07-22 | N/A | SAN DIEGO | N/A | Not Available | 185 | 133 | N/A | 2024-01-18 | Not Available | Not Available | Not Available | -9.97 | Unknown | -0.82 | 0 | 153.83 | -10.79 | 164.62
| 2026-12-11 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 85 | 61 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.14 | 0 | 1066.55 | 11.14 | 1055.41
| 2026-09-01 | N/A | LA MESA | N/A | Not Available | 55 | 39 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.41 | 0 | 1103.3 | 13.41 | 1089.89
| 2025-03-13 | N/A | SAN DIEGO | N/A | Not Available | 173 | 123 | N/A | 2023-12-06 | Not Available | Not Available | Not Available | -7.55 | Unknown | -0.96 | 0 | 153.87 | -8.51 | 162.38
| 2026-05-23 | N/A | ENCINITAS | N/A | Not Available | 198 | 142 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | -27.15 | Unknown | -0.14 | 0 | 192.83 | -27.29 | 220.12
| 2025-05-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 438 | 314 | N/A |  | Not Available | Not Available | Not Available | 420.6 | Unknown | 200.8 | 0 | 400.91 | 621.4 | -220.49
| 2025-06-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 118 | 84 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | 232.44 | Unknown | 158.5 | 0 | 496.37 | 390.94 | 105.43
| 2025-08-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 226 | 162 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.52 | 0 | 153.49 | 9.52 | 143.97
| 2026-07-11 | N/A | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.72 | 0 | 197.01 | 7.72 | 189.29
| 2023-12-19 | Underserved Community | EL CAJON | N/A | Not Available | 354 | 254 | N/A | 2024-02-15 | Not Available | Not Available | Not Available | -9.88 | Unknown | -2.29 | 0 | 363.72 | -12.17 | 375.89
| 2024-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 226 | 162 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | -7.21 | Unknown | 4.43 | 0 | 98.41 | -2.78 | 101.19
| 2025-03-06 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 43 | 31 | N/A | 2023-06-14 | Not Available | Not Available | Not Available | -6.23 | Unknown | -2.35 | 0 | 495.75 | -8.58 | 504.33
| 2025-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 141 | 101 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | 328.68 | Unknown | 207.44 | 0 | 496.45 | 536.12 | -39.67
| 2025-01-18 | Underserved Community | CHULA VISTA | N/A | Not Available | 206 | 148 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | 342.42 | Unknown | 169.63 | 0 | 364.52 | 512.05 | -147.53
| 2025-03-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 116 | 84 | N/A | 2023-10-18 | Not Available | Not Available | Not Available | 490.35 | Unknown | 224.61 | 0 | 148.7 | 714.96 | -566.26
| 2024-03-21 | N/A | LA MESA | N/A | Not Available | 65 | 47 | N/A | 2023-05-09 | Not Available | Not Available | Not Available | -9.85 | Unknown | -3.72 | 0 | 499.96 | -13.57 | 513.53
| 2024-01-22 | Underserved Community | LAKESIDE | N/A | Not Available | 48 | 34 | N/A | 2023-03-02 | Not Available | Not Available | Not Available | -6.51 | Unknown | -2.47 | 0 | 341 | -8.98 | 349.98
| 2024-12-21 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 668 | 478 | N/A | 2023-07-03 | Not Available | Not Available | Not Available | -7.84 | Unknown | 392.44 | 0 | 480.37 | 384.6 | 95.77
| 2025-06-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A |  | Not Available | Not Available | Not Available | 304.25 | Unknown | 309.07 | 0 | 514.57 | 613.32 | -98.75
| 2026-10-18 | Underserved Community | VISTA | N/A | Not Available | 38 | 28 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.01 | 0 | 197.01 | 12.01 | 185
| 2025-08-28 | Underserved Community | OCEANSIDE | N/A | Not Available | 106 | 76 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | -11.51 | Unknown | 0.75 | 0 | 163.83 | -10.76 | 174.59
| 2025-03-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 307 | 219 | N/A | 2023-12-20 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.07 | 0 | 495.75 | -5.68 | 501.43
| 2025-02-15 | Underserved Community | FALLBROOK | N/A | Not Available | 182 | 130 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -9.46 | Unknown | -3.05 | 0 | 153.75 | -12.51 | 166.26
| 2025-02-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 148 | 106 | N/A | 2023-08-24 | Not Available | Not Available | Not Available | -3.93 | Unknown | 0.9 | 0 | 153.75 | -3.03 | 156.78
| 2026-12-19 | Underserved Community | VISTA | N/A | Not Available | 73 | 53 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.77 | 0 | 1064.43 | 11.77 | 1052.66
| 2026-09-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 31 | 22 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.96 | 0 | 197.01 | 10.96 | 186.05
| 2026-06-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2024-09-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 3 | 0 | 999.88 | 3 | 996.88
| 2025-03-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -15.44 | Unknown | -4.98 | 0 | 500.87 | -20.42 | 521.29
| 2025-09-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 191 | 137 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -5.1 | Unknown | -1.21 | 0 | 483.59 | -6.31 | 489.9
| 2026-01-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -6.58 | Unknown | -1.5 | 0 | 529.2 | -8.08 | 537.28
| 2025-08-18 | N/A | SAN DIEGO | N/A | Not Available | 201 | 145 | N/A | 2024-02-06 | Not Available | Not Available | Not Available | -6.69 | Unknown | -0.32 | 0 | 158.79 | -7.01 | 165.8
| 2025-09-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 212 | 152 | N/A | 2024-03-14 | Not Available | Not Available | Not Available | -8.94 | Unknown | -2.08 | 0 | 515.81 | -11.02 | 526.83
| 2025-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | -3.57 | Unknown | 15.65 | 0 | 534.53 | 12.08 | 522.45
| 2025-09-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 126 | 90 | N/A | 2024-01-09 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.1 | 0 | 515.81 | -5.19 | 521
| 2026-07-18 | N/A | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.56 | 0 | 192.95 | 11.56 | 181.39
| 2026-06-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.67 | 0 | 190.44 | 7.67 | 182.77
| 2025-12-09 | N/A | SAN DIEGO | N/A | Not Available | 152 | 108 | N/A | 2024-07-05 | Not Available | Not Available | Not Available | -2.84 | Unknown | 8.61 | 0 | 163.83 | 5.77 | 158.06
| 2025-10-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 182 | 130 | N/A | 2024-03-15 | Not Available | Not Available | Not Available | -4.77 | Unknown | 2.94 | 0 | 163.83 | -1.83 | 165.66
| 2025-06-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 245 | 175 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -4.76 | Unknown | -1.57 | 0 | 500.87 | -6.33 | 507.2
| 2025-09-26 | N/A | SAN DIEGO | N/A | Not Available | 246 | 176 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -5.05 | Unknown | -1.17 | 0 | 515.81 | -6.22 | 522.03
| 2026-05-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 190 | 136 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.82 | 0 | 1066.51 | 3.82 | 1062.69
| 2026-07-16 | N/A | SAN DIEGO | N/A | Not Available | 152 | 110 | N/A | 2024-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.97 | 0 | 192.95 | 6.97 | 185.98
| 2026-12-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 25.85 | 0 | 1066.55 | 25.85 | 1040.7
| 2026-10-23 | N/A | SAN DIEGO | N/A | Not Available | 53 | 37 | N/A | 2024-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.24 | 0 | 1066.55 | 5.24 | 1061.31
| 2026-04-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 983.86 | 3.17 | 980.69
| 2025-11-11 | N/A | SAN DIEGO | N/A | Not Available | 147 | 105 | N/A | 2024-03-08 | Not Available | Not Available | Not Available | -9.74 | Unknown | -2.28 | 0 | 153.26 | -12.02 | 165.28
| 2025-12-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 149 | 107 | N/A | 2024-01-16 | Not Available | Not Available | Not Available | -10.23 | Unknown | -2.73 | 0 | 515.81 | -12.96 | 528.77
| 2025-12-19 | N/A | SAN DIEGO | N/A | Not Available | 120 | 86 | N/A | 2024-06-13 | Not Available | Not Available | Not Available | -5.45 | Unknown | -1.27 | 0 | 534.57 | -6.72 | 541.29
| 2026-04-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 217 | 155 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.44 | 0 | 1050.61 | 3.44 | 1047.17
| 2025-10-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 203 | 145 | N/A |  | Not Available | Not Available | Not Available | 392.28 | Unknown | 193.95 | 0 | 534.53 | 586.23 | -51.7
| 2026-06-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 252 | 180 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | -1.25 | Unknown | 69.34 | 0 | 192.95 | 68.09 | 124.86
| 2026-10-25 | N/A | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.48 | 0 | 197.01 | 6.48 | 190.53
| 2024-07-20 | N/A | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2023-08-30 | Not Available | Not Available | Not Available | -8.34 | Unknown | -3.16 | 0 | 496.37 | -11.5 | 507.87
| 2026-11-21 | N/A | ENCINITAS | N/A | Not Available | 135 | 97 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.74 | 3981 | 197.01 | 3.74 | 193.27
| 2025-10-17 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 30 | 22 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.19 | 0 | 197.01 | 9.19 | 187.82
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 222 | 160 | N/A |  | Not Available | Not Available | Not Available | 828.62 | Unknown | 438.19 | 0 | 196.44 | 1266.81 | -1070.37
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 105 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -11.26 | Unknown | -6.11 | 0 | 196.44 | -17.37 | 213.81
| 2025-09-28 | Underserved Community | CHULA VISTA | N/A | Not Available | 481 | 343 | N/A | 2024-12-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.71 | 0 | 534.53 | 5.71 | 528.82
| 2025-10-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 221 | 159 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | 159.45 | Unknown | 90.74 | 0 | 534.53 | 250.19 | 284.34
| 2025-10-18 | N/A | SAN DIEGO | N/A | Not Available | 138 | 100 | N/A | 2024-03-04 | Not Available | Not Available | Not Available | -5.32 | Unknown | -1.26 | 0 | 491.58 | -6.58 | 498.16
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 142 | 102 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.4 | 0 | 196.69 | 5.4 | 191.29
| 2023-03-03 | Underserved Community | LEMON GROVE | N/A | Not Available | 35 | 25 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | -31.4 | Unknown | 1255.11 | 0 | 496.37 | 1223.71 | -727.34
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 213 | 153 | N/A |  | Not Available | Not Available | Not Available | 317.94 | Unknown | 209.84 | 0 | 196.44 | 527.78 | -331.34
| 2025-08-02 | N/A | SAN DIEGO | N/A | Not Available | 150 | 108 | N/A | 2024-02-16 | Not Available | Not Available | Not Available | -11.52 | Unknown | -1.14 | 0 | 158.79 | -12.66 | 171.45
| 2026-08-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 183 | 131 | N/A | 2025-02-21 | Not Available | Not Available | Not Available | -12.02 | Unknown | 598.5 | 0 | 1066.51 | 586.48 | 480.03
| 2026-12-02 | N/A | SAN DIEGO | N/A | Not Available | 90 | 64 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.98 | 0 | 1066.55 | 5.98 | 1060.57
| 2026-10-29 | Underserved Community | ESCONDIDO | N/A | Not Available | 108 | 78 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.58 | 0 | 197.01 | 6.58 | 190.43
| 2025-09-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 201 | 143 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | -10.72 | Unknown | -0.96 | 0 | 158.79 | -11.68 | 170.47
| 2025-09-20 | N/A | SAN DIEGO | N/A | Not Available | 95 | 69 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | -9.87 | Unknown | -2.29 | 0 | 529.2 | -12.16 | 541.36
| 2026-05-15 | N/A | LA JOLLA | N/A | Not Available | 119 | 85 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 58.61 | 0 | 1049.43 | 58.61 | 990.82
| 2026-02-03 | N/A | EL CAJON | N/A | Not Available | 63 | 45 | N/A | 2024-04-03 | Not Available | Not Available | Not Available | -6.5 | Unknown | -1.51 | 0 | 501.14 | -8.01 | 509.15
| 2025-01-10 | Underserved Community | CHULA VISTA | N/A | Not Available | 154 | 110 | N/A | 2024-04-03 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.86 | 0 | 534.53 | -4.6 | 539.13
| 2025-06-14 | Underserved Community,Tribal Community | PALA | N/A | Not Available | 297 | 213 | N/A | 2024-04-10 | Not Available | Not Available | Not Available | 47.22 | Unknown | 48.8 | 0 | 483.59 | 96.02 | 387.57
| 2023-05-18 | Underserved Community | OCEANSIDE | N/A | Not Available | 150 | 108 | N/A | 2023-09-15 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.83 | 0 | 496.37 | -6.61 | 502.98
| 2026-09-04 | Underserved Community | SAN MARCOS | N/A | Not Available | 59 | 43 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.27 | 0 | 197.01 | 5.27 | 191.74
| 2025-03-01 | Underserved Community | BONITA | N/A | Not Available | 253 | 181 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -3.8 | Unknown | -0.63 | 0 | 534.53 | -4.43 | 538.96
| 2025-12-05 | N/A | ENCINITAS | N/A | Not Available | 51 | 37 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.17 | 0 | 197.01 | 6.17 | 190.84
| 2025-08-02 | N/A | SAN MARCOS | N/A | Not Available | 161 | 115 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -12.37 | Unknown | -2.12 | 0 | 158.79 | -14.49 | 173.28
| 2027-03-11 | N/A | RANCHO LA COSTA | N/A | Not Available | 62 | 44 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2026-01-06 | N/A | LA JOLLA | N/A | Not Available | 63 | 45 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.44 | 0 | 196.69 | 14.44 | 182.25
| 2024-03-04 | Underserved Community | ESCONDIDO | N/A | Not Available | 151 | 109 | N/A | 2023-08-18 | Not Available | Not Available | Not Available | -5.83 | Unknown | -2.22 | 0 | 464.78 | -8.05 | 472.83
| 2023-06-23 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 134 | 96 | N/A | 2023-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.55 | 0 | 154.99 | -1.55 | 156.54
| 2025-04-01 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 62 | 44 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | 108.06 | Unknown | 80.53 | 0 | 180.38 | 188.59 | -8.21
| 2025-01-31 | N/A | LAGUNA HILLS | N/A | Not Available | 111 | 79 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -12.63 | Unknown | 0.05 | 0 | 117.79 | -12.58 | 130.37
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 266 | 190 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -25.92 | Unknown | 250.86 | 0 | 930.97 | 224.94 | 706.03
| 2025-01-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 136 | 98 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | -11.48 | Unknown | -4.2 | 0 | 154.79 | -15.68 | 170.47
| 2025-03-29 | Underserved Community | ESCONDIDO | N/A | Not Available | 168 | 120 | N/A | 2023-12-29 | Not Available | Not Available | Not Available | -10.61 | Unknown | -2.84 | 0 | 153.83 | -13.45 | 167.28
| 2026-07-23 | N/A | LAGUNA NIGUEL | N/A | Not Available | 68 | 50 | N/A | 2024-09-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 19.78 | 0 | 102.37 | 19.78 | 82.59
| 2025-06-03 | Underserved Community | MISSION VIEJO | N/A | Not Available | 65 | 47 | N/A | 2024-07-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.05 | 0 | 192.51 | 7.05 | 185.46
| 2025-02-02 | Underserved Community | SAN MARCOS | N/A | Not Available | 114 | 82 | N/A | 2023-07-19 | Not Available | Not Available | Not Available | -15.71 | Unknown | -3.89 | 0 | 153.75 | -19.6 | 173.35
| 2027-02-05 | N/A | RANCHO SANTA FE | N/A | Not Available | 24 | 18 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.26 | 0 | 278.69 | 3.26 | 275.43
| 2026-07-03 | N/A | CARLSBAD | N/A | Not Available | 29 | 21 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.44 | 0 | 192.51 | 3.44 | 189.07
| 2024-11-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A | 2023-08-03 | Not Available | Not Available | Not Available | -10.47 | Unknown | -1.62 | 0 | 153.75 | -12.09 | 165.84
| 2024-12-29 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2023-05-24 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.49 | 0 | 495.75 | -5.41 | 501.16
| 2024-09-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 194 | 138 | N/A | 2023-04-27 | Not Available | Not Available | Not Available | -4.96 | Unknown | 61 | 0 | 98.41 | 56.04 | 42.37
| 2025-03-06 | N/A | SAN DIEGO | N/A | Not Available | 308 | 220 | N/A | 2024-04-09 | Not Available | Not Available | Not Available | -10.23 | Unknown | -1.19 | 0 | 148.74 | -11.42 | 160.16
| 2023-08-07 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 46 | 34 | N/A | 2023-12-27 | Not Available | Not Available | Not Available | -17.15 | Unknown | 617.11 | 0 | 513.31 | 599.96 | -86.65
| 2026-08-06 | N/A | ENCINITAS | N/A | Not Available | 39 | 29 | N/A | 2024-12-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.1 | 0 | 197.01 | 10.1 | 186.91
| 2027-01-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 10 | 8 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.31 | 0 | 1066.55 | 6.31 | 1060.24
| 2026-10-28 | N/A | RANCHO SANTA FE | N/A | Not Available | 28 | 20 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.37 | 0 | 197.01 | 7.37 | 189.64
| 2026-06-26 | N/A | CARLSBAD | N/A | Not Available | 25 | 19 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.72 | 0 | 197.01 | 9.72 | 187.29
| 2026-12-06 | N/A | CARLSBAD | N/A | Not Available | 30 | 22 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.45 | 3981 | 197.01 | 8.45 | 188.56
| 2025-06-20 | N/A | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2023-11-10 | Not Available | Not Available | Not Available | -10.98 | Unknown | -3.54 | 0 | 158.51 | -14.52 | 173.03
| 2026-10-28 | N/A | SAN DIEGO | N/A | Not Available | 19 | 13 | N/A | 2024-12-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.68 | 0 | 197.01 | 14.68 | 182.33
| 2026-10-28 | Underserved Community | SPRING VALLEY | N/A | Not Available | 22 | 16 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.53 | 0 | 1066.55 | 5.53 | 1061.02
| 2027-01-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 25 | 19 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | -15.82 | Unknown | -6.85 | 0 | 196.44 | -22.67 | 219.11
| 2026-03-13 | N/A | SAN DIEGO | N/A | Not Available | 18 | 12 | N/A | 2024-06-28 | Not Available | Not Available | Not Available | -6.4 | Unknown | 3.35 | 0 | 192.83 | -3.05 | 195.88
| 2025-07-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 72 | 52 | N/A | 2024-02-27 | Not Available | Not Available | Not Available | -15.1 | Unknown | -3.52 | 0 | 515.81 | -18.62 | 534.43
| 2026-12-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.61 | 0 | 190.44 | 2.61 | 187.83
| 2023-09-18 | Underserved Community | OCEANSIDE | N/A | Not Available | 159 | 113 | N/A | 2024-04-02 | Not Available | Not Available | Not Available | -9.09 | Unknown | -2.13 | 0 | 202.37 | -11.22 | 213.59
| 2025-05-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 193 | 139 | N/A |  | Not Available | Not Available | Not Available | 306.13 | Unknown | 184.06 | 0 | 152.86 | 490.19 | -337.33
| 2024-08-24 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 60 | 44 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | -8.69 | Unknown | -2.33 | 0 | 1393.85 | -11.02 | 1404.87
| 2026-08-14 | Underserved Community | VISTA | N/A | Not Available | 6 | 4 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.98 | 0 | 283.53 | 6.98 | 276.55
| 2026-10-28 | N/A | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2025-04-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.27 | 0 | 197.01 | 7.27 | 189.74
| 2025-04-23 | N/A | SAN DIEGO | N/A | Not Available | 124 | 90 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | -12.4 | Unknown | -2.84 | 0 | 158.51 | -15.24 | 173.75
| 2025-11-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 119 | 85 | N/A | 2023-11-14 | Not Available | Not Available | Not Available | 203.42 | Unknown | 104.51 | 0 | 496.37 | 307.93 | 188.44
| 2025-02-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 126 | 90 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | -8.87 | Unknown | -3.38 | 0 | 29.41 | -12.25 | 41.66
| 2025-03-01 | Underserved Community | BONITA | N/A | Not Available | 76 | 54 | N/A | 2023-07-13 | Not Available | Not Available | Not Available | 280.92 | Unknown | 175.85 | 0 | 495.75 | 456.77 | 38.98
| 2023-07-18 | Underserved Community | EL CAJON | N/A | Not Available | 280 | 200 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | -6.47 | Unknown | -2 | 0 | 499.96 | -8.47 | 508.43
| 2024-11-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 54 | 38 | N/A |  | Not Available | Not Available | Not Available | 819.44 | Unknown | 498.81 | 0 | 363.72 | 1318.25 | -954.53
| 2024-08-26 | N/A | SAN DIEGO | N/A | Not Available | 259 | 185 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.42 | 0 | 143.91 | 3.42 | 140.49
| 2024-02-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A | 2023-03-16 | Not Available | Not Available | Not Available | -4.49 | Unknown | 2.98 | 0 | 363.72 | -1.51 | 365.23
| 2023-12-20 | Underserved Community | VISTA | N/A | Not Available | 145 | 103 | N/A | 2023-06-14 | Not Available | Not Available | Not Available | -9 | Unknown | -3.44 | 0 | 351.99 | -12.44 | 364.43
| 2027-02-03 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 104 | 74 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.44 | 1.76 | 194.68
| 2026-03-12 | N/A | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.12 | 0 | 1103.34 | 12.12 | 1091.22
| 2024-04-27 | N/A | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -5.65 | Unknown | 0.24 | 0 | 158.79 | -5.41 | 164.2
| 2026-05-30 | Underserved Community | POWAY | N/A | Not Available | 260 | 186 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.72 | 0 | 197.01 | 5.72 | 191.29
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 106 | 76 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.21 | 3981 | 192.95 | 6.21 | 186.74
| 2026-12-04 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.12 | 0 | 197.01 | 8.12 | 188.89
| 2025-07-17 | N/A | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -9.35 | Unknown | -2.19 | 0 | 144.99 | -11.54 | 156.53
| 2026-01-31 | N/A | CORONADO | N/A | Not Available | 67 | 49 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | -8.98 | Unknown | -2.07 | 0 | 534.57 | -11.05 | 545.62
| 2026-04-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.29 | 0 | 197.01 | 11.29 | 185.72
| 2026-09-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 171 | 123 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | -12.2 | Unknown | -6.65 | 0 | 1066.51 | -18.85 | 1085.36
| 2026-06-03 | N/A | SAN DIEGO | N/A | Not Available | 264 | 188 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.79 | 0 | 192.95 | 4.79 | 188.16
| 2025-11-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 146 | 104 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -7.88 | Unknown | -1.79 | 0 | 534.53 | -9.67 | 544.2
| 2026-01-05 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 325 | 233 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.96 | 0 | 158.37 | 10.96 | 147.41
| 2026-04-11 | N/A | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -33.05 | Unknown | -4.09 | 0 | 192.83 | -37.14 | 229.97
| 2026-05-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 133 | 95 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.27 | 3981 | 192.51 | 5.27 | 187.24
| 2025-09-27 | N/A | SAN DIEGO | N/A | Not Available | 40 | 30 | N/A | 2023-10-19 | Not Available | Not Available | Not Available | -13.16 | Unknown | -3.6 | 0 | 148.28 | -16.76 | 165.04
| 2024-03-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 282 | 202 | N/A | 2023-12-28 | Not Available | Not Available | Not Available | -3.4 | Unknown | -0.93 | 0 | 496.45 | -4.33 | 500.78
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | -24.41 | Unknown | -13.28 | 0 | 797.33 | -37.69 | 835.02
| 2024-03-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 279 | 199 | N/A | 2023-09-18 | Not Available | Not Available | Not Available | -1.1 | Unknown | -0.39 | 0 | 496.37 | -1.49 | 497.86
| 2025-12-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -3.98 | Unknown | 0.01 | 0 | 1108.97 | -3.97 | 1112.94
| 2026-08-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.11 | 0 | 1050.75 | 4.11 | 1046.64
| 2025-09-22 | N/A | SAN DIEGO | N/A | Not Available | 141 | 101 | N/A | 2024-01-31 | Not Available | Not Available | Not Available | -13.07 | Unknown | -1.82 | 0 | 163.83 | -14.89 | 178.72
| 2027-04-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | -1.25 | Unknown | 61.83 | 0 | 1063.64 | 60.58 | 1003.06
| 2026-03-13 | N/A | SAN DIEGO | N/A | Not Available | 120 | 86 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -21.82 | Unknown | -3.5 | 0 | 162.34 | -25.32 | 187.66
| 2024-06-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A |  | Not Available | Not Available | Not Available | 253.74 | Unknown | 179.19 | 0 | 1050.75 | 432.93 | 617.82
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 142 | 102 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.78 | 0 | 196.69 | 3.78 | 192.91
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 214 | 154 | N/A |  | Not Available | Not Available | Not Available | 266.52 | Unknown | 165.6 | 0 | 196.59 | 432.12 | -235.53
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 142 | 102 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.47 | 0 | 196.69 | 4.47 | 192.22
| 2026-08-01 | Underserved Community | LA MESA | N/A | Not Available | 122 | 88 | N/A | 2024-11-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.77 | 0 | 192.95 | 4.77 | 188.18
| 2025-04-19 | N/A | LA JOLLA | N/A | Not Available | 373 | 267 | N/A | 2024-07-02 | Not Available | Not Available | Not Available | -12.87 | Unknown | 429.16 | 0 | 496.37 | 416.29 | 80.08
| 2025-10-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 210 | 150 | N/A | 2024-04-26 | Not Available | Not Available | Not Available | -7.03 | Unknown | -0.4 | 0 | 158.79 | -7.43 | 166.22
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 104 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | -19.94 | Unknown | 183.17 | 0 | 196.69 | 163.23 | 33.46
| 2024-03-31 | N/A | SAN DIEGO | N/A | Not Available | 200 | 144 | N/A | 2023-10-12 | Not Available | Not Available | Not Available | -9.96 | Unknown | -2.46 | 0 | 153.83 | -12.42 | 166.25
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 104 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -15.58 | Unknown | 286.33 | 0 | 196.69 | 270.75 | -74.06
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 214 | 154 | N/A |  | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.59 | 341.4 | -144.81
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 101 | 73 | N/A |  | Not Available | Not Available | Not Available | 414.31 | Unknown | 273.45 | 0 | 196.44 | 687.76 | -491.32
| 2026-03-15 | Underserved Community | BONITA | N/A | Not Available | 119 | 85 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.23 | 0 | 984.98 | 6.23 | 978.75
| 2025-11-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 179 | 127 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -5.45 | Unknown | -1.28 | 0 | 515.81 | -6.73 | 522.54
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 213 | 153 | N/A |  | Not Available | Not Available | Not Available | 317.94 | Unknown | 209.84 | 0 | 196.44 | 527.78 | -331.34
| 2026-01-16 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-02-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.66 | 3981 | 997.93 | 7.66 | 990.27
| 2025-05-09 | N/A | LAGUNA NIGUEL | N/A | Not Available | 35 | 25 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -17.82 | Unknown | -2.86 | 0 | 180.38 | -20.68 | 201.06
| 2025-02-08 | Underserved Community | OCEANSIDE | N/A | Not Available | 238 | 170 | N/A | 2023-07-07 | Not Available | Not Available | Not Available | -8.52 | Unknown | -3.25 | 0 | 98.41 | -11.77 | 110.18
| 2025-09-10 | N/A | SAN DIEGO | N/A | Not Available | 148 | 106 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -22.03 | Unknown | -3.91 | 0 | 158.79 | -25.94 | 184.73
| 2026-10-01 | Underserved Community | VISTA | N/A | Not Available | 75 | 53 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.36 | 0 | 197.01 | 15.36 | 181.65
| 2026-12-09 | N/A | SANTEE | N/A | Not Available | 84 | 60 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 11 | 0 | 98.9 | 11 | 87.9
| 2026-09-10 | Underserved Community | OCEANSIDE | N/A | Not Available | 124 | 88 | N/A | 2025-02-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.28 | 0 | 197.01 | 9.28 | 187.73
| 2025-03-27 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 109 | 79 | N/A | 2023-06-24 | Not Available | Not Available | Not Available | -5.89 | Unknown | -2.27 | 0 | 619.73 | -8.16 | 627.89
| 2025-07-28 | Underserved Community | OCEANSIDE | N/A | Not Available | 175 | 125 | N/A | 2024-01-12 | Not Available | Not Available | Not Available | -7.2 | Unknown | -0.44 | 0 | 327.98 | -7.64 | 335.62
| 2025-08-07 | Underserved Community | OCEANSIDE | N/A | Not Available | 82 | 58 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | -10.78 | Unknown | -3.9 | 0 | 158.51 | -14.68 | 173.19
| 2025-06-21 | N/A | RANCHO LA COSTA | N/A | Not Available | 167 | 119 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -9.1 | Unknown | -2.92 | 0 | 158.14 | -12.02 | 170.16
| 2025-02-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 316 | 226 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -3.58 | Unknown | -0.94 | 0 | 513.31 | -4.52 | 517.83
| 2026-09-04 | N/A | ENCINITAS | N/A | Not Available | 51 | 37 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 197.01 | 4.01 | 193
| 2025-02-23 | Underserved Community | ESCONDIDO | N/A | Not Available | 213 | 153 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | -10.54 | Unknown | -3.84 | 0 | 513.5 | -14.38 | 527.88
| 2025-10-21 | N/A | CARDIFF | N/A | Not Available | 198 | 142 | N/A | 2024-04-19 | Not Available | Not Available | Not Available | 744.3 | Unknown | 963.77 | 0 | 534.53 | 1708.07 | -1173.54
| 2025-10-10 | Underserved Community | CHULA VISTA | N/A | Not Available | 249 | 177 | N/A | 2024-07-05 | Not Available | Not Available | Not Available | -7.37 | Unknown | -1.37 | 0 | 534.53 | -8.74 | 543.27
| 2026-03-21 | N/A | LA JOLLA | N/A | Not Available | 102 | 72 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 36.84 | 0 | 1049.43 | 36.84 | 1012.59
| 2026-01-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 101 | 73 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -4.29 | Unknown | -1.01 | 0 | 118.78 | -5.3 | 124.08
| 2025-06-13 | Underserved Community | ESCONDIDO | N/A | Not Available | 69 | 49 | N/A | 2024-05-13 | Not Available | Not Available | Not Available | -7.45 | Unknown | -1.71 | 0 | 553.02 | -9.16 | 562.18
| 2025-12-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 118 | 84 | N/A | 2024-04-18 | Not Available | Not Available | Not Available | -4.95 | Unknown | -1.17 | 0 | 641.5 | -6.12 | 647.62
| 2024-09-10 | N/A | DEL MAR | N/A | Not Available | 121 | 87 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -25.38 | Unknown | -8.21 | 0 | 483.59 | -33.59 | 517.18
| 2025-06-14 | Underserved Community | SAN MARCOS | N/A | Not Available | 264 | 190 | N/A | 2024-03-11 | Not Available | Not Available | Not Available | -11.83 | Unknown | -2.73 | 0 | 617.5 | -14.56 | 632.06
| 2026-12-05 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 23 | 17 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.08 | 0 | 197.01 | 18.08 | 178.93
| 2025-03-01 | N/A | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2023-06-02 | Not Available | Not Available | Not Available | -7.77 | Unknown | -2.96 | 0 | 153.75 | -10.73 | 164.48
| 2024-11-15 | Underserved Community | OCEANSIDE | N/A | Not Available | 169 | 121 | N/A | 2023-04-25 | Not Available | Not Available | Not Available | -3.3 | Unknown | -1.26 | 0 | 363.72 | -4.56 | 368.28
| 2024-10-18 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2023-02-23 | Not Available | Not Available | Not Available | -6.75 | Unknown | -2.56 | 0 | 351.99 | -9.31 | 361.3
| 2024-02-22 | Underserved Community | VISTA | N/A | Not Available | 129 | 93 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -8.13 | Unknown | -3.1 | 0 | 464.78 | -11.23 | 476.01
| 2024-02-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 29 | 21 | N/A | 2023-05-03 | Not Available | Not Available | Not Available | -4.1 | Unknown | -1.54 | 0 | 153.75 | -5.64 | 159.39
| 2023-11-28 | N/A | MISSION VIEJO | N/A | Not Available | 141 | 101 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | -8.97 | Unknown | -3.39 | 0 | 67.06 | -12.36 | 79.42
| 2023-11-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -9.35 | Unknown | -2.33 | 0 | 95.13 | -11.68 | 106.81
| 2025-01-25 | Underserved Community | FALLBROOK | N/A | Not Available | 121 | 87 | N/A | 2023-04-20 | Not Available | Not Available | Not Available | -8.9 | Unknown | -3.4 | 0 | 468.73 | -12.3 | 481.03
| 2024-03-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 38 | 28 | N/A | 2023-08-02 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.9 | 0 | 143.95 | -6.86 | 150.81
| 2025-02-19 | N/A | SAN DIEGO | N/A | Not Available | 326 | 234 | N/A | 2024-03-08 | Not Available | Not Available | Not Available | -7.39 | Unknown | -0.55 | 0 | 153.75 | -7.94 | 161.69
| 2023-12-10 | Underserved Community | OCEANSIDE | N/A | Not Available | 145 | 103 | N/A | 2023-02-15 | Not Available | Not Available | Not Available | -11.68 | Unknown | -4.45 | 0 | 98.41 | -16.13 | 114.54
| 2025-06-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 435 | 311 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.9 | 0 | 152.86 | 9.9 | 142.96
| 2025-02-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2023-04-05 | Not Available | Not Available | Not Available | -6.11 | Unknown | -2.33 | 0 | 499.96 | -8.44 | 508.4
| 2025-10-12 | N/A | RANCHO LA COSTA | N/A | Not Available | 261 | 187 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.57 | 0 | 192.95 | 11.57 | 181.38
| 2025-03-20 | N/A | LAS FLORES | N/A | Not Available | 26 | 18 | N/A | 2024-06-11 | Not Available | Not Available | Not Available | -7.66 | Unknown | 1.66 | 0 | 74.16 | -6 | 80.16
| 2025-06-27 | N/A | DANA POINT | N/A | Not Available | 22 | 16 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | 164.59 | Unknown | 117.85 | 0 | 74.22 | 282.44 | -208.22
| 2027-02-18 | N/A | DANA POINT | N/A | Not Available | 25 | 19 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.82 | 0 | 196.44 | 10.82 | 185.62
| 2024-06-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 23 | 17 | N/A | 2023-10-10 | Not Available | Not Available | Not Available | -5.82 | Unknown | -2.12 | 0 | 198.18 | -7.94 | 206.12
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 183 | 131 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | -6.48 | Unknown | 406.12 | 0 | 793.89 | 399.64 | 394.25
| 2026-12-13 | N/A | LAGUNA NIGUEL | N/A | Not Available | 24 | 18 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.66 | 0 | 196.69 | 13.66 | 183.03
| 2024-09-21 | Underserved Community | SAN MARCOS | N/A | Not Available | 143 | 103 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | -8.38 | Unknown | -3.19 | 0 | 153.75 | -11.57 | 165.32
| 2024-08-10 | N/A | ENCINITAS | N/A | Not Available | 34 | 24 | N/A | 2023-10-16 | Not Available | Not Available | Not Available | -6.34 | Unknown | -2.29 | 0 | 153.83 | -8.63 | 162.46
| 2025-02-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2023-05-16 | Not Available | Not Available | Not Available | -18.1 | Unknown | 2106.81 | 0 | 495.75 | 2088.71 | -1592.96
| 2024-05-25 | N/A | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -7.71 | Unknown | -2.07 | 0 | 202.37 | -9.78 | 212.15
| 2026-10-18 | N/A | RANCHO SANTA FE | N/A | Not Available | 46 | 32 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.32 | 0 | 197.01 | 9.32 | 187.69
| 2024-12-05 | N/A | OCEANSIDE | N/A | Not Available | 170 | 122 | N/A | 2023-05-24 | Not Available | Not Available | Not Available | -5.23 | Unknown | -1.99 | 0 | 98.41 | -7.22 | 105.63
| 2026-04-04 | Underserved Community | OCEANSIDE | N/A | Not Available | 291 | 209 | N/A | 2025-02-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.3 | 0 | 162.34 | 9.3 | 153.04
| 2025-08-04 | N/A | ENCINITAS | N/A | Not Available | 39 | 29 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.11 | 0 | 160.61 | 5.11 | 155.5
| 2026-10-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 26 | 18 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.27 | 0 | 643.93 | 5.27 | 638.66
| 2026-11-14 | N/A | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.55 | 0 | 197.01 | 11.55 | 185.46
| 2025-08-21 | Underserved Community | FALLBROOK | N/A | Not Available | 22 | 16 | N/A | 2023-12-01 | Not Available | Not Available | Not Available | -8.05 | Unknown | 0.08 | 0 | 41.57 | -7.97 | 49.54
| 2026-06-25 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 20 | 14 | N/A | 2024-08-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.33 | 0 | 788.08 | 3.33 | 784.75
| 2026-07-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 38 | 28 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.48 | 0 | 283.53 | 8.48 | 275.05
| 2027-04-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 23 | 17 | N/A |  | Not Available | Not Available | Not Available | 303.12 | Unknown | 200.02 | 0 | 421.99 | 503.14 | -81.15
| 2025-11-04 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 48 | 34 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | -11.51 | Unknown | 59.35 | 0 | 400.94 | 47.84 | 353.1
| 2025-06-23 | Underserved Community | FALLBROOK | N/A | Not Available | 29 | 21 | N/A | 2023-12-20 | Not Available | Not Available | Not Available | -19.63 | Unknown | -2.02 | 0 | 41.57 | -21.65 | 63.22
| 2025-03-27 | Underserved Community | CHULA VISTA | N/A | Not Available | 26 | 18 | N/A | 2023-07-24 | Not Available | Not Available | Not Available | -7.37 | Unknown | 1.06 | 0 | 148.74 | -6.31 | 155.05
| 2026-05-01 | N/A | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2024-07-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.66 | 0 | 192.51 | 3.66 | 188.85
| 2027-04-22 | N/A | CHULA VISTA | N/A | Not Available | 24 | 18 | N/A |  | Not Available | Not Available | Not Available | 446.48 | Unknown | 405.53 | 0 | 114.3 | 852.01 | -737.71
| 2027-04-14 | N/A | LAGUNA NIGUEL | N/A | Not Available | 26 | 18 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2025-12-15 | N/A | ENCINITAS | N/A | Not Available | 103 | 73 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -4.55 | Unknown | -1.07 | 0 | 209.87 | -5.62 | 215.49
| 2025-08-18 | N/A | ESCONDIDO | N/A | Not Available | 113 | 81 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | -4.81 | Unknown | 0.07 | 0 | 41.38 | -4.74 | 46.12
| 2026-10-08 | Underserved Community | NATIONAL CITY | N/A | Not Available | 176 | 126 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | -4.62 | Unknown | -2.51 | 0 | 799.9 | -7.13 | 807.03
| 2026-02-15 | N/A | DEL MAR | N/A | Not Available | 148 | 106 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | 502.72 | Unknown | 345.02 | 0 | 209.87 | 847.74 | -637.87
| 2026-04-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 194 | 140 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.54 | 0 | 283.36 | 9.54 | 273.82
| 2026-10-28 | N/A | OCEANSIDE | N/A | Not Available | 71 | 51 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.36 | 0 | 197.01 | 14.36 | 182.65
| 2026-10-17 | N/A | VISTA | N/A | Not Available | 134 | 96 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | -7.91 | Unknown | -2.69 | 0 | 197.01 | -10.6 | 207.61
| 2026-04-05 | Underserved Community | OCEANSIDE | N/A | Not Available | 51 | 37 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.45 | 0 | 197.01 | 14.45 | 182.56
| 2026-04-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 49 | 35 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -4.37 | Unknown | 0.75 | 0 | 192.83 | -3.62 | 196.45
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 83 | 59 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.37 | 3981 | 192.95 | 6.37 | 186.58
| 2026-06-05 | N/A | SAN DIEGO | N/A | Not Available | 177 | 127 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.05 | 3981 | 1049.43 | 6.05 | 1043.38
| 2025-07-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 263 | 187 | N/A | 2024-03-15 | Not Available | Not Available | Not Available | -7.36 | Unknown | -0.53 | 0 | 158.51 | -7.89 | 166.4
| 2025-05-18 | N/A | SAN DIEGO | N/A | Not Available | 233 | 167 | N/A | 2023-09-29 | Not Available | Not Available | Not Available | -3.57 | Unknown | -1.27 | 0 | 496.37 | -4.84 | 501.21
| 2025-08-17 | N/A | SAN DIEGO | N/A | Not Available | 357 | 255 | N/A | 2024-07-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.99 | 3981 | 481.24 | 4.99 | 476.25
| 2025-07-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 160 | 114 | N/A | 2024-02-13 | Not Available | Not Available | Not Available | -21.14 | Unknown | 823.51 | 0 | 515.81 | 802.37 | -286.56
| 2025-09-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 204 | 146 | N/A | 2024-04-08 | Not Available | Not Available | Not Available | -12.52 | Unknown | -2.89 | 0 | 515.81 | -15.41 | 531.22
| 2025-11-29 | N/A | SAN DIEGO | N/A | Not Available | 206 | 148 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -9.07 | Unknown | 0.21 | 0 | 43.07 | -8.86 | 51.93
| 2025-10-26 | N/A | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2024-01-10 | Not Available | Not Available | Not Available | -8.12 | Unknown | -0.94 | 0 | 158.79 | -9.06 | 167.85
| 2024-05-19 | N/A | SAN DIEGO | N/A | Not Available | 164 | 118 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -23.87 | Unknown | 498.56 | 0 | 496.37 | 474.69 | 21.68
| 2027-02-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2025-03-25 | Not Available | Not Available | Not Available | -6.68 | Unknown | -0.77 | 0 | 1063.08 | -7.45 | 1070.53
| 2026-10-21 | N/A | SAN DIEGO | N/A | Not Available | 46 | 32 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 3981 | 197.01 | 5.69 | 191.32
| 2026-05-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.43 | 0 | 1050.75 | 12.43 | 1038.32
| 2026-07-17 | N/A | SAN DIEGO | N/A | Not Available | 118 | 84 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.51 | 0 | 192.95 | 1.51 | 191.44
| 2025-12-11 | N/A | SAN DIEGO | N/A | Not Available | 114 | 82 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -10.26 | Unknown | -0.05 | 0 | 163.83 | -10.31 | 174.14
| 2026-02-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 190 | 136 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.21 | 0 | 162.34 | 8.21 | 154.13
| 2026-05-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.33 | 0 | 1049.43 | 3.33 | 1046.1
| 2025-04-04 | N/A | SAN DIEGO | N/A | Not Available | 126 | 90 | N/A | 2023-07-21 | Not Available | Not Available | Not Available | -10.58 | Unknown | -4.03 | 0 | 496.45 | -14.61 | 511.06
| 2026-03-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 89 | 65 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -6.58 | Unknown | 2.14 | 0 | 192.83 | -4.44 | 197.27
| 2027-03-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | 81.42 | Unknown | 507.33 | 0 | 1063.08 | 588.75 | 474.33
| 2025-07-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | -11.23 | Unknown | -3.61 | 0 | 481.24 | -14.84 | 496.08
| 2025-08-23 | N/A | SAN DIEGO | N/A | Not Available | 115 | 83 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | -6.33 | Unknown | -0.84 | 0 | 158.79 | -7.17 | 165.96
| 2026-09-26 | Underserved Community | SPRING VALLEY | N/A | Not Available | 30 | 22 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.06 | 0 | 1082.97 | 9.06 | 1073.91
| 2025-01-16 | Underserved Community | VISTA | N/A | Not Available | 12 | 8 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -9.81 | Unknown | -2.28 | 0 | 534.53 | -12.09 | 546.62
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 214 | 154 | N/A |  | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.59 | 341.4 | -144.81
| 2026-01-16 | Underserved Community | VISTA | N/A | Not Available | 190 | 136 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.92 | 0 | 163.83 | 7.92 | 155.91
| 2025-03-31 | N/A | SAN DIEGO | N/A | Not Available | 220 | 158 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | -6.26 | Unknown | -0.83 | 0 | 154.99 | -7.09 | 162.08
| 2024-05-23 | N/A | DANA POINT | N/A | Not Available | 201 | 143 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | -6.17 | Unknown | -2.01 | 0 | 158.51 | -8.18 | 166.69
| 2024-09-27 | N/A | SAN CLEMENTE | N/A | Not Available | 126 | 90 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | -5.14 | Unknown | -1.67 | 0 | 158.14 | -6.81 | 164.95
| 2026-03-27 | Underserved Community | SAN MARCOS | N/A | Not Available | 84 | 60 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.97 | 0 | 196.38 | 1.97 | 194.41
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 93 | 67 | N/A |  | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | 341.4 | -144.96
| 2025-07-23 | Underserved Community | LA MESA | N/A | Not Available | 192 | 138 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.18 | 0 | 2465.01 | 9.18 | 2455.83
| 2026-02-22 | N/A | SAN DIEGO | N/A | Not Available | 197 | 141 | N/A | 2024-07-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.45 | 3981 | 496.14 | 8.45 | 487.69
| 2024-10-04 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 378 | 270 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.51 | 0 | 148.28 | 2.51 | 145.77
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 213 | 153 | N/A |  | Not Available | Not Available | Not Available | 277.52 | Unknown | 172.03 | 0 | 196.44 | 449.55 | -253.11
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 101 | 73 | N/A |  | Not Available | Not Available | Not Available | 414.31 | Unknown | 273.45 | 0 | 196.44 | 687.76 | -491.32
| 2026-11-12 | Underserved Community | LAKESIDE | N/A | Not Available | 79 | 57 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.55 | 0 | 197.01 | 7.55 | 189.46
| 2025-04-20 | N/A | SAN DIEGO | N/A | Not Available | 410 | 294 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -5.84 | Unknown | -0.17 | 0 | 153.83 | -6.01 | 159.84
| 2026-10-01 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.97 | 0 | 197.01 | 7.97 | 189.04
| 2025-08-31 | Underserved Community | VISTA | N/A | Not Available | 132 | 94 | N/A | 2024-02-16 | Not Available | Not Available | Not Available | -11.63 | Unknown | -2.7 | 0 | 534.53 | -14.33 | 548.86
| 2026-03-11 | N/A | EL CAJON | N/A | Not Available | 129 | 93 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.75 | 0 | 1016.73 | 10.75 | 1005.98
| 2026-09-03 | N/A | ENCINITAS | N/A | Not Available | 121 | 87 | N/A | 2024-12-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.58 | 0 | 1066.51 | 7.58 | 1058.93
| 2026-09-18 | N/A | CARLSBAD | N/A | Not Available | 34 | 24 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.01 | 0 | 197.01 | 4.01 | 193
| 2026-08-24 | Underserved Community | VISTA | N/A | Not Available | 35 | 25 | N/A | 2024-09-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 1066.51 | 4.71 | 1061.8
| 2025-10-19 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 196 | 140 | N/A | 2024-03-20 | Not Available | Not Available | Not Available | -6.5 | Unknown | -1.51 | 0 | 534.53 | -8.01 | 542.54
| 2026-04-24 | N/A | ENCINITAS | N/A | Not Available | 73 | 53 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -11.33 | Unknown | 3.74 | 0 | 192.83 | -7.59 | 200.42
| 2026-11-12 | Underserved Community | FALLBROOK | N/A | Not Available | 17 | 13 | N/A |  | Not Available | Not Available | Not Available | 606.24 | Unknown | 419.92 | 0 | 1103.34 | 1026.16 | 77.18
| 2025-08-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 150 | 108 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -7.93 | Unknown | -2.15 | 0 | 533.61 | -10.08 | 543.69
| 2026-10-29 | Underserved Community | CHULA VISTA | N/A | Not Available | 159 | 113 | N/A |  | Not Available | Not Available | Not Available | 642.7 | Unknown | 408.31 | 0 | 190.44 | 1051.01 | -860.57
| 2025-09-21 | N/A | LA JOLLA | N/A | Not Available | 171 | 123 | N/A | 2024-02-07 | Not Available | Not Available | Not Available | -9.85 | Unknown | -2.29 | 0 | 515.81 | -12.14 | 527.95
| 2026-03-14 | Underserved Community | CHULA VISTA | N/A | Not Available | 345 | 247 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 16.75 | 3981 | 984.98 | 16.75 | 968.23
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 358.5 | Unknown | 187.64 | 0 | 196.44 | 546.14 | -349.7
| 2024-06-30 | N/A | VALLEY CENTER | N/A | Not Available | 231 | 165 | N/A | 2024-03-27 | Not Available | Not Available | Not Available | -14.58 | Unknown | 695.89 | 0 | 112.14 | 681.31 | -569.17
| 2024-12-09 | Underserved Community | CHULA VISTA | N/A | Not Available | 131 | 93 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | -9.02 | Unknown | 1.35 | 0 | 154.79 | -7.67 | 162.46
| 2025-01-14 | Underserved Community | OCEANSIDE | N/A | Not Available | 77 | 55 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -6.67 | Unknown | -2.54 | 0 | 364.52 | -9.21 | 373.73
| 2025-10-07 | N/A | ENCINITAS | N/A | Not Available | 8 | 6 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | 377.04 | Unknown | 258.76 | 0 | 1032.11 | 635.8 | 396.31
| 2020-12-31 | N/A | LA JOLLA | N/A | Not Available | 168 | 120 | N/A | 2023-03-21 | Not Available | Not Available | Not Available | -6.3 | Unknown | 115.4 | 0 | 545.68 | 109.1 | 436.58
| 2026-10-30 | N/A | LAGUNA NIGUEL | N/A | Not Available | 25 | 19 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.48 | 0 | 104.94 | 10.48 | 94.46
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -24.32 | Unknown | 485.12 | 0 | 9923.78 | 460.8 | 9462.98
| 2024-11-11 | Underserved Community | VISTA | N/A | Not Available | 255 | 183 | N/A | 2023-10-16 | Not Available | Not Available | Not Available | -13.48 | Unknown | -4.99 | 0 | 363.72 | -18.47 | 382.19
| 2025-01-19 | N/A | ENCINITAS | N/A | Not Available | 186 | 134 | N/A | 2023-11-09 | Not Available | Not Available | Not Available | -18.29 | Unknown | -6.54 | 0 | 495.75 | -24.83 | 520.58
| 2025-06-19 | N/A | MISSION VIEJO | N/A | Not Available | 120 | 86 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.82 | 0 | 102.37 | 10.82 | 91.55
| 2026-10-25 | N/A | ENCINITAS | N/A | Not Available | 8 | 6 | N/A | 2024-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.46 | 0 | 197.01 | 9.46 | 187.55
| 2024-10-03 | N/A | POWAY | N/A | Not Available | 172 | 124 | N/A | 2023-04-20 | Not Available | Not Available | Not Available | -7.35 | Unknown | -2.77 | 0 | 517.21 | -10.12 | 527.33
| 2024-03-15 | N/A | LAGUNA NIGUEL | N/A | Not Available | 256 | 182 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | 140.46 | Unknown | 85.13 | 0 | 111.06 | 225.59 | -114.53
| 2024-03-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 59 | 43 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -7.69 | Unknown | -2.91 | 0 | 148.74 | -10.6 | 159.34
| 2026-11-07 | N/A | SAN CLEMENTE | N/A | Not Available | 86 | 62 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.78 | 0 | 105.08 | 15.78 | 89.3
| 2025-07-12 | N/A | SAN DIEGO | N/A | Not Available | 67 | 47 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.5 | 0 | 114.34 | 1.5 | 112.84
| 2025-02-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2023-07-14 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.5 | 0 | 499.96 | -5.42 | 505.38
| 2025-05-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -6.26 | Unknown | -2.25 | 0 | 372.29 | -8.51 | 380.8
| 2026-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2024-11-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.83 | 0 | 190.44 | 6.83 | 183.61
| 2024-11-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 161 | 115 | N/A | 2023-03-24 | Not Available | Not Available | Not Available | -5.15 | Unknown | -1.98 | 0 | 363.72 | -7.13 | 370.85
| 2027-01-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.16 | 0 | 189.89 | 6.16 | 183.73
| 2027-02-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 43 | 31 | N/A | 2025-04-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.88 | 0 | 196.59 | 1.88 | 194.71
| 2026-12-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | -18.86 | Unknown | 14.35 | 0 | 1063.08 | -4.51 | 1067.59
| 2025-10-17 | Underserved Community | LA MESA | N/A | Not Available | 39 | 29 | N/A | 2025-01-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.19 | 0 | 1379.23 | 6.19 | 1373.04
| 2025-06-27 | N/A | SOLANA BEACH | N/A | Not Available | 57 | 41 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -3.4 | Unknown | -0.93 | 0 | 513.31 | -4.33 | 517.64
| 2025-04-01 | Underserved Community | LA MESA | N/A | Not Available | 38 | 28 | N/A | 2024-06-18 | Not Available | Not Available | Not Available | -10.74 | Unknown | 423.28 | 0 | 1510.59 | 412.54 | 1098.05
| 2026-10-12 | N/A | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2024-11-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.71 | 3981 | 197.01 | 3.71 | 193.3
| 2027-01-24 | Underserved Community | OCEANSIDE | N/A | Not Available | 35 | 25 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.64 | 3981 | 196.69 | 6.64 | 190.05
| 2026-01-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 26 | 18 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.01 | 3981 | 196.69 | 5.01 | 191.68
| 2026-11-18 | Underserved Community | EL CAJON | N/A | Not Available | 25 | 19 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.27 | 0 | 1063.08 | 11.27 | 1051.81
| 2021-09-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2024-01-03 | Not Available | Not Available | Not Available | -4.68 | Unknown | -1.26 | 0 | 372.29 | -5.94 | 378.23
| 2026-06-05 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2024-11-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.58 | 3981 | 197.01 | 6.58 | 190.43
| 2026-03-20 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -10.79 | Unknown | -0.08 | 0 | 438.62 | -10.87 | 449.49
| 2025-03-08 | N/A | SAN DIEGO | N/A | Not Available | 382 | 274 | N/A | 2024-04-25 | Not Available | Not Available | Not Available | -10.92 | Unknown | -1.38 | 0 | 153.87 | -12.3 | 166.17
| 2023-07-20 | N/A | SAN DIEGO | N/A | Not Available | 193 | 137 | N/A | 2024-03-28 | Not Available | Not Available | Not Available | -5.28 | Unknown | -1.22 | 0 | 515.81 | -6.5 | 522.31
| 2025-07-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 150 | 108 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.44 | 0 | 514.57 | -1.44 | 516.01
| 2025-09-01 | N/A | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -7.85 | Unknown | -1.12 | 0 | 158.79 | -8.97 | 167.76
| 2024-03-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 157 | 113 | N/A | 2023-08-04 | Not Available | Not Available | Not Available | -10.19 | Unknown | -3.86 | 0 | 496.45 | -14.05 | 510.5
| 2025-12-14 | N/A | SAN DIEGO | N/A | Not Available | 256 | 184 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.75 | 0 | 163.83 | 7.75 | 156.08
| 2025-05-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 103 | N/A | 2024-03-12 | Not Available | Not Available | Not Available | -10.96 | Unknown | -2.55 | 0 | 534.53 | -13.51 | 548.04
| 2025-06-19 | N/A | SAN DIEGO | N/A | Not Available | 117 | 85 | N/A | 2023-09-26 | Not Available | Not Available | Not Available | -8.47 | Unknown | -3.07 | 0 | 496.37 | -11.54 | 507.91
| 2026-04-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 103 | N/A | 2024-10-07 | Not Available | Not Available | Not Available | -4.87 | Unknown | 251.5 | 0 | 1050.75 | 246.63 | 804.12
| 2025-09-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 346 | 248 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | -42.65 | Unknown | 2109.45 | 0 | 515.81 | 2066.8 | -1550.99
| 2025-08-31 | N/A | SAN DIEGO | N/A | Not Available | 148 | 106 | N/A | 2023-12-15 | Not Available | Not Available | Not Available | -10.4 | Unknown | 2.73 | 0 | 148.54 | -7.67 | 156.21
| 2026-01-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 132 | 94 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -11.43 | Unknown | -2.24 | 0 | 529.2 | -13.67 | 542.87
| 2026-01-16 | N/A | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-04-03 | Not Available | Not Available | Not Available | 563.76 | Unknown | 576.97 | 0 | 163.83 | 1140.73 | -976.9
| 2026-09-04 | N/A | SAN DIEGO | N/A | Not Available | 96 | 68 | N/A | 2024-11-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.88 | 0 | 197.01 | 8.88 | 188.13
| 2025-10-08 | N/A | SAN DIEGO | N/A | Not Available | 209 | 149 | N/A | 2024-05-02 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.29 | 0 | 515.81 | -6.76 | 522.57
| 2025-10-08 | N/A | SAN DIEGO | N/A | Not Available | 119 | 85 | N/A | 2024-02-12 | Not Available | Not Available | Not Available | -10.82 | Unknown | 337 | 0 | 515.81 | 326.18 | 189.63
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 214 | 154 | N/A |  | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.59 | 341.4 | -144.81
| 2026-05-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.64 | 3981 | 983.86 | 6.64 | 977.22
| 2025-04-28 | Underserved Community | LA MESA | N/A | Not Available | 56 | 40 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -32.75 | Unknown | -7.57 | 0 | 1050.61 | -40.32 | 1090.93
| 2024-07-25 | Underserved Community | LEMON GROVE | N/A | Not Available | 122 | 88 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | -16.25 | Unknown | 619.6 | 0 | 514.57 | 603.35 | -88.78
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 104 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -20.58 | Unknown | 283.62 | 0 | 196.69 | 263.04 | -66.35
| 2026-01-23 | Underserved Community | LAKESIDE | N/A | Not Available | 79 | 57 | N/A | 2024-04-10 | Not Available | Not Available | Not Available | -4.95 | Unknown | 0.31 | 0 | 648.55 | -4.64 | 653.19
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 105 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -11.87 | Unknown | -6.47 | 0 | 196.44 | -18.34 | 214.78
| 2026-03-01 | Underserved Community | EL CAJON | N/A | Not Available | 381 | 273 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | -44.17 | Unknown | -20.23 | 0 | 585.94 | -64.4 | 650.34
| 2025-09-12 | Underserved Community | SAN MARCOS | N/A | Not Available | 234 | 168 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | -4.46 | Unknown | 0.28 | 0 | 163.83 | -4.18 | 168.01
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 105 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -11.2 | Unknown | -6.09 | 0 | 196.44 | -17.29 | 213.73
| 2026-09-18 | N/A | LAGUNA HILLS | N/A | Not Available | 55 | 39 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.63 | 0 | 197.01 | 5.63 | 191.38
| 2025-04-25 | Underserved Community | BONSALL | N/A | Not Available | 373 | 267 | N/A | 2024-04-05 | Not Available | Not Available | Not Available | -13.23 | Unknown | -1.9 | 0 | 153.83 | -15.13 | 168.96
| 2024-03-28 | N/A | CARLSBAD | N/A | Not Available | 586 | 420 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | 0 | 513.31
| 2025-08-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 171 | 123 | N/A |  | Not Available | Not Available | Not Available | 378.69 | Unknown | 228.08 | 0 | 1202.76 | 606.77 | 595.99
| 2025-09-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 561 | 401 | N/A | 2025-02-17 | Not Available | Not Available | Not Available | -7.58 | Unknown | -1.71 | 0 | 158.79 | -9.29 | 168.08
| 2027-01-14 | N/A | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 196.69 | 8.02 | 188.67
| 2026-04-22 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.54 | 0 | 192.51 | 4.54 | 187.97
| 2026-07-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 267 | 191 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.55 | 0 | 197.01 | 2.55 | 194.46
| 2026-03-25 | Underserved Community | BONITA | N/A | Not Available | 161 | 115 | N/A | 2024-09-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.29 | 0 | 1050.75 | 4.29 | 1046.46
| 2026-06-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 36 | 26 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.15 | 3981 | 141.47 | 2.15 | 139.32
| 2025-09-13 | N/A | ENCINITAS | N/A | Not Available | 141 | 101 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | -8.4 | Unknown | 0.24 | 0 | 158.79 | -8.16 | 166.95
| 2027-02-07 | Underserved Community | EL CAJON | N/A | Not Available | 37 | 27 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 196.59 | 1.99 | 194.6
| 2025-08-03 | N/A | LA JOLLA | N/A | Not Available | 418 | 300 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | -6.92 | Unknown | 3.06 | 0 | 513.31 | -3.86 | 517.17
| 2025-09-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 228 | 164 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -6.69 | Unknown | -1.54 | 0 | 158.79 | -8.23 | 167.02
| 2026-11-26 | N/A | RANCHO LA COSTA | N/A | Not Available | 51 | 37 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | -1.88 | Unknown | 106.91 | 0 | 142.83 | 105.03 | 37.8
| 2026-08-26 | Underserved Community | OCEANSIDE | N/A | Not Available | 39 | 29 | N/A | 2024-10-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.07 | 0 | 197.01 | 6.07 | 190.94
| 2026-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 272 | 194 | N/A | 2024-08-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.67 | 0 | 163.83 | 7.67 | 156.16
| 2026-04-30 | Underserved Community | CHULA VISTA | N/A | Not Available | 233 | 167 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.4 | 0 | 1025.05 | 3.4 | 1021.65
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 358.5 | Unknown | 187.64 | 0 | 196.44 | 546.14 | -349.7
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 1574.55 | Unknown | 722.46 | 0 | 196.44 | 2297.01 | -2100.57
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 761.36 | Unknown | 709.34 | 0 | 196.44 | 1470.7 | -1274.26
| 2023-04-21 | N/A | SAN CLEMENTE | N/A | Not Available | 35 | 25 | N/A | 2023-03-30 | Not Available | Not Available | Not Available | -4.76 | Unknown | -1.78 | 0 | 67.06 | -6.54 | 73.6
| 2024-10-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A | 2023-02-23 | Not Available | Not Available | Not Available | -5.39 | Unknown | -0.83 | 0 | 98.41 | -6.22 | 104.63
| 2023-11-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 153 | 109 | N/A | 2023-05-03 | Not Available | Not Available | Not Available | -6.48 | Unknown | -1.22 | 0 | 98.41 | -7.7 | 106.11
| 2024-10-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 396 | 284 | N/A | 2023-02-13 | Not Available | Not Available | Not Available | -15.11 | Unknown | -4.57 | 0 | 98.41 | -19.68 | 118.09
| 2024-02-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 67 | 49 | N/A | 2023-04-10 | Not Available | Not Available | Not Available | -3.14 | Unknown | -1.18 | 0 | 363.72 | -4.32 | 368.04
| 2024-01-03 | N/A | OCEANSIDE | N/A | Not Available | 138 | 100 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -5.23 | Unknown | -1.99 | 0 | 154.79 | -7.22 | 162.01
| 2024-01-24 | Underserved Community | DANA POINT | N/A | Not Available | 132 | 94 | N/A | 2023-04-03 | Not Available | Not Available | Not Available | -5.23 | Unknown | -1.97 | 0 | 67.06 | -7.2 | 74.26
| 2025-02-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 379 | 271 | N/A | 2024-03-26 | Not Available | Not Available | Not Available | -6.56 | Unknown | -1.49 | 0 | 499.96 | -8.05 | 508.01
| 2024-11-08 | Underserved Community | SAN YSIDRO | N/A | Not Available | 154 | 110 | N/A | 2023-06-14 | Not Available | Not Available | Not Available | -8.4 | Unknown | 6.87 | 0 | 95.13 | -1.53 | 96.66
| 2026-10-01 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 37 | 27 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.08 | 0 | 105.08 | 10.08 | 95
| 2023-11-22 | Underserved Community | LAKESIDE | N/A | Not Available | 412 | 294 | N/A | 2024-03-07 | Not Available | Not Available | Not Available | -5.12 | Unknown | -1.2 | 0 | 341 | -6.32 | 347.32
| 2026-01-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 339 | 243 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.41 | 0 | 139.8 | 2.41 | 137.39
| 2024-01-12 | N/A | CARDIFF | N/A | Not Available | 159 | 115 | N/A | 2023-05-09 | Not Available | Not Available | Not Available | -6.27 | Unknown | -2.37 | 0 | 363.72 | -8.64 | 372.36
| 2027-03-14 | N/A | SAN CLEMENTE | N/A | Not Available | 18 | 12 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.1 | 0 | 57.62 | 6.1 | 51.52
| 2024-05-19 | N/A | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2023-11-14 | Not Available | Not Available | Not Available | -5.31 | Unknown | -1.69 | 0 | 202.37 | -7 | 209.37
| 2024-05-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2023-09-22 | Not Available | Not Available | Not Available | -4.09 | Unknown | 4.25 | 0 | 858.83 | 0.16 | 858.67
| 2025-01-25 | N/A | CARLSBAD | N/A | Not Available | 161 | 115 | N/A | 2023-07-07 | Not Available | Not Available | Not Available | -2.82 | Unknown | -1.07 | 0 | 27354.97 | -3.89 | 27358.86
| 2025-01-20 | N/A | ENCINITAS | N/A | Not Available | 155 | 111 | N/A | 2023-06-02 | Not Available | Not Available | Not Available | -8.64 | Unknown | -3.29 | 0 | 364.52 | -11.93 | 376.45
| 2025-03-06 | N/A | LAGUNA HILLS | N/A | Not Available | 14 | 10 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | 62 | Unknown | 47.03 | 0 | 74.16 | 109.03 | -34.87
| 2024-10-04 | Underserved Community | VALLEY CENTER | N/A | Not Available | 486 | 347 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -8.08 | Unknown | -1.85 | 0 | 436.48 | -9.93 | 446.41
| 2025-09-21 | Underserved Community | VISTA | N/A | Not Available | 92 | 66 | N/A | 2024-04-09 | Not Available | Not Available | Not Available | -6.34 | Unknown | -1.47 | 0 | 158.79 | -7.81 | 166.6
| 2024-03-04 | N/A | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2023-08-10 | Not Available | Not Available | Not Available | -6.86 | Unknown | -1.09 | 0 | 153.75 | -7.95 | 161.7
| 2026-07-29 | N/A | SAN CLEMENTE | N/A | Not Available | 43 | 31 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | 310.07 | Unknown | 221.51 | 0 | 74.22 | 531.58 | -457.36
| 2024-08-09 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 93 | 67 | N/A | 2024-02-01 | Not Available | Not Available | Not Available | 113.13 | Unknown | 84.85 | 0 | 158.79 | 197.98 | -39.19
| 2026-05-06 | N/A | SAN DIEGO | N/A | Not Available | 7 | 5 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | -7.78 | Unknown | 384.41 | 0 | 118.25 | 376.63 | -258.38
| 2025-01-10 | Underserved Community | VISTA | N/A | Not Available | 57 | 41 | N/A | 2023-07-12 | Not Available | Not Available | Not Available | -3.4 | Unknown | -1.31 | 0 | 495.75 | -4.71 | 500.46
| 2026-08-27 | N/A | DANA POINT | N/A | Not Available | 98 | 70 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | 344.96 | Unknown | 248.19 | 0 | 197.01 | 593.15 | -396.14
| 2027-04-14 | N/A | LAGUNA HILLS | N/A | Not Available | 17 | 13 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.38 | 0 | 57.62 | 4.38 | 53.24
| 2026-06-14 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 52 | 38 | N/A | 2024-07-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.71 | 0 | 1050.61 | 7.71 | 1042.9
| 2026-03-12 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.33 | 0 | 999.88 | 6.33 | 993.55
| 2025-07-25 | Underserved Community | CHULA VISTA | N/A | Not Available | 61 | 43 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | 122.45 | Unknown | 88.99 | 0 | 152.86 | 211.44 | -58.58
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 89 | 64 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | 358.5 | Unknown | 187.64 | 0 | 196.59 | 546.14 | -349.55
| 2026-08-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-01-31 | Not Available | Not Available | Not Available | -14.11 | Unknown | 709.13 | 0 | 798.34 | 695.02 | 103.32
| 2025-02-04 | Underserved Community | ESCONDIDO | N/A | Not Available | 42 | 30 | N/A | 2023-11-07 | Not Available | Not Available | Not Available | -10.92 | Unknown | -0.84 | 0 | 158.14 | -11.76 | 169.9
| 2026-05-08 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A |  | Not Available | Not Available | Not Available | 232.61 | Unknown | 164.05 | 0 | 529.2 | 396.66 | 132.54
| 2025-12-20 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A |  | Not Available | Not Available | Not Available | 544.82 | Unknown | 329.05 | 0 | 190.13 | 873.87 | -683.74
| 2025-03-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 82 | 58 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | -3.92 | Unknown | -1.48 | 0 | 465.44 | -5.4 | 470.84
| 2025-05-04 | Underserved Community | CHULA VISTA | N/A | Not Available | 105 | 75 | N/A | 2023-11-06 | Not Available | Not Available | Not Available | 551.03 | Unknown | 331.15 | 0 | 153.83 | 882.18 | -728.35
| 2026-03-07 | Underserved Community | OCEANSIDE | N/A | Not Available | 178 | 128 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.92 | 0 | 207.92 | 12.92 | 195
| 2025-05-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 156 | 112 | N/A | 2024-05-02 | Not Available | Not Available | Not Available | 568.62 | Unknown | 305.61 | 0 | 515.81 | 874.23 | -358.42
| 2025-12-20 | Underserved Community | CHULA VISTA | N/A | Not Available | 145 | 103 | N/A |  | Not Available | Not Available | Not Available | 303.12 | Unknown | 208.03 | 0 | 534.57 | 511.15 | 23.42
| 2025-11-15 | Underserved Community | VALLEY CENTER | N/A | Not Available | 86 | 62 | N/A | 2024-04-18 | Not Available | Not Available | Not Available | -8.41 | Unknown | -0.32 | 0 | 153.26 | -8.73 | 161.99
| 2026-12-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2025-01-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.87 | 0 | 190.44 | 6.87 | 183.57
| 2025-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 110 | 78 | N/A | 2024-02-28 | Not Available | Not Available | Not Available | -4.26 | Unknown | 2.65 | 0 | 687.8 | -1.61 | 689.41
| 2026-11-08 | Underserved Community | OCEANSIDE | N/A | Not Available | 20 | 14 | N/A | 2024-12-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.47 | 3981 | 197.01 | 7.47 | 189.54
| 2025-04-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 164 | 118 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | -5.5 | Unknown | -0.29 | 0 | 40.04 | -5.79 | 45.83
| 2025-07-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 258 | 184 | N/A |  | Not Available | Not Available | Not Available | 335.98 | Unknown | 186.81 | 0 | 152.86 | 522.79 | -369.93
| 2025-05-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 196 | 140 | N/A |  | Not Available | Not Available | Not Available | 364.33 | Unknown | 256.81 | 0 | 152.86 | 621.14 | -468.28
| 2025-02-28 | Underserved Community | CHULA VISTA | N/A | Not Available | 79 | 57 | N/A | 2023-07-24 | Not Available | Not Available | Not Available | -11.44 | Unknown | -11.51 | 0 | 495.75 | -22.95 | 518.7
| 2027-02-28 | Underserved Community | CARLSBAD | N/A | Not Available | 38 | 28 | N/A | 2025-05-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.59 | 1.76 | 194.83
| 2024-01-20 | N/A | SAN DIEGO | N/A | Not Available | 166 | 118 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | -5.12 | Unknown | -1.97 | 0 | 98.41 | -7.09 | 105.5
| 2025-05-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 147 | 105 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -12.88 | Unknown | 1.98 | 0 | 158.51 | -10.9 | 169.41
| 2024-10-21 | N/A | CARDIFF | N/A | Not Available | 147 | 105 | N/A | 2024-01-09 | Not Available | Not Available | Not Available | -8.43 | Unknown | -1.95 | 0 | 496.37 | -10.38 | 506.75
| 2026-04-16 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 22 | 16 | N/A |  | Not Available | Not Available | Not Available | 358.01 | Unknown | 239.74 | 0 | 787.09 | 597.75 | 189.34
| 2025-03-07 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 69 | N/A | 2023-08-30 | Not Available | Not Available | Not Available | -10.96 | Unknown | -0.37 | 0 | 131.25 | -11.33 | 142.58
| 2025-02-13 | N/A | OCEANSIDE | N/A | Not Available | 95 | 69 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | -4.62 | Unknown | -1.75 | 0 | 144.8 | -6.37 | 151.17
| 2026-12-02 | N/A | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | -34.85 | Unknown | -17.28 | 0 | 197.01 | -52.13 | 249.14
| 2024-10-02 | N/A | POWAY | N/A | Not Available | 125 | 89 | N/A | 2024-04-26 | Not Available | Not Available | Not Available | -17.19 | Unknown | -3.98 | 0 | 153.26 | -21.17 | 174.43
| 2025-09-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 427 | 305 | N/A |  | Not Available | Not Available | Not Available | 192.82 | Unknown | 563.83 | 0 | 478.21 | 756.65 | -278.44
| 2026-06-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A |  | Not Available | Not Available | Not Available | 317.18 | Unknown | 186.1 | 0 | 192.95 | 503.28 | -310.33
| 2027-04-09 | Underserved Community | LAGUNA HILLS | N/A | Not Available | 20 | 14 | N/A | 2025-06-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 118.25 | 4.39 | 113.86
| 2026-12-13 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-02-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.94 | 0 | 196.69 | 7.94 | 188.75
| 2024-05-08 | Underserved Community | EL CAJON | N/A | Not Available | 219 | 157 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | -8.38 | Unknown | -0.75 | 0 | 154.99 | -9.13 | 164.12
| 2027-02-10 | N/A | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | -10.84 | Unknown | -4.12 | 0 | 196.44 | -14.96 | 211.4
| 2026-10-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2024-12-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.04 | 0 | 197.01 | 9.04 | 187.97
| 2026-08-28 | Underserved Community | ESCONDIDO | N/A | Not Available | 39 | 29 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.13 | 0 | 197.01 | 6.13 | 190.88
| 2026-03-13 | N/A | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2024-06-11 | Not Available | Not Available | Not Available | -11.53 | Unknown | -1.19 | 3981 | 192.83 | -12.72 | 205.55
| 2026-10-28 | N/A | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.59 | 3981 | 196.69 | 5.59 | 191.1
| 2025-05-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 164 | 118 | N/A | 2023-09-18 | Not Available | Not Available | Not Available | -6.67 | Unknown | -2.53 | 3981 | 465.36 | -9.2 | 474.56
| 2027-03-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A | 2025-04-11 | Not Available | Not Available | Not Available | -4.5 | Unknown | 222.66 | 3981 | 1063.08 | 218.16 | 844.92
| 2026-04-19 | N/A | SAN DIEGO | N/A | Not Available | 171 | 123 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.87 | 3981 | 985.1 | 4.87 | 980.23
| 2025-12-30 | N/A | SAN DIEGO | N/A | Not Available | 96 | 68 | N/A | 2024-03-29 | Not Available | Not Available | Not Available | -3.92 | Unknown | -3.92 | 3981 | 501.14 | -7.84 | 508.98
| 2025-08-10 | N/A | SAN DIEGO | N/A | Not Available | 213 | 153 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | -7.17 | Unknown | -1.66 | 3981 | 158.14 | -8.83 | 166.97
| 2025-11-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 452 | 324 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.28 | 3981 | 501.14 | 5.28 | 495.86
| 2026-02-27 | N/A | LA JOLLA | N/A | Not Available | 84 | 60 | N/A | 2024-07-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.29 | 3981 | 192.51 | 5.29 | 187.22
| 2025-11-03 | N/A | LA JOLLA | N/A | Not Available | 127 | 91 | N/A | 2024-02-26 | Not Available | Not Available | Not Available | -13.41 | Unknown | -3.13 | 3981 | 501.14 | -16.54 | 517.68
| 2025-01-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 150 | 108 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.69 | 3981 | 129.76 | -6.12 | 135.88
| 2025-12-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 60 | 44 | N/A | 2023-03-27 | Not Available | Not Available | Not Available | -4.59 | Unknown | -1.74 | 3981 | 98.41 | -6.33 | 104.74
| 2024-02-24 | N/A | MISSION VIEJO | N/A | Not Available | 120 | 86 | N/A | 2023-04-24 | Not Available | Not Available | Not Available | -7.17 | Unknown | -2.71 | 3981 | 144.8 | -9.88 | 154.68
| 2024-02-06 | N/A | LADERA RANCH | N/A | Not Available | 161 | 115 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | -10.38 | Unknown | -3.96 | 3981 | 154.79 | -14.34 | 169.13
| 2025-03-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 69 | 49 | N/A | 2023-07-24 | Not Available | Not Available | Not Available | -3.4 | Unknown | -1.31 | 3981 | 464.78 | -4.71 | 469.49
| 2023-11-22 | N/A | LAGUNA HILLS | N/A | Not Available | 118 | 84 | N/A | 2023-05-01 | Not Available | Not Available | Not Available | -12.82 | Unknown | -4.84 | 3981 | 154.79 | -17.66 | 172.45
| 2024-10-07 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 179 | 127 | N/A | 2023-04-05 | Not Available | Not Available | Not Available | -4.25 | Unknown | 29.38 | 3981 | 415.76 | 25.13 | 390.63
| 2025-03-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 123 | 89 | N/A | 2023-06-06 | Not Available | Not Available | Not Available | -5.31 | Unknown | -2.04 | 3981 | 153.75 | -7.35 | 161.1
| 2026-01-06 | N/A | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.99 | 3981 | 197.01 | 8.99 | 188.02
| 2027-01-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 19 | 13 | N/A | 2025-01-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.08 | 3981 | 197.01 | 4.08 | 192.93
| 2024-08-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 187 | 133 | N/A | 2024-05-23 | Not Available | Not Available | Not Available | -10.33 | Unknown | -2.4 | 3981 | 158.79 | -12.73 | 171.52
| 2023-01-11 | Underserved Community | SPRING VALLEY | N/A | Not Available | 58 | 42 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | -4.27 | Unknown | -0.64 | 3981 | 98.41 | -4.91 | 103.32
| 2023-07-29 | Underserved Community | VALLEY CENTER | N/A | Not Available | 126 | 90 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -12.93 | Unknown | 1086.93 | 2000 | 545.67 | 1074 | -528.33
| 2026-08-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 30 | 22 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 30.84 | 3981 | 196.69 | 30.84 | 165.85
| 2026-10-07 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.85 | 3981 | 197.01 | 18.85 | 178.16
| 2026-05-19 | N/A | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.17 | 3981 | 192.51 | 8.17 | 184.34
| 2024-03-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 182 | 130 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | -5.33 | Unknown | 261.01 | 3981 | 999.91 | 255.68 | 744.23
| 2024-06-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 163 | 117 | N/A | 2023-11-21 | Not Available | Not Available | Not Available | -10.12 | Unknown | -3.38 | 3981 | 469.58 | -13.5 | 483.08
| 2025-12-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 224 | 160 | N/A | 2024-07-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.41 | 3981 | 501.14 | 5.41 | 495.73
| 2026-04-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 92 | 66 | N/A | 2024-08-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.38 | 3981 | 983.86 | 7.38 | 976.48
| 2026-04-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.33 | 3981 | 1050.75 | 8.33 | 1042.42
| 2026-01-09 | N/A | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-04-17 | Not Available | Not Available | Not Available | -5.5 | Unknown | 3.29 | 3981 | 118.78 | -2.21 | 120.99
| 2025-12-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 372 | 266 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.28 | 3981 | 163.83 | 4.28 | 159.55
| 2024-05-15 | N/A | SAN DIEGO | N/A | Not Available | 103 | 75 | N/A | 2023-08-07 | Not Available | Not Available | Not Available | -6.86 | Unknown | -1.41 | 3981 | 153.83 | -8.27 | 162.1
| 2024-09-01 | Underserved Community | PINE VALLEY | N/A | Not Available | 238 | 170 | N/A | 2024-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.31 | 3981 | 163.83 | 1.31 | 162.52
| 2026-05-23 | Underserved Community | LAKESIDE | N/A | Not Available | 77 | 55 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.51 | 3981 | 192.51 | 8.51 | 184
| 2026-05-23 | Underserved Community | EL CAJON | N/A | Not Available | 51 | 37 | N/A | 2024-08-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.19 | 3981 | 192.95 | 11.19 | 181.76
| 2024-02-01 | N/A | LAGUNA HILLS | N/A | Not Available | 179 | 127 | N/A | 2023-06-08 | Not Available | Not Available | Not Available | -3.76 | Unknown | -1.43 | 3981 | 154.79 | -5.19 | 159.98
| 2026-10-11 | N/A | LAGUNA NIGUEL | N/A | Not Available | 72 | 52 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.48 | 3981 | 197.01 | 2.48 | 194.53
| 2024-02-01 | N/A | COTO DE CAZA | N/A | Not Available | 127 | 91 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | -6.19 | Unknown | -2.33 | 3981 | 154.79 | -8.52 | 163.31
| 2026-10-07 | N/A | LAGUNA NIGUEL | N/A | Not Available | 18 | 14 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 16 | 3981 | 197.01 | 16 | 181.01
| 2024-02-21 | N/A | SAN CLEMENTE | N/A | Not Available | 120 | 86 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | -4.27 | Unknown | -1.63 | 3981 | 154.79 | -5.9 | 160.69
| 2025-06-20 | N/A | DANA POINT | N/A | Not Available | 42 | 30 | N/A | 2024-08-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.02 | 3981 | 192.95 | 10.02 | 182.93
| 2025-02-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A | 2023-02-28 | Not Available | Not Available | Not Available | -4.26 | Unknown | -1.62 | 3981 | 341 | -5.88 | 346.88
| 2026-01-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 54 | 40 | N/A | 2024-05-09 | Not Available | Not Available | Not Available | -4.09 | Unknown | -0.95 | 3981 | 501.14 | -5.04 | 506.18
| 2026-12-30 | N/A | POWAY | N/A | Not Available | 12 | 10 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.26 | 3981 | 196.69 | 10.26 | 186.43
| 2025-03-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 17 | 13 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | -5.12 | Unknown | -1.96 | 3981 | 464.78 | -7.08 | 471.86
| 2026-12-18 | N/A | SAN MARCOS | N/A | Not Available | 72 | 52 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | -12.2 | Unknown | -3.05 | 3981 | 196.69 | -15.25 | 211.94
| 2026-01-21 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.55 | 3981 | 196.44 | 8.55 | 187.89
| 2025-08-08 | Underserved Community | ESCONDIDO | N/A | Not Available | 54 | 38 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.66 | 3981 | 197.01 | 9.66 | 187.35
| 2025-01-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 231 | 165 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1.21 | 3981 | 464.78 | -4.95 | 469.73
| 2025-10-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2024-02-15 | Not Available | Not Available | Not Available | -4.43 | Unknown | -1.04 | 3981 | 483.59 | -5.47 | 489.06
| 2026-04-25 | N/A | ESCONDIDO | N/A | Not Available | 57 | 41 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.23 | 3981 | 205.56 | 13.23 | 192.33
| 2025-09-12 | N/A | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2025-01-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.06 | 3961 | 197.01 | 7.06 | 189.95
| 2026-01-02 | N/A | SAN DIEGO | N/A | Not Available | 188 | 134 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.5 | 3981 | 501.14 | 5.5 | 495.64
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 64 | 46 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.05 | 3981 | 192.95 | 7.05 | 185.9
| 2026-05-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-10-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.91 | 3981 | 985.1 | 2.91 | 982.19
| 2025-07-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 157 | 113 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | -4.26 | Unknown | -1.16 | 3981 | 496.75 | -5.42 | 502.17
| 2026-10-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.15 | 3981 | 1066.55 | 6.15 | 1060.4
| 2024-07-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 259 | 185 | N/A | 2024-03-01 | Not Available | Not Available | Not Available | -3.4 | Unknown | 0.21 | 3981 | 596.29 | -3.19 | 599.48
| 2027-02-26 | N/A | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 3981 | 196.44 | 1.76 | 194.68
| 2025-10-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2024-02-27 | Not Available | Not Available | Not Available | -3.74 | Unknown | -0.87 | 3981 | 501.14 | -4.61 | 505.75
| 2026-03-28 | Underserved Community | SAN MARCOS | N/A | Not Available | 128 | 92 | N/A | 2024-07-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.04 | 3981 | 192.83 | 9.04 | 183.79
| 2024-01-25 | N/A | LAGUNA NIGUEL | N/A | Not Available | 16 | 12 | N/A | 2023-03-06 | Not Available | Not Available | Not Available | -6.35 | Unknown | -2.41 | 3981 | 92.06 | -8.76 | 100.82
| 2024-01-18 | N/A | LAGUNA NIGUEL | N/A | Not Available | 127 | 91 | N/A | 2023-04-27 | Not Available | Not Available | Not Available | -5.23 | Unknown | -1.99 | 3981 | 154.79 | -7.22 | 162.01
| 2023-05-29 | N/A | SAN DIEGO | N/A | Not Available | 166 | 118 | N/A | 2023-08-08 | Not Available | Not Available | Not Available | -5.12 | Unknown | -0.96 | 3981 | 541.85 | -6.08 | 547.93
| 2024-01-16 | N/A | SAN CLEMENTE | N/A | Not Available | 157 | 113 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -4.59 | Unknown | -1.74 | 3981 | 98.41 | -6.33 | 104.74
| 2026-12-10 | N/A | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.85 | 3981 | 197.01 | 2.85 | 194.16
| 2026-02-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 70 | 50 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.19 | 3981 | 150.74 | 8.19 | 142.55
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 650 | 464 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.83 | 3981 | 281.93 | 4.83 | 277.1
| 2025-02-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A | 2023-06-05 | Not Available | Not Available | Not Available | -4.09 | Unknown | -1.54 | 3981 | 464.78 | -5.63 | 470.41
| 2024-03-01 | N/A | SAN DIEGO | N/A | Not Available | 76 | 54 | N/A | 2023-06-06 | Not Available | Not Available | Not Available | -5.29 | Unknown | -2.03 | 3981 | 464.78 | -7.32 | 472.1
| 2025-02-23 | Underserved Community | SAN MARCOS | N/A | Not Available | 78 | 56 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.18 | 3981 | 130.1 | 1.18 | 128.92
| 2024-03-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 90 | 64 | N/A | 2023-04-18 | Not Available | Not Available | Not Available | -3.94 | Unknown | -0.99 | 3981 | 452.24 | -4.93 | 457.17
| 2024-08-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 152 | 108 | N/A | 2024-03-28 | Not Available | Not Available | Not Available | -4.09 | Unknown | -0.95 | 3981 | 481.24 | -5.04 | 486.28
| 2026-04-30 | N/A | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.32 | 3981 | 192.51 | 7.32 | 185.19
| 2026-03-26 | N/A | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A | 2024-07-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.86 | 3981 | 162.34 | 5.86 | 156.48
| 2026-03-15 | N/A | SAN DIEGO | N/A | Not Available | 276 | 198 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.34 | 3981 | 983.86 | 7.34 | 976.52
| 2026-04-17 | N/A | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | -6.9 | Unknown | -1.09 | 3981 | 192.83 | -7.99 | 200.82
| 2025-12-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2024-03-25 | Not Available | Not Available | Not Available | -4.26 | Unknown | -0.99 | 3981 | 501.14 | -5.25 | 506.39
| 2020-12-31 | N/A | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2023-08-16 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1.41 | 3981 | 465.36 | -5.15 | 470.51
| 2026-03-04 | N/A | SAN DIEGO | N/A | Not Available | 74 | 54 | N/A | 2024-05-16 | Not Available | Not Available | Not Available | -3.92 | Unknown | -0.92 | 3981 | 501.18 | -4.84 | 506.02
| 2024-05-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 201 | 143 | N/A | 2023-11-28 | Not Available | Not Available | Not Available | -3.92 | Unknown | -0.61 | 3981 | 594.61 | -4.53 | 599.14
| 2024-05-19 | Underserved Community | LA MESA | N/A | Not Available | 109 | 79 | N/A | 2023-12-20 | Not Available | Not Available | Not Available | -4.43 | Unknown | -0.04 | 3981 | 617.39 | -4.47 | 621.86
| 2025-06-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 83 | 59 | N/A | 2023-09-27 | Not Available | Not Available | Not Available | -13.06 | Unknown | -4.73 | 3981 | 469.58 | -17.79 | 487.37
| 2025-11-16 | Underserved Community | VALLEY CENTER | N/A | Not Available | 106 | 76 | N/A | 2024-05-17 | Not Available | Not Available | Not Available | -13.9 | Unknown | -3.24 | 3981 | 501.18 | -17.14 | 518.32
| 2024-01-16 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 193 | 139 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | -4.45 | Unknown | -1.68 | 3981 | 98.41 | -6.13 | 104.54
| 2024-03-22 | N/A | SAN DIEGO | N/A | Not Available | 185 | 132 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -3.93 | Unknown | -0.32 | 3981 | 153.87 | -4.25 | 158.12
| 2027-01-31 | Underserved Community | LA MESA | N/A | Not Available | 23 | 17 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 28.25 | 3981 | 1064.43 | 28.25 | 1036.18
| 2026-06-03 | Underserved Community | CHULA VISTA | N/A | Not Available | 47 | 33 | N/A |  | Not Available | Not Available | Not Available | 253.74 | Unknown | 177.19 | 3981 | 192.95 | 430.93 | -237.98
| 2026-07-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 108 | 78 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.95 | 3981 | 197.01 | 9.95 | 187.06
| 2026-10-08 | N/A | SAN DIEGO | N/A | Not Available | 47 | 35 | N/A | 2024-11-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.54 | 3981 | 197.01 | 9.54 | 187.47
| 2025-03-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.84 | 3981 | 464.78 | -6.62 | 471.4
| 2025-03-20 | N/A | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2023-06-21 | Not Available | Not Available | Not Available | -8.64 | Unknown | -3.3 | 3981 | 464.78 | -11.94 | 476.72
| 2026-09-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.75 | 3981 | 196.69 | 1.75 | 194.94
| 2025-10-27 | N/A | SAN MARCOS | N/A | Not Available | 149 | 107 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | -12.86 | Unknown | -2.87 | 3981 | 1066.55 | -15.73 | 1082.28
| 2025-05-22 | Underserved Community | LA JOLLA | N/A | Not Available | 161 | 115 | N/A | 2023-09-25 | Not Available | Not Available | Not Available | -4.78 | Unknown | -1.77 | 3981 | 465.36 | -6.55 | 471.91
| 2026-10-31 | N/A | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.68 | 3981 | 1066.55 | 6.68 | 1059.87
| 2026-12-09 | N/A | CARLSBAD | N/A | Not Available | 69 | 49 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.27 | 3981 | 197.01 | 7.27 | 189.74
| 2025-02-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 256 | 184 | N/A | 2023-07-28 | Not Available | Not Available | Not Available | -5.62 | Unknown | -2.13 | 3981 | 465.36 | -7.75 | 473.11
| 2026-04-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2024-09-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 31.32 | 3981 | 984.98 | 31.32 | 953.66
| 2026-08-20 | N/A | SAN DIEGO | N/A | Not Available | 94 | 68 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.69 | 3981 | 197.01 | 2.69 | 194.32
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 73 | 53 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.43 | 3981 | 192.95 | 10.43 | 182.52
| 2024-07-07 | Underserved Community | LA MESA | N/A | Not Available | 118 | 84 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -5.31 | Unknown | -0.77 | 3981 | 153.83 | -6.08 | 159.91
| 2024-03-03 | Underserved Community | LA MESA | N/A | Not Available | 161 | 115 | N/A | 2023-07-31 | Not Available | Not Available | Not Available | -4.45 | Unknown | -0.52 | 3981 | 154.79 | -4.97 | 159.76
| 2025-12-27 | N/A | SAN DIEGO | N/A | Not Available | 365 | 261 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.34 | 3981 | 501.14 | 5.34 | 495.8
| 2024-08-24 | N/A | SAN DIEGO | N/A | Not Available | 217 | 155 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -4.61 | Unknown | -1.74 | 3981 | 468.73 | -6.35 | 475.08
| 2026-03-14 | Underserved Community | CHULA VISTA | N/A | Not Available | 43 | 31 | N/A |  | Not Available | Not Available | Not Available | 185.02 | Unknown | 127.01 | 3981 | 1086.86 | 312.03 | 774.83
| 2026-11-08 | Underserved Community | ESCONDIDO | N/A | Not Available | 35 | 25 | N/A | 2024-12-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.52 | 3981 | 197.01 | 3.52 | 193.49
| 2026-12-31 | N/A | SAN DIEGO | N/A | Not Available | 16 | 12 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.68 | 3981 | 196.69 | 10.68 | 186.01
| 2026-09-26 | N/A | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.75 | 3981 | 197.01 | 5.75 | 191.26
| 2025-07-25 | Underserved Community | FALLBROOK | N/A | Not Available | 107 | 77 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -3.76 | Unknown | 0.77 | 3981 | 163.83 | -2.99 | 166.82
| 2026-01-01 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | -18.79 | Unknown | -10.19 | 3981 | 196.44 | -28.98 | 225.42
| 2026-03-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2024-07-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.66 | 3941 | 186.09 | 8.66 | 177.43
| 2026-12-02 | N/A | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 135.49 | 3981 | 196.69 | 135.49 | 61.2
| 2025-10-13 | N/A | SAN DIEGO | N/A | Not Available | 270 | 194 | N/A |  | Not Available | Not Available | Not Available | 179.54 | Unknown | 126.17 | 0 | 163.83 | 322 | -158.17
| 2026-11-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 23 | 17 | N/A |  | Not Available | Not Available | Not Available | 125.68 | Unknown | 92.69 | 0 | 184.29 | 307.69 | -123.4
| 2024-10-12 | N/A | LAGUNA HILLS | N/A | Not Available | 25 | 17 | N/A | 2023-11-06 | Not Available | Not Available | Not Available | 4377.75 | Unknown | 2396.91 | 0 | 148.28 | 7473.37 | -7325.09
| 2023-08-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 145 | 105 | N/A | 2023-09-26 | Not Available | Not Available | Not Available | -10.73 | Unknown | -2.9 | 3981 | 594.61 | -13.63 | 608.24
| 2026-07-10 | Underserved Community | JULIAN | N/A | Not Available | 205 | 147 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | 254.7 | Unknown | 182.55 | 0 | 180.5 | 562.38 | -381.88
| 2025-09-06 | N/A | DEL MAR | N/A | Not Available | 28 | 20 | N/A | 2023-10-03 | Not Available | Not Available | Not Available | 367.35 | Unknown | 227.79 | 0 | 154.99 | 688.23 | -533.24
| 2025-07-26 | Underserved Community | RAMONA | N/A | Not Available | 122 | 87 | N/A |  | Not Available | Not Available | Not Available | 1275.22 | Unknown | 746.89 | 0 | 547.46 | 2351.6 | -1804.14
| 2024-04-18 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | 79 | 57 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | 243.74 | Unknown | 117.73 | 0 | 479.76 | 392.75 | 87.01
| 2027-04-13 | Underserved Community | FALLBROOK | N/A | Not Available | 35 | 25 | N/A |  | Not Available | Not Available | Not Available | 192.42 | Unknown | 112.08 | 0 | 118.25 | 422.59 | -304.34
| 2024-12-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2023-03-02 | Not Available | Not Available | Not Available | -6.71 | Unknown | -2.55 | 3981 | 363.72 | -9.26 | 372.98
| 2023-11-17 | N/A | SAN CLEMENTE | N/A | Not Available | 176 | 126 | N/A | 2023-04-18 | Not Available | Not Available | Not Available | -12.85 | Unknown | -4.88 | 3981 | 98.41 | -17.73 | 116.14
| 2024-11-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 183 | 131 | N/A | 2023-03-07 | Not Available | Not Available | Not Available | -10.39 | Unknown | -3.96 | 3981 | 341 | -14.35 | 355.35
| 2023-10-14 | N/A | ESCONDIDO | N/A | Not Available | 26 | 18 | N/A | 2022-02-09 | Not Available | Not Available | Not Available | -15.72 | Unknown | -5.98 | 3981 | 129.76 | -21.7 | 151.46
| 2026-01-29 | N/A | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | -32.97 | Unknown | -17.92 | 3981 | 196.69 | -50.89 | 247.58
| 2026-09-30 | N/A | CARLSBAD | N/A | Not Available | 57 | 41 | N/A | 2024-12-10 | Not Available | Not Available | Not Available | 251.36 | Unknown | 179.23 | 0 | 288.94 | 473.64 | -184.7
| 2023-10-24 | N/A | LAGUNA NIGUEL | N/A | Not Available | 30 | 22 | N/A |  | Not Available | Not Available | Not Available | -11.36 | Unknown | -4.32 | 3981 | 98.41 | -15.68 | 114.09
| 2025-01-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 7 | 5 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | 430.86 | Unknown | 272.46 | 0 | 154.79 | 851.02 | -696.23
| 2023-12-19 | N/A | SAN CLEMENTE | N/A | Not Available | 67 | 47 | N/A | 2023-06-26 | Not Available | Not Available | Not Available | 236.04 | Unknown | 151.11 | 0 | 495.75 | 476.51 | 19.24
| 2024-03-11 | N/A | MISSION VIEJO | N/A | Not Available | 14 | 10 | N/A | 2023-06-05 | Not Available | Not Available | Not Available | 421.38 | Unknown | 276.97 | 0 | 143.83 | 879.94 | -736.11
| 2025-04-15 | N/A | CARDIFF | N/A | Not Available | 15 | 11 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | 493.36 | Unknown | 339.92 | 0 | 100.49 | 839.64 | -739.15
| 2024-03-16 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 25 | 19 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | 602.36 | Unknown | 365.05 | 0 | 153.75 | 1084.56 | -930.81
| 2024-11-29 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2023-05-01 | Not Available | Not Available | Not Available | 775.76 | Unknown | 1221.86 | 0 | 1100.51 | 2085.47 | -984.96
| 2025-01-31 | Underserved Community | VISTA | N/A | Not Available | 2 | 2 | N/A | 2023-02-01 | Not Available | Not Available | Not Available | 354.06 | Unknown | 246.42 | 0 | 363.72 | 724.92 | -361.2
| 2023-09-13 | Underserved Community | OCEANSIDE | N/A | Not Available | 1 | 1 | N/A | 2023-03-23 | Not Available | Not Available | Not Available | 343.06 | Unknown | 219.59 | 0 | 363.72 | 682.55 | -318.83
| 2024-02-23 | N/A | OCEANSIDE | N/A | Not Available | 65 | 47 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | 384.36 | Unknown | 243.33 | 0 | 153.75 | 815.46 | -661.71
| 2024-02-04 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 56 | 40 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | 280.92 | Unknown | 178.49 | 3981 | 154.79 | 548.77 | -393.98
| 2024-01-18 | N/A | CAPISTRANO BEACH | N/A | Not Available | 96 | 68 | N/A |  | Not Available | Not Available | Not Available | 26227.76 | Unknown | 36832.31 | 0 | 625.02 | 64835.19 | -64210.17
| 2023-11-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 85 | 61 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | 475.52 | Unknown | 310.33 | 0 | 363.72 | 986.77 | -623.05
| 2023-05-31 | N/A | LAGUNA NIGUEL | N/A | Not Available | 140 | 100 | N/A | 2023-07-05 | Not Available | Not Available | Not Available | 419.12 | Unknown | 264.79 | 3981 | 98.41 | 769.23 | -670.82
| 2026-04-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -4.11 | Unknown | -0.67 | 3981 | 984.98 | -4.78 | 989.76
| 2025-06-21 | N/A | SAN DIEGO | N/A | Not Available | 157 | 113 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | -5.58 | Unknown | -1.8 | 3981 | 469.58 | -7.38 | 476.96
| 2024-04-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 136 | 98 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | 404.44 | Unknown | 186.19 | 0 | 496.37 | 634.01 | -137.64
| 2024-08-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 109 | 79 | N/A | 2024-02-29 | Not Available | Not Available | Not Available | -14.65 | Unknown | -0.01 | 3981 | 621.39 | -14.66 | 636.05
| 2025-12-07 | N/A | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -11.68 | Unknown | 0.44 | 3981 | 163.83 | -11.24 | 175.07
| 2025-10-23 | N/A | SAN DIEGO | N/A | Not Available | 138 | 98 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | 362.52 | Unknown | 264.29 | 0 | 163.83 | 666.63 | -502.8
| 2027-01-30 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | 584.32 | Unknown | 1723.63 | 0 | 1064.43 | 2391.76 | -1327.33
| 2024-07-07 | N/A | LAGUNA HILLS | N/A | Not Available | 246 | 176 | N/A | 2024-02-27 | Not Available | Not Available | Not Available | 289.98 | Unknown | 186.44 | 0 | 158.79 | 529.59 | -370.8
| 2024-07-16 | Underserved Community | EL CAJON | N/A | Not Available | 292 | 208 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | 611.82 | Unknown | 307.14 | 0 | 1116.87 | 1272.72 | -155.85
| 2026-11-20 | N/A | OCEANSIDE | N/A | Not Available | 64 | 46 | N/A | 2024-11-27 | Not Available | Not Available | Not Available | 366.82 | Unknown | 259.81 | 3981 | 197.01 | 668.66 | -471.65
| 2023-06-02 | N/A | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | 44.74 | Unknown | 55.16 | Unknwn | Unknown | 99.9 | Unknown
| 2024-08-02 | N/A | ALPINE | N/A | Not Available | 204 | 146 | N/A | 2023-12-08 | Not Available | Not Available | Not Available | -19.08 | Unknown | -3.61 | 3981 | 154.99 | -22.69 | 177.68
| 2024-10-27 | N/A | SAN CLEMENTE | N/A | Not Available | 92 | 66 | N/A | 2024-01-11 | Not Available | Not Available | Not Available | 413.26 | Unknown | 267.81 | 0 | 158.79 | 948.99 | -790.2
| 2025-02-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 353 | 253 | N/A | 2023-04-06 | Not Available | Not Available | Not Available | -5.4 | Unknown | -2.05 | 3981 | 130.1 | -7.45 | 137.55
| 2024-03-16 | N/A | LAGUNA NIGUEL | N/A | Not Available | 125 | 89 | N/A | 2023-08-24 | Not Available | Not Available | Not Available | 1549.98 | Unknown | 1043.5 | 0 | 110.98 | 3287.8 | -3176.82
| 2025-04-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2023-05-25 | Not Available | Not Available | Not Available | -4.74 | Unknown | -1.8 | 3981 | 464.78 | -6.54 | 471.32
| 2024-01-21 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 120 | 86 | N/A | 2023-04-03 | Not Available | Not Available | Not Available | -6.69 | Unknown | -2.53 | 3981 | 98.66 | -9.22 | 107.88
| 2024-02-02 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 153 | 109 | N/A | 2023-04-21 | Not Available | Not Available | Not Available | -7.9 | Unknown | -3.02 | 3981 | 154.79 | -10.92 | 165.71
| 2023-12-14 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 174 | 124 | N/A | 2023-07-10 | Not Available | Not Available | Not Available | -9.87 | Unknown | -3.75 | 3981 | 154.79 | -13.62 | 168.41
| 2025-02-28 | N/A | SAN DIEGO | N/A | Not Available | 68 | 50 | N/A | 2023-05-08 | Not Available | Not Available | Not Available | -10.02 | Unknown | -3.81 | 3981 | 464.78 | -13.83 | 478.61
| 2026-06-28 | N/A | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -6 | Unknown | -0.97 | 3981 | 983.86 | -6.97 | 990.83
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 174 | 124 | N/A | 2023-09-19 | Not Available | Not Available | Not Available | 151.99 | Unknown | 126.85 | 3981 | 281.93 | 278.84 | 3.09
| 2025-07-27 | N/A | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2024-01-17 | Not Available | Not Available | Not Available | -5.97 | Unknown | -0.2 | 3981 | 158.79 | -6.17 | 164.96
| 2024-03-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A | 2023-05-11 | Not Available | Not Available | Not Available | -7.63 | Unknown | -2.91 | 3981 | 464.78 | -10.54 | 475.32
| 2025-02-12 | N/A | VALLEY CENTER | N/A | Not Available | 70 | 50 | N/A | 2023-07-18 | Not Available | Not Available | Not Available | -18.59 | Unknown | 234.81 | 3981 | 142.48 | 216.22 | -73.74
| 2023-12-26 | Underserved Community | SPRING VALLEY | N/A | Not Available | 127 | 91 | N/A | 2023-05-08 | Not Available | Not Available | Not Available | -8.29 | Unknown | -2.16 | 3981 | 98.41 | -10.45 | 108.86
| 2025-01-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 22 | 16 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | 1229.03 | Unknown | 764.88 | 0 | 153.75 | 2373.7 | -2219.95
| 2024-11-21 | Underserved Community | ESCONDIDO | N/A | Not Available | 59 | 43 | N/A |  | Not Available | Not Available | Not Available | 472.08 | Unknown | 299.64 | 3981 | 129.76 | 947.92 | -818.16
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 100 | 72 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 325.02 | 0 | 192.95 | 939.59 | -746.64
| 2026-02-09 | N/A | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -4.79 | Unknown | 56.35 | 3981 | 163.83 | 861.74 | -697.91
| 2025-08-30 | Underserved Community | VISTA | N/A | Not Available | 104 | 74 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | 341.61 | Unknown | 237.01 | 0 | 163.83 | 594.38 | -430.55
| 2026-08-28 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | 251.36 | Unknown | 180.46 | 0 | 197.01 | 543.32 | -346.31
| 2025-05-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 18 | 14 | N/A |  | Not Available | Not Available | Not Available | 582.92 | Unknown | 419.71 | 0 | 192.83 | 1167.2 | -974.37
| 2025-03-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2023-09-27 | Not Available | Not Available | Not Available | 53.29 | Unknown | 1135.38 | 0 | 496.37 | 1218.15 | -721.78
| 2025-10-24 | N/A | SANTEE | N/A | Not Available | 11 | 9 | N/A |  | Not Available | Not Available | Not Available | 350.92 | Unknown | 247.98 | 0 | 158.79 | 607.9 | -449.11
| 2026-09-11 | Underserved Community | CHULA VISTA | N/A | Not Available | 194 | 140 | N/A |  | Not Available | Not Available | Not Available | 343.65 | Unknown | 174.07 | 3981 | 190.44 | 517.72 | -327.28
| 2025-06-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 66 | 48 | N/A | 2024-01-24 | Not Available | Not Available | Not Available | 437.19 | Unknown | 320.61 | 0 | 481.75 | 820.11 | -338.36
| 2024-03-29 | N/A | ENCINITAS | N/A | Not Available | 49 | 35 | N/A | 2023-08-22 | Not Available | Not Available | Not Available | 495.69 | Unknown | 321.18 | 0 | 496.37 | 938.61 | -442.24
| 2024-01-09 | Underserved Community | OCEANSIDE | N/A | Not Available | 246 | 176 | N/A | 2024-12-23 | Not Available | Not Available | Not Available | 559.23 | Unknown | 593.67 | 0 | 162.34 | 1259.6 | -1097.26
| 2025-08-20 | N/A | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | 229.93 | Unknown | 112.51 | 0 | 158.79 | 430.88 | -272.09
| 2025-07-11 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 67 | N/A | 2023-11-10 | Not Available | Not Available | Not Available | -4.51 | Unknown | 45.11 | 7962 | 502.87 | 40.6 | 462.27
| 2024-03-22 | N/A | SAN DIEGO | N/A | Not Available | 187 | 133 | N/A | 2023-09-26 | Not Available | Not Available | Not Available | 711.84 | Unknown | 447.08 | 0 | 153.83 | 1321.24 | -1167.41
| 2025-07-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2023-12-15 | Not Available | Not Available | Not Available | 509.52 | Unknown | 319.64 | 0 | 158.79 | 1169.8 | -1011.01
| 2027-04-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | -8.86 | Unknown | 438.46 | 3981 | 450.11 | 429.6 | 20.51
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | 251.36 | Unknown | 180.46 | 0 | 197.01 | 543.32 | -346.31
| 2025-10-13 | N/A | SAN DIEGO | N/A | Not Available | 270 | 194 | N/A |  | Not Available | Not Available | Not Available | 118.54 | Unknown | 83.83 | 0 | 163.83 | 213.22 | -49.39
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | 303.12 | Unknown | 218.66 | 0 | 184.29 | 653.62 | -469.33
| 2025-06-19 | N/A | SAN DIEGO | N/A | Not Available | 277 | 197 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | 398.66 | Unknown | 180.2 | 3981 | 469.58 | 578.86 | -109.28
| 2027-02-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 53 | 39 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | -16.96 | Unknown | -9.21 | 3981 | 996.66 | -26.17 | 1022.83
| 2027-04-09 | Underserved Community | OCEANSIDE | N/A | Not Available | 50 | 36 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | 533.76 | Unknown | 352.27 | 3981 | 118.25 | 886.03 | -767.78
| 2026-02-22 | N/A | ESCONDIDO | N/A | Not Available | 88 | 62 | N/A | 2024-05-24 | Not Available | Not Available | Not Available | -7.5 | Unknown | -1.73 | 3981 | 162.34 | -9.23 | 171.57
| 2024-01-04 | N/A | MISSION VIEJO | N/A | Not Available | 33 | 23 | N/A | 2023-03-29 | Not Available | Not Available | Not Available | -10.79 | Unknown | -4.11 | 3981 | 98.41 | -14.9 | 113.31
| 2024-02-02 | N/A | LAGUNA HILLS | N/A | Not Available | 174 | 124 | N/A | 2023-05-19 | Not Available | Not Available | Not Available | -9.95 | Unknown | -3.77 | 3981 | 154.79 | -13.72 | 168.51
| 2023-11-21 | N/A | SAN CLEMENTE | N/A | Not Available | 169 | 121 | N/A | 2023-05-01 | Not Available | Not Available | Not Available | -18.98 | Unknown | -10.36 | 3981 | 98.41 | -29.34 | 127.75
| 2024-02-10 | N/A | COTO DE CAZA | N/A | Not Available | 344 | 246 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -13.45 | Unknown | -5.11 | 3885 | 154.79 | -18.56 | 173.35
| 2025-05-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 231 | 165 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | 1238.93 | Unknown | 624.35 | 3981 | 465.36 | 1863.28 | -1397.92
| 2024-11-09 | N/A | LAGUNA NIGUEL | N/A | Not Available | 93 | 67 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -9.14 | Unknown | -2.64 | 3981 | 158.79 | -11.78 | 170.57
| 2026-11-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | 251.36 | Unknown | 179.76 | 0 | 184.29 | 493.65 | -309.36
| 2027-03-10 | Underserved Community | FALLBROOK | N/A | Not Available | 31 | 23 | N/A |  | Not Available | Not Available | Not Available | 303.12 | Unknown | 229.05 | 0 | 1063.64 | 846.72 | 216.92
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 180.46 | 0 | 197.01 | 543.32 | -346.31
| 2027-02-10 | Underserved Community | OCEANSIDE | N/A | Not Available | 21 | 15 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | 382.05 | Unknown | 301.08 | 0 | 278.5 | 925.56 | -647.06
| 2025-10-25 | N/A | RANCHO SANTA FE | N/A | Not Available | 14 | 10 | N/A | 2024-03-29 | Not Available | Not Available | Not Available | 1056.72 | Unknown | 739.9 | 0 | 202.87 | 1882.38 | -1679.51
| 2026-01-24 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2024-06-14 | Not Available | Not Available | Not Available | -5.1 | Unknown | 0.65 | 3981 | 192.83 | -4.45 | 197.28
| 2025-06-22 | N/A | RAMONA | N/A | Not Available | 37 | 27 | N/A | 2023-11-01 | Not Available | Not Available | Not Available | 627.7 | Unknown | 421.93 | 0 | 158.51 | 1536.43 | -1377.92
| 2024-05-09 | N/A | CARLSBAD | N/A | Not Available | 27 | 19 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | 515.24 | Unknown | 334.1 | 0 | 196.1 | 1019.66 | -823.56
| 2026-08-22 | N/A | DEL MAR | N/A | Not Available | 15 | 11 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | 502.72 | Unknown | 351.58 | 0 | 288.94 | 869.84 | -580.9
| 2026-08-08 | N/A | ENCINITAS | N/A | Not Available | 23 | 17 | N/A | 2024-10-03 | Not Available | Not Available | Not Available | 303.12 | Unknown | 550.06 | 0 | 631.94 | 877.75 | -245.81
| 2026-03-01 | N/A | ENCINITAS | N/A | Not Available | 125 | 89 | N/A | 2024-08-07 | Not Available | Not Available | Not Available | 434.02 | Unknown | 334.39 | 0 | 163.83 | 794.05 | -630.22
| 2024-04-27 | N/A | SAN CLEMENTE | N/A | Not Available | 13 | 9 | N/A | 2023-07-21 | Not Available | Not Available | Not Available | 402.28 | Unknown | 261 | 0 | 496.45 | 822.04 | -325.59
| 2024-11-23 | N/A | ENCINITAS | N/A | Not Available | 32 | 22 | N/A | 2023-06-09 | Not Available | Not Available | Not Available | 484.72 | Unknown | 309.93 | 0 | 153.75 | 955.93 | -802.18
| 2024-04-04 | N/A | COTO DE CAZA | N/A | Not Available | 17 | 13 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | 236.04 | Unknown | 151.14 | 0 | 110.98 | 476.54 | -365.56
| 2026-01-29 | N/A | CARLSBAD | N/A | Not Available | 49 | 35 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | 1342.37 | Unknown | 576.16 | 0 | 142.6 | 2077.3 | -1934.7
| 2025-07-18 | Underserved Community | OCEANSIDE | N/A | Not Available | 7 | 5 | N/A | 2024-07-22 | Not Available | Not Available | Not Available | 273.28 | Unknown | 189.94 | 0 | 1049.43 | 476.52 | 572.91
| 2025-03-15 | Underserved Community | JULIAN | N/A | Not Available | 35 | 25 | N/A |  | Not Available | Not Available | Not Available | 421.38 | Unknown | 265.98 | 0 | 98.41 | 819.51 | -721.1
| 2027-02-26 | Underserved Community | OCEANSIDE | N/A | Not Available | 9 | 7 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | 1130.91 | Unknown | 754.89 | 0 | 196.44 | 1936.76 | -1740.32
| 2025-01-04 | Underserved Community | OCEANSIDE | N/A | Not Available | 72 | 52 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | 244.24 | Unknown | 193.7 | 0 | 144.8 | 1163.04 | -1018.24
| 2024-03-06 | N/A | SAN DIEGO | N/A | Not Available | 61 | 43 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -11.12 | Unknown | -3.06 | 3981 | 154.79 | -14.18 | 168.97
| 2026-03-05 | N/A | ENCINITAS | N/A | Not Available | 19 | 15 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | 513.24 | Unknown | 359.29 | 0 | 162.34 | 883.43 | -721.09
| 2023-12-20 | Underserved Community | LA MESA | N/A | Not Available | 127 | 91 | N/A | 2023-04-18 | Not Available | Not Available | Not Available | -8.39 | Unknown | -1.97 | 3981 | 98.41 | -10.36 | 108.77
| 2025-09-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 158 | 112 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -7.78 | Unknown | -2.07 | 3981 | 483.59 | -9.85 | 493.44
| 2024-10-31 | N/A | SAN DIEGO | N/A | Not Available | 159 | 113 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -27.35 | Unknown | 723.02 | 3981 | 501.14 | 695.67 | -194.53
| 2026-05-09 | Underserved Community | ESCONDIDO | N/A | Not Available | 104 | 74 | N/A | 2024-08-09 | Not Available | Not Available | Not Available | 359.73 | Unknown | 227.08 | 0 | 192.83 | 710.02 | -517.19
| 2026-07-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 64 | 46 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | 780.48 | Unknown | 541.63 | 0 | 192.95 | 1420.37 | -1227.42
| 2024-07-07 | N/A | LAGUNA HILLS | N/A | Not Available | 205 | 147 | N/A | 2023-11-02 | Not Available | Not Available | Not Available | 241.04 | Unknown | 166.48 | 0 | 158.14 | 525.44 | -367.3
| 2026-10-31 | N/A | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A |  | Not Available | Not Available | Not Available | 392.75 | Unknown | 248.72 | 0 | 197.01 | 723.71 | -526.7
| 2026-11-13 | Underserved Community | SANTA YSABEL | N/A | Not Available | 168 | 120 | N/A |  | Not Available | Not Available | Not Available | 737.88 | Unknown | 520.75 | 0 | 999.91 | 1516.49 | -516.58
| 2026-07-09 | N/A | ENCINITAS | N/A | Not Available | 36 | 26 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | 1178.76 | Unknown | 902.84 | 3981 | 1050.75 | 2458.36 | -1407.61
| 2025-09-25 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2023-12-21 | Not Available | Not Available | Not Available | -27.72 | Unknown | -8.95 | 3981 | 483.59 | -36.67 | 520.26
| 2025-05-01 | Underserved Community | ESCONDIDO | N/A | Not Available | 160 | 114 | N/A | 2023-09-26 | Not Available | Not Available | Not Available | 291.46 | Unknown | 197.9 | 0 | 154.99 | 791 | -636.01
| 2026-09-26 | N/A | ENCINITAS | N/A | Not Available | 156 | 112 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | 1054.16 | Unknown | 747.2 | 3981 | 197.01 | 2036.51 | -1839.5
| 2026-09-13 | Underserved Community | OCEANSIDE | N/A | Not Available | 56 | 40 | N/A | 2024-10-28 | Not Available | Not Available | Not Available | 382.05 | Unknown | 272.74 | 0 | 197.01 | 717.47 | -520.46
| 2025-12-21 | N/A | CARLSBAD | N/A | Not Available | 110 | 78 | N/A | 2024-03-25 | Not Available | Not Available | Not Available | 396.27 | Unknown | 272.93 | 0 | 163.83 | 673.97 | -510.14
| 2026-03-01 | N/A | BONITA | N/A | Not Available | 300 | 214 | N/A |  | Not Available | Not Available | Not Available | 467.58 | Unknown | 246.64 | 3941 | 186.4 | 714.22 | -527.82
| 2027-02-21 | Underserved Community | ESCONDIDO | N/A | Not Available | 49 | 35 | N/A |  | Not Available | Not Available | Not Available | 606.24 | Unknown | 450.97 | 0 | 196.59 | 1309.75 | -1113.16
| 2024-01-03 | N/A | LAGUNA NIGUEL | N/A | Not Available | 22 | 16 | N/A | 2023-03-22 | Not Available | Not Available | Not Available | -10.64 | Unknown | -4.05 | 3981 | 98.41 | -14.69 | 113.1
| 2025-07-05 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -8.35 | Unknown | -1.69 | 3981 | 153.83 | -10.04 | 163.87
| 2025-04-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 1 | 1 | N/A | 2023-08-15 | Not Available | Not Available | Not Available | -9.7 | Unknown | -3.7 | 3981 | 465.36 | -13.4 | 478.76
| 2025-06-12 | N/A | SAN DIEGO | N/A | Not Available | 221 | 159 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | -7.8 | Unknown | -1.8 | 3981 | 465.36 | -9.6 | 474.96
| 2025-04-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 27 | 19 | N/A | 2023-06-28 | Not Available | Not Available | Not Available | -7.5 | Unknown | -2.86 | 3981 | 153.75 | -10.36 | 164.11
| 2025-02-14 | Underserved Community | ESCONDIDO | N/A | Not Available | 187 | 133 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | -10.57 | Unknown | -2.82 | 3981 | 130.1 | -13.39 | 143.49
| 2024-01-26 | Underserved Community | DANA POINT | N/A | Not Available | 171 | 123 | N/A | 2023-05-25 | Not Available | Not Available | Not Available | -5.83 | Unknown | -2.22 | 3981 | 98.66 | -8.05 | 106.71
| 2026-01-31 | N/A | SAN DIEGO | N/A | Not Available | 104 | 74 | N/A | 2024-05-17 | Not Available | Not Available | Not Available | -7.1 | Unknown | -1.65 | 3981 | 501.14 | -8.75 | 509.89
| 2024-02-01 | N/A | MISSION VIEJO | N/A | Not Available | 327 | 233 | N/A | 2023-06-07 | Not Available | Not Available | Not Available | -4.1 | Unknown | -1.55 | 3981 | 154.79 | -5.65 | 160.44
| 2024-03-16 | Underserved Community | SPRING VALLEY | N/A | Not Available | 59 | 43 | N/A | 2023-06-23 | Not Available | Not Available | Not Available | -23.79 | Unknown | 751.19 | 3981 | 143.83 | 727.4 | -583.57
| 2024-06-13 | Underserved Community | SPRING VALLEY | N/A | Not Available | 46 | 34 | N/A | 2023-07-14 | Not Available | Not Available | Not Available | -3.57 | Unknown | -1.36 | 3981 | 523.37 | -4.93 | 528.3
| 2025-04-05 | N/A | SAN DIEGO | N/A | Not Available | 156 | 112 | N/A | 2023-08-09 | Not Available | Not Available | Not Available | -6.5 | Unknown | -2.45 | 3981 | 465.44 | -8.95 | 474.39
| 2026-08-20 | N/A | SAN MARCOS | N/A | Not Available | 86 | 62 | N/A |  | Not Available | Not Available | Not Available | 5816.58 | Unknown | 4075.13 | 0 | 197.01 | 11001.5 | -10804.49
| 2027-03-03 | Underserved Community | ESCONDIDO | N/A | Not Available | 41 | 29 | N/A |  | Not Available | Not Available | Not Available | 374 | Unknown | 663.3 | 0 | 1063.08 | 1122.43 | -59.35
| 2026-07-12 | N/A | CARLSBAD | N/A | Not Available | 232 | 166 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | 502.72 | Unknown | 352.07 | 0 | 192.95 | 922.54 | -729.59
| 2025-07-19 | N/A | ENCINITAS | N/A | Not Available | 101 | 73 | N/A | 2024-02-16 | Not Available | Not Available | Not Available | 612.39 | Unknown | 437.23 | 0 | 163.83 | 1162.68 | -998.85
| 2024-04-05 | N/A | RAMONA | N/A | Not Available | 98 | 70 | N/A |  | Not Available | Not Available | Not Available | 1034.8 | Unknown | 563.87 | 3981 | 205.44 | 1598.67 | -1393.23
| 2023-10-31 | Underserved Community | EL CAJON | N/A | Not Available | 137 | 99 | N/A | 2023-11-17 | Not Available | Not Available | Not Available | -24.82 | Unknown | 575.6 | 3981 | 582.57 | 550.78 | 31.79
| 2026-07-18 | Underserved Community | VISTA | N/A | Not Available | 204 | 146 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | 2809.56 | Unknown | 1306.5 | 0 | 192.95 | 4629.31 | -4436.36
| 2024-04-17 | Underserved Community | VISTA | N/A | Not Available | 175 | 125 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | 393.77 | Unknown | 372.96 | 0 | 153.83 | 888.47 | -734.64
| 2025-12-04 | Underserved Community | VISTA | N/A | Not Available | 165 | 117 | N/A | 2024-04-19 | Not Available | Not Available | Not Available | 603.72 | Unknown | 425.55 | 0 | 163.83 | 1144.61 | -980.78
| 2025-04-26 | N/A | LA JOLLA | N/A | Not Available | 315 | 225 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | 370.8 | Unknown | 207.51 | 0 | 496.37 | 632.54 | -136.17
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | 129.47 | Unknown | 89.75 | 0 | 196.44 | 234.51 | -38.07
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 397.41 | Unknown | 166.53 | 0 | 196.44 | 586.87 | -390.43
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 397.41 | Unknown | 166.53 | 0 | 196.44 | 586.87 | -390.43
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 264.94 | Unknown | 111 | 0 | 196.44 | 391.23 | -194.79
| 2025-10-14 | Underserved Community | FALLBROOK | N/A | Not Available | 15 | 11 | N/A |  | Not Available | Not Available | Not Available | 630.6 | Unknown | 443.46 | 0 | 1066.51 | 1208.33 | -141.82
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.14 | 0 | 196.44 | 350.57 | -154.13
| 2024-12-20 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 54 | 38 | N/A | 2024-01-30 | Not Available | Not Available | Not Available | 378.69 | Unknown | 280.91 | 0 | 148.54 | 720.86 | -572.32
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | 194.21 | Unknown | 134.61 | 0 | 196.44 | 351.75 | -155.31
| 2025-11-28 | N/A | LA JOLLA | N/A | Not Available | 111 | 80 | N/A | 2024-02-28 | Not Available | Not Available | Not Available | -7.33 | Unknown | -1.7 | 3981 | 501.14 | -9.03 | 510.17
| 2024-07-20 | Underserved Community | JACUMBA | N/A | Not Available | 61 | 43 | N/A |  | Not Available | Not Available | Not Available | 252.46 | Unknown | 97.86 | Unknwn | Unknown | 369.21 | Unknown
| 2025-10-09 | Underserved Community | FALLBROOK | N/A | Not Available | 121 | 87 | N/A | 2024-03-11 | Not Available | Not Available | Not Available | 582.92 | Unknown | 413.96 | 0 | 641.46 | 1189.06 | -547.6
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | 237.62 | Unknown | 122.76 | 0 | 196.44 | 383.31 | -186.87
| 2024-01-24 | Underserved Community | LAKESIDE | N/A | Not Available | 810 | 580 | N/A | 2025-06-10 | Not Available | Not Available | Not Available | 314.48 | Unknown | 129.11 | 0 | 496.45 | 561.51 | -65.06
| 2024-11-16 | N/A | SAN CLEMENTE | N/A | Not Available | 60 | 42 | N/A | 2024-01-30 | Not Available | Not Available | Not Available | 638.58 | Unknown | 449.24 | 0 | 148.54 | 1149.08 | -1000.54
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 132.47 | Unknown | 91.76 | 0 | 196.44 | 239.52 | -43.08
| 2026-03-02 | N/A | CORONADO | N/A | Not Available | 106 | 76 | N/A | 2024-05-23 | Not Available | Not Available | Not Available | -8.03 | Unknown | -1.84 | 3981 | 162.34 | -9.87 | 172.21
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 1190.82 | Unknown | 914.94 | 0 | 196.44 | 2143.98 | -1947.54
| 2024-02-14 | N/A | LAGUNA NIGUEL | N/A | Not Available | 132 | 94 | N/A | 2023-06-19 | Not Available | Not Available | Not Available | 358.71 | Unknown | 233.96 | 3981 | 153.75 | 767.09 | -613.34
| 2024-01-30 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 129 | 93 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | -5.87 | Unknown | 3.86 | 3981 | 154.79 | -2.01 | 156.8
| 2025-02-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2023-05-08 | Not Available | Not Available | Not Available | -20.27 | Unknown | -7.71 | 3981 | 468.73 | -27.98 | 496.71
| 2024-02-04 | N/A | MISSION VIEJO | N/A | Not Available | 161 | 115 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | -18.09 | Unknown | -8.46 | 3981 | 154.79 | -26.55 | 181.34
| 2024-10-12 | N/A | DEL MAR | N/A | Not Available | 171 | 123 | N/A | 2023-07-24 | Not Available | Not Available | Not Available | 862.2 | Unknown | 540.09 | 0 | 98.41 | 1640.17 | -1541.76
| 2025-02-16 | N/A | MISSION VIEJO | N/A | Not Available | 67 | 49 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | 360.2 | Unknown | 271.33 | 0 | 192.83 | 815.81 | -622.98
| 2025-02-01 | Underserved Community | ESCONDIDO | N/A | Not Available | 43 | 31 | N/A |  | Not Available | Not Available | Not Available | -9.81 | Unknown | 0.52 | 3981 | 153.87 | -9.29 | 163.16
| 2025-05-31 | N/A | SAN DIEGO | N/A | Not Available | 205 | 147 | N/A | 2023-10-05 | Not Available | Not Available | Not Available | 254.76 | Unknown | 163.15 | 0 | 465.36 | 461.29 | 4.07
| 2025-05-08 | Underserved Community | ESCONDIDO | N/A | Not Available | 278 | 200 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | -13.59 | Unknown | -1.97 | 3981 | 320.64 | -15.56 | 336.2
| 2025-09-20 | Underserved Community | RAMONA | N/A | Not Available | 35 | 25 | N/A | 2023-12-26 | Not Available | Not Available | Not Available | 1057.35 | Unknown | 760.41 | 0 | 483.59 | 2317.48 | -1833.89
| 2024-03-13 | N/A | SANTEE | N/A | Not Available | 172 | 124 | N/A | 2023-08-03 | Not Available | Not Available | Not Available | -26.48 | Unknown | 501.09 | 3981 | 540.82 | 474.61 | 66.21
| 2025-07-13 | N/A | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2024-01-11 | Not Available | Not Available | Not Available | -7.75 | Unknown | -2.08 | 3981 | 483.59 | -9.83 | 493.42
| 2024-01-06 | Underserved Community | LA MESA | N/A | Not Available | 111 | 79 | N/A | 2023-05-02 | Not Available | Not Available | Not Available | -7.26 | Unknown | -2.75 | 3885 | 98.41 | -10.01 | 108.42
| 2024-01-04 | N/A | LAS FLORES | N/A | Not Available | 396 | 282 | N/A | 2024-02-28 | Not Available | Not Available | Not Available | -16.84 | Unknown | -4.24 | 3981 | 98.41 | -21.08 | 119.49
| 2024-03-17 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 135 | 97 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -41.06 | Unknown | 998.08 | 3981 | 464.78 | 957.02 | -492.24
| 2024-02-07 | N/A | DANA POINT | N/A | Not Available | 56 | 40 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | 236.04 | Unknown | 143.13 | 3981 | 144.8 | 379.17 | -234.37
| 2025-12-01 | N/A | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2024-02-29 | Not Available | Not Available | Not Available | 560.98 | Unknown | 701.36 | 3981 | 501.14 | 1262.34 | -761.2
| 2026-08-09 | N/A | SAN DIEGO | N/A | Not Available | 46 | 32 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | 377.04 | Unknown | 272.2 | 0 | 192.95 | 802.83 | -609.88
| 2026-07-23 | N/A | SAN DIEGO | N/A | Not Available | 95 | 67 | N/A |  | Not Available | Not Available | Not Available | 400.32 | Unknown | 293.11 | 0 | 197.01 | 875.15 | -678.14
| 2026-11-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 26 | 18 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | 251.36 | Unknown | 185.25 | 0 | 184.29 | 615.21 | -430.92
| 2025-05-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 141 | 101 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | 264.18 | Unknown | 176.01 | 3981 | 465.36 | 558.11 | -92.75
| 2024-05-18 | N/A | SAN DIEGO | N/A | Not Available | 266 | 190 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | 378.69 | Unknown | 273.67 | 0 | 202.87 | 765.52 | -562.65
| 2025-01-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A |  | Not Available | Not Available | Not Available | 606.24 | Unknown | 430.45 | 0 | 192.95 | 1214.28 | -1021.33
| 2026-11-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | 251.36 | Unknown | 180.46 | 0 | 197.01 | 543.32 | -346.31
| 2024-10-24 | N/A | SAN DIEGO | N/A | Not Available | 162 | 116 | N/A | 2024-03-07 | Not Available | Not Available | Not Available | 138.96 | Unknown | 103.23 | 0 | 153.26 | 290.22 | -136.96
| 2024-08-10 | N/A | SAN DIEGO | N/A | Not Available | 83 | 59 | N/A | 2023-10-11 | Not Available | Not Available | Not Available | 244.9 | Unknown | 173.15 | 0 | 497.98 | 653.89 | -155.91
| 2024-09-21 | N/A | SAN CLEMENTE | N/A | Not Available | 343 | 245 | N/A | 2025-01-27 | Not Available | Not Available | Not Available | 507.58 | Unknown | 382.7 | 0 | 180.38 | 1053.58 | -873.2
| 2026-09-23 | N/A | VALLEY CENTER | N/A | Not Available | 97 | 69 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | 502.72 | Unknown | 350.34 | 0 | 1066.55 | 981.97 | 84.58
| 2026-10-21 | N/A | LAKESIDE | N/A | Not Available | 43 | 31 | N/A |  | Not Available | Not Available | Not Available | 1103.55 | Unknown | 767.73 | 0 | 196.44 | 1960.34 | -1763.9
| 2025-12-20 | N/A | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-03-22 | Not Available | Not Available | Not Available | 487.96 | Unknown | 338.79 | 3981 | 501.14 | 841.02 | -339.88
| 2027-04-21 | Underserved Community | ESCONDIDO | N/A | Not Available | 15 | 11 | N/A |  | Not Available | Not Available | Not Available | 418.58 | Unknown | 322.13 | 0 | 118.25 | 1132.65 | -1014.4
| 2026-06-14 | N/A | VALLEY CENTER | N/A | Not Available | 128 | 92 | N/A | 2024-10-21 | Not Available | Not Available | Not Available | 303.12 | Unknown | 228.99 | 0 | 197.01 | 638.7 | -441.69
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 143 | 103 | N/A |  | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | 350.53 | -154.09
| 2026-05-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 210 | 150 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | 1508.16 | Unknown | 1078.19 | 0 | 192.83 | 3132.07 | -2939.24
| 2024-12-06 | N/A | SAN CLEMENTE | N/A | Not Available | 50 | 36 | N/A | 2024-03-19 | Not Available | Not Available | Not Available | 297.05 | Unknown | 210.31 | 0 | 163.83 | 561.37 | -397.54
| 2026-04-30 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A |  | Not Available | Not Available | Not Available | 291.46 | Unknown | 223.56 | 0 | 192.83 | 994.33 | -801.5
| 2025-09-11 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 104 | N/A | 2024-01-24 | Not Available | Not Available | Not Available | 278.73 | Unknown | 163.65 | 0 | 515.81 | 501.34 | 14.47
| 2025-05-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 155 | 111 | N/A | 2023-10-11 | Not Available | Not Available | Not Available | 579.65 | Unknown | 374.11 | 0 | 154.99 | 1425.44 | -1270.45
| 2026-11-26 | N/A | POWAY | N/A | Not Available | 15 | 11 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 175.23 | 0 | 196.69 | 486.36 | -289.67
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 167 | 119 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | 264.18 | Unknown | 176.06 | 0 | 143.91 | 558.16 | -414.25
| 2026-11-08 | Underserved Community | ESCONDIDO | N/A | Not Available | 28 | 20 | N/A |  | Not Available | Not Available | Not Available | 465.14 | Unknown | 332.02 | 3981 | 197.01 | 975.76 | -778.75
| 2026-01-16 | Underserved Community | VALLEY CENTER | N/A | Not Available | 64 | 46 | N/A |  | Not Available | Not Available | Not Available | 241.68 | Unknown | 177.42 | 0 | 192.51 | 489.41 | -296.9
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 397.41 | Unknown | 166.53 | 0 | 196.44 | 586.87 | -390.43
| 2026-06-11 | N/A | SAN DIEGO | N/A | Not Available | 100 | 71 | N/A | 2024-07-26 | Not Available | Not Available | Not Available | 162.73 | Unknown | 112.55 | 0 | 192.51 | 280.16 | -87.65
| 2025-04-29 | N/A | LAGUNA NIGUEL | N/A | Not Available | 15 | 11 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | 289.08 | Unknown | 213.67 | 0 | 162.34 | 672.54 | -510.2
| 2024-06-19 | Underserved Community | DANA POINT | N/A | Not Available | 113 | 81 | N/A | 2023-10-23 | Not Available | Not Available | Not Available | 626.04 | Unknown | 410.15 | 3981 | 143.91 | 1252.94 | -1109.03
| 2024-07-26 | N/A | SAN CLEMENTE | N/A | Not Available | 80 | 58 | N/A | 2023-09-25 | Not Available | Not Available | Not Available | 246.68 | Unknown | 163.71 | 3981 | 144.99 | 451.23 | -306.24
| 2025-01-11 | N/A | SAN CLEMENTE | N/A | Not Available | 49 | 35 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | 378.69 | Unknown | 267.85 | 0 | 153.26 | 646.6 | -493.34
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 132.47 | Unknown | 91.76 | 0 | 196.44 | 239.52 | -43.08
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | 521.31 | Unknown | 426.45 | 0 | 196.44 | 963.05 | -766.61
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | 257.08 | Unknown | 178.2 | 0 | 196.44 | 465.85 | -269.41
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 264.94 | Unknown | 111 | 0 | 196.44 | 391.23 | -194.79
| 2024-03-03 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 112 | 80 | N/A | 2023-05-25 | Not Available | Not Available | Not Available | 134.23 | Unknown | 86.95 | 3981 | 143.83 | 263.26 | -119.43
| 2024-01-18 | N/A | LAGUNA HILLS | N/A | Not Available | 168 | 120 | N/A | 2023-06-02 | Not Available | Not Available | Not Available | 195.14 | Unknown | 141.37 | 3981 | 154.79 | 536.84 | -382.05
| 2023-12-19 | N/A | SOLANA BEACH | N/A | Not Available | 138 | 100 | N/A | 2023-07-11 | Not Available | Not Available | Not Available | 924.06 | Unknown | 355.19 | 0 | 98.66 | 1386.62 | -1287.96
| 2026-08-13 | N/A | DEL MAR | N/A | Not Available | 20 | 14 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | 2239.45 | Unknown | 1304.63 | 0 | 799.9 | 3769.41 | -2969.51
| 2024-03-16 | N/A | OCEANSIDE | N/A | Not Available | 20 | 14 | N/A | 2023-07-28 | Not Available | Not Available | Not Available | 313.7 | Unknown | 190 | 0 | 153.87 | 584.86 | -430.99
| 2027-02-24 | Underserved Community | SAN MARCOS | N/A | Not Available | 54 | 38 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 333.46 | 0 | 196.59 | 1024.13 | -827.54
| 2026-10-28 | Underserved Community | VISTA | N/A | Not Available | 51 | 37 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | 729.92 | Unknown | 506.9 | 0 | 279.3 | 1330.54 | -1051.24
| 2026-05-30 | Underserved Community | VISTA | N/A | Not Available | 46 | 32 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | 253.4 | Unknown | 176.29 | 0 | 192.83 | 442.99 | -250.16
| 2025-01-24 | N/A | SAN CLEMENTE | N/A | Not Available | 16 | 12 | N/A | 2024-03-27 | Not Available | Not Available | Not Available | 279.15 | Unknown | 195.56 | 0 | 153.26 | 531.62 | -378.36
| 2026-07-01 | N/A | RANCHO SANTA FE | N/A | Not Available | 26 | 18 | N/A | 2024-08-09 | Not Available | Not Available | Not Available | 695.4 | Unknown | 492.71 | 0 | 283.53 | 1224.53 | -941
| 2025-01-31 | N/A | DANA POINT | N/A | Not Available | 18 | 14 | N/A | 2024-03-15 | Not Available | Not Available | Not Available | 378.98 | Unknown | 267.44 | 0 | 85.4 | 753.33 | -667.93
| 2025-06-26 | N/A | RAMONA | N/A | Not Available | 31 | 23 | N/A | 2023-09-13 | Not Available | Not Available | Not Available | 588.42 | Unknown | 272.73 | 0 | 40.04 | 1090.53 | -1050.49
| 2025-04-02 | N/A | DANA POINT | N/A | Not Available | 11 | 9 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | 378.9 | Unknown | 301.1 | 0 | 180.5 | 1067.23 | -886.73
| 2024-11-13 | N/A | SAN CLEMENTE | N/A | Not Available | 63 | 45 | N/A | 2023-01-05 | Not Available | Not Available | Not Available | 537.72 | Unknown | 395.27 | 0 | 515.81 | 1109.87 | -594.06
| 2025-10-09 | Underserved Community | SPRING VALLEY | N/A | Not Available | 71 | 51 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | 1703.16 | Unknown | 910.85 | 0 | 1032.11 | 5501.66 | -4469.55
| 2025-08-01 | Underserved Community | VISTA | N/A | Not Available | 185 | 133 | N/A | 2025-02-05 | Not Available | Not Available | Not Available | 285.38 | Unknown | 132.4 | 0 | 1443.38 | 437.51 | 1005.87
| 2025-03-26 | N/A | SANTEE | N/A | Not Available | 110 | 78 | N/A |  | Not Available | Not Available | Not Available | 879.23 | Unknown | 639.6 | 0 | 197.01 | 2007.35 | -1810.34
| 2024-01-24 | N/A | LAGUNA NIGUEL | N/A | Not Available | 44 | 32 | N/A | 2023-04-20 | Not Available | Not Available | Not Available | 601.69 | Unknown | 421.92 | 3981 | 98.41 | 1613.58 | -1515.17
| 2026-03-11 | N/A | SAN DIEGO | N/A | Not Available | 11 | 9 | N/A |  | Not Available | Not Available | Not Available | 502.72 | Unknown | 350.36 | 0 | 196.44 | 981.99 | -785.55
| 2025-02-01 | Underserved Community | RAMONA | N/A | Not Available | 51 | 37 | N/A | 2023-11-06 | Not Available | Not Available | Not Available | 244.9 | Unknown | 233.13 | 0 | 481.24 | 700.17 | -218.93
| 2024-10-24 | N/A | DEL MAR | N/A | Not Available | 36 | 26 | N/A | 2023-03-10 | Not Available | Not Available | Not Available | 514.59 | Unknown | 378.76 | 0 | 95.13 | 941.05 | -845.92
| 2024-02-21 | Underserved Community | VISTA | N/A | Not Available | 67 | 49 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | 465.88 | Unknown | 296.73 | 0 | 153.75 | 963.53 | -809.78
| 2024-02-23 | Underserved Community | BOULEVARD | N/A | Not Available | 126 | 90 | N/A |  | Not Available | Not Available | Not Available | 1008.4 | Unknown | 629.8 | 0 | 499.96 | 2109.88 | -1609.92
| 2024-03-06 | Underserved Community | DANA POINT | N/A | Not Available | 8 | 6 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | 480.94 | Unknown | 306.66 | 0 | 110.98 | 968.55 | -857.57
| 2025-02-09 | N/A | RAMONA | N/A | Not Available | 195 | 139 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | 510.02 | Unknown | 252.74 | 0 | 702.37 | 1082.16 | -379.79
| 2024-03-06 | N/A | SAN CLEMENTE | N/A | Not Available | 27 | 19 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | 997.47 | Unknown | 571.21 | 0 | 110.98 | 1850.31 | -1739.33
| 2024-02-23 | N/A | LAGUNA NIGUEL | N/A | Not Available | 196 | 140 | N/A | 2023-10-20 | Not Available | Not Available | Not Available | 653.9 | Unknown | 452.92 | 0 | 110.98 | 1311.02 | -1200.04
| 2026-02-22 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 13 | 9 | N/A |  | Not Available | Not Available | Not Available | 126.23 | Unknown | 98.77 | 0 | 158.37 | 243.3 | -84.93
| 2026-07-23 | N/A | MISSION VIEJO | N/A | Not Available | 36 | 26 | N/A | 2024-09-03 | Not Available | Not Available | Not Available | 1031.55 | Unknown | 1060.28 | 0 | 192.95 | 2698.94 | -2505.99
| 2027-01-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 98 | 70 | N/A |  | Not Available | Not Available | Not Available | 318.38 | Unknown | 224.49 | 0 | 196.69 | 639.26 | -442.57
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 65 | 47 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | 377.04 | Unknown | 272.14 | 3981 | 192.95 | 802.77 | -609.82
| 2025-07-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A | 2024-04-12 | Not Available | Not Available | Not Available | 223.18 | Unknown | 125.83 | 0 | 153.49 | 407.97 | -254.48
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 20 | 14 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 178.46 | 0 | 192.95 | 501.54 | -308.59
| 2026-01-13 | Underserved Community | VISTA | N/A | Not Available | 56 | 40 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | 502.72 | Unknown | 356.23 | 0 | 196.69 | 972.75 | -776.06
| 2024-05-09 | N/A | SAN CLEMENTE | N/A | Not Available | 57 | 41 | N/A | 2023-08-30 | Not Available | Not Available | Not Available | 247.86 | Unknown | 236.68 | 3981 | 143.91 | 1233.33 | -1089.42
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 20 | 14 | N/A |  | Not Available | Not Available | Not Available | 377.04 | Unknown | 235 | 0 | 192.95 | 701.66 | -508.71
| 2025-11-02 | N/A | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2024-03-07 | Not Available | Not Available | Not Available | 291.46 | Unknown | 207.03 | 0 | 463.92 | 594.57 | -130.65
| 2026-04-30 | N/A | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A |  | Not Available | Not Available | Not Available | 633.3 | Unknown | 462.56 | 0 | 192.83 | 1374.25 | -1181.42
| 2024-10-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2023-10-30 | Not Available | Not Available | Not Available | 309 | Unknown | 199.08 | 0 | 158.51 | 562.31 | -403.8
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A |  | Not Available | Not Available | Not Available | 303.12 | Unknown | 213.5 | 0 | 197.01 | 633.61 | -436.6
| 2025-10-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 155 | 111 | N/A |  | Not Available | Not Available | Not Available | 252.46 | Unknown | 175.78 | 0 | 534.53 | 464.84 | 69.69
| 2026-03-26 | Underserved Community | VALLEY CENTER | N/A | Not Available | 85 | 61 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | 1015.16 | Unknown | 554.33 | 0 | 233 | 1606.01 | -1373.01
| 2024-08-29 | N/A | LAGUNA NIGUEL | N/A | Not Available | 141 | 101 | N/A | 2023-10-12 | Not Available | Not Available | Not Available | 282.51 | Unknown | 182.72 | 0 | 158.51 | 583.15 | -424.64
| 2026-05-23 | Underserved Community | RAMONA | N/A | Not Available | 6 | 4 | N/A |  | Not Available | Not Available | Not Available | 384.84 | Unknown | 274.67 | 0 | 110.62 | 826.37 | -715.75
| 2025-10-31 | N/A | RANCHO LA COSTA | N/A | Not Available | 171 | 123 | N/A | 2024-05-17 | Not Available | Not Available | Not Available | 493.36 | Unknown | 340.34 | 0 | 162.34 | 846.79 | -684.45
| 2025-10-31 | N/A | CORONADO | N/A | Not Available | 147 | 105 | N/A |  | Not Available | Not Available | Not Available | 504.92 | Unknown | 354.85 | 0 | 158.37 | 932.97 | -774.6
| 2026-06-06 | Underserved Community | FALLBROOK | N/A | Not Available | 119 | 85 | N/A |  | Not Available | Not Available | Not Available | 930.28 | Unknown | 669.55 | 0 | 1086.86 | 1991.66 | -904.8
| 2024-10-10 | Underserved Community | DANA POINT | N/A | Not Available | 132 | 94 | N/A | 2024-02-21 | Not Available | Not Available | Not Available | 699.36 | Unknown | 523.16 | 0 | 158.79 | 1695.14 | -1536.35
| 2025-04-17 | N/A | RAMONA | N/A | Not Available | 103 | 73 | N/A |  | Not Available | Not Available | Not Available | 314.94 | Unknown | 201.64 | 0 | 143.95 | 752.08 | -608.13
| 2026-03-05 | Underserved Community | POWAY | N/A | Not Available | 31 | 23 | N/A | 2024-03-27 | Not Available | Not Available | Not Available | 454.77 | Unknown | 321.3 | 0 | 163.83 | 905.77 | -741.94
| 2025-04-13 | N/A | RAMONA | N/A | Not Available | 154 | 110 | N/A |  | Not Available | Not Available | Not Available | 241.05 | Unknown | 191.23 | 0 | 143.95 | 550.2 | -406.25
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 63 | 45 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 183.77 | 0 | 192.95 | 583.78 | -390.83
| 2025-04-18 | Underserved Community | SPRING VALLEY | N/A | Not Available | 13 | 9 | N/A |  | Not Available | Not Available | Not Available | 73.69 | Unknown | 53.4 | 0 | 529.2 | 162.7 | 366.5
| 2026-08-05 | N/A | CARLSBAD | N/A | Not Available | 38 | 28 | N/A | 2024-09-12 | Not Available | Not Available | Not Available | 1005.44 | Unknown | 703.21 | 0 | 192.95 | 1739.72 | -1546.77
| 2025-06-06 | N/A | CARLSBAD | N/A | Not Available | 150 | 108 | N/A | 2024-10-25 | Not Available | Not Available | Not Available | 857.1 | Unknown | 602.56 | 0 | 192.83 | 1553.18 | -1360.35
| 2023-08-01 | Underserved Community | VISTA | N/A | Not Available | 185 | 133 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | 312.08 | Unknown | 192.7 | 0 | 513.31 | 601.07 | -87.76
| 2026-10-08 | Underserved Community | ESCONDIDO | N/A | Not Available | 36 | 26 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 324.96 | 0 | 197.01 | 939.53 | -742.52
| 2025-10-05 | N/A | CARLSBAD | N/A | Not Available | 64 | 46 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | 639.39 | Unknown | 379.53 | 0 | 158.14 | 1190.8 | -1032.66
| 2026-07-18 | N/A | ENCINITAS | N/A | Not Available | 55 | 39 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | 502.72 | Unknown | 376.7 | 0 | 1050.75 | 1261.83 | -211.08
| 2024-04-07 | N/A | LAGUNA NIGUEL | N/A | Not Available | 82 | 58 | N/A | 2023-06-27 | Not Available | Not Available | Not Available | 421.38 | Unknown | 265.65 | 0 | 143.83 | 772.35 | -628.52
| 2024-11-23 | N/A | ENCINITAS | N/A | Not Available | 112 | 80 | N/A | 2023-10-11 | Not Available | Not Available | Not Available | 647.97 | Unknown | 384.04 | 0 | 153.83 | 1295.35 | -1141.52
| 2026-06-10 | N/A | SAN DIEGO | N/A | Not Available | 100 | 71 | N/A | 2024-07-31 | Not Available | Not Available | Not Available | 527.72 | Unknown | 365.27 | 0 | 192.95 | 896.44 | -703.49
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | 315.45 | Unknown | 154.6 | 0 | 196.44 | 492.98 | -296.54
| 2026-12-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 82 | 58 | N/A |  | Not Available | Not Available | Not Available | 627.87 | Unknown | 483.21 | 0 | 1063.64 | 1698.96 | -635.32
| 2024-10-20 | N/A | COTO DE CAZA | N/A | Not Available | 8 | 6 | N/A | 2023-10-26 | Not Available | Not Available | Not Available | 128.81 | Unknown | 86.33 | 0 | 158.51 | 287.39 | -128.88
| 2024-09-15 | N/A | LAGUNA NIGUEL | N/A | Not Available | 71 | 51 | N/A | 2023-10-19 | Not Available | Not Available | Not Available | 2104.74 | Unknown | 1561.73 | 0 | 148.28 | 5945.75 | -5797.47
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 46 | 33 | N/A |  | Not Available | Not Available | Not Available | 132.47 | Unknown | 91.76 | 0 | 196.44 | 239.52 | -43.08
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | 453.15 | Unknown | 243.15 | 0 | 196.44 | 734.52 | -538.08
| 2026-07-11 | Underserved Community | ESCONDIDO | N/A | Not Available | 44 | 32 | N/A |  | Not Available | Not Available | Not Available | 1621.68 | Unknown | 1166.62 | 0 | 1260.93 | 3538.47 | -2277.54
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.14 | 0 | 196.44 | 350.57 | -154.13
| 2027-03-04 | Underserved Community | PALOMAR MT | N/A | Not Available | 80 | 58 | N/A |  | Not Available | Not Available | Not Available | 2121.74 | Unknown | 1409.02 | 0 | 1276.4 | 3569.97 | -2293.57
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | 257.08 | Unknown | 178.2 | 0 | 196.44 | 465.85 | -269.41
| 2024-09-05 | N/A | SAN CLEMENTE | N/A | Not Available | 94 | 68 | N/A | 2024-01-09 | Not Available | Not Available | Not Available | 302.88 | Unknown | 172.49 | 0 | 158.79 | 516.21 | -357.42
| 2025-01-01 | N/A | CARDIFF | N/A | Not Available | 188 | 134 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | 502.72 | Unknown | 376.71 | 0 | 163.83 | 1261.84 | -1098.01
| 2023-08-31 | N/A | LAGUNA NIGUEL | N/A | Not Available | 43 | 31 | N/A | 2023-09-26 | Not Available | Not Available | Not Available | 712.42 | Unknown | 470.26 | 0 | 111.03 | 1422.65 | -1311.62
| 2026-08-22 | N/A | DEL MAR | N/A | Not Available | 17 | 13 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | 314.2 | Unknown | 219.72 | 0 | 288.94 | 543.64 | -254.7
| 2024-03-06 | Underserved Community | MISSION VIEJO | N/A | Not Available | 143 | 103 | N/A | 2023-06-29 | Not Available | Not Available | Not Available | 191.9 | Unknown | 126.67 | 0 | 110.98 | 410.26 | -299.28
| 2023-10-26 | N/A | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | 276.98 | Unknown | 178.49 | 0 | 98.41 | 544.83 | -446.42
| 2026-03-03 | Underserved Community | ESCONDIDO | N/A | Not Available | 30 | 22 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 323.87 | 0 | 196.44 | 969.15 | -772.71
| 2024-06-27 | N/A | SAN CLEMENTE | N/A | Not Available | 26 | 18 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | 658.95 | Unknown | 428.7 | 0 | 111.03 | 1260.92 | -1149.89
| 2025-10-26 | N/A | SAN DIEGO | N/A | Not Available | 18 | 14 | N/A | 2024-02-13 | Not Available | Not Available | Not Available | 291.46 | Unknown | 210.68 | 0 | 163.83 | 578.37 | -414.54
| 2025-03-11 | Underserved Community | OCEANSIDE | N/A | Not Available | 36 | 26 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | 253.07 | Unknown | 182.06 | 0 | 207.92 | 486.94 | -279.02
| 2026-09-27 | N/A | VISTA | N/A | Not Available | 29 | 21 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | 382.05 | Unknown | 271.12 | 0 | 197.01 | 715.85 | -518.84
| 2026-10-10 | N/A | DEL MAR | N/A | Not Available | 59 | 43 | N/A | 2024-12-06 | Not Available | Not Available | Not Available | 413.38 | Unknown | 292.66 | 0 | 279.3 | 749.09 | -469.79
| 2025-11-25 | N/A | SOLANA BEACH | N/A | Not Available | 18 | 14 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | 1212.48 | Unknown | 846.43 | 0 | 288.94 | 2111.89 | -1822.95
| 2026-10-08 | N/A | ENCINITAS | N/A | Not Available | 20 | 14 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | 509.4 | Unknown | 361.04 | 0 | 288.94 | 947.39 | -658.45
| 2026-12-18 | N/A | ENCINITAS | N/A | Not Available | 32 | 24 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | 502.72 | Unknown | 355.95 | 0 | 197.01 | 964.33 | -767.32
| 2026-01-19 | N/A | ENCINITAS | N/A | Not Available | 28 | 20 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | 489.8 | Unknown | 339.74 | 0 | 163.83 | 855.23 | -691.4
| 2025-01-30 | N/A | DANA POINT | N/A | Not Available | 3 | 3 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | 408.26 | Unknown | 313.96 | 0 | 117.79 | 911.5 | -793.71
| 2026-01-16 | N/A | DEL MAR | N/A | Not Available | 119 | 85 | N/A | 2024-08-08 | Not Available | Not Available | Not Available | 695.4 | Unknown | 492.67 | 0 | 162.34 | 1224.49 | -1062.15
| 2024-12-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A |  | Not Available | Not Available | Not Available | 480.57 | Unknown | 1110.53 | 0 | 495.75 | 1702.81 | -1207.06
| 2025-02-20 | N/A | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2023-07-03 | Not Available | Not Available | Not Available | 252.1 | Unknown | 162.09 | 0 | 153.75 | 503.55 | -349.8
| 2024-05-31 | N/A | CARLSBAD | N/A | Not Available | 69 | 49 | N/A | 2023-12-27 | Not Available | Not Available | Not Available | 282.54 | Unknown | 182.88 | 0 | 221.57 | 497.48 | -275.91
| 2025-06-05 | N/A | VALLEY CENTER | N/A | Not Available | 63 | 45 | N/A | 2023-10-18 | Not Available | Not Available | Not Available | 246.68 | Unknown | 164.94 | 0 | 465.36 | 529.54 | -64.18
| 2026-11-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A |  | Not Available | Not Available | Not Available | 216.15 | Unknown | 2095.46 | 0 | 799.93 | 2381.42 | -1581.49
| 2026-05-15 | Underserved Community | CHULA VISTA | N/A | Not Available | 55 | 39 | N/A |  | Not Available | Not Available | Not Available | 809.38 | Unknown | 489.03 | 0 | 1050.61 | 1345.72 | -295.11
| 2024-12-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 28 | 20 | N/A |  | Not Available | Not Available | Not Available | 421.38 | Unknown | 269.82 | 0 | 154.79 | 825.24 | -670.45
| 2024-01-19 | N/A | MISSION VIEJO | N/A | Not Available | 17 | 13 | N/A | 2023-06-16 | Not Available | Not Available | Not Available | 2084.68 | Unknown | 1054.37 | 0 | 110.98 | 5219.42 | -5108.44
| 2024-08-09 | N/A | SAN CLEMENTE | N/A | Not Available | 13 | 9 | N/A | 2024-03-01 | Not Available | Not Available | Not Available | 677.11 | Unknown | 499.74 | 0 | 117.79 | 1358.26 | -1240.47
| 2025-10-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A |  | Not Available | Not Available | Not Available | 372.6 | Unknown | 201.11 | 0 | 534.53 | 601.15 | -66.62
| 2025-01-11 | Underserved Community | ESCONDIDO | N/A | Not Available | 70 | 50 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | 239.31 | Unknown | 2233.05 | 0 | 153.75 | 2597.22 | -2443.47
| 2024-12-31 | Underserved Community | BONSALL | N/A | Not Available | 18 | 12 | N/A |  | Not Available | Not Available | Not Available | 266.88 | Unknown | 174.36 | 0 | 98.41 | 535.04 | -436.63
| 2024-03-31 | N/A | LAGUNA NIGUEL | N/A | Not Available | 138 | 98 | N/A | 2023-09-20 | Not Available | Not Available | Not Available | 493.36 | Unknown | 329.86 | 0 | 110.98 | 1059.06 | -948.08
| 2025-01-03 | N/A | ENCINITAS | N/A | Not Available | 47 | 33 | N/A | 2023-04-19 | Not Available | Not Available | Not Available | 344.78 | Unknown | 226.67 | 0 | 351.99 | 719.97 | -367.98
| 2025-02-08 | N/A | SAN DIEGO | N/A | Not Available | 150 | 108 | N/A |  | Not Available | Not Available | Not Available | 280.92 | Unknown | 185.1 | 0 | 149.62 | 583.94 | -434.32
| 2023-11-15 | Underserved Community | OCEANSIDE | N/A | Not Available | 395 | 283 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | 244.9 | Unknown | 173.62 | 0 | 144.8 | 451.61 | -306.81
| 2025-03-27 | N/A | RAMONA | N/A | Not Available | 57 | 41 | N/A |  | Not Available | Not Available | Not Available | 2079.04 | Unknown | 1023.07 | 0 | 153.75 | 3546.67 | -3392.92
| 2025-01-19 | Underserved Community | JULIAN | N/A | Not Available | 108 | 78 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | 362.52 | Unknown | 242.64 | 0 | 153.75 | 782.04 | -628.29
| 2025-03-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 162 | 116 | N/A |  | Not Available | Not Available | Not Available | 361.54 | Unknown | 196.94 | 0 | 154.99 | 586.05 | -431.06
| 2024-07-31 | N/A | SAN CLEMENTE | N/A | Not Available | 134 | 96 | N/A | 2023-09-20 | Not Available | Not Available | Not Available | 1134.44 | Unknown | 902.73 | 0 | 153.83 | 3444.49 | -3290.66
| 2024-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A |  | Not Available | Not Available | Not Available | 356.64 | Unknown | 259.04 | 0 | 520.23 | 749.72 | -229.49
| 2025-01-19 | Underserved Community | OCEANSIDE | N/A | Not Available | 93 | 67 | N/A | 2023-06-06 | Not Available | Not Available | Not Available | 110.99 | Unknown | 71.99 | 0 | 98.66 | 233.1 | -134.44
| 2024-03-06 | Underserved Community | VISTA | N/A | Not Available | 14 | 10 | N/A | 2023-03-14 | Not Available | Not Available | Not Available | 475.52 | Unknown | 307.24 | 0 | 363.72 | 922.72 | -559
| 2023-03-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 41 | 29 | N/A | 2023-05-25 | Not Available | Not Available | Not Available | 421.38 | Unknown | 267.71 | 0 | 464.78 | 823.13 | -358.35
| 2024-02-02 | N/A | MISSION VIEJO | N/A | Not Available | 70 | 50 | N/A | 2023-07-27 | Not Available | Not Available | Not Available | 329.26 | Unknown | 212.15 | 0 | 110.98 | 708.86 | -597.88
| 2026-06-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 53 | 37 | N/A |  | Not Available | Not Available | Not Available | 262.57 | Unknown | 187.14 | 0 | 192.51 | 585.7 | -393.19
| 2024-03-21 | N/A | SOUTH LAGUNA | N/A | Not Available | 193 | 139 | N/A | 2023-07-07 | Not Available | Not Available | Not Available | 114.09 | Unknown | 84.41 | 3981 | 153.87 | 252.98 | -99.11
| 2026-10-28 | N/A | VALLEY CENTER | N/A | Not Available | 142 | 102 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 175.19 | 0 | 197.01 | 491.01 | -294
| 2027-01-21 | N/A | RANCHO SANTA FE | N/A | Not Available | 6 | 4 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | 502.72 | Unknown | 353.06 | 0 | 196.69 | 961.44 | -764.75
| 2026-07-31 | N/A | LADERA RANCH | N/A | Not Available | 43 | 31 | N/A | 2024-08-30 | Not Available | Not Available | Not Available | 244.71 | Unknown | 190.03 | 0 | 192.95 | 655.31 | -462.36
| 2025-10-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 182 | 130 | N/A | 2024-03-20 | Not Available | Not Available | Not Available | 470.56 | Unknown | 213.93 | 0 | 534.53 | 724.05 | -189.52
| 2026-03-04 | N/A | SAN MARCOS | N/A | Not Available | 13 | 9 | N/A |  | Not Available | Not Available | Not Available | 377.04 | Unknown | 262.77 | 0 | 196.44 | 736.52 | -540.08
| 2026-02-28 | N/A | DEL MAR | N/A | Not Available | 53 | 37 | N/A | 2024-03-21 | Not Available | Not Available | Not Available | 1093.12 | Unknown | 755.72 | 0 | 163.83 | 1861.57 | -1697.74
| 2027-03-27 | Underserved Community | FALLBROOK | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | 256.56 | Unknown | 193.84 | 0 | 1063.64 | 686.6 | 377.04
| 2024-05-19 | N/A | DEL MAR | N/A | Not Available | 194 | 138 | N/A | 2023-11-16 | Not Available | Not Available | Not Available | 209.04 | Unknown | 138 | 0 | 158.14 | 402.13 | -243.99
| 2026-07-23 | Underserved Community | RAMONA | N/A | Not Available | 75 | 53 | N/A |  | Not Available | Not Available | Not Available | 502.72 | Unknown | 350.67 | 0 | 985.1 | 925.08 | 60.02
| 2026-03-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 112 | 80 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | 521.55 | Unknown | 362.2 | 0 | 163.83 | 907.92 | -744.09
| 2026-09-17 | N/A | ENCINITAS | N/A | Not Available | 26 | 20 | N/A | 2024-10-04 | Not Available | Not Available | Not Available | 314.2 | Unknown | 220.63 | 0 | 197.01 | 557.31 | -360.3
| 2026-09-11 | N/A | ENCINITAS | N/A | Not Available | 133 | 95 | N/A | 2025-01-22 | Not Available | Not Available | Not Available | 729.92 | Unknown | 509.37 | 0 | 1066.51 | 1354.52 | -288.01
| 2026-08-28 | N/A | SOLANA BEACH | N/A | Not Available | 184 | 132 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | 502.72 | Unknown | 353.89 | 0 | 197.01 | 950.36 | -753.35
| 2024-08-17 | N/A | MISSION VIEJO | N/A | Not Available | 155 | 111 | N/A | 2023-11-09 | Not Available | Not Available | Not Available | 168.4 | Unknown | 107.99 | 0 | 158.51 | 330.4 | -171.89
| 2026-02-15 | N/A | ENCINITAS | N/A | Not Available | 67 | 47 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | 347.7 | Unknown | 245.12 | 0 | 162.34 | 655.6 | -493.26
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 69 | 49 | N/A |  | Not Available | Not Available | Not Available | 502.72 | Unknown | 367.48 | 0 | 192.95 | 1167.49 | -974.54
| 2026-11-07 | Underserved Community | ESCONDIDO | N/A | Not Available | 21 | 15 | N/A |  | Not Available | Not Available | Not Available | 465.14 | Unknown | 332.04 | 0 | 999.88 | 975.78 | 24.1
| 2024-08-22 | N/A | MISSION VIEJO | N/A | Not Available | 60 | 44 | N/A | 2023-10-23 | Not Available | Not Available | Not Available | 1330.78 | Unknown | 889.62 | 0 | 158.51 | 2792.08 | -2633.57
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | 210.3 | Unknown | 103.02 | 0 | 196.44 | 328.61 | -132.17
| 2024-02-20 | N/A | SAN CLEMENTE | N/A | Not Available | 72 | 52 | N/A | 2024-03-19 | Not Available | Not Available | Not Available | 522.61 | Unknown | 403.1 | 0 | 163.83 | 1057.7 | -893.87
| 2026-10-14 | Underserved Community | FALLBROOK | N/A | Not Available | 40 | 28 | N/A |  | Not Available | Not Available | Not Available | 502.72 | Unknown | 364.95 | 0 | 1066.51 | 1121.81 | -55.3
| 2024-09-27 | N/A | SANTEE | N/A | Not Available | 99 | 71 | N/A |  | Not Available | Not Available | Not Available | 668.26 | Unknown | 519.75 | 0 | 158.14 | 1626.16 | -1468.02
| 2025-09-30 | N/A | DANA POINT | N/A | Not Available | 4 | 4 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | 401.99 | Unknown | 602.14 | 0 | 184.29 | 1290.93 | -1106.64
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.14 | 0 | 196.44 | 350.57 | -154.13
| 2024-07-27 | N/A | DANA POINT | N/A | Not Available | 115 | 83 | N/A | 2023-10-17 | Not Available | Not Available | Not Available | 771.77 | Unknown | 491.43 | 0 | 158.51 | 1318.83 | -1160.32
| 2024-12-20 | N/A | LAGUNA NIGUEL | N/A | Not Available | 40 | 28 | N/A | 2024-01-22 | Not Available | Not Available | Not Available | 434.72 | Unknown | 289.8 | 0 | 148.54 | 864.5 | -715.96
| 2024-07-12 | N/A | LAGUNA NIGUEL | N/A | Not Available | 103 | 73 | N/A | 2023-09-20 | Not Available | Not Available | Not Available | 465.74 | Unknown | 309.12 | 3981 | 143.91 | 973.99 | -830.08
| 2025-02-09 | N/A | SAN MARCOS | N/A | Not Available | 39 | 27 | N/A |  | Not Available | Not Available | Not Available | 351.15 | Unknown | 226.26 | 0 | 154.79 | 733.5 | -578.71
| 2025-04-20 | N/A | LA JOLLA | N/A | Not Available | 133 | 95 | N/A | 2023-11-16 | Not Available | Not Available | Not Available | 811.91 | Unknown | 506.14 | 0 | 372.35 | 1590.1 | -1217.75
| 2024-10-18 | N/A | LAGUNA NIGUEL | N/A | Not Available | 93 | 67 | N/A | 2024-12-13 | Not Available | Not Available | Not Available | 306.2 | Unknown | 218.01 | 0 | 105.08 | 540.51 | -435.43
| 2024-08-16 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 165 | 119 | N/A | 2023-10-10 | Not Available | Not Available | Not Available | 142.18 | Unknown | 100.11 | 0 | 111.81 | 343.58 | -231.77
| 2025-11-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 17 | 13 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | 959.02 | Unknown | 684.94 | 0 | 158.79 | 1674.71 | -1515.92
| 2024-03-01 | N/A | MISSION VIEJO | N/A | Not Available | 111 | 79 | N/A | 2023-05-26 | Not Available | Not Available | Not Available | 195.14 | Unknown | 127.84 | 3991 | 153.75 | 414.67 | -260.92
| 2027-01-15 | Underserved Community | JULIAN | N/A | Not Available | 3 | 3 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | 382.05 | Unknown | 202.71 | 0 | 999.91 | 658.22 | 341.69
| 2024-04-07 | N/A | SOUTH LAGUNA | N/A | Not Available | 124 | 88 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | 261.15 | Unknown | 200.95 | 0 | 117.79 | 549.41 | -431.62
| 2026-10-08 | Underserved Community | EL CAJON | N/A | Not Available | 21 | 15 | N/A |  | Not Available | Not Available | Not Available | 606.24 | Unknown | 420.33 | 0 | 1066.55 | 1093.18 | -26.63
| 2024-03-27 | Underserved Community | SAN MARCOS | N/A | Not Available | 134 | 96 | N/A | 2023-09-11 | Not Available | Not Available | Not Available | 434.81 | Unknown | 286.58 | 0 | 40.01 | 960.94 | -920.93
| 2025-02-20 | N/A | SAN DIEGO | N/A | Not Available | 21 | 15 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | 491.61 | Unknown | 313.64 | 0 | 153.75 | 961.64 | -807.89
| 2024-01-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 56 | 40 | N/A |  | Not Available | Not Available | Not Available | 561.84 | Unknown | 360.1 | 0 | 599.97 | 1171.66 | -571.69
| 2024-03-21 | N/A | MISSION VIEJO | N/A | Not Available | 16 | 12 | N/A | 2023-05-12 | Not Available | Not Available | Not Available | 413.07 | Unknown | 264.68 | 0 | 110.98 | 834.14 | -723.16
| 2024-01-14 | N/A | SAN CLEMENTE | N/A | Not Available | 90 | 64 | N/A | 2023-06-12 | Not Available | Not Available | Not Available | 280.92 | Unknown | 178.49 | 3981 | 92.06 | 548.77 | -456.71
| 2025-01-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 46 | 34 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | 386.43 | Unknown | 266.03 | 0 | 158.14 | 1131.56 | -973.42
| 2025-02-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A |  | Not Available | Not Available | Not Available | 252.1 | Unknown | 162.09 | 0 | 153.75 | 503.55 | -349.8
| 2025-05-08 | Underserved Community | CHULA VISTA | N/A | Not Available | 54 | 38 | N/A |  | Not Available | Not Available | Not Available | 529.05 | Unknown | 327.84 | 0 | 156.93 | 905.61 | -748.68
| 2024-12-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2023-06-01 | Not Available | Not Available | Not Available | 4221.91 | Unknown | 1656.58 | 0 | 154.79 | 6555.3 | -6400.51
| 2025-05-30 | N/A | SAN DIEGO | N/A | Not Available | 2 | 2 | N/A |  | Not Available | Not Available | Not Available | 280.92 | Unknown | 178.48 | 0 | 153.75 | 548.76 | -395.01
| 2024-10-31 | N/A | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A |  | Not Available | Not Available | Not Available | 236.04 | Unknown | 395.42 | 0 | 1125 | 719.56 | 405.44
| 2025-06-15 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 162 | 116 | N/A |  | Not Available | Not Available | Not Available | 367.35 | Unknown | 236.86 | 0 | 500.87 | 659.36 | -158.49
| 2025-06-15 | N/A | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2023-10-27 | Not Available | Not Available | Not Available | 298.96 | Unknown | 207.32 | 0 | 149.82 | 801.08 | -651.26
| 2026-07-09 | N/A | MISSION VIEJO | N/A | Not Available | 12 | 8 | N/A | 2024-08-14 | Not Available | Not Available | Not Available | 349.34 | Unknown | 275.79 | 0 | 180.5 | 1031.44 | -850.94
| 2025-03-18 | Underserved Community | NATIONAL CITY | N/A | Not Available | 227 | 163 | N/A |  | Not Available | Not Available | Not Available | 248.04 | Unknown | 184.93 | 0 | 496.37 | 488.12 | 8.25
| 2026-11-10 | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Not Available | 60 | 42 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | 866.68 | Unknown | 412.09 | 3981 | 114.3 | 1314.93 | -1200.63
| 2026-07-12 | N/A | LAGUNA NIGUEL | N/A | Not Available | 36 | 26 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | 492.57 | Unknown | 367.21 | 0 | 180.5 | 1324.44 | -1143.94
| 2024-04-05 | N/A | SAN CLEMENTE | N/A | Not Available | 88 | 64 | N/A | 2023-11-27 | Not Available | Not Available | Not Available | 838.15 | Unknown | 557 | 3981 | 153.83 | 1986.48 | -1832.65
| 2025-01-11 | Underserved Community | ESCONDIDO | N/A | Not Available | 35 | 25 | N/A | 2023-10-04 | Not Available | Not Available | Not Available | 523.12 | Unknown | 339.72 | 0 | 465.36 | 1021.96 | -556.6
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 107 | 77 | N/A |  | Not Available | Not Available | Not Available | 191.03 | Unknown | 140.36 | 0 | 192.95 | 460.97 | -268.02
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 72 | 52 | N/A |  | Not Available | Not Available | Not Available | 125.68 | Unknown | 89.5 | 0 | 192.95 | 256.04 | -63.09
| 2024-06-12 | N/A | MISSION VIEJO | N/A | Not Available | 30 | 22 | N/A | 2023-09-11 | Not Available | Not Available | Not Available | 246.68 | Unknown | 160.89 | 3981 | 143.91 | 525.49 | -381.58
| 2026-11-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 31 | 23 | N/A |  | Not Available | Not Available | Not Available | 628.4 | Unknown | 438.1 | 0 | 197.01 | 1200.92 | -1003.91
| 2027-01-30 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 55 | 39 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | 604.91 | Unknown | 1762.06 | 0 | 1064.43 | 2461.3 | -1396.87
| 2024-02-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 187 | 133 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | 309 | Unknown | 206.58 | 0 | 500.87 | 662.98 | -162.11
| 2025-10-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 146 | 104 | N/A |  | Not Available | Not Available | Not Available | 252.46 | Unknown | 175.78 | 0 | 534.53 | 464.84 | 69.69
| 2025-10-02 | N/A | SAN DIEGO | N/A | Not Available | 211 | 151 | N/A | 2024-10-08 | Not Available | Not Available | Not Available | 375.24 | Unknown | 270.8 | 0 | 529.2 | 782.37 | -253.17
| 2026-11-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | 303.12 | Unknown | 218.66 | 0 | 197.01 | 653.62 | -456.61
| 2025-04-07 | N/A | SAN DIEGO | N/A | Not Available | 406 | 290 | N/A | 2024-05-16 | Not Available | Not Available | Not Available | 1112.01 | Unknown | 1012.33 | 0 | 153.87 | 2137.43 | -1983.56
| 2026-10-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 32 | 24 | N/A |  | Not Available | Not Available | Not Available | 245.43 | Unknown | 635.94 | 0 | 196.44 | 945.83 | -749.39
| 2026-04-11 | N/A | RAMONA | N/A | Not Available | 73 | 53 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | 392.28 | Unknown | 202.29 | 0 | 496.14 | 677.46 | -181.32
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | 129.47 | Unknown | 89.75 | 0 | 196.44 | 234.51 | -38.07
| 2024-08-17 | Underserved Community | EL CAJON | N/A | Not Available | 128 | 92 | N/A | 2024-04-03 | Not Available | Not Available | Not Available | 286.76 | Unknown | 207.43 | 0 | 158.79 | 640.08 | -481.29
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | 257.08 | Unknown | 178.2 | 0 | 196.44 | 465.85 | -269.41
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | 333.95 | Unknown | 167.02 | 0 | 196.44 | 523.9 | -327.46
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 514.16 | Unknown | 282.91 | 0 | 196.44 | 848.34 | -651.9
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 223 | 160 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | 194.21 | Unknown | 134.61 | 0 | 196.44 | 351.75 | -155.31
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.14 | 0 | 196.44 | 350.57 | -154.13
| 2024-11-28 | N/A | LAGUNA HILLS | N/A | Not Available | 42 | 30 | N/A | 2024-01-19 | Not Available | Not Available | Not Available | 541.11 | Unknown | 394.23 | 0 | 148.54 | 1185.33 | -1036.79
| 2026-03-11 | Underserved Community | VALLEY CENTER | N/A | Not Available | 64 | 46 | N/A |  | Not Available | Not Available | Not Available | 362.52 | Unknown | 254.29 | 0 | 984.98 | 674.24 | 310.74
| 2024-10-20 | N/A | SAN CLEMENTE | N/A | Not Available | 117 | 83 | N/A | 2024-01-23 | Not Available | Not Available | Not Available | 382.48 | Unknown | 282.68 | 0 | 838.21 | 773.92 | 64.29
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 661.64 | Unknown | 521.42 | 0 | 196.44 | 1213.63 | -1017.19
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 132.47 | Unknown | 91.76 | 0 | 196.44 | 239.52 | -43.08
| 2025-01-24 | N/A | LAGUNA NIGUEL | N/A | Not Available | 190 | 136 | N/A | 2024-07-10 | Not Available | Not Available | Not Available | 274.6 | Unknown | 1892.12 | 0 | 153.26 | 2182.84 | -2029.58
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 132.47 | Unknown | 91.76 | 0 | 196.44 | 239.52 | -43.08
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A |  | Not Available | Not Available | Not Available | 625.08 | Unknown | 314.9 | 0 | 196.44 | 970.55 | -774.11
| 2023-07-31 | N/A | LAS FLORES | N/A | Not Available | 119 | 85 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | 165.12 | Unknown | 136.06 | 0 | 111.67 | 523.43 | -411.76
| 2025-01-23 | Underserved Community | VISTA | N/A | Not Available | 95 | 69 | N/A | 2023-06-05 | Not Available | Not Available | Not Available | 2258.74 | Unknown | 1176.67 | 0 | 499.96 | 3495.35 | -2995.39
| 2025-06-21 | N/A | CAPISTRANO BEACH | N/A | Not Available | 23 | 17 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | 1152.94 | Unknown | 1327.36 | 0 | 192.51 | 2543.27 | -2350.76
| 2025-08-14 | N/A | LAGUNA NIGUEL | N/A | Not Available | 21 | 15 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | 1095.74 | Unknown | 814.98 | 0 | 180.5 | 2770.6 | -2590.1
| 2024-10-26 | Underserved Community | OCEANSIDE | N/A | Not Available | 186 | 134 | N/A | 2023-08-21 | Not Available | Not Available | Not Available | 1775.86 | Unknown | 971.73 | 0 | 363.72 | 3005.07 | -2641.35
| 2025-02-05 | N/A | SAN CLEMENTE | N/A | Not Available | 11 | 9 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | 525.67 | Unknown | 365.43 | 0 | 151.87 | 1130.66 | -978.79
| 2024-12-20 | N/A | LAS FLORES | N/A | Not Available | 357 | 255 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | 126.23 | Unknown | 105.99 | 0 | 163.83 | 288.93 | -125.1
| 2024-03-28 | N/A | LAGUNA HILLS | N/A | Not Available | 282 | 202 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | 227.07 | Unknown | 137.78 | 0 | 111.06 | 419.33 | -308.27
| 2026-05-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 42 | 30 | N/A |  | Not Available | Not Available | Not Available | 521.55 | Unknown | 362.2 | 0 | 1050.61 | 907.92 | 142.69
| 2026-12-11 | Underserved Community | ESCONDIDO | N/A | Not Available | 28 | 20 | N/A |  | Not Available | Not Available | Not Available | 345.62 | Unknown | 224.21 | 0 | 197.01 | 644.58 | -447.57
| 2027-03-29 | Underserved Community | ENCINITAS | N/A | Not Available | 21 | 15 | N/A | 2025-04-09 | Not Available | Not Available | Not Available | 382.05 | Unknown | 272.76 | 0 | 196.59 | 833.78 | -637.19
| 2027-07-05 | Underserved Community | SAN MARCOS | N/A | Not Available | 16 | 12 | N/A | 2024-08-07 | Not Available | Not Available | Not Available | 1328.75 | Unknown | 779.78 | 0 | 180.5 | 2541.54 | -2361.04
| 2026-02-24 | Underserved Community | OCEANSIDE | N/A | Not Available | 27 | 19 | N/A | 2025-02-26 | Not Available | Not Available | Not Available | 502.72 | Unknown | 354.42 | 0 | 278.5 | 970.94 | -692.44
| 2026-03-05 | Underserved Community | VISTA | N/A | Not Available | 56 | 40 | N/A | 2024-05-31 | Not Available | Not Available | Not Available | 416.11 | Unknown | 306.7 | 0 | 534.57 | 957.7 | -423.13
| 2025-10-19 | N/A | ENCINITAS | N/A | Not Available | 15 | 11 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | 986.78 | Unknown | 847.03 | 0 | 209.87 | 2142.85 | -1932.98
| 2024-10-13 | N/A | DANA POINT | N/A | Not Available | 15 | 11 | N/A | 2024-01-05 | Not Available | Not Available | Not Available | 806.31 | Unknown | 606.67 | 0 | 158.79 | 1849.5 | -1690.71
| 2026-11-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 179.76 | 0 | 197.01 | 493.65 | -296.64
| 2025-09-30 | N/A | CARLSBAD | N/A | Not Available | 13 | 9 | N/A | 2024-10-04 | Not Available | Not Available | Not Available | 502.72 | Unknown | 353.02 | 0 | 197.01 | 891.7 | -694.69
| 2025-03-29 | N/A | CARDIFF | N/A | Not Available | 8 | 6 | N/A | 2024-04-10 | Not Available | Not Available | Not Available | 264.18 | Unknown | 181.92 | 0 | 209.87 | 449.28 | -239.41
| 2024-05-04 | Underserved Community | JULIAN | N/A | Not Available | 20 | 14 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | 379.8 | Unknown | 171.4 | 0 | 495.75 | 640.56 | -144.81
| 2025-12-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 92 | 66 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | 256.62 | Unknown | 182.06 | 0 | 163.83 | 509.91 | -346.08
| 2024-11-08 | Underserved Community | JULIAN | N/A | Not Available | 3 | 3 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | 1979.2 | Unknown | 1360.63 | 0 | 142.83 | 3379.39 | -3236.56
| 2027-01-06 | N/A | DEL MAR | N/A | Not Available | 9 | 7 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | 502.72 | Unknown | 350.35 | 0 | 197.01 | 984.11 | -787.1
| 2025-12-05 | N/A | CARLSBAD | N/A | Not Available | 5 | 3 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | 303.12 | Unknown | 216.96 | 0 | 288.94 | 561.86 | -272.92
| 2024-12-15 | Underserved Community | FALLBROOK | N/A | Not Available | 20 | 14 | N/A |  | Not Available | Not Available | Not Available | 421.38 | Unknown | 265.98 | 0 | 599.97 | 819.51 | -219.54
| 2026-03-20 | N/A | SAN DIEGO | N/A | Not Available | 321 | 229 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | 531.86 | Unknown | 378.75 | 0 | 192.51 | 1058.01 | -865.5
| 2024-12-04 | N/A | SAN CLEMENTE | N/A | Not Available | 64 | 46 | N/A | 2024-03-13 | Not Available | Not Available | Not Available | 509.23 | Unknown | 367.08 | 0 | 158.79 | 984.38 | -825.59
| 2025-10-04 | N/A | ENCINITAS | N/A | Not Available | 112 | 80 | N/A | 2024-03-18 | Not Available | Not Available | Not Available | 264.18 | Unknown | 185.36 | 0 | 203.23 | 487.43 | -284.2
| 2024-02-01 | Underserved Community | DANA POINT | N/A | Not Available | 20 | 14 | N/A | 2023-04-07 | Not Available | Not Available | Not Available | 295.05 | Unknown | 190.43 | 3981 | 98.66 | 595.61 | -496.95
| 2025-03-28 | Underserved Community | ESCONDIDO | N/A | Not Available | 25 | 19 | N/A | 2023-06-08 | Not Available | Not Available | Not Available | 421.38 | Unknown | 267.74 | 0 | 40.01 | 823.16 | -783.15
| 2024-12-22 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 60 | 44 | N/A |  | Not Available | Not Available | Not Available | 237.76 | Unknown | 152.31 | 0 | 363.72 | 479.43 | -115.71
| 2025-01-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 31 | 23 | N/A | 2023-05-24 | Not Available | Not Available | Not Available | 465.88 | Unknown | 290.82 | 0 | 153.75 | 885.14 | -731.39
| 2024-04-03 | Underserved Community | OCEANSIDE | N/A | Not Available | 50 | 36 | N/A | 2023-04-05 | Not Available | Not Available | Not Available | 1710.28 | Unknown | 1070.78 | 0 | 483.84 | 3017.34 | -2533.5
| 2024-02-08 | N/A | MISSION VIEJO | N/A | Not Available | 216 | 154 | N/A | 2023-10-09 | Not Available | Not Available | Not Available | 804.96 | Unknown | 731.72 | 0 | 111.67 | 3533.44 | -3421.77
| 2024-03-07 | N/A | SAN CLEMENTE | N/A | Not Available | 74 | 52 | N/A | 2023-07-11 | Not Available | Not Available | Not Available | 579.33 | Unknown | 372.42 | 0 | 495.75 | 1133.34 | -637.59
| 2025-01-16 | N/A | CARLSBAD | N/A | Not Available | 66 | 48 | N/A | 2023-05-10 | Not Available | Not Available | Not Available | 418.94 | Unknown | 260.2 | 0 | 341.75 | 772.33 | -430.58
| 2024-03-06 | N/A | MISSION VIEJO | N/A | Not Available | 14 | 10 | N/A | 2023-05-18 | Not Available | Not Available | Not Available | 532.76 | Unknown | 350.81 | 0 | 110.98 | 1174.53 | -1063.55
| 2024-10-03 | N/A | SAN DIEGO | N/A | Not Available | 167 | 119 | N/A | 2023-07-17 | Not Available | Not Available | Not Available | 280.92 | Unknown | 180.66 | 0 | 98.41 | 579.5 | -481.09
| 2024-03-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | 290.19 | Unknown | 250.62 | 0 | 363.72 | 652.52 | -288.8
| 2025-01-30 | Underserved Community | VISTA | N/A | Not Available | 85 | 61 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | 465.88 | Unknown | 290.81 | 0 | 364.52 | 885.13 | -520.61
| 2024-05-09 | N/A | SAN DIEGO | N/A | Not Available | 107 | 77 | N/A | 2023-08-19 | Not Available | Not Available | Not Available | 372.45 | Unknown | 247.03 | 0 | 153.75 | 796.36 | -642.61
| 2024-10-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A |  | Not Available | Not Available | Not Available | 243.32 | Unknown | 165.58 | 0 | 98.41 | 564.68 | -466.27
| 2024-03-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 19 | 15 | N/A | 2023-05-19 | Not Available | Not Available | Not Available | 842.76 | Unknown | 535.45 | 0 | 153.75 | 1646.29 | -1492.54
| 2025-01-03 | N/A | CARDIFF | N/A | Not Available | 68 | 48 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | 837.89 | Unknown | 477.75 | 0 | 499.96 | 1557.56 | -1057.6
| 2025-09-12 | N/A | RAMONA | N/A | Not Available | 57 | 41 | N/A | 2024-04-04 | Not Available | Not Available | Not Available | 591.09 | Unknown | 313.68 | 0 | 163.83 | 1216.73 | -1052.9
| 2024-03-13 | N/A | SAN DIEGO | N/A | Not Available | 23 | 17 | N/A | 2024-03-15 | Not Available | Not Available | Not Available | 264.18 | Unknown | 188.33 | 0 | 163.83 | 490.4 | -326.57
| 2025-08-01 | N/A | POWAY | N/A | Not Available | 115 | 83 | N/A |  | Not Available | Not Available | Not Available | 510.06 | Unknown | 339.95 | 0 | 723.7 | 1066.76 | -343.06
| 2024-08-09 | N/A | EL CAJON | N/A | Not Available | 78 | 56 | N/A |  | Not Available | Not Available | Not Available | 397.48 | Unknown | 422.48 | 0 | 158.79 | 2473.2 | -2314.41
| 2024-12-04 | N/A | LAGUNA NIGUEL | N/A | Not Available | 58 | 42 | N/A | 2024-02-26 | Not Available | Not Available | Not Available | 581.96 | Unknown | 427.55 | 0 | 163.83 | 1255.69 | -1091.86
| 2026-06-19 | N/A | SAN DIEGO | N/A | Not Available | 9 | 7 | N/A | 2024-07-18 | Not Available | Not Available | Not Available | 1023.73 | Unknown | 714.91 | 0 | 282.95 | 1853 | -1570.05
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 28 | 20 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | 606.24 | Unknown | 424.24 | 0 | 197.01 | 1066.44 | -869.43
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 86 | 62 | N/A |  | Not Available | Not Available | Not Available | 254.7 | Unknown | 181.98 | 0 | 192.95 | 525.47 | -332.52
| 2025-09-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A |  | Not Available | Not Available | Not Available | 582.92 | Unknown | 412.25 | 0 | 158.79 | 1211.92 | -1053.13
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A |  | Not Available | Not Available | Not Available | 303.12 | Unknown | 218.66 | 0 | 197.01 | 653.62 | -456.61
| 2026-06-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A |  | Not Available | Not Available | Not Available | 1044.82 | Unknown | 2232.71 | 0 | 1050.75 | 3374.89 | -2324.14
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | 303.12 | Unknown | 218.66 | 0 | 184.29 | 653.62 | -469.33
| 2024-08-02 | N/A | SAN DIEGO | N/A | Not Available | 13 | 9 | N/A |  | Not Available | Not Available | Not Available | 757.22 | Unknown | 543.96 | 0 | 700.41 | 1326.86 | -626.45
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A |  | Not Available | Not Available | Not Available | 251.36 | Unknown | 185.25 | 0 | 197.01 | 615.21 | -418.2
| 2025-10-31 | N/A | SAN DIEGO | N/A | Not Available | 153 | 109 | N/A | 2023-12-15 | Not Available | Not Available | Not Available | 254.76 | Unknown | 157.16 | 0 | 158.79 | 498.68 | -339.89
| 2026-11-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | 251.36 | Unknown | 179.76 | 0 | 184.29 | 493.65 | -309.36
| 2025-02-09 | N/A | LAGUNA NIGUEL | N/A | Not Available | 64 | 46 | N/A | 2024-03-21 | Not Available | Not Available | Not Available | 136.6 | Unknown | 105.62 | 0 | 163.83 | 278.24 | -114.41
| 2026-03-03 | Underserved Community | RAMONA | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | 1279.36 | Unknown | 617 | 0 | 142.53 | 2118.83 | -1976.3
| 2024-12-07 | N/A | SAN CLEMENTE | N/A | Not Available | 97 | 69 | N/A | 2024-03-04 | Not Available | Not Available | Not Available | 184.21 | Unknown | 144.76 | 0 | 153.26 | 417.41 | -264.15
| 2026-09-10 | Underserved Community | RAMONA | N/A | Not Available | 178 | 128 | N/A |  | Not Available | Not Available | Not Available | 757.8 | Unknown | 570.38 | 0 | 999.88 | 1966.35 | -966.47
| 2024-11-02 | N/A | SAN DIEGO | N/A | Not Available | 138 | 98 | N/A | 2023-11-14 | Not Available | Not Available | Not Available | 254.76 | Unknown | 165.43 | 0 | 513.31 | 506.95 | 6.36
| 2026-01-06 | Underserved Community | RAMONA | N/A | Not Available | 42 | 30 | N/A |  | Not Available | Not Available | Not Available | 764.1 | Unknown | 411.55 | 0 | 196.69 | 2132.48 | -1935.79
| 2025-07-18 | Underserved Community | SAN MARCOS | N/A | Not Available | 84 | 60 | N/A | 2023-10-20 | Not Available | Not Available | Not Available | 257.62 | Unknown | 172.6 | 0 | 154.99 | 574.72 | -419.73
| 2026-06-06 | Underserved Community | SAN MARCOS | N/A | Not Available | 93 | 67 | N/A | 2024-08-14 | Not Available | Not Available | Not Available | 377.04 | Unknown | 285.9 | 0 | 192.95 | 879.31 | -686.36
| 2024-05-25 | N/A | ENCINITAS | N/A | Not Available | 332 | 237 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | 766.07 | Unknown | 658.5 | 0 | 158.79 | 1430.93 | -1272.14
| 2025-07-26 | Underserved Community | VISTA | N/A | Not Available | 168 | 120 | N/A | 2024-01-02 | Not Available | Not Available | Not Available | 302.11 | Unknown | 222.25 | 0 | 515.81 | 666.62 | -150.81
| 2025-09-15 | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Not Available | 5 | 3 | N/A |  | Not Available | Not Available | Not Available | 2240.79 | Unknown | 1480.92 | 3981 | 153.83 | 4669.31 | -4515.48
| 2025-11-13 | Underserved Community | ESCONDIDO | N/A | Not Available | 64 | 46 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 312.83 | 3981 | 197.01 | 854.47 | -657.46
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 134 | 96 | N/A |  | Not Available | Not Available | Not Available | 253.4 | Unknown | 175.91 | 0 | 374 | 451.75 | -77.75
| 2024-08-07 | N/A | LAGUNA NIGUEL | N/A | Not Available | 257 | 183 | N/A | 2024-05-08 | Not Available | Not Available | Not Available | 120.96 | Unknown | 81 | 0 | 113.9 | 274.21 | -160.31
| 2025-09-19 | Underserved Community | SAN MARCOS | N/A | Not Available | 30 | 22 | N/A |  | Not Available | Not Available | Not Available | 566.56 | Unknown | 397.53 | 0 | 184.29 | 1070.68 | -886.39
| 2025-03-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2023-08-16 | Not Available | Not Available | Not Available | 362.52 | Unknown | 202.26 | 0 | 496.37 | 594.26 | -97.89
| 2026-11-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A |  | Not Available | Not Available | Not Available | 125.68 | Unknown | 92.69 | 0 | 184.29 | 307.69 | -123.4
| 2025-11-04 | Underserved Community | RAMONA | N/A | Not Available | 59 | 43 | N/A |  | Not Available | Not Available | Not Available | 356.12 | Unknown | 200.13 | 0 | 196.44 | 674.99 | -478.55
| 2024-05-22 | Underserved Community | DANA POINT | N/A | Not Available | 27 | 19 | N/A | 2023-10-20 | Not Available | Not Available | Not Available | 978.84 | Unknown | 667.88 | 0 | 114.15 | 2269.52 | -2155.37
| 2025-08-03 | N/A | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | 529.05 | Unknown | 333.13 | 0 | 153.83 | 967.12 | -813.29
| 2026-05-13 | N/A | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | 483.36 | Unknown | 337.42 | 0 | 274.07 | 873.47 | -599.4
| 2025-09-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | 367.35 | Unknown | 271.82 | 0 | 534.53 | 790.05 | -255.52
| 2025-05-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 28 | 20 | N/A | 2023-08-30 | Not Available | Not Available | Not Available | 437.19 | Unknown | 287.45 | 0 | 465.36 | 964.19 | -498.83
| 2026-09-14 | Underserved Community | VISTA | N/A | Not Available | 39 | 27 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | 507.21 | Unknown | 468.54 | 0 | 1032.11 | 1045.81 | -13.7
| 2025-04-26 | Underserved Community | FALLBROOK | N/A | Not Available | 23 | 17 | N/A | 2023-07-12 | Not Available | Not Available | Not Available | 351.15 | Unknown | 226.23 | 0 | 153.87 | 777.01 | -623.14
| 2025-09-06 | N/A | OCEANSIDE | N/A | Not Available | 50 | 36 | N/A | 2024-02-07 | Not Available | Not Available | Not Available | 367.35 | Unknown | 261.09 | 1000 | 158.79 | 689.8 | -531.01
| 2026-05-20 | N/A | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | 695.4 | Unknown | 500.97 | 0 | 192.51 | 1285.48 | -1092.97
| 2027-01-15 | Underserved Community | VISTA | N/A | Not Available | 18 | 12 | N/A |  | Not Available | Not Available | Not Available | 1054.16 | Unknown | 748.95 | 0 | 278.82 | 2038.26 | -1759.44
| 2024-06-14 | N/A | LAGUNA HILLS | N/A | Not Available | 25 | 19 | N/A | 2023-08-08 | Not Available | Not Available | Not Available | 387.94 | Unknown | 260.08 | 0 | 143.91 | 806.78 | -662.87
| 2027-02-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 34 | 24 | N/A |  | Not Available | Not Available | Not Available | 454.68 | Unknown | 313.85 | 0 | 196.44 | 853.66 | -657.22
| 2025-01-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 29 | 21 | N/A |  | Not Available | Not Available | Not Available | 280.92 | Unknown | 178.48 | 0 | 154.79 | 548.76 | -393.97
| 2024-09-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 2 | 2 | N/A |  | Not Available | Not Available | Not Available | 1043.21 | Unknown | 561.26 | 0 | 148.7 | 1852.49 | -1703.79
| 2024-02-06 | Underserved Community | BONSALL | N/A | Not Available | 30 | 22 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | 1008.4 | Unknown | 626.54 | 0 | 594.91 | 1880.62 | -1285.71
| 2025-04-12 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 118 | 84 | N/A |  | Not Available | Not Available | Not Available | 315.58 | Unknown | 189.31 | 0 | 153.49 | 541.49 | -388
| 2025-01-01 | N/A | CARDIFF | N/A | Not Available | 190 | 136 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | 3447.24 | Unknown | 1892.24 | 0 | 163.83 | 5365.42 | -5201.59
| 2026-10-04 | Underserved Community | NATIONAL CITY | N/A | Not Available | 154 | 110 | N/A |  | Not Available | Not Available | Not Available | 591.99 | Unknown | 272.5 | 0 | 1066.51 | 1028.12 | 38.39
| 2026-02-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A |  | Not Available | Not Available | Not Available | 483.36 | Unknown | 336.95 | 0 | 529.2 | 883.41 | -354.21
| 2024-06-26 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 1 | 1 | N/A | 2023-12-05 | Not Available | Not Available | Not Available | 1056.89 | Unknown | 677.55 | 0 | 158.51 | 2325.91 | -2167.4
| 2025-06-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 189 | 135 | N/A |  | Not Available | Not Available | Not Available | 1028.38 | Unknown | 1788.28 | 0 | 500.87 | 3093.29 | -2592.42
| 2024-11-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A |  | Not Available | Not Available | Not Available | 364.98 | Unknown | 232.67 | 0 | 95.13 | 729.8 | -634.67
| 2026-01-14 | Underserved Community | OCEANSIDE | N/A | Not Available | 101 | 73 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | 362.52 | Unknown | 251.18 | 0 | 202.87 | 618.93 | -416.06
| 2023-11-10 | N/A | RANCHO LA COSTA | N/A | Not Available | 32 | 24 | N/A | 2023-04-17 | Not Available | Not Available | Not Available | 686.12 | Unknown | 437.53 | 0 | 98.66 | 1263.61 | -1164.95
| 2025-01-01 | N/A | CARDIFF | N/A | Not Available | 187 | 133 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | 377.04 | Unknown | 263.71 | 0 | 163.83 | 652.4 | -488.57
| 2025-02-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | 280.92 | Unknown | 178.5 | 0 | 341.75 | 548.78 | -207.03
| 2025-07-25 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2023-11-02 | Not Available | Not Available | Not Available | 257.62 | Unknown | 182.3 | 0 | 154.99 | 675.76 | -520.77
| 2025-09-10 | Underserved Community | CHULA VISTA | N/A | Not Available | 45 | 33 | N/A |  | Not Available | Not Available | Not Available | 934.8 | Unknown | 962.67 | 0 | 163.83 | 1952.62 | -1788.79
| 2024-03-10 | Underserved Community | RAMONA | N/A | Not Available | 43 | 31 | N/A | 2023-04-26 | Not Available | Not Available | Not Available | 1658.08 | Unknown | 794.06 | 0 | 363.72 | 3412.06 | -3048.34
| 2024-02-20 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 193 | 137 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | 368.37 | Unknown | 229.8 | 0 | 110.98 | 639.01 | -528.03
| 2024-01-10 | Underserved Community | JAMUL | N/A | Not Available | 84 | 60 | N/A |  | Not Available | Not Available | Not Available | 296.36 | Unknown | 161.6 | 0 | 363.72 | 592 | -228.28
| 2024-12-05 | Underserved Community | FALLBROOK | N/A | Not Available | 667 | 477 | N/A | 2024-12-12 | Not Available | Not Available | Not Available | 390.24 | Unknown | 276.04 | 0 | 436.48 | 784.01 | -347.53
| 2024-11-10 | N/A | RANCHO LA COSTA | N/A | Not Available | 48 | 34 | N/A | 2023-04-10 | Not Available | Not Available | Not Available | 1194.69 | Unknown | 690.8 | 0 | 98.41 | 2216.51 | -2118.1
| 2025-01-02 | N/A | RANCHO SANTA FE | N/A | Not Available | 10 | 8 | N/A | 2023-04-13 | Not Available | Not Available | Not Available | 944.17 | Unknown | 530.81 | 0 | 154.79 | 1739.28 | -1584.49
| 2025-02-10 | N/A | CARLSBAD | N/A | Not Available | 63 | 45 | N/A | 2023-05-22 | Not Available | Not Available | Not Available | 472.08 | Unknown | 299.78 | 0 | 143.83 | 928.02 | -784.19
| 2024-04-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 52 | 38 | N/A | 2023-06-07 | Not Available | Not Available | Not Available | 602.54 | Unknown | 1328.86 | 0 | 495.75 | 2020.76 | -1525.01
| 2025-03-06 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | 431.12 | Unknown | 271.75 | 0 | 496.45 | 743.71 | -247.26
| 2025-04-19 | Underserved Community | LA JOLLA | N/A | Not Available | 16 | 12 | N/A | 2023-11-03 | Not Available | Not Available | Not Available | 445.83 | Unknown | 258.06 | 3981 | 481.24 | 834.03 | -352.79
| 2024-01-30 | N/A | LAGUNA NIGUEL | N/A | Not Available | 91 | 65 | N/A | 2023-06-19 | Not Available | Not Available | Not Available | 400.18 | Unknown | 251.86 | 0 | 111.67 | 766.58 | -654.91
| 2024-02-22 | N/A | COTO DE CAZA | N/A | Not Available | 69 | 49 | N/A | 2023-05-26 | Not Available | Not Available | Not Available | 504.51 | Unknown | 500.47 | 0 | 111.67 | 1094.34 | -982.67
| 2024-10-11 | Underserved Community | ESCONDIDO | N/A | Not Available | 70 | 50 | N/A | 2023-03-29 | Not Available | Not Available | Not Available | 425.81 | Unknown | 240.67 | 0 | 341 | 798.63 | -457.63
| 2024-02-14 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | 65 | 47 | N/A |  | Not Available | Not Available | Not Available | 236.04 | Unknown | 151.24 | 0 | 111.67 | 476.64 | -364.97
| 2025-02-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 274 | 196 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | 716.96 | Unknown | 519.18 | 0 | 154.79 | 1398.46 | -1243.67
| 2023-04-28 | N/A | SAN MARCOS | N/A | Not Available | 7 | 5 | N/A | 2023-04-11 | Not Available | Not Available | Not Available | 243.32 | Unknown | 154.29 | 0 | 599.97 | 485.71 | 114.26
| 2025-03-01 | Underserved Community | POWAY | N/A | Not Available | 2 | 2 | N/A |  | Not Available | Not Available | Not Available | 280.92 | Unknown | 195.94 | 0 | 341 | 616.12 | -275.12
| 2025-02-16 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A |  | Not Available | Not Available | Not Available | 735.13 | Unknown | 487.67 | 0 | 92.3 | 1753.99 | -1661.69
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 51 | 37 | N/A |  | Not Available | Not Available | Not Available | 314.2 | Unknown | 231.09 | 0 | 192.95 | 725.61 | -532.66
| 2026-07-29 | N/A | SAN MARCOS | N/A | Not Available | 23 | 17 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | 571.14 | Unknown | 362.06 | 0 | 197.01 | 1112.39 | -915.38
| 2025-09-18 | N/A | ENCINITAS | N/A | Not Available | 52 | 38 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | 489.8 | Unknown | 348.37 | 0 | 163.83 | 873.74 | -709.91
| 2025-04-05 | Underserved Community | POWAY | N/A | Not Available | 26 | 18 | N/A | 2023-08-11 | Not Available | Not Available | Not Available | 817.34 | Unknown | 425.87 | 0 | 465.36 | 1479.05 | -1013.69
| 2025-08-07 | N/A | CARLSBAD | N/A | Not Available | 60 | 44 | N/A | 2024-02-20 | Not Available | Not Available | Not Available | 378.69 | Unknown | 269.08 | 0 | 158.79 | 684.46 | -525.67
| 2024-10-01 | Underserved Community | RAMONA | N/A | Not Available | 42 | 30 | N/A |  | Not Available | Not Available | Not Available | 254.7 | Unknown | 197.64 | 0 | 999.88 | 737.99 | 261.89
| 2024-12-06 | Underserved Community | SANTA YSABEL | N/A | Not Available | 35 | 25 | N/A |  | Not Available | Not Available | Not Available | 632.07 | Unknown | 464.56 | 0 | 511.58 | 1192.57 | -680.99
| 2024-08-28 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 50 | 36 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | 1252.61 | Unknown | 814.73 | 0 | 158.14 | 2786.45 | -2628.31
| 2027-05-06 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-05-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2027-03-19 | N/A | SAN DIEGO | N/A | Not Available | 47 | 35 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown
| 2027-04-30 | N/A | SAN DIEGO | N/A | Not Available | 384 | 275 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 352.71 | Unknown | Unknown
| 2026-11-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-04 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-04-10 | Underserved Community | EL CAJON | N/A | Not Available | 63 | 45 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 225 | 161 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 225 | 161 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-05-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | 15 | 11 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-31 | N/A | OCEANSIDE | N/A | Not Available | 43 | 31 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-05-03 | N/A | POWAY | N/A | Not Available | 148 | 106 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 984.98 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 68 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-02-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 12 | 10 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-20 | Underserved Community | VISTA | N/A | Not Available | 10 | 8 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2026-12-21 | N/A | ENCINITAS | N/A | Not Available | 50 | 36 | N/A | 2025-04-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.82 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-05 | N/A | SANTEE | N/A | Not Available | 37 | 27 | N/A | 2025-06-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-04-17 | N/A | POWAY | N/A | Not Available | 14 | 10 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-18 | N/A | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-02-03 | Underserved Community | OCEANSIDE | N/A | Not Available | 56 | 40 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.5 | Unknown | Unknown
| 2027-02-26 | N/A | SOLANA BEACH | N/A | Not Available | 18 | 14 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.42 | Unknown | Unknown
| 2027-05-05 | N/A | CARLSBAD | N/A | Not Available | 35 | 25 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 11 | 7 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-01-29 | N/A | CARLSBAD | N/A | Not Available | 86 | 62 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-02-03 | Underserved Community | VISTA | N/A | Not Available | 60 | 42 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-03 | N/A | ENCINITAS | N/A | Not Available | 42 | 30 | N/A | 2025-04-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-20 | Underserved Community | LA JOLLA | N/A | Not Available | 50 | 36 | N/A | 2025-06-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 185 | 133 | N/A | 2024-09-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 139.89 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 310 | 222 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 554.38 | Unknown | Unknown
| 2026-11-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 151 | 109 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.91 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-20 | Underserved Community | OCEANSIDE | N/A | Not Available | 46 | 34 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-20 | Underserved Community | LA MESA | N/A | Not Available | 35 | 25 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.64 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 225 | 161 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2026-09-04 | Underserved Community | EL CAJON | N/A | Not Available | 42 | 30 | N/A | 2024-09-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2399.67 | Unknown | Unknown
| 2027-04-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 43 | 31 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 225 | 161 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 225 | 161 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 65 | 47 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2026-08-02 | Underserved Community | EL CAJON | N/A | Not Available | 57 | 41 | N/A | 2024-10-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1087 | Unknown | Unknown
| 2027-02-11 | Underserved Community | EL CAJON | N/A | Not Available | 97 | 69 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1240.48 | Unknown | Unknown
| 2027-04-10 | N/A | ENCINITAS | N/A | Not Available | 58 | 42 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.71 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 68 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-23 | Underserved Community | MISSION VIEJO | N/A | Not Available | 31 | 23 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-04-07 | N/A | DEL MAR | N/A | Not Available | 15 | 11 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2027-02-20 | N/A | SAN DIEGO | N/A | Not Available | 26 | 18 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-01-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 49 | 35 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-06-03 | Underserved Community | VISTA | N/A | Not Available | 1 | 1 | N/A | 2024-07-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2027-03-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 14 | 10 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2025-06-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-20 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-04-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 996.71 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 23 | 17 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-11 | N/A | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1101.15 | Unknown | Unknown
| 2026-12-06 | N/A | SAN DIEGO | N/A | Not Available | 67 | 49 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 32 | 23 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 52 | 38 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-01-07 | Underserved Community | ESCONDIDO | N/A | Not Available | 113 | 81 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-04-04 | N/A | POWAY | N/A | Not Available | 55 | 39 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 69 | 49 | N/A | 2025-06-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-04-18 | N/A | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-26 | Underserved Community | SANTEE | N/A | Not Available | 41 | 29 | N/A | 2025-06-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.62 | Unknown | Unknown
| 2027-02-14 | N/A | LA JOLLA | N/A | Not Available | 40 | 28 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-01-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 77 | 55 | N/A | 2025-04-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-03-03 | Underserved Community | OCEANSIDE | N/A | Not Available | 43 | 31 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 91 | 65 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 216 | 155 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 68 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 68 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-02-16 | N/A | COTO DE CAZA | N/A | Not Available | 56 | 40 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-01-03 | N/A | LAGUNA NIGUEL | N/A | Not Available | 73 | 53 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 243 | 173 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2027-01-30 | N/A | POWAY | N/A | Not Available | 23 | 17 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-12 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.13 | Unknown | Unknown
| 2027-02-06 | Underserved Community | OCEANSIDE | N/A | Not Available | 27 | 19 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 33 | 25 | N/A | 2025-05-28 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 834.32 | Unknown | Unknown
| 2027-03-10 | N/A | SOLANA BEACH | N/A | Not Available | 14 | 10 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 71 | 51 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-01-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 60 | 44 | N/A | 2025-04-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-04 | N/A | SAN DIEGO | N/A | Not Available | 83 | 59 | N/A | 2025-05-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-14 | N/A | SOLANA BEACH | N/A | Not Available | 15 | 11 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-04-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2025-06-25 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 76 | 54 | N/A | 2025-03-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2027-04-20 | N/A | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-08 | Underserved Community | RAMONA | N/A | Not Available | 50 | 36 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-05 | Underserved Community | LA MESA | N/A | Not Available | 82 | 58 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-25 | N/A | POWAY | N/A | Not Available | 51 | 37 | N/A | 2025-06-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2026-10-22 | Underserved Community | SAN MARCOS | N/A | Not Available | 53 | 39 | N/A | 2024-12-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 95 | 68 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-12 | N/A | LAGUNA HILLS | N/A | Not Available | 36 | 26 | N/A | 2025-04-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 20 | 14 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-04-02 | Underserved Community | CHULA VISTA | N/A | Not Available | 46 | 34 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-02-13 | N/A | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-07 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 23 | 17 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-30 | N/A | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2025-05-29 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-04 | N/A | DANA POINT | N/A | Not Available | 40 | 28 | N/A | 2025-06-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 82 | 58 | N/A | 2025-06-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-06 | Underserved Community | VALLEY CENTER | N/A | Not Available | 37 | 27 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 33 | 25 | N/A | 2025-06-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-12-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 113 | 81 | N/A | 2025-04-25 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 310 | 222 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 463.93 | Unknown | Unknown
| 2027-01-31 | N/A | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A | 2025-04-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 189.89 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 310 | 222 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 554.38 | Unknown | Unknown
| 2027-02-17 | N/A | SAN DIEGO | N/A | Not Available | 53 | 37 | N/A | 2025-04-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-05-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 143 | 103 | N/A | 2024-10-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.5 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-18 | N/A | SOLANA BEACH | N/A | Not Available | 40 | 28 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1099.76 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 53 | 39 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-02-27 | N/A | SAN MARCOS | N/A | Not Available | 53 | 39 | N/A | 2025-04-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-04-17 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 36 | 26 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 178 | 128 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 67 | 49 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-28 | N/A | SAN DIEGO | N/A | Not Available | 40 | 28 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-11-20 | Underserved Community | OCEANSIDE | N/A | Not Available | 108 | 78 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2027-01-28 | Underserved Community | ESCONDIDO | N/A | Not Available | 84 | 60 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 227.87 | Unknown | Unknown
| 2027-04-28 | Underserved Community | LAGUNA HILLS | N/A | Not Available | 28 | 20 | N/A | 2025-05-28 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-26 | N/A | LA JOLLA | N/A | Not Available | 51 | 37 | N/A | 2025-05-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 350.98 | Unknown | Unknown
| 2027-02-26 | N/A | CARLSBAD | N/A | Not Available | 16 | 12 | N/A | 2025-03-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-12-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 46 | 32 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-23 | Underserved Community | ENCINITAS | N/A | Not Available | 35 | 25 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-16 | N/A | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2025-04-03 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-11-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 35 | 25 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-04 | Underserved Community | CHULA VISTA | N/A | Not Available | 49 | 35 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-13 | N/A | SAN CLEMENTE | N/A | Not Available | 84 | 60 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-04-23 | Underserved Community | ESCONDIDO | N/A | Not Available | 51 | 37 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2025-06-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 31 | 23 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 28 | 20 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 31 | 23 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 107 | 77 | N/A | 2025-06-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 996.66 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 321 | 229 | N/A | 2025-03-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 463.93 | Unknown | Unknown
| 2025-07-31 | N/A | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 481.24 | Unknown | Unknown
| 2025-07-31 | Underserved Community | ESCONDIDO | N/A | Not Available | 119 | 85 | N/A |  | Not Available | Not Available | Not Available | 837.95 | 4.04 | 1687.57 | 0 | 591.49 | 2529.56 | -1938.07
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 314 | 224 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 463.93 | Unknown | Unknown
| 2026-03-06 | N/A | POWAY | N/A | Not Available | 56 | 40 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 639.53 | Unknown | Unknown
| 2027-04-11 | Underserved Community | OCEANSIDE | N/A | Not Available | 34 | 24 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2023-03-17 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 386 | 276 | N/A | 2023-12-28 | Not Available | Not Available | Not Available | -15.69 | 16.38 | 175.15 | 0 | 3500.25 | 175.84 | 3324.41
| 2023-12-13 | Underserved Community | EL CAJON | N/A | Not Available | 98 | 70 | N/A | 2023-04-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2026-12-10 | N/A | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-04-01 | N/A | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-11 | N/A | DEL MAR | N/A | Not Available | 20 | 14 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-09 | N/A | SAN DIEGO | N/A | Not Available | 10 | 8 | N/A | 2025-05-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-19 | Underserved Community | LA MESA | N/A | Not Available | 21 | 15 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-04-17 | N/A | SANTEE | N/A | Not Available | 20 | 14 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-15 | N/A | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2025-06-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-04 | Underserved Community | EL CAJON | N/A | Not Available | 83 | 59 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | 4.43 | 26.97 | 0 | 1049.43 | 31.4 | 1018.03
| 2025-10-26 | N/A | ENCINITAS | N/A | Not Available | 25 | 17 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-09-24 | N/A | CARLSBAD | N/A | Not Available | 78 | 56 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 122 | 88 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 380.88 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 335 | 239 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 554.38 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 312 | 224 | N/A | 2025-03-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 463.93 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 322 | 230 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 554.38 | Unknown | Unknown
| 2026-01-23 | N/A | SAN DIEGO | N/A | Not Available | 122 | 88 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-07-09 | Underserved Community | RANCHITA | N/A | Not Available | 61 | 43 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 119 | 85 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2025-07-03 | Underserved Community | OCEANSIDE | N/A | Not Available | 696 | 498 | N/A | 2025-05-28 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2027-05-19 | N/A | ENCINITAS | N/A | Not Available | 13 | 9 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-11-18 | Underserved Community | ALPINE | N/A | Not Available | 15 | 11 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 183.91 | Unknown | Unknown
| 2027-02-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 68 | 48 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-01-29 | Underserved Community | VISTA | N/A | Not Available | 30 | 22 | N/A |  | Not Available | Not Available | Not Available | 1261.2 | -6458 | 3716.73 | 0 | 7020.22 | -1331.28 | 8351.5
| 2024-09-29 | Underserved Community | LA MESA | N/A | Not Available | 519 | 371 | N/A | 2023-12-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2024-02-23 | Underserved Community | VISTA | N/A | Not Available | 487 | 349 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown
| 2022-02-13 | N/A |  | N/A | Not Available | 358 | 256 | N/A | 2023-12-05 | Not Available | Not Available | Not Available | -30.49 | 64.17 | 1853.06 | 0 | 5514.48 | 1886.74 | 3627.74
| 2026-09-12 | N/A | RANCHO LA COSTA | N/A | Not Available | 157 | 113 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2025-08-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 99 | 71 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | -45.82 | 3.92 | 2326.11 | 0 | 4177.18 | 2284.21 | 1892.97
| 2026-12-24 | N/A | POWAY | N/A | Not Available | 91 | 65 | N/A | 2025-06-11 | Not Available | Not Available | Not Available | Unknown | 44.24 | 1329.9 | 0 | 337.5 | 1374.14 | -1036.64
| 2026-03-24 | Underserved Community | MISSION VIEJO | N/A | Not Available | 19 | 13 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 16 | 12 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 25 | 18 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-15 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2025-06-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2028-01-20 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2025-03-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-07-09 | Underserved Community | LA MESA | N/A | Not Available | 201 | 145 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1049.43 | Unknown | Unknown
| 2024-08-11 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 7 | 5 | N/A | 2023-08-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2024-05-03 | N/A | LAGUNA NIGUEL | N/A | Not Available | 3 | 3 | N/A | 2023-05-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2023-07-20 | Underserved Community | CARLSBAD | N/A | Not Available | 38 | 28 | N/A |  | Not Available | Not Available | Not Available | Unknown | -415 | 2179.93 | 0 | 465.44 | 1764.93 | -1299.49
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 314 | 224 | N/A | 2025-03-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 554.38 | Unknown | Unknown
| 2026-05-06 | N/A | SAN DIEGO | N/A | Not Available | 309 | 221 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2026-10-30 | N/A | SAN DIEGO | N/A | Not Available | 217 | 155 | N/A | 2025-05-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 491.24 | Unknown | Unknown
| 2027-04-16 | N/A | SAN DIEGO | N/A | Not Available | 38 | 28 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-08 | Underserved Community | BOULEVARD | N/A | Not Available | 158 | 112 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.57 | Unknown | Unknown
| 2024-07-07 | Underserved Community | LA MESA | N/A | Not Available | 663 | 475 | N/A | 2025-04-01 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 481.24 | Unknown | Unknown
| 2025-07-06 | Underserved Community | OCEANSIDE | N/A | Not Available | 673 | 481 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-02-28 | N/A | POWAY | N/A | Not Available | 68 | 50 | N/A | 2025-04-28 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-03-05 | Underserved Community | ALPINE | N/A | Not Available | 39 | 27 | N/A | 2025-04-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 183.76 | Unknown | Unknown
| 2026-11-18 | Underserved Community | MISSION VIEJO | N/A | Not Available | 60 | 42 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-07 | N/A | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-04 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-01-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 756 | 540 | N/A | 2023-09-13 | Not Available | Not Available | Not Available | -3.51 | 9.22 | 0.49 | 3981 | 1233.78 | 6.2 | 1227.58
| 2026-08-20 | N/A | SAN DIEGO | N/A | Not Available | 160 | 114 | N/A | 2025-04-28 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 34 | 24 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-01-24 | N/A | SAN DIEGO | N/A | Not Available | 96 | 68 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-09-30 | N/A | SAN DIEGO | N/A | Not Available | 255 | 183 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 419.11 | Unknown | Unknown
| 2027-06-12 | N/A | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-11-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 62 | 44 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1099.76 | Unknown | Unknown
| 2026-02-14 | N/A | SAN DIEGO | N/A | Not Available | 391 | 279 | N/A |  | Not Available | Not Available | Not Available | 10373.28 | 8.46 | 27097.25 | 0 | 192.95 | 38651.41 | -38458.46
| 2026-08-23 | Underserved Community | LA MESA | N/A | Not Available | 240 | 172 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1067.34 | Unknown | Unknown
| 2026-02-22 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 350 | 250 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 648.92 | Unknown | Unknown
| 2026-11-10 | Underserved Community | ESCONDIDO | N/A | Not Available | 162 | 116 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2026-01-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 81 | 59 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-12-05 | N/A | SAN DIEGO | N/A | Not Available | 133 | 95 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2024-04-28 | N/A | RANCHO LA COSTA | N/A | Not Available | 532 | 380 | N/A | 2024-10-04 | Not Available | Not Available | Not Available | 754.08 | 3.93 | 572.81 | 0 | 177.75 | 1357.79 | -1180.04
| 2023-08-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 504 | 360 | N/A |  | Not Available | Not Available | Not Available | 983.08 | -1321 | 402.56 | 0 | 1320.66 | 328.94 | 991.72
| 2025-07-27 | Underserved Community | OCEANSIDE | N/A | Not Available | 414 | 296 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 209.87 | Unknown | Unknown
| 2025-02-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 203 | 145 | N/A | 2024-11-06 | Not Available | Not Available | Not Available | -25.64 | -193 | 1308.47 | 0 | 192.51 | 1089.83 | -897.32
| 2026-05-16 | N/A | ESCONDIDO | N/A | Not Available | 22 | 16 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | 2.06 | 15.4 | 0 | 496.11 | 17.46 | 478.65
| 2025-11-25 | Underserved Community | VISTA | N/A | Not Available | 142 | 102 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2026-01-02 | N/A | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2025-06-10 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-21 | Underserved Community | ESCONDIDO | N/A | Not Available | 7 | 5 | N/A | 2025-03-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 996.66 | Unknown | Unknown
| 2026-09-13 | N/A | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 996.66 | Unknown | Unknown
| 2027-03-11 | Underserved Community | SANTEE | N/A | Not Available | 73 | 53 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-10-30 | Underserved Community | RANCHITA | N/A | Not Available | 97 | 69 | N/A | 2024-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 483.59 | Unknown | Unknown
| 2026-02-14 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 144 | 104 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 400.94 | Unknown | Unknown
| 2024-02-06 | Underserved Community | PINE VALLEY | N/A | Not Available | 47 | 35 | N/A | 2023-06-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 286 | 204 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.73 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 322 | 230 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 554.38 | Unknown | Unknown
| 2026-05-23 | N/A | SAN DIEGO | N/A | Not Available | 286 | 204 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.73 | Unknown | Unknown
| 2027-01-23 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | 115 | 83 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-04-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 34 | 24 | N/A | 2025-06-06 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2024-05-01 | Not Available | Not Available | Not Available | -4.81 | 58.6 | 234.9 | 0 | 842.2 | 288.69 | 553.51
| 2026-06-13 | N/A | SAN DIEGO | N/A | Not Available | 332 | 238 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | -48.3 | 56.95 | 2912.31 | 0 | 631.94 | 2920.96 | -2289.02
| 2026-02-26 | Underserved Community | RAMONA | N/A | Not Available | 113 | 81 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-02-04 | Underserved Community | VISTA | N/A | Not Available | 55 | 39 | N/A | 2025-05-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1544.01 | Unknown | Unknown
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | 327 | 233 | N/A | 2023-12-14 | Not Available | Not Available | Not Available | -27.03 | 41.03 | 1248.45 | 0 | 1857.75 | 1262.45 | 595.3
| 2027-04-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2025-05-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-04-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 10 | 8 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-03-25 | Underserved Community | OCEANSIDE | N/A | Not Available | 31 | 23 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.69 | Unknown | Unknown
| 2027-02-13 | N/A | SAN DIEGO | N/A | Not Available | 30 | 22 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-02 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-03 | N/A | SAN DIEGO | N/A | Not Available | 18 | 14 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-04-06 | N/A | CARLSBAD | N/A | Not Available | 663 | 473 | N/A | 2025-06-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-03-11 | Underserved Community | MISSION VIEJO | N/A | Not Available | 72 | 52 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-02 | N/A | CARLSBAD | N/A | Not Available | 223 | 159 | N/A | 2025-06-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-05-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 787.98 | Unknown | Unknown
| 2025-12-03 | N/A | CARLSBAD | N/A | Not Available | 168 | 120 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2024-12-29 | N/A | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 92.06 | Unknown | Unknown
| 2024-11-30 | Underserved Community | JAMUL | N/A | Not Available | 111 | 79 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.34 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 499 | 357 | N/A | 2025-04-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2024-11-16 | Underserved Community | VISTA | N/A | Not Available | 35 | 25 | N/A | 2024-07-30 | Not Available | Not Available | Not Available | Unknown | -984 | 21.53 | 0 | 983.86 | -962.47 | 1946.33
| 2024-04-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 51 | 37 | N/A | 2024-02-12 | Not Available | Not Available | Not Available | -6.54 | -356 | -0.24 | 0 | 356.38 | -362.78 | 719.16
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 53 | 37 | N/A | 2025-05-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-07-12 | Underserved Community | ALPINE | N/A | Not Available | 372 | 266 | N/A | 2024-12-20 | Not Available | Not Available | Not Available | -43.28 | 51.59 | 744.27 | 0 | 1077.64 | 752.58 | 325.06
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 801 | 573 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 239.45 | Unknown | Unknown
| 2025-10-10 | N/A | SAN DIEGO | N/A | Not Available | 175 | 125 | N/A | 2024-03-20 | Not Available | Not Available | Not Available | -5.31 | 0.9 | -1.87 | 0 | 163.83 | -6.28 | 170.11
| 2024-06-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 175 | 125 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | 348.87 | -1175.21 | 1289.81 | 0 | 560.32 | 645.75 | -85.43
| 2025-02-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 135 | 97 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | -0.63 | -193 | 78.73 | 0 | 192.51 | -114.9 | 307.41
| 2024-04-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 188 | 134 | N/A | 2023-10-25 | Not Available | Not Available | Not Available | -6.85 | 15.64 | 7.07 | 0 | 80.74 | 15.86 | 64.88
| 2023-06-23 | Underserved Community | LA MESA | N/A | Not Available | 60 | 43 | N/A | 2023-02-27 | Not Available | Not Available | Not Available | -7.16 | 0.6 | 7.22 | 0 | 389.76 | 0.66 | 389.1
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 253 | 181 | N/A | 2024-10-10 | Not Available | Not Available | Not Available | Unknown | 2.97 | -32.54 | 0 | 197.01 | -29.57 | 226.58
| 2024-03-21 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 148 | 106 | N/A | 2024-07-31 | Not Available | Not Available | Not Available | 2163.28 | 17.14 | 4392.94 | 0 | 2270.95 | 6943.06 | -4672.11
| 2026-06-12 | N/A | DANA POINT | N/A | Not Available | 33 | 25 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | 72.04 | 1.39 | 194.34 | 0 | 302.37 | 267.77 | 34.6
| 2023-02-21 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-01-08 | Not Available | Not Available | Not Available | -14.99 | 0.28 | -8.44 | 0 | 158.79 | -23.15 | 181.94
| 2025-05-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 97 | 69 | N/A | 2023-10-06 | Not Available | Not Available | Not Available | -8.06 | 5.67 | 615.75 | 0 | 663.87 | 613.36 | 50.51
| 2026-08-21 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 86 | 62 | N/A | 2025-06-11 | Not Available | Not Available | Not Available | Unknown | -105 | 57.93 | 0 | 104.77 | -47.07 | 151.84
| 2027-03-24 | Underserved Community | EL CAJON | N/A | Not Available | 85 | 61 | N/A | 2025-06-16 | Not Available | Not Available | Not Available | Unknown | 4.93 | 6.79 | 0 | 117.46 | 11.72 | 105.74
| 2026-08-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | 5.77 | 433.51 | 0 | 377.71 | 439.28 | -61.57
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 170 | 122 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1653.85 | 0 | 1653.85
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 101 | 73 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-08-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 257 | 183 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1103.3 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 73 | 53 | N/A | 2024-07-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.5 | 0 | 192.83 | 5.5 | 187.33
| 2027-04-16 | N/A | SAN DIEGO | N/A | Not Available | 39 | 29 | N/A | 2025-05-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-12-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.19 | 0 | 196.69 | 5.19 | 191.5
| 2024-08-01 | Underserved Community | VISTA | N/A | Not Available | 435 | 311 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 135 | 97 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 192.83 | 4.71 | 188.12
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 166 | 118 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1653.85 | 0 | 1653.85
| 2023-06-16 | Underserved Community | ESCONDIDO | N/A | Not Available | 337 | 241 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1674.31 | 0 | 265.82 | 1674.31 | -1408.49
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 126 | 90 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 101 | 73 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 283.36 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 80 | 58 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.78 | 0 | 180.38 | 1.78 | 178.6
| 2025-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-06-23 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 159 | 113 | N/A | 2024-08-19 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.56 | 0 | 645.75 | -1.56 | 647.31
| 2027-04-21 | N/A | ESCONDIDO | N/A | Not Available | 5 | 5 | N/A | 2025-05-19 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 176 | 126 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 192.83 | 4.71 | 188.12
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 163 | 117 | N/A | 2024-08-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1653.85 | 0 | 1653.85
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 101 | 73 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 80 | 58 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.78 | 0 | 192.83 | 1.78 | 191.05
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 101 | 73 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2021-08-26 | N/A | SOLANA BEACH | N/A | Not Available | 147 | 105 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1874.65 | 0 | 1874.8 | 1874.65 | 0.15
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 185 | 133 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.72 | 0 | 192.83 | 8.72 | 184.11
| 2024-04-20 | Underserved Community | VISTA | N/A | Not Available | 453 | 325 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 164.62 | 0 | 164.62
| 2024-04-20 | Underserved Community | VISTA | N/A | Not Available | 451 | 323 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 164.62 | 0 | 164.62
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 80 | 58 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.5 | 0 | 192.83 | 5.5 | 187.33
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 101 | 73 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 283.36 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 126 | 90 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 410 | 294 | N/A | 2025-06-18 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.09 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 386 | 276 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.09 | Unknown | Unknown
| 2024-11-03 | N/A | SOLANA BEACH | N/A | Not Available | 332 | 238 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 158.79 | 0 | 158.79
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 184 | 132 | N/A | 2024-09-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1653.85 | 0 | 1653.85
| 2025-03-13 | Underserved Community | RAMONA | N/A | Not Available | 22 | 16 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2024-05-08 | N/A | LAGUNA NIGUEL | N/A | Not Available | 171 | 123 | N/A | 2024-02-14 | Not Available | Not Available | Not Available | 472.29 | 12.93 | 298.18 | 0 | 177.82 | 1016.95 | -839.13
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 106 | 76 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.17 | 0 | 180.09 | 3.17 | 176.92
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 64 | 46 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | -10.35 | Unknown | -1.64 | 0 | 283.36 | -11.99 | 295.35
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 172 | 124 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.38 | 0 | 192.83 | 7.38 | 185.45
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 98 | 70 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.94 | 0 | 192.83 | 9.94 | 182.89
| 2024-05-31 | Underserved Community | CAPISTRANO BEACH | N/A | Not Available | 36 | 26 | N/A | 2025-01-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.32 | 0 | 105.72 | 12.32 | 93.4
| 2026-03-14 | Underserved Community | ESCONDIDO | N/A | Not Available | 78 | 56 | N/A | 2024-07-01 | Not Available | Not Available | Not Available | -14.47 | Unknown | -3.33 | 0 | 117.7 | -17.8 | 135.5
| 2023-12-27 | N/A | DANA POINT | N/A | Not Available | 238 | 170 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -16.09 | Unknown | -6.09 | 0 | 67.06 | -22.18 | 89.24
| 2021-11-19 | Underserved Community | ESCONDIDO | N/A | Not Available | 276 | 197 | N/A | 2024-02-20 | Not Available | Not Available | Not Available | -11.11 | -851 | 16.07 | 0 | 850.97 | -846.04 | 1697.01
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 106 | 76 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.66 | 0 | 192.83 | 3.66 | 189.17
| 2025-02-15 | Underserved Community | FALLBROOK | N/A | Not Available | 96 | 68 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -4.96 | Unknown | -1.9 | 0 | 594.91 | -6.86 | 601.77
| 2025-12-21 | N/A | RANCHO SANTA FE | N/A | Not Available | 75 | 53 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.03 | 0 | 192.83 | 7.03 | 185.8
| 2025-01-20 | N/A | ESCONDIDO | N/A | Not Available | 122 | 88 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -11.47 | Unknown | -4.37 | 0 | 153.75 | -15.84 | 169.59
| 2026-09-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 109.65 | 0 | 3613.34 | 109.65 | 3503.69
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 67 | 49 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | -3.63 | Unknown | -0.58 | 0 | 192.83 | -4.21 | 197.04
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 121 | 87 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.92 | 0 | 192.83 | 6.92 | 185.91
| 2025-05-25 | N/A | SAN DIEGO | N/A | Not Available | 240 | 172 | N/A | 2023-09-14 | Not Available | Not Available | Not Available | -4.96 | Unknown | 27.38 | 0 | 153.83 | 22.42 | 131.41
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 64 | 46 | N/A | 2024-07-08 | Not Available | Not Available | Not Available | -6.75 | Unknown | -1.07 | 0 | 283.36 | -7.82 | 291.18
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 73 | 53 | N/A | 2024-07-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.96 | 0 | 192.83 | 2.96 | 189.87
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 67 | 49 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | -8.05 | Unknown | -1.28 | 0 | 192.83 | -9.33 | 202.16
| 2027-03-18 | N/A | SAN DIEGO | N/A | Not Available | 32 | 22 | N/A | 2025-05-02 | Not Available | Not Available | Not Available | -8.08 | Unknown | 402.32 | 0 | 118.25 | 394.24 | -275.99
| 2026-02-06 | N/A | SAN DIEGO | N/A | Not Available | 282 | 202 | N/A | 2024-10-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.41 | 3981 | 163.83 | 1.41 | 162.42
| 2025-03-18 | N/A | SAN DIEGO | N/A | Not Available | 17 | 13 | N/A | 2024-03-29 | Not Available | Not Available | Not Available | -6 | Unknown | 1.06 | 0 | 163.83 | -4.94 | 168.77
| 2026-04-23 | N/A | SAN DIEGO | N/A | Not Available | 126 | 90 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.51 | 0 | 192.95 | -0.51 | 193.46
| 2025-08-20 | N/A | SAN DIEGO | N/A | Not Available | 121 | 87 | N/A | 2023-12-15 | Not Available | Not Available | Not Available | -4.45 | Unknown | -0.27 | 3981 | 153.83 | -4.72 | 158.55
| 2026-12-31 | N/A | SAN DIEGO | N/A | Not Available | 109 | 77 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | Unknown | 1.71 | 1.3 | 0 | 196.44 | 3.01 | 193.43
| 2026-06-05 | N/A | SAN DIEGO | N/A | Not Available | 261 | 187 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.57 | 0 | 192.95 | 8.57 | 184.38
| 2025-12-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 50 | 36 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 80.4 | 0 | 3232.48 | 80.4 | 3152.08
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 165 | 119 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.06 | 0 | 207.92 | 7.06 | 200.86
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 351 | 251 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.55 | 0 | 192.83 | 5.55 | 187.28
| 2025-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 125 | 89 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 585.18 | 3981 | 196.69 | 585.18 | -388.49
| 2025-10-30 | Underserved Community | SAN MARCOS | N/A | Not Available | 156 | 112 | N/A | 2023-03-07 | Not Available | Not Available | Not Available | -9.76 | Unknown | -2.22 | 0 | 98.41 | -11.98 | 110.39
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 72 | 52 | N/A | 2024-07-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.52 | 0 | 283.36 | 3.52 | 279.84
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 121 | 87 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.12 | 0 | 180.09 | 5.12 | 174.97
| 2026-07-10 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 118 | 84 | N/A | 2024-09-13 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.35 | 0 | 192.95 | -0.35 | 193.3
| 2024-04-12 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 72 | 52 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 632.98 | 0 | 619.73 | 632.98 | -13.25
| 2026-03-14 | N/A | SOLANA BEACH | N/A | Not Available | 69 | 49 | N/A | 2024-05-24 | Not Available | Not Available | Not Available | 486.17 | Unknown | 339.53 | 0 | 162.34 | 851.79 | -689.45
| 2027-02-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.2 | 0 | 196.44 | 14.2 | 182.24
| 2024-03-23 | N/A | SAN CLEMENTE | N/A | Not Available | 70 | 50 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1116.75 | 0 | 495.75 | 1116.75 | -621
| 2025-11-06 | Underserved Community | LA MESA | N/A | Not Available | 114 | 82 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.1 | 0 | 105.08 | 9.1 | 95.98
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 135 | 97 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.69 | 0 | 192.83 | 2.69 | 190.14
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 101 | 73 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.94 | 0 | 162.34 | 8.94 | 153.4
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 176 | 126 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.7 | 0 | 748.15 | 9.7 | 738.45
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 135 | 97 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.64 | 0 | 192.83 | 6.64 | 186.19
| 2023-09-30 | N/A | DANA POINT | N/A | Not Available | 107 | 77 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 664.74 | 0 | 111.03 | 664.74 | -553.71
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 72 | 52 | N/A | 2024-07-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.34 | 0 | 283.36 | 7.34 | 276.02
| 2024-02-16 | Underserved Community | FALLBROOK | N/A | Not Available | 148 | 106 | N/A | 2023-06-02 | Not Available | Not Available | Not Available | -4.45 | Unknown | -1.68 | 0 | 594.91 | -6.13 | 601.04
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 122 | 88 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.34 | 0 | 192.83 | 11.34 | 181.49
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 218 | 156 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.49 | 0 | 192.83 | 10.49 | 182.34
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | 166 | 118 | N/A | 2024-08-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.19 | 0 | 645.75 | 9.19 | 636.56
| 2026-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | 214 | 154 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.52 | 0 | 1050.75 | 6.52 | 1044.23
| 2025-11-06 | Underserved Community | LA MESA | N/A | Not Available | 120 | 86 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | 439.29 | Unknown | 579.9 | 0 | 105.08 | 1019.19 | -914.11
| 2025-12-21 | Underserved Community | ESCONDIDO | N/A | Not Available | 58 | 42 | N/A | 2024-04-29 | Not Available | Not Available | Not Available | -16.44 | Unknown | -16.44 | 0 | 153.26 | -32.88 | 186.14
| 2025-01-04 | Underserved Community | BONSALL | N/A | Not Available | 85 | 61 | N/A | 2023-03-29 | Not Available | Not Available | Not Available | -7 | Unknown | -2.66 | 0 | 436.48 | -9.66 | 446.14
| 2025-09-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 308 | 220 | N/A | 2024-10-09 | Not Available | Not Available | Not Available | Unknown | 58.49 | 598.7 | 0 | 714.51 | 657.19 | 57.32
| 2023-08-02 | Underserved Community | OCEANSIDE | N/A | Not Available | 172 | 124 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | 285.38 | Unknown | 141.57 | 0 | 1623.84 | 426.95 | 1196.89
| 2025-12-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 48 | 34 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.62 | 0 | 197.01 | 10.62 | 186.39
| 2026-08-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 63 | 45 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 590.55 | 0 | 197.01 | 590.55 | -393.54
| 2026-05-27 | N/A | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A | 2024-08-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.53 | 0 | 192.51 | 9.53 | 182.98
| 2024-09-30 | Underserved Community | BONSALL | N/A | Not Available | 54 | 40 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 65 | 0 | 142.83 | 65 | 77.83
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 116 | 84 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.38 | 0 | 192.83 | 4.38 | 188.45
| 2025-03-24 | N/A | SAN DIEGO | N/A | Not Available | 580 | 414 | N/A | 2024-12-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.67 | 0 | 153.75 | 7.67 | 146.08
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 67 | 49 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | -8.04 | Unknown | -1.29 | 0 | 180.38 | -9.33 | 189.71
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 135 | 97 | N/A | 2024-09-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.16 | 0 | 180.38 | 11.16 | 169.22
| 2026-07-29 | N/A | SAN DIEGO | N/A | Not Available | 281 | 201 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.65 | 0 | 192.95 | 1.65 | 191.3
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 80 | 58 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.8 | 0 | 180.38 | 6.8 | 173.58
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 98 | 70 | N/A | 2024-08-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 3 | 0 | 192.83 | 3 | 189.83
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 106 | 76 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 14.49 | 0 | 192.83 | 14.49 | 178.34
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 78 | 56 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.64 | 0 | 283.36 | 1.64 | 281.72
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 766 | 548 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.59 | 0 | 239.45 | 9.59 | 229.86
| 2025-03-14 | N/A | SAN CLEMENTE | N/A | Not Available | 96 | 68 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | 144.08 | Unknown | 113.71 | 0 | 197.01 | 257.79 | -60.78
| 2026-09-06 | N/A | SAN DIEGO | N/A | Not Available | 268 | 192 | N/A | 2025-06-02 | Not Available | Not Available | Not Available | Unknown | 13.39 | 2218.03 | 0 | 118.25 | 2231.42 | -2113.17
| 2026-08-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 115 | 83 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.7 | 0 | 283.53 | 4.7 | 278.83
| 2025-03-28 | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Not Available | 43 | 31 | N/A | 2023-11-02 | Not Available | Not Available | Not Available | -11.62 | Unknown | -0.15 | 0 | 153.22 | -11.77 | 164.99
| 2027-01-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | -7.04 | Unknown | 348.21 | 0 | 1063.64 | 341.17 | 722.47
| 2025-06-04 | Underserved Community | FALLBROOK | N/A | Not Available | 175 | 125 | N/A | 2023-12-07 | Not Available | Not Available | Not Available | -10.57 | Unknown | 0.78 | 3981 | 158.51 | -9.79 | 168.3
| 2025-06-27 | Underserved Community | PAUMA VALLEY | N/A | Not Available | 233 | 167 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | 285.38 | Unknown | 1575.29 | 0 | 655.07 | 1880.69 | -1225.62
| 2024-09-21 | Underserved Community | OCEANSIDE | N/A | Not Available | 206 | 148 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -16.48 | -164 | -3.82 | 0 | 163.83 | -184.3 | 348.13
| 2023-11-10 | N/A | SAN CLEMENTE | N/A | Not Available | 167 | 119 | N/A | 2023-07-21 | Not Available | Not Available | Not Available | -9.95 | Unknown | -3.79 | 0 | 495.75 | -13.74 | 509.49
| 2024-02-24 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 131 | 93 | N/A | 2023-05-25 | Not Available | Not Available | Not Available | -7.5 | Unknown | -2.85 | 0 | 166.47 | -10.35 | 176.82
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 79 | 57 | N/A | 2024-07-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.88 | 0 | 192.83 | 1.88 | 190.95
| 2025-09-18 | N/A | SAN DIEGO | N/A | Not Available | 422 | 302 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | 13.4 | -90.94 | 0 | 197.01 | -77.54 | 274.55
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 116 | 84 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.64 | 0 | 180.38 | 4.64 | 175.74
| 2025-10-17 | Underserved Community | VISTA | N/A | Not Available | 45 | 33 | N/A | 2024-01-10 | Not Available | Not Available | Not Available | -7.65 | Unknown | 59.91 | 0 | 483.59 | 52.26 | 431.33
| 2025-03-20 | Underserved Community | JULIAN | N/A | Not Available | 15 | 11 | N/A | 2023-05-31 | Not Available | Not Available | Not Available | 232.94 | Unknown | 153.31 | 0 | 495.75 | 537.03 | -41.28
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 94 | 68 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.16 | 0 | 192.83 | 4.16 | 188.67
| 2024-09-29 | N/A | CARLSBAD | N/A | Not Available | 360 | 258 | N/A | 2024-09-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.21 | 0 | 1387.03 | 7.21 | 1379.82
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 172 | 124 | N/A | 2024-10-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.56 | 0 | 192.83 | 5.56 | 187.27
| 2025-11-09 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 86 | 62 | N/A | 2023-06-21 | Not Available | Not Available | Not Available | 249.03 | Unknown | 440.38 | 0 | 499.96 | 731.01 | -231.05
| 2027-02-05 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.86 | 0 | 196.59 | 1.86 | 194.73
| 2025-12-29 | Underserved Community | BONITA | N/A | Not Available | 156 | 112 | N/A | 2024-05-06 | Not Available | Not Available | Not Available | 368.45 | Unknown | 162.75 | 0 | 153.49 | 531.2 | -377.71
| 2026-04-02 | Underserved Community | ESCONDIDO | N/A | Not Available | 214 | 152 | N/A |  | Not Available | Not Available | Not Available | 502.72 | Unknown | 2296.26 | 0 | 192.83 | 2937.49 | -2744.66
| 2026-05-09 | N/A | SAN DIEGO | N/A | Not Available | 205 | 147 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.68 | 0 | 192.51 | 7.68 | 184.83
| 2024-06-21 | N/A | SAN CLEMENTE | N/A | Not Available | 137 | 97 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 492.09 | 0 | 620.49 | 492.09 | 128.4
| 2025-08-07 | N/A | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.3 | 0 | 192.83 | 6.3 | 186.53
| 2026-11-20 | N/A | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 197.01 | 4.39 | 192.62
| 2026-02-28 | N/A | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2024-08-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.1 | 0 | 192.51 | 5.1 | 187.41
| 2024-01-02 | N/A | MISSION VIEJO | N/A | Not Available | 140 | 100 | N/A | 2023-05-29 | Not Available | Not Available | Not Available | 170.25 | Unknown | 620.03 | 0 | 110.98 | 947.2 | -836.22
| 2025-02-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 113 | 81 | N/A | 2023-04-24 | Not Available | Not Available | Not Available | -5.06 | Unknown | -1.94 | 0 | 599.97 | -7 | 606.97
| 2023-06-23 | N/A | ESCONDIDO | N/A | Not Available | 251 | 179 | N/A | 2024-06-25 | Not Available | Not Available | Not Available | -13.58 | 10.92 | 1446.9 | 0 | 721.76 | 1444.24 | -722.48
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | 233 | 167 | N/A | 2023-08-08 | Not Available | Not Available | Not Available | 4.62 | Unknown | 143.6 | 0 | 330.53 | 148.22 | 182.31
| 2023-05-31 | N/A | DANA POINT | N/A | Not Available | 233 | 167 | N/A | 2023-10-23 | Not Available | Not Available | Not Available | -8.57 | Unknown | -2.77 | 0 | 158.51 | -11.34 | 169.85
| 2024-12-04 | N/A | SOLANA BEACH | N/A | Not Available | 448 | 320 | N/A | 2024-05-29 | Not Available | Not Available | Not Available | -14.49 | Unknown | 1839.48 | 0 | 98.41 | 1824.99 | -1726.58
| 2023-06-23 | N/A | SD 1169-D1 | N/A | Not Available | 392 | 280 | N/A | 2025-04-21 | Not Available | Not Available | Not Available | 82.69 | Unknown | 69.48 | 0 | 2062.07 | 152.17 | 1909.9
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 221 | 157 | N/A | 2023-08-07 | Not Available | Not Available | Not Available | -12.18 | Unknown | -4.66 | 0 | 154.79 | -16.84 | 171.63
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 64 | 46 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | -7.66 | Unknown | -1.2 | 0 | 283.36 | -8.86 | 292.22
| 2024-02-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 112 | 80 | N/A | 2023-04-26 | Not Available | Not Available | Not Available | -9.68 | Unknown | -3.68 | 0 | 341 | -13.36 | 354.36
| 2022-02-22 | Underserved Community | RAMONA | N/A | Not Available | 138 | 100 | N/A | 2023-07-14 | Not Available | Not Available | Not Available | -42.2 | Unknown | -16.12 | 0 | 100.58 | -58.32 | 158.9
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 217 | 155 | N/A | 2023-07-24 | Not Available | Not Available | Not Available | -16.72 | Unknown | -6.4 | 0 | 154.79 | -23.12 | 177.91
| 2022-05-03 | Underserved Community | JULIAN | N/A | Not Available | 587 | 419 | N/A |  | Not Available | Not Available | Not Available | 1018.8 | Unknown | 854.57 | 0 | 98.32 | 4277.89 | -4179.57
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 67 | 49 | N/A | 2024-07-16 | Not Available | Not Available | Not Available | -6.39 | Unknown | -1.02 | 0 | 192.83 | -7.41 | 200.24
| 2027-01-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 43 | 31 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | -30 | Unknown | -14.54 | 0 | 196.44 | -44.54 | 240.98
| 2026-09-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 149 | 107 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | -16.8 | Unknown | 839.5 | 0 | 288.94 | 822.7 | -533.76
| 2025-07-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 123 | 89 | N/A |  | Not Available | Not Available | Not Available | 305.88 | Unknown | 166.07 | 0 | 152.86 | 513.28 | -360.42
| 2026-09-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 195 | 139 | N/A |  | Not Available | Not Available | Not Available | 1469.7 | Unknown | 991.33 | 0 | 450.11 | 2771.67 | -2321.56
| 2024-08-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 177 | 127 | N/A | 2023-07-21 | Not Available | Not Available | Not Available | -13.68 | 41.36 | 1751.57 | 3981 | 520 | 1779.25 | -1259.25
| 2026-03-24 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 45 | 33 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | 129 | Unknown | 188.21 | 0 | 142.38 | 317.21 | -174.83
| 2024-10-26 | Underserved Community | SAN MARCOS | N/A | Not Available | 142 | 102 | N/A | 2023-03-22 | Not Available | Not Available | Not Available | -11.38 | Unknown | -1.56 | 0 | 98.41 | -12.94 | 111.35
| 2025-11-02 | N/A | SAN DIEGO | N/A | Not Available | 224 | 160 | N/A | 2024-07-03 | Not Available | Not Available | Not Available | -50.56 | Unknown | 1715.32 | 3981 | 744.3 | 1664.76 | -920.46
| 2024-02-23 | N/A | LAGUNA NIGUEL | N/A | Not Available | 412 | 294 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | -5.47 | Unknown | -1.27 | 0 | 110.98 | -6.74 | 117.72
| 2025-12-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A |  | Not Available | Not Available | Not Available | 344.6 | Unknown | 169.36 | 0 | 98.41 | 513.96 | -415.55
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 78 | 56 | N/A | 2024-07-29 | Not Available | Not Available | Not Available | -136.6 | Unknown | -78.31 | 0 | 283.36 | -214.91 | 498.27
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 64 | 46 | N/A | 2024-07-10 | Not Available | Not Available | Not Available | -9.13 | Unknown | -1.46 | 0 | 192.83 | -10.59 | 203.42
| 2026-09-23 | Underserved Community | MOUNT LAGUNA | N/A | Not Available | 49 | 35 | N/A |  | Not Available | Not Available | Not Available | 769.68 | Unknown | 461 | 0 | 1066.55 | 1280.61 | -214.06
| 2025-03-14 | N/A | CORONADO | N/A | Not Available | 280 | 200 | N/A | 2024-06-07 | Not Available | Not Available | Not Available | -12.08 | 57.05 | 1050.85 | 0 | 665.42 | 1095.82 | -430.4
| 2024-08-28 | N/A | DANA POINT | N/A | Not Available | 22 | 16 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | 633.37 | Unknown | 399.28 | 0 | 111.03 | 1185.02 | -1073.99
| 2025-10-30 | N/A | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -4.73 | Unknown | 0.21 | 0 | 163.83 | -4.52 | 168.35
| 2026-03-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 263 | 189 | N/A |  | Not Available | Not Available | Not Available | 602.63 | Unknown | 398.29 | 0 | 1050.75 | 1000.92 | 49.83
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 64 | 46 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | -8.95 | Unknown | -1.41 | 0 | 192.83 | -10.36 | 203.19
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 321 | 229 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | -16.12 | Unknown | 135.48 | 0 | 239.23 | 119.36 | 119.87
| 2024-11-30 | Underserved Community | POWAY | N/A | Not Available | 53 | 39 | N/A | 2024-02-13 | Not Available | Not Available | Not Available | -34.32 | Unknown | -34.38 | 0 | 85.4 | -68.7 | 154.1
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 263 | 189 | N/A | 2024-03-12 | Not Available | Not Available | Not Available | -19.44 | Unknown | 440.82 | 0 | 1456.82 | 421.38 | 1035.44
| 2025-02-22 | Underserved Community | FALLBROOK | N/A | Not Available | 121 | 87 | N/A | 2023-05-11 | Not Available | Not Available | Not Available | -17.36 | Unknown | -6.59 | 0 | 594.91 | -23.95 | 618.86
| 2024-04-16 | Underserved Community | RAMONA | N/A | Not Available | 7 | 5 | N/A |  | Not Available | Not Available | Not Available | 1451.68 | Unknown | 935.69 | 0 | 364.52 | 3347.29 | -2982.77
| 2026-03-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 41 | 29 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -11.88 | Unknown | -2.74 | 0 | 163.83 | -14.62 | 178.45
| 2025-07-21 | N/A | SAN DIEGO | N/A | Not Available | 112 | 80 | N/A |  | Not Available | Not Available | Not Available | -8.6 | Unknown | -2.78 | 0 | 154.99 | -11.38 | 166.37
| 2025-06-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 115 | 83 | N/A | 2023-10-30 | Not Available | Not Available | Not Available | 612.25 | Unknown | 338.92 | 0 | 148.7 | 951.17 | -802.47
| 2026-06-04 | N/A | SAN DIEGO | N/A | Not Available | 344 | 246 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | -1.57 | Unknown | 77.28 | 0 | 192.95 | 75.71 | 117.24
| 2023-10-31 | N/A | DANA POINT | N/A | Not Available | 233 | 167 | N/A | 2023-06-19 | Not Available | Not Available | Not Available | 1848.98 | Unknown | 1102.73 | 3981 | 98.41 | 3128.51 | -3030.1
| 2024-09-25 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 274 | 196 | N/A | 2024-07-02 | Not Available | Not Available | Not Available | 286.36 | Unknown | 184.8 | 0 | 147.93 | 513.78 | -365.85
| 2024-10-18 | N/A | RAMONA | N/A | Not Available | 500 | 358 | N/A |  | Not Available | Not Available | Not Available | 748.36 | 20.11 | 680.82 | 0 | 144.8 | 1538.65 | -1393.85
| 2024-02-06 | N/A | SAN CLEMENTE | N/A | Not Available | 157 | 113 | N/A | 2023-06-30 | Not Available | Not Available | Not Available | -6.52 | Unknown | -2.5 | 0 | 110.98 | -9.02 | 120
| 2024-01-30 | N/A | COTO DE CAZA | N/A | Not Available | 385 | 275 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | -9.5 | Unknown | -3.62 | 0 | 67.06 | -13.12 | 80.18
| 2026-10-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | -4.5 | Unknown | 224.69 | 0 | 197.01 | 220.19 | -23.18
| 2026-09-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 184 | 132 | N/A |  | Not Available | Not Available | Not Available | 314.2 | Unknown | 219.05 | 0 | 142.83 | 583.96 | -441.13
| 2025-07-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 131 | 93 | N/A | 2023-11-09 | Not Available | Not Available | Not Available | -9.19 | Unknown | -2.95 | 0 | 158.51 | -12.14 | 170.65
| 2023-12-01 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 149 | 107 | N/A | 2023-06-15 | Not Available | Not Available | Not Available | -13.97 | Unknown | 80.65 | 0 | 110.98 | 66.68 | 44.3
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | 429 | 307 | N/A | 2024-04-01 | Not Available | Not Available | Not Available | -23.62 | 35.75 | 2103.47 | 0 | 599.96 | 2115.6 | -1515.64
| 2024-12-20 | Underserved Community | SAN MARCOS | N/A | Not Available | 171 | 123 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | -8.71 | Unknown | -2.12 | 0 | 154.79 | -10.83 | 165.62
| 2024-01-18 | Underserved Community | ESCONDIDO | N/A | Not Available | 142 | 102 | N/A | 2023-07-06 | Not Available | Not Available | Not Available | -4.98 | Unknown | 0.01 | 3981 | 197.9 | -4.97 | 202.87
| 2024-05-15 | N/A | SAN CLEMENTE | N/A | Not Available | 230 | 164 | N/A | 2023-07-20 | Not Available | Not Available | Not Available | -5.65 | Unknown | -2.15 | 0 | 111.06 | -7.8 | 118.86
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 67 | 49 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | -4.91 | Unknown | -0.8 | 0 | 192.83 | -5.71 | 198.54
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 323 | 231 | N/A | 2023-09-11 | Not Available | Not Available | Not Available | -18.6 | Unknown | -7.04 | 0 | 239.45 | -25.64 | 265.09
| 2025-04-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 202 | 144 | N/A | 2024-03-13 | Not Available | Not Available | Not Available | -9.65 | Unknown | -2.25 | 0 | 513.5 | -11.9 | 525.4
| 2025-09-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A |  | Not Available | Not Available | Not Available | 349.42 | Unknown | 193.63 | 0 | 158.37 | 543.05 | -384.68
| 2025-08-08 | Underserved Community | CHULA VISTA | N/A | Not Available | 323 | 231 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | -2.2 | Unknown | 117.75 | 0 | 153.49 | 115.55 | 37.94
| 2025-03-13 | N/A | SAN DIEGO | N/A | Not Available | 317 | 227 | N/A | 2024-01-26 | Not Available | Not Available | Not Available | -10.54 | Unknown | -1.3 | 0 | 153.83 | -11.84 | 165.67
| 2023-06-23 | Underserved Community | EL CAJON | N/A | Not Available | 151 | 109 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | 63.28 | Unknown | 64.37 | 0 | 163.83 | 127.65 | 36.18
| 2019-03-30 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 53 | 39 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | -13.77 | Unknown | 778.48 | 0 | 4457.15 | 764.71 | 3692.44
| 2023-08-29 | Underserved Community | La Mesa | N/A | Not Available | 208 | 150 | N/A | 2023-06-26 | Not Available | Not Available | Not Available | -33.41 | Unknown | 1349.2 | 0 | 95.13 | 1315.79 | -1220.66
| 2025-05-22 | Underserved Community | SAN DIEGO | N/A | Not Available | 259 | 185 | N/A | 2025-05-01 | Not Available | Not Available | Not Available | -67.88 | Unknown | 3356.53 | 0 | 1050.75 | 3288.65 | -2237.9
| 2025-11-25 | Underserved Community | EL CAJON | N/A | Not Available | 113 | 81 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | -3.31 | 0 | 999.88 | -3.31 | 1003.19
| 2026-01-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 101 | 73 | N/A | 2025-05-13 | Not Available | Not Available | Not Available | 70.66 | Unknown | 574.32 | 0 | 1330.58 | 644.98 | 685.6
| 2025-08-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 229 | 163 | N/A | 2025-04-28 | Not Available | Not Available | Not Available | 74.05 | -289 | 542.32 | 0 | 288.94 | 327.37 | -38.43
| 2025-03-05 | N/A | SAN DIEGO | N/A | Not Available | 166 | 118 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.61 | 0 | 105.72 | 2.61 | 103.11
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 82 | 60 | N/A | 2024-09-05 | Not Available | Not Available | Not Available | -23.33 | Unknown | 1257.7 | 0 | 3199.34 | 1234.37 | 1964.97
| 2020-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 114 | 82 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | -22.15 | Unknown | 1213.4 | 0 | 3454.1 | 1191.25 | 2262.85
| 2025-03-01 | Underserved Community | BONITA | N/A | Not Available | 329 | 235 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | -25.84 | -306.29 | 1328.85 | 0 | 877.61 | 996.72 | -119.11
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 65 | 47 | N/A | 2025-04-14 | Not Available | Not Available | Not Available | -52.76 | Unknown | 1391.63 | 0 | 4593.98 | 1338.87 | 3255.11
| 2022-02-13 | N/A |  | N/A | Not Available | 357 | 255 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | -20.4 | 13.52 | 1319.27 | 0 | 2119.64 | 1312.39 | 807.25
| 2025-05-02 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 69 | 49 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 102.37 | 0 | 102.37
| 2025-01-11 | Underserved Community | OCEANSIDE | N/A | Not Available | 175 | 125 | N/A | 2023-05-15 | Not Available | Not Available | Not Available | -19.93 | Unknown | 576.07 | 0 | 98.41 | 556.14 | -457.73
| 2022-02-13 | N/A |  | N/A | Not Available | 235 | 169 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | -4.7 | Unknown | 244.03 | 0 | 253.53 | 239.33 | 14.2
| 2025-03-05 | N/A | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | -12.51 | Unknown | 685.21 | 0 | 197.01 | 672.7 | -475.69
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 72 | 52 | N/A | 2025-04-07 | Not Available | Not Available | Not Available | -9.76 | Unknown | 865.44 | 0 | 4733.36 | 855.68 | 3877.68
| 2023-02-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 354 | 254 | N/A | 2024-10-03 | Not Available | Not Available | Not Available | 1397.89 | Unknown | 2150.03 | 0 | 721.94 | 3547.92 | -2825.98
| 2026-01-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | -54.47 | -1331 | 555.89 | 0 | 1330.58 | -829.58 | 2160.16
| 2025-03-30 | Underserved Community | CHULA VISTA | N/A | Not Available | 62 | 44 | N/A | 2024-04-15 | Not Available | Not Available | Not Available | -14.93 | Unknown | -3.47 | 0 | 499.18 | -18.4 | 517.58
| 2023-06-23 | N/A | DEL MAR | N/A | Not Available | 62 | 44 | N/A | 2025-06-30 | Not Available | Not Available | Not Available | Unknown | -3282 | 719.8 | 0 | 3282.48 | -2562.2 | 5844.68
| 2026-02-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 195 | 139 | N/A | 2025-06-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.88 | 0 | 999.91 | 7.88 | 992.03
| 2026-08-19 | N/A | MISSION VIEJO | N/A | Not Available | 45 | 33 | N/A | 2025-05-22 | Not Available | Not Available | Not Available | -25.84 | Unknown | 3083.71 | 0 | 102.37 | 3057.87 | -2955.5
| 2025-10-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 147 | 105 | N/A | 2025-04-02 | Not Available | Not Available | Not Available | -80.42 | Unknown | 1012.61 | 0 | 1930.86 | 932.19 | 998.67
| 2026-06-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2025-06-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 791.01 | 0 | 118.25 | 791.01 | -672.76
| 2024-05-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 652.52 | 0 | 997.93 | 652.52 | 345.41
| 2019-03-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 113 | 81 | N/A | 2025-02-04 | Not Available | Not Available | Not Available | -14.79 | Unknown | 749.5 | 0 | 2660.35 | 734.71 | 1925.64
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | -30.52 | Unknown | 1525.64 | 0 | 3438.39 | 1495.12 | 1943.27
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | 415 | 297 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | -5.1 | Unknown | 275.05 | 0 | 445.48 | 269.95 | 175.53
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | 368 | 264 | N/A | 2024-03-14 | Not Available | Not Available | Not Available | -31.14 | Unknown | -32.34 | 0 | 566.12 | -63.48 | 629.6
| 2026-12-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A | 2025-03-11 | Not Available | Not Available | Not Available | -16.77 | Unknown | 804.8 | 0 | 1066.55 | 788.03 | 278.52
| 2020-12-31 | N/A | SAN DIEGO | N/A | Not Available | 219 | 157 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | -41.76 | Unknown | 2188.35 | 0 | 2452.15 | 2146.59 | 305.56
| 2027-01-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2025-05-08 | Not Available | Not Available | Not Available | 73.32 | Unknown | 1223.43 | 0 | 1328.9 | 1296.75 | 32.15
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | 238 | 170 | N/A | 2024-06-03 | Not Available | Not Available | Not Available | -18.27 | 25.18 | 1115.86 | 0 | 2376.82 | 1122.77 | 1254.05
| 2026-08-27 | N/A | OCEANSIDE | N/A | Not Available | 112 | 80 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | 1181.66 | Unknown | 3274.38 | 0 | 197.01 | 4860.76 | -4663.75
| 2025-05-21 | N/A | SAN DIEGO | N/A | Not Available | 281 | 201 | N/A |  | Not Available | Not Available | Not Available | -6.93 | Unknown | 342.63 | 0 | 1050.75 | 335.7 | 715.05
| 2027-03-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 5.56 | 0 | 79.48 | 5.56 | 73.92
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | 387 | 277 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | -12.25 | 8.58 | 1679.5 | 0 | 1071.67 | 1675.83 | -604.16
| 2020-12-31 | N/A | DEL MAR | N/A | Not Available | 121 | 87 | N/A | 2024-04-17 | Not Available | Not Available | Not Available | -18.71 | Unknown | 39.77 | 0 | 2447.55 | 21.06 | 2426.49
| 2024-04-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 137 | 99 | N/A | 2023-12-20 | Not Available | Not Available | Not Available | -23.79 | Unknown | -27.36 | 0 | 481.24 | -51.15 | 532.39
| 2026-02-18 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | 85 | 61 | N/A |  | Not Available | Not Available | Not Available | Unknown | -279 | 812.28 | 0 | 278.69 | 533.28 | -254.59
| 2020-12-31 | N/A | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | -0.62 | Unknown | 89.16 | 0 | 3213.99 | 88.54 | 3125.45
| 2025-02-28 | N/A | CORONADO | N/A | Not Available | 71 | 51 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.54 | 0 | 985.1 | -0.54 | 985.64
| 2025-02-28 | N/A | CORONADO | N/A | Not Available | 73 | 53 | N/A | 2024-11-14 | Not Available | Not Available | Not Available | -9.18 | Unknown | -9.18 | 0 | 985.1 | -18.36 | 1003.46
| 2023-06-23 | N/A | VC 1070-H1 | N/A | Not Available | 338 | 242 | N/A |  | Not Available | Not Available | Not Available | 1110.94 | Unknown | 4490.89 | 0 | 306.85 | 5601.83 | -5294.98
| 2025-12-30 | Underserved Community | EL CAJON | N/A | Not Available | 113 | 81 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.49 | 0 | 1596.68 | 10.49 | 1586.19
| 2018-08-30 | Underserved Community | SAN DIEGO | N/A | Not Available | 109 | 79 | N/A | 2024-03-12 | Not Available | Not Available | Not Available | -35.75 | Unknown | 1620.83 | 0 | 1865.12 | 1585.08 | 280.04
| 2020-12-31 | N/A | SAN DIEGO | N/A | Not Available | 184 | 132 | N/A | 2023-04-25 | Not Available | Not Available | Not Available | -6.02 | Unknown | 29.14 | 0 | 545.68 | 23.12 | 522.56
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | 715 | 511 | N/A | 2025-06-18 | Not Available | Not Available | Not Available | -9.16 | 20.47 | 3123.69 | 0 | 1145.65 | 3135 | -1989.35
| 2023-06-23 | N/A | OCEANSIDE | N/A | Not Available | 82 | 60 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 1089.83 | 0 | 661.08 | 1089.83 | -428.75
| 2022-12-01 | Underserved Community | OCEANSIDE | N/A | Not Available | 162 | 116 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 167.77 | Unknown | Unknown
| 2024-08-09 | Underserved Community | VISTA | N/A | Not Available | 189 | 135 | N/A | 2024-05-07 | Not Available | Not Available | Not Available | -24.43 | Unknown | -24.7 | 0 | 158.14 | -49.13 | 207.27
| 2026-09-16 | Underserved Community | SANTEE | N/A | Not Available | 49 | 35 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | 1.3 | 444.68 | 0 | 352.95 | 445.98 | -93.03
| 2023-06-12 | Underserved Community | OCEANSIDE | N/A | Not Available | 306 | 218 | N/A | 2025-03-07 | Not Available | Not Available | Not Available | 852.05 | 0.83 | 3945.54 | 0 | 1860.6 | 4961.37 | -3100.77
| 2025-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 76 | 54 | N/A | 2025-05-28 | Not Available | Not Available | Not Available | -7.75 | Unknown | 382.98 | 0 | 1063.08 | 375.23 | 687.85
| 2025-11-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 153 | 109 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | 544.49 | Unknown | 1955.36 | 0 | 197.01 | 2543.9 | -2346.89
| 2025-09-07 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 70 | 50 | N/A | 2024-06-19 | Not Available | Not Available | Not Available | -11.29 | Unknown | -2.6 | 0 | 496.14 | -13.89 | 510.03
| 2025-04-30 | N/A | CORONADO | N/A | Not Available | 252 | 180 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | -0.63 | Unknown | 44.46 | 0 | 999.88 | 43.83 | 956.05
| 2025-10-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 59 | 43 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | -20.19 | Unknown | 1000.75 | 0 | 1593.32 | 980.56 | 612.76
| 2025-04-04 | N/A | SAN DIEGO | N/A | Not Available | 167 | 119 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | -14.08 | Unknown | 702.2 | 0 | 955.23 | 688.12 | 267.11
| 2027-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-05-12 | Not Available | Not Available | Not Available | -8.24 | Unknown | 407.5 | 0 | 465.64 | 399.26 | 66.38
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 88 | 64 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.2 | 0 | 192.83 | 5.2 | 187.63
| 2027-01-09 | Underserved Community | EL CAJON | N/A | Not Available | 112 | 80 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | -20.4 | Unknown | 1008.93 | 0 | 1030.1 | 988.53 | 41.57
| 2025-10-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 181 | 129 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -24.69 | Unknown | 635.25 | 0 | 483.59 | 610.56 | -126.97
| 2025-02-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 328 | 234 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | -0.31 | Unknown | 528.64 | 0 | 1050.75 | 528.33 | 522.42
| 2022-06-30 | Underserved Community | OCEANSIDE | N/A | Not Available | 260 | 186 | N/A | 2023-09-18 | Not Available | Not Available | Not Available | -28.2 | -782.7 | 13.83 | 3981 | 799.62 | -797.07 | 1596.69
| 2025-07-17 | Underserved Community | OCEANSIDE | N/A | Not Available | 87 | 63 | N/A | 2024-01-31 | Not Available | Not Available | Not Available | -12.4 | Unknown | -3.04 | 0 | 551.31 | -15.44 | 566.75
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 98 | 70 | N/A | 2024-08-16 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.88 | 0 | 192.83 | 8.88 | 183.95
| 2025-09-27 | N/A | CARDIFF | N/A | Not Available | 131 | 95 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.81 | 3981 | 1050.75 | 5.81 | 1044.94
| 2024-11-06 | Underserved Community | SPRING VALLEY | N/A | Not Available | 45 | 33 | N/A | 2023-12-20 | Not Available | Not Available | Not Available | -51.43 | Unknown | 1596.75 | 0 | 499.18 | 1545.32 | -1046.14
| 2025-09-11 | Underserved Community | EL CAJON | N/A | Not Available | 73 | 53 | N/A | 2025-01-15 | Not Available | Not Available | Not Available | -15.56 | Unknown | -802.7 | 0 | 105.08 | -818.26 | 923.34
| 2025-09-11 | Underserved Community | EL CAJON | N/A | Not Available | 72 | 52 | N/A | 2025-01-16 | Not Available | Not Available | Not Available | -18.28 | Unknown | -942.6 | 0 | 105.08 | -960.88 | 1065.96
| 2025-05-07 | N/A | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-10-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.94 | 0 | 212.05 | 5.94 | 206.11
| 2025-03-28 | N/A | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2024-08-06 | Not Available | Not Available | Not Available | -23.48 | Unknown | 1181.92 | 0 | 2232.84 | 1158.44 | 1074.4
| 2025-04-16 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | 54 | 38 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -38.44 | Unknown | 709.6 | 0 | 595.44 | 671.16 | -75.72
| 2025-07-31 | N/A | ENCINITAS | N/A | Not Available | 133 | 95 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.51 | 0 | 1313.54 | -1.51 | 1315.05
| 2025-09-15 | Underserved Community | CHULA VISTA | N/A | Not Available | 273 | 195 | N/A |  | Not Available | Not Available | Not Available | 360.48 | Unknown | 254.99 | 0 | 158.37 | 615.47 | -457.1
| 2024-05-04 | N/A | SOLANA BEACH | N/A | Not Available | 134 | 96 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -14.16 | Unknown | -3.29 | 3981 | 534.53 | -17.45 | 551.98
| 2025-01-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 73 | 53 | N/A |  | Not Available | Not Available | Not Available | 525.12 | -245 | 1446.58 | 0 | 999.88 | 1877.92 | -878.04
| 2024-12-01 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 496 | 354 | N/A | 2025-06-17 | Not Available | Not Available | Not Available | 113.54 | Unknown | 68.95 | 0 | Unknown | 182.49 | Unknown
| 2027-02-13 | Underserved Community | VISTA | N/A | Not Available | 29 | 21 | N/A | 2025-04-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-08-22 | Underserved Community | OCEANSIDE | N/A | Not Available | 65 | 47 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.6 | 0 | 999.88 | -0.6 | 1000.48
| 2025-01-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.1 | 0 | 780.89 | -1.1 | 781.99
| 2024-08-30 | Underserved Community | WARNER SPRINGS | N/A | Not Available | 116 | 84 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 694.83 | 0 | 840.62 | 694.83 | 145.79
| 2024-07-30 | Underserved Community | SPRING VALLEY | N/A | Not Available | 82 | 58 | N/A | 2023-10-26 | Not Available | Not Available | Not Available | -12.25 | Unknown | 219.09 | 0 | 518.15 | 206.84 | 311.31
| 2020-12-31 | N/A | DEL MAR | N/A | Not Available | 92 | 66 | N/A | 2025-01-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 58.38 | 0 | 5046.93 | 58.38 | 4988.55
| 2025-12-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 80 | 58 | N/A | 2024-09-17 | Not Available | Not Available | Not Available | -26.09 | Unknown | 1366.12 | 0 | 3248.5 | 1340.03 | 1908.47
| 2022-02-13 | N/A |  | N/A | Not Available | 206 | 148 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | 69.27 | Unknown | 1509.06 | 0 | 700.41 | 1578.33 | -877.92
| 2025-09-06 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 99 | 71 | N/A | 2025-05-07 | Not Available | Not Available | Not Available | 205.74 | Unknown | 834.43 | 0 | 1784.57 | 1057.29 | 727.28
| 2025-03-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 256 | 184 | N/A | 2023-11-29 | Not Available | Not Available | Not Available | -18.74 | Unknown | 414.24 | 0 | 500.87 | 395.5 | 105.37
| 2025-12-23 | N/A | SAN DIEGO | N/A | Not Available | 196 | 140 | N/A | 2025-05-05 | Not Available | Not Available | Not Available | -6.8 | Unknown | 1069.55 | 0 | 1066.51 | 1062.75 | 3.76
| 2027-02-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 120 | 86 | N/A | 2024-11-21 | Not Available | Not Available | Not Available | -14.88 | Unknown | 748.16 | 0 | 2817.87 | 733.28 | 2084.59
| 2023-06-23 | Underserved Community | FALLBROOK | N/A | Not Available | 148 | 106 | N/A | 2023-06-09 | Not Available | Not Available | Not Available | -16.19 | -850.99 | 653.5 | 0 | 1560.63 | -213.68 | 1774.31
| 2025-09-11 | Underserved Community | EL CAJON | N/A | Not Available | 107 | 77 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.5 | 0 | 105.08 | -0.5 | 105.58
| 2025-12-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 102 | 74 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | -20.3 | Unknown | 1012.9 | 0 | 1066.55 | 992.6 | 73.95
| 2025-09-11 | Underserved Community | EL CAJON | N/A | Not Available | 113 | 81 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.98 | 0 | 105.08 | -0.98 | 106.06
| 2025-04-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 87 | 63 | N/A | 2024-10-30 | Not Available | Not Available | Not Available | -18.77 | Unknown | -18.77 | 0 | 1201.16 | -37.54 | 1238.7
| 2025-07-29 | Underserved Community | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | -41.36 | Unknown | -2130.47 | 0 | 512.23 | -2171.83 | 2684.06
| 2022-02-13 | N/A |  | N/A | Not Available | 370 | 264 | N/A | 2023-08-29 | Not Available | Not Available | Not Available | -24.05 | 88.97 | 713.46 | 0 | 1782.33 | 778.38 | 1003.95
| 2026-08-29 | Underserved Community | OCEANSIDE | N/A | Not Available | 69 | 49 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.29 | 0 | 1249.88 | 5.29 | 1244.59
| 2025-10-05 | Underserved Community | OCEANSIDE | N/A | Not Available | 281 | 201 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.29 | 0 | 1015.58 | -0.29 | 1015.87
| 2023-06-23 | Underserved Community | ESCONDIDO | N/A | Not Available | 299 | 215 | N/A | 2023-12-13 | Not Available | Not Available | Not Available | -13.71 | Unknown | 153.7 | 0 | 42.77 | 139.99 | -97.22
| 2026-10-10 | Underserved Community | LAKESIDE | N/A | Not Available | 24 | 18 | N/A | 2025-01-30 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.59 | 0 | 2439.97 | 5.59 | 2434.38
| 2025-04-18 | Underserved Community | EL CAJON | N/A | Not Available | 8 | 6 | N/A | 2024-04-23 | Not Available | Not Available | Not Available | -39.81 | Unknown | 1091 | 0 | 534.57 | 1051.19 | -516.62
| 2025-12-04 | Underserved Community | LA MESA | N/A | Not Available | 130 | 94 | N/A | 2025-05-06 | Not Available | Not Available | Not Available | -1.25 | -288 | 63.8 | 0 | 288.44 | -225.45 | 513.89
| 2024-05-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 203 | 145 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 247.03 | 0 | 1049.43 | 247.03 | 802.4
| 2023-06-15 | Underserved Community | VISTA | N/A | Not Available | 77 | 55 | N/A | 2024-04-24 | Not Available | Not Available | Not Available | -10.62 | Unknown | -2.48 | 3981 | Unknown | -13.1 | Unknown
| 2026-03-20 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 144 | 104 | N/A | 2025-06-18 | Not Available | Not Available | Not Available | 40.9 | Unknown | 363.39 | 0 | 1064.43 | 404.29 | 660.14
| 2026-02-16 | Underserved Community | SPRING VALLEY | N/A | Not Available | 77 | 55 | N/A | 2024-05-07 | Not Available | Not Available | Not Available | -39.4 | Unknown | 1380.12 | 0 | 529.2 | 1340.72 | -811.52
| 2026-05-21 | N/A | CARLSBAD | N/A | Not Available | 125 | 89 | N/A | 2024-10-09 | Not Available | Not Available | Not Available | 733.02 | Unknown | 1489.67 | 0 | 192.83 | 2276.42 | -2083.59
| 2024-10-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 158 | 114 | N/A | 2023-02-14 | Not Available | Not Available | Not Available | -5.49 | Unknown | 1399.87 | 0 | 98.41 | 1394.38 | -1295.97
| 2027-03-04 | Underserved Community | VISTA | N/A | Not Available | 50 | 36 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | -28.12 | Unknown | 2622.12 | 0 | 118.25 | 2594 | -2475.75
| 2024-10-22 | Underserved Community | LA MESA | N/A | Not Available | 210 | 150 | N/A | 2024-08-12 | Not Available | Not Available | Not Available | -32.64 | Unknown | -38.73 | 0 | 94.07 | -71.37 | 165.44
| 2026-10-30 | N/A | LAGUNA HILLS | N/A | Not Available | 82 | 58 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2022-02-13 | N/A |  | N/A | Not Available | 241 | 173 | N/A | 2024-07-25 | Not Available | Not Available | Not Available | -5.6 | 40.5 | 902.34 | 0 | 1925.44 | 937.24 | 988.2
| 2025-03-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 233 | 167 | N/A | 2024-02-09 | Not Available | Not Available | Not Available | -18.86 | -515 | 342.33 | 0 | 627.61 | -191.53 | 819.14
| 2025-08-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 594 | 424 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | -17.5 | Unknown | 883.83 | 0 | 186.52 | 866.33 | -679.81
| 2025-08-09 | Underserved Community | ESCONDIDO | N/A | Not Available | 228 | 164 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 1569.76 | 0 | 1576.29 | 1569.76 | 6.53
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 88 | 64 | N/A | 2024-08-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 15.33 | 0 | 192.83 | 15.33 | 177.5
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 142 | 102 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.28 | 0 | 192.83 | 9.28 | 183.55
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 176 | 126 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.56 | 0 | 192.83 | 5.56 | 187.27
| 2025-08-09 | Underserved Community | VALLEY CENTER | N/A | Not Available | 240 | 172 | N/A | 2024-04-02 | Not Available | Not Available | Not Available | -27.25 | Unknown | 634.65 | 0 | 481.24 | 607.4 | -126.16
| 2024-05-12 | N/A | LADERA RANCH | N/A | Not Available | 479 | 343 | N/A | 2023-10-23 | Not Available | Not Available | Not Available | 2027.11 | Unknown | 1565.35 | 3981 | 143.91 | 6354.08 | -6210.17
| 2024-11-13 | N/A | SAN DIEGO | N/A | Not Available | 85 | 61 | N/A | 2023-12-26 | Not Available | Not Available | Not Available | -22.72 | Unknown | 500.38 | 0 | 499.18 | 477.66 | 21.52
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 341 | 243 | N/A | 2024-06-24 | Not Available | Not Available | Not Available | -8.22 | Unknown | 29.1 | 0 | 76.08 | 20.88 | 55.2
| 2025-04-24 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-08-21 | Not Available | Not Available | Not Available | -8.97 | Unknown | 446.79 | 3981 | 787.09 | 437.82 | 349.27
| 2025-02-26 | Underserved Community | SPRING VALLEY | N/A | Not Available | 121 | 87 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -30.74 | Unknown | 1005.78 | 0 | 529.2 | 975.04 | -445.84
| 2025-06-23 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2024-01-31 | Not Available | Not Available | Not Available | -26.02 | Unknown | 1209.63 | 0 | 515.81 | 1183.61 | -667.8
| 2023-06-23 | N/A | ENCINITAS | N/A | Not Available | 286 | 204 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 676.98 | 0 | 154.99 | 676.98 | -521.99
| 2023-09-28 | Underserved Community | ESCONDIDO | N/A | Not Available | 235 | 167 | N/A | 2023-07-26 | Not Available | Not Available | Not Available | -7.2 | Unknown | 3.49 | 0 | 247.29 | -3.71 | 251
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 164 | 118 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.57 | 0 | 192.83 | 3.57 | 189.26
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 92 | 66 | N/A | 2024-08-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.46 | 0 | 192.83 | 6.46 | 186.37
| 2023-12-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 69 | 49 | N/A | 2023-03-03 | Not Available | Not Available | Not Available | -7.98 | Unknown | -1.8 | 0 | 95.13 | -9.78 | 104.91
| 2026-02-28 | Underserved Community | SAN DIEGO | N/A | Not Available | 140 | 100 | N/A | 2024-07-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.57 | 0 | 162.34 | 5.57 | 156.77
| 2026-03-07 | N/A | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A |  | Not Available | Not Available | Not Available | 377.04 | Unknown | 278.71 | 0 | 192.95 | 809.34 | -616.39
| 2025-01-24 | Underserved Community | SAN CLEMENTE | N/A | Not Available | 427 | 305 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.81 | 0 | 153.26 | 9.81 | 143.45
| 2025-07-26 | Underserved Community | SAN DIEGO | N/A | Not Available | 128 | 92 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | -21.82 | -197 | 353.5 | 0 | 197.01 | 134.68 | 62.33
| 2025-07-23 | Underserved Community | SAN DIEGO | N/A | Not Available | 107 | 77 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | -9.64 | Unknown | 485.11 | 0 | 985.1 | 475.47 | 509.63
| 2024-09-30 | Underserved Community | DANA POINT | N/A | Not Available | 246 | 176 | N/A | 2025-04-15 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.5 | Unknown | Unknown
| 2023-11-30 | N/A | SAN CLEMENTE | N/A | Not Available | 107 | 77 | N/A | 2024-01-17 | Not Available | Not Available | Not Available | -92.76 | Unknown | 2836.28 | 0 | 158.79 | 2743.52 | -2584.73
| 2026-08-28 | Underserved Community | DANA POINT | N/A | Not Available | 87 | 63 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | -24.15 | Unknown | 1199.85 | 0 | 1050.75 | 1175.7 | -124.95
| 2026-03-19 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 80 | 58 | N/A | 2024-06-20 | Not Available | Not Available | Not Available | -4.89 | Unknown | -8.82 | 0 | 661.55 | -13.71 | 675.26
| 2025-09-11 | Underserved Community | EL CAJON | N/A | Not Available | 119 | 85 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | -25.84 | Unknown | -1330.7 | 0 | 105.08 | -1356.54 | 1461.62
| 2025-04-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 98 | 70 | N/A | 2024-10-28 | Not Available | Not Available | Not Available | -15.77 | Unknown | 839.02 | 0 | 1231.48 | 823.25 | 408.23
| 2026-04-29 | N/A | CARLSBAD | N/A | Not Available | 125 | 89 | N/A | 2024-09-06 | Not Available | Not Available | Not Available | -8.05 | Unknown | 403.62 | 0 | 1050.61 | 395.57 | 655.04
| 2025-05-26 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 345 | 247 | N/A | 2024-04-02 | Not Available | Not Available | Not Available | -59.66 | Unknown | -67.31 | 0 | 154.99 | -126.97 | 281.96
| 2026-09-25 | N/A | RANCHO SANTA FE | N/A | Not Available | 53 | 39 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 49.36 | 0 | 197.01 | 49.36 | 147.65
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 92 | 66 | N/A | 2024-08-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.57 | 0 | 192.83 | 6.57 | 186.26
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | 287 | 205 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -6.2 | Unknown | 6.65 | 0 | 158.37 | 0.45 | 157.92
| 2023-03-15 | N/A | ENCINITAS | N/A | Not Available | 220 | 158 | N/A |  | Not Available | Not Available | Not Available | Unknown | Unknown | 2109.94 | 0 | 434.6 | 2109.94 | -1675.34
| 2025-05-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 177 | 127 | N/A | 2024-09-23 | Not Available | Not Available | Not Available | -32.49 | Unknown | 1616.61 | 0 | 496.14 | 1584.12 | -1087.98
| 2024-05-01 | N/A | ENCINITAS | N/A | Not Available | 268 | 192 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -28.22 | Unknown | 1155.43 | 3981 | 500.87 | 1127.21 | -626.34
| 2027-02-18 | Underserved Community | ESCONDIDO | N/A | Not Available | 21 | 15 | N/A | 2025-03-05 | Not Available | Not Available | Not Available | -25.84 | Unknown | 1288.4 | 3981 | 134.91 | 1262.56 | -1127.65
| 2025-04-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 360 | 258 | N/A | 2025-06-05 | Not Available | Not Available | Not Available | -17.39 | Unknown | 859.89 | 0 | 337.59 | 842.5 | -504.91
| 2024-11-27 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 187 | 133 | N/A | 2024-06-10 | Not Available | Not Available | Not Available | Unknown | Unknown | -2.14 | 0 | 501.14 | -2.14 | 503.28
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 78 | 56 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.7 | 0 | 192.83 | 4.7 | 188.13
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 78 | 56 | N/A | 2024-07-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.65 | 0 | 192.83 | 1.65 | 191.18
| 2026-05-01 | N/A | ENCINITAS | N/A | Not Available | 92 | 66 | N/A | 2024-08-08 | Not Available | Not Available | Not Available | -12.92 | Unknown | 644.44 | 0 | 984.98 | 631.52 | 353.46
| 2024-05-18 | Underserved Community | VISTA | N/A | Not Available | 252 | 180 | N/A | 2024-01-29 | Not Available | Not Available | Not Available | -7.19 | Unknown | -1.66 | 0 | 158.79 | -8.85 | 167.64
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 126 | 90 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 167 | 120 | N/A | 2025-03-13 | Not Available | Not Available | Not Available | 315.45 | Unknown | 154.6 | 0 | 196.44 | 492.98 | -296.54
| 2025-12-28 | Underserved Community | EL CAJON | N/A | Not Available | 184 | 132 | N/A | 2024-07-03 | Not Available | Not Available | Not Available | -20.29 | Unknown | -0.79 | 0 | 163.83 | -21.08 | 184.91
| 2024-01-20 | Underserved Community | LA MESA | N/A | Not Available | 185 | 133 | N/A | 2024-05-17 | Not Available | Not Available | Not Available | -18.54 | Unknown | 623.05 | 0 | 44.44 | 604.51 | -560.07
| 2025-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2025-05-20 | Not Available | Not Available | Not Available | -9.61 | Unknown | 475.55 | 0 | 1063.08 | 465.94 | 597.14
| 2025-04-03 | Underserved Community | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-08-07 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.01 | 0 | 496.14 | -1.01 | 497.15
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 607 | 435 | N/A | 2024-11-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 17.18 | 3981 | 197.9 | 17.18 | 180.72
| 2023-03-23 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 108 | 78 | N/A | 2024-10-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 73.22 | 0 | 464.73 | 73.22 | 391.51
| 2023-06-19 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 148 | 106 | N/A | 2023-12-11 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.27 | 0 | 513.31 | -1.27 | 514.58
| 2025-08-29 | N/A | SAN DIEGO | N/A | Not Available | 165 | 117 | N/A | 2025-04-24 | Not Available | Not Available | Not Available | -0.63 | Unknown | 71.52 | 0 | 89.51 | 70.89 | 18.62
| 2025-04-12 | Underserved Community | EL CAJON | N/A | Not Available | 284 | 204 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | -25.57 | Unknown | 1263.6 | 0 | 984.98 | 1238.03 | -253.05
| 2024-03-31 | N/A | LAGUNA HILLS | N/A | Not Available | 120 | 86 | N/A | 2023-06-20 | Not Available | Not Available | Not Available | 137.3 | Unknown | 153.53 | 0 | 143.83 | 332.91 | -189.08
| 2024-07-26 | N/A | MISSION VIEJO | N/A | Not Available | 61 | 43 | N/A | 2026-10-18 | Not Available | Not Available | Not Available | 1403.29 | Unknown | 912.1 | 0 | 153.83 | 2478.01 | -2324.18
| 2025-12-19 | Underserved Community | CHULA VISTA | N/A | Not Available | 201 | 145 | N/A | 2025-04-17 | Not Available | Not Available | Not Available | -19.15 | Unknown | 949.89 | 0 | 288.94 | 930.74 | -641.8
| 2025-06-01 | Underserved Community | SAN DIEGO | N/A | Not Available | 53 | 39 | N/A | 2024-11-07 | Not Available | Not Available | Not Available | -14.67 | -4151 | 769.34 | 3981 | 4038.73 | -3396.33 | 7435.06
| 2025-09-11 | Underserved Community | EL CAJON | N/A | Not Available | 112 | 80 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.8 | 0 | 105.08 | -0.8 | 105.88
| 2023-02-07 | Underserved Community | ESCONDIDO | N/A | Not Available | 105 | 75 | N/A | 2023-10-24 | Not Available | Not Available | Not Available | -16.78 | Unknown | 48.65 | 0 | 758.89 | 31.87 | 727.02
| 2025-03-21 | Underserved Community | FALLBROOK | N/A | Not Available | 106 | 76 | N/A | 2023-09-12 | Not Available | Not Available | Not Available | 437.19 | Unknown | 1459.41 | 0 | 496.45 | 2073.48 | -1577.03
| 2026-04-19 | Underserved Community | OCEANSIDE | N/A | Not Available | 146 | 104 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | -24.15 | Unknown | 1199.32 | 0 | 192.83 | 1175.17 | -982.34
| 2024-08-03 | N/A | MISSION VIEJO | N/A | Not Available | 47 | 35 | N/A |  | Not Available | Not Available | Not Available | 1067.79 | Unknown | 2510.34 | 0 | 111.81 | 4000.7 | -3888.89
| 2025-02-13 | Underserved Community | VISTA | N/A | Not Available | 85 | 61 | N/A | 2023-06-14 | Not Available | Not Available | Not Available | -13.19 | Unknown | -5.01 | 0 | 495.75 | -18.2 | 513.95
| 2025-04-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 97 | 69 | N/A | 2023-11-22 | Not Available | Not Available | Not Available | 4848.72 | Unknown | 2341.02 | 0 | 481.24 | 9403.24 | -8922
| 2025-02-12 | Underserved Community | ESCONDIDO | N/A | Not Available | 217 | 155 | N/A | 2023-09-21 | Not Available | Not Available | Not Available | -33.19 | Unknown | 1152.54 | 0 | 468.73 | 1119.35 | -650.62
| 2027-03-17 | N/A | SAN CLEMENTE | N/A | Not Available | 18 | 12 | N/A | 2025-06-10 | Not Available | Not Available | Not Available | -6.46 | Unknown | 681 | 0 | 118.25 | 674.54 | -556.29
| 2026-03-14 | Underserved Community | ESCONDIDO | N/A | Not Available | 101 | 73 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | 244.42 | Unknown | 757.92 | 0 | 529.2 | 1002.34 | -473.14
| 2027-02-06 | Underserved Community | OCEANSIDE | N/A | Not Available | 49 | 35 | N/A | 2025-04-10 | Not Available | Not Available | Not Available | -49.76 | Unknown | 1983.35 | 0 | 196.44 | 1933.59 | -1737.15
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 79 | 57 | N/A | 2024-07-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.66 | 0 | 192.83 | 3.66 | 189.17
| 2026-01-18 | Underserved Community | ESCONDIDO | N/A | Not Available | 73 | 53 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -14.98 | Unknown | -3.47 | 0 | 751.74 | -18.45 | 770.19
| 2024-08-22 | N/A | DANA POINT | N/A | Not Available | 140 | 100 | N/A | 2023-11-21 | Not Available | Not Available | Not Available | 814.1 | Unknown | 574.51 | 0 | 158.14 | 2174.63 | -2016.49
| 2025-06-16 | Underserved Community | VISTA | N/A | Not Available | 189 | 135 | N/A | 2024-08-15 | Not Available | Not Available | Not Available | -8.37 | Unknown | 257.72 | 0 | 210 | 249.35 | -39.35
| 2026-04-30 | N/A | SAN DIEGO | N/A | Not Available | 164 | 118 | N/A | 2024-10-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 3981 | 192.51 | 3.85 | 188.66
| 2026-07-29 | N/A | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A | 2024-10-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.13 | 0 | 192.95 | 4.13 | 188.82
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | 164 | 118 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.71 | 0 | 180.09 | 4.71 | 175.38
| 2024-01-20 | N/A | SAN DIEGO | N/A | Not Available | 273 | 195 | N/A |  | Not Available | Not Available | Not Available | Unknown | -1000 | 425.48 | 0 | 999.91 | -574.52 | 1574.43
| 2025-04-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A | 2024-09-10 | Not Available | Not Available | Not Available | -6.75 | Unknown | 338.61 | 0 | 496.14 | 331.86 | 164.28
| 2024-04-24 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 310 | 222 | N/A | 2024-02-01 | Not Available | Not Available | Not Available | Unknown | Unknown | -1.62 | 0 | 513.31 | -1.62 | 514.93
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | 762 | 544 | N/A | 2025-05-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.9 | Unknown | Unknown
| 2024-08-31 | N/A | SAN DIEGO | N/A | Not Available | 367 | 263 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | -15.57 | Unknown | 963.95 | 0 | 496.14 | 948.38 | -452.24
| 2025-11-07 | N/A | SAN DIEGO | N/A | Not Available | 235 | 169 | N/A | 2024-09-04 | Not Available | Not Available | Not Available | -11 | Unknown | 551.47 | 0 | 485.94 | 540.47 | -54.53
| 2025-10-07 | N/A | SAN CLEMENTE | N/A | Not Available | 62 | 44 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | -34.99 | Unknown | 1742.86 | 0 | 105.08 | 1707.87 | -1602.79
| 2025-03-15 | Underserved Community | SAN DIEGO | N/A | Not Available | 274 | 196 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | -15.21 | -1051 | 760.26 | 0 | 1050.61 | -305.95 | 1356.56
| 2025-03-26 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 128 | 92 | N/A | 2024-09-11 | Not Available | Not Available | Not Available | -6.74 | Unknown | 338.92 | 0 | 496.14 | 332.18 | 163.96
| 2024-09-12 | Underserved Community | FALLBROOK | N/A | Not Available | 167 | 120 | N/A | 2023-03-17 | Not Available | Not Available | Not Available | -14.5 | Unknown | 869.7 | 0 | 376.27 | 855.2 | -478.93
| 2025-05-02 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | 99 | 71 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 0.04 | 0 | 102.37 | 0.04 | 102.33
| 2025-01-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 93 | 67 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | -74.44 | Unknown | 2396.17 | 0 | 501.18 | 2321.73 | -1820.55
| 2024-01-18 | N/A | SAN CLEMENTE | N/A | Not Available | 343 | 245 | N/A | 2023-09-07 | Not Available | Not Available | Not Available | -25.13 | Unknown | 649.95 | 0 | 67.06 | 624.82 | -557.76
| 2027-06-04 | Underserved Community | LEMON GROVE | N/A | Not Available | 115 | 83 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | 120.22 | 160.69 | Unknwn | Unknown | 280.91 | Unknown
| 2024-06-06 | Underserved Community | LEMON GROVE | N/A | Not Available | 184 | 132 | N/A | 2023-11-02 | Not Available | Not Available | Not Available | -7.71 | Unknown | -2.48 | 0 | 1135.03 | -10.19 | 1145.22
| 2027-02-05 | N/A | SAN DIEGO | N/A | Not Available | 54 | 38 | N/A | 2025-04-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2024-05-24 | Underserved Community | SANTEE | N/A | Not Available | 449 | 321 | N/A | 2024-08-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.46 | 0 | 496.37 | 10.46 | 485.91
| 2025-09-12 | Underserved Community | EL CAJON | N/A | Not Available | 117 | 83 | N/A | 2025-02-06 | Not Available | Not Available | Not Available | -1.57 | Unknown | 96.55 | 0 | 1333.25 | 94.98 | 1238.27
| 2027-04-21 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 41 | 29 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.64 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 510 | 364 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-06-04 | N/A | LAGUNA HILLS | N/A | Not Available | 6 | 4 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 174 | 124 | N/A | 2024-08-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.02 | 0 | 1049.43 | 8.02 | 1041.41
| 2025-04-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 599 | 429 | N/A | 2025-02-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.91 | 0 | 515.81 | 9.91 | 505.9
| 2027-01-10 | N/A | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2025-04-16 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3961 | 196.44 | Unknown | Unknown
| 2024-03-07 | Underserved Community | EL CAJON | N/A | Not Available | 238 | 170 | N/A | 2024-05-20 | Not Available | Not Available | Not Available | -6.68 | -1163 | 14.23 | 0 | 1011.9 | -1155.45 | 2167.35
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 510 | 364 | N/A | 2025-05-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-04-05 | Underserved Community | CHULA VISTA | N/A | Not Available | 112 | 80 | N/A | 2023-08-24 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1.41 | 0 | 480.37 | -5.15 | 485.52
| 2026-05-28 | Underserved Community | SPRING VALLEY | N/A | Not Available | 136 | 98 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | -1108 | 14.95 | 0 | 1049.43 | -1093.05 | 2142.48
| 2025-05-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 43 | 31 | N/A | 2023-08-24 | Not Available | Not Available | Not Available | -8.54 | Unknown | -3.24 | 0 | 465.36 | -11.78 | 477.14
| 2024-08-04 | Underserved Community | LAKESIDE | N/A | Not Available | 106 | 76 | N/A | 2023-10-23 | Not Available | Not Available | Not Available | -17.86 | Unknown | -5.95 | 0 | 496.37 | -23.81 | 520.18
| 2026-02-21 | Underserved Community | VISTA | N/A | Not Available | 274 | 196 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | Unknown | 30.68 | 0 | 1016.73 | 30.68 | 986.05
| 2025-09-18 | N/A | LA MESA | N/A | Not Available | 134 | 96 | N/A | 2023-12-14 | Not Available | Not Available | Not Available | -10.14 | Unknown | 58.76 | 0 | 601.78 | 48.62 | 553.16
| 2025-05-29 | Underserved Community | LAKESIDE | N/A | Not Available | 60 | 44 | N/A | 2024-08-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.33 | 0 | 668.23 | 8.33 | 659.9
| 2024-08-30 | Underserved Community | POWAY | N/A | Not Available | 24 | 18 | N/A | 2023-12-19 | Not Available | Not Available | Not Available | -9.38 | Unknown | -2.49 | 0 | 515.81 | -11.87 | 527.68
| 2026-04-15 | Underserved Community | FALLBROOK | N/A | Not Available | 86 | 62 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | -9.31 | Unknown | -1.5 | 0 | 1260.77 | -10.81 | 1271.58
| 2026-05-04 | Underserved Community | OCEANSIDE | N/A | Not Available | 77 | 55 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | -12.07 | Unknown | 674.25 | 0 | 1220.14 | 662.18 | 557.96
| 2025-01-24 | N/A | LAGUNA HILLS | N/A | Not Available | 29 | 21 | N/A | 2024-08-05 | Not Available | Not Available | Not Available | 204.13 | 4.88 | 114.34 | 0 | 192.95 | 334.22 | -141.27
| 2026-07-09 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | 36 | 26 | N/A | 2024-10-07 | Not Available | Not Available | Not Available | -3 | Unknown | 158.25 | 0 | 1117.69 | 155.25 | 962.44
| 2026-06-04 | Underserved Community | SAN MARCOS | N/A | Not Available | 197 | 141 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.43 | 0 | 192.51 | 6.43 | 186.08
| 2027-01-24 | Underserved Community | CARLSBAD | N/A | Not Available | 80 | 58 | N/A | 2025-04-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.14 | 0 | 196.69 | 3.14 | 193.55
| 2023-09-12 | Underserved Community | VISTA | N/A | Not Available | 16 | 12 | N/A | 2023-09-13 | Not Available | Not Available | Not Available | -23.92 | Unknown | 614.15 | 0 | 480.37 | 590.23 | -109.86
| 2026-10-31 | N/A | SAN DIEGO | N/A | Not Available | 60 | 44 | N/A | 2025-02-19 | Not Available | Not Available | Not Available | -11.87 | Unknown | -2.73 | 0 | 196.69 | -14.6 | 211.29
| 2027-05-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 60 | 44 | N/A | 2024-06-17 | Not Available | Not Available | Not Available | -57.51 | Unknown | 2442.27 | 0 | 529.2 | 2384.76 | -1855.56
| 2026-11-11 | N/A | CARDIFF | N/A | Not Available | 13 | 9 | N/A | 2025-01-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.48 | 0 | 136.26 | 8.48 | 127.78
| 2024-10-19 | Underserved Community | EL CAJON | N/A | Not Available | 56 | 40 | N/A | 2024-02-05 | Not Available | Not Available | Not Available | -7.78 | Unknown | -1.8 | 0 | 515.81 | -9.58 | 525.39
| 2024-10-22 | Underserved Community | LA MESA | N/A | Not Available | 114 | 82 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -42.71 | Unknown | 1970.85 | 0 | 85.5 | 1928.14 | -1842.64
| 2023-06-23 | Disadvantaged Community,Underserved Community |  | N/A | Not Available | 515 | 369 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | -23.63 | Unknown | 1372.74 | 0 | 218.58 | 1349.11 | -1130.53
| 2025-11-17 | Underserved Community | SAN MARCOS | N/A | Not Available | 58 | 42 | N/A | 2024-01-11 | Not Available | Not Available | Not Available | -6.36 | Unknown | -1.7 | 0 | 158.79 | -8.06 | 166.85
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 373 | 267 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | -9.56 | Unknown | -3.68 | 0 | 163.83 | -13.24 | 177.07
| 2026-07-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 226 | 162 | N/A |  | Not Available | Not Available | Not Available | 385.62 | Unknown | 227.97 | 0 | 190.44 | 613.59 | -423.15
| 2026-11-22 | N/A | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2025-01-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.26 | 0 | 105.72 | 5.26 | 100.46
| 2026-04-25 | N/A | SAN DIEGO | N/A | Not Available | 106 | 76 | N/A | 2025-01-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.72 | 0 | 197.01 | 10.72 | 186.29
| 2027-04-23 | Underserved Community | BONSALL | N/A | Not Available | 21 | 15 | N/A |  | Not Available | Not Available | Not Available | 1641.98 | Unknown | 1083.66 | 0 | 465.64 | 2725.64 | -2260
| 2026-11-20 | Underserved Community | VALLEY CENTER | N/A | Not Available | 56 | 40 | N/A |  | Not Available | Not Available | Not Available | 509.4 | Unknown | 360.72 | 0 | 196.59 | 983.63 | -787.04
| 2027-01-23 | Underserved Community | FALLBROOK | N/A | Not Available | 72 | 52 | N/A |  | Not Available | Not Available | Not Available | 360.69 | Unknown | 1488.69 | 0 | 196.44 | 2203.63 | -2007.19
| 2025-10-13 | N/A | SAN DIEGO | N/A | Not Available | 270 | 194 | N/A |  | Not Available | Not Available | Not Available | 179.54 | Unknown | 126.17 | 0 | 163.83 | 322 | -158.17
| 2027-05-12 | N/A | DANA POINT | N/A | Not Available | 14 | 10 | N/A | 2025-06-25 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 118.25 | 2.02 | 116.23
| 2025-04-17 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | 32 | 23 | N/A | 2023-10-11 | Not Available | Not Available | Not Available | 252.46 | Unknown | 162.96 | 0 | 153.22 | 415.42 | -262.2
| 2027-03-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2025-04-29 | Not Available | Not Available | Not Available | -22.98 | Unknown | 1136.54 | 0 | 1029.34 | 1113.56 | -84.22
| 2025-04-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 219 | 157 | N/A | 2024-06-06 | Not Available | Not Available | Not Available | -7.32 | Unknown | 6.76 | 0 | 163.83 | -0.56 | 164.39
| 2026-10-01 | Underserved Community | CHULA VISTA | N/A | Not Available | 6 | 4 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | 3.65 | 440.86 | 0 | 443.85 | 444.51 | -0.66
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | 573 | 409 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | -0.06 | 0 | 153.83 | -0.06 | 153.89
| 2026-06-25 | Underserved Community | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A |  | Not Available | Not Available | Not Available | 567.57 | Unknown | 664.02 | 0 | 197.01 | 1231.59 | -1034.58
| 2026-12-18 | N/A | SAN MARCOS | N/A | Not Available | 99 | 71 | N/A |  | Not Available | Not Available | Not Available | 303.12 | Unknown | 215.91 | 3981 | 288.94 | 646.1 | -357.16
| 2027-05-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | -8.43 | Unknown | 432.51 | 0 | 435.59 | 424.08 | 11.51
| 2026-10-03 | Underserved Community | SPRING VALLEY | N/A | Not Available | 29 | 21 | N/A | 2024-11-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.04 | 0 | 197.01 | 10.04 | 186.97
| 2025-11-29 | Underserved Community | ESCONDIDO | N/A | Not Available | 122 | 88 | N/A |  | Not Available | Not Available | Not Available | 232.51 | Unknown | 1275.08 | 0 | 1101.15 | 1572.05 | -470.9
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | 280 | 200 | N/A |  | Not Available | Not Available | Not Available | 1003.2 | Unknown | 626.57 | 3981 | 192.95 | 2081.82 | -1888.87
| 2025-07-10 | Underserved Community | FALLBROOK | N/A | Not Available | 70 | 50 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | -6.37 | Unknown | 0.83 | 0 | 170.64 | -5.54 | 176.18
| 2025-07-31 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2024-01-24 | Not Available | Not Available | Not Available | -4.27 | Unknown | 3.83 | 0 | 152.86 | -0.44 | 153.3
| 2026-09-10 | N/A | SAN DIEGO | N/A | Not Available | 58 | 42 | N/A | 2024-12-13 | Not Available | Not Available | Not Available | Unknown | 1.12 | 5.38 | 3981 | 197.01 | 6.5 | 190.51
| 2026-07-22 | Underserved Community | LAKESIDE | N/A | Not Available | 57 | 41 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.85 | 0 | 180.5 | 3.85 | 176.65
| 2025-09-21 | N/A | DEL MAR | N/A | Not Available | 40 | 30 | N/A | 2024-02-29 | Not Available | Not Available | Not Available | -6.34 | Unknown | 0.15 | 0 | 163.83 | -6.19 | 170.02
| 2027-04-01 | Underserved Community | SPRING VALLEY | N/A | Not Available | 8 | 6 | N/A | 2025-05-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | 1.99 | 116.26
| 2026-10-26 | Underserved Community | ESCONDIDO | N/A | Not Available | 71 | 51 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | 465.14 | Unknown | 330.29 | 0 | 197.01 | 871.12 | -674.11
| 2026-09-16 | Underserved Community | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | -3.15 | Unknown | 192.72 | 0 | 1038.54 | 189.57 | 848.97
| 2024-10-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 341 | 245 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | -18.73 | Unknown | 1253.71 | 0 | 1244.39 | 1234.98 | 9.41
| 2024-03-01 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 435 | 311 | N/A |  | Not Available | Not Available | Not Available | -7.48 | 40.35 | 390.97 | 0 | 603.92 | 423.84 | 180.08
| 2025-08-28 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 51 | 37 | N/A | 2023-12-12 | Not Available | Not Available | Not Available | 244.9 | Unknown | 175.58 | 0 | 152.86 | 420.48 | -267.62
| 2026-01-21 | Underserved Community | CHULA VISTA | N/A | Not Available | 276 | 198 | N/A | 2025-01-03 | Not Available | Not Available | Not Available | -18.82 | Unknown | 937.88 | 0 | 1066.51 | 919.06 | 147.45
| 2026-02-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 28 | 20 | N/A | 2025-03-17 | Not Available | Not Available | Not Available | 879.76 | Unknown | 617.99 | 0 | 196.69 | 1673.69 | -1477
| 2026-04-16 | Underserved Community | VISTA | N/A | Not Available | 123 | 87 | N/A | 2024-08-28 | Not Available | Not Available | Not Available | 1022.77 | Unknown | 1973.17 | 0 | 1050.61 | 2995.94 | -1945.33
| 2025-06-25 | N/A | LAGUNA HILLS | N/A | Not Available | 179 | 129 | N/A | 2024-09-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.51 | 0 | 181.16 | 1.51 | 179.65
| 2024-03-13 | N/A | CARLSBAD | N/A | Not Available | 56 | 40 | N/A | 2024-03-22 | Not Available | Not Available | Not Available | -7.2 | Unknown | -1.67 | 0 | 196.33 | -8.87 | 205.2
| 2024-06-08 | N/A | SAN CLEMENTE | N/A | Not Available | 63 | 45 | N/A | 2024-03-28 | Not Available | Not Available | Not Available | -6.68 | Unknown | -1.53 | 0 | 143.91 | -8.21 | 152.12
| 2024-12-14 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 45 | 33 | N/A | 2024-03-19 | Not Available | Not Available | Not Available | -21.94 | Unknown | -5.09 | 0 | 158.79 | -27.03 | 185.82
| 2026-02-09 | Underserved Community | OCEANSIDE | N/A | Not Available | 24 | 18 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.99 | 0 | 196.44 | 5.99 | 190.45
| 2027-01-16 | Underserved Community | OCEANSIDE | N/A | Not Available | 28 | 20 | N/A | 2025-03-14 | Not Available | Not Available | Not Available | 377.04 | Unknown | 265.75 | 0 | 196.69 | 724.96 | -528.27
| 2025-01-31 | N/A | SAN CLEMENTE | N/A | Not Available | 53 | 39 | N/A | 2025-03-20 | Not Available | Not Available | Not Available | 43.89 | Unknown | 2575.58 | 0 | 196.69 | 2619.47 | -2422.78
| 2023-03-03 | N/A | CARLSBAD | N/A | Not Available | 16 | 12 | N/A | 2023-05-30 | Not Available | Not Available | Not Available | 529.05 | Unknown | 341.7 | 0 | 153.83 | 1104.3 | -950.47
| 2026-10-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 20 | 14 | N/A | 2024-11-22 | Not Available | Not Available | Not Available | Unknown | Unknown | 39.57 | 0 | 197.01 | 39.57 | 157.44
| 2027-01-31 | N/A | CARDIFF | N/A | Not Available | 15 | 11 | N/A | 2025-02-25 | Not Available | Not Available | Not Available | 630.6 | Unknown | 526.16 | 0 | 1063.08 | 2061.16 | -998.08
| 2026-08-21 | Underserved Community | LAKESIDE | N/A | Not Available | 17 | 13 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.63 | 0 | 180.5 | 2.63 | 177.87
| 2024-03-07 | Underserved Community | LA MESA | N/A | Not Available | 34 | 24 | N/A | 2024-04-30 | Not Available | Not Available | Not Available | -3.4 | Unknown | 0.21 | 0 | 648.92 | -3.19 | 652.11
| 2026-07-08 | N/A | SAN DIEGO | N/A | Not Available | 33 | 23 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | 8.73 | -39.44 | 0 | 550.12 | -30.71 | 580.83
| 2025-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2024-03-04 | Not Available | Not Available | Not Available | -6.23 | Unknown | -1.43 | 0 | 1202.76 | -7.66 | 1210.42
| 2025-11-01 | Underserved Community | LAKESIDE | N/A | Not Available | 182 | 130 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | -18.33 | 1.52 | 0.6 | 0 | 639.69 | -16.21 | 655.9
| 2024-01-10 | Underserved Community | VISTA | N/A | Not Available | 135 | 97 | N/A | 2024-05-28 | Not Available | Not Available | Not Available | 380.1 | Unknown | 861.85 | 0 | 480.37 | 1247.18 | -766.81
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 49 | 35 | N/A | 2024-10-29 | Not Available | Not Available | Not Available | 509.4 | Unknown | 361.55 | 0 | 197.01 | 954.54 | -757.53
| 2026-09-11 | Underserved Community | SAN MARCOS | N/A | Not Available | 56 | 40 | N/A | 2024-12-02 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2026-10-09 | Underserved Community | SAN MARCOS | N/A | Not Available | 115 | 83 | N/A | 2025-02-07 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.76 | 0 | 197.01 | 9.76 | 187.25
| 2026-09-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 78 | 56 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | -44.42 | Unknown | 1407.22 | 0 | 197.01 | 1362.8 | -1165.79
| 2026-08-27 | N/A | SAN DIEGO | N/A | Not Available | 253 | 181 | N/A | 2025-06-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.33 | 0 | 197.01 | 3.33 | 193.68
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 270 | 194 | N/A | 2025-05-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 17.52 | 0 | 197.01 | 17.52 | 179.49
| 2026-12-16 | N/A | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2025-02-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.46 | 0 | 197.01 | 7.46 | 189.55
| 2026-09-17 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-11-15 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.23 | 0 | 197.01 | 8.23 | 188.78
| 2026-01-15 | Underserved Community | MISSION VIEJO | N/A | Not Available | 85 | 61 | N/A | 2025-04-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.58 | 0 | 196.69 | 4.58 | 192.11
| 2025-05-23 | N/A | LA JOLLA | N/A | Not Available | 55 | 39 | N/A | 2023-09-22 | Not Available | Not Available | Not Available | -5.14 | Unknown | -0.71 | 0 | 153.83 | -5.85 | 159.68
| 2027-03-01 | N/A | SANTEE | N/A | Not Available | 40 | 28 | N/A |  | Not Available | Not Available | Not Available | 1198.85 | 3.71 | 792.91 | 0 | 118.25 | 1995.47 | -1877.22
| 2026-09-19 | Underserved Community | SAN MARCOS | N/A | Not Available | 26 | 18 | N/A | 2025-02-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.59 | 0 | 196.69 | 12.59 | 184.1
| 2025-02-22 | N/A | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A |  | Not Available | Not Available | Not Available | 537.96 | 1.86 | 1252.45 | 3981 | 244.63 | 1900.73 | -1656.1
| 2026-01-17 | N/A | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2025-03-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.69 | 0 | 196.44 | 7.69 | 188.75
| 2026-07-29 | Underserved Community | ESCONDIDO | N/A | Not Available | 16 | 12 | N/A | 2024-10-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 13.5 | 0 | 197.01 | 13.5 | 183.51
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 84 | 60 | N/A |  | Not Available | Not Available | Not Available | 317.94 | Unknown | 209.84 | 0 | 196.44 | 527.78 | -331.34
| 2026-07-15 | Underserved Community | SPRING VALLEY | N/A | Not Available | 22 | 16 | N/A | 2024-10-04 | Not Available | Not Available | Not Available | -11.6 | Unknown | 578.84 | 3981 | 1131.85 | 567.24 | 564.61
| 2026-09-17 | N/A | SAN DIEGO | N/A | Not Available | 70 | 50 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.94 | 0 | 197.01 | 12.94 | 184.07
| 2026-05-06 | Underserved Community | EL CAJON | N/A | Not Available | 22 | 16 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | -157.19 | -26.91 | 3981 | 190.44 | -184.1 | 374.54
| 2023-02-02 | Underserved Community | BONSALL | N/A | Not Available | 201 | 143 | N/A | 2023-07-31 | Not Available | Not Available | Not Available | 2969.17 | Unknown | 3185.06 | 0 | 436.48 | 6676.04 | -6239.56
| 2025-01-05 | Underserved Community | OCEANSIDE | N/A | Not Available | 545 | 389 | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-09-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 129 | 93 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | 7.6 | -17.1 | 0 | 669.15 | -9.5 | 678.65
| 2027-01-27 | Underserved Community | ESCONDIDO | N/A | Not Available | 15 | 11 | N/A | 2025-03-26 | Not Available | Not Available | Not Available | -12.53 | Unknown | -6.81 | 0 | 1063.08 | -19.34 | 1082.42
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 52 | 38 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.46 | 0 | 197.01 | 4.46 | 192.55
| 2026-09-21 | Underserved Community | SAN MARCOS | N/A | Not Available | 69 | 49 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-01-09 | Underserved Community | LEMON GROVE | N/A | Not Available | 24 | 18 | N/A | 2025-01-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.75 | 0 | 196.69 | 1.75 | 194.94
| 2027-01-15 | N/A | SAN DIEGO | N/A | Not Available | 26 | 20 | N/A | 2025-01-31 | Not Available | Not Available | Not Available | Unknown | Unknown | 18.84 | 0 | 196.69 | 18.84 | 177.85
| 2026-12-10 | N/A | SAN DIEGO | N/A | Not Available | 36 | 26 | N/A | 2025-01-10 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.59 | 0 | 197.01 | 5.59 | 191.42
| 2026-09-13 | Underserved Community | SAN DIEGO | N/A | Not Available | 80 | 58 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.57 | 0 | 197.01 | 3.57 | 193.44
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 19 | 14 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-06-30 | Underserved Community | ESCONDIDO | N/A | Not Available | 9 | 7 | N/A | 2024-03-06 | Not Available | Not Available | Not Available | -10.74 | Unknown | -1.34 | 0 | 40.01 | -12.08 | 52.09
| 2026-03-13 | N/A | ENCINITAS | N/A | Not Available | 115 | 83 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.16 | 0 | 197.01 | 7.16 | 189.85
| 2026-08-19 | N/A | POWAY | N/A | Not Available | 19 | 14 | N/A | 2024-10-02 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.11 | 0 | 1103.3 | 6.11 | 1097.19
| 2026-12-19 | Underserved Community | RAMONA | N/A | Not Available | 29 | 21 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | 382.05 | Unknown | 257.72 | 0 | 997.93 | 639.77 | 358.16
| 2026-12-30 | N/A | SAN DIEGO | N/A | Not Available | 29 | 21 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 10 | 0 | 197.01 | 10 | 187.01
| 2026-01-13 | Underserved Community | POWAY | N/A | Not Available | 30 | 22 | N/A | 2025-02-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.44 | 0 | 997.93 | 7.44 | 990.49
| 2027-01-27 | N/A | SAN MARCOS | N/A | Not Available | 30 | 22 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | -12.53 | Unknown | -6.77 | 0 | 334.21 | -19.3 | 353.51
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | 62 | 44 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.25 | 0 | 197.01 | 4.25 | 192.76
| 2026-09-11 | N/A | SAN DIEGO | N/A | Not Available | 71 | 51 | N/A | 2024-12-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.58 | 3981 | 197.01 | 5.58 | 191.43
| 2026-09-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 85 | 61 | N/A |  | Not Available | Not Available | Not Available | 318.38 | Unknown | 222.74 | 0 | 196.69 | 637.51 | -440.82
| 2027-01-08 | N/A | SANTEE | N/A | Not Available | 45 | 32 | N/A | 2025-04-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 1.75 | 0 | 196.69 | 1.75 | 194.94
| 2026-05-22 | Underserved Community | ESCONDIDO | N/A | Not Available | 128 | 92 | N/A | 2025-01-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.14 | 0 | 1103.3 | 5.14 | 1098.16
| 2026-09-11 | N/A | SAN DIEGO | N/A | Not Available | 116 | 84 | N/A | 2024-12-20 | Not Available | Not Available | Not Available | -19.69 | Unknown | -3.77 | 0 | 197.01 | -23.46 | 220.47
| 2025-12-17 | Underserved Community | LA MESA | N/A | Not Available | 67 | 49 | N/A | 2025-02-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.69 | 0 | 1087.12 | 7.69 | 1079.43
| 2025-12-04 | Underserved Community | SAN DIEGO | N/A | Not Available | 33 | 25 | N/A | 2024-05-30 | Not Available | Not Available | Not Available | -3.92 | Unknown | -0.92 | 3981 | 501.14 | -4.84 | 505.98
| 2026-09-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 8 | 6 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.9 | 3981 | 999.88 | 5.9 | 993.98
| 2026-09-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2025-01-29 | Not Available | Not Available | Not Available | Unknown | 4.21 | -12.28 | 0 | 196.69 | -8.07 | 204.76
| 2025-09-06 | Underserved Community | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-03-22 | Not Available | Not Available | Not Available | -4.06 | Unknown | 4.05 | 0 | 153.49 | -0.01 | 153.5
| 2026-02-09 | Underserved Community | SAN DIEGO | N/A | Not Available | 57 | 41 | N/A | 2024-05-15 | Not Available | Not Available | Not Available | -4.93 | Unknown | 0.3 | 0 | 648.92 | -4.63 | 653.55
| 2023-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2023-11-20 | Not Available | Not Available | Not Available | 47.77 | Unknown | 7188.22 | 0 | 158.14 | 7301.07 | -7142.93
| 2026-08-21 | N/A | POWAY | N/A | Not Available | 47 | 33 | N/A | 2024-11-12 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1103.3 | 0 | 1103.3
| 2026-07-22 | Underserved Community | LAKESIDE | N/A | Not Available | 41 | 29 | N/A | 2024-10-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.32 | 0 | 180.5 | 12.32 | 168.18
| 2024-11-29 | Underserved Community | EL CAJON | N/A | Not Available | 118 | 84 | N/A | 2024-06-27 | Not Available | Not Available | Not Available | -11.63 | Unknown | -1.86 | 0 | 499.18 | -13.49 | 512.67
| 2026-07-29 | N/A | POWAY | N/A | Not Available | 33 | 23 | N/A | 2024-11-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.92 | 0 | 197.01 | 7.92 | 189.09
| 2026-08-07 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 111 | 79 | N/A | 2024-12-17 | Not Available | Not Available | Not Available | -0.62 | Unknown | 36.61 | 0 | 190.44 | 35.99 | 154.45
| 2026-09-08 | N/A | SAN DIEGO | N/A | Not Available | 132 | 94 | N/A | 2025-01-24 | Not Available | Not Available | Not Available | 515.15 | Unknown | 363.24 | 0 | 197.01 | 1023.88 | -826.87
| 2026-09-19 | N/A | SAN DIEGO | N/A | Not Available | 49 | 35 | N/A | 2024-11-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.65 | 0 | 197.01 | 4.65 | 192.36
| 2026-09-12 | N/A | SAN DIEGO | N/A | Not Available | 80 | 58 | N/A | 2024-11-21 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.37 | 0 | 197.01 | 6.37 | 190.64
| 2026-07-15 | Underserved Community | SPRING VALLEY | N/A | Not Available | 12 | 8 | N/A | 2024-09-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 60.76 | 0 | 1066.51 | 60.76 | 1005.75
| 2026-10-14 | Underserved Community | ESCONDIDO | N/A | Not Available | 43 | 31 | N/A | 2025-01-17 | Not Available | Not Available | Not Available | 491.71 | Unknown | 314.08 | 0 | 197.01 | 878.29 | -681.28
| 2026-03-27 | N/A | SAN MARCOS | N/A | Not Available | 115 | 83 | N/A | 2024-11-20 | Not Available | Not Available | Not Available | Unknown | 4.44 | -40.26 | 3981 | 141.76 | -35.82 | 177.58
| 2024-01-13 | N/A | MISSION VIEJO | N/A | Not Available | 210 | 150 | N/A | 2023-05-26 | Not Available | Not Available | Not Available | -14.52 | Unknown | -5.52 | 0 | 67.06 | -20.04 | 87.1
| 2025-04-19 | Underserved Community | SAN DIEGO | N/A | Not Available | 151 | 109 | N/A | 2024-01-11 | Not Available | Not Available | Not Available | -11.3 | Unknown | 20.25 | 3981 | 465.36 | 8.95 | 456.41
| 2025-03-14 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 192 | 138 | N/A |  | Not Available | Not Available | Not Available | 378.69 | 11.34 | 1868.49 | 0 | 2015.13 | 2258.52 | -243.39
| 2026-10-31 | N/A | SAN DIEGO | N/A | Not Available | 64 | 46 | N/A | 2024-12-27 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.12 | 0 | 197.01 | 7.12 | 189.89
| 2026-08-23 | Underserved Community | VISTA | N/A | Not Available | 57 | 41 | N/A | 2025-06-03 | Not Available | Not Available | Not Available | 1231.33 | Unknown | 1411.46 | 0 | 1786.42 | 2642.79 | -856.37
| 2026-01-02 | Underserved Community | SAN DIEGO | N/A | Not Available | 42 | 30 | N/A | 2025-02-28 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.07 | 0 | 997.93 | 9.07 | 988.86
| 2025-11-27 | Underserved Community | OCEANSIDE | N/A | Not Available | 27 | 19 | N/A | 2024-11-19 | Not Available | Not Available | Not Available | Unknown | 84.76 | -572.86 | 0 | 279.3 | -488.1 | 767.4
| 2025-09-18 | N/A | SAN DIEGO | N/A | Not Available | 101 | 73 | N/A | 2024-12-05 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.03 | 0 | 197.01 | 9.03 | 187.98
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 30 | 21 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 31 | 22 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2023-08-17 | Underserved Community | SAN MARCOS | N/A | Not Available | 133 | 95 | N/A | 2023-04-12 | Not Available | Not Available | Not Available | -35.77 | Unknown | -12.45 | 0 | 144.8 | -48.22 | 193.02
| 2026-06-14 | Underserved Community | SAN DIEGO | N/A | Not Available | 11 | 9 | N/A | 2024-08-01 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.04 | 0 | 2810.38 | 3.04 | 2807.34
| 2027-01-06 | Underserved Community | ESCONDIDO | N/A | Not Available | 22 | 16 | N/A | 2025-03-31 | Not Available | Not Available | Not Available | -13.33 | Unknown | -7.23 | 0 | 999.91 | -20.56 | 1020.47
| 2026-08-12 | N/A | SAN DIEGO | N/A | Not Available | 18 | 14 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | 606.24 | Unknown | 431.01 | 0 | 197.01 | 1227.85 | -1030.84
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | 23 | 17 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | 599.07 | Unknown | 373.73 | 0 | 197.01 | 1024.33 | -827.32
| 2026-09-02 | Underserved Community | CHULA VISTA | N/A | Not Available | 34 | 24 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | -0.63 | Unknown | 34.34 | 0 | 197.01 | 33.71 | 163.3
| 2026-07-17 | Underserved Community | SAN DIEGO | N/A | Not Available | 47 | 33 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | 266.88 | Unknown | 193.4 | 0 | 180.5 | 581.44 | -400.94
| 2026-09-20 | N/A | SAN DIEGO | N/A | Not Available | 33 | 25 | N/A | 2024-11-05 | Not Available | Not Available | Not Available | 46.36 | Unknown | 64.27 | 0 | 197.01 | 110.63 | 86.38
| 2026-12-16 | Underserved Community | EL CAJON | N/A | Not Available | 71 | 51 | N/A | 2025-03-19 | Not Available | Not Available | Not Available | -19.93 | Unknown | -10.86 | 0 | 1032.15 | -30.79 | 1062.94
| 2026-08-14 | N/A | SAN DIEGO | N/A | Not Available | 100 | 72 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.53 | 0 | 197.01 | 8.53 | 188.48
| 2026-10-22 | N/A | CARDIFF | N/A | Not Available | 17 | 13 | N/A | 2025-02-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.66 | 0 | 315.66 | 7.66 | 308
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 22 | 16 | N/A | 2024-09-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.4 | 0 | 186.52 | 11.4 | 175.12
| 2024-07-18 | Underserved Community | SAN DIEGO | N/A | Not Available | 117 | 83 | N/A | 2025-03-12 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.52 | 0 | 1066.51 | 4.52 | 1061.99
| 2025-04-16 | N/A | SOLANA BEACH | N/A | Not Available | 43 | 31 | N/A | 2024-05-21 | Not Available | Not Available | Not Available | -4.27 | Unknown | -0.99 | 0 | 104.94 | -5.26 | 110.2
| 2026-09-06 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 15 | 11 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.88 | 0 | 1066.51 | 4.88 | 1061.63
| 2026-10-15 | Underserved Community | ESCONDIDO | N/A | Not Available | 52 | 38 | N/A | 2024-12-26 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.47 | 0 | 1066.6 | 9.47 | 1057.13
| 2026-11-20 | N/A | SAN DIEGO | N/A | Not Available | 27 | 19 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.23 | 0 | 196.69 | 10.23 | 186.46
| 2026-08-27 | N/A | SAN DIEGO | N/A | Not Available | 119 | 85 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.69 | 3981 | 197.01 | 5.69 | 191.32
| 2026-09-13 | N/A | LA JOLLA | N/A | Not Available | 97 | 69 | N/A | 2025-01-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.57 | 0 | 1066.51 | 8.57 | 1057.94
| 2026-08-17 | Underserved Community | ESCONDIDO | N/A | Not Available | 88 | 62 | N/A | 2024-12-09 | Not Available | Not Available | Not Available | Unknown | Unknown | 6.84 | 0 | 197.01 | 6.84 | 190.17
| 2026-08-18 | Underserved Community | SAN MARCOS | N/A | Not Available | 55 | 39 | N/A | 2024-11-08 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.91 | 0 | 197.01 | 2.91 | 194.1
| 2026-09-10 | Underserved Community | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2024-11-26 | Not Available | Not Available | Not Available | -31.37 | Unknown | 1556.88 | 0 | 1066.51 | 1525.51 | -459
| 2026-09-03 | Underserved Community | SAN MARCOS | N/A | Not Available | 91 | 65 | N/A | 2024-12-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 5.98 | 0 | 197.01 | 5.98 | 191.03
| 2026-10-10 | Underserved Community | JACUMBA | N/A | Not Available | 106 | 76 | N/A | 2025-03-27 | Not Available | Not Available | Not Available | 1431.33 | Unknown | 1262.54 | 0 | 1066.51 | 2743.8 | -1677.29
| 2026-08-27 | N/A | SAN DIEGO | N/A | Not Available | 91 | 65 | N/A | 2024-11-18 | Not Available | Not Available | Not Available | Unknown | Unknown | 12.84 | 0 | 197.01 | 12.84 | 184.17
| 2026-09-07 | Underserved Community | SAN DIEGO | N/A | Not Available | 44 | 32 | N/A | 2024-10-23 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.13 | 0 | 1066.51 | 4.13 | 1062.38
| 2026-08-20 | Underserved Community | CHULA VISTA | N/A | Not Available | 45 | 33 | N/A | 2024-10-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.34 | 0 | 352.02 | 2.34 | 349.68
| 2026-06-25 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 79 | 57 | N/A | 2024-11-04 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.74 | 0 | 197.01 | 11.74 | 185.27
| 2026-12-11 | Underserved Community | SAN DIEGO | N/A | Not Available | 56 | 40 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | -12.49 | Unknown | -4.53 | 0 | 196.69 | -17.02 | 213.71
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 25 | 18 | N/A | 2025-04-22 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-06 | N/A | SAN DIEGO | N/A | Not Available | 23 | 16 | N/A |  | Not Available | Not Available | Not Available | 254.7 | Unknown | 171.3 | 0 | 196.59 | 426 | -229.41
| 2026-01-25 | N/A | ENCINITAS | N/A | Not Available |  |  | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 11.18 | 0 | 163.83 | 11.18 | 152.65
| 2026-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 94 | 68 | N/A | 2025-02-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 4.88 | 0 | 1050.75 | 4.88 | 1045.87
| 2025-01-22 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | 69 | 49 | N/A | 2024-05-10 | Not Available | Not Available | Not Available | -11.58 | Unknown | -2.67 | 0 | 153.26 | -14.25 | 167.51
| 2025-05-31 | N/A | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2023-11-15 | Not Available | Not Available | Not Available | -3.74 | Unknown | -1 | 0 | 513.31 | -4.74 | 518.05
| 2026-05-21 | Underserved Community | CHULA VISTA | N/A | Not Available | 50 | 36 | N/A | 2024-10-14 | Not Available | Not Available | Not Available | -2.81 | Unknown | 151.59 | 0 | 197.01 | 148.78 | 48.23
| 2024-04-17 | N/A | SOLANA BEACH | N/A | Not Available | 43 | 31 | N/A | 2024-01-25 | Not Available | Not Available | Not Available | -4.62 | 2.76 | -6.35 | 0 | 158.79 | -8.21 | 167
| 2025-11-05 | N/A | SAN DIEGO | N/A | Not Available | 45 | 33 | N/A | 2024-12-17 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.74 | 0 | 197.01 | 8.74 | 188.27
| 2026-09-02 | Underserved Community | CHULA VISTA | N/A | Not Available | 34 | 24 | N/A | 2024-10-11 | Not Available | Not Available | Not Available | -0.31 | Unknown | 21.67 | 0 | 197.01 | 21.36 | 175.65
| 2026-09-10 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 105 | 75 | N/A | 2024-12-19 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.58 | 0 | 1066.51 | 7.58 | 1058.93
| 2025-02-15 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | 33 | 24 | N/A |  | Not Available | Not Available | Not Available | 407.84 | Unknown | 217.34 | 0 | 517.29 | 680.33 | -163.04
| 2023-08-24 | Underserved Community | LAKESIDE | N/A | Not Available | 30 | 22 | N/A | 2023-02-28 | Not Available | Not Available | Not Available | -21.33 | Unknown | -8.08 | 3981 | 92.06 | -29.41 | 121.47
| 2026-10-17 | N/A | CARDIFF | N/A | Not Available | 74 | 54 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.46 | 0 | 1066.55 | 3.46 | 1063.09
| 2026-08-27 | Underserved Community | SAN DIEGO | N/A | Not Available | 127 | 91 | N/A | 2025-04-08 | Not Available | Not Available | Not Available | -8.07 | Unknown | 399.42 | 0 | 999.95 | 391.35 | 608.6
| 2026-10-17 | Underserved Community | VALLEY CENTER | N/A | Not Available | 78 | 56 | N/A | 2025-01-23 | Not Available | Not Available | Not Available | 251.36 | Unknown | 169.57 | 3981 | 197.01 | 420.93 | -223.92
| 2025-09-28 | N/A | LA JOLLA | N/A | Not Available | 24 | 18 | N/A | 2024-02-22 | Not Available | Not Available | Not Available | -7.98 | Unknown | -0.64 | 0 | 163.83 | -8.62 | 172.45
| 2024-05-22 | Underserved Community | EL CAJON | N/A | Not Available | 51 | 37 | N/A | 2024-02-02 | Not Available | Not Available | Not Available | -17.65 | Unknown | -4.09 | 0 | 643.81 | -21.74 | 665.55
| 2026-07-18 | Underserved Community | EL CAJON | N/A | Not Available | 172 | 122 | N/A | 2025-05-30 | Not Available | Not Available | Not Available | -1.5 | Unknown | 74.21 | 0 | 1066.55 | 72.71 | 993.84
| 2027-01-06 | Underserved Community | SPRING VALLEY | N/A | Not Available | 17 | 13 | N/A | 2025-01-24 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.57 | 0 | 197.01 | 10.57 | 186.44
| 2026-11-20 | N/A | SAN DIEGO | N/A | Not Available | 25 | 17 | N/A | 2025-02-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 3.15 | 0 | 196.69 | 3.15 | 193.54
| 2025-10-17 | Underserved Community | LA JOLLA | N/A | Not Available | 34 | 24 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | -79.55 | Unknown | 3009.1 | 0 | 197.01 | 2929.55 | -2732.54
| 2025-08-20 | N/A | LAGUNA HILLS | N/A | Not Available | 28 | 20 | N/A | 2024-10-15 | Not Available | Not Available | Not Available | 418.58 | Unknown | 290.56 | 0 | 197.01 | 709.14 | -512.13
| 2026-08-05 | N/A | SAN DIEGO | N/A | Not Available | 75 | 53 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | 2.83 | 434.92 | 0 | 1412.81 | 437.75 | 975.06
| 2026-01-12 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | 134 | 96 | N/A |  | Not Available | Not Available | Not Available | 307.05 | Unknown | 152.8 | 0 | 534.57 | 459.85 | 74.72
| 2026-10-28 | N/A | SAN DIEGO | N/A | Not Available | 66 | 48 | N/A | 2025-01-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.49 | 0 | 197.01 | 7.49 | 189.52
| 2026-08-12 | Underserved Community | SAN DIEGO | N/A | Not Available | 37 | 27 | N/A | 2024-12-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 9.63 | 0 | 1577.5 | 9.63 | 1567.87
| 2027-02-03 | Underserved Community | SANTEE | N/A | Not Available | 21 | 15 | N/A | 2025-03-06 | Not Available | Not Available | Not Available | Unknown | Unknown | 7.64 | 0 | 196.44 | 7.64 | 188.8
| 2026-07-16 | N/A | SAN CLEMENTE | N/A | Not Available | 29 | 21 | N/A | 2024-11-11 | Not Available | Not Available | Not Available | Unknown | Unknown | 10.77 | 3981 | 1523.75 | 10.77 | 1512.98
| 2026-01-26 | N/A | SAN DIEGO | N/A | Not Available | 24 | 18 | N/A | 2025-03-03 | Not Available | Not Available | Not Available | Unknown | 15.43 | -156.56 | 0 | 196.44 | -141.13 | 337.57
| 2026-09-08 | Underserved Community | SAN DIEGO | N/A | Not Available | 162 | 116 | N/A | 2025-02-03 | Not Available | Not Available | Not Available | Unknown | Unknown | 8.99 | 0 | 197.01 | 8.99 | 188.02
| 2026-08-06 | N/A | SAN DIEGO | N/A | Not Available | 77 | 55 | N/A | 2024-12-18 | Not Available | Not Available | Not Available | -12.3 | Unknown | 625.63 | 0 | 888.75 | 613.33 | 275.42

## MPU Ongoing
Per Decision, Main Panel Upgrade (MPU) Data template to only include simple disconnect/reconnect work; All others would fall under Rule 16
MPU Project Identifier | Preliminary Project Data |  |  |  | MPU Specific End To End Data | [7 empty] | MPU Costing Components
Project Identifier # (project #) | Customer Desired Energization Date (Date) | Community type: Disadvantage Community (DAC) Underserved Community Tribal Community | City Project is Located in (City) | AHJ (Authority Having Jurisdiction) for permitting based off Project's location (AHJ) | Size of Installed Main Panel Upgrade (Amps) | Timing to Complete Main Panel Upgrade (Calendar Days) | Timing to Complete Main Panel Upgrade (Business Days) | Reason why upgrade was cancelled and/or rescheduled (Reason) | Main Panel Upgrade - Initial Schedule Date (Date) | Main Panel Upgrade - Rescheduled Date (as needed) (Date) | Additional Time from Initial Scheduled Date to Rescheduled Date (Calendar Days) | Additional Time from Initial Scheduled Date to Rescheduled Date (Business Days) | Total Staffing, Labor, and Material Cost ($$$ - Capital and Expense) | Project Costs ($$$) for anything else IOU covers | Total Construction/Overhead Costs ($$$) | Customer Allowance ($$$) | Estimated Costs ($$$) at Time of Design | Actual Costs ($$$) at Time of Energization | Difference of Estimated and Actual Costs at Time of Energization ($$$)
| 2026-07-26 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | -1.88 | Unknown | 95.93 | 0 | 197.01 | Unknown | Unknown
| 2026-05-16 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 117.46 | Unknown | Unknown
| 2027-04-07 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 118.25 | Unknown | Unknown
| 2027-04-09 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 1.99 | 0 | 118.25 | Unknown | Unknown
| 2026-08-29 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.58 | 0 | 197.01 | Unknown | Unknown
| 2027-03-24 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.39 | 0 | 118.25 | Unknown | Unknown
| 2026-03-28 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 619.9 | 0 | 997.19 | Unknown | Unknown
| 2027-05-13 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | 2025-06-20 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 117.46 | Unknown | Unknown
| 2027-05-14 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 117.46 | Unknown | Unknown
| 2027-05-22 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | 2025-06-13 | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 118.25 | Unknown | Unknown
| 2027-05-14 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 4.5 | 0 | 118.25 | Unknown | Unknown
| 2027-03-14 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 4.39 | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 50.71 | Unknown | 33.47 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 308.51 | Unknown | 203.6 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 76.07 | Unknown | 50.23 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | Unknown | Unknown
| 2027-04-16 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.02 | 0 | 117.46 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 205.67 | Unknown | 135.73 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 50.71 | Unknown | 33.47 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 76.07 | Unknown | 50.23 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 76.07 | Unknown | 50.23 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 308.51 | Unknown | 203.6 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 411.33 | Unknown | 271.43 | 0 | 196.44 | Unknown | Unknown
| 2027-01-14 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 187.18 | Unknown | 496.28 | 0 | 196.69 | Unknown | Unknown
| 2027-04-01 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 3.38 | 0 | 57.62 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 411.33 | Unknown | 271.43 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 76.07 | Unknown | 50.23 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 308.51 | Unknown | 203.6 | 0 | 196.44 | Unknown | Unknown
| 2026-12-23 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 3.94 | 3981 | 196.69 | Unknown | Unknown
| 2027-03-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 2.92 | 3981 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 101.43 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2026-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 98.27 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 318.38 | Unknown | 150.97 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 385.62 | Unknown | 194.85 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 257.08 | Unknown | 178.25 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 191.03 | Unknown | 132.45 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 191.03 | Unknown | 132.45 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 88.11 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 136.01 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2027-02-13 | N/A | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-10-07 | Underserved Community | BOULEVARD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1032.11 | Unknown | Unknown
| 2025-07-01 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2025-12-09 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2027-04-17 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.64 | Unknown | Unknown
| 2025-04-25 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.01 | Unknown | Unknown
| 2027-02-12 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-04-24 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 200.98 | Unknown | Unknown
| 2026-12-18 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-04-14 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-27 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-02-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 797.33 | Unknown | Unknown
| 2025-05-31 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2024-01-22 | N/A | SOUTH LAGUNA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 400.91 | Unknown | Unknown
| 2027-05-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-05-22 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-05-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown
| 2026-02-27 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2027-02-13 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-07-21 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.34 | Unknown | Unknown
| 2026-04-24 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 547.46 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 321.36 | Unknown | 222.82 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 191.03 | Unknown | 132.45 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 202.46 | Unknown | 141.06 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-12-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 999.91 | Unknown | Unknown
| 2026-11-22 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-21 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2025-10-10 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2026-06-07 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 787.98 | Unknown | Unknown
| 2026-04-09 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-08-22 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1059.04 | Unknown | Unknown
| 2026-01-22 | Underserved Community | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-11-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-09-03 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.08 | Unknown | Unknown
| 2025-12-23 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2024-09-22 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-06-06 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 74 | Unknown | Unknown
| 2025-01-25 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 92.06 | Unknown | Unknown
| 2025-01-24 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 400.91 | Unknown | Unknown
| 2025-09-25 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.26 | Unknown | Unknown
| 2025-07-09 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 289.22 | Unknown | 183.45 | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 142 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 191.03 | Unknown | 132.45 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 90.64 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 90.64 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 302.77 | Unknown | 188.12 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2024-02-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 481.24 | Unknown | Unknown
| 2026-12-04 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-10-01 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-10-01 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2271.64 | Unknown | Unknown
| 2027-05-31 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 320.34 | Unknown | Unknown
| 2027-01-16 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 798.34 | Unknown | Unknown
| 2027-05-19 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-11-01 | N/A | RANCHO SANTA FE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2024-10-20 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-10-14 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.08 | Unknown | Unknown
| 2026-09-19 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-06-11 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-10-16 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 279.3 | Unknown | Unknown
| 2025-01-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 668.22 | Unknown | Unknown
| 2027-04-15 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-12-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 483.59 | Unknown | Unknown
| 2025-05-07 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2025-04-15 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 74.16 | Unknown | Unknown
| 2026-11-29 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.95 | Unknown | Unknown
| 2024-12-02 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2024-03-16 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 679.79 | Unknown | 723.19 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 257.08 | Unknown | 178.25 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 229.96 | Unknown | 131.15 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 179.25 | Unknown | 75.99 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 90.64 | 0 | 196.44 | Unknown | Unknown
| 2024-07-17 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown
| 2020-08-30 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 725.48 | Unknown | Unknown
| 2026-08-30 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-04-22 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2027-03-05 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-11-22 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2027-04-21 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2026-12-05 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.64 | Unknown | Unknown
| 2027-04-22 | Underserved Community | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-11 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2024-08-30 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-06-24 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-12-19 | N/A | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-09-19 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.26 | Unknown | Unknown
| 2024-08-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-03-18 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2025-09-13 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2026-11-08 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2025-06-09 | Underserved Community | BONSALL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.75 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 176.75 | Unknown | 115.99 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 132.1 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 192.82 | Unknown | 136.01 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 88.11 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 191.03 | Unknown | 132.45 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 90.64 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 128.54 | Unknown | 94.67 | 0 | 196.44 | Unknown | Unknown
| 2027-02-06 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-02-05 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-03-31 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-03-14 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2026-11-05 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2027-04-05 | N/A | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-01-23 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2027-01-07 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-04-27 | Underserved Community | JULIAN | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.87 | Unknown | Unknown
| 2025-12-18 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 787.09 | Unknown | Unknown
| 2023-08-16 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2027-05-06 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-02-12 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-10-12 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2027-02-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-01-18 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 818.45 | Unknown | Unknown
| 2025-04-09 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 74.16 | Unknown | Unknown
| 2024-09-07 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2024-04-05 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-05-28 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 283.36 | Unknown | Unknown
| 2027-03-05 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-11-14 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 499.96 | Unknown | Unknown
| 2026-12-02 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-01-09 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-18 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 655.1 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-06-28 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1087 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2026-09-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-11-13 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-03 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2024-12-26 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.93 | Unknown | Unknown
| 2026-02-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2027-01-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.04 | Unknown | Unknown
| 2026-09-12 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-01-23 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 189.89 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-01-11 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.87 | Unknown | Unknown
| 2027-03-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-08-21 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.14 | Unknown | Unknown
| 2027-05-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-12-03 | N/A | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2024-05-05 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2027-05-08 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-15 | N/A | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.18 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-03-22 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-07 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-10-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-27 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 529.2 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-09-21 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-08-02 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1126.97 | Unknown | Unknown
| 2024-08-08 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-08-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2025-05-14 | N/A | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3336.08 | Unknown | Unknown
| 2026-01-07 | Underserved Community | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-12-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 408.95 | Unknown | Unknown
| 2027-02-18 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2027-01-27 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-02-02 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 67.23 | Unknown | Unknown
| 2025-09-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2025-07-10 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-06-18 | N/A | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2026-10-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 174.75 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-09-03 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2027-04-25 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-14 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2027-05-21 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-26 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-18 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-02-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2025-01-18 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.57 | Unknown | Unknown
| 2026-04-19 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2024-08-15 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2024-05-24 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2027-05-27 | N/A | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-04-23 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-04-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2025-06-23 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2024-03-13 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2023-11-18 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2024-05-08 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2023-01-02 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 158.51 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2024-12-10 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.26 | Unknown | Unknown
| 2026-09-23 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-02-02 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2026-07-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2027-01-31 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2026-06-26 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2025-12-07 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-04-16 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2026-01-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.57 | Unknown | Unknown
| 2026-01-09 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-30 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1260.77 | Unknown | Unknown
| 2025-01-09 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-06-24 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 139.89 | Unknown | Unknown
| 2026-10-31 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-02-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-07-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 171.92 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2026-03-18 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2026-04-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2026-04-05 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 162.34 | Unknown | Unknown
| 2025-04-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-06-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2024-03-29 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown
| 2026-06-08 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-10-09 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2027-04-21 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 996.71 | Unknown | Unknown
| 2025-07-31 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2027-01-06 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-05-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-08-12 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2027-01-13 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-05-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2025-07-18 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2024-07-12 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 143.91 | Unknown | Unknown
| 2026-08-08 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-04-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2025-07-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.26 | Unknown | Unknown
| 2026-03-22 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown
| 2027-04-02 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-09-28 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-05-23 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2026-11-22 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2027-02-22 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-07-26 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2027-04-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2025-08-29 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 41.57 | Unknown | Unknown
| 2024-08-30 | Underserved Community | PALOMAR MT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1260.93 | Unknown | Unknown
| 2026-11-11 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-12 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-08-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 641.68 | Unknown | Unknown
| 2026-08-28 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-11-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-08-16 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-03-08 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2026-05-07 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2027-01-07 | Underserved Community | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-09-13 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2026-10-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2026-09-23 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 669.27 | Unknown | Unknown
| 2027-06-04 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown
| 2026-11-15 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-08-23 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-06-20 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-09-11 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 518.15 | Unknown | Unknown
| 2024-07-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-08-12 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-09-26 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-01-10 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown
| 2023-12-28 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown
| 2024-12-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2024-08-06 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-02-24 | Underserved Community,Tribal Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 144.8 | Unknown | Unknown
| 2025-07-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 482.43 | Unknown | Unknown
| 2024-12-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 371.82 | Unknown | Unknown
| 2024-05-30 | N/A | RANCHO LA COSTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2027-03-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2026-07-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-03-18 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 655.1 | Unknown | Unknown
| 2025-10-25 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2027-06-16 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-13 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-28 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1328.99 | Unknown | Unknown
| 2025-04-12 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2026-01-04 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-08-31 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-08-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3941 | 190.44 | Unknown | Unknown
| 2027-04-03 | Underserved Community | JULIAN | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.62 | Unknown | Unknown
| 2026-02-01 | Underserved Community | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2027-04-08 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 435.59 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2024-10-24 | N/A | SOUTH LAGUNA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-03-21 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-06-27 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-03-18 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2026-02-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.38 | Unknown | Unknown
| 2026-07-01 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2026-07-25 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2027-02-21 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-09-03 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2024-09-03 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-03-08 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 529.2 | Unknown | Unknown
| 2024-06-03 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-07-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 483.59 | Unknown | Unknown
| 2026-02-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 529.2 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-31 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.62 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-05-30 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2026-12-09 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1032.15 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-12-20 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2026-11-25 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1101.15 | Unknown | Unknown
| 2026-08-12 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2024-07-11 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-03-13 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 162.34 | Unknown | Unknown
| 2024-09-25 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-05-08 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.52 | Unknown | Unknown
| 2026-09-12 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-03-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2027-02-03 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-11-13 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-03-04 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2024-09-22 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2026-03-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-23 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-21 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 196.59 | Unknown | Unknown
| 2024-10-23 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.54 | Unknown | Unknown
| 2025-10-16 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2025-07-07 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-09-11 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-03-21 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2024-06-10 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2026-05-14 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2027-04-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 118.25 | Unknown | Unknown
| 2026-09-03 | N/A | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2025-05-01 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.5 | Unknown | Unknown
| 2025-03-18 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.87 | Unknown | Unknown
| 2027-03-27 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-06-12 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2026-06-11 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2026-06-07 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 788.08 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-04-10 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.01 | Unknown | Unknown
| 2024-02-22 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.67 | Unknown | Unknown
| 2023-10-24 | N/A | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2024-02-06 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2026-04-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 396.91 | Unknown | Unknown
| 2024-09-20 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2024-09-11 | Underserved Community | PINE VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2026-07-11 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-01-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown
| 2024-11-30 | N/A | LAS FLORES | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 91.93 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 157.02 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-01-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2026-03-07 | N/A | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-09 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-07-25 | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1260.93 | Unknown | Unknown
| 2024-05-22 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-04-10 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2024-09-27 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-09-20 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-06-02 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-03-14 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2027-03-03 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-05-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2026-03-26 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-05-01 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-07-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-09-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-06-25 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2024-06-13 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 154.99 | Unknown | Unknown
| 2027-04-30 | Underserved Community | JULIAN | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-06-04 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 192.51 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-07-19 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2027-02-19 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 223.59 | Unknown | Unknown
| 2025-08-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-09-03 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-04-06 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1441.2 | Unknown | Unknown
| 2024-06-05 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 143.91 | Unknown | Unknown
| 2025-08-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2024-10-27 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-11-03 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2027-01-30 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.13 | Unknown | Unknown
| 2026-01-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 501.14 | Unknown | Unknown
| 2027-05-20 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 558.88 | Unknown | Unknown
| 2026-05-15 | N/A | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 192.51 | Unknown | Unknown
| 2025-08-02 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-02-14 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-04-10 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-22 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.88 | Unknown | Unknown
| 2026-08-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2026-12-05 | N/A | LAS FLORES | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-03-27 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 522.89 | Unknown | Unknown
| 2027-04-29 | N/A | COTO DE CAZA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-07-14 | N/A | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 482.43 | Unknown | Unknown
| 2024-01-31 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 95.37 | Unknown | Unknown
| 2024-03-11 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2024-01-11 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2024-02-10 | N/A | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 376.27 | Unknown | Unknown
| 2024-02-20 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 499.96 | Unknown | Unknown
| 2024-01-06 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2024-11-04 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 436.48 | Unknown | Unknown
| 2026-07-23 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-09-05 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1381.13 | Unknown | Unknown
| 2027-03-13 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1164.31 | Unknown | Unknown
| 2026-07-22 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.5 | Unknown | Unknown
| 2026-01-15 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-09-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 501.14 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-10-03 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.88 | Unknown | Unknown
| 2027-04-10 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2024-05-17 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-07-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-02-06 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-04-02 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-26 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-08-22 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-09-30 | Underserved Community | DESCANSO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1037.05 | Unknown | Unknown
| 2023-08-15 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2026-03-29 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2025-02-08 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-03-18 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 655.1 | Unknown | Unknown
| 2027-04-25 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-12-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-02-12 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2025-05-23 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-05-22 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.05 | Unknown | Unknown
| 2024-09-03 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1157.82 | Unknown | Unknown
| 2024-05-25 | Underserved Community | JAMUL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-12-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-07-03 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2027-02-14 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-05-15 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2026-04-24 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.61 | Unknown | Unknown
| 2024-03-10 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.87 | Unknown | Unknown
| 2025-09-06 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 533.61 | Unknown | Unknown
| 2024-06-30 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 143.91 | Unknown | Unknown
| 2027-01-13 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 189.89 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-08 | N/A | COTO DE CAZA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2022-03-19 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2026-03-14 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2027-03-16 | Underserved Community | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-12-07 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 105.72 | Unknown | Unknown
| 2027-01-30 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-08-19 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1131.85 | Unknown | Unknown
| 2027-01-27 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 227.87 | Unknown | Unknown
| 2025-08-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-01-19 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.18 | Unknown | Unknown
| 2027-04-28 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-12-05 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2026-11-17 | Underserved Community | JULIAN | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-06-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 192.95 | Unknown | Unknown
| 2027-06-03 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 419.11 | Unknown | Unknown
| 2026-08-10 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-08-30 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1087 | Unknown | Unknown
| 2027-01-08 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-04-25 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown
| 2025-07-06 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2027-03-25 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1029.34 | Unknown | Unknown
| 2024-08-15 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-04-22 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-10-06 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2024-12-05 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-03-29 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2024-08-09 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2024-07-25 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 528.12 | Unknown | Unknown
| 2025-12-27 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2026-03-26 | Disadvantaged Community,Underserved Community,Tribal Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown
| 2026-12-02 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1103.34 | Unknown | Unknown
| 2026-10-10 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2025-05-06 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 984.98 | Unknown | Unknown
| 2026-01-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 501.14 | Unknown | Unknown
| 2025-11-08 | N/A | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1032.15 | Unknown | Unknown
| 2027-02-19 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-05-06 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 192.51 | Unknown | Unknown
| 2024-01-06 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 376.27 | Unknown | Unknown
| 2025-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 797.87 | Unknown | Unknown
| 2024-02-15 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown
| 2024-02-20 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 495.75 | Unknown | Unknown
| 2024-02-21 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.66 | Unknown | Unknown
| 2025-01-26 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2023-08-08 | N/A | CAPISTRANO BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 436.48 | Unknown | Unknown
| 2024-03-16 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown
| 2025-02-27 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.78 | Unknown | Unknown
| 2024-06-06 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2025-10-27 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-02 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-02-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2026-05-30 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-09-30 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2026-03-02 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 529.2 | Unknown | Unknown
| 2025-08-21 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown
| 2025-03-16 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.87 | Unknown | Unknown
| 2024-04-27 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.87 | Unknown | Unknown
| 2025-04-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-10-01 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-05-31 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-03-18 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-02 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2026-04-04 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2023-12-15 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-09-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-07-11 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2027-04-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 118.25 | Unknown | Unknown
| 2025-09-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-04-16 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.78 | Unknown | Unknown
| 2026-02-27 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-12-16 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.95 | Unknown | Unknown
| 2026-03-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2025-05-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2025-05-28 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-10-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-05-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-03-25 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown
| 2024-09-08 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2025-10-02 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-09-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-09 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-06-06 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.28 | Unknown | Unknown
| 2024-04-25 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.52 | Unknown | Unknown
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 207.92 | Unknown | Unknown
| 2024-05-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-03-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2027-02-13 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-10-19 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2024-03-03 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-08-13 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1103.3 | Unknown | Unknown
| 2027-01-15 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-01-30 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2025-02-18 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-03-16 | N/A | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.78 | Unknown | Unknown
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-04-04 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-10-19 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2026-01-24 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 984.98 | Unknown | Unknown
| 2024-01-31 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 158.14 | Unknown | Unknown
| 2023-11-29 | Underserved Community | DESCANSO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2026-11-05 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1066.55 | Unknown | Unknown
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 207.92 | Unknown | Unknown
| 2025-01-17 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2025-05-02 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.74 | Unknown | Unknown
| 2027-03-14 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.69 | Unknown | Unknown
| 2026-04-19 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2024-02-23 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2024-05-05 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 202.87 | Unknown | Unknown
| 2027-02-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2026-10-22 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-02 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-06-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 744.39 | Unknown | Unknown
| 2027-10-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2024-01-12 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2027-03-31 | Underserved Community | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-01-23 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 62.73 | Unknown | Unknown
| 2026-09-12 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-05-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 500.87 | Unknown | Unknown
| 2023-06-20 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2023-12-31 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 202.37 | Unknown | Unknown
| 2027-02-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 189.89 | Unknown | Unknown
| 2027-03-14 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-08-08 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-05-09 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2024-01-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.01 | Unknown | Unknown
| 2027-03-13 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-10-02 | Underserved Community | BORREGO SPRINGS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 142.83 | Unknown | Unknown
| 2026-09-17 | Underserved Community | SAN YSIDRO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2025-05-16 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-09-25 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-04-03 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown
| 2024-05-10 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2025-11-08 | N/A | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-01-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.87 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-03-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2025-11-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.57 | Unknown | Unknown
| 2026-05-29 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2024-06-06 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-08-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2026-08-22 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-08-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-07-17 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-11-14 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2024-09-15 | Underserved Community | BONSALL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2027-03-11 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-02 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 450.11 | Unknown | Unknown
| 2027-04-28 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2025-02-13 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 112.22 | Unknown | Unknown
| 2026-06-05 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.52 | Unknown | Unknown
| 2025-04-19 | N/A | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.04 | Unknown | Unknown
| 2024-06-13 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 143.91 | Unknown | Unknown
| 2025-12-10 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-11-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-07-03 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 143.91 | Unknown | Unknown
| 2024-06-06 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.28 | Unknown | Unknown
| 2026-02-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 156.93 | Unknown | Unknown
| 2027-04-22 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-09-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-09-26 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2025-06-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 500.87 | Unknown | Unknown
| 2024-05-19 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 143.91 | Unknown | Unknown
| 2024-11-03 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2027-03-31 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-04-01 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2024-06-08 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.5 | Unknown | Unknown
| 2026-09-16 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-26 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2027-04-07 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-04-13 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.04 | Unknown | Unknown
| 2025-06-06 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2024-03-06 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-07-09 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-06-13 | Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 282.95 | Unknown | Unknown
| 2025-01-18 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 364.52 | Unknown | Unknown
| 2025-08-29 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2026-12-04 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-03-15 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2026-12-09 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2024-04-18 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2024-03-06 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.81 | Unknown | Unknown
| 2027-03-26 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.42 | Unknown | Unknown
| 2025-01-13 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 207.92 | Unknown | Unknown
| 2026-04-18 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2027-05-11 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-01-03 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-01-29 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-08-29 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2027-02-24 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-02-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 209.87 | Unknown | Unknown
| 2025-05-22 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.75 | Unknown | Unknown
| 2025-08-20 | Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2023-12-10 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.53 | Unknown | Unknown
| 2026-12-17 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-04-03 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 345.13 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2025-07-13 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 500.87 | Unknown | Unknown
| 2024-06-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 744.39 | Unknown | Unknown
| 2024-05-10 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 202.87 | Unknown | Unknown
| 2024-03-06 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-11-21 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 929.65 | Unknown | Unknown
| 2027-02-13 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 493.55 | Unknown | Unknown
| 2026-08-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2026-10-23 | Underserved Community | CAMPO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-04-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown
| 2025-05-15 | Underserved Community | BORREGO SPRINGS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 547.46 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-03-21 | Underserved Community | BORREGO SPRINGS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-04-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 400.94 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-16 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-01-22 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-11-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2024-04-24 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-09-05 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-08-22 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-10-09 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2025-04-03 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-10-04 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-08-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-04-26 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 198.18 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-06-12 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2024-05-10 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2026-05-24 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-04-09 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2024-11-21 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.66 | Unknown | Unknown
| 2025-10-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-10-22 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-09-19 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.54 | Unknown | Unknown
| 2025-05-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-10-02 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 207.92 | Unknown | Unknown
| 2025-05-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2026-08-26 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-06-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-09-30 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2024-06-02 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-03-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-03-14 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.62 | Unknown | Unknown
| 2025-09-18 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 910.75 | Unknown | Unknown
| 2027-05-26 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 150.77 | Unknown | Unknown
| 2027-01-28 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-10 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2027-05-05 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-11-07 | Underserved Community | SAN YSIDRO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2026-08-31 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-01-10 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 98.41 | Unknown | Unknown
| 2025-07-24 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown
| 2026-12-19 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2024-09-28 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2024-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2025-03-26 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown
| 2026-03-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-02-06 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 154.79 | Unknown | Unknown
| 2025-03-06 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-07-16 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-05-04 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-11-08 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-11-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2024-01-09 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-05-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2439.17 | Unknown | Unknown
| 2026-02-05 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.57 | Unknown | Unknown
| 2025-02-21 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 396.91 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-05-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2027-05-06 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 432.62 | Unknown | Unknown
| 2026-11-01 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.72 | Unknown | Unknown
| 2025-04-27 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown
| 2026-04-23 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 983.86 | Unknown | Unknown
| 2025-07-14 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2026-04-26 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.61 | Unknown | Unknown
| 2023-12-22 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 98.41 | Unknown | Unknown
| 2026-07-10 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 283.53 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-03-15 | N/A | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.78 | Unknown | Unknown
| 2026-04-18 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 38.41 | Unknown | Unknown
| 2024-08-29 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-02-04 | Underserved Community | CAMPO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2026-11-07 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-09-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.04 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2025-07-12 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2025-01-16 | Underserved Community | Oceanside | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-08-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-11-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 156.93 | Unknown | Unknown
| 2025-09-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2024-04-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2025-06-02 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 483.59 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-07-25 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1341.26 | Unknown | Unknown
| 2026-08-29 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-05-24 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-04-06 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-12-10 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2025-01-03 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 371.82 | Unknown | Unknown
| 2027-02-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 797.33 | Unknown | Unknown
| 2027-02-26 | N/A | RANCHO LA COSTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-11-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2027-03-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2023-03-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-07-08 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 102.37 | Unknown | Unknown
| 2026-09-17 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.08 | Unknown | Unknown
| 2024-05-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
| 2026-10-01 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2027-03-21 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-11 | N/A | LAS FLORES | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 57.62 | Unknown | Unknown
| 2026-09-17 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.82 | Unknown | Unknown
| 2026-10-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 374 | Unknown | Unknown
| 2025-08-16 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 46.04 | Unknown | Unknown
| 2024-10-07 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 74 | Unknown | Unknown
| 2025-12-29 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 209.87 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2024-06-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 744.39 | Unknown | Unknown
| 2024-11-30 | N/A | CAPISTRANO BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 76.18 | Unknown | Unknown
| 2023-11-08 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-12-19 | N/A | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-06-30 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-11-23 | N/A | RANCHO LA COSTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-11-19 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-03-01 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-12-15 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2024-12-11 | N/A | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2023-11-08 | N/A | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-08-21 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-03-04 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2027-02-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2026-08-18 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2025-05-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.7 | Unknown | Unknown
| 2024-06-14 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 154.99 | Unknown | Unknown
| 2026-06-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-12-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1135.78 | Unknown | Unknown
| 2020-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1576 | Unknown | Unknown
| 2025-04-04 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 425.49 | Unknown | Unknown
| 2026-12-11 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-06-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 744.39 | Unknown | Unknown
| 2024-06-29 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 744.39 | Unknown | Unknown
| 2026-09-18 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-11 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2026-05-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-01-18 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-02-07 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 1000 | 154.79 | Unknown | Unknown
| 2027-02-25 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2027-05-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2026-09-19 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.72 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2027-01-30 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-09-14 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 261.57 | Unknown | Unknown
| 2026-12-11 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-11-07 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.14 | Unknown | Unknown
| 2024-05-08 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2026-01-09 | Underserved Community | BONSALL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.18 | Unknown | Unknown
| 2025-09-19 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown
| 2025-06-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 386.87 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-05-09 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-07-24 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown
| 2026-05-15 | N/A | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 192.95 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2025-07-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2026-04-03 | N/A | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown
| 2026-07-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2024-07-13 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2026-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-07-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2023-10-03 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 89.01 | Unknown | Unknown
| 2026-09-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-08-12 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-04-28 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 531.02 | Unknown | Unknown
| 2024-04-19 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2026-09-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-12-02 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-04-28 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-10-28 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2025-09-22 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 483.59 | Unknown | Unknown
| 2024-05-16 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 497.98 | Unknown | Unknown
| 2025-12-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.26 | Unknown | Unknown
| 2025-10-09 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1202.76 | Unknown | Unknown
| 2026-05-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 192.95 | Unknown | Unknown
| 2025-08-02 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown
| 2025-07-17 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2024-03-31 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2025-08-22 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-05-30 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2025-04-11 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.87 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-12-19 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 184 | Unknown | Unknown
| 2025-05-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.7 | Unknown | Unknown
| 2027-02-08 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 196.44 | Unknown | Unknown
| 2025-01-23 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 1000 | 154.79 | Unknown | Unknown
| 2027-03-21 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-09-09 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2027-04-01 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 57.62 | Unknown | Unknown
| 2025-09-04 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-11-20 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-02-26 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.69 | Unknown | Unknown
| 2025-02-27 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.44 | Unknown | Unknown
| 2025-05-11 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 40.04 | Unknown | Unknown
| 2025-10-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2027-02-14 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.93 | Unknown | Unknown
| 2025-11-21 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-12-10 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown
| 2027-03-07 | N/A | RANCHO SANTA FE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2025-05-22 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-02-10 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-19 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-12-26 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.72 | Unknown | Unknown
| 2026-07-08 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 102.37 | Unknown | Unknown
| 2025-05-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 483.59 | Unknown | Unknown
| 2026-12-28 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.13 | Unknown | Unknown
| 2026-08-23 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2024-06-28 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 143.91 | Unknown | Unknown
| 2027-05-15 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-04-03 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.53 | Unknown | Unknown
| 2026-11-04 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-16 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2027-03-02 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.69 | Unknown | Unknown
| 2024-02-06 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 154.79 | Unknown | Unknown
| 2027-02-19 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2026-09-24 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2026-02-20 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-10-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-05-25 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-05-19 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-10-10 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-01-30 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 207.92 | Unknown | Unknown
| 2026-10-07 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 142.83 | Unknown | Unknown
| 2027-03-13 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-02-15 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 95.13 | Unknown | Unknown
| 2025-08-17 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 386.87 | Unknown | Unknown
| 2025-02-03 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2027-01-24 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2026-08-01 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 102.37 | Unknown | Unknown
| 2023-12-10 | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2024-09-11 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2027-01-15 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-07-15 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-01-22 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2023-10-27 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-04-18 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 787.09 | Unknown | Unknown
| 2026-12-18 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-11-30 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 76.18 | Unknown | Unknown
| 2026-11-25 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2026-05-14 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2025-05-25 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2026-03-10 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-01-20 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 376.27 | Unknown | Unknown
| 2027-04-09 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-01-24 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 499.96 | Unknown | Unknown
| 2027-03-24 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-22 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2023-10-12 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 615.98 | Unknown | Unknown
| 2027-05-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1010.55 | Unknown | Unknown
| 2027-05-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 113.54 | Unknown | Unknown
| 2026-05-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-06-10 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-06 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2027-06-08 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-01-22 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 118.25 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2026-02-13 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2025-07-17 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2026-03-11 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2024-07-18 | N/A | SOUTH LAGUNA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2025-02-13 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-12-30 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 189.89 | Unknown | Unknown
| 2026-09-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-04-03 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-07-18 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 209.87 | Unknown | Unknown
| 2026-10-01 | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-02-05 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2023-12-16 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-07-01 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 279.3 | Unknown | Unknown
| 2024-08-02 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown
| 2025-05-19 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 180.5 | Unknown | Unknown
| 2025-12-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.14 | Unknown | Unknown
| 2024-01-06 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 154.79 | Unknown | Unknown
| 2025-06-23 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown
| 2024-04-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2023-09-16 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2026-11-18 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-12-09 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-01-14 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-08-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.22 | Unknown | Unknown
| 2025-12-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2025-07-22 | Underserved Community | SAN YSIDRO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2024-03-28 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.06 | Unknown | Unknown
| 2023-11-22 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 92.06 | Unknown | Unknown
| 2025-12-18 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2025-02-11 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.16 | Unknown | Unknown
| 2024-04-05 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-07-15 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 879.74 | Unknown | Unknown
| 2023-04-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 532.86 | Unknown | Unknown
| 2026-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2024-04-04 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-03-10 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2025-07-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2027-04-01 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-02-23 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2027-05-22 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 447.04 | Unknown | Unknown
| 2027-05-05 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-06-11 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-06-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-06 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 57.62 | Unknown | Unknown
| 2027-05-21 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2027-05-21 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown
| 2027-06-17 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-04-08 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-16 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2027-04-21 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-12-06 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1329 | Unknown | Unknown
| 2027-04-09 | N/A | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-03-31 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-04-01 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-14 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-14 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 109.88 | Unknown | Unknown
| 2027-06-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 462.47 | Unknown | Unknown
| 2027-04-22 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | 2025-05-20 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-22 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-22 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-04-03 | Underserved Community | PALA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-05-21 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-14 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-05-01 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 435.59 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2026-07-01 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 310.2 | Unknown | Unknown
| 2027-03-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-09-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-01-27 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-03-06 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-03-19 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-11-06 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2026-10-06 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-08-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown
| 2026-06-07 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2025-10-03 | Underserved Community | JAMUL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-09-18 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-12-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-07-24 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2024-10-30 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2023-12-31 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2025-04-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-03-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 190.44 | Unknown | Unknown
| 2023-03-09 | N/A | RANCHO SANTA FE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.7 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2023-11-29 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-05-31 | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.6 | Unknown | Unknown
| 2027-04-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-02-26 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.4 | Unknown | Unknown
| 2027-05-13 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2024-10-21 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-01-09 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2024-06-01 | N/A | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown
| 2027-05-28 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-07 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-01 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-12-08 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 184 | Unknown | Unknown
| 2027-05-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-04-14 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-29 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-07 | Underserved Community | PALOMAR MT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-12-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-04-25 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 77.99 | Unknown | Unknown
| 2027-04-24 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2026-09-25 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-06-03 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.99 | Unknown | Unknown
| 2027-03-19 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.99 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.99 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-04-08 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 75.89 | Unknown | Unknown
| 2027-03-27 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2025-07-03 | Underserved Community | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-23 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-04-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 189.89 | Unknown | Unknown
| 2025-12-10 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 501.14 | Unknown | Unknown
| 2025-09-22 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2024-05-24 | N/A | COTO DE CAZA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2024-07-11 | N/A | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2026-05-23 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-02-14 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-01-16 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.75 | Unknown | Unknown
| 2026-02-13 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 983.86 | Unknown | Unknown
| 2024-09-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2025-02-17 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2024-09-23 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-10-31 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.79 | Unknown | Unknown
| 2024-01-05 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2024-08-12 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2023-09-21 | N/A | RANCHO SANTA FE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2023-11-21 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-08-07 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2025-10-03 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-07-06 | N/A | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.88 | Unknown | Unknown
| 2026-07-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-08-07 | N/A | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown
| 2023-09-09 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2026-08-22 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-02-21 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-09-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2027-02-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-01-16 | Underserved Community,Tribal Community | PALA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 464.78 | Unknown | Unknown
| 2025-08-21 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown
| 2024-10-12 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2025-04-13 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 594.91 | Unknown | Unknown
| 2027-03-31 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-02-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.53 | Unknown | Unknown
| 2026-04-30 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 529.2 | Unknown | Unknown
| 2027-06-06 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-06-17 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-09 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 432.62 | Unknown | Unknown
| 2027-06-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-06-04 | N/A | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-06-03 | Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2027-03-04 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2027-06-03 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2026-08-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2027-03-20 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2027-04-29 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.71 | Unknown | Unknown
| 2027-05-15 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 442 | Unknown | Unknown
| 2027-04-29 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | 2025-06-27 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-01 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-05-01 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-25 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-05-15 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-03-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-04-22 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-06-16 | N/A | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-04-20 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2027-05-13 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.62 | Unknown | Unknown
| 2027-05-08 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.62 | Unknown | Unknown
| 2025-11-08 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 310.2 | Unknown | Unknown
| 2025-11-16 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2025-04-22 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-09 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2025-09-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-09-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-12-23 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-10-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.91 | Unknown | Unknown
| 2026-09-12 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-05-04 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-10-02 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2025-05-18 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown
| 2025-11-13 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2024-07-13 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2025-01-12 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2023-10-12 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 739.61 | Unknown | Unknown
| 2025-05-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.22 | Unknown | Unknown
| 2024-09-15 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-03-26 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 92.06 | Unknown | Unknown
| 2024-09-21 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.79 | Unknown | Unknown
| 2025-01-27 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2027-03-10 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-21 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.93 | Unknown | Unknown
| 2026-12-17 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 114.3 | Unknown | Unknown
| 2025-07-07 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown
| 2025-05-30 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2024-09-27 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown
| 2026-03-14 | N/A | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.7 | Unknown | Unknown
| 2025-01-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-10-14 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 196.69 | Unknown | Unknown
| 2026-06-25 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-06-29 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.34 | Unknown | Unknown
| 2027-01-09 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-06-03 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-05-14 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2027-06-04 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2027-05-12 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 432.62 | Unknown | Unknown
| 2027-04-08 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-05-26 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 150.77 | Unknown | Unknown
| 2027-05-08 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-11-23 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.13 | Unknown | Unknown
| 2027-02-20 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2027-05-05 | Underserved Community | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-26 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-29 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-07 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-20 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-12-03 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2025-02-06 | N/A | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 273.45 | Unknown | Unknown
| 2024-10-23 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-04-15 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.99 | Unknown | Unknown
| 2025-06-03 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 465.36 | Unknown | Unknown
| 2025-05-01 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1554.67 | Unknown | Unknown
| 2025-10-23 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-04-23 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-11-20 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2023-03-01 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-09-07 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown
| 2024-09-30 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.08 | Unknown | Unknown
| 2026-02-27 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2027-04-24 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2023-01-02 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 625.02 | Unknown | Unknown
| 2025-02-01 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2026-03-12 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2024-09-18 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-05-17 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-08-21 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2024-08-25 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2024-05-12 | Underserved Community | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2024-11-14 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-05-22 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-06-06 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-02-02 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 499.96 | Unknown | Unknown
| 2027-05-16 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2026-10-10 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 999.88 | Unknown | Unknown
| 2027-04-28 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1297.06 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-06 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-06-03 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 453.45 | Unknown | Unknown
| 2027-04-23 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-23 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-06-11 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2027-05-04 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-14 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-03 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 155.38 | Unknown | Unknown
| 2027-02-11 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-07 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-10-29 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-01-04 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-11-01 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2028-05-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 462.47 | Unknown | Unknown
| 2026-10-29 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 109.88 | Unknown | Unknown
| 2026-05-19 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 195.85 | Unknown | Unknown
| 2025-12-08 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1275.73 | Unknown | Unknown
| 2027-03-20 | N/A | SOUTH LAGUNA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2027-06-12 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1057.64 | Unknown | Unknown
| 2027-05-05 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-01-24 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.61 | Unknown | Unknown
| 2027-02-17 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 189.89 | Unknown | Unknown
| 2027-01-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2025-12-31 | Underserved Community | RAMONA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 418.96 | Unknown | Unknown
| 2026-09-17 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-06-08 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2024-04-22 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 656.66 | Unknown | Unknown
| 2025-08-28 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 189.11 | Unknown | Unknown
| 2026-12-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-11-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-09-25 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-07-31 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.95 | Unknown | Unknown
| 2027-04-07 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 776.13 | Unknown | Unknown
| 2026-12-18 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.04 | Unknown | Unknown
| 2026-04-08 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-03-15 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-06-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 670.61 | Unknown | Unknown
| 2027-05-22 | N/A | COTO DE CAZA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-29 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-18 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2024-08-18 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2026-08-22 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2026-06-16 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1267.82 | Unknown | Unknown
| 2025-03-31 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-11-19 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-01-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.99 | Unknown | Unknown
| 2025-05-22 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 533.61 | Unknown | Unknown
| 2027-02-22 | Underserved Community | BONSALL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.38 | Unknown | Unknown
| 2026-05-08 | N/A | ALPINE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-05-21 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-29 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-06-17 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2025-09-19 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-28 | Underserved Community | SANTEE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-10-07 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-04-10 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2027-04-16 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-10-05 | N/A | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-31 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 733.24 | Unknown | Unknown
| 2026-01-14 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-06-03 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-04-28 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-09-25 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-03-06 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-09-07 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2027-01-27 | N/A | RANCHO SANTA FE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-01-02 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2026-02-23 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-05-20 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1402.71 | Unknown | Unknown
| 2026-02-12 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2026-08-04 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2665.55 | Unknown | Unknown
| 2025-03-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1137.56 | Unknown | Unknown
| 2027-03-14 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-07-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2027-05-01 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-12 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-01-14 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.94 | Unknown | Unknown
| 2026-11-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2025-10-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-04-17 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-01-06 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-02-02 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 480.37 | Unknown | Unknown
| 2027-03-06 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 79.48 | Unknown | Unknown
| 2026-05-30 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-06-03 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-04-07 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.73 | Unknown | Unknown
| 2026-09-11 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 335.29 | Unknown | Unknown
| 2027-03-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-03-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 797.75 | Unknown | Unknown
| 2025-01-10 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2025-04-11 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 462.11 | Unknown | Unknown
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 700.5 | Unknown | Unknown
| 2026-07-23 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-10-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | Unknown | Unknown | Unknown
| 2024-05-22 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2026-01-24 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 76.08 | Unknown | Unknown
| 2026-11-11 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-08 | Underserved Community | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 22587 | 158.81 | Unknown | Unknown
| 2024-02-05 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2026-03-18 | Underserved Community | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 119.21 | Unknown | Unknown
| 2023-06-23 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 105.72 | Unknown | Unknown
| 2025-02-02 | Underserved Community | BONSALL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-11-06 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-04-02 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3217.13 | Unknown | Unknown
| 2025-11-07 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 79.48 | Unknown | Unknown
| 2024-09-15 | N/A | CAPISTRANO BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 645.75 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2023-12-14 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2023-06-23 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 218.77 | Unknown | Unknown
| 2025-04-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1838.05 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-09-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-04-03 | N/A | LAS FLORES | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2022-02-13 | N/A | San Diego | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-03-31 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 675.2 | Unknown | Unknown
| 2022-02-13 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1400.87 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-02-22 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 102.29 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 344.81 | Unknown | Unknown
| 2024-05-22 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1678.53 | Unknown | Unknown
| 2025-06-12 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 465.36 | Unknown | Unknown
| 2025-07-20 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | 2024-04-25 | Not Available | Not Available | Not Available | -5.15 | 41.57 | 205.73 | 0 | 41.57 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 310.8 | Unknown | Unknown
| 2023-06-23 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-02-07 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2027-03-04 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 76.04 | Unknown | Unknown
| 2027-03-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-03-22 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2024-04-24 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2024-03-20 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown
| 2024-04-06 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2026-02-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3941 | 186.4 | Unknown | Unknown
| 2026-04-05 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2024-09-19 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1501.35 | Unknown | Unknown
| 2023-09-22 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 67.06 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-10-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1365.86 | Unknown | Unknown
| 2025-04-12 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 103.96 | Unknown | Unknown
| 2027-04-30 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2025-10-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2024-05-02 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2024-06-27 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.59 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2024-06-27 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.59 | Unknown | Unknown
| 2023-06-23 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 4454.26 | Unknown | Unknown
| 2026-08-06 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2024-06-01 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2024-02-22 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 116.77 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 389.9 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 312.3 | Unknown | Unknown
| 2025-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-02-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 196.44 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 389.9 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 312.3 | Unknown | Unknown
| 2027-05-05 | Underserved Community | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-10-16 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-02-02 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 92.3 | Unknown | Unknown
| 2024-10-18 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2027-05-02 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-02-06 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.67 | Unknown | Unknown
| 2023-04-04 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2024-02-27 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2025-03-01 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 84.66 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 344.81 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 299.18 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-08-06 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-04-13 | N/A | ALISO VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.06 | Unknown | Unknown
| 2025-08-15 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 656.75 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-03-23 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 594.91 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2026-05-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2022-04-29 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 173.12 | Unknown | Unknown
| 2024-05-09 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2024-05-24 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2025-02-01 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 337.59 | Unknown | Unknown
| 2024-12-31 | N/A | COTO DE CAZA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 184.29 | Unknown | Unknown
| 2025-10-24 | N/A | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2026-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 344.81 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-12-19 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.7 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 312.3 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 408.42 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 312.3 | Unknown | Unknown
| 2025-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | 2025-06-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-11-02 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1030.1 | Unknown | Unknown
| 2025-02-16 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 236.83 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.96 | Unknown | Unknown
| 2025-07-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-01-30 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 92.06 | Unknown | Unknown
| 2027-05-23 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 1045.46 | Unknown | Unknown
| 2024-03-21 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2024-02-08 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.67 | Unknown | Unknown
| 2027-03-17 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1349.17 | Unknown | Unknown
| 2025-05-12 | Underserved Community | La Jolla | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown
| 2023-02-28 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.67 | Unknown | Unknown
| 2026-08-11 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2024-07-21 | N/A | LADERA RANCH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2024-04-25 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2023-12-29 | N/A | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2024-02-22 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.79 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-11-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-06-09 | Underserved Community | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2024-06-09 | Underserved Community | CAPISTRANO BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2024-04-13 | N/A | SAN CLEMENTE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.06 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 481.71 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-07-02 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 389.9 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 312.3 | Unknown | Unknown
| 2025-03-04 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3941 | 186.09 | Unknown | Unknown
| 2026-07-04 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 312.3 | Unknown | Unknown
| 2027-05-19 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-03-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.13 | Unknown | Unknown
| 2021-07-29 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1271.08 | Unknown | Unknown
| 2024-04-13 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 111.03 | Unknown | Unknown
| 2023-11-28 | Underserved Community | SAN JUAN CAPISTRANO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2024-03-10 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2025-03-31 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2026-09-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-03-06 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2024-02-24 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 379.24 | Unknown | Unknown
| 2023-05-30 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3753.77 | 431.76 | Unknown | Unknown
| 2023-06-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 773.84 | Unknown | Unknown
| 2025-11-03 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-04-19 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown
| 2026-04-30 | Underserved Community | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2024-01-12 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2025-06-13 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2026-03-28 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 139.57 | Unknown | Unknown
| 2025-11-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-04-03 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2025-06-23 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown
| 2024-03-14 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2024-01-21 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 67.06 | Unknown | Unknown
| 2024-06-30 | N/A | SOUTH LAGUNA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-03-05 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 84.66 | Unknown | Unknown
| 2025-12-16 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 344.81 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 154.79 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 344.81 | Unknown | Unknown
| 2025-11-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-06-06 | N/A | SOLANA BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 555.11 | Unknown | Unknown
| 2027-03-11 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-04-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2025-01-05 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 239.38 | Unknown | Unknown
| 2025-12-08 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-06-09 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 428.69 | Unknown | Unknown
| 2027-01-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2027-02-18 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown
| 2027-02-13 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-02-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-11-26 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.44 | Unknown | Unknown
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3232.84 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1892.71 | Unknown | Unknown
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3347.64 | Unknown | Unknown
| 2025-01-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.14 | Unknown | Unknown
| 2027-03-21 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 797.37 | Unknown | Unknown
| 2027-03-04 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown
| 2022-02-13 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 65.52 | Unknown | Unknown
| 2023-06-23 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 452.82 | Unknown | Unknown
| 2023-06-23 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 218.58 | Unknown | Unknown
| 2026-01-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 301.6 | Unknown | Unknown
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 711.08 | Unknown | Unknown
| 2025-04-01 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.38 | Unknown | Unknown
| 2026-02-17 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-03-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 633.01 | Unknown | Unknown
| 2026-05-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2025-09-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | 359.73 | Unknown | 303.71 | 0 | 288.94 | Unknown | Unknown
| 2025-11-26 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.44 | Unknown | Unknown
| 2018-12-31 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1648.49 | Unknown | Unknown
| 2026-03-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2020-12-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 545.68 | Unknown | Unknown
| 2025-06-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1171.36 | Unknown | Unknown
| 2026-03-20 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 150.77 | Unknown | Unknown
| 2025-01-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-04-04 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-01-16 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 421.99 | Unknown | Unknown
| 2026-04-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 449.47 | Unknown | Unknown
| 2026-11-04 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-11-26 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.44 | Unknown | Unknown
| 2022-02-13 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1194.76 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 458.19 | Unknown | Unknown
| 2023-06-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1741.22 | Unknown | Unknown
| 2025-11-04 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.11 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2023-06-23 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 175.97 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2026-02-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1329.61 | Unknown | Unknown
| 2020-03-27 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 743.75 | Unknown | Unknown
| 2026-05-09 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 600.17 | Unknown | Unknown
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3613.66 | Unknown | Unknown
| 2022-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 545.68 | Unknown | Unknown
| 2026-01-22 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2026-03-20 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.69 | Unknown | Unknown
| 2026-04-11 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2026-04-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 527.55 | Unknown | Unknown
| 2025-11-26 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.44 | Unknown | Unknown
| 2020-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 4250.71 | Unknown | Unknown
| 2020-12-31 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2442.63 | Unknown | Unknown
| 2025-01-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.14 | Unknown | Unknown
| 2024-11-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.44 | Unknown | Unknown
| 2025-09-12 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 218.58 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 330.53 | Unknown | Unknown
| 2026-01-06 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 157.02 | Unknown | Unknown
| 2025-05-06 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1032.15 | Unknown | Unknown
| 2025-12-04 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2863.81 | Unknown | Unknown
| 2025-12-15 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2025-11-26 | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.44 | Unknown | Unknown
| 2026-11-20 | Underserved Community | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | 2025-06-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown
| 2025-09-05 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2021-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | 2025-06-30 | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2707.96 | Unknown | Unknown
| 2024-02-22 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.79 | Unknown | Unknown
| 2024-11-06 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 501.14 | Unknown | Unknown
| 2026-04-25 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2025-03-15 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown
| 2024-11-16 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 166.7 | Unknown | Unknown
| 2025-07-02 | N/A | RANCHO LA COSTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2672.39 | Unknown | Unknown
| 2026-09-05 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2025-08-06 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1101.15 | Unknown | Unknown
| 2023-03-01 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 67.06 | Unknown | Unknown
| 2025-03-25 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1142.7 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3323.92 | Unknown | Unknown
| 2018-12-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3406.99 | Unknown | Unknown
| 2025-12-18 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2020.71 | Unknown | Unknown
| 2025-01-20 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.14 | Unknown | Unknown
| 2027-02-04 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2024-01-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 499.96 | Unknown | Unknown
| 2026-03-20 | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 151.78 | Unknown | Unknown
| 2025-11-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 104.77 | Unknown | Unknown
| 2027-04-01 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 675.2 | Unknown | Unknown
| 2022-02-13 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 65.52 | Unknown | Unknown
| 2025-01-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2025-08-15 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1103.3 | Unknown | Unknown
| 2026-12-06 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2027-01-28 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2027-02-13 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 9.43 | 0 | 196.59 | Unknown | Unknown
| 2026-12-09 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2024-08-21 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 513.5 | Unknown | Unknown
| 2027-04-21 | Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.71 | Unknown | Unknown
| 2027-05-02 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.64 | Unknown | Unknown
| 2026-02-27 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 162.34 | Unknown | Unknown
| 2024-11-12 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 96.43 | Unknown | Unknown
| 2025-01-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 985.1 | Unknown | Unknown
| 2027-04-21 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 85.73 | Unknown | Unknown
| 2024-08-03 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 451.25 | Unknown | Unknown
| 2024-08-02 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 2891 | 540.15 | Unknown | Unknown
| 2024-10-01 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2024-05-09 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1447.41 | Unknown | Unknown
| 2025-12-23 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1064.43 | Unknown | Unknown
| 2025-02-27 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1103.73 | Unknown | Unknown
| 2025-07-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 7962 | 3259.16 | Unknown | Unknown
| 2026-04-15 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 675.2 | Unknown | Unknown
| 2025-06-17 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2025-05-30 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.27 | Unknown | Unknown
| 2025-11-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.55 | Unknown | Unknown
| 2026-10-17 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2024-05-09 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1447.41 | Unknown | Unknown
| 2025-11-19 | Underserved Community | LA MESA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 411.7 | Unknown | Unknown
| 2024-06-06 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown
| 2026-09-04 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-12-06 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 446.88 | Unknown | Unknown
| 2027-04-14 | N/A | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-06-06 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2025-06-28 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | -13.7 | Unknown | -705.12 | 0 | 932.56 | Unknown | Unknown
| 2027-02-11 | Underserved Community | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 392.11 | Unknown | Unknown
| 2027-04-03 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-12-09 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2026-02-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 408.95 | Unknown | Unknown
| 2024-06-29 | N/A | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown
| 2027-04-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-09-13 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown
| 2025-06-26 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 3671.6 | Unknown | Unknown
| 2025-04-08 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown
| 2025-11-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 101.44 | Unknown | Unknown
| 2025-10-09 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3941 | 158.37 | Unknown | Unknown
| 2027-01-29 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2476.55 | Unknown | Unknown
| 2023-06-23 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3753.77 | 104.74 | Unknown | Unknown
| 2024-08-31 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2025-07-13 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown
| 2025-04-19 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 594.91 | Unknown | Unknown
| 2025-08-10 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.22 | Unknown | Unknown
| 2025-01-30 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 700.41 | Unknown | Unknown
| 2026-08-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.13 | Unknown | Unknown
| 2026-01-29 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown
| 2027-02-10 | N/A | CARDIFF | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 278.69 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-01-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 857.76 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-03-21 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 186.52 | Unknown | Unknown
| 2027-04-18 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 155.17 | Unknown | Unknown
| 2027-02-26 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-11-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2026-05-29 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2025-12-04 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1085.63 | Unknown | Unknown
| 2027-05-21 | Underserved Community | EL CAJON | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-05-20 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown
| 2027-06-25 | Underserved Community | IMPERIAL BEACH | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 432.62 | Unknown | Unknown
| 2026-12-06 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown
| 2027-03-05 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-04-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 419.11 | Unknown | Unknown
| 2025-07-10 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown
| 2027-05-18 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 969.63 | Unknown | Unknown
| 2027-02-24 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 196.59 | Unknown | Unknown
| 2025-08-22 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.13 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown
| 2027-03-28 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown
| 2027-03-10 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 196.59 | Unknown | Unknown
| 2027-01-27 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2025-06-04 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown
| 2026-04-04 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1063.13 | Unknown | Unknown
| 2026-07-26 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2025-08-21 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2027-04-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-04-17 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown
| 2026-05-14 | N/A | DEL MAR | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 985.1 | Unknown | Unknown
| 2026-01-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1028.79 | Unknown | Unknown
| 2026-12-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown
| 2027-05-24 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown
| 2026-10-14 | Underserved Community | OCEANSIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2027-06-10 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 279.44 | Unknown | Unknown
| 2027-03-29 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 114.3 | Unknown | Unknown
| 2027-04-10 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 183.71 | Unknown | Unknown
| 2027-06-03 | Underserved Community | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2024-09-24 | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 9613.41 | Unknown | Unknown
| 2025-11-04 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 288.94 | Unknown | Unknown
| 2027-05-02 | N/A | DANA POINT | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2024-10-06 | N/A | LAGUNA NIGUEL | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 148.54 | Unknown | Unknown
| 2026-11-19 | Underserved Community | ESCONDIDO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 562.71 | Unknown | Unknown
| 2027-05-09 | Underserved Community | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-06-03 | Underserved Community | LAGUNA HILLS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-04-10 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2027-05-04 | Underserved Community | VALLEY CENTER | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2026-01-01 | Underserved Community | CHULA VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown
| 2027-01-25 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 142.42 | Unknown | Unknown
| 2025-01-16 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 341 | Unknown | Unknown
| 2027-02-24 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | 1.76 | 0 | 196.59 | Unknown | Unknown
| 2025-05-15 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown
| 2027-01-15 | Underserved Community | LEMON GROVE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 435.59 | Unknown | Unknown
| 2027-04-08 | Underserved Community | LAKESIDE | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2026-08-19 | N/A | CORONADO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown
| 2027-02-19 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1100.34 | Unknown | Unknown
| 2023-08-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 2801.91 | Unknown | Unknown
| 2027-04-09 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown
| 2026-07-18 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-10-25 | N/A | MISSION VIEJO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2023-08-02 | N/A | POWAY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 819.44 | Unknown | Unknown
| 2027-01-03 | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.13 | Unknown | Unknown
| 2024-08-26 | Underserved Community | FALLBROOK | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-07-19 | Underserved Community | BONITA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-04-01 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 984.98 | Unknown | Unknown
| 2026-07-25 | Underserved Community | SAN MARCOS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 861.4 | Unknown | Unknown
| 2026-12-19 | Underserved Community | SPRING VALLEY | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-01-16 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 447.04 | Unknown | Unknown
| 2026-11-12 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 435.59 | Unknown | Unknown
| 2025-09-05 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 98.3 | Unknown | Unknown
| 2023-11-01 | N/A | SOUTH LAGUNA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown
| 2025-04-27 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 465.36 | Unknown | Unknown
| 2025-10-19 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 153.26 | Unknown | Unknown
| 2027-02-11 | N/A | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown
| 2027-01-29 | N/A | CARLSBAD | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown
| 2026-02-07 | N/A | ENCINITAS | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 361.03 | Unknown | Unknown
| 2024-12-07 | Underserved Community | VISTA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown
| 2026-10-31 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown
| 2025-10-14 | N/A | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown
| 2026-06-17 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown
| 2026-01-24 | Underserved Community | LA JOLLA | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown
| 2026-07-29 | Underserved Community | SAN DIEGO | N/A | Not Available | Unknown | Unknown | N/A | Unknown | Not Available | Not Available | Not Available | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown

## MPU Cancelled-Rejected
Per Decision, Main Panel Upgrade (MPU) Data template to only include simple disconnect/reconnect work; All others would fall under Rule 16
MPU Project Identifier | Preliminary Project Data |  |  |  | MPU Specific End To End Data | [7 empty] | MPU Costing Components
Project Identifier # (project #) | Customer Desired Energization Date (Date) | Community type: Disadvantage Community (DAC) Underserved Community Tribal Community | City Project is Located in (City) | AHJ (Authority Having Jurisdiction) for permitting based off Project's location (AHJ) | Size of Installed Main Panel Upgrade (Amps) | Timing to Complete Main Panel Upgrade (Calendar Days) | Timing to Complete Main Panel Upgrade (Business Days) | Reason why upgrade was cancelled and/or rescheduled (Reason) | Main Panel Upgrade - Initial Schedule Date (Date) | Main Panel Upgrade - Rescheduled Date (as needed) (Date) | Additional Time from Initial Scheduled Date to Rescheduled Date (Calendar Days) | Additional Time from Initial Scheduled Date to Rescheduled Date (Business Days) | Total Staffing, Labor, and Material Cost ($$$ - Capital and Expense) | Project Costs ($$$) for anything else IOU covers | Total Construction/Overhead Costs ($$$) | Customer Allowance ($$$) | Estimated Costs ($$$) at Time of Design | Actual Costs ($$$) at Time of Energization | Difference of Estimated and Actual Costs at Time of Energization ($$$)
| N/A | N/A | PAUMA VALLEY | N/A | N/A | N/A | N/A | Cancelled/Rejected per customer request | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LADERA RANCH | N/A | N/A | N/A | N/A | Cancelled/Rejected - Duplicate | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | Cancelled/Rejected per customer request | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA NIGEL | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA HILLS | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | MISSION VIEJO | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA HILLS | N/A | N/A | N/A | N/A | Cancelled - Utilized for billing purposes only | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | BORREGO SPRINGS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CAMPO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VALLEY CENTER | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | MISSION VIEJO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA NIGEL | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAS FLORES | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | COTO DE CAZA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | JAMUL | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LEMON GROVE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | EL CAJON | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN CLEMENTE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN JUAN CAPISTRANO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | DANA POINT | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA HILLS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA JOLLA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA NIGEL | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | JULIAN | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARDIFF | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LA MESA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARDIFF | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | LAGUNA NIGEL | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | DEL MAR | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ALPINE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | BONITA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SPRING VALLEY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CHULA VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ESCONDIDO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | FALLBROOK | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | RANCHO LA COSTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | OCEANSIDE | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN MARCOS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | JULIAN | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | VISTA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POWAY | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | ENCINITAS | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | SAN DIEGO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | RAMONA | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | POTRERO | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| N/A | N/A | CARLSBAD | N/A | N/A | N/A | N/A | Cancelled - not needed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Notes
Notes
General
In addition to solar only jobs, SDG&E now also excludes jobs associated with Rule 20 projects to align with the approach taken by the other IOUs. SDG&E aligns with the interpreations that these jobs are primarily related to Rule 20, which is not included in the scope of the Energization Decision. Additionally, jobs triggered by conversions do not accurately reflect the tariffs subject to timeline compliance requirements.
Due to data entry errors, delayed input, and current system limitations, some jobs may display a step end date that precedes the step start date. In such cases, the step duration is excluded from the step level aggregation. However, if the AFS date occurs before the Energized date, the job's duration is still included in the overall end to end cycle time.
Aggregate
Jobs are excluded from aggregation if they meet any of the following criteria: 1)The end-to-end duration is negative (the Energized date is before the AFS date) 2) Any individual step duration is negative. (Step end date is before step start date). 3) Any individual step's end date is later than energization date. 4) Any date data errors are present (1999, 9999, 2032, 2026, 2027, etc.). 5) Durations exceeding two standard deviations above the job population average by tariff type.
"Holistic Energization Steps - Average, Median, and Standard Deviation Reporting Requirements" and "Individual & Aggregated Energization Steps - Average, Median, and Standard Deviation Reporting Requirements" Tables only include jobs (tariff jobs) energized as of 6/30/2025 based on AFS to energization timeframe. % Reporting Requirements" and "Energization Reporting Requirements (End-Use)" tables only include jobs (tariff and MPU jobs) energized as of 6/30/2025" based on the AFS to energization timeframe.
“End-to-End Cycle Time (Data Point: 1 to 8)” was revised from summing the eight steps (including concurrencies and customer time) to a direct calculation from the AFS date to the Energization/Meter Set date. This updated approach still includes customer time but eliminates duplicative concurrent time across steps, providing a more accurate measure of the overall project timeline. The change aligns better with the original data requirement in Appendix B of D.24-09-020 and is consistent with how the other IOUs interpret this data field. As a result, SDG&E has removed the previously reported data point “End-to-End Cycle Time (Data Point: AFS to Energize/Meter Set)” from the March report.
The data field “% of energization projects deemed complete annually” is calculated based on the total population rather than a strict annual subset. Since the reporting framework follows a biannual schedule and uses a rolling format, the structure incorporates data from multiple years, resulting in a continuously expanding dataset that does not clearly define a single year reporting parameter.
"Total (Sum) Reporting Requirements" includes both ongoing and closed jobs.
"Concurrent Steps Requirement" table - SDG&E's current systems can only partially capture concurrent steps due to the challenges of mapping the 8 steps to SDG&E's process.
Requirement numbers 8 and 10 in the "Energization Reporting Requirements (End-Use)" are marked as "N/A" because the data is duplicative of 10.1.
MPU
"Customer Desired Energization Date" - SDG&E's online portal only requires this data for New Construction Projects. For upgrades, if it is not populated, it defaults to one year from date of application.
"AHJ (Authority Having Jurisdiction) for permitting based off Project's location" only includes instances where SDG&E requires permitting. SDG&E does not have the capability to report on customer required permitting.
"Reason why upgrade was cancelled and/or rescheduled" - SDG&E could only manually collect narrative data on cancelled projects defined as "rejected," aligning with the tariff data template.
"Total Staffing, Labor, and Material Cost ($$$ - Capital and Expense)," "Project Costs ($$$) for anything else IOU covers," and "Total Construction/Overhead Costs ($$$)" - SDG&E populated all available data in its current system based on availability at the time of reporting. Therefore, some data is unknown.
Tariff
Data in "AHJ (Authority Having Jurisdiction) for permitting based off Project's location" only includes instances where SDG&E requires permitting. SDG&E does not have the capability to report on customer-required permitting.
"Total Site Capacity at Time of Customer's Application for Service (kW)" data is limited to jobs that have an existing Meter/Premise ID. Calculation is based on using customer's max kW for 12 months in 2024.
"Total Site Capacity Requested (kW)" and "Customer Desired Energization Date" - Accuracy and availability of these data fields is subject to what customer provides in application.
"Additional Capacity (kW) installed for future electric load deployment (as applicable)" and "Did customer install additional capacity to support future load growth?" -Only Rule 45 data is available from SDG&E's current systems.
"Date IOU identifies the need for an upstream capacity project and alerts customer of need for upstream capacity project" - SDG&E does not track the date customer is notified of the need for upstream capacity project; the date provided represents the date SDG&E identifies the need for an upstream capacity project.
"Time to complete upstream capacity project" reflects the duration from the date an upstream capacity upgrade is identified to the date the upstream capacity upgrade is completed. This duration includes the time SDG&E spent on refining the upgrade scope and timeline with customers to meet their energization needs.
"Customer Desired Energization Date" -SDG&E's online portal only requires this information for New Construction Projects. For upgrades, if it is not populated, it defaults to one year from date of application.
"If full energization of applicant site not feasible in a timely manner, explanation whether load management/flexible service options were installed/utilized to provide applicant with timely service," "Amount of load (kW) provided to applicant using flexible service options," Estimate when full service will be provided to the applicant for customers using flexible service and/or receiving tiered load schedules - These data fields are not applicable to SDG&E because it does not provide flexible service options.
"At the time energization provided, remaining (or total) unserved load requested by the applicant" - SDG&E provides service based on the customer's request. It does not provide partial load. Therefore, this data field is not applicable to SDG&E.
"Date when need for R15/16/29/45 upgrade identified" is based on the job creation date.
Fo "Date of IOU rejection of application" and "IOU reason for rejection of applicatio" - SDG&E classifies any job that does not result in an AFS within 18 months of initial request as “rejected” until systems can more accurately align with data requirements.
SDG&E systems can only partially report on all of the 8 Step data points due to the complexities of mapping the 8 steps to SDG&E's processes and the need for system enhancements. Therefore, data may be missing or inaccurate, resulting in erroneous dates and duration calculations.
“Step 3: Customer Dependencies (Customer)” - The dates represent the start of the first customer hold and the end of the last customer hold. The total duration reflects only the cumulative time of the holds themselves and excludes any gaps between them. For example, the start date may show 4/1/25 and the end date 5/30/25, but the total duration could be 20 days because it sums only the actual hold periods, not the intervals of time in between them.
"Step 8 - Data Point End" - SDG&E implemented a multi-step reasoning check. SDG&E’s report first seeks the meter set date, if available. If the meter set date is unavailable, the service completion date is utilized. In the absence of both these data points, the energized date is employed.
"Concurrent Steps" - SDG&E's current systems can only partially report on all data points in this section.
"R15/R16/R45 Energization Average meeting/exceeding Average Energization Target" and "R15/R16/R45 Energization Maximum meeting/exceeding Maximum Energization Target" - Calculation is based on the duration between AFS to Energized date. Jobs with outliers or data errors are not calculated. It is unknown whether SDG&E is exceeding timelines because customer dependencies cannot be removed from the calculation at this time.
SDG&E's current systems cannot provide narrative details for jobs exceeding energization targets at this time without excessive manual processing.
SDG&E's current systems can only partially report on the circuit location.