| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-27 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 629.33 | Unknown | Unknown | Unknown | 11.13 | 618.2 | 3981 | 1096.01 | 629.33 | 466.68 | Yes | N/A | N/A | 2024-06-17 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-07-12 | 29 | 21 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-08-28 | 48 | 34 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-28 | 2024-09-16 | 20 | 14 | 2024-09-16 | 2024-09-16 | 1 | 1 | 48 | 34 | 50 | 36 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-29 | -1450 | -1037 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 599.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-10 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | 426 | 305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 1524.13 | Unknown | Unknown | Unknown | 22.29 | 1501.84 | 3981 | 2606.6 | 1524.13 | 1082.47 | Yes | N/A | N/A | 2023-05-15 | 2023-09-08 | 117 | 85 | 2023-09-08 | 2024-03-12 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2025-02-20 | 346 | 248 | Unknown | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-03-05 | 21 | 15 | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 463 | 333 | 208 | 148 | 671 | 481 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-13 | 857 | 612 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 7578.83 | 1096.31 | Unknown | Unknown | -13368 | 19850.52 | Unknown | 13319.06 | 7578.83 | 5740.23 | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | 2023-10-05 | 18 | 14 | 2023-09-19 | 2023-10-30 | 42 | 30 | 2023-10-17 | 2023-10-25 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | 2023-10-30 | 2023-12-18 | 50 | 36 | 2023-12-18 | 2023-12-18 | 1 | 1 | 43 | 31 | 78 | 58 | 121 | 89 | Steps 2,3,5,6,7 | 66 | 48 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 110 | 79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1090.76 | 1820.16 | Unknown | 536.16 | -2001 | 735.44 | 0 | 2000.5 | 1090.76 | 909.74 | Yes | N/A | N/A | 2023-04-07 | 2023-04-12 | 6 | 4 | 2023-04-12 | 2023-05-09 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-07-01 | 1 | 1 | 6 | 4 | 29 | 21 | 35 | 25 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-24 | 107 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 440.13 | 2047.04 | Unknown | 398.4 | -3239 | 1233.69 | Unknown | 3239.04 | 440.13 | 2798.91 | Yes | N/A | N/A | 2024-10-09 | 2024-10-09 | 1 | 1 | 2024-10-09 | 2025-01-07 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 1 | 1 | 94 | 68 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-15 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 42418.9 | 4418.57 | Unknown | Unknown | 6.5 | 37993.83 | Unknown | 31288.78 | 42418.9 | -11130.12 | Yes | N/A | N/A | 2024-02-14 | 2024-02-14 | 1 | 1 | 2024-02-14 | 2024-07-19 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-07-16 | 12 | 8 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-23 | 29 | 21 | 2024-08-23 | 2024-08-23 | 1 | 1 | 1 | 1 | 199 | 143 | 200 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LEMON GROVE | LEMON GROVE | 31955 | 31955 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-15 | 194 | 139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2024-01-08 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 19175.19 | Unknown | Unknown | Unknown | Unknown | 19175.19 | 249433 | 22263.14 | 19175.19 | 3087.95 | Yes | N/A | N/A | 2023-04-20 | 2024-02-05 | 292 | 208 | 2024-02-05 | 2024-03-11 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-27 | 23 | 17 | 2024-03-11 | 2024-10-31 | 235 | 169 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-11-19 | 2024-12-11 | 23 | 17 | 2024-12-11 | 2024-11-25 | Unknown | Unknown | 527 | 377 | 82 | 60 | 609 | 437 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -436 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1363.31 | Unknown | Unknown | Unknown | 4.39 | 1358.92 | 3981 | 2600.65 | 1363.31 | 1237.34 | Yes | N/A | N/A | 2024-07-10 | 2024-10-09 | 92 | 66 | 2024-10-09 | 2024-10-11 | 3 | 3 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-04-14 | 1 | 1 | 92 | 66 | 4 | 4 | 96 | 70 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-11 | -5 | -4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-05-24 | IOU Designed & Installed | N/A | No | N/A | -121.85 | -10.96 | Unknown | Unknown | -520.48 | 409.59 | Unknown | 532.87 | -121.85 | 654.72 | Yes | N/A | N/A | 2023-03-24 | 2023-03-24 | 1 | 1 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2023-05-24 | 38 | 28 | Unknown | 2023-05-23 | Unknown | Unknown | 2023-05-24 | 2023-09-06 | 106 | 76 | 2023-09-06 | 2023-09-06 | 1 | 1 | 39 | 29 | 107 | 77 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 23412.56 | 23412.56 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-21 | -55 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 7117.46 | Unknown | Unknown | Unknown | 45.94 | 7071.52 | 7962 | 2735.44 | 7117.46 | -4382.02 | Yes | N/A | N/A | 2024-08-08 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-21 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-23 | 21 | 15 | 2024-08-21 | 2025-01-16 | 149 | 107 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-01-28 | 2025-04-01 | 64 | 46 | 2025-04-01 | 2025-03-27 | Unknown | Unknown | 149 | 107 | 106 | 76 | 255 | 183 | Steps 2,3,5,6,7 | 177 | 127 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -443 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-26 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 6964.65 | 1786.8 | Unknown | 252.5 | 59.64 | 4865.71 | 3981 | 832.05 | 6964.65 | -6132.6 | Yes | N/A | N/A | 2024-03-25 | 2024-04-12 | 19 | 15 | 2024-04-12 | 2024-04-12 | 1 | 1 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-08-28 | 139 | 99 | Unknown | 2024-08-23 | Unknown | Unknown | 2024-08-28 | 2024-09-20 | 24 | 18 | 2024-09-20 | 2024-09-20 | 1 | 1 | 158 | 114 | 26 | 20 | 184 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-09 | -474 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-05-14 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 709.18 | -39.28 | Unknown | Unknown | Unknown | 748.46 | 3981 | 1236.79 | 709.18 | 527.61 | Yes | N/A | N/A | 2024-04-19 | 2024-05-14 | 26 | 18 | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-16 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-05-28 | 13 | 9 | 2024-05-28 | 2024-05-23 | Unknown | Unknown | 29 | 21 | 14 | 10 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | -177 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-18 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | -7.3 | -5.29 | Unknown | Unknown | Unknown | -2.01 | Unknown | 496.37 | -7.3 | 503.67 | Yes | N/A | N/A | 2023-05-10 | 2023-05-18 | 9 | 7 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-09-11 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-15 | 5 | 5 | 2023-09-15 | 2023-09-15 | 1 | 1 | 36 | 26 | 6 | 6 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | -256 | -184 | No | 2023-04-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-07-18 | IOU Designed & Installed | N/A | Yes | 38 | -6.83 | -4.95 | Unknown | Unknown | Unknown | -1.88 | Unknown | 581.01 | -6.83 | 587.84 | Yes | N/A | N/A | 2023-04-24 | 2023-06-01 | 39 | 29 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-07-18 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 80 | 58 | 2 | 2 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -348 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-11-11 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 56987.47 | 4705.06 | Unknown | Unknown | 180.39 | 52102.02 | Unknown | 65009.86 | 56987.47 | 8022.39 | Yes | N/A | N/A | 2024-05-30 | 2024-10-25 | 149 | 107 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-26 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-05-06 | 36 | 26 | 2025-05-06 | 2025-05-06 | 1 | 1 | 149 | 107 | 57 | 41 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -607 | -435 | No | 2024-07-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-26 | 2024-10-10 | IOU Designed & Installed | N/A | Yes | 34 | 666.41 | -12.92 | Unknown | Unknown | Unknown | 679.33 | 3981 | 1767.22 | 666.41 | 1100.81 | Yes | N/A | N/A | 2024-07-23 | 2024-08-26 | 35 | 25 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-04 | 39 | 29 | 2024-08-26 | 2024-10-10 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-16 | 7 | 5 | 2024-10-16 | 2024-10-14 | Unknown | Unknown | 81 | 59 | 47 | 35 | 128 | 94 | Steps 2,3,5,6,7 | 39 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -494 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-22 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 455.34 | -8.4 | Unknown | Unknown | 4.07 | 459.67 | 3981 | 600.77 | 455.34 | 145.43 | Yes | N/A | N/A | 2023-05-09 | 2023-05-22 | 14 | 10 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-10-04 | 136 | 98 | Unknown | 2023-09-27 | Unknown | Unknown | 2023-10-04 | 2023-10-17 | 14 | 10 | 2023-10-17 | 2023-10-17 | 1 | 1 | 150 | 108 | 15 | 11 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 124 | 124 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 39.43 | Unknown | Unknown | Unknown | Unknown | 39.43 | 3981 | 1118.5 | 39.43 | 1079.07 | Yes | N/A | N/A | 2024-07-08 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-07-08 | 54 | 38 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-11-11 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-03 | 23 | 17 | 2024-12-03 | 2025-02-27 | 87 | 63 | 127 | 91 | 164 | 118 | 291 | 209 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -660 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 76.33 | -0.62 | Unknown | Unknown | Unknown | 76.95 | 3981 | 1443.1 | 76.33 | 1366.77 | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-01-10 | 39 | 29 | 2025-01-10 | 2025-01-10 | 1 | 1 | 22 | 16 | 41 | 31 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 656.82 | -6.02 | Unknown | Unknown | 9.52 | 653.32 | 3981 | 676.1 | 656.82 | 19.28 | Yes | N/A | N/A | 2023-03-23 | 2023-04-25 | 34 | 24 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-08-30 | 128 | 92 | Unknown | 2023-08-15 | Unknown | Unknown | 2023-08-30 | 2023-09-20 | 22 | 16 | 2023-09-20 | 2023-09-20 | 1 | 1 | 162 | 116 | 23 | 17 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -535 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 301.79 | 185.02 | Unknown | Unknown | Unknown | 116.77 | Unknown | 480.37 | 301.79 | 178.58 | Yes | N/A | N/A | 2023-08-24 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-08-24 | 29 | 21 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-11-08 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-15 | 8 | 6 | 2023-11-15 | 2023-11-15 | 1 | 1 | 77 | 55 | 38 | 28 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 860.47 | 257.37 | Unknown | Unknown | 45.17 | 557.93 | 3981 | 732.54 | 860.47 | -127.93 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-10 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2025-08-15 | 463 | 331 | 2025-08-15 | 2024-05-24 | Unknown | Unknown | 40 | 30 | 464 | 332 | 504 | 362 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-27 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-10 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 3014.65 | 844.49 | Unknown | Unknown | Unknown | 2170.16 | Unknown | 1634.63 | 3014.65 | -1380.02 | Yes | N/A | N/A | 2024-10-08 | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-10-10 | 38 | 28 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-31 | 22 | 16 | 2024-10-31 | 2024-10-31 | 1 | 1 | 1 | 1 | 61 | 45 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-18 | -1113 | -796 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 978.98 | Unknown | Unknown | Unknown | 13.53 | 965.45 | 0 | 868.24 | 978.98 | -110.74 | Yes | N/A | N/A | 2023-10-19 | 2023-10-19 | 1 | 1 | 2023-10-19 | 2023-11-07 | 20 | 14 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 1 | 1 | 21 | 15 | 22 | 16 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1086-F4 CYPRES PT PH1 | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -66 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-06 | 2023-01-06 | 2024-09-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 185778.42 | 22105.49 | Unknown | Unknown | 18291.36 | 145381.57 | Unknown | 77575.91 | 185778.42 | -108202.51 | Yes | N/A | N/A | 2023-01-06 | 2024-02-02 | 393 | 281 | 2024-02-02 | 2024-05-17 | 106 | 76 | 2023-08-31 | 2024-05-02 | 13 | 9 | 2023-08-30 | 2024-05-02 | 77 | 55 | 2024-05-28 | Unknown | Unknown | Unknown | 2024-05-28 | 2024-09-03 | 99 | 71 | 2024-09-16 | 2024-09-26 | 11 | 9 | 2024-09-26 | 2024-09-26 | 1 | 1 | 406 | 290 | 294 | 212 | 700 | 502 | Steps 2,3,5,6,7 | 506 | 362 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 469 | 336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 46758.45 | 12672.91 | Unknown | 785.33 | 1791.24 | 31508.97 | 3981 | Not available | 46758.45 | Unknown | Yes | N/A | N/A | 2024-02-02 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-05-02 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | 2024-05-02 | 2024-12-26 | 239 | 171 | Unknown | 2024-12-11 | Unknown | Unknown | 2025-01-09 | 2025-02-13 | 36 | 26 | 2025-02-13 | 2025-02-13 | 1 | 1 | 239 | 171 | 186 | 134 | 425 | 305 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-12 | 599 | 428 | No | 2022-03-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-07 | 2022-03-07 | Unknown | IOU Designed & Installed | N/A | Yes | 725 | 15.53 | -13.82 | Unknown | Unknown | Unknown | 29.35 | Unknown | 517.29 | 15.53 | 501.76 | Yes | N/A | N/A | 2022-03-07 | 2024-03-01 | 726 | 520 | 2024-03-01 | 2024-03-01 | 1 | 1 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-07-03 | 1 | 1 | 726 | 520 | 2 | 2 | 728 | 522 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 797.05 | 797.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 3039.53 | 625 | Unknown | Unknown | Unknown | 2414.53 | 3941 | 298.31 | 3039.53 | -2741.22 | Yes | N/A | N/A | 2024-07-18 | 2024-10-07 | 82 | 58 | 2024-10-07 | 2024-10-16 | 10 | 8 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-31 | 11 | 9 | 2024-10-31 | 2024-10-31 | 1 | 1 | 88 | 62 | 22 | 18 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 47.42 | Unknown | Unknown | Unknown | Unknown | 47.42 | Unknown | 363.17 | 47.42 | 315.75 | Yes | N/A | N/A | 2024-07-02 | 2024-09-01 | 62 | 44 | 2024-09-01 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-02-03 | 1 | 1 | 62 | 44 | 1 | 1 | 63 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 2540.72 | 582.92 | Unknown | 235.84 | 8.36 | 1713.6 | 3991 | 661.64 | 2540.72 | -1879.08 | Yes | N/A | N/A | 2023-07-13 | 2023-08-02 | 21 | 15 | 2023-08-02 | 2023-08-16 | 15 | 11 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-09-21 | 37 | 27 | Unknown | 2023-09-20 | Unknown | Unknown | 2023-09-21 | 2023-10-02 | 12 | 8 | 2023-10-02 | 2023-10-02 | 1 | 1 | 58 | 42 | 28 | 20 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 172.2 | 172.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 1248.79 | Unknown | Unknown | Unknown | 15.2 | 1233.59 | 3981 | 1365.73 | 1248.79 | 116.94 | Yes | N/A | N/A | 2024-09-17 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-10-23 | 45 | 33 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-06 | 2024-12-10 | 66 | 47 | Unknown | 2025-02-27 | Unknown | Unknown | 2024-12-10 | 2025-01-27 | 49 | 35 | 2025-01-27 | 2025-01-27 | 1 | 1 | 66 | 47 | 95 | 69 | 161 | 116 | Steps 2,3,5,6,7 | 79 | 57 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 164 | 164 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20706.34 | 8650.21 | Unknown | Unknown | Unknown | 12056.13 | 3981 | 2211.98 | 20706.34 | -18494.36 | Yes | N/A | N/A | 2023-10-10 | 2024-02-21 | 135 | 97 | 2024-02-21 | 2024-02-23 | 3 | 3 | 2023-12-04 | 2024-03-27 | 6 | 4 | 2024-02-20 | 2024-03-28 | 35 | 26 | 2024-02-23 | 2024-03-18 | 25 | 17 | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-04-01 | 1 | 1 | 166 | 118 | 39 | 30 | 205 | 148 | Steps 2,3,5,6,7 | 151 | 109 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | 554 | 397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2607.35 | Unknown | Unknown | Unknown | -289 | 2896.35 | Unknown | 242.96 | 2607.35 | -2364.39 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | 2023-03-27 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2023-09-19 | 177 | 127 | Unknown | 2023-09-21 | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-09-29 | Unknown | Unknown | 178 | 128 | 33 | 23 | 211 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | 141 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 8217.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-12-26 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 53 | 39 | 53 | 39 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 164.05 | 164.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 324 | 233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5744.53 | 273.47 | Unknown | Unknown | -1109 | 6580.06 | 7962 | 2554.58 | 5744.53 | -3189.95 | Yes | N/A | N/A | 2023-08-02 | 2023-08-18 | 17 | 13 | 2023-08-18 | 2024-07-18 | 336 | 240 | 2024-07-18 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-03-21 | Unknown | Unknown | 17 | 13 | 336 | 240 | 353 | 253 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-02 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 1051.86 | -20.4 | Unknown | Unknown | Unknown | 1072.26 | 3241 | 1693.67 | 1051.86 | 641.81 | Yes | N/A | N/A | 2024-11-25 | 2024-12-02 | 8 | 6 | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-19 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-14 | 27 | 19 | 2025-01-14 | 2025-01-14 | 1 | 1 | 25 | 19 | 29 | 21 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -185 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3181.34 | Unknown | Unknown | Unknown | 158.91 | 3022.43 | 98668 | 11225.43 | 3181.34 | 8044.09 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | 2023-04-24 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2024-06-06 | 410 | 294 | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-09 | Unknown | Unknown | 411 | 295 | 34 | 24 | 445 | 319 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-28 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | -1565.54 | -1.5 | Unknown | Unknown | -1708 | 143.96 | 3981 | 3198.33 | -1565.54 | 4763.87 | Yes | N/A | N/A | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-30 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-04-01 | 62 | 44 | Unknown | 2025-02-25 | Unknown | Unknown | 2025-04-01 | 2025-04-10 | 10 | 8 | 2025-04-10 | 2025-04-10 | 1 | 1 | 85 | 61 | 12 | 10 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 3225 | 3225 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-25 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 784.19 | -4.1 | Unknown | Unknown | 3.21 | 785.08 | 3981 | 652.72 | 784.19 | -131.47 | Yes | N/A | N/A | 2023-12-12 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2024-01-05 | 117 | 85 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-02-15 | 42 | 30 | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-02-20 | 6 | 4 | 2024-02-20 | 2024-02-20 | 1 | 1 | 42 | 30 | 124 | 90 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 246 | 177 | No | 2022-11-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-16 | 2022-11-16 | 2023-10-17 | IOU Designed & Installed | N/A | Yes | 267 | 219.24 | -11.09 | Unknown | Unknown | 1.41 | 228.92 | 3941 | 1518.97 | 219.24 | 1299.73 | Yes | N/A | N/A | 2022-11-16 | 2023-08-10 | 268 | 192 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-05 | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-11-01 | 16 | 12 | 2023-11-01 | 2023-11-01 | 1 | 1 | 268 | 192 | 17 | 13 | 285 | 205 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -268 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-10 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 3694.61 | 1008.2 | Unknown | Unknown | 11.86 | 2674.55 | 0 | 860.44 | 3694.61 | -2834.17 | Yes | N/A | N/A | 2024-01-02 | 2024-01-04 | 3 | 3 | 2024-01-04 | 2024-01-04 | 1 | 1 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-12-04 | 330 | 236 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-02-27 | 86 | 62 | 2025-02-27 | 2025-02-27 | 1 | 1 | 333 | 239 | 88 | 64 | 421 | 303 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-31 | 559 | 400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 4270.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-02-14 | 2 | 2 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -359 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-04 | 2023-11-04 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 381.14 | -19.08 | Unknown | Unknown | -680.66 | 1080.88 | Unknown | 696.69 | 381.14 | 315.55 | Yes | N/A | N/A | 2023-11-04 | 2023-11-04 | 1 | 0 | 2023-11-04 | 2023-11-04 | 1 | 0 | 2023-11-04 | 2023-12-07 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-20 | 30 | 22 | Unknown | 2025-03-18 | Unknown | Unknown | 2024-03-20 | 2024-06-14 | 87 | 63 | 2024-06-14 | 2024-06-14 | 1 | 1 | 65 | 46 | 89 | 64 | 154 | 110 | Steps 2,3,5,6,7 | 363 | 259 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | 626.4 | 626.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 73 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-04-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 67991.47 | 9818.63 | Unknown | Unknown | -8174 | 66346.84 | 42014.84 | 62626.11 | 67991.47 | -5365.36 | Yes | N/A | N/A | 2024-02-15 | 2024-02-16 | 2 | 2 | 2024-02-16 | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-26 | 27 | 19 | 2024-03-26 | 2024-04-24 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-13 | 21 | 15 | 2024-05-13 | 2024-05-13 | 1 | 1 | 29 | 21 | 36 | 26 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-14 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-11-05 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 419.73 | -7.02 | Unknown | Unknown | Unknown | 426.75 | 3981 | 1837.66 | 419.73 | 1417.93 | Yes | N/A | N/A | 2024-10-29 | 2024-09-14 | Unknown | Unknown | 2024-09-14 | 2024-11-05 | 53 | 37 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-01-24 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-03-26 | 62 | 44 | 2025-03-26 | 2025-03-26 | 1 | 1 | 81 | 59 | 116 | 82 | 197 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -592 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 53.99 | Unknown | Unknown | Unknown | Unknown | 53.99 | 3981 | 1095.03 | 53.99 | 1041.04 | Yes | N/A | N/A | 2024-06-26 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-06-26 | 44 | 32 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-09-04 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-17 | 14 | 10 | 2024-09-17 | 2024-09-17 | 1 | 1 | 71 | 51 | 59 | 43 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-24 | -185 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-05-17 | IOU Designed & Installed | N/A | No | N/A | 3627.17 | Unknown | Unknown | Unknown | Unknown | 3627.17 | 3981 | 996.71 | 3627.17 | -2630.46 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | 2023-03-07 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-05-03 | 58 | 42 | Unknown | 2023-03-31 | Unknown | Unknown | 2023-05-17 | 2023-06-22 | 37 | 27 | 2023-06-22 | 2023-06-22 | 1 | 1 | 59 | 43 | 66 | 48 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 623 | 446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 769.63 | -13.72 | Unknown | Unknown | Unknown | 783.35 | 3662 | 1666.04 | 769.63 | 896.41 | Yes | N/A | N/A | 2022-12-13 | 2023-03-22 | 100 | 72 | 2023-03-22 | 2023-05-24 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 100 | 72 | 73 | 53 | 173 | 125 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | ES 1130-F7 | COUNTY OF SAN DIEGO-NORTH of 56 | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-09-03 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 32868.41 | 11342.17 | Unknown | Unknown | -14500.15 | 36026.39 | 2339 | 38731.27 | 32868.41 | 5862.86 | Yes | N/A | N/A | 2024-04-17 | 2024-05-14 | 28 | 20 | 2024-05-14 | 2024-11-06 | 177 | 127 | 2024-08-07 | 2024-10-25 | 21 | 15 | 2024-10-08 | 2025-01-22 | 45 | 33 | 2024-12-12 | Unknown | Unknown | Unknown | 2024-12-12 | 2025-03-04 | 83 | 59 | 2025-03-18 | 2025-04-09 | 23 | 17 | 2025-04-09 | 2025-04-09 | 1 | 1 | 49 | 35 | 329 | 237 | 378 | 272 | Steps 2,3,5,6,7 | 149 | 107 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-16 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1032.45 | Unknown | Unknown | Unknown | Unknown | 1032.45 | 3981 | 1182.35 | 1032.45 | 149.9 | Yes | N/A | N/A | 2024-04-24 | 2024-09-17 | 147 | 105 | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-18 | 1 | 1 | 147 | 105 | 2 | 2 | 149 | 107 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -532 | -381 | No | 2024-12-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-17 | 2025-03-27 | IOU Designed & Installed | N/A | Yes | 77 | 640.57 | -32.99 | Unknown | Unknown | 9.57 | 663.99 | 3981 | 1395.74 | 640.57 | 755.17 | Yes | N/A | N/A | 2024-12-16 | 2025-02-19 | 66 | 48 | 2025-02-19 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-02-24 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-03-27 | 81 | 59 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-27 | 2025-04-03 | 8 | 6 | 2025-04-03 | 2025-04-02 | Unknown | Unknown | 197 | 143 | 8 | 6 | 205 | 149 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -121 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-05 | 2023-08-30 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | -4.33 | -3.4 | Unknown | Unknown | Unknown | -0.93 | 3241 | 861.09 | -4.33 | 865.42 | Yes | N/A | N/A | 2023-08-05 | 2023-12-12 | 130 | 92 | 2023-12-12 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-11-07 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-01-11 | 66 | 48 | 2024-01-11 | 2024-01-11 | 1 | 1 | 200 | 142 | 67 | 49 | 267 | 191 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-28 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 828.31 | -21.2 | Unknown | Unknown | Unknown | 849.51 | 3981 | 1432.2 | 828.31 | 603.89 | Yes | N/A | N/A | 2024-06-26 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-06-28 | 45 | 33 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-09 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-22 | 14 | 10 | 2024-07-22 | 2024-07-18 | Unknown | Unknown | 12 | 8 | 59 | 43 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-09 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 15.81 | -14.06 | Unknown | Unknown | Unknown | 29.87 | Unknown | 941.78 | 15.81 | 925.97 | Yes | N/A | N/A | 2024-04-08 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-09 | 44 | 32 | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-15 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-17 | 33 | 25 | 2024-05-17 | 2024-05-17 | 1 | 1 | 7 | 5 | 78 | 58 | 85 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 33.95 | Unknown | Unknown | Unknown | Unknown | 33.95 | 3981 | 1442.98 | 33.95 | 1409.03 | Yes | N/A | N/A | 2024-06-28 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-07-12 | 87 | 63 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-08-22 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-10 | 20 | 14 | 2024-09-10 | 2024-09-09 | Unknown | Unknown | 42 | 30 | 107 | 77 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -288 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.8 | -11.82 | Unknown | Unknown | Unknown | 12.62 | 3981 | 707.93 | 0.8 | 707.13 | Yes | N/A | N/A | 2023-03-10 | 2023-05-09 | 61 | 43 | 2023-05-09 | 2023-05-20 | 12 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-20 | 2023-08-24 | 97 | 69 | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-23 | Unknown | Unknown | 158 | 112 | 12 | 9 | 170 | 121 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | JULIAN | N/A | 4250 | 4250 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-30 | 522 | 373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-15 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 9109.88 | -145.93 | Unknown | Unknown | -3734 | 12989.81 | Unknown | 3733.69 | 9109.88 | -5376.19 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-12-17 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-05-05 | 120 | 86 | 2025-05-05 | 2025-05-05 | 1 | 1 | 1 | 1 | 248 | 178 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 305 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 276.36 | -9.58 | Unknown | Unknown | Unknown | 285.94 | 7962 | 1749.59 | 276.36 | 1473.23 | Yes | N/A | N/A | 2023-04-14 | 2023-04-17 | 4 | 2 | 2023-04-17 | 2023-05-17 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-05-08 | 6 | 4 | 2023-05-17 | 2023-06-29 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-08-02 | Unknown | Unknown | 48 | 34 | 37 | 27 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | 665 | 476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-07-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3975.25 | -68.16 | Unknown | Unknown | 66.13 | 3977.28 | 40815 | 2308.47 | 3975.25 | -1666.78 | Yes | N/A | N/A | 2023-06-21 | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-10-24 | 138 | 98 | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-08-17 | 2024-07-30 | 8 | 6 | 2023-10-24 | 2024-08-09 | 291 | 209 | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-27 | Unknown | Unknown | 292 | 210 | 146 | 104 | 438 | 314 | Steps 2,3,5,6,7 | 348 | 248 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-24 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | -7.57 | -7.21 | Unknown | Unknown | Unknown | -0.36 | 3981 | 163.83 | -7.57 | 171.4 | Yes | N/A | N/A | 2024-01-22 | 2024-03-18 | 57 | 41 | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-15 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-18 | 4 | 4 | 2024-04-18 | 2024-04-18 | 1 | 1 | 85 | 61 | 7 | 7 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 607.98 | -11.7 | Unknown | Unknown | Unknown | 619.68 | 3981 | 1416.65 | 607.98 | 808.67 | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2025-03-06 | 221 | 159 | 2025-03-06 | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-30 | 33 | 25 | 2024-07-29 | 2024-08-30 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-12 | 14 | 10 | 2024-09-12 | 2024-09-12 | 1 | 1 | 34 | 26 | 269 | 195 | 303 | 221 | Steps 2,3,5,6,7 | 32 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 2882.1 | 616.69 | Unknown | Unknown | -387.88 | 2653.29 | Unknown | 278.35 | 2882.1 | -2603.75 | Yes | N/A | N/A | 2024-08-22 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-09-18 | 76 | 54 | 2024-09-18 | 2024-09-27 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2025-01-16 | 112 | 80 | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-16 | 1 | 1 | 122 | 88 | 78 | 56 | 200 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -170 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | Unknown | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | 800.28 | -29.54 | Unknown | Unknown | 0.29 | 829.53 | 3981 | 891.91 | 800.28 | 91.63 | Yes | N/A | N/A | 2023-06-27 | 2023-05-04 | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-18 | 14 | 10 | 2023-06-27 | 2023-09-13 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-10-10 | 28 | 20 | 2023-10-10 | 2023-10-10 | 1 | 1 | 79 | 57 | 43 | 31 | 122 | 88 | Steps 2,3,5,6,7 | 83 | 59 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 163.1 | 163.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -500 | -357 | No | 2024-01-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2024-04-16 | IOU Designed & Installed | N/A | Yes | 38 | 209.37 | -17.58 | Unknown | Unknown | Unknown | 226.95 | 3981 | 1700.84 | 209.37 | 1491.47 | Yes | N/A | N/A | 2024-01-26 | 2024-02-22 | 28 | 20 | 2024-02-22 | 2024-03-04 | 12 | 8 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-04-16 | 69 | 49 | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-16 | 2024-04-22 | 7 | 5 | 2024-04-22 | 2024-04-19 | Unknown | Unknown | 97 | 69 | 19 | 13 | 116 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 52 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -810.1 | 1220.94 | Unknown | 341.24 | -2853 | 480.72 | 0 | 2852.6 | -810.1 | 3662.7 | Yes | N/A | N/A | 2023-06-08 | 2023-06-08 | 1 | 1 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-25 | -187 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 1807.26 | 1071.68 | Unknown | Unknown | Unknown | 735.58 | 3981 | 858.26 | 1807.26 | -949 | Yes | N/A | N/A | 2024-05-23 | 2024-07-01 | 40 | 28 | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-08-29 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-19 | 22 | 16 | 2024-09-19 | 2024-09-19 | 1 | 1 | 100 | 72 | 24 | 18 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -275 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-07-10 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | -1235 | 1512.53 | Unknown | 156.37 | -3622 | 718.1 | Unknown | 3621.79 | -1235 | 4856.79 | Yes | N/A | N/A | 2024-06-28 | 2024-07-10 | 13 | 9 | 2024-07-10 | 2024-09-11 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-07-19 | 2024-09-11 | 55 | 39 | 2024-09-11 | 2024-09-11 | 1 | 1 | 13 | 9 | 121 | 87 | 134 | 96 | Steps 2,3,5,6,7 | 54 | 38 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -272 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-07-09 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 1353.61 | 520.44 | Unknown | 206.26 | -1986 | 2612.91 | Unknown | 1864.5 | 1353.61 | 510.89 | Yes | N/A | N/A | 2024-06-19 | 2024-07-24 | 36 | 26 | 2024-07-24 | 2024-07-26 | 3 | 3 | 2024-07-26 | 2024-09-17 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2025-05-20 | 246 | 176 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | 2025-05-20 | 1 | 1 | 336 | 240 | 5 | 5 | 341 | 245 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-11 | -519 | -372 | No | 2024-10-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-12-09 | 2025-03-04 | IOU Designed & Installed | N/A | Yes | 46 | 60.96 | -0.62 | Unknown | Unknown | Unknown | 61.58 | 3981 | 1766.16 | 60.96 | 1705.2 | Yes | N/A | N/A | 2024-10-28 | 2024-12-13 | 47 | 35 | 2024-12-13 | 2024-12-19 | 7 | 5 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-03-04 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-10 | 7 | 5 | 2025-03-10 | 2025-03-10 | 1 | 1 | 123 | 89 | 15 | 11 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | 265 | 190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2025-02-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 16360.43 | 273.47 | Unknown | Unknown | -1074.17 | 17161.13 | 7962 | 2300.41 | 16360.43 | -14060.02 | Yes | N/A | N/A | 2024-02-23 | 2024-04-18 | 56 | 40 | 2024-04-18 | 2024-08-14 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2025-03-27 | 226 | 162 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-02-20 | 2025-05-05 | 75 | 53 | 2025-05-05 | 2025-03-27 | Unknown | Unknown | 282 | 202 | 194 | 138 | 476 | 340 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | -591 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 3036.91 | 640.51 | Unknown | Unknown | 8.78 | 2387.62 | 3981 | 1434.82 | 3036.91 | -1602.09 | Yes | N/A | N/A | 2025-02-18 | 2025-02-28 | 11 | 9 | 2025-02-28 | 2025-03-03 | 4 | 2 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-06-11 | 101 | 73 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-18 | 8 | 6 | 2025-06-18 | 2025-06-18 | 1 | 1 | 112 | 82 | 13 | 9 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-16 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 27.73 | Unknown | Unknown | Unknown | Unknown | 27.73 | 3981 | 1537.6 | 27.73 | 1509.87 | Yes | N/A | N/A | 2024-08-01 | 2024-07-08 | Unknown | Unknown | 2024-07-08 | 2024-08-16 | 40 | 30 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-26 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-06 | 12 | 10 | 2024-09-06 | 2024-09-04 | Unknown | Unknown | 11 | 7 | 52 | 40 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 16 | 12 | No | 2022-06-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-14 | 2022-06-06 | Unknown | IOU Designed & Installed | N/A | Yes | 515 | 4.69 | -5.88 | Unknown | Unknown | Unknown | 10.57 | 3885 | 803.47 | 4.69 | 798.78 | Yes | N/A | N/A | 2022-02-14 | 2023-11-03 | 628 | 450 | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2024-01-16 | 1 | 1 | 628 | 450 | 2 | 2 | 630 | 452 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -164 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 596.67 | -33.67 | Unknown | Unknown | Unknown | 630.34 | 3981 | 850.48 | 596.67 | 253.81 | Yes | N/A | N/A | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-23 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-03-15 | 53 | 39 | 2024-03-15 | 2024-03-28 | 14 | 10 | 16 | 12 | 68 | 50 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | Unknown | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 1214.2 | -24.15 | Unknown | Unknown | Unknown | 1238.35 | 3981 | 1640.98 | 1214.2 | 426.78 | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-29 | 7 | 5 | 2024-07-23 | 2024-07-31 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-07 | 8 | 6 | 2024-08-07 | 2024-08-07 | 1 | 1 | 10 | 8 | 17 | 13 | 27 | 21 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1636 | 1169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-11 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3961 | 4791.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-11 | 9 | 7 | 2024-12-11 | 2025-01-16 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-21 | 41 | 29 | 2025-01-16 | 2025-06-03 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 148 | 106 | 81 | 59 | 229 | 165 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-21 | 16 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | -2374.35 | 3441.37 | Unknown | 149.29 | -7433 | 1467.99 | Unknown | 7433.35 | -2374.35 | 9807.7 | Yes | N/A | N/A | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-07 | 2 | 2 | 2025-05-07 | 2025-05-07 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-17 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 460.6 | -11.95 | Unknown | Unknown | 5.43 | 467.12 | 3981 | 325.32 | 460.6 | -135.28 | Yes | N/A | N/A | 2023-09-14 | 2023-10-10 | 27 | 19 | 2023-10-10 | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-19 | 2 | 2 | 2023-10-10 | 2023-10-23 | 14 | 10 | 2023-10-10 | 2023-11-08 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-14 | 7 | 5 | 2023-11-14 | 2023-11-14 | 1 | 1 | 59 | 43 | 22 | 16 | 81 | 59 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -99 | -71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 1044.16 | -10.64 | Unknown | Unknown | 6.89 | 1047.91 | Unknown | 1992.56 | 1044.16 | 948.4 | Yes | N/A | N/A | 2023-04-10 | 2023-04-18 | 9 | 7 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-10-20 | 186 | 134 | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-20 | 2023-11-17 | 29 | 21 | 2023-11-17 | 2023-11-17 | 1 | 1 | 195 | 141 | 30 | 22 | 225 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.77 | 7.06 | Unknown | Unknown | Unknown | 8.71 | Unknown | 1917.16 | 15.77 | 1901.39 | Yes | N/A | N/A | 2025-04-03 | 2025-04-05 | 3 | 2 | 2025-04-05 | 2025-04-09 | 5 | 3 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-06 | 1 | 1 | 3 | 2 | 6 | 4 | 9 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.78 | -20.11 | Unknown | Unknown | Unknown | 15.33 | Unknown | 3226.35 | -4.78 | 3231.13 | Yes | N/A | N/A | 2024-08-09 | 2025-02-18 | 194 | 138 | 2025-02-18 | 2025-03-06 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 194 | 138 | 18 | 14 | 212 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 391 | 391 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-09 | 55 | 40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 1070.22 | 398.66 | Unknown | Unknown | 7.56 | 664 | 3981 | 542.2 | 1070.22 | -528.02 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-11-03 | 240 | 172 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-12-21 | 49 | 35 | 2023-12-21 | 2023-11-03 | Unknown | Unknown | 241 | 173 | 49 | 35 | 290 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -206 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 57766.84 | 727.65 | Unknown | 45.66 | Unknown | 56993.53 | 2787178 | 38795.3 | 57766.84 | -18971.54 | Yes | N/A | N/A | 2023-12-12 | 2024-04-08 | 119 | 85 | 2024-04-08 | 2024-04-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-07-16 | 86 | 62 | Unknown | 2024-06-13 | Unknown | Unknown | 2024-07-18 | 2024-08-01 | 15 | 11 | 2024-08-01 | 2024-07-21 | Unknown | Unknown | 205 | 147 | 30 | 22 | 235 | 169 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -13.39 | -10.55 | Unknown | Unknown | Unknown | -2.84 | Unknown | 148.62 | -13.39 | 162.01 | Yes | N/A | N/A | 2023-03-27 | 2023-05-01 | 36 | 26 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 36 | 26 | 1 | 1 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -714 | -511 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 5566.76 | 1504.84 | Unknown | 296.65 | Unknown | 3765.27 | 3981 | 1434.94 | 5566.76 | -4131.82 | Yes | N/A | N/A | 2024-10-30 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-10-30 | 2 | 2 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-10-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-13 | 15 | 11 | 2024-11-13 | 2024-11-13 | 1 | 1 | 1 | 1 | 18 | 14 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-06-17 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 239.08 | -4.08 | Unknown | Unknown | Unknown | 243.16 | Unknown | 1533.09 | 239.08 | 1294.01 | Yes | N/A | N/A | 2024-05-01 | 2024-06-11 | 42 | 30 | 2024-06-11 | 2024-06-17 | 7 | 5 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-26 | 29 | 21 | 2024-08-26 | 2024-08-26 | 1 | 1 | 85 | 61 | 37 | 27 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 116 | 116 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-15 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -0.81 | -3.92 | Unknown | Unknown | Unknown | 3.11 | Unknown | 296.76 | -0.81 | 297.57 | Yes | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | 2023-09-15 | 9 | 7 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-12-04 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-08 | 5 | 5 | 2023-12-08 | 2023-12-08 | 1 | 1 | 82 | 58 | 15 | 13 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-10-02 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 1461.67 | 412.74 | Unknown | Unknown | Unknown | 1048.93 | Unknown | 1619.93 | 1461.67 | 158.26 | Yes | N/A | N/A | 2024-09-23 | 2024-10-02 | 10 | 8 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-21 | 29 | 21 | 2024-11-21 | 2024-11-21 | 1 | 1 | 33 | 25 | 31 | 23 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 50.05 | 50.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | -8.57 | -7.37 | Unknown | Unknown | Unknown | -1.2 | 3241 | 906.17 | -8.57 | 914.74 | Yes | N/A | N/A | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-17 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-07-15 | 60 | 42 | 2024-07-15 | 2024-07-15 | 1 | 1 | 25 | 19 | 62 | 44 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-02 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-16 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | 4208.09 | 1117.74 | Unknown | 955.8 | Unknown | 2134.55 | Unknown | 203.86 | 4208.09 | -4004.23 | Yes | N/A | N/A | 2023-11-14 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2023-11-16 | 24 | 18 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-11-20 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-22 | 3 | 3 | 2023-11-22 | 2023-11-22 | 1 | 1 | 5 | 3 | 28 | 22 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 235 | 168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-19 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 2374.03 | Unknown | Unknown | Unknown | -1519 | 3893.03 | Unknown | 1650.02 | 2374.03 | -724.01 | Yes | N/A | N/A | 2024-09-17 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2025-03-10 | 294 | 210 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-04-07 | 26 | 18 | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 321 | 229 | 321 | 229 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 728 | 728 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 677.92 | -57.01 | Unknown | Unknown | Unknown | 734.93 | 7962 | 918.1 | 677.92 | 240.18 | Yes | N/A | N/A | 2024-02-08 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-03-27 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-05 | 26 | 18 | 2024-03-27 | 2024-04-17 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-02 | Unknown | Unknown | 22 | 16 | 88 | 62 | 110 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 949 | 678 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 505.6 | 40.9 | Unknown | Unknown | Unknown | 464.7 | 0 | 439.25 | 505.6 | -66.35 | Yes | N/A | N/A | 2023-08-22 | 2024-03-11 | 203 | 145 | 2024-03-11 | 2025-02-11 | 338 | 242 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-01 | 33 | 25 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1 | 1 | 203 | 145 | 372 | 268 | 575 | 413 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -456 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1039.62 | -9.8 | Unknown | Unknown | 32.29 | 1017.13 | 3981 | 502.06 | 1039.62 | -537.56 | Yes | N/A | N/A | 2023-02-14 | 2023-03-06 | 21 | 15 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | Unknown | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2023-09-06 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-16 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6853.27 | -149.81 | Unknown | Unknown | Unknown | 7003.08 | Unknown | 1069.67 | 6853.27 | -5783.6 | Yes | N/A | N/A | 2023-10-31 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2023-11-28 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 41 | 29 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-18 | -116 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.98 | Unknown | Unknown | Unknown | Unknown | 7.98 | 3981 | 102.29 | 7.98 | 94.31 | Yes | N/A | N/A | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-25 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 1201.08 | Unknown | Unknown | Unknown | 13.23 | 1187.85 | 3981 | 1043.93 | 1201.08 | -157.15 | Yes | N/A | N/A | 2024-08-06 | 2024-09-20 | 46 | 34 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-11-13 | 55 | 39 | Unknown | 2024-11-11 | Unknown | Unknown | 2024-11-13 | 2024-12-04 | 22 | 16 | 2024-12-04 | 2024-12-04 | 1 | 1 | 101 | 73 | 24 | 18 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | Chula Vista | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2024-04-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2943.66 | 403.68 | Unknown | 109.48 | -10325 | 12755.5 | Unknown | 12051.86 | 2943.66 | 9108.2 | Yes | N/A | N/A | 2023-11-09 | 2024-01-08 | 61 | 43 | 2024-01-08 | 2024-04-02 | 86 | 62 | 2024-01-17 | 2024-01-25 | 9 | 7 | 2024-04-02 | 2024-04-22 | 14 | 9 | 2024-04-16 | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-18 | 2024-04-30 | 13 | 9 | 2024-04-30 | 2024-04-30 | 1 | 1 | 70 | 50 | 115 | 82 | 185 | 132 | Steps 2,3,5,6,7 | 82 | 58 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 1600 | 1600 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-09-10 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 170.25 | -3 | Unknown | Unknown | Unknown | 173.25 | 3981 | 1456.61 | 170.25 | 1286.36 | Yes | N/A | N/A | 2024-10-15 | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-15 | 8 | 6 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-18 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-01 | 15 | 11 | 2024-11-01 | 2024-11-01 | 1 | 1 | 4 | 4 | 24 | 18 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | -663 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 295.96 | -17.46 | Unknown | Unknown | Unknown | 313.42 | 3981 | 827.84 | 295.96 | 531.88 | Yes | N/A | N/A | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-09 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-11-15 | 38 | 28 | 2023-11-15 | 2023-11-15 | 1 | 1 | 16 | 12 | 40 | 30 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-27 | -556 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1362.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2025-01-02 | 58 | 42 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-03-27 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-19 | 24 | 17 | 2025-04-19 | 2025-04-19 | 1 | 0 | 85 | 61 | 83 | 59 | 168 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | -349 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 8.11 | Unknown | Unknown | Unknown | Unknown | 8.11 | Unknown | 192.95 | 8.11 | 184.84 | Yes | N/A | N/A | 2024-08-08 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-08 | 2 | 2 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-15 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-23 | 9 | 7 | 2024-08-23 | 2024-08-23 | 1 | 1 | 8 | 6 | 12 | 10 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -122 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 921.36 | 264.18 | Unknown | 75.44 | -589.15 | 1170.89 | 0 | 654.98 | 921.36 | -266.38 | Yes | N/A | N/A | 2023-03-30 | 2023-06-02 | 65 | 47 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-04 | 10 | 8 | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2024-10-08 | 371 | 265 | 2024-10-08 | 2024-10-08 | 1 | 1 | 75 | 55 | 372 | 266 | 447 | 321 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 99 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | Unknown | Customer elected Applicant Install | Step 2 Engineering & Design | No | N/A | 4354 | -67.7 | Unknown | Unknown | 52.58 | 4369.12 | 11943 | 1002.97 | 4354 | -3351.03 | Yes | N/A | N/A | 2023-06-09 | 2023-07-25 | 47 | 33 | 2023-07-25 | 2023-09-27 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-08-06 | 315 | 225 | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-08-08 | 84 | 60 | 362 | 258 | 149 | 107 | 511 | 365 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-28 | 605 | 434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-06-19 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 109432.53 | 42696.03 | Unknown | Unknown | -15113 | 81849.5 | Unknown | 15112.52 | 109432.53 | -94320.01 | Yes | N/A | N/A | 2023-04-28 | 2023-05-02 | 5 | 3 | 2023-05-02 | 2023-08-11 | 102 | 74 | 2023-07-27 | 2023-10-17 | 2 | 2 | 2023-07-28 | 2023-08-22 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-10-02 | 2023-10-26 | 25 | 19 | 2023-10-26 | 2023-10-26 | 1 | 1 | 7 | 5 | 154 | 112 | 161 | 117 | Steps 2,3,5,6,7 | 96 | 68 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -262 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2024-02-14 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | -1167.47 | -13.76 | Unknown | Unknown | -1183 | 29.29 | 7860.12 | 2230.64 | -1167.47 | 3398.11 | Yes | N/A | N/A | 2023-03-27 | 2024-02-12 | 323 | 231 | 2024-02-12 | 2024-02-14 | 3 | 3 | 2024-02-14 | 2024-03-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-05-07 | 82 | 58 | Unknown | 2024-04-22 | Unknown | Unknown | 2024-05-07 | 2024-05-09 | 3 | 3 | 2024-05-09 | 2024-05-09 | 1 | 1 | 440 | 314 | 7 | 7 | 447 | 321 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | 335.78 | -22.31 | Unknown | Unknown | Unknown | 358.09 | 3981 | 703.58 | 335.78 | 367.8 | Yes | N/A | N/A | 2023-02-16 | 2023-02-16 | 1 | 1 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2023-06-28 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-08-01 | 35 | 25 | 2023-08-01 | 2023-08-01 | 1 | 1 | 134 | 96 | 36 | 26 | 170 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-19 | 189 | 136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-06-01 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 7296.72 | 2979.25 | Unknown | Unknown | 238.26 | 4079.21 | 3981 | 945.91 | 7296.72 | -6350.81 | Yes | N/A | N/A | 2023-05-19 | 2023-06-01 | 14 | 10 | 2023-06-01 | 2023-06-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-08-31 | 85 | 61 | Unknown | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2024-04-08 | 200 | 142 | 2024-04-08 | 2023-10-25 | Unknown | Unknown | 99 | 71 | 208 | 148 | 307 | 219 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -409 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.32 | -5.48 | Unknown | Unknown | Unknown | 9.8 | 3981 | 350.43 | 4.32 | 346.11 | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-01-08 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | CALTRANS-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-13 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 1897.93 | 159.3 | Unknown | Unknown | Unknown | 1738.63 | Unknown | 689.82 | 1897.93 | -1208.11 | Yes | N/A | N/A | 2024-05-08 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-13 | 41 | 29 | 2024-05-13 | Unknown | Unknown | Unknown | 2024-05-08 | 2024-07-08 | 62 | 44 | 2024-05-13 | 2024-07-08 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-24 | 17 | 13 | 2024-07-24 | 2024-07-24 | 1 | 1 | 57 | 41 | 121 | 87 | 178 | 128 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 2096.87 | 260.79 | Unknown | 61.31 | Unknown | 1774.77 | 3981 | 1230.79 | 2096.87 | -866.08 | Yes | N/A | N/A | 2024-04-11 | 2024-04-17 | 7 | 5 | 2024-04-17 | 2024-04-18 | 2 | 2 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-02-24 | 313 | 223 | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | 2025-02-27 | 1 | 1 | 320 | 228 | 7 | 7 | 327 | 235 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 11000 | 11000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-16 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 385.39 | -30.26 | Unknown | Unknown | Unknown | 415.65 | Unknown | 1992.19 | 385.39 | 1606.8 | Yes | N/A | N/A | 2023-01-31 | 2023-02-07 | 8 | 6 | 2023-02-07 | 2023-02-17 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 8 | 6 | 12 | 10 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | -417 | -298 | No | 2023-11-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-04-05 | 2024-05-20 | IOU Designed & Installed | N/A | Yes | 150 | 3096.68 | 522.41 | Unknown | 149.13 | Unknown | 2425.14 | Unknown | 1244.28 | 3096.68 | -1852.4 | Yes | N/A | N/A | 2023-11-28 | 2024-04-26 | 151 | 109 | 2024-04-26 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | 2024-04-05 | 2024-05-07 | 33 | 23 | 2024-05-08 | 2024-05-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-23 | 4 | 4 | 2024-05-23 | 2024-05-23 | 1 | 1 | 164 | 118 | 38 | 28 | 202 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -482 | -345 | No | 2024-09-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-30 | 2025-03-11 | IOU Designed & Installed | N/A | Yes | 154 | 2122.16 | -42.05 | Unknown | Unknown | Unknown | 2164.21 | Unknown | 1730.99 | 2122.16 | -391.17 | Yes | N/A | N/A | 2024-09-05 | 2025-02-06 | 155 | 111 | 2025-02-06 | 2024-09-30 | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-03-11 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-14 | 35 | 25 | 2025-04-14 | 2025-04-14 | 1 | 1 | 318 | 228 | 36 | 26 | 354 | 254 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | -635 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-11-18 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 40.15 | Unknown | Unknown | Unknown | Unknown | 40.15 | Unknown | 1513.5 | 40.15 | 1473.35 | Yes | N/A | N/A | 2024-10-24 | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-11-18 | 49 | 35 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-03 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-23 | 21 | 15 | 2024-12-23 | 2024-12-23 | 1 | 1 | 16 | 12 | 71 | 51 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 2333.1 | 2333.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-05 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 2656.21 | 306.56 | Unknown | Unknown | Unknown | 2349.65 | 3981 | 2512.99 | 2656.21 | -143.22 | Yes | N/A | N/A | 2024-09-03 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-09-03 | 54 | 38 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-22 | 50 | 36 | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-22 | 2024-10-30 | 9 | 7 | 2024-10-30 | 2024-10-30 | 1 | 1 | 50 | 36 | 64 | 46 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-22 | -334 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | -4202.14 | 1060.34 | Unknown | 186.47 | -5975 | 526.05 | Unknown | 5975.08 | -4202.14 | 10177.22 | Yes | N/A | N/A | 2024-02-02 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-02-23 | 4 | 4 | 2024-02-23 | 2024-02-23 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -730 | -523 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-02-22 | IOU Designed & Installed | N/A | No | N/A | 489.52 | 237.76 | Unknown | 88.1 | Unknown | 163.66 | Unknown | 64.88 | 489.52 | -424.64 | Yes | N/A | N/A | 2023-02-21 | 2023-02-21 | 1 | 1 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-02-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | 2023-02-22 | 1 | 1 | 2023-02-22 | 2023-02-22 | 1 | 1 | 3 | 3 | 2 | 2 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | -21.2 | Unknown | Unknown | Unknown | 7.51 | -28.71 | Unknown | 1812.3 | -21.2 | 1833.5 | Yes | N/A | N/A | 2024-08-20 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-21 | 10 | 8 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-11-25 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-19 | 25 | 19 | 2024-12-19 | 2024-12-19 | 1 | 1 | 98 | 70 | 36 | 28 | 134 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -157 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 11391.97 | 725.18 | Unknown | 114.73 | 309.41 | 10242.65 | 0 | 10914.2 | 11391.97 | -477.77 | Yes | N/A | N/A | 2024-08-05 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-02-20 | 32 | 22 | 2024-08-30 | 2025-02-04 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-06-26 | 143 | 103 | 2025-06-26 | 2025-06-26 | 1 | 1 | 159 | 113 | 176 | 126 | 335 | 239 | Steps 2,3,5,6,7 | 174 | 124 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -487 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 20303.9 | 8442.17 | Unknown | Unknown | 86.66 | 11775.07 | Unknown | 17581.42 | 20303.9 | -2722.48 | Yes | N/A | N/A | 2025-02-04 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-06-30 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-30 | 20 | 14 | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-17 | 34 | 24 | 2025-06-17 | 2025-06-17 | 1 | 1 | 0 | 0 | 216 | 154 | 216 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 85 | 85 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | -1687.11 | Unknown | Unknown | Unknown | -1709 | 21.89 | Unknown | 1591.33 | -1687.11 | 3278.44 | Yes | N/A | N/A | 2024-07-25 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-07-26 | 100 | 72 | 2024-07-26 | 2024-08-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-09-26 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-10 | 15 | 11 | 2024-10-10 | 2024-10-09 | Unknown | Unknown | 64 | 46 | 115 | 83 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 906.63 | -15.59 | Unknown | Unknown | Unknown | 922.22 | Unknown | 1066.55 | 906.63 | 159.92 | Yes | N/A | N/A | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2025-01-09 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-20 | 32 | 24 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-01-31 | 1 | 1 | 1 | 1 | 97 | 71 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 1599.61 | 475.14 | Unknown | Unknown | Unknown | 1124.47 | 3981 | 1460.16 | 1599.61 | -139.45 | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-10-03 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-24 | 22 | 16 | 2024-10-24 | 2024-10-24 | 1 | 1 | 43 | 31 | 24 | 18 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 414.05 | 414.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -705 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-08-14 | IOU Designed & Installed | N/A | No | N/A | 599.11 | -17.49 | Unknown | Unknown | Unknown | 616.6 | Unknown | 351.99 | 599.11 | -247.12 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-08-14 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-12-11 | 120 | 86 | 2023-12-11 | 2023-12-11 | 1 | 1 | 167 | 119 | 121 | 87 | 288 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | -186 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1636.7 | 1254.26 | Unknown | 825.44 | -1039 | 596 | Unknown | 1039.27 | 1636.7 | -597.43 | Yes | N/A | N/A | 2023-10-27 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | 2023-05-09 | IOU Designed & Installed | N/A | No | N/A | 3082.29 | 421.38 | Unknown | 1035.51 | 18.14 | 1607.26 | 3241 | 165.03 | 3082.29 | -2917.26 | Yes | N/A | N/A | 2022-11-29 | 2023-03-28 | 120 | 86 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-05-09 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-05-10 | 2 | 2 | 2023-05-10 | 2023-05-10 | 1 | 1 | 163 | 117 | 3 | 3 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-10-16 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 80.19 | Unknown | Unknown | Unknown | Unknown | 80.19 | Unknown | 1451.12 | 80.19 | 1370.93 | Yes | N/A | N/A | 2024-09-25 | 2024-10-11 | 17 | 13 | 2024-10-11 | 2024-10-16 | 6 | 4 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2025-01-23 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-03-03 | 40 | 28 | 2025-03-03 | 2025-03-03 | 1 | 1 | 117 | 85 | 47 | 33 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-21 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 6899.65 | Unknown | Unknown | Unknown | Unknown | 6899.65 | 3981 | 1141.63 | 6899.65 | -5758.02 | Yes | N/A | N/A | 2024-10-18 | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-21 | 15 | 11 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2025-01-28 | 100 | 72 | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-28 | 2025-02-03 | 7 | 5 | 2025-02-03 | 2025-02-03 | 1 | 1 | 100 | 72 | 23 | 17 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-10-13 | 944 | 675 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1144.69 | -16.25 | Unknown | Unknown | -1163 | 34.56 | 3981 | 1760.29 | -1144.69 | 2904.98 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | 2023-06-21 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2024-04-17 | 302 | 216 | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-05-14 | 1 | 1 | 303 | 217 | 128 | 92 | 431 | 309 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-12 | 613 | 440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1459.1 | -14.8 | Unknown | Unknown | 6.27 | 1467.63 | Unknown | 2702.7 | 1459.1 | 1243.6 | Yes | N/A | N/A | 2023-09-13 | 2024-05-10 | 241 | 173 | 2024-05-10 | 2024-05-13 | 4 | 2 | 2023-10-09 | 2024-03-20 | 159 | 115 | 2023-09-29 | 2024-08-07 | 68 | 48 | 2024-05-13 | 2024-07-30 | 79 | 57 | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 479 | 345 | 72 | 50 | 551 | 395 | Steps 2,3,5,6,7 | 476 | 340 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -583 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-13 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 974 | 248.19 | Unknown | Unknown | Unknown | 725.81 | Unknown | 1993.02 | 974 | 1019.02 | Yes | N/A | N/A | 2025-01-08 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-13 | 18 | 12 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-11 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-04-03 | 52 | 38 | 2025-04-03 | 2025-04-03 | 1 | 1 | 30 | 22 | 71 | 51 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | 2023-07-14 | IOU Designed & Installed | N/A | No | N/A | 634.92 | 236.04 | Unknown | Unknown | Unknown | 398.88 | Unknown | 837.2 | 634.92 | 202.28 | Yes | N/A | N/A | 2023-06-22 | 2023-06-22 | 1 | 1 | 2023-06-22 | 2023-06-22 | 1 | 1 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-07-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-07-17 | 4 | 2 | 2023-07-17 | 2023-07-17 | 1 | 1 | 24 | 18 | 6 | 4 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-03-29 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 4420.58 | 1306.92 | Unknown | 19.76 | Unknown | 3093.9 | 3981 | 931.18 | 4420.58 | -3489.4 | Yes | N/A | N/A | 2024-01-24 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-03-29 | 122 | 88 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-10-04 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-18 | 15 | 11 | 2024-10-18 | 2024-10-11 | Unknown | Unknown | 190 | 136 | 137 | 99 | 327 | 235 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-27 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 1196.31 | 445.84 | Unknown | Unknown | Unknown | 750.47 | 3981 | 963.92 | 1196.31 | -232.39 | Yes | N/A | N/A | 2023-09-27 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-10-30 | 109 | 77 | 2023-10-30 | 2023-11-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-11-30 | 4 | 4 | 2023-11-30 | 2023-11-30 | 1 | 1 | 58 | 42 | 114 | 82 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-10 | 57 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-05-06 | 2025-01-04 | IOU Designed & Installed | N/A | No | N/A | 36269.67 | 4777.18 | Unknown | 713.83 | 302.94 | 30475.72 | 37590.18 | 25237.39 | 36269.67 | -11032.28 | Yes | N/A | N/A | 2024-04-19 | 2024-04-24 | 6 | 4 | 2024-04-24 | 2024-10-08 | 168 | 120 | 2024-08-06 | 2024-08-25 | 20 | 14 | 2024-10-11 | 2024-10-21 | 11 | 7 | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-11 | 2024-12-23 | 74 | 52 | 2025-01-04 | 2025-01-06 | 3 | 1 | 2025-01-06 | 2025-01-06 | 1 | 1 | 26 | 18 | 257 | 181 | 283 | 199 | Steps 2,3,5,6,7 | 76 | 54 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -584 | -419 | No | 2024-11-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-12-02 | 2025-03-27 | IOU Designed & Installed | N/A | Yes | 23 | -15.85 | -12.2 | Unknown | Unknown | 1.7 | -5.35 | 3981 | 1268.2 | -15.85 | 1284.05 | Yes | N/A | N/A | 2024-11-26 | 2024-12-19 | 24 | 18 | 2024-12-19 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-03-27 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-03-31 | 5 | 3 | 2025-03-31 | 2025-03-31 | 1 | 1 | 130 | 94 | 6 | 4 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-12 | 715 | 512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2556.09 | -8.14 | Unknown | Unknown | 23.41 | 2540.82 | Unknown | 685.72 | 2556.09 | -1870.37 | Yes | N/A | N/A | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-05 | 2024-06-18 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-03-31 | 2024-05-21 | 52 | 37 | 2024-06-18 | 2024-11-21 | 157 | 113 | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-11-26 | Unknown | Unknown | 158 | 114 | 158 | 113 | 316 | 227 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -444 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-26 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1290.26 | Unknown | Unknown | Unknown | 44.55 | 1245.71 | 3981 | 1086.65 | 1290.26 | -203.61 | Yes | N/A | N/A | 2024-03-18 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-16 | 64 | 46 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-10-29 | 197 | 141 | Unknown | 2024-10-25 | Unknown | Unknown | 2024-10-29 | 2024-11-13 | 16 | 12 | 2024-11-13 | 2024-11-13 | 1 | 1 | 197 | 141 | 81 | 59 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -196 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1575.56 | 415.69 | Unknown | Unknown | Unknown | 1159.87 | Unknown | 1668.08 | 1575.56 | 92.52 | Yes | N/A | N/A | 2023-04-20 | 2025-04-29 | 741 | 529 | 2025-04-29 | 2025-05-23 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 741 | 529 | 48 | 36 | 789 | 565 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 215.13 | -10.45 | Unknown | Unknown | 4.13 | 221.45 | 3981 | 671.4 | 215.13 | 456.27 | Yes | N/A | N/A | 2023-04-04 | 2023-04-20 | 17 | 13 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 17 | 13 | 1 | 1 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 107 | 107 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | -305 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-03-29 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 3313.39 | 2916.95 | Unknown | Unknown | -21972 | 22368.44 | Unknown | 21971.56 | 3313.39 | 18658.17 | Yes | N/A | N/A | 2024-02-01 | 2024-03-06 | 35 | 25 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-09-13 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-24 | 24 | 18 | 2024-10-24 | 2024-10-24 | 1 | 1 | 35 | 25 | 31 | 23 | 66 | 48 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1278.86 | -25.7 | Unknown | Unknown | Unknown | 1304.56 | 3981 | 1657.76 | 1278.86 | 378.9 | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-21 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | -479 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | -4.29 | -8.29 | Unknown | Unknown | Unknown | 4 | 3981 | 785.92 | -4.29 | 790.21 | Yes | N/A | N/A | 2023-03-08 | 2023-05-25 | 79 | 57 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-09-28 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-11 | 14 | 10 | 2023-10-11 | 2023-09-28 | Unknown | Unknown | 206 | 148 | 14 | 10 | 220 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -570 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 19947.38 | 11833.44 | Unknown | 86.76 | 300 | 7727.18 | Unknown | 483.59 | 19947.38 | -19463.79 | Yes | N/A | N/A | 2023-11-13 | 2024-01-02 | 51 | 37 | 2024-01-02 | 2024-01-05 | 4 | 4 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-09 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-24 | 16 | 12 | 2024-01-24 | 2024-01-24 | 1 | 1 | 56 | 40 | 21 | 17 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-21 | 233 | 168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-04-26 | 2023-05-04 | IOU Designed & Installed | N/A | No | N/A | 13506.93 | 753.17 | Unknown | Unknown | 112.7 | 12641.06 | 3981 | 1093.42 | 13506.93 | -12413.51 | Yes | N/A | N/A | 2023-03-01 | 2023-04-25 | 56 | 40 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-05-04 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-07-12 | 70 | 50 | 2023-07-12 | 2023-07-12 | 1 | 1 | 65 | 47 | 71 | 51 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | -206 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-07-09 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 21798.25 | 3801.92 | Unknown | Unknown | 76.39 | 17919.94 | 0 | 55358.48 | 21798.25 | 33560.23 | Yes | N/A | N/A | 2024-06-18 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-18 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-11 | 31 | 23 | 2025-06-11 | 2025-06-11 | 1 | 1 | 0 | 0 | 89 | 65 | 89 | 65 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-09-25 | 2024-10-05 | IOU Designed & Installed | N/A | No | N/A | 4816.28 | 4833.6 | Unknown | 1512.1 | -4512 | 2982.58 | Unknown | 4511.8 | 4816.28 | -304.48 | Yes | N/A | N/A | 2024-06-26 | 2024-10-01 | 98 | 70 | 2024-10-01 | 2024-10-29 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-05 | 2024-11-06 | 33 | 23 | 2024-11-06 | 2024-11-06 | 1 | 1 | 98 | 70 | 64 | 46 | 162 | 116 | Steps 2,3,5,6,7 | 24 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 867.3 | -16.8 | Unknown | Unknown | Unknown | 884.1 | 3981 | 1543.58 | 867.3 | 676.28 | Yes | N/A | N/A | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | 2024-08-08 | 3 | 3 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-10-14 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-29 | 16 | 12 | 2024-10-29 | 2024-10-29 | 1 | 1 | 69 | 49 | 20 | 16 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | Valley Center | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | 560 | 401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | -3192.4 | 922.47 | Unknown | 212.32 | -7045 | 2717.81 | 4637.62 | 25506.8 | -3192.4 | 28699.2 | Yes | N/A | N/A | 2024-12-31 | 2025-01-02 | 3 | 3 | 2025-01-02 | 2025-04-03 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-17 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-05-05 | 33 | 23 | 2025-05-05 | 2025-05-05 | 1 | 1 | 3 | 3 | 130 | 92 | 133 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 263.13 | -4.98 | Unknown | Unknown | Unknown | 268.11 | Unknown | 466.88 | 263.13 | 203.75 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-05 | 27 | 19 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-07-31 | 1 | 1 | 2 | 2 | 79 | 57 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15.4 | 15.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -501 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-04-21 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | -901.14 | -8.08 | Unknown | Unknown | -1303 | 409.94 | Unknown | Not available | -901.14 | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-04-15 | 91 | 65 | 2025-04-15 | 2025-04-21 | 7 | 5 | 2025-04-21 | 2025-05-06 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-08 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-19 | 12 | 8 | 2025-05-19 | 2025-05-19 | 1 | 1 | 110 | 80 | 20 | 14 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -170 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 2709.81 | 608.53 | Unknown | Unknown | 1.5 | 2099.78 | 3981 | 969.97 | 2709.81 | -1739.84 | Yes | N/A | N/A | 2024-04-22 | 2024-06-03 | 43 | 31 | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-09-09 | 99 | 71 | Unknown | 2024-08-29 | Unknown | Unknown | 2024-09-09 | 2024-09-12 | 4 | 4 | 2024-09-12 | 2024-09-12 | 1 | 1 | 142 | 102 | 6 | 6 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 11.75 | 11.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-28 | 312 | 224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-10-04 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | 3081.62 | 706.83 | Unknown | 289.43 | Unknown | 2085.36 | 3981 | 497.61 | 3081.62 | -2584.01 | Yes | N/A | N/A | 2023-06-08 | 2023-10-04 | 119 | 85 | 2023-10-04 | 2024-02-14 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | 2024-02-14 | 2024-10-31 | 261 | 187 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | 2025-04-05 | 3 | 2 | 380 | 272 | 138 | 99 | 518 | 371 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -458 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 676.97 | -12.92 | Unknown | Unknown | Unknown | 689.89 | 3981 | 1546.95 | 676.97 | 869.98 | Yes | N/A | N/A | 2024-08-01 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-08-09 | 80 | 58 | 2024-08-09 | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-17 | 9 | 6 | 2024-08-01 | 2025-02-05 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-11 | 7 | 5 | 2025-02-11 | 2025-02-11 | 1 | 1 | 189 | 135 | 97 | 70 | 286 | 205 | Steps 2,3,5,6,7 | 16 | 11 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -392 | -281 | No | 2024-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | Yes | 151 | 69.47 | -0.94 | Unknown | Unknown | 0.14 | 70.27 | 3981 | 1046.76 | 69.47 | 977.29 | Yes | N/A | N/A | 2024-02-16 | 2024-07-16 | 152 | 108 | 2024-07-16 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2024-12-12 | Unknown | Unknown | 152 | 108 | 0 | 0 | 152 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -458 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2024-10-18 | 130 | 94 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-06-23 | 249 | 177 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 249 | 177 | 133 | 97 | 382 | 274 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | -326 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 1341.28 | 409.4 | Unknown | Unknown | Unknown | 931.88 | 3981 | 1010.77 | 1341.28 | -330.51 | Yes | N/A | N/A | 2024-01-24 | 2024-02-13 | 21 | 15 | 2024-02-13 | 2024-02-14 | 2 | 2 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-09-27 | 227 | 163 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-07 | 11 | 7 | 2024-10-07 | 2024-10-03 | Unknown | Unknown | 248 | 178 | 13 | 9 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | 256 | 183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-31 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 62623.37 | 3873.08 | Unknown | Unknown | 37.16 | 58713.13 | 0 | 28647.19 | 62623.37 | -33976.18 | Yes | N/A | N/A | 2023-12-15 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-01-09 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-03-11 | 41 | 29 | 2025-03-11 | 2025-03-11 | 1 | 1 | 0 | 0 | 92 | 66 | 92 | 66 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | -30 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 714.6 | -11.95 | Unknown | Unknown | 22.54 | 704.01 | 3981 | 679.07 | 714.6 | -35.53 | Yes | N/A | N/A | 2023-06-06 | 2023-07-07 | 32 | 24 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2024-01-26 | 204 | 146 | Unknown | 2023-12-11 | Unknown | Unknown | 2024-01-26 | 2024-02-12 | 18 | 12 | 2024-02-12 | 2024-02-12 | 1 | 1 | 236 | 170 | 19 | 13 | 255 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-17 | 175 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | -2.23 | -4.39 | Unknown | Unknown | Unknown | 2.16 | 3885 | 717.75 | -2.23 | 719.98 | Yes | N/A | N/A | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-08-28 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-08 | 12 | 10 | 2023-09-08 | 2023-09-08 | 1 | 1 | 26 | 18 | 14 | 12 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-09-30 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 614.49 | -11.7 | Unknown | Unknown | Unknown | 626.19 | 3981 | 3047.79 | 614.49 | 2433.3 | Yes | N/A | N/A | 2024-08-19 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-10-02 | 64 | 46 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-12-03 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-11 | 9 | 7 | 2024-12-11 | 2024-12-11 | 1 | 1 | 63 | 45 | 74 | 54 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 273 | 196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-31 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 981.82 | -11.11 | Unknown | Unknown | 44.75 | 948.18 | 3991 | 308.44 | 981.82 | -673.38 | Yes | N/A | N/A | 2023-08-21 | 2023-09-11 | 22 | 16 | 2023-09-11 | 2025-03-17 | 554 | 396 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2024-02-20 | 163 | 117 | Unknown | 2024-01-05 | Unknown | Unknown | 2024-02-20 | 2024-02-26 | 7 | 5 | 2024-02-26 | 2024-02-28 | 3 | 3 | 185 | 133 | 564 | 404 | 749 | 537 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | -7.6 | -6.19 | Unknown | Unknown | Unknown | -1.41 | Unknown | 946.25 | -7.6 | 953.85 | Yes | N/A | N/A | 2024-05-09 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-05-09 | 56 | 40 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-05 | 20 | 14 | 2024-06-05 | 2024-06-05 | 1 | 1 | 9 | 7 | 77 | 55 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -376 | -270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-25 | 2024-05-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 22.43 | Unknown | Unknown | Unknown | Unknown | 22.43 | 3885 | 1457.44 | 22.43 | 1435.01 | Yes | N/A | N/A | 2024-05-25 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-05-25 | 194 | 139 | 2024-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-10-21 | 1 | 1 | 0 | 0 | 195 | 140 | 195 | 140 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 86.1 | 86.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -613 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-16 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 18.65 | -16.57 | Unknown | Unknown | Unknown | 35.22 | 3981 | 1024.22 | 18.65 | 1005.57 | Yes | N/A | N/A | 2024-03-27 | 2024-04-03 | 8 | 6 | 2024-04-03 | 2024-04-16 | 14 | 10 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-06-11 | 51 | 37 | 2024-06-11 | 2024-05-13 | Unknown | Unknown | 15 | 11 | 65 | 47 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 412.05 | 412.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-25 | -841 | -602 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | 966.23 | 192.21 | Unknown | Unknown | 6.41 | 767.61 | 3981 | 1583.29 | 966.23 | 617.06 | Yes | N/A | N/A | 2023-05-02 | 2023-05-18 | 17 | 13 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-07-21 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-08-07 | 18 | 12 | 2023-08-07 | 2023-08-07 | 1 | 1 | 82 | 60 | 19 | 13 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | 56 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2024-03-23 | IOU Designed & Installed | N/A | No | N/A | 1423.74 | 441.72 | Unknown | 97.86 | Unknown | 884.16 | 3981 | 1940.46 | 1423.74 | 516.72 | Yes | N/A | N/A | 2023-03-01 | 2023-06-14 | 106 | 76 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2024-03-23 | 284 | 203 | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-23 | 2024-03-26 | 4 | 2 | 2024-03-26 | 2024-03-26 | 1 | 1 | 390 | 279 | 5 | 3 | 395 | 282 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | 149 | 149 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-31 | 490 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-14 | 2023-02-23 | 2023-04-28 | IOU Designed & Installed | N/A | No | N/A | 4527.92 | Unknown | Unknown | Unknown | Unknown | 4527.92 | 3991 | 644.82 | 4527.92 | -3883.1 | Yes | N/A | N/A | 2021-12-14 | 2023-02-23 | 437 | 313 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-04-28 | 65 | 47 | Unknown | 2023-04-25 | Unknown | Unknown | 2023-04-28 | 2023-05-08 | 11 | 7 | 2023-05-08 | 2023-05-05 | Unknown | Unknown | 502 | 360 | 11 | 7 | 513 | 367 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | 2393.64 | 504.14 | Unknown | Unknown | Unknown | 1889.5 | 3981 | 1035.45 | 2393.64 | -1358.19 | Yes | N/A | N/A | 2025-05-07 | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-07 | 6 | 4 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-23 | 17 | 13 | 2025-05-07 | 2025-05-07 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-30 | 24 | 18 | 2025-05-30 | 2025-05-30 | 1 | 1 | 1 | 1 | 48 | 36 | 49 | 37 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1978.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-03-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-06 | 41 | 29 | 2025-05-06 | 2025-05-06 | 1 | 1 | 3 | 3 | 43 | 31 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | 407.04 | 407.04 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 583 | 418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | 2022-04-26 | 2023-12-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 60116.45 | 13670.97 | Unknown | 1794.93 | 8310.44 | 36340.11 | 0 | 65311.65 | 60116.45 | 5195.2 | Yes | N/A | N/A | 2022-04-26 | 2023-02-24 | 305 | 219 | 2023-02-24 | 2023-08-15 | 173 | 123 | 2023-07-05 | 2023-10-02 | 58 | 42 | 2023-07-06 | 2023-07-10 | 5 | 3 | 2023-08-23 | Unknown | Unknown | Unknown | 2023-08-23 | 2024-05-15 | 267 | 191 | 2023-12-27 | 2024-12-04 | 344 | 246 | 2024-12-04 | 2024-12-04 | 1 | 1 | 363 | 261 | 790 | 564 | 1153 | 825 | Steps 2,3,5,6,7 | 269 | 191 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | -550 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | 2711.58 | 659.28 | Unknown | 113.51 | Unknown | 1938.79 | 3981 | 1660.65 | 2711.58 | -1050.93 | Yes | N/A | N/A | 2025-03-05 | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-03-05 | 13 | 9 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-07 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-04-29 | 54 | 38 | 2025-04-29 | 2025-04-29 | 1 | 1 | 3 | 3 | 68 | 48 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13.5 | 13.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -94 | -68 | No | 2024-06-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | Yes | 11 | 44.57 | Unknown | Unknown | Unknown | Unknown | 44.57 | 3981 | 3086.98 | 44.57 | 3042.41 | Yes | N/A | N/A | 2024-06-07 | 2024-06-18 | 12 | 8 | 2024-06-18 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | 2024-12-11 | 2024-12-11 | 1 | 1 | 12 | 8 | 1 | 1 | 13 | 9 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAKESIDE | COUNTY OF SAN DIEGO-NORTH of 56 | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -248 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-21 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 2470.43 | 3960.63 | Unknown | 2750.42 | -14871 | 10630.38 | Unknown | 14726.32 | 2470.43 | 12255.89 | Yes | N/A | N/A | 2024-08-02 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2025-02-04 | 222 | 158 | 2024-09-27 | 2024-11-22 | 14 | 10 | 2024-11-21 | 2025-01-30 | 35 | 25 | 2025-02-04 | 2025-03-19 | 44 | 32 | 2025-02-06 | 2025-03-20 | 43 | 31 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | 2025-04-11 | Unknown | Unknown | 58 | 42 | 301 | 215 | 359 | 257 | Steps 2,3,5,6,7 | 172 | 122 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 5.79 | Unknown | Unknown | Unknown | Unknown | 5.79 | Unknown | 1636.18 | 5.79 | 1630.39 | Yes | N/A | N/A | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-07 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-24 | 46 | 32 | 2025-03-24 | 2025-03-24 | 1 | 1 | 4 | 4 | 48 | 34 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 42.56 | Unknown | Unknown | Unknown | Unknown | 42.56 | Unknown | 623.63 | 42.56 | 581.07 | Yes | N/A | N/A | 2024-12-03 | 2024-12-27 | 25 | 19 | 2024-12-27 | 2025-01-22 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 25 | 19 | 28 | 20 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Carlsbad | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -305 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2024-12-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 447.77 | 558.59 | Unknown | 79.66 | -10929.74 | 10739.26 | Unknown | 10685.43 | 447.77 | 10237.66 | Yes | N/A | N/A | 2023-10-26 | 2024-04-17 | 175 | 125 | 2024-04-17 | 2024-10-02 | 169 | 121 | 2024-06-07 | 2024-08-30 | 72 | 52 | 2024-07-03 | 2024-09-30 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-30 | 44 | 32 | 2025-01-30 | 2025-01-30 | 1 | 1 | 247 | 177 | 271 | 195 | 518 | 372 | Steps 2,3,5,6,7 | 175 | 125 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-20 | 463 | 330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6232.84 | Unknown | Unknown | Unknown | Unknown | 6232.84 | 95509 | 9961.33 | 6232.84 | 3728.49 | Yes | N/A | N/A | 2023-09-19 | 2023-12-04 | 77 | 55 | 2023-12-04 | 2024-02-20 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-08-02 | 165 | 119 | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-08-25 | Unknown | Unknown | 242 | 174 | 79 | 57 | 321 | 231 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | 363 | 260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | -244.13 | Unknown | Unknown | Unknown | -1073.6 | 829.47 | 3981 | 1238.82 | -244.13 | 1482.95 | Yes | N/A | N/A | 2024-04-18 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-04-18 | 101 | 73 | 2024-04-18 | 2025-01-13 | 271 | 193 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-10-16 | 182 | 130 | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-16 | 2025-02-12 | 120 | 86 | 2025-02-12 | 2025-02-11 | Unknown | Unknown | 453 | 323 | 221 | 159 | 674 | 482 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -504 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 1542.35 | Unknown | Unknown | Unknown | 8.75 | 1533.6 | 3981 | 3844.08 | 1542.35 | 2301.73 | Yes | N/A | N/A | 2024-10-03 | 2024-11-03 | 32 | 22 | 2024-11-03 | 2024-12-19 | 47 | 34 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-27 | 71 | 51 | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-04-09 | 42 | 30 | 2025-04-09 | 2025-04-09 | 1 | 1 | 103 | 73 | 90 | 65 | 193 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | DEL MAR | DEL MAR | 20003 | 20003 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-10 | 421 | 301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-12-19 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 601.14 | -12.08 | Unknown | Unknown | Unknown | 613.22 | 3981 | 1930.84 | 601.14 | 1329.7 | Yes | N/A | N/A | 2024-04-10 | 2024-12-19 | 254 | 182 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-23 | 2025-03-13 | 81 | 59 | 2024-12-19 | 2025-05-01 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-05 | 5 | 3 | 2025-05-05 | 2025-05-05 | 1 | 1 | 388 | 278 | 88 | 64 | 476 | 342 | Steps 2,3,5,6,7 | 84 | 60 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 668.15 | 668.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | 66 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 94.09 | Unknown | Unknown | Unknown | Unknown | 94.09 | 3981 | 914.01 | 94.09 | 819.92 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-06 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -472 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1108.6 | -12.73 | Unknown | Unknown | -1109 | 13.13 | 3885 | 1881.58 | -1108.6 | 2990.18 | Yes | N/A | N/A | 2023-05-15 | 2023-08-01 | 79 | 57 | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-16 | 1 | 1 | 88 | 64 | 2 | 2 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Commercial | N/A | Santee | SANTEE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-19 | 1672 | 1195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 85345.16 | 10659.56 | Unknown | Unknown | 2892.62 | 71792.98 | 1128880.72 | 57952.15 | 85345.16 | -27393.01 | Yes | N/A | N/A | 2024-03-05 | 2024-06-17 | 105 | 75 | 2024-06-17 | 2024-06-28 | 12 | 10 | 2024-05-07 | 2024-06-25 | 14 | 10 | 2024-05-28 | 2024-07-10 | 26 | 18 | 2024-06-28 | Unknown | Unknown | Unknown | 2025-01-08 | 2025-05-06 | 119 | 85 | 2024-10-10 | 2025-06-18 | 252 | 180 | 2025-06-18 | 2025-06-18 | 1 | 1 | 119 | 85 | 410 | 294 | 529 | 379 | Steps 2,3,5,6,7 | 300 | 214 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | -438 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-11-02 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | -9.32 | -7.59 | Unknown | Unknown | Unknown | -1.73 | Unknown | 513.31 | -9.32 | 522.63 | Yes | N/A | N/A | 2023-10-19 | 2023-10-31 | 13 | 9 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2024-03-28 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-16 | 20 | 14 | 2024-04-16 | 2024-04-16 | 1 | 1 | 161 | 115 | 22 | 16 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | -563 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-09-10 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | -1224.75 | Unknown | Unknown | Unknown | -1291 | 66.25 | 3981 | 2345.1 | -1224.75 | 3569.85 | Yes | N/A | N/A | 2024-07-03 | 2024-08-27 | 56 | 40 | 2024-08-27 | 2024-09-10 | 15 | 11 | 2024-09-10 | 2024-09-13 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-28 | 46 | 32 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-28 | 2024-10-30 | 3 | 3 | 2024-10-30 | 2024-10-30 | 1 | 1 | 106 | 76 | 19 | 15 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | 64 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-27 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 32133.22 | 9419.94 | Unknown | 1037.57 | -1031 | 22706.71 | 55259 | 27715.77 | 32133.22 | -4417.45 | Yes | N/A | N/A | 2023-08-29 | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2024-03-20 | 216 | 154 | 2023-10-01 | 2024-03-05 | 11 | 8 | 2024-03-12 | 2024-11-12 | 246 | 176 | 2024-03-20 | 2024-09-12 | 177 | 127 | 2024-05-28 | 2024-09-10 | 106 | 76 | 2024-11-15 | 2024-12-06 | 22 | 16 | 2024-12-06 | 2024-12-06 | 1 | 1 | 188 | 135 | 591 | 423 | 779 | 558 | Steps 2,3,5,6,7 | 515 | 368 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -148 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-30 | 2023-09-18 | IOU Designed & Installed | N/A | No | N/A | 359.55 | -12.46 | Unknown | Unknown | Unknown | 372.01 | 3981 | 818.41 | 359.55 | 458.86 | Yes | N/A | N/A | 2023-05-16 | 2023-05-30 | 15 | 11 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-09-18 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-10-05 | 18 | 14 | 2023-10-05 | 2023-10-05 | 1 | 1 | 127 | 91 | 19 | 15 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | 62 | 45 | No | 2023-07-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-08-01 | 2024-05-06 | IOU Designed & Installed | N/A | Yes | 281 | 687.57 | -20.14 | Unknown | Unknown | Unknown | 707.71 | 3981 | 722.98 | 687.57 | 35.41 | Yes | N/A | N/A | 2023-07-20 | 2024-04-26 | 282 | 202 | 2024-04-26 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2024-05-06 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-15 | 10 | 8 | 2024-05-15 | 2024-05-30 | 16 | 12 | 562 | 402 | 26 | 20 | 588 | 422 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-24 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 230.33 | -4.5 | Unknown | Unknown | Unknown | 234.83 | 3981 | 1348.01 | 230.33 | 1117.68 | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-27 | 35 | 25 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2 | 2 | 37 | 27 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-23 | 101 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 17.57 | -15.58 | Unknown | Unknown | Unknown | 33.15 | 3981 | 507.27 | 17.57 | 489.7 | Yes | N/A | N/A | 2022-01-10 | 2023-03-21 | 436 | 312 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-07-02 | 6 | 4 | 436 | 312 | 6 | 4 | 442 | 316 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | 371 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 127197.04 | 13590.43 | Unknown | Unknown | 165.72 | 113440.89 | 0 | 64242.49 | 127197.04 | -62954.55 | Yes | N/A | N/A | 2024-03-04 | 2024-03-04 | 1 | 1 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-02-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-09 | 38 | 28 | 2025-04-09 | 2025-04-09 | 1 | 1 | 1 | 1 | 90 | 66 | 91 | 67 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1810.45 | -38.1 | Unknown | Unknown | Unknown | 1848.55 | 31061.47 | 674.17 | 1810.45 | -1136.28 | Yes | N/A | N/A | 2023-04-27 | 2023-08-10 | 106 | 76 | 2023-08-10 | 2023-08-29 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2024-05-02 | 248 | 178 | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-17 | 3 | 3 | 354 | 254 | 23 | 17 | 377 | 271 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | 297 | 212 | No | 2023-06-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2024-04-16 | IOU Designed & Installed | N/A | Yes | 104 | 2095.47 | -14.26 | Unknown | Unknown | 162.21 | 1947.52 | 3981 | 964.58 | 2095.47 | -1130.89 | Yes | N/A | N/A | 2023-03-24 | 2023-09-21 | 182 | 130 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2024-04-16 | 313 | 223 | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-16 | 2024-06-06 | 52 | 38 | 2024-06-06 | 2024-04-22 | Unknown | Unknown | 495 | 353 | 52 | 38 | 547 | 391 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 328.35 | -13.44 | Unknown | Unknown | Unknown | 341.79 | 7962 | 1001.38 | 328.35 | 673.03 | Yes | N/A | N/A | 2023-12-05 | 2023-12-18 | 14 | 10 | 2023-12-18 | 2023-12-19 | 2 | 2 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 14 | 10 | 3 | 3 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-26 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-05-01 | IOU Designed & Installed | N/A | No | N/A | -63 | 996.2 | Unknown | 62.95 | -1735 | 612.85 | Unknown | 1734.76 | -63 | 1797.76 | Yes | N/A | N/A | 2023-04-07 | 2023-04-27 | 21 | 15 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-05-04 | 4 | 4 | 2023-05-04 | 2023-05-04 | 1 | 1 | 21 | 15 | 5 | 5 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -318 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | 3361.67 | 918.32 | Unknown | Unknown | Unknown | 2443.35 | 3981 | 1220.62 | 3361.67 | -2141.05 | Yes | N/A | N/A | 2025-03-03 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-03 | 4 | 2 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-03 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-09 | 7 | 5 | 2025-04-09 | 2025-04-09 | 1 | 1 | 32 | 24 | 12 | 8 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -530 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-06-03 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 6.57 | Unknown | Unknown | Unknown | Unknown | 6.57 | 3981 | 1673.41 | 6.57 | 1666.84 | Yes | N/A | N/A | 2024-05-17 | 2024-06-03 | 18 | 12 | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-08-12 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-20 | 9 | 7 | 2024-08-20 | 2024-08-19 | Unknown | Unknown | 89 | 63 | 10 | 8 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | 208.76 | -8.43 | Unknown | Unknown | Unknown | 217.19 | Unknown | 287.46 | 208.76 | 78.7 | Yes | N/A | N/A | 2024-01-29 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2024-01-29 | 110 | 78 | 2024-01-29 | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-12 | 15 | 11 | 2024-01-29 | 2024-02-16 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-15 | 29 | 21 | 2024-03-15 | 2024-03-15 | 1 | 1 | 19 | 15 | 155 | 111 | 174 | 126 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.35 | 2.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -74 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 568.86 | -10.38 | Unknown | Unknown | Unknown | 579.24 | 7782 | 1486.33 | 568.86 | 917.47 | Yes | N/A | N/A | 2024-03-07 | 2024-07-25 | 141 | 101 | 2024-07-25 | 2024-11-13 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-20 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-17 | 1 | 1 | 179 | 129 | 113 | 81 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -724 | -517 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 1039.72 | 258.94 | Unknown | 21.86 | Unknown | 758.92 | Unknown | 1845.21 | 1039.72 | 805.49 | Yes | N/A | N/A | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-06 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | 2025-02-06 | 1 | 1 | 4 | 4 | 6 | 4 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21.45 | 21.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-29 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-06-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1726.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-03-04 | 42 | 30 | 2025-03-04 | 2025-03-13 | 10 | 8 | 2025-02-14 | 2025-03-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-06-30 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 2025-06-30 | 2025-06-30 | 1 | 1 | 180 | 128 | 12 | 10 | 192 | 138 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | -482 | -345 | No | 2023-02-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | Yes | 41 | -10.44 | -7.56 | Unknown | Unknown | Unknown | -2.88 | Unknown | 363.72 | -10.44 | 374.16 | Yes | N/A | N/A | 2023-02-03 | 2023-03-16 | 42 | 30 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 42 | 30 | 1 | 1 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 24989 | 24989 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-09-08 | 613 | 438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 478.06 | -18.9 | Unknown | Unknown | 9.29 | 487.67 | 15924 | 730.65 | 478.06 | 252.59 | Yes | N/A | N/A | 2023-02-07 | 2023-03-21 | 43 | 31 | 2023-03-21 | 2023-09-28 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2024-04-02 | 188 | 134 | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-13 | Unknown | Unknown | 231 | 165 | 192 | 138 | 423 | 303 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 127514.05 | 127514.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-06 | 258 | 185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 213.28 | -11.6 | Unknown | Unknown | Unknown | 224.88 | 3981 | 531.11 | 213.28 | 317.83 | Yes | N/A | N/A | 2023-10-23 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-10-23 | 56 | 40 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2024-05-24 | 215 | 155 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-10 | 18 | 12 | 2024-06-10 | 2024-06-20 | 11 | 9 | 215 | 155 | 85 | 61 | 300 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | 93 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 769.95 | -11.95 | Unknown | Unknown | Unknown | 781.9 | 3981 | 716.04 | 769.95 | -53.91 | Yes | N/A | N/A | 2023-05-24 | 2023-06-06 | 14 | 10 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-03 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -500 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-04-03 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | 434.64 | -10.57 | Unknown | Unknown | 8.36 | 436.85 | 3981 | 680.98 | 434.64 | 246.34 | Yes | N/A | N/A | 2023-03-09 | 2023-04-03 | 26 | 18 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-08-23 | 143 | 103 | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-23 | 2023-08-31 | 9 | 7 | 2023-08-31 | 2023-08-31 | 1 | 1 | 169 | 121 | 10 | 8 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 17398.55 | 3826.29 | Unknown | Unknown | 571.87 | 13000.39 | 7962 | 1628.03 | 17398.55 | -15770.52 | Yes | N/A | N/A | 2024-05-22 | 2024-05-29 | 8 | 6 | 2024-05-29 | 2024-06-27 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-19 | 9 | 7 | 2024-06-27 | 2024-09-13 | 79 | 57 | Unknown | 2024-07-19 | Unknown | Unknown | 2024-07-26 | 2025-02-18 | 208 | 148 | 2025-02-18 | 2024-10-15 | Unknown | Unknown | 87 | 63 | 247 | 177 | 334 | 240 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -8 | -7 | No | 2023-10-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | 2024-07-11 | IOU Designed & Installed | N/A | Yes | 195 | 908.21 | Unknown | Unknown | Unknown | 5.03 | 903.18 | Unknown | 800.33 | 908.21 | -107.88 | Yes | N/A | N/A | 2023-10-06 | 2024-04-18 | 196 | 140 | 2024-04-18 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-07-11 | 270 | 194 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-07-31 | 21 | 15 | 2024-07-31 | 2024-07-31 | 1 | 1 | 466 | 334 | 22 | 16 | 488 | 350 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -112 | -81 | No | 2024-05-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-10 | 2024-08-27 | IOU Designed & Installed | N/A | Yes | 133 | 61.96 | Unknown | Unknown | Unknown | Unknown | 61.96 | 3981 | 1562.13 | 61.96 | 1500.17 | Yes | N/A | N/A | 2024-05-31 | 2024-10-11 | 134 | 96 | 2024-10-11 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-08-27 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-21 | 56 | 40 | 2024-10-21 | 2024-10-18 | Unknown | Unknown | 213 | 153 | 56 | 40 | 269 | 193 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -542 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-09-05 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | -14.21 | -11.53 | Unknown | Unknown | Unknown | -2.68 | Unknown | 153.83 | -14.21 | 168.04 | Yes | N/A | N/A | 2023-08-28 | 2023-09-05 | 9 | 7 | 2023-09-05 | 2023-09-05 | 1 | 1 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2024-02-13 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-02-20 | 8 | 6 | 2024-02-20 | 2024-02-20 | 1 | 1 | 171 | 123 | 10 | 8 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -663 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-01-17 | IOU Designed & Installed | N/A | No | N/A | 62.85 | -12.75 | Unknown | Unknown | Unknown | 75.6 | 3981 | 1103.21 | 62.85 | 1040.36 | Yes | N/A | N/A | 2024-01-09 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-01-09 | 14 | 10 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-02-13 | 28 | 20 | 2024-02-13 | 2024-02-13 | 1 | 1 | 9 | 7 | 43 | 31 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-10 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 508.49 | 241.68 | Unknown | 90.75 | Unknown | 176.06 | Unknown | 192.83 | 508.49 | -315.66 | Yes | N/A | N/A | 2024-03-20 | 2024-05-09 | 51 | 37 | 2024-05-09 | 2024-06-06 | 29 | 21 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-30 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-05 | 7 | 5 | 2024-08-05 | 2024-08-05 | 1 | 1 | 106 | 76 | 37 | 27 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -236 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.03 | Unknown | Unknown | Unknown | Unknown | 30.03 | 3981 | 1186.88 | 30.03 | 1156.85 | Yes | N/A | N/A | 2024-02-15 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-05-19 | 213 | 151 | 2024-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-19 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-08 | Unknown | Unknown | 0 | 0 | 213 | 151 | 213 | 151 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-12 | 511 | 366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | 2023-05-12 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 23792.02 | 1080.37 | Unknown | 94.02 | Unknown | 22617.63 | 962429 | 27331.5 | 23792.02 | 3539.48 | Yes | N/A | N/A | 2022-05-23 | 2023-04-03 | 316 | 226 | 2023-04-03 | 2024-05-01 | 395 | 283 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | 2024-05-01 | 2024-05-06 | 6 | 4 | 2024-05-06 | 2024-05-06 | 1 | 1 | 316 | 226 | 402 | 288 | 718 | 514 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -466 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-20 | 2023-08-20 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | -11.65 | -8.82 | Unknown | Unknown | Unknown | -2.83 | Unknown | 480.37 | -11.65 | 492.02 | Yes | N/A | N/A | 2023-08-20 | 2023-08-20 | 1 | 0 | 2023-08-20 | 2023-08-20 | 1 | 0 | 2023-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-20 | 2023-10-31 | 73 | 52 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-12-05 | 36 | 26 | 2023-12-05 | 2023-12-05 | 1 | 1 | 74 | 52 | 38 | 27 | 112 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | 192.1 | 192.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 1086.41 | 389.06 | Unknown | Unknown | Unknown | 697.35 | 3281 | 635.54 | 1086.41 | -450.87 | Yes | N/A | N/A | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2024-01-02 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-05 | 4 | 4 | 2024-01-05 | 2024-03-27 | 83 | 59 | 126 | 90 | 88 | 64 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -557 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 944.12 | 647.68 | Unknown | Unknown | Unknown | 296.44 | Unknown | 425.49 | 944.12 | -518.63 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-08-12 | 18 | 13 | 2023-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-10-11 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-16 | 6 | 4 | 2023-10-16 | 2023-10-16 | 1 | 1 | 78 | 56 | 25 | 18 | 103 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 1608.96 | 493.36 | Unknown | Unknown | Unknown | 1115.6 | 3981 | 909.97 | 1608.96 | -698.99 | Yes | N/A | N/A | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-07-11 | 224 | 160 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-12 | 2 | 2 | 2024-07-12 | 2024-07-12 | 1 | 1 | 225 | 161 | 4 | 4 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -501 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1639.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2025-01-07 | 16 | 12 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-05-14 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-02 | 20 | 14 | 2025-06-02 | 2025-06-02 | 1 | 1 | 128 | 92 | 37 | 27 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-13 | 33 | 24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 357.98 | Unknown | Unknown | Unknown | Unknown | 357.98 | 3981 | 1044.29 | 357.98 | 686.31 | Yes | N/A | N/A | 2023-12-11 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2024-12-16 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | 2023-08-31 | IOU Designed & Installed | N/A | No | N/A | 1571.4 | -32.61 | Unknown | Unknown | Unknown | 1604.01 | 3885 | 1066.7 | 1571.4 | -504.7 | Yes | N/A | N/A | 2023-04-04 | 2023-04-11 | 8 | 6 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-05-10 | 30 | 22 | 2023-04-11 | 2023-08-31 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-10-05 | 36 | 26 | 2023-10-05 | 2023-10-05 | 1 | 1 | 151 | 109 | 67 | 49 | 218 | 158 | Steps 2,3,5,6,7 | 29 | 21 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-18 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 1112.09 | Unknown | Unknown | Unknown | -1241.93 | 2354.02 | Unknown | 1292.5 | 1112.09 | 180.41 | Yes | N/A | N/A | 2024-08-01 | 2024-10-11 | 72 | 52 | 2024-10-11 | 2024-10-11 | 1 | 1 | 2024-10-11 | 2024-10-16 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-12-04 | 48 | 34 | Unknown | 2024-10-28 | Unknown | Unknown | 2024-12-04 | 2025-02-12 | 71 | 51 | 2025-02-12 | 2025-02-12 | 1 | 1 | 126 | 90 | 73 | 53 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -596 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-07-10 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 2382.5 | 269.18 | Unknown | 63.72 | 0.26 | 2049.34 | 3981 | 1096.01 | 2382.5 | -1286.49 | Yes | N/A | N/A | 2024-06-06 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-07-10 | 71 | 51 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-28 | 50 | 36 | Unknown | 2024-08-22 | Unknown | Unknown | 2024-08-28 | 2024-09-28 | 32 | 23 | 2024-09-28 | 2024-08-30 | Unknown | Unknown | 50 | 36 | 103 | 74 | 153 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | SANTEE | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-27 | -27 | -20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-09-10 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 2790.06 | 1148.84 | Unknown | 235.29 | Unknown | 1405.93 | Unknown | 1029.85 | 2790.06 | -1760.21 | Yes | N/A | N/A | 2024-06-18 | 2024-10-02 | 107 | 77 | 2024-10-02 | 2024-10-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-07 | 28 | 20 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-10-31 | 8 | 6 | 2024-10-31 | 2024-10-31 | 1 | 1 | 107 | 77 | 38 | 28 | 145 | 105 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | La Mesa | La Mesa | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | 2024-12-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 88766.68 | 21282.38 | Unknown | 78.77 | -35543.39 | 102948.92 | 0 | 38302.01 | 88766.68 | -50464.67 | Yes | N/A | N/A | 2023-08-09 | 2023-11-14 | 98 | 70 | 2023-11-14 | 2024-07-11 | 241 | 173 | 2023-11-28 | 2024-08-27 | 197 | 139 | 2023-12-20 | 2024-10-23 | 139 | 101 | 2024-08-27 | Unknown | Unknown | Unknown | 2024-08-27 | 2024-11-01 | 67 | 49 | 2024-12-12 | 2025-01-23 | 43 | 31 | 2025-01-23 | 2025-01-23 | 1 | 1 | 295 | 209 | 491 | 355 | 786 | 564 | Steps 2,3,5,6,7 | 534 | 382 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | -529 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 1325.98 | 448.44 | Unknown | 41.33 | Unknown | 836.21 | Unknown | 934.24 | 1325.98 | -391.74 | Yes | N/A | N/A | 2024-01-24 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-01-24 | 140 | 100 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-06 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-11 | 35 | 25 | 2024-03-11 | 2024-03-11 | 1 | 1 | 7 | 5 | 176 | 126 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-06 | 1577 | 1126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 43997.94 | 12222.24 | Unknown | 44.2 | -7012 | 38743.5 | Unknown | 36099.39 | 43997.94 | -7898.55 | Yes | N/A | N/A | 2025-02-06 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-10 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-25 | 16 | 12 | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-27 | 2025-03-03 | 5 | 3 | 2025-03-03 | 2025-03-02 | Unknown | Unknown | 16 | 12 | 25 | 17 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 116 | 116 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 1498.56 | -3.63 | Unknown | Unknown | 65.96 | 1436.23 | 3981 | 591.83 | 1498.56 | -906.73 | Yes | N/A | N/A | 2023-06-27 | 2023-04-12 | Unknown | Unknown | 2023-04-12 | 2023-09-14 | 156 | 112 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2024-07-09 | 300 | 214 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | 2024-06-28 | Unknown | Unknown | 300 | 214 | 157 | 113 | 457 | 327 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-04 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | -5.91 | -4.79 | Unknown | Unknown | Unknown | -1.12 | Unknown | 158.79 | -5.91 | 164.7 | Yes | N/A | N/A | 2023-12-11 | 2024-01-05 | 26 | 20 | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-25 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-03-25 | 61 | 43 | 2024-03-25 | 2024-03-25 | 1 | 1 | 47 | 35 | 63 | 45 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -571 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-17 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 1360.33 | -26.63 | Unknown | Unknown | Unknown | 1386.96 | 3981 | 1708.48 | 1360.33 | 348.15 | Yes | N/A | N/A | 2024-10-01 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-10-17 | 25 | 19 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-15 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-01-22 | 69 | 49 | 2025-01-22 | 2025-01-22 | 1 | 1 | 30 | 22 | 95 | 69 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -159 | -115 | No | 2023-08-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | 2024-10-25 | IOU Designed & Installed | N/A | Yes | 396 | 2645.1 | 400.32 | Unknown | 181.72 | Unknown | 2063.06 | 3981 | 1146.68 | 2645.1 | -1498.42 | Yes | N/A | N/A | 2023-08-07 | 2024-09-06 | 397 | 285 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2024-10-25 | 438 | 314 | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-25 | 2024-11-04 | 11 | 7 | 2024-11-04 | 2024-11-04 | 1 | 1 | 835 | 599 | 13 | 9 | 848 | 608 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 7.69 | Unknown | Unknown | Unknown | Unknown | 7.69 | 3981 | 197.01 | 7.69 | 189.32 | Yes | N/A | N/A | 2024-10-17 | 2024-11-06 | 21 | 15 | 2024-11-06 | 2024-11-15 | 10 | 8 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-16 | 11 | 7 | 2024-12-16 | 2024-12-16 | 1 | 1 | 43 | 31 | 22 | 16 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 93 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-02-12 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | -6.05 | -25.35 | Unknown | Unknown | Unknown | 19.3 | 3981 | 1829.4 | -6.05 | 1835.45 | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | 2025-02-12 | 34 | 24 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-25 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-07 | 14 | 10 | 2025-04-07 | 2025-04-04 | Unknown | Unknown | 43 | 31 | 48 | 34 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10099.3 | Unknown | Unknown | Unknown | Unknown | 10099.3 | 149015 | 8755.16 | 10099.3 | -1344.14 | Yes | N/A | N/A | 2024-02-01 | 2024-01-15 | Unknown | Unknown | 2024-01-15 | 2024-02-12 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-09-11 | 213 | 153 | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-14 | Unknown | Unknown | 213 | 153 | 29 | 21 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 548 | 393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 1007.52 | Unknown | Unknown | Unknown | Unknown | 1007.52 | 98711 | Not available | 1007.52 | Unknown | Yes | N/A | N/A | 2024-01-04 | 2024-01-04 | 1 | 1 | 2024-01-04 | 2024-06-04 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2025-07-03 | 395 | 283 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 396 | 284 | 154 | 110 | 550 | 394 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 893.38 | -11.56 | Unknown | Unknown | 6.54 | 898.4 | 3981 | 782.17 | 893.38 | -111.21 | Yes | N/A | N/A | 2024-02-16 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-03-15 | 59 | 43 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-06-19 | 97 | 69 | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-06-26 | 8 | 6 | 2024-06-26 | 2024-06-26 | 1 | 1 | 97 | 69 | 68 | 50 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -444 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 410.88 | -9.27 | Unknown | Unknown | Unknown | 420.15 | 3981 | 889.64 | 410.88 | 478.76 | Yes | N/A | N/A | 2024-02-28 | 2023-07-12 | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-06-20 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-25 | 6 | 4 | 2024-06-25 | 2024-06-24 | Unknown | Unknown | 114 | 82 | 6 | 4 | 120 | 86 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 697 | 697 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-12-05 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 9077.4 | -31.48 | Unknown | Unknown | 1.97 | 9106.91 | Unknown | 16813.16 | 9077.4 | 7735.76 | Yes | N/A | N/A | 2024-09-27 | 2024-11-13 | 48 | 34 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-04-03 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-05-06 | 22 | 16 | 2025-05-06 | 2025-05-06 | 1 | 1 | 48 | 34 | 47 | 35 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | CALTRANS-Orange County, LAGUNA BEACH | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -275 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.3 | -10.92 | Unknown | Unknown | Unknown | 23.22 | 3981 | 2328.77 | 12.3 | 2316.47 | Yes | N/A | N/A | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | 2024-03-29 | 2 | 2 | 2024-03-29 | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-08 | 11 | 7 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-04-18 | 1 | 1 | 1 | 1 | 14 | 10 | 15 | 11 | Steps 2,3,5,6,7 | 10 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 14838.66 | Unknown | Unknown | Unknown | 29.65 | 14809.01 | 3981 | 1546.39 | 14838.66 | -13292.27 | Yes | N/A | N/A | 2023-06-27 | 2023-06-28 | 2 | 2 | 2023-06-28 | 2023-06-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-10-12 | 106 | 76 | Unknown | 2023-12-07 | Unknown | Unknown | 2023-12-11 | 2023-12-20 | 10 | 8 | 2023-12-20 | 2023-12-19 | Unknown | Unknown | 108 | 78 | 12 | 10 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-19 | 236 | 169 | No | 2022-07-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | Unknown | IOU Designed & Installed | N/A | Yes | 426 | 525.12 | -11.33 | Unknown | Unknown | 113.91 | 422.54 | 3981 | 153.83 | 525.12 | -371.29 | Yes | N/A | N/A | 2022-06-08 | 2023-09-14 | 464 | 332 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-07-26 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 464 | 332 | 1 | 1 | 465 | 333 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-06-01 | IOU Designed & Installed | N/A | No | N/A | 1109.96 | 354.06 | Unknown | 134.04 | Unknown | 621.86 | 3981 | 1940.46 | 1109.96 | 830.5 | Yes | N/A | N/A | 2023-03-28 | 2023-04-24 | 28 | 20 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-06-01 | 39 | 29 | Unknown | 2023-05-23 | Unknown | Unknown | 2023-06-01 | 2023-06-07 | 7 | 5 | 2023-06-07 | 2023-06-07 | 1 | 1 | 67 | 49 | 8 | 6 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | -73 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1342.81 | -24.32 | Unknown | Unknown | Unknown | 1367.13 | Unknown | 344.91 | 1342.81 | -997.9 | Yes | N/A | N/A | 2024-03-20 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-08-22 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-31 | 36 | 26 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 0 | 0 | 202 | 146 | 202 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -349 | -250 | No | 2024-06-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-06-13 | IOU Designed & Installed | N/A | Yes | 6 | 14.19 | -12.62 | Unknown | Unknown | Unknown | 26.81 | 3941 | 1423.07 | 14.19 | 1408.88 | Yes | N/A | N/A | 2024-06-06 | 2024-06-12 | 7 | 5 | 2024-06-12 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-21 | 9 | 7 | 2024-06-21 | 2024-06-21 | 1 | 1 | 15 | 11 | 10 | 8 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -115 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 34.36 | Unknown | Unknown | Unknown | Unknown | 34.36 | 3981 | 510.17 | 34.36 | 475.81 | Yes | N/A | N/A | 2023-09-07 | 2023-06-16 | Unknown | Unknown | 2023-06-16 | 2023-09-29 | 106 | 76 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2024-08-05 | 312 | 222 | Unknown | 2024-07-18 | Unknown | Unknown | 2024-08-05 | 2024-09-25 | 52 | 38 | 2024-09-25 | 2024-09-24 | Unknown | Unknown | 312 | 222 | 158 | 114 | 470 | 336 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | 8196500 | 8196500 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-01 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | 19692.23 | 2478.04 | Unknown | Unknown | Unknown | 17214.19 | Unknown | 18992.76 | 19692.23 | -699.47 | Yes | N/A | N/A | 2024-10-14 | 2024-10-14 | 1 | 1 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-03-20 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-24 | 31 | 23 | 2025-04-24 | 2025-04-24 | 1 | 1 | 1 | 1 | 76 | 56 | 77 | 57 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-06 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 6.76 | -5.98 | Unknown | Unknown | Unknown | 12.74 | Unknown | 1505.47 | 6.76 | 1498.71 | Yes | N/A | N/A | 2024-05-07 | 2024-05-16 | 10 | 8 | 2024-05-16 | 2024-06-06 | 22 | 16 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-17 | 5 | 3 | 2024-06-17 | 2024-06-17 | 1 | 1 | 18 | 14 | 28 | 20 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 384 | 275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-16 | 2024-10-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 56797.9 | 21201.53 | Unknown | 1332.39 | 1640.61 | 32623.37 | 0 | 35071.06 | 56797.9 | -21726.84 | Yes | N/A | N/A | 2023-08-15 | 2023-08-17 | 3 | 3 | 2023-08-17 | 2024-01-12 | 149 | 107 | 2023-08-24 | 2023-09-01 | 9 | 7 | 2023-12-15 | 2023-12-19 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-02 | 2 | 2 | 2024-10-02 | 2024-10-02 | 1 | 1 | 12 | 10 | 157 | 113 | 169 | 123 | Steps 2,3,5,6,7 | 141 | 101 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | 380 | 271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-23 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 5628.24 | Unknown | Unknown | Unknown | Unknown | 5628.24 | 3981 | 609.53 | 5628.24 | -5018.71 | Yes | N/A | N/A | 2025-01-22 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-02-04 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-17 | 42 | 30 | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-03-18 | 36 | 26 | 2025-03-18 | 2025-03-17 | Unknown | Unknown | 42 | 30 | 51 | 37 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-03 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-06-04 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 4434.11 | -93.32 | Unknown | Unknown | 9.98 | 4517.45 | 3981 | 1399.86 | 4434.11 | -3034.25 | Yes | N/A | N/A | 2024-02-16 | 2024-05-28 | 103 | 73 | 2024-05-28 | 2024-06-04 | 8 | 6 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-09-28 | 110 | 79 | 2024-09-28 | 2024-08-09 | Unknown | Unknown | 111 | 79 | 118 | 85 | 229 | 164 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-02 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 1265.82 | -24.15 | Unknown | Unknown | Unknown | 1289.97 | 3981 | 1413.82 | 1265.82 | 148 | Yes | N/A | N/A | 2024-07-22 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-07-24 | 27 | 19 | 2024-07-24 | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-30 | 9 | 7 | 2024-08-23 | 2024-10-02 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-17 | 16 | 12 | 2024-10-17 | 2024-10-17 | 1 | 1 | 41 | 29 | 53 | 39 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | ENCINITAS | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 511 | 366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2024-03-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 5879.3 | 595.35 | Unknown | 70.49 | 22.4 | 5191.06 | 63423 | 3899.38 | 5879.3 | -1979.92 | Yes | N/A | N/A | 2023-10-02 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-12-05 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-02-27 | 1 | 1 | 2023-12-05 | 2024-03-13 | 100 | 72 | Unknown | 2024-03-18 | Unknown | Unknown | 2024-03-22 | 2024-03-28 | 7 | 5 | 2024-03-28 | 2024-03-26 | Unknown | Unknown | 100 | 72 | 168 | 120 | 268 | 192 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | -446 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1348.99 | -11.69 | Unknown | Unknown | Unknown | 1360.68 | 3885 | 786.58 | 1348.99 | -562.41 | Yes | N/A | N/A | 2023-02-08 | 2023-02-23 | 16 | 12 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -641 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 2.15 | Unknown | Unknown | Unknown | Unknown | 2.15 | 3981 | 1389.2 | 2.15 | 1387.05 | Yes | N/A | N/A | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | 2025-03-06 | 252 | 180 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-17 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-07-30 | 14 | 10 | 2024-07-30 | 2024-07-30 | 1 | 1 | 21 | 15 | 267 | 191 | 288 | 206 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | -542 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | 85.28 | -14.56 | Unknown | Unknown | Unknown | 99.84 | Unknown | 1185.52 | 85.28 | 1100.24 | Yes | N/A | N/A | 2024-01-31 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-01-31 | 97 | 69 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-22 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-04-03 | 42 | 30 | 2024-04-03 | 2024-04-02 | Unknown | Unknown | 23 | 17 | 139 | 99 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -662 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 702.91 | -13.77 | Unknown | Unknown | Unknown | 716.68 | Unknown | 1666.57 | 702.91 | 963.66 | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-17 | 18 | 14 | 2024-09-27 | 2024-10-21 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-05 | 16 | 12 | 2024-11-05 | 2024-11-05 | 1 | 1 | 26 | 18 | 36 | 28 | 62 | 46 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 346 | 346 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-27 | 2022-12-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.18 | -17.78 | Unknown | Unknown | Unknown | 8.6 | 3981 | 753.87 | -9.18 | 763.05 | Yes | N/A | N/A | 2022-12-27 | 2023-07-17 | 203 | 145 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 203 | 145 | 1 | 1 | 204 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-29 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 5828.51 | 1492.4 | Unknown | Unknown | 101.5 | 4234.61 | 3981 | 818.23 | 5828.51 | -5010.28 | Yes | N/A | N/A | 2024-04-17 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-04-29 | 40 | 28 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-12-02 | 218 | 156 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-13 | 12 | 10 | 2024-12-13 | 2024-12-13 | 1 | 1 | 218 | 156 | 53 | 39 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 546 | 546 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -465 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 4218.84 | 541.28 | Unknown | Unknown | 29.71 | 3647.85 | 3981 | 1122.46 | 4218.84 | -3096.38 | Yes | N/A | N/A | 2024-07-08 | 2024-09-06 | 61 | 45 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-17 | 42 | 30 | Unknown | 2024-11-20 | Unknown | Unknown | 2024-10-17 | 2024-11-21 | 36 | 26 | 2024-11-21 | 2024-11-21 | 1 | 1 | 103 | 75 | 38 | 28 | 141 | 103 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 2720.5 | 332.61 | Unknown | Unknown | Unknown | 2387.89 | 3981 | 1110.16 | 2720.5 | -1610.34 | Yes | N/A | N/A | 2023-10-05 | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-10-30 | 103 | 73 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-12-06 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-01-08 | 34 | 24 | 2024-01-08 | 2024-01-08 | 1 | 1 | 38 | 28 | 138 | 98 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -536 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-12-02 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 7.57 | -9.57 | Unknown | Unknown | Unknown | 17.14 | Unknown | 1017.13 | 7.57 | 1009.56 | Yes | N/A | N/A | 2023-10-10 | 2023-12-02 | 54 | 39 | 2023-12-02 | 2023-12-02 | 1 | 0 | 2023-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-02 | 2023-12-21 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-16 | 27 | 19 | 2024-01-16 | 2024-01-16 | 1 | 1 | 74 | 53 | 29 | 20 | 103 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -261 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 32.87 | Unknown | Unknown | Unknown | Unknown | 32.87 | 3981 | 1352.75 | 32.87 | 1319.88 | Yes | N/A | N/A | 2024-02-22 | 2024-03-12 | 20 | 14 | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | Unknown | Unknown | Unknown | 2024-03-12 | 2025-01-03 | 116 | 84 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 20 | 14 | 118 | 86 | 138 | 100 | Steps 2,3,5,6,7 | 297 | 213 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 8381.4 | 8381.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-08-14 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-02 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | -370.01 | Unknown | Unknown | Unknown | -414 | 43.99 | 3981 | 1408.49 | -370.01 | 1778.5 | Yes | N/A | N/A | 2024-09-27 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-10-02 | 37 | 27 | 2024-10-02 | 2024-10-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-12-03 | 44 | 32 | Unknown | 2024-11-18 | Unknown | Unknown | 2024-12-03 | 2024-12-27 | 25 | 19 | 2024-12-27 | 2024-12-27 | 1 | 1 | 67 | 49 | 63 | 47 | 130 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | -32 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7293.55 | 4095.34 | Unknown | 1323.93 | Unknown | 1874.28 | Unknown | 6245.55 | 7293.55 | -1048 | Yes | N/A | N/A | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-24 | 72 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | 2023-06-27 | IOU Designed & Installed | N/A | No | N/A | -3.12 | -9.28 | Unknown | Unknown | Unknown | 6.16 | 3981 | 1400.09 | -3.12 | 1403.21 | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-06-27 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-07-05 | 9 | 7 | 2023-07-05 | 2023-07-05 | 1 | 1 | 48 | 34 | 10 | 8 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Rancho Santa Fe | COUNTY OF SAN DIEGO-NORTH of 56 | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | 272 | 195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-04-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1953.05 | 300.29 | Unknown | Unknown | -8994 | 10646.76 | 2926.86 | 11920.73 | 1953.05 | 9967.68 | Yes | N/A | N/A | 2023-04-13 | 2023-06-16 | 65 | 47 | 2023-06-16 | 2023-08-14 | 60 | 42 | 2023-04-17 | 2023-04-27 | 11 | 9 | 2023-08-09 | 2023-10-06 | 59 | 42 | 2023-08-14 | Unknown | Unknown | Unknown | 2023-08-29 | 2024-08-20 | 358 | 256 | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 76 | 56 | 478 | 341 | 554 | 397 | Steps 2,3,5,6,7 | 172 | 124 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 55.01 | Unknown | Unknown | Unknown | Unknown | 55.01 | 3941 | 1416.44 | 55.01 | 1361.43 | Yes | N/A | N/A | 2024-07-25 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-25 | 9 | 7 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-07-29 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-15 | 18 | 14 | 2024-08-15 | 2024-08-15 | 1 | 1 | 5 | 3 | 28 | 22 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-29 | 1055 | 754 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 37.67 | Unknown | Unknown | Unknown | Unknown | 37.67 | 3981 | 1066.04 | 37.67 | 1028.37 | Yes | N/A | N/A | 2023-12-21 | 2024-01-05 | 16 | 12 | 2024-01-05 | 2024-01-08 | 4 | 2 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | 16 | 12 | 5 | 3 | 21 | 15 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 90.05 | 90.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 1889.55 | -49.54 | Unknown | Unknown | 60.73 | 1878.36 | 3981 | 1877.73 | 1889.55 | -11.82 | Yes | N/A | N/A | 2024-09-20 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-10-11 | 67 | 49 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-12-27 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-04-04 | 99 | 71 | 2025-04-04 | 2025-04-03 | Unknown | Unknown | 78 | 56 | 166 | 120 | 244 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 35.7 | 35.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -329 | -236 | No | 2024-05-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-07-09 | IOU Designed & Installed | N/A | Yes | 117 | 179.74 | -3 | Unknown | Unknown | 0.8 | 181.94 | 3981 | 1465.02 | 179.74 | 1285.28 | Yes | N/A | N/A | 2024-05-16 | 2024-09-10 | 118 | 84 | 2024-09-10 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-07-09 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-11-18 | 133 | 95 | 2024-11-18 | 2025-02-27 | 102 | 74 | 173 | 123 | 235 | 169 | 408 | 292 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-10-28 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 36.24 | Unknown | Unknown | Unknown | Unknown | 36.24 | Unknown | 1609.49 | 36.24 | 1573.25 | Yes | N/A | N/A | 2024-09-18 | 2024-10-24 | 37 | 27 | 2024-10-24 | 2024-10-28 | 5 | 3 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2025-01-06 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-21 | 16 | 12 | 2025-01-21 | 2025-01-21 | 1 | 1 | 108 | 78 | 22 | 16 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -459 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-04-07 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | 53.93 | -14.8 | Unknown | Unknown | Unknown | 68.73 | 3981 | 1322.26 | 53.93 | 1268.33 | Yes | N/A | N/A | 2023-03-10 | 2023-05-02 | 54 | 38 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-09-14 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-05 | 22 | 16 | 2023-10-05 | 2023-10-05 | 1 | 1 | 190 | 136 | 23 | 17 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 445.05 | 445.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -368 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 999.06 | Unknown | Unknown | Unknown | 16.95 | 982.11 | 3981 | 1084.26 | 999.06 | 85.2 | Yes | N/A | N/A | 2023-12-27 | 2024-01-21 | 26 | 18 | 2024-01-21 | 2024-01-29 | 9 | 6 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-25 | Unknown | Unknown | 26 | 18 | 9 | 6 | 35 | 24 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | 31 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1241.21 | 305.36 | Unknown | 25.2 | -1774 | 202.23 | Unknown | 1773.84 | -1241.21 | 3015.05 | Yes | N/A | N/A | 2023-10-04 | 2023-10-18 | 15 | 11 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -254 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | -6.09 | -4.78 | Unknown | Unknown | Unknown | -1.31 | Unknown | 499.18 | -6.09 | 505.27 | Yes | N/A | N/A | 2023-12-06 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-12-06 | 43 | 31 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-11 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-02-01 | 53 | 39 | 2024-02-01 | 2024-02-01 | 1 | 1 | 6 | 4 | 97 | 71 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 16655 | 16655 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-26 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 922.66 | -14.5 | Unknown | Unknown | 11.69 | 925.47 | Unknown | 1156.78 | 922.66 | 234.12 | Yes | N/A | N/A | 2024-05-08 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-05-17 | 58 | 42 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-17 | 32 | 22 | Unknown | 2024-06-14 | Unknown | Unknown | 2024-06-17 | 2024-07-01 | 15 | 11 | 2024-07-01 | 2024-07-01 | 1 | 1 | 32 | 22 | 74 | 54 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -426 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-01 | 2022-03-01 | 2024-10-02 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 72229.27 | 23601.08 | Unknown | Unknown | 307.86 | 48320.33 | 40918 | 34410.98 | 72229.27 | -37818.29 | Yes | N/A | N/A | 2022-03-01 | 2023-05-25 | 451 | 323 | 2023-05-25 | 2024-02-01 | 253 | 181 | 2023-07-11 | 2024-01-29 | 121 | 87 | 2023-07-24 | 2024-09-30 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-08-29 | 199 | 143 | 2024-10-02 | 2024-10-31 | 30 | 22 | 2024-10-31 | 2024-10-31 | 1 | 1 | 572 | 410 | 496 | 356 | 1068 | 766 | Steps 2,3,5,6,7 | 394 | 282 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | N/A | 324 | 324 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 117 | 84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 63.05 | -23.42 | Unknown | Unknown | 0.27 | 86.2 | 37378 | 710.2 | 63.05 | 647.15 | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | 2023-02-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | 2023-11-22 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2023-12-27 | Unknown | Unknown | 296 | 212 | 2 | 2 | 298 | 214 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | 175 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2470.52 | -17.15 | Unknown | Unknown | -2745 | 291.63 | 0 | 2146.95 | -2470.52 | 4617.47 | Yes | N/A | N/A | 2023-05-11 | 2023-04-07 | Unknown | Unknown | 2023-04-07 | 2023-06-15 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-12 | 7 | 5 | 2023-06-15 | 2024-08-27 | 440 | 314 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-29 | 27 | 19 | 440 | 314 | 104 | 74 | 544 | 388 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 70880 | 70880 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | -214 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.59 | -19.26 | Unknown | Unknown | Unknown | 22.85 | 0 | 236.4 | 3.59 | 232.81 | Yes | N/A | N/A | 2023-03-22 | 2023-03-15 | Unknown | Unknown | 2023-03-15 | 2023-04-20 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-03-01 | 1 | 1 | 0 | 0 | 38 | 28 | 38 | 28 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 372 | 267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2025-01-31 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 5334.88 | 102.24 | Unknown | Unknown | -7265.48 | 12498.12 | Unknown | 7266.73 | 5334.88 | 1931.85 | Yes | N/A | N/A | 2024-08-07 | 2025-01-31 | 178 | 128 | 2025-01-31 | 2025-03-04 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-03-18 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-08 | 23 | 17 | 2025-05-08 | 2025-05-08 | 1 | 1 | 178 | 128 | 88 | 64 | 266 | 192 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 148.35 | 148.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | -416 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-03 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 7848.92 | 972.93 | Unknown | 226.94 | 131.87 | 6517.18 | 3981 | 2028.34 | 7848.92 | -5820.58 | Yes | N/A | N/A | 2024-05-29 | 2024-05-30 | 2 | 2 | 2024-05-30 | 2024-06-03 | 5 | 3 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2025-01-28 | 240 | 172 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-25 | 29 | 21 | 2025-02-25 | 2025-02-25 | 1 | 1 | 242 | 174 | 35 | 25 | 277 | 199 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 289 | 206 | No | 2023-08-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | Unknown | IOU Designed & Installed | N/A | Yes | 194 | 42.58 | -11.07 | Unknown | Unknown | Unknown | 53.65 | 3981 | 1409.34 | 42.58 | 1366.76 | Yes | N/A | N/A | 2023-08-31 | 2024-03-12 | 195 | 139 | 2024-03-12 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-04-15 | Unknown | Unknown | 195 | 139 | 0 | 0 | 195 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -620 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 617.8 | -22.63 | Unknown | Unknown | 8.84 | 631.59 | 3981 | 548.83 | 617.8 | -68.97 | Yes | N/A | N/A | 2023-03-27 | 2023-04-04 | 9 | 7 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2023-05-11 | 38 | 28 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-05-17 | Unknown | Unknown | 9 | 7 | 38 | 28 | 47 | 35 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-18 | 705 | 504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-18 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | 148.54 | -9.45 | Unknown | Unknown | Unknown | 157.99 | Unknown | 430.47 | 148.54 | 281.93 | Yes | N/A | N/A | 2023-10-17 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-10-25 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2024-01-24 | 92 | 66 | 2024-01-24 | 2024-01-24 | 1 | 1 | 0 | 0 | 130 | 94 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | 571 | 408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2858.85 | 2781.1 | Unknown | Unknown | -9286 | 9363.75 | 3503769 | 91567.04 | 2858.85 | 88708.19 | Yes | N/A | N/A | 2023-05-10 | 2024-03-20 | 316 | 226 | 2024-03-20 | 2024-03-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-05-16 | 51 | 37 | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-02 | Unknown | Unknown | 367 | 263 | 8 | 6 | 375 | 269 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-22 | 1374 | 983 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-14 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 1292.41 | 559.58 | Unknown | Unknown | Unknown | 732.83 | Unknown | 1965.59 | 1292.41 | 673.18 | Yes | N/A | N/A | 2025-02-07 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-04-03 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-27 | 5 | 5 | 2025-06-27 | 2025-06-27 | 1 | 1 | 0 | 0 | 63 | 47 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 7.02 | Unknown | Unknown | Unknown | Unknown | 7.02 | 3981 | 197.01 | 7.02 | 189.99 | Yes | N/A | N/A | 2024-09-10 | 2024-10-03 | 24 | 18 | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-11 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-01 | 22 | 16 | 2024-11-01 | 2024-11-01 | 1 | 1 | 33 | 25 | 24 | 18 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 5.07 | Unknown | Unknown | Unknown | Unknown | 5.07 | 3981 | 192.51 | 5.07 | 187.44 | Yes | N/A | N/A | 2024-06-26 | 2024-06-28 | 3 | 3 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-01 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-08-01 | 32 | 24 | 2024-08-01 | 2024-08-01 | 1 | 1 | 7 | 5 | 34 | 26 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | -570 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2023-06-16 | IOU Designed & Installed | N/A | No | N/A | -48.76 | -35.88 | Unknown | Unknown | Unknown | -12.88 | 3981 | 154.79 | -48.76 | 203.55 | Yes | N/A | N/A | 2023-03-16 | 2023-04-06 | 22 | 16 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-06-16 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-29 | 14 | 10 | 2023-06-29 | 2023-06-29 | 1 | 1 | 94 | 68 | 15 | 11 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -631 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | Unknown | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 52.11 | Unknown | Unknown | Unknown | Unknown | 52.11 | Unknown | 1577.29 | 52.11 | 1525.18 | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-12-19 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-24 | 37 | 27 | 2025-01-24 | 2025-01-24 | 1 | 1 | 53 | 39 | 39 | 29 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 1929.13 | -48.85 | Unknown | Unknown | -454.19 | 2432.17 | 3981 | 2008.29 | 1929.13 | 79.16 | Yes | N/A | N/A | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | 2023-10-30 | 11 | 7 | 2023-10-30 | 2023-11-16 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-12-28 | 60 | 44 | Unknown | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-01-17 | 21 | 15 | 2024-01-17 | 2024-01-17 | 1 | 1 | 79 | 59 | 33 | 23 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 0.35 | -10.26 | Unknown | Unknown | Unknown | 10.61 | 3981 | 844.98 | 0.35 | 844.63 | Yes | N/A | N/A | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-17 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-11-01 | 16 | 12 | 2023-11-01 | 2023-11-01 | 1 | 1 | 59 | 43 | 18 | 14 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-08 | 403 | 288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-17 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1364.71 | -13.43 | Unknown | Unknown | -1923 | 571.72 | Unknown | 1922.45 | -1364.71 | 3287.16 | Yes | N/A | N/A | 2021-09-17 | 2023-02-13 | 515 | 367 | 2023-02-13 | 2023-04-14 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-19 | 14 | 10 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-16 | 1 | 1 | 515 | 367 | 76 | 56 | 591 | 423 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-26 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -15.31 | -4.62 | Unknown | Unknown | 1.96 | -12.65 | 3981 | 705.99 | -15.31 | 721.3 | Yes | N/A | N/A | 2023-04-06 | 2023-06-20 | 76 | 54 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-07-17 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-20 | 4 | 4 | 2023-07-20 | 2023-07-20 | 1 | 1 | 104 | 74 | 5 | 5 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 11524 | 11524 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-01 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 334.88 | -6.4 | Unknown | Unknown | Unknown | 341.28 | Unknown | 499.14 | 334.88 | 164.26 | Yes | N/A | N/A | 2024-12-11 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-12-13 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-22 | 1 | 1 | 0 | 0 | 96 | 70 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 366.28 | -3.31 | Unknown | Unknown | 2.14 | 367.45 | 3981 | 722.1 | 366.28 | 355.82 | Yes | N/A | N/A | 2023-01-30 | 2023-02-07 | 9 | 7 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-04-26 | Unknown | Unknown | 9 | 7 | 0 | 0 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -675 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 2081.08 | -50.33 | Unknown | Unknown | Unknown | 2131.41 | 3981 | 2035.16 | 2081.08 | -45.92 | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-27 | 37 | 27 | 2025-03-27 | 2025-03-27 | 1 | 1 | 3 | 3 | 39 | 29 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 107 | 107 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-21 | 888 | 635 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-09 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 39.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-09 | 2 | 2 | 2025-05-09 | 2025-05-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-30 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-30 | 21 | 15 | 2025-06-30 | 2025-06-27 | Unknown | Unknown | 19 | 15 | 27 | 19 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | 134 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1193.6 | -6.48 | Unknown | Unknown | -737.07 | 1937.15 | Unknown | 739.61 | 1193.6 | -453.99 | Yes | N/A | N/A | 2023-10-11 | 2024-01-25 | 107 | 77 | 2024-01-25 | 2024-06-20 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-10-23 | 7 | 5 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | 107 | 77 | 156 | 112 | 263 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2995 | 2995 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-01-01 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 964.3 | -19.38 | Unknown | Unknown | Unknown | 983.68 | Unknown | 1963.85 | 964.3 | 999.55 | Yes | N/A | N/A | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | 2025-05-16 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | 2025-05-29 | 1 | 1 | 117 | 85 | 11 | 9 | 128 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-19 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 26.88 | Unknown | Unknown | Unknown | Unknown | 26.88 | 3981 | 1316.43 | 26.88 | 1289.55 | Yes | N/A | N/A | 2024-07-05 | 2024-07-19 | 15 | 11 | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-09-12 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-09-24 | 13 | 9 | 2024-09-24 | 2024-09-20 | Unknown | Unknown | 71 | 51 | 14 | 10 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-26 | 321 | 230 | No | 2022-11-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2022-11-30 | 2023-03-29 | IOU Designed & Installed | N/A | Yes | 520 | 6.7 | Unknown | Unknown | Unknown | Unknown | 6.7 | Unknown | 708.72 | 6.7 | 702.02 | Yes | N/A | N/A | 2022-11-30 | 2024-05-03 | 521 | 373 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-30 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2024-08-12 | 503 | 359 | 2024-08-12 | 2024-08-12 | 1 | 1 | 521 | 373 | 504 | 360 | 1025 | 733 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-24 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 21.31 | Unknown | Unknown | Unknown | Unknown | 21.31 | Unknown | 1608.93 | 21.31 | 1587.62 | Yes | N/A | N/A | 2024-07-11 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-07-24 | 52 | 38 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-12 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-15 | 4 | 4 | 2024-08-15 | 2024-08-15 | 1 | 1 | 20 | 14 | 57 | 43 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-11-13 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 221.67 | Unknown | Unknown | Unknown | -1158 | 1379.67 | Unknown | 1158.4 | 221.67 | 936.73 | Yes | N/A | N/A | 2024-10-30 | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-11-22 | 50 | 36 | 2024-11-22 | 2025-01-29 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-04-01 | 57 | 41 | Unknown | 2025-03-25 | Unknown | Unknown | 2025-04-01 | 2025-04-14 | 14 | 10 | 2025-04-14 | 2025-04-11 | Unknown | Unknown | 126 | 90 | 64 | 46 | 190 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | -611 | -438 | No | 2025-03-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-24 | 2025-06-16 | IOU Designed & Installed | N/A | Yes | 41 | 1340.03 | Unknown | Unknown | Unknown | -1171.39 | 2511.42 | Unknown | 1042.16 | 1340.03 | -297.87 | Yes | N/A | N/A | 2025-03-14 | 2025-04-23 | 41 | 29 | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | 2025-04-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-06-16 | 67 | 47 | Unknown | 2025-06-06 | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 2 | 2 | 2025-06-17 | 2025-06-17 | 1 | 1 | 114 | 80 | 5 | 5 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -43 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2035.95 | Unknown | Unknown | Unknown | Unknown | 2035.95 | 3981 | 763.78 | 2035.95 | -1272.17 | Yes | N/A | N/A | 2023-12-14 | 2024-01-18 | 36 | 26 | 2024-01-18 | 2024-01-22 | 5 | 3 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 36 | 26 | 6 | 4 | 42 | 30 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-16 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 541.35 | -10.2 | Unknown | Unknown | Unknown | 551.55 | Unknown | 866.38 | 541.35 | 325.03 | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | 2024-05-17 | 3 | 3 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-08-02 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-21 | 20 | 14 | 2024-08-21 | 2024-08-21 | 1 | 1 | 79 | 57 | 24 | 18 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -371 | -266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-02 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 79.9 | Unknown | Unknown | Unknown | 29.91 | 49.99 | Unknown | 1479.8 | 79.9 | 1399.9 | Yes | N/A | N/A | 2024-07-01 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-07-02 | 27 | 19 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-02-21 | 228 | 164 | 2025-02-21 | 2025-02-21 | 1 | 1 | 8 | 6 | 256 | 184 | 264 | 190 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | 195 | 140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 1112.1 | Unknown | Unknown | Unknown | 28.11 | 1083.99 | 3981 | 1390.69 | 1112.1 | 278.59 | Yes | N/A | N/A | 2023-10-19 | 2024-05-14 | 209 | 149 | 2024-05-14 | 2024-05-30 | 17 | 13 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-11-04 | 159 | 113 | Unknown | 2024-10-29 | Unknown | Unknown | 2024-11-04 | 2024-11-14 | 11 | 9 | 2024-11-14 | 2025-02-27 | 106 | 76 | 368 | 262 | 134 | 98 | 502 | 360 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-03 | 93 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 2.26 | -1.98 | Unknown | Unknown | Unknown | 4.24 | Unknown | 309.71 | 2.26 | 307.45 | Yes | N/A | N/A | 2024-04-22 | 2024-04-22 | 1 | 1 | 2024-04-22 | 2024-06-03 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-24 | 33 | 25 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-11-04 | 95 | 67 | 2024-11-04 | 2024-11-04 | 1 | 1 | 1 | 1 | 172 | 124 | 173 | 125 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -351 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 4338.23 | 854.37 | Unknown | Unknown | 3.9 | 3479.96 | 3981 | 1951.49 | 4338.23 | -2386.74 | Yes | N/A | N/A | 2024-08-01 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-10-09 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2025-01-24 | 108 | 78 | 2025-01-24 | 2025-01-24 | 1 | 1 | 70 | 50 | 110 | 80 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-30 | 2023-09-04 | IOU Designed & Installed | N/A | No | N/A | 366.73 | 108.72 | Unknown | 58.96 | Unknown | 199.05 | Unknown | 196.27 | 366.73 | -170.46 | Yes | N/A | N/A | 2023-08-23 | 2023-08-23 | 1 | 1 | 2023-08-23 | 2023-08-30 | 8 | 6 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-04 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-09-04 | 2023-09-07 | 4 | 4 | 2023-09-07 | 2023-09-07 | 1 | 1 | 7 | 5 | 13 | 11 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-20 | 212 | 153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 70.75 | Unknown | Unknown | Unknown | Unknown | 70.75 | Unknown | 1004.74 | 70.75 | 933.99 | Yes | N/A | N/A | 2024-03-28 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-04-18 | 39 | 29 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 0 | 0 | 39 | 29 | 39 | 29 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-18 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 129.06 | -1.88 | Unknown | Unknown | Unknown | 130.94 | 3981 | 1469.78 | 129.06 | 1340.72 | Yes | N/A | N/A | 2024-07-17 | 2024-07-18 | 2 | 2 | 2024-07-18 | 2025-03-06 | 232 | 166 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-20 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-09 | 21 | 15 | 2024-09-09 | 2024-09-09 | 1 | 1 | 36 | 26 | 254 | 182 | 290 | 208 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-27 | 173 | 124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2058.88 | -55.97 | Unknown | Unknown | Unknown | 2114.85 | 7962 | 1060.76 | 2058.88 | -998.12 | Yes | N/A | N/A | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-04-08 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-14 | 22 | 16 | 2024-04-08 | 2024-04-17 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-04-17 | Unknown | Unknown | 11 | 9 | 70 | 50 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.78 | -3.46 | Unknown | Unknown | Unknown | -1.32 | 3981 | 363.72 | -4.78 | 368.5 | Yes | N/A | N/A | 2023-03-13 | 2023-03-13 | 1 | 1 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 102 | 73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 21837.49 | 4679.67 | Unknown | 4748.44 | -5927.05 | 18336.43 | Unknown | 6336.03 | 21837.49 | -15501.46 | Yes | N/A | N/A | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | 2024-03-26 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-04-24 | 58 | 42 | 2024-03-26 | 2958465 | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | 2024-04-30 | 2024-05-13 | 14 | 10 | 2024-05-13 | 2024-05-13 | 1 | 1 | 1 | 1 | 113 | 81 | 114 | 82 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-25 | -579 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-30 | 2024-03-18 | IOU Designed & Installed | N/A | No | N/A | 2108.83 | 267.31 | Unknown | 15.65 | Unknown | 1825.87 | Unknown | 1107.56 | 2108.83 | -1001.27 | Yes | N/A | N/A | 2024-01-22 | 2024-01-30 | 9 | 7 | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-13 | 15 | 11 | 2024-01-30 | 2024-03-18 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-03-25 | 8 | 6 | 2024-03-25 | 2024-03-25 | 1 | 1 | 58 | 42 | 25 | 19 | 83 | 61 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | -350 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 622 | -8.17 | Unknown | Unknown | 10.7 | 619.47 | 3981 | 1133.4 | 622 | 511.4 | Yes | N/A | N/A | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-02-07 | 87 | 63 | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-02-08 | 2 | 2 | 2024-02-08 | 2024-02-08 | 1 | 1 | 88 | 64 | 4 | 4 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-21 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-23 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 1041.98 | Unknown | Unknown | Unknown | Unknown | 1041.98 | 3981 | 1190.83 | 1041.98 | 148.85 | Yes | N/A | N/A | 2024-10-10 | 2024-11-28 | 50 | 36 | 2024-11-28 | 2024-12-10 | 13 | 9 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-03-03 | 84 | 60 | Unknown | 2025-02-25 | Unknown | Unknown | 2025-03-03 | 2025-03-11 | 9 | 7 | 2025-03-11 | 2025-03-11 | 1 | 1 | 134 | 96 | 23 | 17 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -277 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 503.3 | 1082.6 | Unknown | 352.16 | -1610 | 678.54 | Unknown | 1621.29 | 503.3 | 1117.99 | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2023-10-03 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 1230.94 | -24.15 | Unknown | Unknown | Unknown | 1255.09 | 3981 | 1485.54 | 1230.94 | 254.6 | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-21 | 21 | 15 | 2024-09-30 | 2024-10-28 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-20 | 24 | 18 | 2024-11-20 | 2024-11-20 | 1 | 1 | 30 | 22 | 47 | 35 | 77 | 57 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 CMR PA9 WO2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 578 | 415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-10 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 145.68 | Unknown | Unknown | Unknown | Unknown | 145.68 | 104085 | Not available | 145.68 | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | 2024-09-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-09-10 | 2024-10-15 | 36 | 26 | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-16 | 2024-10-18 | 3 | 3 | 2024-10-18 | 2024-10-18 | 1 | 1 | 37 | 27 | 7 | 7 | 44 | 34 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 387 | 387 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | -54 | -40 | No | 2022-10-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-28 | 2022-10-28 | 2024-03-08 | IOU Designed & Installed | N/A | Yes | 376 | 15915.48 | -7.92 | Unknown | Unknown | 1717.17 | 14206.23 | 3981 | 458.16 | 15915.48 | -15457.32 | Yes | N/A | N/A | 2022-10-28 | 2023-10-24 | 362 | 258 | 2023-10-24 | 2023-11-08 | 16 | 12 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2024-03-08 | 333 | 239 | Unknown | 2024-03-11 | Unknown | Unknown | 2024-03-08 | 2024-03-22 | 15 | 11 | 2024-03-22 | 2024-03-25 | 4 | 2 | 695 | 497 | 35 | 25 | 730 | 522 | Steps 2,3,5,6,7 | 3 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21820 | 21820 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-30 | -501 | -358 | No | 2024-01-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-20 | 2024-07-10 | IOU Designed & Installed | N/A | Yes | 173 | 600.69 | -14.35 | Unknown | Unknown | Unknown | 615.04 | 3981 | 1591.35 | 600.69 | 990.66 | Yes | N/A | N/A | 2024-01-31 | 2024-07-22 | 174 | 124 | 2024-07-22 | 2024-02-20 | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-07-10 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-19 | 41 | 29 | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 316 | 226 | 41 | 29 | 357 | 255 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 158.05 | 158.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 257.27 | Unknown | Unknown | Unknown | Unknown | 257.27 | Unknown | 449.58 | 257.27 | 192.31 | Yes | N/A | N/A | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | 2024-09-04 | 15 | 11 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-11-15 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-26 | 12 | 8 | 2024-11-26 | 2024-11-26 | 1 | 1 | 74 | 54 | 28 | 20 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2422.29 | -4.28 | Unknown | Unknown | 124.82 | 2301.75 | 57607 | 1156.42 | 2422.29 | -1265.87 | Yes | N/A | N/A | 2024-01-10 | 2024-03-27 | 78 | 56 | 2024-03-27 | 2024-03-29 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-12 | 1 | 1 | 78 | 56 | 4 | 4 | 82 | 60 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 32.89 | Unknown | Unknown | Unknown | Unknown | 32.89 | Unknown | 1387.08 | 32.89 | 1354.19 | Yes | N/A | N/A | 2024-05-28 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-28 | 48 | 34 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-07-10 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-24 | 15 | 11 | 2024-07-24 | 2024-07-24 | 1 | 1 | 44 | 32 | 64 | 46 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -284 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-02-12 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | -5389.22 | 3926.25 | Unknown | 1075.82 | -15057 | 4665.71 | Unknown | 15056.94 | -5389.22 | 20446.16 | Yes | N/A | N/A | 2024-01-09 | 2024-02-14 | 37 | 27 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-18 | 8 | 6 | 2024-03-18 | 2024-03-18 | 1 | 1 | 37 | 27 | 9 | 7 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-09 | 8 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | -2427.02 | 2398.76 | Unknown | 48.29 | -6008 | 1133.93 | Unknown | 6007.79 | -2427.02 | 8434.81 | Yes | N/A | N/A | 2024-09-17 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-17 | 4 | 4 | 2024-10-17 | 2024-10-17 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | 487 | 349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-17 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 21679.92 | Unknown | Unknown | Unknown | 204.34 | 21475.58 | 3662 | 458.91 | 21679.92 | -21221.01 | Yes | N/A | N/A | 2023-10-03 | 2023-10-17 | 15 | 11 | 2023-10-17 | 2024-04-09 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-10-26 | 10 | 8 | 2024-04-09 | 2025-02-03 | 301 | 215 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-02-14 | 2025-04-07 | 53 | 37 | 2025-04-07 | 2025-03-13 | Unknown | Unknown | 316 | 226 | 239 | 171 | 555 | 397 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1696.36 | 58.86 | Unknown | Unknown | 70.06 | 1567.44 | 240801 | 20572.12 | 1696.36 | 18875.76 | Yes | N/A | N/A | 2023-09-07 | 2023-09-13 | 7 | 5 | 2023-09-13 | 2024-02-06 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-01 | 21 | 15 | 2024-02-06 | 2025-02-21 | 382 | 274 | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-21 | 1 | 1 | 389 | 279 | 169 | 121 | 558 | 400 | Steps 2,3,5,6,7 | 450 | 322 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 66791 | 66791 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-03-07 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 6661.78 | Unknown | Unknown | Unknown | -2607 | 9268.78 | Unknown | 2606.5 | 6661.78 | -4055.28 | Yes | N/A | N/A | 2024-03-20 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-04-24 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-04-29 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-24 | 21 | 15 | 2024-10-24 | 2024-10-24 | 1 | 1 | 0 | 0 | 76 | 54 | 76 | 54 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -400 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | 2023-12-16 | IOU Designed & Installed | N/A | No | N/A | 1128.29 | -2.04 | Unknown | Unknown | 18.94 | 1111.39 | Unknown | 1938.21 | 1128.29 | 809.92 | Yes | N/A | N/A | 2023-04-26 | 2023-06-01 | 37 | 27 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-12-16 | 199 | 142 | Unknown | 2023-12-04 | Unknown | Unknown | 2023-12-16 | 2024-01-21 | 37 | 25 | 2024-01-21 | 2024-01-21 | 1 | 0 | 236 | 169 | 38 | 25 | 274 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | -662 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 581.65 | -11.7 | Unknown | Unknown | Unknown | 593.35 | 3981 | 1676.31 | 581.65 | 1094.66 | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-19 | 29 | 21 | 2025-02-19 | 2025-02-19 | 1 | 1 | 8 | 6 | 31 | 23 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 346.13 | Unknown | Unknown | Unknown | Unknown | 346.13 | 3981 | 1120.15 | 346.13 | 774.02 | Yes | N/A | N/A | 2024-06-27 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-07-19 | 60 | 44 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-21 | 1 | 1 | 0 | 0 | 61 | 45 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 19400 | 19400 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-31 | 480 | 343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3353.85 | 2819.07 | Unknown | 617.02 | -1401 | 1318.76 | Unknown | 1400.96 | 3353.85 | -1952.89 | Yes | N/A | N/A | 2024-05-28 | 2024-05-31 | 4 | 4 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-07-23 | 1 | 1 | 4 | 4 | 1 | 1 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | -292 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 23690.77 | 3656.86 | Unknown | 228.57 | 1114.94 | 18690.4 | 0 | 6901.86 | 23690.77 | -16788.91 | Yes | N/A | N/A | 2024-01-09 | 2024-01-29 | 21 | 15 | 2024-01-29 | 2024-02-02 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-04-15 | 50 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-03-14 | 156 | 112 | 2025-03-14 | 2025-03-14 | 1 | 1 | 21 | 15 | 212 | 152 | 233 | 167 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2025-01-15 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 7761.54 | Unknown | Unknown | Unknown | -9959 | 17720.54 | Unknown | 17983.62 | 7761.54 | 10222.08 | Yes | N/A | N/A | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-03-31 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-15 | 14 | 10 | 2025-04-15 | 2025-04-15 | 1 | 1 | 1 | 1 | 20 | 14 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 321.05 | 321.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 877.06 | -9.75 | Unknown | Unknown | Unknown | 886.81 | Unknown | 928.27 | 877.06 | 51.21 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-12-15 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-08 | 25 | 17 | 2024-01-08 | 2024-01-08 | 1 | 1 | 38 | 28 | 27 | 19 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-11 | 325 | 234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-22 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | Not available | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-22 | 7 | 5 | 2024-07-22 | 2024-12-11 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-04-22 | 133 | 95 | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-02 | 1 | 1 | 140 | 100 | 144 | 104 | 284 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | 68 | 49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10.02 | -8.88 | Unknown | Unknown | Unknown | 18.9 | 7862 | 1718.97 | 10.02 | 1708.95 | Yes | N/A | N/A | 2023-05-22 | 2024-01-02 | 226 | 162 | 2024-01-02 | 2024-02-02 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-06-12 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-07-01 | Unknown | Unknown | 358 | 256 | 32 | 24 | 390 | 280 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -838 | -600 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | -28.27 | -20.5 | Unknown | Unknown | Unknown | -7.77 | 3754 | 330.53 | -28.27 | 358.8 | Yes | N/A | N/A | 2023-06-19 | 2023-06-20 | 2 | 2 | 2023-06-20 | 2025-03-06 | 626 | 448 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-09-13 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-10-02 | 20 | 14 | 2023-10-02 | 2023-10-02 | 1 | 1 | 88 | 64 | 647 | 463 | 735 | 527 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 1100 | 1100 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2022-05-11 | 1143 | 818 | No | 2023-04-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-13 | 2022-09-23 | 2024-07-18 | IOU Designed & Installed | N/A | Yes | 597 | 291168 | -1163.52 | Unknown | Unknown | 11519.27 | 280812.25 | 0 | 75168.41 | 291168 | -215999.59 | Yes | N/A | N/A | 2021-04-13 | 2023-06-16 | 795 | 569 | 2023-06-16 | 2024-06-26 | 377 | 269 | 2023-08-31 | 2023-12-12 | 11 | 9 | 2023-10-24 | 2025-06-04 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2024-07-18 | 2025-06-27 | 345 | 247 | 2025-06-27 | 2025-06-27 | 1 | 1 | 806 | 578 | 734 | 526 | 1540 | 1104 | Steps 2,3,5,6,7 | 636 | 454 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-24 | 2022-10-24 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 7.68 | Unknown | Unknown | Unknown | Unknown | 7.68 | Unknown | 192.95 | 7.68 | 185.27 | Yes | N/A | N/A | 2022-10-24 | 2024-08-14 | 661 | 473 | 2024-08-14 | 2024-08-15 | 2 | 2 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-19 | 5 | 3 | 2024-08-19 | 2024-08-19 | 1 | 1 | 662 | 474 | 8 | 6 | 670 | 480 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 32.31 | Unknown | Unknown | Unknown | Unknown | 32.31 | 3981 | 2096.76 | 32.31 | 2064.45 | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-16 | 14 | 10 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2024-12-19 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-24 | 37 | 27 | 2025-01-24 | 2025-01-24 | 1 | 1 | 5 | 5 | 52 | 38 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1008.56 | Unknown | Unknown | Unknown | Unknown | 1008.56 | 3981 | 1084.39 | 1008.56 | 75.83 | Yes | N/A | N/A | 2024-08-29 | 2024-09-05 | 8 | 6 | 2024-09-05 | 2024-09-09 | 5 | 3 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 8 | 6 | 6 | 4 | 14 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-06-02 | IOU Designed & Installed | N/A | No | N/A | 944.5 | 372.45 | Unknown | Unknown | Unknown | 572.05 | 3981 | 966.57 | 944.5 | 22.07 | Yes | N/A | N/A | 2023-03-08 | 2023-04-07 | 31 | 23 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-06-02 | 57 | 41 | Unknown | 2023-05-24 | Unknown | Unknown | 2023-06-02 | 2023-06-05 | 4 | 2 | 2023-06-05 | 2023-06-05 | 1 | 1 | 88 | 64 | 5 | 3 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | 629 | 450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-07 | 2021-10-07 | 2024-07-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 26000.29 | 3038.64 | Unknown | Unknown | 395.74 | 22565.91 | 137500 | 44942.48 | 26000.29 | 18942.19 | Yes | N/A | N/A | 2021-10-07 | 2023-02-14 | 496 | 354 | 2023-02-14 | 2023-06-21 | 128 | 92 | 2023-03-22 | 2023-07-31 | 64 | 46 | 2023-06-22 | 2023-12-20 | 182 | 130 | 2023-06-21 | Unknown | Unknown | Unknown | 2023-07-12 | 2024-07-01 | 356 | 254 | 2024-07-01 | 2024-07-25 | 25 | 19 | 2024-07-25 | 2024-07-25 | 1 | 1 | 560 | 400 | 692 | 496 | 1252 | 896 | Steps 2,3,5,6,7 | 312 | 222 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 6720 | 6720 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-13 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 106.18 | -0.94 | Unknown | Unknown | Unknown | 107.12 | Unknown | 4013.36 | 106.18 | 3907.18 | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | 2024-04-17 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-07 | 36 | 26 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | 1 | 1 | 86 | 62 | 87 | 63 | Steps 2,3,5,6,7 | 20 | 14 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-30 | 831 | 595 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-22 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 14180.49 | 271.47 | Unknown | Unknown | -132.94 | 14041.96 | 3981 | 2662.92 | 14180.49 | -11517.57 | Yes | N/A | N/A | 2023-02-17 | 2023-02-22 | 6 | 4 | 2023-02-22 | 2024-04-01 | 405 | 289 | 2023-09-19 | 2023-09-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2025-01-06 | 281 | 201 | Unknown | 2024-12-26 | Unknown | Unknown | 2025-01-22 | 2025-02-24 | 34 | 24 | 2025-02-24 | 2025-02-07 | Unknown | Unknown | 288 | 206 | 439 | 313 | 727 | 519 | Steps 2,3,5,6,7 | 195 | 139 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1249.15 | 1249.15 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-06-27 | -354 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-02-07 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 822.66 | -16.86 | Unknown | Unknown | Unknown | 839.52 | 3981 | 876.89 | 822.66 | 54.23 | Yes | N/A | N/A | 2024-01-10 | 2023-02-05 | Unknown | Unknown | 2023-02-05 | 2024-02-06 | 367 | 262 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-06-28 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-09 | 12 | 8 | 2024-07-09 | 2024-07-08 | Unknown | Unknown | 143 | 103 | 379 | 270 | 522 | 373 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 182.05 | 182.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-21 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 1556.85 | 494.4 | Unknown | 86.76 | 59.01 | 916.68 | 3981 | 1070.11 | 1556.85 | -486.74 | Yes | N/A | N/A | 2023-09-06 | 2023-09-19 | 14 | 10 | 2023-09-19 | 2023-09-21 | 3 | 3 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-11-07 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-11-02 | 362 | 259 | 2024-11-02 | 2023-11-07 | Unknown | Unknown | 62 | 44 | 365 | 262 | 427 | 306 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62.4 | 62.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-07 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.75 | -5.95 | Unknown | Unknown | Unknown | 10.7 | Unknown | 719.4 | 4.75 | 714.65 | Yes | N/A | N/A | 2023-04-21 | 2023-04-21 | 1 | 1 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-01-29 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Fallbrook | COUNTY OF SAN DIEGO-NORTH of 56 | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-16 | 1012 | 723 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 460553.69 | 76793.57 | Unknown | 3762.98 | 10542.08 | 369455.06 | 252941 | Not available | 460553.69 | Unknown | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | 2024-03-01 | 365 | 261 | 2024-02-08 | 2024-03-19 | 28 | 18 | 2024-02-09 | 2024-06-03 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-09-23 | 173 | 123 | 2024-09-23 | 2024-09-23 | 1 | 1 | 29 | 19 | 648 | 462 | 677 | 481 | Steps 2,3,5,6,7 | 61 | 43 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -675 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 2156.45 | 582.92 | Unknown | Unknown | Unknown | 1573.53 | Unknown | 519.64 | 2156.45 | -1636.81 | Yes | N/A | N/A | 2023-10-30 | 2023-11-09 | 11 | 9 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-28 | 20 | 14 | Unknown | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2023-11-30 | 3 | 3 | 2023-11-30 | 2023-11-30 | 1 | 1 | 31 | 23 | 5 | 5 | 36 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 0.38 | -10.61 | Unknown | Unknown | Unknown | 10.99 | Unknown | 974.07 | 0.38 | 973.69 | Yes | N/A | N/A | 2023-10-04 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-10-04 | 43 | 31 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-10-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-10-25 | 22 | 16 | 2023-10-25 | 2023-10-25 | 1 | 1 | 1 | 1 | 66 | 48 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 100.45 | -1.5 | Unknown | Unknown | Unknown | 101.95 | 3981 | 1371.25 | 100.45 | 1270.8 | Yes | N/A | N/A | 2024-07-25 | 2024-07-09 | Unknown | Unknown | 2024-07-09 | 2024-07-26 | 18 | 14 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-09-13 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-20 | 8 | 6 | 2024-09-20 | 2024-09-25 | 6 | 4 | 50 | 36 | 32 | 24 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.02 | -14.82 | Unknown | Unknown | Unknown | 9.8 | 3981 | 922.3 | -5.02 | 927.32 | Yes | N/A | N/A | 2023-02-21 | 2023-04-17 | 56 | 40 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 56 | 40 | 1 | 1 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 271 | 194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-02-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 4965.89 | Unknown | Unknown | Unknown | -10176 | 15141.89 | Unknown | 10176.26 | 4965.89 | 5210.37 | Yes | N/A | N/A | 2024-01-04 | 2024-01-08 | 5 | 3 | 2024-01-08 | 2024-02-07 | 31 | 23 | 2024-01-09 | 2024-01-10 | 2 | 2 | 2024-01-30 | 2024-02-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-27 | 20 | 14 | 2024-02-27 | 2024-02-27 | 1 | 1 | 7 | 5 | 61 | 45 | 68 | 50 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | 1 | 2 | No | 2023-12-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2024-07-11 | IOU Designed & Installed | N/A | Yes | 181 | 1687.76 | 352.32 | Unknown | Unknown | Unknown | 1335.44 | 3981 | 1445.3 | 1687.76 | -242.46 | Yes | N/A | N/A | 2023-12-13 | 2024-06-11 | 182 | 130 | 2024-06-11 | 2024-06-26 | 16 | 12 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-07-11 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-18 | 8 | 6 | 2024-07-18 | 2024-07-18 | 1 | 1 | 394 | 282 | 25 | 19 | 419 | 301 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-28 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | 2023-12-08 | IOU Designed & Installed | N/A | No | N/A | 373.15 | 191.07 | Unknown | 65.08 | Unknown | 117 | 3961 | 158.14 | 373.15 | -215.01 | Yes | N/A | N/A | 2023-10-30 | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2023-11-03 | 89 | 65 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-12-08 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-11 | 4 | 2 | 2023-12-11 | 2023-12-11 | 1 | 1 | 36 | 26 | 94 | 68 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | -163 | -116 | No | 2023-10-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | 2024-01-31 | IOU Designed & Installed | N/A | Yes | 72 | 249.97 | -12.51 | Unknown | Unknown | 7.24 | 255.24 | Unknown | 813.73 | 249.97 | 563.76 | Yes | N/A | N/A | 2023-10-23 | 2023-12-23 | 62 | 45 | 2023-12-23 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-01-31 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-03-15 | 45 | 33 | 2024-03-15 | 2024-03-15 | 1 | 1 | 155 | 112 | 46 | 34 | 201 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-28 | -89 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.98 | -5.94 | Unknown | Unknown | Unknown | 3.96 | 3981 | 861.66 | -1.98 | 863.64 | Yes | N/A | N/A | 2023-02-07 | 2023-05-01 | 84 | 60 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-08-31 | 1 | 1 | 84 | 60 | 1 | 1 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-15 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 602.5 | -11.81 | Unknown | Unknown | Unknown | 614.31 | 3981 | 1258.24 | 602.5 | 655.74 | Yes | N/A | N/A | 2024-03-07 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-03-15 | 40 | 30 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-03 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-18 | 16 | 12 | 2024-04-18 | 2024-04-18 | 1 | 1 | 20 | 14 | 57 | 43 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | -647 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-08 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2901.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-04-08 | 20 | 14 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-30 | 53 | 39 | Unknown | 2025-04-30 | Unknown | Unknown | 2025-05-30 | 2025-06-04 | 6 | 4 | 2025-06-04 | 2025-06-04 | 1 | 1 | 53 | 39 | 27 | 19 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -290 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-04-14 | IOU Designed & Installed | N/A | No | N/A | 4813.89 | 414.43 | Unknown | 55.05 | -5200 | 9544.41 | Unknown | 4694.84 | 4813.89 | -119.05 | Yes | N/A | N/A | 2024-02-28 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-04-05 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-14 | 2024-04-22 | 9 | 6 | 2024-04-22 | 2024-04-22 | 1 | 1 | 0 | 0 | 60 | 43 | 60 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -569 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5.82 | -5.19 | Unknown | Unknown | Unknown | 11.01 | Unknown | 987.89 | 5.82 | 982.07 | Yes | N/A | N/A | 2024-01-30 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2024-01-31 | 108 | 78 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 109 | 79 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 150.8 | Unknown | Unknown | Unknown | 9.35 | 141.45 | Unknown | 1585.67 | 150.8 | 1434.87 | Yes | N/A | N/A | 2024-09-10 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-10-28 | 98 | 70 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-14 | 1 | 1 | 0 | 0 | 99 | 71 | 99 | 71 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-26 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | -161.41 | 244.9 | Unknown | Unknown | -885 | 478.69 | Unknown | 885.44 | -161.41 | 1046.85 | Yes | N/A | N/A | 2023-10-04 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-10-26 | 93 | 67 | 2023-10-26 | 2023-11-03 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-09 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-01-02 | 55 | 39 | 2024-01-02 | 2024-01-02 | 1 | 1 | 16 | 12 | 149 | 107 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-03 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 1930.07 | 1284.48 | Unknown | Unknown | Unknown | 645.59 | Unknown | 149.82 | 1930.07 | -1780.25 | Yes | N/A | N/A | 2023-08-08 | 2023-09-27 | 51 | 37 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-26 | 29 | 21 | 2023-10-26 | 2023-10-26 | 1 | 1 | 53 | 39 | 31 | 23 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -265 | -190 | No | 2023-05-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2024-05-16 | IOU Designed & Installed | N/A | Yes | 168 | 572.46 | -20.39 | Unknown | Unknown | 8.63 | 584.22 | 3961 | 1168.78 | 572.46 | 596.32 | Yes | N/A | N/A | 2023-05-15 | 2023-10-24 | 163 | 117 | 2023-10-24 | 2023-10-30 | 7 | 5 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2024-05-16 | 294 | 210 | Unknown | 2024-04-03 | Unknown | Unknown | 2024-05-16 | 2024-06-14 | 30 | 22 | 2024-06-14 | 2024-06-14 | 1 | 1 | 457 | 327 | 38 | 28 | 495 | 355 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 130.13 | -1.56 | Unknown | Unknown | Unknown | 131.69 | 3981 | 2956.09 | 130.13 | 2825.96 | Yes | N/A | N/A | 2023-07-06 | 2023-11-19 | 137 | 97 | 2023-11-19 | 2023-12-01 | 13 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-28 | 9 | 7 | 2023-12-01 | 2024-12-05 | 371 | 265 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-20 | 1 | 1 | 508 | 362 | 23 | 18 | 531 | 380 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-04 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 868.72 | -5.14 | Unknown | Unknown | 13.71 | 860.15 | 3981 | 886.05 | 868.72 | 17.33 | Yes | N/A | N/A | 2023-08-15 | 2023-11-28 | 106 | 76 | 2023-11-28 | 2023-11-29 | 2 | 2 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-05-23 | 177 | 127 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-05-23 | 2024-05-24 | 2 | 2 | 2024-05-24 | 2024-05-24 | 1 | 1 | 283 | 203 | 5 | 5 | 288 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -17 | -13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-31 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 13188.71 | 8740.72 | Unknown | Unknown | -6481.8 | 10929.79 | 7962 | 20706.34 | 13188.71 | 7517.63 | Yes | N/A | N/A | 2024-05-09 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-11-26 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-15 | 8 | 6 | 2024-11-26 | 2025-05-13 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-17 | 13 | 9 | 2025-06-17 | 2025-06-04 | Unknown | Unknown | 169 | 121 | 233 | 167 | 402 | 288 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Carlsbad | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 3 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-12-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 131672.58 | 59438.08 | Unknown | Unknown | -64335 | 136569.5 | Unknown | 76895.66 | 131672.58 | -54776.92 | Yes | N/A | N/A | 2023-01-24 | 2023-05-12 | 109 | 79 | 2023-05-12 | 2023-08-31 | 112 | 80 | 2023-06-26 | 2023-12-14 | 48 | 36 | 2023-08-29 | 2023-09-08 | 11 | 9 | 2023-09-11 | Unknown | Unknown | Unknown | 2023-09-11 | 2023-11-29 | 80 | 58 | 2023-12-01 | 2023-12-21 | 21 | 15 | 2023-12-21 | 2023-12-21 | 1 | 1 | 157 | 115 | 225 | 163 | 382 | 278 | Steps 2,3,5,6,7 | 173 | 125 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 52.79 | Unknown | Unknown | Unknown | Unknown | 52.79 | 3981 | 1372.72 | 52.79 | 1319.93 | Yes | N/A | N/A | 2024-08-15 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-15 | 4 | 4 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-27 | 13 | 9 | 2024-08-27 | 2024-08-27 | 1 | 1 | 1 | 1 | 18 | 14 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DESCANSO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 2676.83 | 525.12 | Unknown | 562.57 | Unknown | 1589.14 | 3981 | 1244.48 | 2676.83 | -1432.35 | Yes | N/A | N/A | 2025-01-29 | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-29 | 17 | 13 | 2025-01-29 | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-12 | 7 | 5 | 2025-01-29 | 2025-03-24 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-03-24 | 1 | 1 | 55 | 39 | 26 | 20 | 81 | 59 | Steps 2,3,5,6,7 | 42 | 30 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -608 | -435 | No | 2024-02-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | Yes | 32 | -7.23 | -5.88 | Unknown | Unknown | Unknown | -1.35 | 3981 | 1083.81 | -7.23 | 1091.04 | Yes | N/A | N/A | 2024-02-29 | 2024-03-29 | 30 | 22 | 2024-03-29 | 2024-04-01 | 4 | 2 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-05-24 | 1 | 1 | 30 | 22 | 5 | 3 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-04 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-20 | 2025-06-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1741.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-20 | 21 | 15 | 2025-02-20 | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-27 | 7 | 5 | 2025-02-20 | 2025-06-24 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-06-30 | 7 | 5 | 2025-06-30 | 2025-06-30 | 1 | 1 | 125 | 89 | 36 | 26 | 161 | 115 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 28.47 | Unknown | Unknown | Unknown | Unknown | 28.47 | 3981 | 1474.65 | 28.47 | 1446.18 | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-13 | 23 | 17 | 2024-11-13 | 2024-11-13 | 1 | 1 | 8 | 6 | 25 | 19 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -96 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1999.85 | 1146.53 | Unknown | Unknown | -3724 | 577.62 | Unknown | 3723.53 | -1999.85 | 5723.38 | Yes | N/A | N/A | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | 4 | 3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-06-29 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 2847.46 | 1682.49 | Unknown | 93.32 | -25378.09 | 26449.74 | 0 | 24008.93 | 2847.46 | 21161.47 | Yes | N/A | N/A | 2023-05-02 | 2023-11-07 | 190 | 136 | 2023-11-07 | 2024-07-12 | 249 | 179 | 2024-01-30 | 2024-02-21 | 23 | 17 | 2024-03-24 | 2024-06-25 | 23 | 16 | 2024-08-12 | Unknown | Unknown | Unknown | 2024-08-12 | 2024-11-07 | 88 | 64 | 2024-08-27 | 2025-01-07 | 134 | 96 | 2025-01-07 | 2025-01-07 | 1 | 1 | 213 | 153 | 495 | 356 | 708 | 509 | Steps 2,3,5,6,7 | 236 | 170 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | 2023-04-13 | IOU Designed & Installed | N/A | No | N/A | 362.09 | 118.88 | Unknown | 44.05 | Unknown | 199.16 | 3885 | 724.85 | 362.09 | 362.76 | Yes | N/A | N/A | 2023-02-27 | 2023-02-27 | 1 | 1 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-04-13 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-04-14 | 2 | 2 | 2023-04-14 | 2023-04-14 | 1 | 1 | 47 | 35 | 3 | 3 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 835.99 | -16.8 | Unknown | Unknown | Unknown | 852.79 | 3981 | 1696.1 | 835.99 | 860.11 | Yes | N/A | N/A | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-15 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-30 | 16 | 12 | 2025-04-30 | 2025-04-30 | 1 | 1 | 6 | 4 | 18 | 14 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | 2023-08-25 | IOU Designed & Installed | N/A | No | N/A | 1059.45 | 361.68 | Unknown | 40.84 | Unknown | 656.93 | 3981 | 969.55 | 1059.45 | -89.9 | Yes | N/A | N/A | 2023-04-17 | 2023-04-17 | 1 | 1 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2023-08-25 | 131 | 95 | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-08-28 | 4 | 2 | 2023-08-28 | 2023-08-28 | 1 | 1 | 132 | 96 | 5 | 3 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 700.11 | -6.54 | Unknown | Unknown | 25.81 | 680.84 | 3981 | 637.18 | 700.11 | -62.93 | Yes | N/A | N/A | 2023-05-02 | 2023-05-24 | 23 | 17 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2024-01-02 | 224 | 160 | Unknown | 2023-12-14 | Unknown | Unknown | 2024-01-02 | 2024-01-11 | 10 | 8 | 2024-01-11 | 2024-01-11 | 1 | 1 | 247 | 177 | 11 | 9 | 258 | 186 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | -185 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-15 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 389.17 | -12.66 | Unknown | Unknown | 59.69 | 342.14 | 3981 | 675.11 | 389.17 | 285.94 | Yes | N/A | N/A | 2022-12-15 | 2023-02-09 | 57 | 41 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 57 | 41 | 1 | 1 | 58 | 42 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 106 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 114754.64 | 20122.57 | Unknown | 864.23 | -4848.79 | 98616.63 | Unknown | 4935.88 | 114754.64 | -109818.76 | Yes | N/A | N/A | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2023-12-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-16 | 30 | 22 | 2024-02-16 | 2024-02-16 | 1 | 1 | 1 | 1 | 82 | 60 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-19 | 22 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-07-05 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 1992.87 | 507.48 | Unknown | Unknown | Unknown | 1485.39 | 7962 | 944.7 | 1992.87 | -1048.17 | Yes | N/A | N/A | 2024-01-18 | 2024-07-05 | 170 | 122 | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2025-03-13 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-03-13 | 1 | 1 | 422 | 302 | 3 | 3 | 425 | 305 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1019 | 728 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2191.65 | -46.8 | Unknown | Unknown | 17.32 | 2221.13 | Unknown | 2069.81 | 2191.65 | -121.84 | Yes | N/A | N/A | 2023-06-09 | 2023-06-12 | 4 | 2 | 2023-06-12 | 2023-06-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-06-20 | 8 | 6 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-16 | 1 | 1 | 4 | 2 | 25 | 19 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | 114 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-05-04 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | 696.63 | 218.6 | Unknown | Unknown | Unknown | 478.03 | 0 | 1053.79 | 696.63 | 357.16 | Yes | N/A | N/A | 2023-04-28 | 2023-05-02 | 5 | 3 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2024-04-26 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-04-29 | 4 | 2 | 2024-04-29 | 2024-04-29 | 1 | 1 | 364 | 260 | 5 | 3 | 369 | 263 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 49.05 | 49.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | 252.4 | 122.45 | Unknown | Unknown | Unknown | 129.95 | 3981 | 1090.55 | 252.4 | 838.15 | Yes | N/A | N/A | 2024-01-29 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-01-29 | 98 | 70 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-04-26 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-23 | 28 | 20 | 2024-05-23 | 2024-05-23 | 1 | 1 | 89 | 65 | 127 | 91 | 216 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -515 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 4566.65 | 722.66 | Unknown | 305.35 | 17.5 | 3521.14 | 3981 | 1173.98 | 4566.65 | -3392.67 | Yes | N/A | N/A | 2024-09-25 | 2024-10-30 | 36 | 26 | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-01-29 | 91 | 65 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-01-29 | 2025-03-18 | 49 | 35 | 2025-03-18 | 2025-03-18 | 1 | 1 | 127 | 91 | 51 | 37 | 178 | 128 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-18 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 1376.32 | 159.88 | Unknown | Unknown | Unknown | 1216.44 | 3981 | 1104.02 | 1376.32 | -272.3 | Yes | N/A | N/A | 2024-07-16 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-18 | 14 | 10 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-09-23 | 68 | 48 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-23 | 2024-09-26 | 4 | 4 | 2024-09-26 | 2024-09-26 | 1 | 1 | 68 | 48 | 19 | 15 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | -98 | -71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1638.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-07-25 | 23 | 17 | 2024-07-25 | 2024-07-31 | 7 | 5 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-02-07 | 1 | 1 | 23 | 17 | 8 | 6 | 31 | 23 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 184 | 184 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -590 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-11 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 8.66 | -10.88 | Unknown | Unknown | Unknown | 19.54 | Unknown | 916.71 | 8.66 | 908.05 | Yes | N/A | N/A | 2024-01-09 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-01-26 | 5 | 5 | 2024-01-26 | 2024-01-26 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | -148 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | Unknown | 2023-04-03 | IOU Designed & Installed | N/A | No | N/A | 738.91 | 243.32 | Unknown | 88.1 | Unknown | 407.49 | 3885 | 784.31 | 738.91 | 45.4 | Yes | N/A | N/A | 2023-02-13 | 2023-02-13 | 1 | 1 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | 2023-04-03 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-04-06 | 4 | 4 | 2023-04-06 | 2023-04-06 | 1 | 1 | 51 | 37 | 5 | 5 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-10-12 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 582.31 | 183.68 | Unknown | Unknown | 11.49 | 387.14 | Unknown | 878.28 | 582.31 | 295.97 | Yes | N/A | N/A | 2023-09-12 | 2023-10-12 | 31 | 23 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2024-02-21 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-07-03 | 134 | 96 | 2024-07-03 | 2024-07-03 | 1 | 1 | 164 | 118 | 136 | 98 | 300 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1880.39 | -19.46 | Unknown | Unknown | 3.38 | 1896.47 | 8703 | 4726.8 | 1880.39 | 2846.41 | Yes | N/A | N/A | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | 2024-07-08 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-01-22 | 199 | 143 | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-11 | Unknown | Unknown | 201 | 145 | 112 | 80 | 313 | 225 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -140 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -456.17 | Unknown | Unknown | Unknown | -511 | 54.83 | 7947.01 | 1562.97 | -456.17 | 2019.14 | Yes | N/A | N/A | 2023-09-07 | 2024-01-09 | 125 | 89 | 2024-01-09 | 2024-04-30 | 113 | 81 | 2024-04-30 | 2024-05-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 133 | 95 | 114 | 82 | 247 | 177 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-04 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 1522.46 | Unknown | Unknown | Unknown | 102.15 | 1420.31 | 3981 | 685.11 | 1522.46 | -837.35 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-09-03 | 300 | 214 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-09-03 | 2024-11-25 | 84 | 60 | 2024-11-25 | 2024-11-25 | 1 | 1 | 301 | 215 | 86 | 62 | 387 | 277 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -150 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 4748.81 | Unknown | Unknown | Unknown | -7195 | 11943.81 | Unknown | 6672.04 | 4748.81 | 1923.23 | Yes | N/A | N/A | 2024-05-15 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-10 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-05-15 | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-06-25 | 2024-07-25 | 31 | 23 | 2024-07-25 | 2024-07-24 | Unknown | Unknown | 0 | 0 | 73 | 53 | 73 | 53 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | -710 | -509 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1020 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-16 | 7 | 5 | 2025-06-16 | 2025-06-16 | 1 | 1 | 6 | 4 | 9 | 7 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -137 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | 249.4 | -17.06 | Unknown | Unknown | Unknown | 266.46 | 3981 | 788.31 | 249.4 | 538.91 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-08-18 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-10-02 | 46 | 32 | 2023-10-02 | 2023-10-02 | 1 | 1 | 136 | 98 | 47 | 33 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 286 | 286 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -73 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 436.72 | -7.43 | Unknown | Unknown | 1.55 | 442.6 | 17711 | 1268.95 | 436.72 | 832.23 | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-29 | 25 | 19 | 2024-08-23 | 2024-08-26 | 4 | 2 | 2024-08-26 | 2024-09-26 | 32 | 24 | 2024-08-29 | 2024-11-25 | 89 | 63 | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-07 | Unknown | Unknown | 94 | 66 | 57 | 43 | 151 | 109 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | -272 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2023-05-05 | IOU Designed & Installed | N/A | No | N/A | -0.87 | -2.55 | Unknown | Unknown | Unknown | 1.68 | Unknown | 255.53 | -0.87 | 256.4 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-05-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-06-12 | 39 | 27 | 2023-06-12 | 2023-06-12 | 1 | 1 | 4 | 4 | 40 | 28 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-01-01 | 1688 | 1207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-21 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | 83905.34 | 8258.91 | Unknown | 757.54 | -13354.71 | 88243.6 | Unknown | 41642.6 | 83905.34 | -42262.74 | Yes | N/A | N/A | 2022-10-18 | 2023-02-01 | 107 | 77 | 2023-02-01 | 2023-04-26 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-01-11 | 2023-05-02 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 107 | 77 | 108 | 78 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -316 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-26 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 651.31 | -12.92 | Unknown | Unknown | Unknown | 664.23 | Unknown | 1050.75 | 651.31 | 399.44 | Yes | N/A | N/A | 2024-07-23 | 2024-07-25 | 3 | 3 | 2024-07-25 | 2024-07-26 | 2 | 2 | 2024-07-26 | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-16 | 23 | 17 | 2024-07-26 | 2024-10-07 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-18 | 12 | 10 | 2024-10-18 | 2024-10-18 | 1 | 1 | 77 | 55 | 38 | 30 | 115 | 85 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 82.4 | 82.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | 38 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9981.12 | 272.1 | Unknown | Unknown | -1120 | 10829.02 | 3981 | 1903.47 | 9981.12 | -8077.65 | Yes | N/A | N/A | 2024-03-01 | 2024-05-22 | 83 | 59 | 2024-05-22 | 2024-05-31 | 10 | 8 | 2024-05-31 | 2024-06-25 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2025-01-09 | 15 | 11 | 109 | 77 | 25 | 19 | 134 | 96 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | -23 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 444.03 | -21.87 | Unknown | Unknown | Unknown | 465.9 | Unknown | 1296.77 | 444.03 | 852.74 | Yes | N/A | N/A | 2023-03-31 | 2023-04-20 | 21 | 15 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2023-12-05 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 559.29 | -5.88 | Unknown | Unknown | Unknown | 565.17 | Unknown | 403.93 | 559.29 | -155.36 | Yes | N/A | N/A | 2024-11-11 | 2024-11-14 | 4 | 4 | 2024-11-14 | 2024-12-26 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-20 | 37 | 27 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-13 | 1 | 1 | 4 | 4 | 81 | 59 | 85 | 63 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO, CA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-22 | 602 | 431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 15094.87 | -94.06 | Unknown | Unknown | -592.3 | 15781.23 | 8880 | 10323.06 | 15094.87 | -4771.81 | Yes | N/A | N/A | 2023-09-20 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-12-26 | 118 | 84 | 2023-11-30 | 2023-12-21 | 4 | 4 | 2023-12-05 | 2024-01-03 | 20 | 16 | 2024-02-12 | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-15 | 4 | 4 | 2024-02-26 | 2024-03-15 | 19 | 15 | 2024-03-15 | 2024-03-15 | 1 | 1 | 4 | 4 | 162 | 120 | 166 | 124 | Steps 2,3,5,6,7 | 42 | 30 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -286 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 196.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-04-18 | 2 | 2 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-06-10 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-19 | 10 | 8 | 2025-06-19 | 2025-06-19 | 1 | 1 | 54 | 38 | 13 | 11 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 59.05 | 59.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 11130.7 | 4005.97 | Unknown | 93.03 | 64.9 | 6966.8 | 3981 | 870.07 | 11130.7 | -10260.63 | Yes | N/A | N/A | 2023-02-24 | 2023-06-14 | 111 | 79 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-10-23 | 132 | 94 | Unknown | 2023-10-19 | Unknown | Unknown | 2023-10-23 | 2023-11-01 | 10 | 8 | 2023-11-01 | 2023-11-01 | 1 | 1 | 243 | 173 | 11 | 9 | 254 | 182 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | La Mesa | LA MESA | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 310 | 223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -825.13 | 3154.74 | Unknown | Unknown | -10257 | 6277.13 | 3507 | 17558.02 | -825.13 | 18383.15 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | 2024-05-29 | 435 | 311 | 2023-07-06 | 2025-01-09 | 58 | 42 | 2023-07-28 | 2024-06-17 | 35 | 25 | 2024-05-29 | Unknown | Unknown | Unknown | 2025-03-18 | 2025-03-21 | 4 | 4 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1 | 1 | 59 | 43 | 475 | 341 | 534 | 384 | Steps 2,3,5,6,7 | 878 | 626 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 157.2 | 157.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 60.28 | Unknown | Unknown | Unknown | 1.26 | 59.02 | 3241 | 2145.67 | 60.28 | 2085.39 | Yes | N/A | N/A | 2024-07-25 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-25 | 11 | 9 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-12-02 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-02-05 | 66 | 48 | 2025-02-05 | 2025-02-05 | 1 | 1 | 131 | 93 | 78 | 58 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7133.19 | 2923.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-31 | 10 | 8 | 2025-01-31 | 2025-05-06 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-06-17 | 78 | 56 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-17 | 2025-06-19 | 3 | 3 | 2025-06-19 | 2025-06-19 | 1 | 1 | 174 | 124 | 14 | 12 | 188 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 257 | 184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | -2992.54 | 302.11 | Unknown | Unknown | -3502 | 207.35 | Unknown | 3502.18 | -2992.54 | 6494.72 | Yes | N/A | N/A | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | 2024-06-26 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-24 | 27 | 19 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-15 | 7 | 5 | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 65 | 47 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-30 | 432 | 309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-11-04 | 2022-07-11 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 43822.46 | 10874.69 | Unknown | Unknown | 276.11 | 32671.66 | 102235.31 | 17847.49 | 43822.46 | -25974.97 | Yes | N/A | N/A | 2021-11-04 | 2023-03-07 | 489 | 349 | 2023-03-07 | 2023-08-02 | 149 | 107 | 2023-04-12 | 2024-01-23 | 12 | 10 | 2023-03-25 | 2024-02-27 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2024-03-26 | 212 | 152 | 2023-12-04 | 2024-03-06 | 94 | 68 | 2024-03-06 | 2024-03-06 | 1 | 1 | 501 | 359 | 505 | 363 | 1006 | 722 | Steps 2,3,5,6,7 | 529 | 377 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 554 | 397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | Unknown | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | -1100.57 | Unknown | Unknown | Unknown | -1174 | 73.43 | 0 | 1265.53 | -1100.57 | 2366.1 | Yes | N/A | N/A | 2023-01-19 | 2023-02-08 | 21 | 15 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2024-12-04 | 626 | 448 | Unknown | 2024-11-22 | Unknown | Unknown | 2024-12-04 | 2024-12-06 | 3 | 3 | 2024-12-06 | 2024-12-05 | Unknown | Unknown | 647 | 463 | 3 | 3 | 650 | 466 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | -428 | -307 | No | 2024-05-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-28 | 2024-08-08 | IOU Designed & Installed | N/A | Yes | 94 | 538.57 | -10.2 | Unknown | Unknown | Unknown | 548.77 | 11933 | 1453.51 | 538.57 | 914.94 | Yes | N/A | N/A | 2024-05-24 | 2024-08-26 | 95 | 67 | 2024-08-26 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | 2024-05-28 | 2024-07-18 | 52 | 38 | 2024-05-28 | 2024-08-08 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-11-04 | 89 | 63 | 2024-11-04 | 2024-11-05 | 2 | 2 | 168 | 120 | 143 | 103 | 311 | 223 | Steps 2,3,5,6,7 | 51 | 37 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -139 | -100 | No | 2022-09-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | Unknown | IOU Designed & Installed | N/A | Yes | 410 | 339.02 | -16.7 | Unknown | Unknown | 19.29 | 336.43 | 3981 | 876.51 | 339.02 | 537.49 | Yes | N/A | N/A | 2022-08-12 | 2023-10-25 | 440 | 314 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-12 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-03-01 | 1 | 1 | 440 | 314 | 1 | 1 | 441 | 315 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 203.2 | 203.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | 168 | 121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | -228.43 | 588.04 | Unknown | Unknown | -2523 | 1706.53 | Unknown | 2233.95 | -228.43 | 2462.38 | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-04-07 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-05-12 | 88 | 62 | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-12 | 2025-05-30 | 19 | 15 | 2025-05-30 | 2025-05-30 | 1 | 1 | 120 | 86 | 21 | 17 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -645 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 492.29 | -9.61 | Unknown | Unknown | Unknown | 501.9 | Unknown | 856.84 | 492.29 | 364.55 | Yes | N/A | N/A | 2024-02-22 | 2024-01-12 | Unknown | Unknown | 2024-01-12 | 2024-02-22 | 42 | 30 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-04 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 12 | 10 | 2024-03-15 | 2024-03-15 | 1 | 1 | 12 | 8 | 55 | 41 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -459 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 780.46 | 244.9 | Unknown | Unknown | Unknown | 535.56 | 3981 | 1041.7 | 780.46 | 261.24 | Yes | N/A | N/A | 2023-10-24 | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2024-01-26 | 173 | 125 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-04-22 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-04-24 | 3 | 3 | 2024-04-24 | 2024-04-24 | 1 | 1 | 88 | 62 | 177 | 129 | 265 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 5078.58 | 1091.37 | Unknown | 595.73 | 6.67 | 3384.81 | 3981 | 2423.17 | 5078.58 | -2655.41 | Yes | N/A | N/A | 2024-04-11 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-06-21 | 81 | 59 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-09-16 | 88 | 62 | Unknown | 2024-09-04 | Unknown | Unknown | 2024-09-16 | 2024-09-19 | 4 | 4 | 2024-09-19 | 2024-09-17 | Unknown | Unknown | 88 | 62 | 85 | 63 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 284 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 3023.39 | 939.54 | Unknown | Unknown | Unknown | 2083.85 | 3981 | 1434.72 | 3023.39 | -1588.67 | Yes | N/A | N/A | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-09-06 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-11 | 36 | 26 | 2024-10-11 | 2024-10-11 | 1 | 1 | 53 | 39 | 38 | 28 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-19 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 1044.18 | 306.5 | Unknown | Unknown | 43.33 | 694.35 | 3981 | 737.79 | 1044.18 | -306.39 | Yes | N/A | N/A | 2023-10-16 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2023-10-19 | 77 | 55 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-30 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-11-09 | 377 | 270 | 2024-11-09 | 2024-11-09 | 1 | 0 | 12 | 8 | 455 | 325 | 467 | 333 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 1094.83 | 183.23 | Unknown | Unknown | Unknown | 911.6 | 3981 | 1515.33 | 1094.83 | 420.5 | Yes | N/A | N/A | 2024-12-02 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-12-02 | 6 | 4 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-01-13 | 36 | 26 | 2025-01-13 | 2025-01-13 | 1 | 1 | 8 | 6 | 43 | 31 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-07 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 237.35 | -9.58 | Unknown | Unknown | Unknown | 246.93 | Unknown | 807.84 | 237.35 | 570.49 | Yes | N/A | N/A | 2024-02-07 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2024-02-07 | 91 | 65 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-13 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-03-21 | 9 | 7 | 2024-03-21 | 2024-03-21 | 1 | 1 | 36 | 26 | 101 | 73 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | 120.05 | 120.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 24 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-03-11 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 26824.98 | 245.37 | Unknown | Unknown | -4241.44 | 30821.05 | 2972 | 11466.73 | 26824.98 | -15358.25 | Yes | N/A | N/A | 2024-02-01 | 2024-03-08 | 37 | 27 | 2024-03-08 | 2024-03-28 | 21 | 15 | 2024-05-20 | 2024-05-24 | 5 | 5 | 2024-03-19 | 2024-05-24 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-17 | 48 | 34 | 2024-06-17 | 2024-06-17 | 1 | 1 | 42 | 32 | 137 | 99 | 179 | 131 | Steps 2,3,5,6,7 | 66 | 48 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-01-24 | 1315 | 940 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-25 | 2024-04-03 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 1856.23 | 272.1 | Unknown | Unknown | -1891.91 | 3476.04 | Unknown | 1833.96 | 1856.23 | -22.27 | Yes | N/A | N/A | 2022-01-25 | 2024-04-03 | 800 | 572 | 2024-04-03 | 2024-06-27 | 86 | 62 | 2024-05-17 | 2024-05-21 | 5 | 3 | 2024-04-04 | 2024-08-22 | 69 | 51 | 2024-06-27 | 2024-07-24 | 28 | 20 | Unknown | 2024-07-22 | Unknown | Unknown | 2024-08-19 | 2024-09-23 | 36 | 26 | 2024-09-23 | 2024-08-31 | Unknown | Unknown | 833 | 595 | 191 | 139 | 1024 | 734 | Steps 2,3,5,6,7 | 144 | 102 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 236 | 236 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -353 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-26 | 2023-08-28 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 1508.26 | 493.36 | Unknown | Unknown | Unknown | 1014.9 | 3981 | 859.96 | 1508.26 | -648.3 | Yes | N/A | N/A | 2023-08-26 | 2023-08-28 | 3 | 1 | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2024-07-31 | 339 | 243 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-05 | 6 | 4 | 2024-08-05 | 2024-08-05 | 1 | 1 | 342 | 244 | 8 | 6 | 350 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 27.77 | Unknown | Unknown | Unknown | Unknown | 27.77 | 3981 | 1409.63 | 27.77 | 1381.86 | Yes | N/A | N/A | 2024-08-05 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-06 | 6 | 4 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-09-04 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-14 | 41 | 29 | 2024-10-14 | 2024-10-14 | 1 | 1 | 31 | 23 | 48 | 34 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 392.05 | 392.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 54 | 39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-23 | 2023-05-04 | 2023-05-19 | IOU Designed & Installed | N/A | No | N/A | 172.29 | 67.89 | Unknown | Unknown | 2.09 | 102.31 | 3981 | 802.49 | 172.29 | 630.2 | Yes | N/A | N/A | 2023-04-23 | 2023-05-04 | 12 | 9 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-05-19 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-08-30 | 104 | 74 | 2023-08-30 | 2023-05-24 | Unknown | Unknown | 28 | 21 | 104 | 74 | 132 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-29 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 1011.86 | -8.9 | Unknown | Unknown | Unknown | 1020.76 | 0 | 1050.75 | 1011.86 | 38.89 | Yes | N/A | N/A | 2024-08-22 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-10-03 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-26 | 31 | 23 | 2024-10-03 | 2025-06-05 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 2 | 2 | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 246 | 176 | 176 | 128 | 422 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -299 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 23.88 | Unknown | Unknown | Unknown | Unknown | 23.88 | 3241 | 974.28 | 23.88 | 950.4 | Yes | N/A | N/A | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-08-01 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-06 | 6 | 4 | 2024-08-06 | 2024-08-05 | Unknown | Unknown | 33 | 25 | 7 | 5 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -129 | -94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | -21.18 | -17.2 | Unknown | Unknown | Unknown | -3.98 | Unknown | 496.75 | -21.18 | 517.93 | Yes | N/A | N/A | 2023-11-14 | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2023-11-14 | 56 | 40 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-02-22 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-04-30 | 69 | 49 | 2024-04-30 | 2024-04-30 | 1 | 1 | 101 | 73 | 126 | 90 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-15 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 35.5 | Unknown | Unknown | Unknown | Unknown | 35.5 | Unknown | 1631.29 | 35.5 | 1595.79 | Yes | N/A | N/A | 2024-11-04 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-15 | 29 | 21 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-04 | 14 | 10 | 2024-12-04 | 2024-12-04 | 1 | 1 | 7 | 5 | 44 | 32 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 931.05 | 931.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.93 | -8.7 | Unknown | Unknown | Unknown | 5.77 | Unknown | 973.54 | -2.93 | 976.47 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-06-30 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 668.05 | 668.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 1625.03 | Unknown | Unknown | Unknown | 20.56 | 1604.47 | 3981 | 1130.51 | 1625.03 | -494.52 | Yes | N/A | N/A | 2024-08-22 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-03 | 27 | 19 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-12-20 | 109 | 79 | Unknown | 2024-12-03 | Unknown | Unknown | 2024-12-20 | 2025-01-14 | 26 | 18 | 2025-01-14 | 2025-01-13 | Unknown | Unknown | 109 | 79 | 53 | 37 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | -349 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 1294.5 | 246.68 | Unknown | Unknown | 23.09 | 1024.73 | 3941 | 958.26 | 1294.5 | -336.24 | Yes | N/A | N/A | 2024-03-18 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-03-29 | 93 | 67 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-05-14 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-28 | 46 | 34 | 2024-06-28 | 2024-05-16 | Unknown | Unknown | 47 | 33 | 139 | 101 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -655 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 19.15 | Unknown | Unknown | Unknown | Unknown | 19.15 | 3981 | 1567.34 | 19.15 | 1548.19 | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-11 | 2 | 2 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-25 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-15 | 21 | 15 | 2024-10-15 | 2024-10-15 | 1 | 1 | 17 | 13 | 24 | 18 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 285.13 | Unknown | Unknown | Unknown | Unknown | 285.13 | 0 | 466.88 | 285.13 | 181.75 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-09-04 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 3 | 3 | 154 | 110 | 157 | 113 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 19586.5 | 596.5 | Unknown | 51 | 7.41 | 18931.59 | 32898 | 17467.92 | 19586.5 | -2118.58 | Yes | N/A | N/A | 2024-01-03 | 2024-03-14 | 72 | 52 | 2024-03-14 | 2024-04-18 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-02-21 | 310 | 222 | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-02 | 2025-04-09 | 8 | 6 | 2025-04-09 | 2025-04-09 | 1 | 1 | 382 | 274 | 45 | 33 | 427 | 307 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21.2 | 21.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -514 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-05 | 2025-01-05 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 1605.13 | 410.5 | Unknown | Unknown | Unknown | 1194.63 | 3981 | 3669.25 | 1605.13 | 2064.12 | Yes | N/A | N/A | 2025-01-05 | 2025-02-10 | 37 | 26 | 2025-02-10 | 2025-03-03 | 22 | 16 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-12 | 30 | 22 | 2025-06-12 | 2025-06-12 | 1 | 1 | 46 | 33 | 53 | 39 | 99 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -443 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-08-11 | IOU Designed & Installed | N/A | No | N/A | 36.47 | Unknown | Unknown | Unknown | Unknown | 36.47 | 3981 | 1438.73 | 36.47 | 1402.26 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-08-11 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-08-11 | 2024-08-26 | 16 | 11 | 2024-08-26 | 2024-08-21 | Unknown | Unknown | 49 | 35 | 17 | 12 | 66 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | El Cajon | EL CAJON | 2272 | 2272 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-01 | 116 | 83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-14 | 2025-04-27 | IOU Designed & Installed | N/A | No | N/A | 27891.02 | 6009.29 | Unknown | 496.91 | Unknown | 21384.82 | Unknown | 11960.32 | 27891.02 | -15930.7 | Yes | N/A | N/A | 2025-02-11 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-04-01 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-05-07 | 42 | 32 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-27 | 2025-04-27 | 1 | 0 | 2025-04-27 | 2025-04-27 | 1 | 0 | 0 | 0 | 99 | 71 | 99 | 71 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | -1798.56 | Unknown | Unknown | Unknown | -1824 | 25.44 | Unknown | 1823.56 | -1798.56 | 3622.12 | Yes | N/A | N/A | 2024-06-04 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-07-03 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-11 | 7 | 5 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-13 | 20 | 14 | 2024-08-13 | 2024-08-13 | 1 | 1 | 0 | 0 | 71 | 51 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | -347 | -250 | No | 2022-11-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-18 | 2023-09-11 | IOU Designed & Installed | N/A | Yes | 122 | 561.31 | -8.91 | Unknown | Unknown | 18.75 | 551.47 | 3885 | 747.02 | 561.31 | 185.71 | Yes | N/A | N/A | 2022-11-14 | 2023-03-16 | 123 | 89 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-18 | 2023-09-11 | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-11 | 2023-09-20 | 10 | 8 | 2023-09-20 | 2023-09-18 | Unknown | Unknown | 123 | 89 | 10 | 8 | 133 | 97 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -508 | -365 | No | 2023-02-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | Yes | 42 | 632.69 | -12.3 | Unknown | Unknown | 4.82 | 640.17 | 3981 | 551.5 | 632.69 | -81.19 | Yes | N/A | N/A | 2023-02-02 | 2023-03-16 | 43 | 31 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-10 | 1 | 1 | 43 | 31 | 1 | 1 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -569 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 2610.39 | -50.82 | Unknown | Unknown | Unknown | 2661.21 | Unknown | 1960.39 | 2610.39 | -650 | Yes | N/A | N/A | 2024-09-05 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-09-24 | 70 | 50 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-11-11 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-20 | 40 | 30 | 2024-12-20 | 2024-12-20 | 1 | 1 | 49 | 35 | 111 | 81 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | 85 | 62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 322.31 | -27.71 | Unknown | Unknown | Unknown | 350.02 | 3961 | 163.83 | 322.31 | -158.48 | Yes | N/A | N/A | 2023-06-27 | 2024-01-17 | 205 | 147 | 2024-01-17 | 2024-01-26 | 10 | 8 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-06-20 | 1 | 1 | 205 | 147 | 11 | 9 | 216 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -317 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 4481.35 | 1180.18 | Unknown | Unknown | Unknown | 3301.17 | 3981 | 1367.57 | 4481.35 | -3113.78 | Yes | N/A | N/A | 2025-04-24 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-24 | 18 | 14 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-20 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-18 | 30 | 22 | 2025-06-18 | 2025-06-18 | 1 | 1 | 27 | 19 | 49 | 37 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -437 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 9522.16 | Unknown | Unknown | Unknown | -608.51 | 10130.67 | Unknown | 649.08 | 9522.16 | -8873.08 | Yes | N/A | N/A | 2023-12-06 | 2024-01-17 | 43 | 31 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-24 | 11 | 9 | 2024-02-09 | 2024-06-03 | 116 | 82 | Unknown | 2025-03-18 | Unknown | Unknown | 2024-06-03 | 2024-07-23 | 51 | 37 | 2024-07-23 | 2024-06-27 | Unknown | Unknown | 159 | 113 | 62 | 46 | 221 | 159 | Steps 2,3,5,6,7 | 393 | 281 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.51 | -4.48 | Unknown | Unknown | Unknown | 2.97 | 3981 | 217.6 | -1.51 | 219.11 | Yes | N/A | N/A | 2023-01-10 | 2023-02-07 | 29 | 21 | 2023-02-07 | 2023-02-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 29 | 21 | 9 | 7 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -320 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9.82 | -8.75 | Unknown | Unknown | Unknown | 18.57 | 3981 | 1508.94 | 9.82 | 1499.12 | Yes | N/A | N/A | 2023-04-17 | 2023-04-17 | 1 | 1 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-03-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | 25 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 2955.62 | Unknown | Unknown | Unknown | -1169 | 4124.62 | Unknown | 1169.02 | 2955.62 | -1786.6 | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-08-13 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-06 | 16 | 12 | 2024-09-06 | 2024-09-06 | 1 | 1 | 1 | 1 | 37 | 27 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA9 PH1 | San Diego PA9 PH1 | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 491 | 352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | 2024-05-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 118782.68 | 11170.86 | Unknown | Unknown | 19332.04 | 88279.78 | 0 | 50054.7 | 118782.68 | -68727.98 | Yes | N/A | N/A | 2022-04-27 | 2023-01-31 | 280 | 200 | 2023-01-31 | 2023-05-31 | 121 | 87 | 2023-02-22 | 2024-04-08 | 232 | 166 | 2023-03-22 | 2023-07-28 | 73 | 53 | 2023-11-08 | Unknown | Unknown | Unknown | 2023-11-08 | 2024-05-02 | 177 | 127 | 2024-05-08 | 2024-07-23 | 77 | 55 | 2024-07-23 | 2024-07-23 | 1 | 1 | 512 | 366 | 449 | 323 | 961 | 689 | Steps 2,3,5,6,7 | 481 | 343 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-13 | 407 | 292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3981 | 761.6 | Unknown | 761.6 | Yes | N/A | N/A | 2024-05-06 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-06 | 48 | 34 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-08-06 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-23 | 18 | 14 | 2024-08-23 | 2024-08-23 | 1 | 1 | 93 | 67 | 67 | 49 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 3874 | 3874 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-15 | 39 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 38285.05 | 12017.58 | Unknown | Unknown | 45.18 | 26222.29 | 672303 | 35858.6 | 38285.05 | -2426.45 | Yes | N/A | N/A | 2023-04-21 | 2023-04-11 | Unknown | Unknown | 2023-04-11 | 2023-08-21 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2025-02-24 | 554 | 396 | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-03-26 | Unknown | Unknown | 554 | 396 | 133 | 95 | 687 | 491 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-03-14 | IOU Designed & Installed | N/A | No | N/A | -4.15 | -12.24 | Unknown | Unknown | Unknown | 8.09 | 3981 | 671.78 | -4.15 | 675.93 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-03-14 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-06-27 | 106 | 76 | 2023-06-27 | 2023-03-20 | Unknown | Unknown | 20 | 14 | 106 | 76 | 126 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 53.23 | -0.63 | Unknown | Unknown | Unknown | 53.86 | 3981 | 1460.16 | 53.23 | 1406.93 | Yes | N/A | N/A | 2024-08-28 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-09-04 | 21 | 15 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-08 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-21 | 14 | 10 | 2024-10-21 | 2024-10-21 | 1 | 1 | 35 | 25 | 36 | 26 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -304 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1932.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-05-15 | 14 | 10 | 2024-05-15 | 2024-07-22 | 69 | 49 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-05-27 | Unknown | Unknown | 14 | 10 | 69 | 49 | 83 | 59 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | 67 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-04 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1017.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-04-04 | 74 | 54 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2025-06-03 | 426 | 304 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-04 | 2 | 2 | 2025-06-04 | 2025-06-04 | 1 | 1 | 426 | 304 | 77 | 57 | 503 | 361 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-03 | 980 | 701 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-04 | 2024-04-10 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 46.29 | Unknown | Unknown | Unknown | 6.39 | 39.9 | 3981 | 676.72 | 46.29 | 630.43 | Yes | N/A | N/A | 2022-05-04 | 2024-04-03 | 701 | 501 | 2024-04-03 | 2024-04-10 | 8 | 6 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-10-24 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-03-05 | 133 | 95 | 2025-03-05 | 2025-04-09 | 36 | 26 | 899 | 643 | 177 | 127 | 1076 | 770 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-11 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1107.26 | -11.11 | Unknown | Unknown | Unknown | 1118.37 | 3981 | 178.14 | 1107.26 | -929.12 | Yes | N/A | N/A | 2024-08-16 | 2024-12-12 | 119 | 85 | 2024-12-12 | 2024-12-31 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-28 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | 2025-01-29 | 2025-01-28 | Unknown | Unknown | 148 | 106 | 20 | 14 | 168 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | -6.52 | -5.29 | Unknown | Unknown | Unknown | -1.23 | Unknown | 515.81 | -6.52 | 522.33 | Yes | N/A | N/A | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-03-15 | 65 | 47 | 2024-03-15 | 2024-03-15 | 1 | 1 | 23 | 17 | 67 | 49 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-23 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1450.03 | Unknown | Unknown | Unknown | 20.37 | 1429.66 | 3981 | 1074.83 | 1450.03 | -375.2 | Yes | N/A | N/A | 2024-07-19 | 2024-07-30 | 12 | 8 | 2024-07-30 | 2024-08-22 | 24 | 18 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-01-21 | 153 | 109 | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-21 | 2025-02-20 | 31 | 23 | 2025-02-20 | 2025-02-20 | 1 | 1 | 165 | 117 | 56 | 42 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -487 | -350 | No | 2023-02-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-02-02 | 2023-06-07 | IOU Designed & Installed | N/A | Yes | 125 | 1560.36 | 627.67 | Unknown | Unknown | Unknown | 932.69 | 3885 | 755.77 | 1560.36 | -804.59 | Yes | N/A | N/A | 2023-01-26 | 2023-06-07 | 133 | 95 | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-06-07 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-06-12 | 6 | 4 | 2023-06-12 | 2023-06-12 | 1 | 1 | 259 | 185 | 7 | 5 | 266 | 190 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -261 | -188 | No | 2023-05-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2024-05-28 | IOU Designed & Installed | N/A | Yes | 241 | 587 | 367.35 | Unknown | Unknown | Unknown | 219.65 | Unknown | 479.76 | 587 | -107.24 | Yes | N/A | N/A | 2023-05-15 | 2024-01-11 | 242 | 174 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2024-05-28 | 380 | 272 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | 2024-05-28 | 1 | 1 | 622 | 446 | 2 | 2 | 624 | 448 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 1659.88 | Unknown | Unknown | Unknown | -596.83 | 2256.71 | 3981 | 4586.23 | 1659.88 | 2926.35 | Yes | N/A | N/A | 2024-11-06 | 2024-12-06 | 31 | 23 | 2024-12-06 | 2024-12-16 | 11 | 7 | 2024-12-16 | 2025-01-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-03-03 | 42 | 30 | Unknown | 2025-02-27 | Unknown | Unknown | 2025-03-03 | 2025-03-10 | 8 | 6 | 2025-03-10 | 2025-03-10 | 1 | 1 | 110 | 80 | 20 | 14 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -698 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-12 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 652.1 | 362.52 | Unknown | 27.33 | Unknown | 262.25 | Unknown | 192.95 | 652.1 | -459.15 | Yes | N/A | N/A | 2024-08-07 | 2024-08-12 | 6 | 4 | 2024-08-12 | 2024-08-20 | 9 | 7 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-27 | 7 | 5 | 2024-08-27 | 2024-08-27 | 1 | 1 | 8 | 6 | 17 | 13 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1223.81 | -24.15 | Unknown | Unknown | Unknown | 1247.96 | 3981 | 1818.2 | 1223.81 | 594.39 | Yes | N/A | N/A | 2024-09-20 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-09-20 | 2 | 2 | 2024-09-20 | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-10 | 21 | 15 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-18 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | 13 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-28 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 1115.88 | -20.4 | Unknown | Unknown | Unknown | 1136.28 | 3981 | 800.84 | 1115.88 | -315.04 | Yes | N/A | N/A | 2023-09-22 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-09-28 | 51 | 37 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2024-07-17 | 294 | 210 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-07 | 22 | 16 | 2024-08-07 | 2024-08-07 | 1 | 1 | 294 | 210 | 74 | 54 | 368 | 264 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | -638 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 38.12 | Unknown | Unknown | Unknown | Unknown | 38.12 | Unknown | 197.01 | 38.12 | 158.89 | Yes | N/A | N/A | 2024-09-27 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-10-03 | 28 | 20 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-07 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-11 | 5 | 5 | 2024-10-11 | 2024-10-11 | 1 | 1 | 5 | 3 | 34 | 26 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 156.05 | 156.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -383 | -275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-04 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | -1121.63 | Unknown | Unknown | Unknown | -1189.48 | 67.85 | 3981 | 2478.16 | -1121.63 | 3599.79 | Yes | N/A | N/A | 2024-04-03 | 2023-12-26 | Unknown | Unknown | 2023-12-26 | 2024-04-04 | 101 | 73 | 2024-04-04 | 2024-05-24 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-09-24 | 124 | 88 | Unknown | 2024-08-27 | Unknown | Unknown | 2024-09-24 | 2024-11-25 | 63 | 45 | 2024-11-25 | 2024-11-25 | 1 | 1 | 175 | 125 | 165 | 119 | 340 | 244 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 269.08 | Unknown | Unknown | Unknown | Unknown | 269.08 | 3981 | 1398.72 | 269.08 | 1129.64 | Yes | N/A | N/A | 2024-06-27 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-10-04 | 102 | 74 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-06 | 1 | 1 | 0 | 0 | 103 | 75 | 103 | 75 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 1212.1 | Unknown | Unknown | Unknown | 14.07 | 1198.03 | 3981 | 1150.97 | 1212.1 | -61.13 | Yes | N/A | N/A | 2024-08-22 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-23 | 47 | 33 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-12-16 | 85 | 61 | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-16 | 2025-01-06 | 22 | 16 | 2025-01-06 | 2025-01-06 | 1 | 1 | 85 | 61 | 70 | 50 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-19 | 918 | 657 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1323.62 | 125.39 | Unknown | Unknown | 25.55 | 1172.68 | 10149 | 1255.45 | 1323.62 | -68.17 | Yes | N/A | N/A | 2023-04-14 | 2023-04-17 | 4 | 2 | 2023-04-17 | 2023-06-20 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2024-09-26 | 465 | 333 | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-11-22 | Unknown | Unknown | 469 | 335 | 65 | 47 | 534 | 382 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -365 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 2727.74 | Unknown | Unknown | Unknown | 85.74 | 2642 | 3981 | 1369.12 | 2727.74 | -1358.62 | Yes | N/A | N/A | 2024-02-08 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-04-17 | 71 | 51 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-17 | 31 | 23 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-05-17 | 2024-10-24 | 161 | 115 | 2024-10-24 | 2024-10-24 | 1 | 1 | 31 | 23 | 233 | 167 | 264 | 190 | Steps 2,3,5,6,7 | 136 | 96 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | -312 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | 484.01 | -16.88 | Unknown | Unknown | Unknown | 500.89 | Unknown | 288.14 | 484.01 | -195.87 | Yes | N/A | N/A | 2023-11-29 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2023-11-29 | 31 | 23 | 2023-11-29 | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-08 | 8 | 6 | 2023-11-29 | 2023-11-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-11 | 12 | 8 | 2023-12-11 | 2023-12-11 | 1 | 1 | 2 | 2 | 52 | 38 | 54 | 40 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 480 | 480 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 991.58 | -19.31 | Unknown | Unknown | Unknown | 1010.89 | 7962 | 1203.17 | 991.58 | 211.59 | Yes | N/A | N/A | 2024-05-24 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-07-17 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-09 | 32 | 24 | 2024-07-17 | 2024-07-25 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-09-05 | Unknown | Unknown | 9 | 7 | 101 | 73 | 110 | 80 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 68.4 | Unknown | Unknown | Unknown | Unknown | 68.4 | Unknown | 1711.47 | 68.4 | 1643.07 | Yes | N/A | N/A | 2024-10-15 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-17 | 8 | 6 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 0 | 0 | 9 | 7 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 140 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 4294.24 | 809.45 | Unknown | Unknown | -493 | 3977.79 | 3941 | 1565.03 | 4294.24 | -2729.21 | Yes | N/A | N/A | 2024-01-11 | 2023-02-01 | Unknown | Unknown | 2023-02-01 | 2024-01-11 | 345 | 247 | 2024-01-11 | 2024-04-03 | 84 | 60 | 2024-04-03 | 2024-11-15 | 30 | 22 | 2024-04-03 | 2024-11-18 | 230 | 164 | Unknown | 2024-09-27 | Unknown | Unknown | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | 2024-11-18 | 1 | 1 | 314 | 224 | 377 | 271 | 691 | 495 | Steps 2,3,5,6,7 | 226 | 162 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-24 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 301.54 | -8.28 | Unknown | Unknown | Unknown | 309.82 | 3941 | 924.78 | 301.54 | 623.24 | Yes | N/A | N/A | 2024-01-19 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-01-19 | 39 | 29 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-22 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-08 | 18 | 14 | 2024-02-08 | 2024-02-08 | 1 | 1 | 4 | 2 | 58 | 44 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | DANA POINT | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | -214 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-18 | 2024-03-31 | IOU Designed & Installed | N/A | No | N/A | 2949.4 | 942.11 | Unknown | 151.69 | Unknown | 1855.6 | 3981 | 1083.75 | 2949.4 | -1865.65 | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2023-12-18 | 14 | 10 | 2023-12-18 | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-22 | 35 | 25 | 2023-12-18 | 2024-03-31 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-03-31 | 2024-04-05 | 6 | 5 | 2024-04-05 | 2024-04-03 | Unknown | Unknown | 106 | 76 | 55 | 40 | 161 | 116 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-03-02 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | -4.84 | -3.92 | Unknown | Unknown | Unknown | -0.92 | 3981 | 941.03 | -4.84 | 945.87 | Yes | N/A | N/A | 2024-02-07 | 2023-12-26 | Unknown | Unknown | 2023-12-26 | 2024-03-02 | 68 | 49 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-11 | 10 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-04-08 | 29 | 21 | 2024-04-08 | 2024-04-08 | 1 | 1 | 10 | 6 | 98 | 71 | 108 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 613 | 440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 13208.5 | 419 | Unknown | 42.09 | -2872 | 15619.41 | Unknown | 2460.33 | 13208.5 | -10748.17 | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-08-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-11-07 | 86 | 62 | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-20 | 2024-11-25 | 6 | 4 | 2024-11-25 | 2024-11-22 | Unknown | Unknown | 87 | 63 | 29 | 21 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 59 | 59 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-07 | -508 | -363 | No | 2023-12-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-05-10 | IOU Designed & Installed | N/A | Yes | 72 | 862.48 | -7.4 | Unknown | Unknown | 5.23 | 864.65 | 3981 | 1159.74 | 862.48 | 297.26 | Yes | N/A | N/A | 2023-12-27 | 2024-03-04 | 69 | 49 | 2024-03-04 | 2024-03-08 | 5 | 5 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-05-10 | 68 | 50 | Unknown | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-05-17 | 8 | 6 | 2024-05-17 | 2024-05-17 | 1 | 1 | 137 | 99 | 14 | 12 | 151 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -670 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-30 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 103.73 | -1.5 | Unknown | Unknown | Unknown | 105.23 | 3981 | 1269.35 | 103.73 | 1165.62 | Yes | N/A | N/A | 2025-01-28 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-30 | 17 | 13 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-18 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-10 | 21 | 15 | 2025-03-10 | 2025-03-09 | Unknown | Unknown | 20 | 14 | 38 | 28 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-04-10 | 2023-05-31 | IOU Designed & Installed | N/A | No | N/A | 1029.93 | 586.51 | Unknown | 93.19 | Unknown | 350.23 | Unknown | 154.79 | 1029.93 | -875.14 | Yes | N/A | N/A | 2023-03-23 | 2023-04-10 | 19 | 13 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-05-31 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-07 | 8 | 6 | 2023-06-07 | 2023-06-07 | 1 | 1 | 71 | 51 | 9 | 7 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | -480 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | -862.37 | 189.48 | Unknown | Unknown | -1966 | 914.15 | Unknown | 2172.18 | -862.37 | 3034.55 | Yes | N/A | N/A | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | 2024-12-13 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-12-18 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-20 | 3 | 3 | 2024-12-20 | 2024-12-20 | 1 | 1 | 184 | 134 | 5 | 5 | 189 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 336 | 241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-05-05 | IOU Designed & Installed | N/A | No | N/A | -1074.75 | 2050.62 | Unknown | 265.75 | -4306 | 914.88 | Unknown | 4305.71 | -1074.75 | 5380.46 | Yes | N/A | N/A | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-05 | 2024-05-24 | 20 | 15 | 2024-05-24 | 2024-05-24 | 1 | 1 | 1 | 1 | 21 | 16 | 22 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 983.58 | -7.04 | Unknown | Unknown | 9.08 | 981.54 | 3981 | 1349.35 | 983.58 | 365.77 | Yes | N/A | N/A | 2024-09-13 | 2024-12-28 | 107 | 76 | 2024-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-04-10 | 87 | 63 | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-10 | 2025-04-23 | 14 | 10 | 2025-04-23 | 2025-04-23 | 1 | 1 | 194 | 139 | 15 | 11 | 209 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 60.35 | 60.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-03 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 1887.46 | -2.5 | Unknown | Unknown | 19.29 | 1870.67 | 3981 | 1189.69 | 1887.46 | -697.77 | Yes | N/A | N/A | 2024-10-01 | 2024-10-11 | 11 | 9 | 2024-10-11 | 2024-10-30 | 20 | 14 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-02-05 | 98 | 70 | Unknown | 2025-01-15 | Unknown | Unknown | 2025-02-05 | 2025-02-20 | 16 | 12 | 2025-02-20 | 2025-02-19 | Unknown | Unknown | 109 | 79 | 36 | 26 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-22 | -74 | -54 | No | 2021-03-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-12 | Unknown | Unknown | IOU Designed & Installed | N/A | Yes | 118 | 1562.25 | -11.23 | Unknown | Unknown | Unknown | 1573.48 | 0 | 603.94 | 1562.25 | -958.31 | Yes | N/A | N/A | 2021-03-12 | 2025-03-05 | 1455 | 1039 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-11-09 | Unknown | Unknown | 2021-11-09 | 2021-11-09 | Unknown | Unknown | 1455 | 1039 | 0 | 0 | 1455 | 1039 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-04 | 793 | 568 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-04 | 2021-10-04 | 2024-11-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 230220 | 62818.09 | Unknown | Unknown | -16814.82 | 184216.73 | 2357584.96 | 180575.35 | 230220 | -49644.65 | Yes | N/A | N/A | 2021-10-04 | 2023-07-14 | 649 | 465 | 2023-07-14 | 2024-09-04 | 419 | 299 | 2023-07-31 | 2024-12-13 | 305 | 218 | 2023-12-06 | 2024-06-20 | 14 | 10 | 2024-09-04 | 2025-07-10 | 310 | 222 | 2024-08-07 | 2025-05-06 | 273 | 195 | 2024-11-20 | 2024-12-05 | 16 | 12 | 2024-12-05 | 2024-12-05 | 1 | 1 | 1264 | 905 | 723 | 517 | 1987 | 1422 | Steps 2,3,5,6,7 | 1278 | 914 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -571 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-30 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 1681.67 | -44.12 | Unknown | Unknown | Unknown | 1725.79 | Unknown | 1005.23 | 1681.67 | -676.44 | Yes | N/A | N/A | 2023-11-01 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-11-30 | 102 | 74 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-15 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-17 | 34 | 24 | 2024-01-17 | 2024-01-17 | 1 | 1 | 16 | 12 | 137 | 99 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -75 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1021.59 | Unknown | Unknown | Unknown | 5.68 | 1015.91 | Unknown | 2132.24 | 1021.59 | 1110.65 | Yes | N/A | N/A | 2023-11-27 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-12-01 | 38 | 28 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-07-29 | 1 | 1 | 0 | 0 | 39 | 29 | 39 | 29 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-14 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 1129.68 | Unknown | Unknown | Unknown | 18.61 | 1111.07 | 3981 | 1239.92 | 1129.68 | 110.24 | Yes | N/A | N/A | 2024-03-13 | 2024-03-28 | 16 | 12 | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-08-01 | 127 | 91 | Unknown | 2024-07-03 | Unknown | Unknown | 2024-08-01 | 2024-08-15 | 15 | 11 | 2024-08-15 | 2024-08-15 | 1 | 1 | 143 | 103 | 17 | 13 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | -254 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 18.68 | Unknown | Unknown | Unknown | Unknown | 18.68 | 3981 | 1974.71 | 18.68 | 1956.03 | Yes | N/A | N/A | 2024-06-04 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-08-05 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-05 | 20 | 14 | 2024-08-05 | 2024-08-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-19 | 11 | 7 | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 2 | 2 | 107 | 75 | 109 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -22 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1340.05 | Unknown | Unknown | Unknown | 9.13 | 1330.92 | 3981 | 2393.66 | 1340.05 | 1053.61 | Yes | N/A | N/A | 2024-06-28 | 2024-09-04 | 69 | 49 | 2024-09-04 | 2024-09-17 | 14 | 10 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-01 | 1 | 1 | 69 | 49 | 15 | 11 | 84 | 60 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 30.35 | 30.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -389 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 670.78 | -14.47 | Unknown | Unknown | 11.89 | 673.36 | 3981 | 656.47 | 670.78 | -14.31 | Yes | N/A | N/A | 2023-03-16 | 2023-06-05 | 82 | 58 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-10-11 | 129 | 93 | Unknown | 2023-10-09 | Unknown | Unknown | 2023-10-11 | 2023-10-16 | 6 | 4 | 2023-10-16 | 2023-12-21 | 67 | 49 | 211 | 151 | 73 | 53 | 284 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 155.05 | 155.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-05 | 374 | 269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 957.09 | 562.86 | Unknown | 280.67 | -1144 | 1257.56 | 3981 | 2569.38 | 957.09 | 1612.29 | Yes | N/A | N/A | 2023-10-20 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | 2023-10-20 | 58 | 42 | 2023-10-20 | 2024-01-22 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-06-10 | 141 | 101 | Unknown | 2024-05-22 | Unknown | Unknown | 2024-06-10 | 2024-06-13 | 4 | 4 | 2024-06-13 | 2024-06-13 | 1 | 1 | 236 | 168 | 63 | 47 | 299 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6805 | 6805 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-11 | -381 | -274 | No | 2024-02-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-03-22 | IOU Designed & Installed | N/A | Yes | 8 | -8.15 | -16 | Unknown | Unknown | Unknown | 7.85 | 3981 | 1194.46 | -8.15 | 1202.61 | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | 2024-03-08 | 9 | 7 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-03-27 | 6 | 4 | 2024-03-27 | 2024-03-26 | Unknown | Unknown | 16 | 12 | 15 | 11 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 128.05 | 128.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-07-15 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 3057.76 | 934.08 | Unknown | 161.79 | -385 | 2346.89 | 3981 | 1123.54 | 3057.76 | -1934.22 | Yes | N/A | N/A | 2024-06-14 | 2024-07-10 | 27 | 19 | 2024-07-10 | 2024-07-15 | 6 | 4 | 2024-07-15 | 2024-07-23 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-11-01 | 102 | 74 | Unknown | 2024-08-29 | Unknown | Unknown | 2024-11-01 | 2024-11-13 | 13 | 9 | 2024-11-13 | 2024-11-13 | 1 | 1 | 138 | 100 | 20 | 14 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -545 | -390 | No | 2023-03-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | -12.35 | -8.94 | Unknown | Unknown | Unknown | -3.41 | Unknown | 363.72 | -12.35 | 376.07 | Yes | N/A | N/A | 2023-03-23 | 2023-04-07 | 16 | 12 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-08-11 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-07 | 176 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 1248.64 | -21.07 | Unknown | Unknown | Unknown | 1269.71 | 3981 | 747.41 | 1248.64 | -501.23 | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2024-05-30 | 402 | 288 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-03 | 5 | 3 | 2024-06-03 | 2024-05-31 | Unknown | Unknown | 403 | 289 | 5 | 3 | 408 | 292 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -612 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-02-26 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1750.08 | 416.72 | Unknown | 107.23 | Unknown | 1226.13 | 3981 | 1645.51 | 1750.08 | -104.57 | Yes | N/A | N/A | 2025-01-16 | 2025-02-07 | 23 | 17 | 2025-02-07 | 2025-02-26 | 20 | 14 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-04-01 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-07 | 7 | 5 | 2025-04-07 | 2025-04-07 | 1 | 1 | 58 | 42 | 28 | 20 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | -649 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-04-02 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 5.17 | Unknown | Unknown | Unknown | Unknown | 5.17 | Unknown | 118.25 | 5.17 | 113.08 | Yes | N/A | N/A | 2025-03-21 | 2025-05-13 | 54 | 38 | 2025-05-13 | 2025-05-16 | 4 | 4 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-28 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-02 | 6 | 4 | 2025-06-02 | 2025-06-02 | 1 | 1 | 67 | 47 | 11 | 9 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | 182 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1312 | 236.04 | Unknown | 155.78 | Unknown | 920.18 | Unknown | 392.34 | 1312 | -919.66 | Yes | N/A | N/A | 2023-02-13 | 2023-02-15 | 3 | 3 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-03-31 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 196 | 141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-27 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -412.07 | -16.62 | Unknown | Unknown | -461 | 65.55 | 3981 | 1159.22 | -412.07 | 1571.29 | Yes | N/A | N/A | 2021-12-27 | 2023-06-14 | 535 | 383 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-06-14 | 1 | 1 | 535 | 383 | 1 | 1 | 536 | 384 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-27 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-29 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 2502.35 | 660.78 | Unknown | Unknown | Unknown | 1841.57 | Unknown | 5123.5 | 2502.35 | 2621.15 | Yes | N/A | N/A | 2024-10-11 | 2024-10-29 | 19 | 13 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-02-24 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-19 | 24 | 18 | 2025-03-19 | 2025-03-19 | 1 | 1 | 138 | 98 | 25 | 19 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.19 | -5.12 | Unknown | Unknown | Unknown | -1.07 | 3981 | 54726.99 | -6.19 | 54733.18 | Yes | N/A | N/A | 2023-05-01 | 2023-05-01 | 1 | 1 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-07-07 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 162 | 162 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-06 | -411 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2024-03-01 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 1709.11 | -36.52 | Unknown | Unknown | Unknown | 1745.63 | Unknown | 1045.8 | 1709.11 | -663.31 | Yes | N/A | N/A | 2023-11-08 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2024-03-01 | 225 | 161 | 2024-03-01 | Unknown | Unknown | Unknown | 2024-03-04 | 2024-05-01 | 59 | 43 | 2024-03-01 | 2024-05-07 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-21 | 15 | 11 | 2024-05-21 | 2024-05-21 | 1 | 1 | 68 | 48 | 300 | 216 | 368 | 264 | Steps 2,3,5,6,7 | 61 | 43 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 149.1 | -2.74 | Unknown | Unknown | Unknown | 151.84 | Unknown | 472.65 | 149.1 | 323.55 | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-08-15 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-08-06 | 44 | 32 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-08-27 | 1 | 1 | 1 | 1 | 109 | 79 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-09 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 1514.36 | 385.62 | Unknown | Unknown | Unknown | 1128.74 | 3981 | 1591.16 | 1514.36 | 76.8 | Yes | N/A | N/A | 2024-12-16 | 2025-01-09 | 25 | 19 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-02-26 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-04 | 7 | 5 | 2025-03-04 | 2025-03-04 | 1 | 1 | 74 | 54 | 9 | 7 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-08-01 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 1031.86 | Unknown | Unknown | Unknown | Unknown | 1031.86 | 3981 | 1106.45 | 1031.86 | 74.59 | Yes | N/A | N/A | 2024-04-29 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-08-01 | 119 | 85 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2025-01-13 | 166 | 118 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-01-13 | 2025-01-24 | 12 | 10 | 2025-01-24 | 2025-01-24 | 1 | 1 | 166 | 118 | 132 | 96 | 298 | 214 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 175 | 175 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | -375 | -270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2023-03-03 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 699.36 | 252.1 | Unknown | Unknown | Unknown | 447.26 | 3981 | 780.04 | 699.36 | 80.68 | Yes | N/A | N/A | 2022-11-22 | 2023-03-03 | 102 | 74 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-07-27 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-31 | 5 | 3 | 2023-07-31 | 2023-07-31 | 1 | 1 | 249 | 179 | 6 | 4 | 255 | 183 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 1345 | Unknown | Unknown | Unknown | 18.06 | 1326.94 | 3981 | 1376.75 | 1345 | 31.75 | Yes | N/A | N/A | 2024-10-01 | 2024-11-08 | 39 | 29 | 2024-11-08 | 2024-11-20 | 13 | 9 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-02-25 | 98 | 70 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-25 | 2025-03-10 | 14 | 10 | 2025-03-10 | 2025-03-07 | Unknown | Unknown | 137 | 99 | 27 | 19 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-08-30 | 2008 | 1435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8.98 | -6.5 | Unknown | Unknown | Unknown | -2.48 | Unknown | 744.77 | -8.98 | 753.75 | Yes | N/A | N/A | 2023-06-23 | 2023-06-28 | 6 | 4 | 2023-06-28 | 2023-07-19 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-02-28 | 1 | 1 | 6 | 4 | 23 | 17 | 29 | 21 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -247 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1588.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-08-05 | 110 | 78 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2025-05-19 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-13 | 26 | 20 | 2025-06-13 | 2025-06-13 | 1 | 1 | 288 | 206 | 137 | 99 | 425 | 305 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-27 | -38 | -29 | No | 2021-09-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-14 | 2021-09-14 | 2023-06-09 | IOU Designed & Installed | N/A | Yes | 545 | 1743.45 | 582.35 | Unknown | 200.48 | Unknown | 960.62 | 3981 | 1636.87 | 1743.45 | -106.58 | Yes | N/A | N/A | 2021-09-14 | 2023-03-13 | 546 | 390 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-09-14 | 2023-06-09 | Unknown | Unknown | Unknown | 2023-05-23 | Unknown | Unknown | 2023-06-09 | 2023-06-19 | 11 | 7 | 2023-06-19 | 2023-06-19 | 1 | 1 | 546 | 390 | 12 | 8 | 558 | 398 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | BONSALL | COUNTY OF SAN DIEGO-NORTH of 56 | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -233 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-09 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 11472.5 | 4029.38 | Unknown | Unknown | -8127 | 15570.12 | 3981 | 16503.74 | 11472.5 | 5031.24 | Yes | N/A | N/A | 2023-05-24 | 2023-05-31 | 8 | 6 | 2023-05-31 | 2023-07-10 | 41 | 29 | 2023-05-31 | 2023-12-14 | 2 | 2 | 2023-07-05 | 2023-08-17 | 34 | 20 | 2023-07-10 | 2024-01-30 | 205 | 147 | 2023-08-02 | 2023-12-21 | 142 | 102 | 2024-01-02 | 2024-01-17 | 16 | 12 | 2024-01-17 | 2024-02-01 | 16 | 12 | 215 | 155 | 249 | 175 | 464 | 330 | Steps 2,3,5,6,7 | 421 | 301 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 809.25 | 259.49 | Unknown | Unknown | Unknown | 549.76 | Unknown | 938.83 | 809.25 | 129.58 | Yes | N/A | N/A | 2024-04-25 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-04-25 | 88 | 64 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-19 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-16 | 28 | 20 | 2024-07-16 | 2024-07-16 | 1 | 1 | 56 | 40 | 117 | 85 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -452 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-22 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | 947.93 | Unknown | 947.93 | Yes | N/A | N/A | 2024-04-04 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-04-22 | 47 | 33 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-10-31 | 193 | 139 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-26 | 27 | 19 | 2024-11-26 | 2024-11-20 | Unknown | Unknown | 193 | 139 | 74 | 52 | 267 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 209.12 | 209.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-21 | 118 | 85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 390.89 | -17.87 | Unknown | Unknown | Unknown | 408.76 | Unknown | 844.2 | 390.89 | 453.31 | Yes | N/A | N/A | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | 2023-12-01 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-02-16 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 62.1 | 62.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -296 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-14 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 1147.22 | -12.97 | Unknown | Unknown | 6.83 | 1153.36 | 3981 | 1096.58 | 1147.22 | -50.64 | Yes | N/A | N/A | 2024-02-01 | 2024-02-14 | 14 | 10 | 2024-02-14 | 2024-03-08 | 24 | 18 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-04-29 | 53 | 37 | Unknown | 2024-04-26 | Unknown | Unknown | 2024-04-29 | 2024-05-13 | 15 | 11 | 2024-05-13 | 2024-05-09 | Unknown | Unknown | 67 | 47 | 39 | 29 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-18 | 460 | 329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 3340.34 | Unknown | Unknown | Unknown | Unknown | 3340.34 | 3981 | 1495.53 | 3340.34 | -1844.81 | Yes | N/A | N/A | 2024-02-09 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2024-02-09 | 173 | 125 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-04-01 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-25 | 25 | 19 | 2024-04-25 | 2024-04-22 | Unknown | Unknown | 41 | 29 | 198 | 144 | 239 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.57 | -0.31 | Unknown | Unknown | Unknown | 15.88 | Unknown | 1526.94 | 15.57 | 1511.37 | Yes | N/A | N/A | 2024-07-16 | 2024-08-01 | 17 | 13 | 2024-08-01 | 2024-08-12 | 12 | 8 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 17 | 13 | 13 | 9 | 30 | 22 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | -661 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-09 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1609 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-05-12 | 25 | 17 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-13 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-12 | 31 | 23 | 2025-06-12 | 2025-06-12 | 1 | 1 | 5 | 3 | 57 | 41 | 62 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-03-28 | 1552 | 1109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 17.22 | -12.86 | Unknown | Unknown | Unknown | 30.08 | 0 | 1052.1 | 17.22 | 1034.88 | Yes | N/A | N/A | 2023-07-11 | 2023-07-24 | 14 | 10 | 2023-07-24 | 2023-08-28 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-13 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-06-27 | 1 | 1 | 14 | 10 | 38 | 28 | 52 | 38 | Steps 2,3,5,6,7 | 259 | 185 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-07-01 | 1330 | 951 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 10683.1 | 2202.74 | Unknown | Unknown | -457.98 | 8938.34 | Unknown | 1209.21 | 10683.1 | -9473.89 | Yes | N/A | N/A | 2023-09-18 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-10-12 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-12-07 | 51 | 37 | 2023-10-12 | 2024-01-24 | 105 | 75 | Unknown | 2024-01-19 | Unknown | Unknown | 2024-01-25 | 2024-02-23 | 30 | 22 | 2024-02-23 | 2024-02-21 | Unknown | Unknown | 105 | 75 | 109 | 79 | 214 | 154 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 174 | 174 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 325 | 234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 604.92 | -11.3 | Unknown | Unknown | Unknown | 616.22 | 7962 | 1581.95 | 604.92 | 977.03 | Yes | N/A | N/A | 2023-07-26 | 2024-10-28 | 461 | 329 | 2024-10-28 | 2025-01-28 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-01-11 | 2025-01-31 | 21 | 15 | 2025-01-28 | 2025-02-20 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-20 | Unknown | Unknown | 485 | 347 | 114 | 82 | 599 | 429 | Steps 2,3,5,6,7 | 3 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -334 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 7.91 | Unknown | Unknown | Unknown | Unknown | 7.91 | Unknown | 499.14 | 7.91 | 491.23 | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-07 | 20 | 14 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2 | 2 | 21 | 15 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 282.15 | 282.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-04 | -359 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 748.12 | Unknown | Unknown | Unknown | Unknown | 748.12 | Unknown | 499.14 | 748.12 | -248.98 | Yes | N/A | N/A | 2024-12-04 | 2024-12-04 | 1 | 1 | 2024-12-04 | 2024-12-10 | 7 | 5 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-01-22 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-10 | 20 | 14 | 2025-02-10 | 2025-02-10 | 1 | 1 | 45 | 33 | 28 | 20 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -74 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 374.15 | 1168.76 | Unknown | 28.05 | -1376 | 553.34 | Unknown | 1376.02 | 374.15 | 1001.87 | Yes | N/A | N/A | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 364 | 261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | 2024-06-01 | IOU Designed & Installed | N/A | No | N/A | -1682.84 | 1910.88 | Unknown | Unknown | -4425 | 831.28 | Unknown | 4425.1 | -1682.84 | 6107.94 | Yes | N/A | N/A | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-05 | 2024-06-21 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-04 | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-01 | 2024-06-21 | 21 | 15 | 2024-06-21 | 2024-06-21 | 1 | 1 | 1 | 1 | 132 | 96 | 133 | 97 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | Both | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 102 | 73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-14 | 2022-03-14 | 2023-12-07 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 29565.71 | 4058.04 | Unknown | 74.73 | 192.73 | 25240.21 | 303200 | 58320.97 | 29565.71 | 28755.26 | Yes | N/A | N/A | 2022-03-14 | 2023-02-21 | 345 | 247 | 2023-02-21 | 2023-04-07 | 46 | 34 | 2023-02-27 | 2023-03-09 | 11 | 9 | 2023-04-07 | 2023-04-18 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2024-05-06 | 287 | 205 | 2023-12-07 | 2024-05-13 | 159 | 113 | 2024-05-13 | 2024-05-13 | 1 | 1 | 356 | 256 | 505 | 361 | 861 | 617 | Steps 2,3,5,6,7 | 190 | 136 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-25 | -227 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-18 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 22.86 | -6.4 | Unknown | Unknown | 22.65 | 6.61 | 3981 | 825.99 | 22.86 | 803.13 | Yes | N/A | N/A | 2023-08-10 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-18 | 10 | 8 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-08-29 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2024-10-10 | 409 | 293 | 2024-10-10 | 2024-10-10 | 1 | 1 | 12 | 8 | 420 | 302 | 432 | 310 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | 596 | 596 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | -167 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-22 | 2022-12-22 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | -1899.37 | 409.2 | Unknown | 19.7 | -9681 | 7352.73 | Unknown | 9408.53 | -1899.37 | 11307.9 | Yes | N/A | N/A | 2022-12-22 | 2023-04-05 | 105 | 75 | 2023-04-05 | 2023-10-06 | 185 | 133 | 2023-04-05 | 2023-04-12 | 8 | 6 | 2023-03-05 | 2024-06-21 | 137 | 100 | 2023-09-14 | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-10 | 27 | 19 | 2023-10-12 | 2023-10-30 | 19 | 13 | 2023-10-30 | 2023-10-30 | 1 | 1 | 113 | 81 | 369 | 266 | 482 | 347 | Steps 2,3,5,6,7 | 503 | 360 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Jamul | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-05 | 274 | 197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 87082.48 | 7357.95 | Unknown | Unknown | -12100.57 | 91825.1 | 1820 | 28008.97 | 87082.48 | -59073.51 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | 2024-06-28 | 152 | 110 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-29 | 2024-07-02 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-12-04 | 128 | 92 | 2024-12-04 | 2024-12-04 | 1 | 1 | 2 | 2 | 285 | 205 | 287 | 207 | Steps 2,3,5,6,7 | 15 | 11 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -408 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 21765.32 | 75.57 | Unknown | Unknown | 6.17 | 21683.58 | 3981 | 817.01 | 21765.32 | -20948.31 | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | 2024-11-26 | 188 | 134 | 2024-10-17 | 2024-10-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-02-11 | 72 | 52 | 2025-02-11 | 2025-01-16 | Unknown | Unknown | 2 | 2 | 260 | 186 | 262 | 188 | Steps 2,3,5,6,7 | 40 | 28 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -383 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 3113.97 | 763.73 | Unknown | 255.29 | Unknown | 2094.95 | 7962 | 1581.73 | 3113.97 | -1532.24 | Yes | N/A | N/A | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | 2024-06-06 | 120 | 86 | 2024-06-28 | 2024-07-01 | 4 | 2 | 2024-06-11 | 2024-07-24 | 42 | 32 | 2024-06-06 | 2024-10-14 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-16 | 2 | 2 | 2024-10-16 | 2024-10-16 | 1 | 1 | 136 | 96 | 165 | 121 | 301 | 217 | Steps 2,3,5,6,7 | 68 | 48 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | 390 | 279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1193.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-22 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2025-05-07 | 687 | 491 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 0 | 0 | 688 | 492 | 688 | 492 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-07-10 | 34 | 25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 1431.54 | 300.29 | Unknown | Unknown | -9438.81 | 10570.06 | 3981 | 13044.64 | 1431.54 | 11613.1 | Yes | N/A | N/A | 2023-07-10 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-09-06 | 120 | 86 | 2023-08-29 | 2023-08-31 | 3 | 3 | 2023-09-05 | 2023-09-06 | 2 | 2 | 2023-09-06 | 2024-07-23 | 322 | 230 | 2024-01-25 | 2024-07-18 | 176 | 126 | 2024-11-06 | 2024-11-06 | 1 | 1 | 2024-11-06 | 2024-08-13 | Unknown | Unknown | 325 | 233 | 299 | 215 | 624 | 448 | Steps 2,3,5,6,7 | 188 | 134 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | -873 | -625 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-17 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1969.35 | 502.72 | Unknown | 260.39 | Unknown | 1206.24 | 3981 | 1529.49 | 1969.35 | -439.86 | Yes | N/A | N/A | 2024-07-12 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-07-17 | 56 | 40 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-10-18 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-21 | 4 | 2 | 2024-10-21 | 2024-10-21 | 1 | 1 | 94 | 68 | 61 | 43 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-15 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-16 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 1417.97 | 380.61 | Unknown | Unknown | 51.18 | 986.18 | 3981 | 896.8 | 1417.97 | -521.17 | Yes | N/A | N/A | 2023-10-16 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-10-16 | 76 | 54 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-12-09 | 421 | 301 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-08-27 | 262 | 188 | 2025-08-27 | 2024-12-10 | Unknown | Unknown | 421 | 301 | 338 | 242 | 759 | 543 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -220 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1383.24 | -15.44 | Unknown | Unknown | -1378 | 10.2 | 3981 | 1486.89 | -1383.24 | 2870.13 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -73 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 852.82 | Unknown | Unknown | Unknown | 3.77 | 849.05 | 3981 | 657.09 | 852.82 | -195.73 | Yes | N/A | N/A | 2023-04-11 | 2023-04-11 | 1 | 1 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-03 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-06 | 1031 | 738 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 6760.07 | 1309.22 | Unknown | 380.4 | 240.79 | 4829.66 | 1786 | 283.56 | 6760.07 | -6476.51 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | 2023-02-17 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2025-03-03 | 746 | 532 | Unknown | 2025-03-17 | Unknown | Unknown | 2025-03-24 | 2025-04-07 | 15 | 11 | 2025-04-07 | 2025-04-02 | Unknown | Unknown | 747 | 533 | 19 | 15 | 766 | 548 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | -150 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 302.55 | -13 | Unknown | Unknown | Unknown | 315.55 | 3981 | 403.01 | 302.55 | 100.46 | Yes | N/A | N/A | 2024-01-09 | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-01-23 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-03-12 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-03-28 | Unknown | Unknown | 50 | 36 | 19 | 13 | 69 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-20 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 648.27 | -13.25 | Unknown | Unknown | Unknown | 661.52 | Unknown | 1893.74 | 648.27 | 1245.47 | Yes | N/A | N/A | 2024-12-05 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-05 | 3 | 3 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-02 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-11 | 41 | 29 | 2025-02-11 | 2025-02-11 | 1 | 1 | 29 | 21 | 45 | 33 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 256 | 183 | No | 2023-02-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-05-15 | IOU Designed & Installed | N/A | Yes | 42 | 2437.14 | 252.1 | Unknown | 89.36 | 14.05 | 2081.63 | 3241 | 678.41 | 2437.14 | -1758.73 | Yes | N/A | N/A | 2023-02-15 | 2023-04-10 | 55 | 39 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-05-15 | 76 | 54 | Unknown | 2023-05-01 | Unknown | Unknown | 2023-05-15 | 2023-05-16 | 2 | 2 | 2023-05-16 | 2023-05-16 | 1 | 1 | 131 | 93 | 3 | 3 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-21 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 299.52 | -9.56 | Unknown | Unknown | Unknown | 309.08 | Unknown | 821.48 | 299.52 | 521.96 | Yes | N/A | N/A | 2024-02-29 | 2024-04-02 | 34 | 24 | 2024-04-02 | 2024-04-09 | 8 | 6 | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-29 | 21 | 15 | Unknown | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-05-20 | 22 | 16 | 2024-05-20 | 2024-05-20 | 1 | 1 | 55 | 39 | 31 | 23 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 1457.38 | Unknown | Unknown | Unknown | 6.43 | 1450.95 | 3981 | 1060.43 | 1457.38 | -396.95 | Yes | N/A | N/A | 2025-03-05 | 2025-03-10 | 6 | 4 | 2025-03-10 | 2025-03-20 | 11 | 9 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-05-02 | 44 | 32 | Unknown | 2025-04-25 | Unknown | Unknown | 2025-05-02 | 2025-05-16 | 15 | 11 | 2025-05-16 | 2025-05-15 | Unknown | Unknown | 50 | 36 | 26 | 20 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | 32 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | 8.59 | Unknown | Unknown | Unknown | Unknown | 8.59 | 0 | 154.99 | 8.59 | 146.4 | Yes | N/A | N/A | 2023-09-19 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-11-21 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-08-26 | 280 | 200 | 2024-08-26 | 2024-08-26 | 1 | 1 | 55 | 39 | 282 | 202 | 337 | 241 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | -59 | -44 | No | 2022-08-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | Unknown | IOU Designed & Installed | N/A | Yes | 395 | 1430.91 | -10.83 | Unknown | Unknown | 10.69 | 1431.05 | 3885 | 1037.56 | 1430.91 | -393.35 | Yes | N/A | N/A | 2022-08-12 | 2023-09-11 | 396 | 282 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-29 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | 396 | 282 | 2 | 2 | 398 | 284 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1339.05 | 1339.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-11-21 | -607 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-16 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3885 | 2807.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2025-01-16 | 30 | 22 | 2025-01-16 | 2025-02-10 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-03-12 | 55 | 39 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-03-12 | 2025-03-24 | 13 | 9 | 2025-03-24 | 2025-03-24 | 1 | 1 | 81 | 57 | 44 | 32 | 125 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 373.47 | 126.23 | Unknown | Unknown | Unknown | 247.24 | Unknown | 911.14 | 373.47 | 537.67 | Yes | N/A | N/A | 2024-02-08 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-02-08 | 133 | 95 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-03-14 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-04-04 | 22 | 16 | 2024-04-04 | 2024-04-04 | 1 | 1 | 36 | 26 | 156 | 112 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 107.2 | 107.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -610 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 53.94 | -14.81 | Unknown | Unknown | Unknown | 68.75 | 3981 | 880.79 | 53.94 | 826.85 | Yes | N/A | N/A | 2023-06-26 | 2023-06-29 | 4 | 4 | 2023-06-29 | 2023-07-05 | 7 | 5 | 2023-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2023-10-10 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-13 | 4 | 4 | 2023-10-13 | 2023-10-13 | 1 | 1 | 102 | 74 | 12 | 10 | 114 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | -116 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.7 | -6.48 | Unknown | Unknown | Unknown | -1.22 | Unknown | 98.41 | -7.7 | 106.11 | Yes | N/A | N/A | 2023-02-28 | 2023-03-20 | 21 | 15 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | -9.82 | -7.96 | Unknown | Unknown | Unknown | -1.86 | 3941 | 835.93 | -9.82 | 845.75 | Yes | N/A | N/A | 2023-12-01 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2023-12-01 | 30 | 22 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-02-02 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-15 | 43 | 31 | 2024-03-15 | 2024-03-15 | 1 | 1 | 64 | 46 | 74 | 54 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | -10.32 | -7.57 | Unknown | Unknown | Unknown | -2.75 | Unknown | 514.57 | -10.32 | 524.89 | Yes | N/A | N/A | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-11-09 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-13 | 5 | 3 | 2023-11-13 | 2023-11-13 | 1 | 1 | 32 | 24 | 7 | 5 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-10 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.31 | -3.95 | Unknown | Unknown | Unknown | -0.36 | Unknown | 98.41 | -4.31 | 102.72 | Yes | N/A | N/A | 2023-01-23 | 2023-02-07 | 16 | 12 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | 81 | 58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-03-04 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3071.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-03-03 | 33 | 23 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-04-08 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-23 | 16 | 12 | 2025-04-23 | 2025-04-23 | 1 | 1 | 36 | 26 | 50 | 36 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 2069.15 | -41.56 | Unknown | Unknown | Unknown | 2110.71 | 3981 | 1865.22 | 2069.15 | -203.93 | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-13 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-04-16 | 63 | 45 | 2025-04-16 | 2025-04-16 | 1 | 1 | 5 | 5 | 65 | 47 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -16.04 | -12.79 | Unknown | Unknown | Unknown | -3.25 | 3981 | 158.79 | -16.04 | 174.83 | Yes | N/A | N/A | 2023-11-08 | 2024-01-08 | 62 | 44 | 2024-01-08 | 2024-01-11 | 4 | 4 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 62 | 44 | 5 | 5 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -437 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.43 | -5.19 | Unknown | Unknown | Unknown | 5.62 | 3981 | 883.5 | 0.43 | 883.07 | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | 2023-09-28 | 186 | 134 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2023-11-29 | Unknown | Unknown | 1 | 1 | 186 | 134 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | 299 | 214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 501.23 | -37.58 | Unknown | Unknown | Unknown | 538.81 | 3941 | 865.86 | 501.23 | 364.63 | Yes | N/A | N/A | 2024-03-19 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-19 | 42 | 30 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2025-03-03 | 350 | 250 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-03 | 32 | 24 | 2025-04-03 | 2025-03-10 | Unknown | Unknown | 350 | 250 | 74 | 54 | 424 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Laguna Niguel | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | -336 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2023-06-18 | IOU Designed & Installed | N/A | No | N/A | 157.61 | 702.75 | Unknown | 168.32 | -2269 | 1555.54 | Unknown | 2268.86 | 157.61 | 2111.25 | Yes | N/A | N/A | 2023-05-25 | 2023-05-25 | 1 | 1 | 2023-05-25 | 2023-06-15 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-18 | 2023-06-21 | 4 | 3 | 2023-06-21 | 2023-06-21 | 1 | 1 | 1 | 1 | 28 | 21 | 29 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-30 | 2022-06-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11489.93 | Unknown | Unknown | Unknown | -908 | 12397.93 | 0 | 1647.8 | 11489.93 | -9842.13 | Yes | N/A | N/A | 2022-06-30 | 2023-02-08 | 224 | 160 | 2023-02-08 | 2023-03-23 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-02-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-07-17 | Unknown | Unknown | 224 | 160 | 59 | 43 | 283 | 203 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | PALOMAR MT | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-29 | -346 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-05-26 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 44850.51 | 6856.25 | Unknown | Unknown | -11284.56 | 49278.82 | 6768 | 26507.48 | 44850.51 | -18343.03 | Yes | N/A | N/A | 2023-04-20 | 2023-05-24 | 35 | 25 | 2023-05-24 | 2023-12-04 | 195 | 139 | 2023-08-31 | 2023-09-06 | 7 | 5 | 2023-08-02 | 2023-09-11 | 5 | 3 | 2023-12-04 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-01-22 | 48 | 34 | 2024-01-22 | 2024-01-18 | Unknown | Unknown | 42 | 30 | 248 | 176 | 290 | 206 | Steps 2,3,5,6,7 | 130 | 92 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.2 | 16.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-10 | 365 | 262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 3699.28 | -14.99 | Unknown | Unknown | 117.94 | 3596.33 | 7962 | 565.55 | 3699.28 | -3133.73 | Yes | N/A | N/A | 2023-04-05 | 2023-06-01 | 58 | 42 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-10-05 | 127 | 91 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-10-05 | 2023-10-10 | 6 | 4 | 2023-10-10 | 2023-10-10 | 1 | 1 | 185 | 133 | 7 | 5 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -259 | -186 | No | 2025-01-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-27 | 2025-04-17 | IOU Designed & Installed | N/A | Yes | 47 | 1423.73 | Unknown | Unknown | Unknown | 5.71 | 1418.02 | 3981 | 1210 | 1423.73 | -213.73 | Yes | N/A | N/A | 2025-01-15 | 2025-03-03 | 48 | 34 | 2025-03-03 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-04-17 | 81 | 59 | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-17 | 2025-04-24 | 8 | 6 | 2025-04-24 | 2025-04-24 | 1 | 1 | 129 | 93 | 9 | 7 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-22 | 2024-03-22 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 1895.98 | Unknown | Unknown | Unknown | Unknown | 1895.98 | Unknown | 828.21 | 1895.98 | -1067.77 | Yes | N/A | N/A | 2024-03-22 | 2024-03-22 | 1 | 1 | 2024-03-22 | 2024-05-24 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-05-29 | 14 | 10 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-21 | 15 | 11 | 2024-06-21 | 2024-06-21 | 1 | 1 | 1 | 1 | 94 | 68 | 95 | 69 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 128.05 | 128.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-22 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2343.95 | Unknown | Unknown | Unknown | 7.8 | 2336.15 | 3981 | 1207.66 | 2343.95 | -1136.29 | Yes | N/A | N/A | 2025-01-07 | 2025-01-28 | 22 | 16 | 2025-01-28 | 2025-01-30 | 3 | 3 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 22 | 16 | 4 | 4 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-06-12 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 3027.49 | 728.49 | Unknown | Unknown | 89.01 | 2209.99 | Unknown | 1466.58 | 3027.49 | -1560.91 | Yes | N/A | N/A | 2024-04-15 | 2024-06-12 | 59 | 43 | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2025-02-28 | 262 | 188 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-18 | 19 | 13 | 2025-03-18 | 2025-03-17 | Unknown | Unknown | 321 | 231 | 20 | 14 | 341 | 245 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 345 | 345 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | -570 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-11-06 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | -11.3 | -8.54 | Unknown | Unknown | Unknown | -2.76 | 3241 | 1165.8 | -11.3 | 1177.1 | Yes | N/A | N/A | 2023-10-09 | 2023-11-06 | 29 | 21 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-12-06 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-20 | 15 | 11 | 2023-12-20 | 2023-12-20 | 1 | 1 | 60 | 44 | 17 | 13 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-16 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 493.42 | -19.05 | Unknown | Unknown | Unknown | 512.47 | 3981 | 1508.07 | 493.42 | 1014.65 | Yes | N/A | N/A | 2023-06-23 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-23 | 2 | 2 | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-07-25 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | 2023-07-25 | 1 | 1 | 33 | 23 | 4 | 4 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1063.48 | -15.19 | Unknown | Unknown | -1076 | 27.71 | 3981 | 1536.96 | -1063.48 | 2600.44 | Yes | N/A | N/A | 2023-07-13 | 2023-08-07 | 26 | 18 | 2023-08-07 | 2023-08-08 | 2 | 2 | 2023-08-08 | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-15 | Unknown | Unknown | 26 | 18 | 2 | 2 | 28 | 20 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -672 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-28 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1714.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-02-28 | 18 | 14 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-19 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-21 | 3 | 3 | 2025-03-21 | 2025-03-21 | 1 | 1 | 21 | 15 | 22 | 18 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-23 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 218.39 | -9.62 | Unknown | Unknown | Unknown | 228.01 | 3981 | 1191.09 | 218.39 | 972.7 | Yes | N/A | N/A | 2024-04-17 | 2024-04-22 | 6 | 4 | 2024-04-22 | 2024-04-24 | 3 | 3 | 2024-04-24 | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-31 | 38 | 28 | 2024-04-24 | 2024-06-04 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-28 | 25 | 19 | 2024-06-28 | 2024-06-28 | 1 | 1 | 48 | 34 | 67 | 51 | 115 | 85 | Steps 2,3,5,6,7 | 37 | 27 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-04 | -69 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 16135.09 | 570.76 | Unknown | 48.45 | Unknown | 15515.88 | Unknown | 2029.65 | 16135.09 | -14105.44 | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-24 | 33 | 23 | 2025-02-24 | 2025-02-24 | 1 | 1 | 1 | 1 | 34 | 24 | 35 | 25 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | -682 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | -28.62 | -20.31 | Unknown | Unknown | Unknown | -8.31 | 3981 | 1293.37 | -28.62 | 1321.99 | Yes | N/A | N/A | 2024-05-21 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-05-30 | 32 | 24 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-12 | 8 | 6 | 2024-06-12 | 2024-06-12 | 1 | 1 | 7 | 5 | 41 | 31 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -662 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 1232.22 | -24.15 | Unknown | Unknown | Unknown | 1256.37 | 3981 | 1714.97 | 1232.22 | 482.75 | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-03 | 2025-01-08 | 37 | 27 | 2024-12-03 | 2025-01-10 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-28 | 19 | 13 | 2025-01-28 | 2025-01-28 | 1 | 1 | 40 | 30 | 58 | 42 | 98 | 72 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -417 | -298 | No | 2024-02-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2024-09-03 | IOU Designed & Installed | N/A | Yes | 4 | 2349.78 | 253.74 | Unknown | Unknown | 44.86 | 2051.18 | 3981 | 1568.4 | 2349.78 | -781.38 | Yes | N/A | N/A | 2024-02-26 | 2024-03-01 | 5 | 5 | 2024-03-01 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-09-03 | 188 | 134 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-18 | 16 | 12 | 2024-09-18 | 2024-09-18 | 1 | 1 | 193 | 139 | 17 | 13 | 210 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-18 | -32 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 20.91 | -16.13 | Unknown | Unknown | Unknown | 37.04 | Unknown | 1372.06 | 20.91 | 1351.15 | Yes | N/A | N/A | 2024-05-24 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-05-24 | 137 | 99 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-17 | 42 | 30 | 2024-07-17 | 2024-07-17 | 1 | 1 | 14 | 10 | 180 | 130 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -330 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-16 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 1369.22 | 447.25 | Unknown | 55.15 | Unknown | 866.82 | 0 | 651.6 | 1369.22 | -717.62 | Yes | N/A | N/A | 2024-02-14 | 2023-02-14 | Unknown | Unknown | 2023-02-14 | 2024-02-16 | 368 | 264 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-02-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-07 | 16 | 12 | 2024-03-07 | 2024-03-07 | 1 | 1 | 6 | 4 | 385 | 277 | 391 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -100 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 12.06 | Unknown | Unknown | Unknown | Unknown | 12.06 | 7962 | 2096.26 | 12.06 | 2084.2 | Yes | N/A | N/A | 2024-08-27 | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-11-05 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-01-23 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-11-14 | 70 | 50 | 2024-11-14 | 2025-01-27 | 75 | 53 | 80 | 58 | 249 | 177 | 329 | 235 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 143 | 102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 429.01 | 2421.06 | Unknown | 509.59 | -3527 | 1025.36 | 0 | 3526.84 | 429.01 | 3097.83 | Yes | N/A | N/A | 2023-03-31 | 2023-04-06 | 7 | 5 | 2023-04-06 | 2023-04-17 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 7 | 5 | 13 | 9 | 20 | 14 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 68.75 | Unknown | Unknown | Unknown | Unknown | 68.75 | 3981 | 1951.15 | 68.75 | 1882.4 | Yes | N/A | N/A | 2024-12-18 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-18 | 2 | 2 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-02-04 | 49 | 35 | 2025-02-04 | 2025-02-04 | 1 | 1 | 1 | 1 | 52 | 38 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11.5 | 11.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-23 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | -11.72 | -9.51 | Unknown | Unknown | Unknown | -2.21 | 3961 | 400.91 | -11.72 | 412.63 | Yes | N/A | N/A | 2024-01-12 | 2024-02-23 | 43 | 31 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-11 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-25 | 15 | 11 | 2024-03-25 | 2024-03-25 | 1 | 1 | 61 | 43 | 17 | 13 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 113.4 | 113.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-25 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.42 | -11.26 | Unknown | Unknown | Unknown | 24.68 | 3981 | 939.02 | 13.42 | 925.6 | Yes | N/A | N/A | 2024-04-17 | 2024-05-02 | 16 | 12 | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-10 | 1 | 1 | 16 | 12 | 2 | 2 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 6604.45 | 966.72 | Unknown | 963.43 | 20.16 | 4654.14 | 1192.8 | 603.96 | 6604.45 | -6000.49 | Yes | N/A | N/A | 2024-03-12 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-08-02 | 50 | 36 | Unknown | 2024-07-23 | Unknown | Unknown | 2024-08-02 | 2024-08-26 | 25 | 17 | 2024-08-26 | 2024-09-18 | 24 | 18 | 50 | 36 | 50 | 36 | 100 | 72 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -429 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-06 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 722.76 | 196.92 | Unknown | Unknown | Unknown | 525.84 | Unknown | 1716.42 | 722.76 | 993.66 | Yes | N/A | N/A | 2024-05-02 | 2024-05-06 | 5 | 3 | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-12-13 | 222 | 160 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-19 | 7 | 5 | 2024-12-19 | 2024-12-19 | 1 | 1 | 227 | 163 | 9 | 7 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | -696 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 46.63 | -0.94 | Unknown | Unknown | Unknown | 47.57 | 3981 | 1171.4 | 46.63 | 1124.77 | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-21 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-02 | 13 | 9 | 2025-06-02 | 2025-06-02 | 1 | 1 | 14 | 10 | 15 | 11 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-08-02 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 840.44 | -17.3 | Unknown | Unknown | Unknown | 857.74 | 3981 | 2107.04 | 840.44 | 1266.6 | Yes | N/A | N/A | 2024-07-09 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-08-02 | 61 | 45 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-09-24 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-05-28 | 247 | 177 | 2025-05-28 | 2025-05-28 | 1 | 1 | 54 | 38 | 309 | 223 | 363 | 261 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-10 | 51 | 38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 1695.19 | 443.47 | Unknown | Unknown | Unknown | 1251.72 | 3981 | 1070.06 | 1695.19 | -625.13 | Yes | N/A | N/A | 2023-05-09 | 2023-05-09 | 1 | 1 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2025-01-23 | 626 | 448 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-01-30 | 8 | 6 | 2025-01-30 | 2025-01-30 | 1 | 1 | 627 | 449 | 9 | 7 | 636 | 456 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | 9 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 657.76 | -7.9 | Unknown | Unknown | 11.44 | 654.22 | 3981 | 676.1 | 657.76 | 18.34 | Yes | N/A | N/A | 2023-02-02 | 2023-05-15 | 103 | 73 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-08-24 | 105 | 75 | Unknown | 2023-08-19 | Unknown | Unknown | 2023-08-24 | 2023-09-05 | 13 | 9 | 2023-09-05 | 2023-11-09 | 66 | 48 | 208 | 148 | 79 | 57 | 287 | 205 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-07 | -23 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8841.72 | 1153.68 | Unknown | 47.32 | -10618 | 575.28 | 0 | 5309.25 | -8841.72 | 14150.97 | Yes | N/A | N/A | 2023-08-23 | 2023-08-28 | 6 | 4 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 6 | 4 | 1 | 1 | 7 | 5 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -331 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 45424.23 | 9878.03 | Unknown | 2130.2 | 6.67 | 33409.33 | Unknown | 25394.77 | 45424.23 | -20029.46 | Yes | N/A | N/A | 2024-07-02 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-11-12 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-28 | 13 | 9 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-13 | 29 | 21 | 2024-12-13 | 2024-12-13 | 1 | 1 | 0 | 0 | 217 | 155 | 217 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 696.25 | -13.2 | Unknown | Unknown | Unknown | 709.45 | 3981 | 1682.54 | 696.25 | 986.29 | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-02-20 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-10 | 19 | 13 | 2025-03-10 | 2025-03-10 | 1 | 1 | 64 | 46 | 21 | 15 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 51.48 | Unknown | Unknown | Unknown | Unknown | 51.48 | 3981 | 1935.27 | 51.48 | 1883.79 | Yes | N/A | N/A | 2025-03-06 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-03-26 | 35 | 25 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-11 | 11 | 9 | 2025-04-11 | 2025-04-11 | 1 | 1 | 7 | 5 | 47 | 35 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -256 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-08-13 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 23.04 | Unknown | Unknown | Unknown | Unknown | 23.04 | 3981 | 1468.28 | 23.04 | 1445.24 | Yes | N/A | N/A | 2024-02-28 | 2024-09-04 | 190 | 136 | 2024-09-04 | 2024-10-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-21 | 6 | 4 | 2024-10-21 | 2024-10-18 | Unknown | Unknown | 190 | 136 | 49 | 35 | 239 | 171 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 163 | 163 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-17 | 269 | 194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 2062.85 | 406.84 | Unknown | Unknown | 43.98 | 1612.03 | 3981 | 1475.24 | 2062.85 | -587.61 | Yes | N/A | N/A | 2023-05-04 | 2023-08-29 | 118 | 84 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2024-01-09 | 134 | 96 | Unknown | 2023-12-05 | Unknown | Unknown | 2024-01-09 | 2024-01-11 | 3 | 3 | 2024-01-11 | 2024-01-11 | 1 | 1 | 252 | 180 | 4 | 4 | 256 | 184 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 170 | 170 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -321 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 525.69 | -22.59 | Unknown | Unknown | Unknown | 548.28 | 7962 | 1108.33 | 525.69 | 582.64 | Yes | N/A | N/A | 2023-10-04 | 2023-11-10 | 38 | 28 | 2023-11-10 | 2024-02-22 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-04-16 | 65 | 47 | 2024-02-22 | 2024-02-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-11 | Unknown | Unknown | 44 | 32 | 170 | 122 | 214 | 154 | Steps 2,3,5,6,7 | 54 | 38 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1108.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-28 | 21 | 15 | 2025-01-28 | 2025-06-16 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-06-10 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-27 | 18 | 14 | 2025-06-27 | 2025-06-27 | 1 | 1 | 274 | 196 | 40 | 30 | 314 | 226 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 268 | 191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-12-02 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | -1155.89 | -8.13 | Unknown | Unknown | -1600 | 452.24 | Unknown | 1180.7 | -1155.89 | 2336.59 | Yes | N/A | N/A | 2024-11-26 | 2024-12-02 | 7 | 5 | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2025-01-22 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-21 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-25 | 5 | 3 | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 90 | 66 | 6 | 4 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 211031 | 211031 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-02 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-10-10 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | 13238.56 | -293.48 | Unknown | Unknown | Unknown | 13532.04 | Unknown | 558.52 | 13238.56 | -12680.04 | Yes | N/A | N/A | 2023-09-20 | 2023-12-18 | 90 | 64 | 2023-12-18 | 2023-12-28 | 11 | 9 | 2023-11-01 | 2023-11-03 | 3 | 3 | 2023-10-31 | 2023-11-10 | 10 | 8 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-25 | 16 | 12 | 2024-01-25 | 2024-01-25 | 1 | 1 | 93 | 67 | 38 | 30 | 131 | 97 | Steps 2,3,5,6,7 | 60 | 44 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | 28 | 21 | No | 2024-05-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-07 | 2024-11-06 | IOU Designed & Installed | N/A | Yes | 59 | 1005.96 | -20.4 | Unknown | Unknown | Unknown | 1026.36 | 3241 | 966.14 | 1005.96 | -39.82 | Yes | N/A | N/A | 2024-05-06 | 2024-07-05 | 61 | 45 | 2024-07-05 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-11-06 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-12-17 | 42 | 30 | 2024-12-17 | 2025-02-13 | 59 | 43 | 245 | 177 | 101 | 73 | 346 | 250 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | RAMONA | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-11 | 71 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-09-19 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 6056.26 | 2375.11 | Unknown | 93.73 | 2.25 | 3585.17 | Unknown | 14036.85 | 6056.26 | 7980.59 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | 2024-11-21 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | 56249.41 | 11888.23 | Unknown | Unknown | 136.05 | 44225.13 | 428575.6 | 42861.39 | 56249.41 | -13388.02 | Yes | N/A | N/A | 2023-04-18 | 2023-04-19 | 2 | 2 | 2023-04-19 | 2023-04-24 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-05-04 | 15 | 11 | 2023-04-24 | 2958465 | Unknown | Unknown | Unknown | 2023-08-03 | Unknown | Unknown | 2023-08-08 | 2023-09-06 | 30 | 22 | 2023-09-06 | 2023-09-01 | Unknown | Unknown | 2 | 2 | 51 | 37 | 53 | 39 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | BOULEVARD | COUNTY OF SAN DIEGO-SOUTH of 56 | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | 468 | 335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 22909.91 | 27639.56 | Unknown | Unknown | -64948 | 60218.35 | 5801 | 131157.01 | 22909.91 | 108247.1 | Yes | N/A | N/A | 2023-08-22 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-18 | 1 | 1 | 2023-11-06 | 2025-05-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | Steps 2,3,5,6,7 | 529 | 379 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 10.57 | -9.38 | Unknown | Unknown | Unknown | 19.95 | 3941 | 1369.94 | 10.57 | 1359.37 | Yes | N/A | N/A | 2024-05-23 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-23 | 43 | 31 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-05-23 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-11 | 20 | 14 | 2024-06-11 | 2024-06-11 | 1 | 1 | 1 | 1 | 64 | 46 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | Imperial Beach | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-26 | 253 | 182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 1388.37 | -26.87 | Unknown | Unknown | Unknown | 1415.24 | 3981 | 1063.34 | 1388.37 | -325.03 | Yes | N/A | N/A | 2024-04-10 | 2024-04-11 | 2 | 2 | 2024-04-11 | 2024-04-23 | 13 | 9 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-05 | 42 | 30 | 2024-04-23 | 2024-10-22 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-12-04 | 44 | 32 | 2024-12-04 | 2024-12-04 | 1 | 1 | 185 | 133 | 100 | 72 | 285 | 205 | Steps 2,3,5,6,7 | 43 | 31 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.22 | -4.95 | Unknown | Unknown | Unknown | 3.73 | 3981 | 1890.87 | -1.22 | 1892.09 | Yes | N/A | N/A | 2024-04-11 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-04-11 | 73 | 53 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-09 | Unknown | Unknown | 0 | 0 | 73 | 53 | 73 | 53 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-29 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-30 | 2023-12-01 | IOU Designed & Installed | N/A | No | N/A | 295.62 | -9.16 | Unknown | Unknown | Unknown | 304.78 | 3981 | 772.57 | 295.62 | 476.95 | Yes | N/A | N/A | 2023-11-15 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-11-30 | 143 | 103 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-12 | 12 | 8 | 2023-12-12 | 2023-12-12 | 1 | 1 | 2 | 2 | 156 | 112 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 218.3 | 218.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-19 | 16 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 742.72 | -9.07 | Unknown | Unknown | 23.98 | 727.81 | 7962 | 310.94 | 742.72 | -431.78 | Yes | N/A | N/A | 2023-02-08 | 2023-02-03 | Unknown | Unknown | 2023-02-03 | 2023-02-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-03 | 2 | 2 | 2023-02-17 | 2023-07-27 | 161 | 115 | Unknown | 2023-07-26 | Unknown | Unknown | 2023-08-01 | 2023-10-16 | 77 | 55 | 2023-10-16 | 2023-08-04 | Unknown | Unknown | 161 | 115 | 94 | 68 | 255 | 183 | Steps 2,3,5,6,7 | 75 | 53 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 3426.03 | 665.33 | Unknown | Unknown | 5.3 | 2755.4 | 3941 | 2141.19 | 3426.03 | -1284.84 | Yes | N/A | N/A | 2024-04-23 | 2024-05-23 | 31 | 23 | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-29 | 12 | 8 | Unknown | 2024-07-19 | Unknown | Unknown | 2024-07-29 | 2024-08-20 | 23 | 17 | 2024-08-20 | 2024-08-20 | 1 | 1 | 43 | 31 | 25 | 19 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 644.38 | Unknown | Unknown | Unknown | -1370.76 | 2015.14 | Unknown | 1224.42 | 644.38 | 580.04 | Yes | N/A | N/A | 2025-01-08 | 2025-02-03 | 27 | 19 | 2025-02-03 | 2025-02-07 | 5 | 5 | 2025-02-07 | 2025-02-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-04-02 | 49 | 35 | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-02 | 2025-04-08 | 7 | 5 | 2025-04-08 | 2025-04-08 | 1 | 1 | 83 | 59 | 13 | 11 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 1106.93 | 246.68 | Unknown | Unknown | -923.1 | 1783.35 | Unknown | 941.61 | 1106.93 | -165.32 | Yes | N/A | N/A | 2024-03-18 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-03-26 | 103 | 73 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-06-04 | 50 | 36 | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-07 | 4 | 4 | 2024-06-07 | 2024-06-07 | 1 | 1 | 50 | 36 | 108 | 78 | 158 | 114 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -669 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-10-06 | IOU Designed & Installed | N/A | No | N/A | 892.51 | -4.27 | Unknown | Unknown | Unknown | 896.78 | 3291 | 494.56 | 892.51 | -397.95 | Yes | N/A | N/A | 2023-09-06 | 2023-09-11 | 6 | 4 | 2023-09-11 | 2023-10-06 | 26 | 20 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-09 | 4 | 2 | 2023-10-09 | 2023-10-09 | 1 | 1 | 7 | 5 | 31 | 23 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -363 | -260 | No | 2024-07-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2025-04-23 | IOU Designed & Installed | N/A | Yes | 126 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1502.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2025-03-21 | 236 | 170 | 2025-03-21 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2025-04-23 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-12 | 51 | 37 | 2025-06-12 | 2025-06-12 | 1 | 1 | 504 | 362 | 52 | 38 | 556 | 400 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-18 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 3.95 | -4.76 | Unknown | Unknown | Unknown | 8.71 | Unknown | 374.43 | 3.95 | 370.48 | Yes | N/A | N/A | 2024-01-02 | 2024-01-02 | 1 | 1 | 2024-01-02 | 2024-01-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-03-04 | 61 | 43 | 2024-03-04 | 2024-03-04 | 1 | 1 | 1 | 1 | 63 | 45 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | 3 | 3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 8524.61 | Unknown | Unknown | Unknown | 181.95 | 8342.66 | 3981 | 698.35 | 8524.61 | -7826.26 | Yes | N/A | N/A | 2023-08-22 | 2023-05-01 | Unknown | Unknown | 2023-05-01 | 2025-03-26 | 696 | 498 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | 2025-03-27 | 2025-04-23 | 28 | 20 | 2025-04-23 | 2025-04-23 | 1 | 1 | 0 | 0 | 725 | 519 | 725 | 519 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | -113 | -82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5805.06 | 398.89 | Unknown | 38.11 | -8865 | 2622.94 | Unknown | 5597.21 | -5805.06 | 11402.27 | Yes | N/A | N/A | 2023-08-09 | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2023-11-08 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-01-26 | 80 | 58 | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 80 | 58 | 95 | 69 | 175 | 127 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -402 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 3570.61 | -50.99 | Unknown | Unknown | Unknown | 3621.6 | Unknown | 477.13 | 3570.61 | -3093.48 | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-28 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-20 | 24 | 18 | 2024-11-20 | 2024-11-20 | 1 | 1 | 12 | 8 | 26 | 20 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 23.05 | 23.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 381.83 | Unknown | Unknown | Unknown | 4.14 | 377.69 | 3981 | 1158.77 | 381.83 | 776.94 | Yes | N/A | N/A | 2024-10-01 | 2024-09-16 | Unknown | Unknown | 2024-09-16 | 2024-10-10 | 25 | 19 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-12-02 | 54 | 38 | Unknown | 2024-11-26 | Unknown | Unknown | 2024-12-02 | 2024-12-19 | 18 | 14 | 2024-12-19 | 2024-12-19 | 1 | 1 | 54 | 38 | 44 | 34 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-17 | 272 | 195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4594.38 | 1374.12 | Unknown | 37.27 | -6619 | 613.23 | Unknown | 6619.37 | -4594.38 | 11213.75 | Yes | N/A | N/A | 2024-02-07 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 1153.34 | -21.9 | Unknown | Unknown | Unknown | 1175.24 | 3981 | 1439.23 | 1153.34 | 285.89 | Yes | N/A | N/A | 2024-09-18 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-16 | 13 | 9 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-23 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-09 | 17 | 13 | 2024-10-09 | 2024-10-09 | 1 | 1 | 6 | 4 | 31 | 23 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-23 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-23 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 527.88 | -8.97 | Unknown | Unknown | 4.28 | 532.57 | 3981 | 1062.08 | 527.88 | 534.2 | Yes | N/A | N/A | 2024-04-16 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-05-21 | 55 | 39 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-14 | 25 | 19 | Unknown | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-07-10 | 27 | 19 | 2024-07-10 | 2024-07-10 | 1 | 1 | 25 | 19 | 83 | 59 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 7200 | 7200 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-05-22 | 247 | 178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 600.82 | -13.76 | Unknown | Unknown | Unknown | 614.58 | 3981 | 599.09 | 600.82 | -1.73 | Yes | N/A | N/A | 2023-11-16 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2023-12-29 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-28 | 12 | 8 | 2023-12-29 | 2024-01-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-01-24 | Unknown | Unknown | 15 | 11 | 108 | 78 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-30 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | -1582.06 | 479.22 | Unknown | 17.49 | -2292 | 213.23 | Unknown | 2291.63 | -1582.06 | 3873.69 | Yes | N/A | N/A | 2024-04-23 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-21 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-12 | 2024-06-21 | 10 | 8 | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 73 | 55 | 73 | 55 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 280 | 201 | No | 2023-09-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2025-01-28 | IOU Designed & Installed | N/A | Yes | 441 | 3346.06 | 502.72 | Unknown | 105.66 | 11.82 | 2725.86 | 3981 | 1252.43 | 3346.06 | -2093.63 | Yes | N/A | N/A | 2023-09-28 | 2024-12-12 | 442 | 316 | 2024-12-12 | 2024-12-12 | 1 | 1 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2025-01-28 | 419 | 299 | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-28 | 2025-02-05 | 9 | 7 | 2025-02-05 | 2025-02-05 | 1 | 1 | 861 | 615 | 11 | 9 | 872 | 624 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | -355 | -254 | No | 2024-03-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | 2025-01-10 | IOU Designed & Installed | N/A | Yes | 131 | 55.39 | Unknown | Unknown | Unknown | Unknown | 55.39 | 3981 | 907.15 | 55.39 | 851.76 | Yes | N/A | N/A | 2024-03-29 | 2024-08-07 | 132 | 94 | 2024-08-07 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2025-01-10 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-22 | 13 | 9 | 2025-01-22 | 2025-01-23 | 2 | 2 | 420 | 300 | 15 | 11 | 435 | 311 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-11 | 330 | 237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 2875 | 612.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-30 | 2025-01-08 | 10 | 8 | 2025-01-08 | 2025-01-23 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-04-28 | 96 | 68 | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-07 | Unknown | Unknown | 106 | 76 | 16 | 12 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | 63 | 46 | No | 2023-05-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | Yes | 682 | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 996.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-01 | 2025-03-12 | 682 | 488 | 2025-03-12 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-03-21 | Unknown | Unknown | 682 | 488 | 0 | 0 | 682 | 488 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 395 | 282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-01 | 2023-08-01 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 74372.77 | 3593.56 | Unknown | 67.47 | 1988.77 | 68722.97 | 56463 | 46275.38 | 74372.77 | -28097.39 | Yes | N/A | N/A | 2021-02-01 | 2023-05-24 | 843 | 603 | 2023-05-24 | 2024-01-30 | 252 | 180 | 2023-09-22 | 2023-09-26 | 5 | 3 | 2023-10-05 | 2024-01-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-06 | Unknown | Unknown | 2024-07-10 | 2025-01-13 | 188 | 134 | 2025-01-13 | 2025-01-13 | 1 | 1 | 848 | 606 | 456 | 326 | 1304 | 932 | Steps 2,3,5,6,7 | 130 | 92 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | CORONADO | CALTRANS-SOUTH of 56, CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 619 | 442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-03 | 2022-06-03 | 2025-02-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 115929.72 | 29572.36 | Unknown | 1539.43 | 2572.37 | 82245.56 | 155215 | 32834.42 | 115929.72 | -83095.3 | Yes | N/A | N/A | 2022-06-03 | 2023-09-01 | 456 | 326 | 2023-09-01 | 2024-04-23 | 236 | 168 | 2023-09-21 | 2024-11-01 | 44 | 32 | 2023-11-17 | 2024-11-06 | 89 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-11-12 | 195 | 139 | 2025-02-25 | 2025-03-10 | 14 | 10 | 2025-03-10 | 2024-12-10 | Unknown | Unknown | 500 | 358 | 534 | 377 | 1034 | 735 | Steps 2,3,5,6,7 | 565 | 403 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 114.13 | -7.1 | Unknown | Unknown | Unknown | 121.23 | Unknown | 854.94 | 114.13 | 740.81 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 74 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -407.19 | 2371.06 | Unknown | 398.97 | -4124 | 946.78 | Unknown | 4123.56 | -407.19 | 4530.75 | Yes | N/A | N/A | 2023-04-20 | 2023-06-13 | 55 | 39 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 55 | 39 | 1 | 1 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-01 | 2023-12-29 | IOU Designed & Installed | N/A | No | N/A | 1331.56 | -17.5 | Unknown | Unknown | 22.34 | 1326.72 | 3981 | 883.28 | 1331.56 | -448.28 | Yes | N/A | N/A | 2023-07-26 | 2023-10-24 | 91 | 65 | 2023-10-24 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-12-29 | 50 | 36 | Unknown | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-03-15 | 78 | 56 | 2024-03-15 | 2024-01-25 | Unknown | Unknown | 141 | 101 | 78 | 56 | 219 | 157 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-30 | -495 | -354 | No | 2024-08-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2025-02-06 | IOU Designed & Installed | N/A | Yes | 63 | 855.92 | Unknown | Unknown | Unknown | 17.87 | 838.05 | 3981 | 1191.83 | 855.92 | 335.91 | Yes | N/A | N/A | 2024-08-29 | 2024-10-31 | 64 | 46 | 2024-10-31 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2025-02-06 | 137 | 99 | Unknown | 2025-02-04 | Unknown | Unknown | 2025-02-06 | 2025-03-05 | 28 | 20 | 2025-03-05 | 2025-02-20 | Unknown | Unknown | 201 | 145 | 28 | 20 | 229 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 148 | 148 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | 177 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-09-20 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 6400.85 | Unknown | Unknown | Unknown | Unknown | 6400.85 | 87597 | 5492.25 | 6400.85 | -908.6 | Yes | N/A | N/A | 2023-07-12 | 2023-06-20 | Unknown | Unknown | 2023-06-20 | 2024-01-03 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-07-25 | 205 | 147 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-28 | 2024-09-18 | 22 | 16 | 2024-09-18 | 2024-08-30 | Unknown | Unknown | 205 | 147 | 220 | 158 | 425 | 305 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2013.69 | -48.29 | Unknown | Unknown | 6.53 | 2055.45 | 3981 | 2100.07 | 2013.69 | 86.38 | Yes | N/A | N/A | 2024-11-19 | 2024-11-20 | 2 | 2 | 2024-11-20 | 2024-11-26 | 7 | 5 | 2024-11-26 | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-18 | 23 | 17 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1 | 1 | 2 | 2 | 31 | 23 | 33 | 25 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-06 | 146 | 105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-08-20 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 14578.17 | Unknown | Unknown | Unknown | Unknown | 14578.17 | 103506 | 5905.83 | 14578.17 | -8672.34 | Yes | N/A | N/A | 2024-07-01 | 2024-08-20 | 51 | 37 | 2024-08-20 | 2025-01-29 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-28 | 8 | 6 | 2025-01-29 | 2025-03-19 | 50 | 36 | Unknown | 2025-03-20 | Unknown | Unknown | 2025-01-21 | 2025-04-07 | 77 | 55 | 2025-04-07 | 2025-04-01 | Unknown | Unknown | 101 | 73 | 248 | 178 | 349 | 251 | Steps 2,3,5,6,7 | 58 | 42 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 59.05 | 59.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -100 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 3722.59 | 582.92 | Unknown | 128.28 | 22.98 | 2988.41 | 3981 | 1569 | 3722.59 | -2153.59 | Yes | N/A | N/A | 2023-02-23 | 2023-03-29 | 35 | 25 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2024-06-21 | 451 | 323 | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-21 | 2024-06-25 | 5 | 3 | 2024-06-25 | 2024-06-25 | 1 | 1 | 486 | 348 | 6 | 4 | 492 | 352 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | -5.44 | -4.79 | Unknown | Unknown | Unknown | -0.65 | Unknown | 153.83 | -5.44 | 159.27 | Yes | N/A | N/A | 2023-05-30 | 2023-07-26 | 58 | 42 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-18 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-09-28 | 42 | 30 | 2023-09-28 | 2023-09-28 | 1 | 1 | 82 | 60 | 43 | 31 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | 153 | 110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -268.46 | -20.73 | Unknown | Unknown | -797.13 | 549.4 | 0 | 767.96 | -268.46 | 1036.42 | Yes | N/A | N/A | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | 2023-11-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-09 | 8 | 6 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-13 | 1 | 1 | 1 | 1 | 16 | 12 | 17 | 13 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -535 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 2762.82 | 785.39 | Unknown | 358.39 | Unknown | 1619.04 | 3981 | 674.31 | 2762.82 | -2088.51 | Yes | N/A | N/A | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-26 | 3 | 3 | 2024-02-08 | 2024-02-14 | 7 | 5 | 2024-03-08 | 2024-05-09 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-15 | 7 | 5 | 2024-05-15 | 2024-05-15 | 1 | 1 | 67 | 49 | 15 | 11 | 82 | 60 | Steps 2,3,5,6,7 | 47 | 33 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 2111.37 | Unknown | Unknown | Unknown | 3.43 | 2107.94 | 3981 | 441.35 | 2111.37 | -1670.02 | Yes | N/A | N/A | 2023-03-01 | 2023-06-30 | 122 | 88 | 2023-06-30 | 2023-11-20 | 144 | 102 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-08-24 | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-06 | 2024-06-14 | 9 | 7 | 2024-06-14 | 2024-06-12 | Unknown | Unknown | 122 | 88 | 153 | 109 | 275 | 197 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | -1228.84 | Unknown | Unknown | Unknown | -1367.08 | 138.24 | 3981 | 3216.48 | -1228.84 | 4445.32 | Yes | N/A | N/A | 2024-10-03 | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-03 | 3 | 3 | 2024-10-03 | 2025-02-10 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-06 | 17 | 13 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-06 | 2025-03-17 | 12 | 8 | 2025-03-17 | 2025-03-17 | 1 | 1 | 148 | 106 | 16 | 12 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAS FLORES | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | 93 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-04-17 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 17227.46 | 3105.38 | Unknown | 6345.19 | Unknown | 7776.89 | 100142 | 6683.62 | 17227.46 | -10543.84 | Yes | N/A | N/A | 2024-03-06 | 2024-01-15 | Unknown | Unknown | 2024-01-15 | 2024-06-28 | 166 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-02 | 5 | 3 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-29 | 2024-08-26 | 29 | 21 | 2024-08-26 | 2024-08-26 | 1 | 1 | 5 | 3 | 196 | 142 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | -126 | -91 | No | 2024-05-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-14 | 2024-08-28 | IOU Designed & Installed | N/A | Yes | 82 | 578.26 | -11.7 | Unknown | Unknown | Unknown | 589.96 | Unknown | 1855.63 | 578.26 | 1277.37 | Yes | N/A | N/A | 2024-05-10 | 2024-07-30 | 82 | 58 | 2024-07-30 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-07 | 18 | 14 | 2024-05-17 | 2024-08-28 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-04 | 8 | 6 | 2024-09-04 | 2024-09-04 | 1 | 1 | 186 | 132 | 27 | 21 | 213 | 153 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-05 | -203 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-23 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 4704.78 | Unknown | Unknown | Unknown | Unknown | 4704.78 | 7962 | 581.57 | 4704.78 | -4123.21 | Yes | N/A | N/A | 2024-04-16 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-08-29 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-24 | 31 | 23 | 2024-08-29 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-21 | 27 | 19 | 2024-10-21 | 2024-10-14 | Unknown | Unknown | 0 | 0 | 222 | 160 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | 16 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 3.59 | Unknown | Unknown | Unknown | Unknown | 3.59 | Unknown | 534.53 | 3.59 | 530.94 | Yes | N/A | N/A | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-09-06 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-12 | 7 | 5 | 2024-09-12 | 2024-09-16 | 5 | 3 | 177 | 127 | 13 | 9 | 190 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1568.44 | 382.05 | Unknown | 133.16 | Unknown | 1053.23 | 3981 | 1529.94 | 1568.44 | -38.5 | Yes | N/A | N/A | 2024-10-09 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-09 | 8 | 6 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-18 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-31 | 14 | 10 | 2024-10-31 | 2024-10-31 | 1 | 1 | 10 | 8 | 23 | 17 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-18 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-09 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 2889.02 | 582.92 | Unknown | 192.18 | 3.41 | 2110.51 | 3981 | 464.16 | 2889.02 | -2424.86 | Yes | N/A | N/A | 2024-02-08 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-02-13 | 77 | 55 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-22 | 39 | 29 | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-22 | 2024-03-28 | 7 | 5 | 2024-03-28 | 2024-03-28 | 1 | 1 | 39 | 29 | 85 | 61 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Fallbrook | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-06 | 1397 | 998 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-02-23 | 2023-09-05 | IOU Designed & Installed | N/A | No | N/A | 6463.11 | 3762.78 | Unknown | Unknown | -16372 | 19072.33 | Unknown | 16551.71 | 6463.11 | 10088.6 | Yes | N/A | N/A | 2023-01-26 | 2023-02-16 | 22 | 16 | 2023-02-16 | 2023-08-31 | 197 | 141 | 2023-03-13 | 2023-07-19 | 129 | 93 | 2023-07-19 | 2023-08-30 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2023-10-03 | 29 | 21 | 2023-10-03 | 2023-10-03 | 1 | 1 | 151 | 109 | 270 | 194 | 421 | 303 | Steps 2,3,5,6,7 | 171 | 123 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 2756.63 | 586.49 | Unknown | Unknown | 4.94 | 2165.2 | 3981 | 1278.11 | 2756.63 | -1478.52 | Yes | N/A | N/A | 2024-03-15 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-03-15 | 4 | 4 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-06-14 | 71 | 51 | 2024-06-14 | 2024-06-14 | 1 | 1 | 22 | 16 | 76 | 56 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -430 | -309 | No | 2024-07-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-29 | 2024-12-18 | IOU Designed & Installed | N/A | Yes | 49 | 1800.01 | 373.64 | Unknown | Unknown | Unknown | 1426.37 | Unknown | 1754.59 | 1800.01 | -45.42 | Yes | N/A | N/A | 2024-07-26 | 2024-09-13 | 50 | 36 | 2024-09-13 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-12-18 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-13 | 27 | 19 | 2025-01-13 | 2025-01-13 | 1 | 1 | 193 | 139 | 28 | 20 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | -7.65 | -5.54 | Unknown | Unknown | Unknown | -2.11 | 3981 | 341 | -7.65 | 348.65 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-08-07 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-09 | 3 | 3 | 2023-08-09 | 2023-08-09 | 1 | 1 | 140 | 100 | 4 | 4 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 410.05 | 410.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -86 | -61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1175.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-11-22 | 1 | 1 | 2024-11-22 | 2024-11-22 | 1 | 1 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-06-02 | 193 | 137 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-06 | 5 | 5 | 2025-06-06 | 2025-06-06 | 1 | 1 | 194 | 138 | 7 | 7 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-07-01 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 376.49 | Unknown | Unknown | Unknown | Unknown | 376.49 | 3981 | 1144.44 | 376.49 | 767.95 | Yes | N/A | N/A | 2024-04-24 | 2024-06-27 | 65 | 47 | 2024-06-27 | 2024-07-01 | 5 | 3 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-10-14 | 105 | 75 | Unknown | 2024-10-11 | Unknown | Unknown | 2024-10-14 | 2024-10-24 | 11 | 9 | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 170 | 122 | 16 | 12 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | 43 | 32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | 883.48 | -37.46 | Unknown | Unknown | Unknown | 920.94 | 3981 | 647.88 | 883.48 | -235.6 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | 2023-12-14 | 304 | 218 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-02-08 | 57 | 41 | 2024-02-08 | 2024-02-08 | 1 | 1 | 305 | 219 | 58 | 42 | 363 | 261 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 86.75 | 86.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | -514 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-06-30 | IOU Designed & Installed | N/A | No | N/A | 4237.82 | -84.41 | Unknown | Unknown | 40.93 | 4281.3 | 3981 | 1434.82 | 4237.82 | -2803 | Yes | N/A | N/A | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-06-30 | 116 | 82 | Unknown | 2025-06-16 | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 2025-06-30 | 2025-06-30 | 1 | 1 | 118 | 84 | 3 | 3 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 699.17 | -11.97 | Unknown | Unknown | 6.01 | 705.13 | 3981 | 768.26 | 699.17 | 69.09 | Yes | N/A | N/A | 2023-07-10 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-08-25 | 138 | 100 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-11-10 | 78 | 56 | Unknown | 2023-11-08 | Unknown | Unknown | 2023-11-10 | 2023-11-22 | 13 | 9 | 2023-11-22 | 2023-11-22 | 1 | 1 | 78 | 56 | 152 | 110 | 230 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | -401 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 413.98 | -11.74 | Unknown | Unknown | 13.21 | 412.51 | 3981 | 767.12 | 413.98 | 353.14 | Yes | N/A | N/A | 2023-03-02 | 2023-03-22 | 21 | 15 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-08-30 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-22 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2302.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-22 | 20 | 14 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-07 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-27 | 21 | 15 | 2025-05-27 | 2025-05-27 | 1 | 1 | 16 | 12 | 42 | 30 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 3262.68 | 2427.28 | Unknown | 47.85 | -1122 | 1909.55 | Unknown | 1122.45 | 3262.68 | -2140.23 | Yes | N/A | N/A | 2024-09-17 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-09 | 2 | 2 | 2024-10-09 | 2024-10-09 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-15 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 876.01 | -7.95 | Unknown | Unknown | Unknown | 883.96 | 3981 | 882.58 | 876.01 | 6.57 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | 2023-03-09 | 2023-03-10 | 2 | 2 | 2023-03-02 | 2023-03-15 | 14 | 10 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-04-25 | Unknown | Unknown | 3 | 3 | 14 | 10 | 17 | 13 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -144 | -104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 36.08 | -32.02 | Unknown | Unknown | Unknown | 68.1 | 7962 | 943.97 | 36.08 | 907.89 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | 2023-12-26 | 12 | 8 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-04-30 | Unknown | Unknown | 1 | 1 | 12 | 8 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | 108 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 871.35 | 2240.2 | Unknown | 558.51 | -2847 | 919.64 | 0 | 2847.34 | 871.35 | 1975.99 | Yes | N/A | N/A | 2023-04-18 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2023-05-31 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 49 | 35 | 49 | 35 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R29/R45 | Both | IOU Design | Commercial | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | 360 KW | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 584 | 417 | No | 2022-09-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-14 | 2022-11-07 | 2023-12-08 | IOU Designed & Installed | N/A | Yes | 156 | 138748.72 | 1027.09 | Unknown | Unknown | 1914.97 | 135806.66 | 0 | 77617.89 | 138748.72 | -61130.83 | Yes | N/A | N/A | 2022-09-14 | 2023-02-17 | 157 | 113 | 2023-02-17 | 2023-12-08 | 295 | 211 | 2023-04-06 | 2023-07-14 | 17 | 13 | 2023-05-09 | 2023-12-01 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | 2023-12-08 | 2024-05-07 | 152 | 108 | 2024-05-07 | 2024-05-07 | 1 | 1 | 174 | 126 | 474 | 340 | 648 | 466 | Steps 2,3,5,6,7 | 448 | 320 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 17503.26 | Unknown | Unknown | Unknown | Unknown | 17503.26 | Unknown | 6620.33 | 17503.26 | -10882.93 | Yes | N/A | N/A | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-09-11 | 2025-02-04 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-14 | 39 | 29 | 2025-03-14 | 2025-03-14 | 1 | 1 | 148 | 106 | 41 | 31 | 189 | 137 | Steps 2,3,5,6,7 | 50 | 36 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-27 | 303 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-09-29 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 15669.59 | -36.91 | Unknown | Unknown | 76.38 | 15630.12 | Unknown | 2997 | 15669.59 | -12672.59 | Yes | N/A | N/A | 2023-08-21 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-12-18 | 125 | 89 | 2023-11-21 | 2023-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-04-04 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-26 | 16 | 12 | 2024-04-26 | 2024-04-25 | Unknown | Unknown | 110 | 80 | 141 | 101 | 251 | 181 | Steps 2,3,5,6,7 | 27 | 19 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-17 | 149 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | Unknown | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | -6.33 | -12.33 | Unknown | Unknown | Unknown | 6 | 3981 | 1260.63 | -6.33 | 1266.96 | Yes | N/A | N/A | 2023-04-13 | 2023-04-13 | 1 | 1 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-10-04 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-10-13 | 10 | 8 | 2023-10-13 | 2023-10-13 | 1 | 1 | 115 | 83 | 11 | 9 | 126 | 92 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | RAMONA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -263 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-11-03 | IOU Designed & Installed | N/A | No | N/A | 2066.5 | 254.7 | Unknown | 107.89 | 38.84 | 1665.07 | 3981 | 1448.98 | 2066.5 | -617.52 | Yes | N/A | N/A | 2024-02-28 | 2024-05-20 | 83 | 59 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | 2024-06-19 | 30 | 22 | 2024-05-20 | 2024-06-20 | 4 | 4 | 2024-05-20 | 2024-11-03 | 168 | 120 | Unknown | 2024-10-25 | Unknown | Unknown | 2024-11-03 | 2024-11-20 | 18 | 13 | 2024-11-20 | 2024-11-20 | 1 | 1 | 281 | 201 | 24 | 19 | 305 | 220 | Steps 2,3,5,6,7 | 61 | 45 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 669.05 | 669.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | 418 | 299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1815.58 | -0.62 | Unknown | Unknown | 3.11 | 1813.09 | Unknown | 1383.45 | 1815.58 | -432.13 | Yes | N/A | N/A | 2023-03-31 | 2025-02-19 | 692 | 494 | 2025-02-19 | 2025-03-05 | 15 | 11 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 692 | 494 | 16 | 12 | 708 | 506 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-30 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 1134.68 | -21.9 | Unknown | Unknown | Unknown | 1156.58 | Unknown | 1879.71 | 1134.68 | 745.03 | Yes | N/A | N/A | 2024-07-25 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-25 | 21 | 15 | 2024-07-25 | 2024-08-21 | 24 | 18 | 2024-08-21 | 2024-08-29 | 9 | 7 | 2024-07-25 | 2024-09-25 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-16 | 22 | 16 | 2024-10-16 | 2024-10-16 | 1 | 1 | 87 | 63 | 53 | 39 | 140 | 102 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-29 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | 2023-06-20 | IOU Designed & Installed | N/A | No | N/A | 413.16 | -11.09 | Unknown | Unknown | 2.03 | 422.22 | 3981 | 2364.86 | 413.16 | 1951.7 | Yes | N/A | N/A | 2023-01-23 | 2023-02-02 | 11 | 9 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-06-20 | 139 | 99 | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-20 | 2023-06-23 | 4 | 4 | 2023-06-23 | 2023-06-23 | 1 | 1 | 150 | 108 | 5 | 5 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -415 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 22.54 | Unknown | Unknown | Unknown | Unknown | 22.54 | 3981 | 999.88 | 22.54 | 977.34 | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-28 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-09 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-16 | 50 | 36 | 2024-12-16 | 2024-12-12 | Unknown | Unknown | 44 | 32 | 61 | 43 | 105 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -487 | -348 | No | 2024-08-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-16 | 2024-11-18 | IOU Designed & Installed | N/A | Yes | 26 | 1321.73 | 251.04 | Unknown | Unknown | 3.45 | 1067.24 | 3981 | 1589.96 | 1321.73 | 268.23 | Yes | N/A | N/A | 2024-08-15 | 2024-09-10 | 27 | 19 | 2024-09-10 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-11-18 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-02-05 | 80 | 58 | 2025-02-05 | 2025-02-05 | 1 | 1 | 122 | 86 | 81 | 59 | 203 | 145 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | -419 | -300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 1515.03 | Unknown | Unknown | Unknown | 15.58 | 1499.45 | 3981 | 1022.5 | 1515.03 | -492.53 | Yes | N/A | N/A | 2024-07-11 | 2024-08-20 | 41 | 29 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-25 | 37 | 27 | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-25 | 2024-10-08 | 14 | 10 | 2024-10-08 | 2024-08-07 | Unknown | Unknown | 78 | 56 | 15 | 11 | 93 | 67 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 23.05 | 23.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 155 | 112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 4813.72 | 1180.4 | Unknown | 691.65 | 28.27 | 2913.4 | 3941 | 684.54 | 4813.72 | -4129.18 | Yes | N/A | N/A | 2023-05-22 | 2023-06-02 | 12 | 10 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-10-13 | 134 | 96 | Unknown | 2023-09-22 | Unknown | Unknown | 2023-10-13 | 2023-11-03 | 22 | 16 | 2023-11-03 | 2023-11-03 | 1 | 1 | 146 | 106 | 23 | 17 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-12 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-26 | 2023-08-21 | IOU Designed & Installed | N/A | No | N/A | -6.11 | -4.43 | Unknown | Unknown | Unknown | -1.68 | Unknown | 495.75 | -6.11 | 501.86 | Yes | N/A | N/A | 2023-05-10 | 2023-05-26 | 17 | 13 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-08-21 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-09-26 | 37 | 27 | 2023-09-26 | 2023-09-26 | 1 | 1 | 105 | 75 | 38 | 28 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | -16.25 | -14.71 | Unknown | Unknown | Unknown | -1.54 | 3885 | 163.83 | -16.25 | 180.08 | Yes | N/A | N/A | 2024-01-05 | 2024-01-31 | 27 | 19 | 2024-01-31 | 2025-03-06 | 401 | 287 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-16 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-15 | 29 | 21 | 2024-03-15 | 2024-03-15 | 1 | 1 | 37 | 27 | 431 | 309 | 468 | 336 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -452 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -731.84 | -5.54 | Unknown | Unknown | -729 | 2.7 | Unknown | 729.2 | -731.84 | 1461.04 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-07-31 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-14 | 15 | 11 | 2023-08-14 | 2023-08-14 | 1 | 1 | 79 | 57 | 16 | 12 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | -2519 | -1800 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-09-06 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 8757.27 | Unknown | Unknown | Unknown | -490 | 9247.27 | Unknown | 10529.93 | 8757.27 | 1772.66 | Yes | N/A | N/A | 2023-08-31 | 2023-09-15 | 16 | 12 | 2023-09-15 | 2023-09-18 | 4 | 2 | 2023-09-15 | 2024-01-08 | 116 | 82 | 2023-09-18 | 2024-01-16 | 121 | 87 | 2023-12-07 | Unknown | Unknown | Unknown | 2023-12-07 | 2024-01-08 | 33 | 23 | 2024-01-18 | 2024-02-07 | 21 | 15 | 2024-02-07 | 2024-02-07 | 1 | 1 | 132 | 94 | 180 | 128 | 312 | 222 | Steps 2,3,5,6,7 | 155 | 109 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | CB 1107-A6 MARJA PH 3B | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 323 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-07 | 2022-06-07 | 2024-10-07 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 139419.97 | 28853.98 | Unknown | Unknown | 14496.27 | 96069.72 | 0 | 68565.26 | 139419.97 | -70854.71 | Yes | N/A | N/A | 2022-06-07 | 2023-06-09 | 368 | 264 | 2023-06-09 | 2023-10-09 | 123 | 87 | 2023-08-14 | 2024-08-27 | 87 | 65 | 2023-10-09 | 2023-10-25 | 17 | 13 | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-17 | 2024-09-18 | 338 | 242 | 2024-10-07 | 2024-11-05 | 30 | 22 | 2024-11-05 | 2024-11-05 | 1 | 1 | 455 | 329 | 509 | 365 | 964 | 694 | Steps 2,3,5,6,7 | 387 | 277 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-23 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 1895.99 | Unknown | Unknown | Unknown | Unknown | 1895.99 | Unknown | 696.43 | 1895.99 | -1199.56 | Yes | N/A | N/A | 2024-05-14 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-04 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-21 | 15 | 11 | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 145 | 145 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-31 | 1193 | 852 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 507.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-22 | 2023-12-13 | 267 | 191 | 2023-12-13 | 2023-12-13 | 1 | 1 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 267 | 191 | 2 | 2 | 269 | 193 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-16 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 461.79 | -17.3 | Unknown | Unknown | 5.13 | 473.96 | 3981 | 975.28 | 461.79 | 513.49 | Yes | N/A | N/A | 2023-07-26 | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-07-26 | 48 | 34 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-11-13 | 111 | 79 | Unknown | 2023-10-20 | Unknown | Unknown | 2023-11-13 | 2023-11-15 | 3 | 3 | 2023-11-15 | 2023-11-15 | 1 | 1 | 111 | 79 | 52 | 38 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | Unknown | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 1140.86 | -21.9 | Unknown | Unknown | Unknown | 1162.76 | 3981 | 1561.65 | 1140.86 | 420.79 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-30 | 30 | 22 | 2024-08-01 | 2024-09-23 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-26 | 4 | 4 | 2024-09-26 | 2024-09-26 | 1 | 1 | 55 | 39 | 36 | 28 | 91 | 67 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | Alpine | COUNTY OF SAN DIEGO-SOUTH of 56 | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-30 | 2024-09-14 | IOU Designed & Installed | N/A | No | N/A | 2294.3 | 1579.02 | Unknown | Unknown | -7788 | 8503.28 | Unknown | 7788.12 | 2294.3 | 5493.82 | Yes | N/A | N/A | 2024-07-15 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-09-05 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-05 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-14 | 2024-09-18 | 5 | 3 | 2024-09-18 | 2024-09-18 | 1 | 1 | 0 | 0 | 72 | 52 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-04-05 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 1023.68 | 325.46 | Unknown | 9.77 | 9.34 | 679.11 | 3981 | 814.57 | 1023.68 | -209.11 | Yes | N/A | N/A | 2024-03-19 | 2024-04-05 | 18 | 14 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-07-10 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-09-28 | 81 | 58 | 2024-09-28 | 2024-09-28 | 1 | 0 | 115 | 83 | 83 | 59 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-18 | 2023-09-05 | IOU Designed & Installed | N/A | No | N/A | 0.5 | -14.59 | Unknown | Unknown | Unknown | 15.09 | 3981 | 909.83 | 0.5 | 909.33 | Yes | N/A | N/A | 2023-08-04 | 2023-08-18 | 15 | 11 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-09-05 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2023-10-30 | 56 | 40 | 2023-10-30 | 2023-10-30 | 1 | 1 | 34 | 24 | 58 | 42 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-23 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -91.59 | -7.66 | Unknown | Unknown | -89 | 5.07 | Unknown | 806.69 | -91.59 | 898.28 | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | 2023-06-20 | 2023-06-20 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -3 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-12 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 16038.88 | Unknown | Unknown | Unknown | 17.97 | 16020.91 | 88193 | 6519.7 | 16038.88 | -9519.18 | Yes | N/A | N/A | 2023-03-22 | 2023-04-05 | 15 | 11 | 2023-04-05 | 2023-08-09 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2024-11-01 | 463 | 331 | 2023-08-09 | 2024-10-01 | 420 | 300 | Unknown | 2025-04-11 | Unknown | Unknown | 2024-10-21 | 2024-11-28 | 39 | 29 | 2024-11-28 | 2024-11-28 | 1 | 1 | 435 | 311 | 630 | 452 | 1065 | 763 | Steps 2,3,5,6,7 | 622 | 446 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-25 | -379 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 1193.33 | 389.27 | Unknown | Unknown | Unknown | 804.06 | Unknown | 883.31 | 1193.33 | -310.02 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2024-02-09 | 263 | 189 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-12 | 4 | 2 | 2024-02-12 | 2024-02-12 | 1 | 1 | 264 | 190 | 5 | 3 | 269 | 193 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -453 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 425.82 | -7.98 | Unknown | Unknown | Unknown | 433.8 | Unknown | 1711.51 | 425.82 | 1285.69 | Yes | N/A | N/A | 2024-11-25 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-25 | 21 | 15 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-02-12 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-04 | 21 | 15 | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 80 | 58 | 42 | 30 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-12 | 2022-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1633.72 | 2952.83 | Unknown | 413.35 | -6192 | 1192.1 | Unknown | 3442.73 | -1633.72 | 5076.45 | Yes | N/A | N/A | 2022-04-12 | 2023-04-11 | 365 | 261 | 2023-04-11 | 2023-05-26 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 365 | 261 | 47 | 35 | 412 | 296 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-03 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 68.67 | Unknown | Unknown | Unknown | Unknown | 68.67 | 3981 | 1125.2 | 68.67 | 1056.53 | Yes | N/A | N/A | 2024-05-29 | 2024-05-30 | 2 | 2 | 2024-05-30 | 2024-06-03 | 5 | 3 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-07-10 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-25 | 16 | 12 | 2024-07-25 | 2024-07-25 | 1 | 1 | 40 | 30 | 22 | 16 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-29 | -438 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 7718.49 | 1706.96 | Unknown | Unknown | 184.01 | 5827.52 | 3981 | 1037.92 | 7718.49 | -6680.57 | Yes | N/A | N/A | 2024-08-16 | 2024-09-20 | 36 | 26 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2025-01-27 | 133 | 95 | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-27 | 2025-04-17 | 81 | 59 | 2025-04-17 | 2025-04-17 | 1 | 1 | 169 | 121 | 83 | 61 | 252 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | -458 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 22.64 | Unknown | Unknown | Unknown | Unknown | 22.64 | Unknown | 1398.42 | 22.64 | 1375.78 | Yes | N/A | N/A | 2024-06-10 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-06-10 | 56 | 40 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-12-31 | 205 | 147 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-08 | 9 | 7 | 2025-01-08 | 2025-01-08 | 1 | 1 | 205 | 147 | 66 | 48 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1736 | 1241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 7785.68 | 1364.29 | Unknown | 2842.85 | Unknown | 3578.54 | 2875.23 | 453.01 | 7785.68 | -7332.67 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-09-03 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-07-23 | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-27 | 2024-10-15 | 19 | 13 | 2024-10-15 | 2024-10-01 | Unknown | Unknown | 1 | 1 | 201 | 143 | 202 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -613 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 2473.53 | 391.31 | Unknown | 150.36 | Unknown | 1931.86 | Unknown | 796.7 | 2473.53 | -1676.83 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-05-09 | 34 | 24 | 2023-04-06 | 2023-05-30 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-06-05 | 7 | 5 | 2023-06-05 | 2023-06-05 | 1 | 1 | 56 | 40 | 42 | 30 | 98 | 70 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 42.32 | Unknown | Unknown | Unknown | Unknown | 42.32 | Unknown | 1599.28 | 42.32 | 1556.96 | Yes | N/A | N/A | 2025-01-22 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-22 | 14 | 10 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-31 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-19 | 20 | 14 | 2025-02-19 | 2025-02-19 | 1 | 1 | 10 | 8 | 35 | 25 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 164 | 164 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | 343 | 246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | 2022-10-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2336.1 | 630.08 | Unknown | Unknown | 13.77 | 1692.25 | 15924 | 772.82 | 2336.1 | -1563.28 | Yes | N/A | N/A | 2022-10-03 | 2023-05-16 | 226 | 162 | 2023-05-16 | 2023-07-25 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2023-09-08 | Unknown | Unknown | 226 | 162 | 71 | 51 | 297 | 213 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -287 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 4141.07 | 906.49 | Unknown | Unknown | Unknown | 3234.58 | 0 | 3209.26 | 4141.07 | -931.81 | Yes | N/A | N/A | 2024-07-11 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2025-04-04 | 299 | 215 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-12 | 28 | 20 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 0 | 0 | 329 | 237 | 329 | 237 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | 34 | 25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -948.88 | 321.22 | Unknown | Unknown | -5200 | 3929.9 | 0 | 6151.65 | -948.88 | 7100.53 | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | 2024-07-23 | 62 | 44 | 2024-06-20 | 2024-10-01 | 102 | 74 | 2024-05-23 | 2025-02-27 | 77 | 55 | 2024-07-23 | 2025-03-04 | 225 | 161 | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-18 | Unknown | Unknown | 328 | 236 | 139 | 99 | 467 | 335 | Steps 2,3,5,6,7 | 383 | 273 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Ranchita | COUNTY OF SAN DIEGO-NORTH of 56 | 810.05 | 810.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | 80 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2023-03-03 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 63939.34 | 14497.15 | Unknown | Unknown | -22768 | 72210.19 | 3373.72 | 48909.93 | 63939.34 | -15029.41 | Yes | N/A | N/A | 2022-11-02 | 2023-05-20 | 200 | 143 | 2023-05-20 | 2024-09-13 | 483 | 345 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-02-13 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-26 | 27 | 19 | 2024-11-26 | 2024-11-26 | 1 | 1 | 200 | 143 | 520 | 372 | 720 | 515 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-11 | -180 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-09 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 6.74 | -6.01 | Unknown | Unknown | Unknown | 12.75 | 3981 | 810.6 | 6.74 | 803.86 | Yes | N/A | N/A | 2023-11-02 | 2023-11-09 | 8 | 6 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-02-21 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-15 | 24 | 18 | 2024-03-15 | 2024-03-15 | 1 | 1 | 113 | 81 | 26 | 20 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -232 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -904.13 | -21.25 | Unknown | Unknown | -1196 | 313.12 | 3981 | 2183.13 | -904.13 | 3087.26 | Yes | N/A | N/A | 2023-03-08 | 2023-06-18 | 103 | 73 | 2023-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-18 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-06-21 | Unknown | Unknown | 103 | 73 | 0 | 0 | 103 | 73 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -591 | -423 | No | 2024-08-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-09-17 | IOU Designed & Installed | N/A | Yes | 55 | 19.25 | Unknown | Unknown | Unknown | Unknown | 19.25 | 3981 | 192.95 | 19.25 | 173.7 | Yes | N/A | N/A | 2024-08-06 | 2024-09-30 | 56 | 40 | 2024-09-30 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-11-06 | 51 | 37 | 2024-11-06 | 2024-11-06 | 1 | 1 | 57 | 41 | 52 | 38 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-25 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-29 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 1486.55 | 512.23 | Unknown | Unknown | Unknown | 974.32 | 3981 | 866.92 | 1486.55 | -619.63 | Yes | N/A | N/A | 2023-09-22 | 2023-09-22 | 1 | 1 | 2023-09-22 | 2023-09-29 | 8 | 6 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-12-04 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-07 | 4 | 4 | 2023-12-07 | 2023-12-07 | 1 | 1 | 68 | 48 | 13 | 11 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -437 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-21 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | -579 | -12.92 | Unknown | Unknown | -1559.39 | 993.31 | Unknown | 1561 | -579 | 2140 | Yes | N/A | N/A | 2024-03-20 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-03-22 | 87 | 63 | 2024-03-22 | 2024-05-03 | 43 | 31 | 2024-07-09 | 2024-07-22 | 14 | 10 | 2024-04-05 | 2024-06-20 | 77 | 55 | Unknown | 2024-06-18 | Unknown | Unknown | 2024-06-20 | 2024-07-25 | 36 | 26 | 2024-07-25 | 2024-07-25 | 1 | 1 | 120 | 86 | 138 | 100 | 258 | 186 | Steps 2,3,5,6,7 | 108 | 76 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | -663 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-17 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 46.63 | -0.94 | Unknown | Unknown | Unknown | 47.57 | Unknown | 1935.12 | 46.63 | 1888.49 | Yes | N/A | N/A | 2025-04-04 | 2025-04-16 | 13 | 9 | 2025-04-16 | 2025-04-17 | 2 | 2 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-13 | 14 | 10 | 2025-05-13 | 2025-05-13 | 1 | 1 | 27 | 19 | 17 | 13 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 371.67 | 1407.71 | Unknown | 335.11 | -1993 | 621.85 | Unknown | 1993.1 | 371.67 | 1621.43 | Yes | N/A | N/A | 2023-05-12 | 2023-05-24 | 13 | 9 | 2023-05-24 | 2023-06-01 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-06-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2023-06-13 | Unknown | Unknown | 20 | 14 | 9 | 7 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -316 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | -1093.73 | 210.3 | Unknown | Unknown | -1878 | 573.97 | Unknown | 1778.59 | -1093.73 | 2872.32 | Yes | N/A | N/A | 2024-12-20 | 2025-04-17 | 119 | 85 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-04-15 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-19 | 5 | 4 | 2025-04-19 | 2025-04-18 | Unknown | Unknown | 153 | 109 | 5 | 4 | 158 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-08 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-09-18 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 11.43 | -10.13 | Unknown | Unknown | Unknown | 21.56 | 3981 | 920.33 | 11.43 | 908.9 | Yes | N/A | N/A | 2023-08-25 | 2023-09-18 | 25 | 17 | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2024-06-20 | 277 | 199 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-02 | 13 | 9 | 2024-07-02 | 2024-12-03 | 155 | 111 | 302 | 216 | 169 | 121 | 471 | 337 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -969.34 | 2020.84 | Unknown | 67.36 | -3874 | 816.46 | 0 | 3874.43 | -969.34 | 4843.77 | Yes | N/A | N/A | 2023-09-07 | 2023-08-28 | Unknown | Unknown | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-03 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 869.34 | -8.06 | Unknown | Unknown | 3.56 | 873.84 | 3981 | 757.99 | 869.34 | -111.35 | Yes | N/A | N/A | 2024-03-14 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-03-19 | 41 | 29 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-06-07 | 81 | 59 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-07 | 2024-06-25 | 19 | 13 | 2024-06-25 | 2024-06-25 | 1 | 1 | 81 | 59 | 61 | 43 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | 336 | 241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 7249.51 | Unknown | Unknown | Unknown | Unknown | 7249.51 | 41767.6 | 3332.01 | 7249.51 | -3917.5 | Yes | N/A | N/A | 2023-05-15 | 2023-05-17 | 3 | 3 | 2023-05-17 | 2023-06-08 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2025-06-05 | 300 | 216 | 2023-06-08 | 2024-08-13 | 433 | 309 | Unknown | 2024-08-19 | Unknown | Unknown | 2024-10-11 | 2024-11-20 | 41 | 29 | 2024-11-20 | 2024-11-12 | Unknown | Unknown | 436 | 312 | 364 | 262 | 800 | 574 | Steps 2,3,5,6,7 | 728 | 520 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | -96 | -69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-06-10 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 6.37 | Unknown | Unknown | Unknown | Unknown | 6.37 | 3241 | 1559.03 | 6.37 | 1552.66 | Yes | N/A | N/A | 2024-05-14 | 2024-06-10 | 28 | 20 | 2024-06-10 | 2024-06-10 | 1 | 1 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-09-27 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-04 | 8 | 6 | 2024-10-04 | 2024-10-04 | 1 | 1 | 138 | 100 | 10 | 8 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SD 1189-J2 CMR PA2 WO1 (E) | SD 1189-J2 CMR PA2 WO1 (E) | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 771 | 552 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-24 | 2025-04-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 90700.87 | 19949.55 | Unknown | 1143.68 | 11074.17 | 58533.47 | 0 | 36721.12 | 90700.87 | -53979.75 | Yes | N/A | N/A | 2022-04-27 | 2023-05-01 | 370 | 264 | 2023-05-01 | 2023-10-19 | 172 | 124 | 2023-05-23 | 2024-04-08 | 254 | 182 | 2023-05-26 | 2023-10-31 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | 2025-04-29 | 1 | 1 | 624 | 446 | 208 | 150 | 832 | 596 | Steps 2,3,5,6,7 | 467 | 333 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Juan Capistrano | San Juan Capistrano | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -326 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-01 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | -2035.61 | 3675.22 | Unknown | 324.78 | -8907 | 2871.39 | Unknown | 8906.85 | -2035.61 | 10942.46 | Yes | N/A | N/A | 2023-09-01 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-10-02 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 2023-10-02 | 2023-10-03 | 2 | 2 | 2023-10-03 | 2023-10-03 | 1 | 1 | 0 | 0 | 38 | 28 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-21 | -105 | -76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -539.91 | 76.15 | Unknown | Unknown | -1556 | 939.94 | Unknown | 1555.75 | -539.91 | 2095.66 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-10-03 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-05 | 1 | 1 | 1 | 1 | 53 | 39 | 54 | 40 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 1157.9 | -22.73 | Unknown | Unknown | Unknown | 1180.63 | 3981 | 2092.23 | 1157.9 | 934.33 | Yes | N/A | N/A | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-31 | 10 | 8 | 2025-01-21 | 2025-02-14 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-27 | 42 | 30 | 2025-03-27 | 2025-03-27 | 1 | 1 | 26 | 20 | 54 | 40 | 80 | 60 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -340 | -244 | No | 2024-04-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | Unknown | IOU Designed & Installed | N/A | Yes | 24 | 39.05 | Unknown | Unknown | Unknown | Unknown | 39.05 | Unknown | 703.67 | 39.05 | 664.62 | Yes | N/A | N/A | 2024-04-01 | 2024-04-25 | 25 | 19 | 2024-04-25 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-14 | 1 | 1 | 25 | 19 | 1 | 1 | 26 | 20 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | -212 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2025-03-04 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 15924 | 1332.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2025-03-04 | 363 | 259 | 2025-03-04 | 2025-03-06 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-03 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-11 | 31 | 23 | 2025-06-11 | 2025-06-05 | Unknown | Unknown | 392 | 280 | 34 | 26 | 426 | 306 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 150.05 | 150.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-13 | 120 | 87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10.84 | -9.66 | Unknown | Unknown | Unknown | 20.5 | 3981 | 818.97 | 10.84 | 808.13 | Yes | N/A | N/A | 2023-06-07 | 2023-06-07 | 1 | 1 | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-03-12 | 6 | 4 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-06-30 | -837 | -598 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.07 | -7.66 | Unknown | Unknown | Unknown | 13.73 | Unknown | 208.9 | 6.07 | 202.83 | Yes | N/A | N/A | 2023-12-13 | 2023-12-26 | 14 | 10 | 2023-12-26 | 2024-01-22 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 14 | 10 | 29 | 21 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | -521 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 543.31 | -10.91 | Unknown | Unknown | 0.14 | 554.08 | 3981 | 1639.94 | 543.31 | 1096.63 | Yes | N/A | N/A | 2025-01-07 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-07 | 12 | 8 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-15 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-05-01 | 107 | 77 | 2025-05-01 | 2025-05-01 | 1 | 1 | 9 | 7 | 120 | 86 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -633 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 4.35 | -5.48 | Unknown | Unknown | Unknown | 9.83 | Unknown | 288.14 | 4.35 | 283.79 | Yes | N/A | N/A | 2024-01-10 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2024-01-18 | 80 | 58 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-01-29 | 5 | 3 | 2024-01-29 | 2024-01-29 | 1 | 1 | 7 | 5 | 86 | 62 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 965.22 | -7.74 | Unknown | Unknown | 17.42 | 955.54 | 3981 | 836.07 | 965.22 | -129.15 | Yes | N/A | N/A | 2024-02-05 | 2024-03-07 | 32 | 24 | 2024-03-07 | 2024-03-07 | 1 | 1 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-05-09 | 64 | 46 | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-09 | 2024-07-03 | 56 | 40 | 2024-07-03 | 2024-05-22 | Unknown | Unknown | 96 | 70 | 57 | 41 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -25.41 | -19.95 | Unknown | Unknown | Unknown | -5.46 | 3241 | 479.76 | -25.41 | 505.17 | Yes | N/A | N/A | 2023-05-24 | 2023-05-24 | 1 | 1 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-07-17 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-10-12 | 88 | 64 | 2023-10-12 | 2023-07-21 | Unknown | Unknown | 56 | 40 | 88 | 64 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1101.77 | 307.12 | Unknown | Unknown | 7.64 | 787.01 | 3981 | 1367.93 | 1101.77 | 266.16 | Yes | N/A | N/A | 2024-09-10 | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-10-03 | 31 | 23 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 0 | 0 | 32 | 24 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | -397 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-11 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 1924.17 | 485.5 | Unknown | Unknown | Unknown | 1438.67 | 3885 | 909.06 | 1924.17 | -1015.11 | Yes | N/A | N/A | 2023-11-10 | 2023-11-11 | 2 | 1 | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-11 | 2024-06-07 | 210 | 150 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-10 | 4 | 2 | 2024-06-10 | 2024-06-10 | 1 | 1 | 212 | 151 | 6 | 3 | 218 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | PAUMA VALLEY | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -215 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-04-11 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 8299.95 | 2036.7 | Unknown | 328.28 | Unknown | 5934.97 | 3981 | 549.22 | 8299.95 | -7750.73 | Yes | N/A | N/A | 2024-03-13 | 2024-03-27 | 15 | 11 | 2024-03-27 | 2024-04-11 | 16 | 12 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2025-01-02 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-28 | 27 | 19 | 2025-01-28 | 2025-01-28 | 1 | 1 | 282 | 202 | 44 | 32 | 326 | 234 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 220 | 220 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -647 | -464 | No | 2025-01-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-07 | 2025-01-22 | IOU Designed & Installed | N/A | Yes | 1 | 33.29 | Unknown | Unknown | Unknown | Unknown | 33.29 | Unknown | 1716.42 | 33.29 | 1683.13 | Yes | N/A | N/A | 2025-01-06 | 2025-01-07 | 2 | 2 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-22 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-03 | 13 | 9 | 2025-02-03 | 2025-02-03 | 1 | 1 | 18 | 14 | 15 | 11 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 218.71 | -11.58 | Unknown | Unknown | 4.11 | 226.18 | 3981 | 563.21 | 218.71 | 344.5 | Yes | N/A | N/A | 2023-02-02 | 2023-02-23 | 22 | 16 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-05-17 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 8.29 | Unknown | Unknown | Unknown | Unknown | 8.29 | Unknown | 1253.31 | 8.29 | 1245.02 | Yes | N/A | N/A | 2024-10-16 | 2024-11-19 | 35 | 25 | 2024-11-19 | 2024-11-21 | 3 | 3 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-03-05 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-31 | 27 | 19 | 2025-03-31 | 2025-03-31 | 1 | 1 | 142 | 102 | 31 | 23 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-12 | -696 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 45.41 | -0.94 | Unknown | Unknown | Unknown | 46.35 | 3981 | 1571.57 | 45.41 | 1526.16 | Yes | N/A | N/A | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-09 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-16 | 8 | 6 | 2025-05-16 | 2025-05-16 | 1 | 1 | 23 | 17 | 10 | 8 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-04 | 223 | 160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2023-09-08 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 48547.35 | 4066.14 | Unknown | Unknown | 168 | 44313.21 | 31783.21 | 21579.3 | 48547.35 | -26968.05 | Yes | N/A | N/A | 2022-11-02 | 2023-09-22 | 325 | 233 | 2023-09-22 | 2024-03-26 | 187 | 133 | 2024-02-13 | 2024-02-22 | 10 | 8 | 2024-01-17 | 2025-03-13 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | 2025-04-15 | 1 | 1 | 335 | 241 | 254 | 182 | 589 | 423 | Steps 2,3,5,6,7 | 78 | 56 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | -424 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 8.44 | -7.52 | Unknown | Unknown | Unknown | 15.96 | 3981 | 270.36 | 8.44 | 261.92 | Yes | N/A | N/A | 2023-07-25 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2024-02-23 | 218 | 156 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-15 | 18 | 14 | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 237 | 171 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-01 | 1114 | 796 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 4741.28 | 651.25 | Unknown | 146.54 | 43.42 | 3900.07 | 53565 | 2181.68 | 4741.28 | -2559.6 | Yes | N/A | N/A | 2023-09-20 | 2023-09-20 | 1 | 1 | 2023-09-20 | 2023-11-20 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2025-04-22 | 520 | 372 | Unknown | 2025-04-25 | Unknown | Unknown | 2025-04-30 | 2025-05-20 | 21 | 15 | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 521 | 373 | 83 | 59 | 604 | 432 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | 82 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-06-25 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | -87.3 | Unknown | Unknown | Unknown | -1025.36 | 938.06 | Unknown | 877.3 | -87.3 | 964.6 | Yes | N/A | N/A | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | 2024-07-19 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-11-26 | 131 | 93 | Unknown | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-06-23 | 201 | 143 | 2025-06-23 | 2024-12-17 | Unknown | Unknown | 132 | 94 | 281 | 201 | 413 | 295 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | -675 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-10 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1611.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-04-10 | 18 | 14 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-14 | 35 | 25 | 2025-05-14 | 2025-05-14 | 1 | 1 | 1 | 1 | 54 | 40 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -528 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | -1633.64 | Unknown | Unknown | Unknown | -1676 | 42.36 | Unknown | 1564.45 | -1633.64 | 3198.09 | Yes | N/A | N/A | 2025-01-23 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-23 | 14 | 10 | 2025-01-23 | 2025-02-19 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-10 | 20 | 14 | 2025-03-10 | 2025-03-10 | 1 | 1 | 29 | 21 | 35 | 25 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | 155 | 111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 58828.05 | 8537.51 | Unknown | Unknown | -1406.64 | 51697.18 | 3049 | 6024.75 | 58828.05 | -52803.3 | Yes | N/A | N/A | 2023-06-14 | 2023-12-18 | 188 | 134 | 2023-12-18 | 2024-01-17 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-09-16 | 55 | 39 | 2024-09-16 | 2024-09-16 | 1 | 1 | 188 | 134 | 92 | 66 | 280 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-16 | 1835 | 1312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 1285.18 | 253.74 | Unknown | Unknown | Unknown | 1031.44 | Unknown | 2270.45 | 1285.18 | 985.27 | Yes | N/A | N/A | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-21 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-24 | 4 | 4 | 2024-10-24 | 2024-10-24 | 1 | 1 | 22 | 16 | 6 | 6 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-22 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 3557.13 | -11.74 | Unknown | Unknown | 29.71 | 3539.16 | 3981 | 1186.27 | 3557.13 | -2370.86 | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-22 | 7 | 5 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-05-12 | 111 | 79 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-05-12 | 2025-05-21 | 10 | 8 | 2025-05-21 | 2025-05-21 | 1 | 1 | 112 | 80 | 18 | 14 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-22 | 793 | 566 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7684.51 | 251.92 | Unknown | Unknown | Unknown | 7432.59 | Unknown | 758.94 | 7684.51 | -6925.57 | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | 2023-09-08 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 1 | 1 | 13 | 11 | 14 | 12 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-10 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 0.46 | -12.57 | Unknown | Unknown | Unknown | 13.03 | 3981 | 902.53 | 0.46 | 902.07 | Yes | N/A | N/A | 2023-09-29 | 2023-10-09 | 11 | 7 | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-19 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-26 | 8 | 6 | 2023-10-26 | 2023-10-26 | 1 | 1 | 21 | 15 | 10 | 8 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-07 | 908 | 649 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1478.14 | -34.16 | Unknown | Unknown | Unknown | 1512.3 | 3981 | 564.01 | 1478.14 | -914.13 | Yes | N/A | N/A | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | 2023-08-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2024-06-06 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-12-01 | 165 | 117 | 288 | 206 | 167 | 119 | 455 | 325 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | -681 | -488 | No | 2025-05-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | 2025-06-10 | IOU Designed & Installed | N/A | Yes | 22 | 483.25 | Unknown | Unknown | Unknown | Unknown | 483.25 | 3981 | 874.97 | 483.25 | 391.72 | Yes | N/A | N/A | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | 2025-05-30 | 23 | 17 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-10 | 12 | 8 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-10 | 2025-06-17 | 8 | 6 | 2025-06-17 | 2025-06-17 | 1 | 1 | 13 | 9 | 32 | 24 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 3067.25 | 501.47 | Unknown | Unknown | 20.66 | 2545.12 | 3981 | 1210.36 | 3067.25 | -1856.89 | Yes | N/A | N/A | 2024-06-18 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-03 | 35 | 25 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-09-03 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-06 | 4 | 4 | 2024-09-06 | 2024-09-06 | 1 | 1 | 63 | 45 | 40 | 30 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-24 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 12.05 | -10.68 | Unknown | Unknown | Unknown | 22.73 | Unknown | 969.18 | 12.05 | 957.13 | Yes | N/A | N/A | 2024-04-22 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-04-24 | 45 | 33 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-30 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-10 | 12 | 8 | 2024-06-10 | 2024-06-10 | 1 | 1 | 37 | 27 | 58 | 42 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 40.15 | Unknown | Unknown | Unknown | Unknown | 40.15 | 3981 | 1975.7 | 40.15 | 1935.55 | Yes | N/A | N/A | 2024-09-25 | 2024-09-30 | 6 | 4 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2024-12-09 | Unknown | Unknown | 6 | 4 | 1 | 1 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -323 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 788 | 570.49 | Unknown | Unknown | Unknown | 217.51 | 23991 | 324.29 | 788 | -463.71 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-10-12 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-13 | 2 | 2 | 2023-10-13 | 2023-10-13 | 1 | 1 | 218 | 156 | 3 | 3 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 120.05 | 120.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 66 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.59 | -6.75 | Unknown | Unknown | Unknown | 14.34 | 3981 | 902.09 | 7.59 | 894.5 | Yes | N/A | N/A | 2024-02-01 | 2024-03-13 | 42 | 30 | 2024-03-13 | 2024-03-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-30 | 12 | 9 | 2024-03-28 | 2024-04-23 | 27 | 19 | Unknown | 2024-06-19 | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-07-29 | Unknown | Unknown | 69 | 49 | 28 | 21 | 97 | 70 | Steps 2,3,5,6,7 | 2 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-06 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 12.09 | Unknown | Unknown | Unknown | Unknown | 12.09 | Unknown | 999.88 | 12.09 | 987.79 | Yes | N/A | N/A | 2024-11-04 | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-11-07 | 11 | 9 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-10 | 22 | 16 | 2024-12-10 | 2024-12-10 | 1 | 1 | 13 | 9 | 34 | 26 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 766.05 | 766.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 297 | 214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1460.96 | -20.16 | Unknown | Unknown | -2567 | 1126.2 | Unknown | 2343.76 | -1460.96 | 3804.72 | Yes | N/A | N/A | 2024-09-04 | 2024-09-05 | 2 | 2 | 2024-09-05 | 2024-09-16 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-04 | 31 | 23 | 2024-09-16 | 2024-12-26 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-23 | Unknown | Unknown | 104 | 76 | 43 | 31 | 147 | 107 | Steps 2,3,5,6,7 | 18 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-10 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 456.12 | -4.15 | Unknown | Unknown | 7.3 | 452.97 | 3981 | 387.3 | 456.12 | -68.82 | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-08-29 | 110 | 78 | Unknown | 2023-07-25 | Unknown | Unknown | 2023-08-29 | 2023-09-01 | 4 | 4 | 2023-09-01 | 2023-08-31 | Unknown | Unknown | 111 | 79 | 4 | 4 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 217.24 | -100.1 | Unknown | Unknown | -1179 | 1496.34 | Unknown | 5378.62 | 217.24 | 5161.38 | Yes | N/A | N/A | 2023-04-04 | 2023-03-22 | Unknown | Unknown | 2023-03-22 | 2023-07-18 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-04-18 | 12 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-07-27 | 2023-08-18 | 23 | 17 | 2023-08-18 | 2023-08-18 | 1 | 1 | 0 | 0 | 155 | 109 | 155 | 109 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 100.8 | 100.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 239 | 172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 54.21 | Unknown | Unknown | Unknown | Unknown | 54.21 | 7962 | 1178.25 | 54.21 | 1124.04 | Yes | N/A | N/A | 2024-02-26 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-06-03 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-08-09 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-27 | Unknown | Unknown | 68 | 50 | 139 | 99 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-27 | -201 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | -7.99 | -15.58 | Unknown | Unknown | Unknown | 7.59 | 3981 | 798.13 | -7.99 | 806.12 | Yes | N/A | N/A | 2023-09-06 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-06 | 9 | 7 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-09-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-10-09 | 20 | 14 | 2023-10-09 | 2023-10-09 | 1 | 1 | 15 | 11 | 30 | 22 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -388 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-08-18 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 358.99 | 112.7 | Unknown | Unknown | 3.13 | 243.16 | 7962 | 828.55 | 358.99 | 469.56 | Yes | N/A | N/A | 2023-06-07 | 2023-08-18 | 73 | 53 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2024-01-03 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-02-12 | 41 | 29 | 2024-02-12 | 2024-02-12 | 1 | 1 | 212 | 152 | 43 | 31 | 255 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 939.11 | 281.98 | Unknown | Unknown | Unknown | 657.13 | Unknown | 10774.83 | 939.11 | 9835.72 | Yes | N/A | N/A | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | 2025-03-13 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-03-31 | 1 | 1 | 1 | 1 | 22 | 16 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-03-11 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 14.06 | -12.49 | Unknown | Unknown | Unknown | 26.55 | 3981 | 614.99 | 14.06 | 600.93 | Yes | N/A | N/A | 2024-01-29 | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2024-03-11 | 160 | 114 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-05-24 | 75 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-05-29 | 6 | 4 | 2024-05-29 | 2024-05-28 | Unknown | Unknown | 75 | 55 | 166 | 118 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -37 | -28 | No | 2023-04-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | Yes | 265 | 130.01 | -11.9 | Unknown | Unknown | Unknown | 141.91 | 3981 | 826.13 | 130.01 | 696.12 | Yes | N/A | N/A | 2023-04-24 | 2024-01-17 | 269 | 193 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-01-24 | 1 | 1 | 269 | 193 | 1 | 1 | 270 | 194 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Jamul | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-24 | -123 | -88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | 2023-05-17 | IOU Designed & Installed | N/A | No | N/A | 111274.09 | 24943.85 | Unknown | Unknown | -4275.96 | 90606.2 | 2892 | 19888.02 | 111274.09 | -91386.07 | Yes | N/A | N/A | 2023-01-18 | 2023-02-07 | 21 | 15 | 2023-02-07 | 2023-03-07 | 29 | 21 | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-06 | 2023-05-16 | 72 | 52 | 2023-03-20 | Unknown | Unknown | Unknown | 2023-03-20 | 2023-03-31 | 12 | 10 | 2023-05-17 | 2023-08-23 | 99 | 71 | 2023-08-23 | 2023-08-23 | 1 | 1 | 22 | 16 | 213 | 155 | 235 | 171 | Steps 2,3,5,6,7 | 61 | 43 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -211 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | 657.22 | Unknown | Unknown | Unknown | 35.62 | 621.6 | 3981 | 1361.26 | 657.22 | 704.04 | Yes | N/A | N/A | 2024-07-29 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-08-09 | 24 | 18 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2025-06-26 | 322 | 230 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-06-28 | 3 | 2 | 2025-06-28 | 2025-06-28 | 1 | 0 | 322 | 230 | 28 | 20 | 350 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | 285 | 204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 16546.99 | 1725.77 | Unknown | 74.8 | -60917.59 | 75664.01 | 0 | 70499.35 | 16546.99 | 53952.36 | Yes | N/A | N/A | 2024-01-09 | 2024-03-12 | 64 | 46 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-01-21 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-11 | 49 | 35 | 2025-03-11 | 2025-03-11 | 1 | 1 | 64 | 46 | 91 | 65 | 155 | 111 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 202.05 | 202.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-06-27 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 1898.56 | 562.86 | Unknown | 57.43 | Unknown | 1278.27 | 3981 | 1115.96 | 1898.56 | -782.6 | Yes | N/A | N/A | 2024-05-28 | 2024-06-04 | 8 | 6 | 2024-06-04 | 2024-06-27 | 24 | 18 | 2024-06-27 | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-11 | 15 | 11 | 2024-06-27 | 2024-07-11 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-25 | 15 | 11 | 2024-07-25 | 2024-07-25 | 1 | 1 | 23 | 17 | 55 | 41 | 78 | 58 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-09 | 406 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2024-01-16 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 6.4 | -5.67 | Unknown | Unknown | Unknown | 12.07 | 3981 | 538.55 | 6.4 | 532.15 | Yes | N/A | N/A | 2023-09-26 | 2024-01-24 | 121 | 87 | 2024-01-24 | 2024-02-01 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-03-28 | 2 | 2 | 2024-02-01 | 2024-04-09 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-29 | 15 | 11 | 2024-04-29 | 2024-04-18 | Unknown | Unknown | 190 | 136 | 26 | 20 | 216 | 156 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | -205 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 910.42 | 265.94 | Unknown | 91.72 | 5.51 | 547.25 | 3981 | 2004.43 | 910.42 | 1094.01 | Yes | N/A | N/A | 2023-10-25 | 2023-11-27 | 34 | 24 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 34 | 24 | 2 | 2 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 2256.04 | 318.38 | Unknown | Unknown | Unknown | 1937.66 | 3981 | 1199.38 | 2256.04 | -1056.66 | Yes | N/A | N/A | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-06 | 4 | 4 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-05-14 | 160 | 114 | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-14 | 2025-05-27 | 14 | 10 | 2025-05-27 | 2025-05-27 | 1 | 1 | 160 | 114 | 19 | 15 | 179 | 129 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 19.4 | 19.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-22 | 435 | 312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 2210.26 | 691.74 | Unknown | Unknown | -253 | 1771.52 | 0 | 996.92 | 2210.26 | -1213.34 | Yes | N/A | N/A | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | 2024-10-21 | 350 | 250 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-10-29 | 358 | 256 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-10-31 | 3 | 3 | 2024-10-31 | 2024-10-30 | Unknown | Unknown | 709 | 507 | 4 | 4 | 713 | 511 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 979.4 | Unknown | Unknown | Unknown | Unknown | 979.4 | 3981 | 1173.98 | 979.4 | 194.58 | Yes | N/A | N/A | 2024-10-25 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-11-03 | 38 | 26 | 2024-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-03 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 0 | 0 | 39 | 27 | 39 | 27 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JACUMBA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-27 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-15 | 2023-05-27 | IOU Designed & Installed | N/A | No | N/A | 958.86 | 475.52 | Unknown | 178.72 | Unknown | 304.62 | Unknown | 363.72 | 958.86 | -595.14 | Yes | N/A | N/A | 2023-02-13 | 2023-02-15 | 3 | 3 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-05-27 | 102 | 73 | Unknown | Unknown | Unknown | Unknown | 2023-05-27 | 2023-05-30 | 4 | 2 | 2023-05-30 | 2023-05-30 | 1 | 1 | 105 | 76 | 5 | 3 | 110 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -561 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 583.71 | -14.96 | Unknown | Unknown | 12.43 | 586.24 | 3981 | 437 | 583.71 | -146.71 | Yes | N/A | N/A | 2023-02-15 | 2023-02-24 | 10 | 8 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-03-29 | 34 | 24 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-06-02 | Unknown | Unknown | 10 | 8 | 34 | 24 | 44 | 32 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-28 | 690 | 494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-07-02 | 2025-02-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 171391.5 | 21290.26 | Unknown | 810.04 | -15426.72 | 164717.92 | 38907 | 72166.18 | 171391.5 | -99225.32 | Yes | N/A | N/A | 2024-04-02 | 2024-10-08 | 190 | 136 | 2024-10-08 | 2024-11-20 | 44 | 32 | 2024-10-23 | 2024-11-01 | 10 | 8 | 2024-08-27 | 2025-01-21 | 94 | 68 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-17 | 72 | 52 | 2025-04-17 | 2025-04-17 | 1 | 1 | 200 | 144 | 211 | 153 | 411 | 297 | Steps 2,3,5,6,7 | 156 | 112 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-31 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 480.9 | -11.09 | Unknown | Unknown | 4.26 | 487.73 | 3981 | 671.58 | 480.9 | 190.68 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-07-31 | 6 | 4 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2024-01-04 | 158 | 114 | Unknown | 2023-12-14 | Unknown | Unknown | 2024-01-04 | 2024-01-23 | 20 | 14 | 2024-01-23 | 2024-01-23 | 1 | 1 | 159 | 115 | 27 | 19 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -426 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-25 | 2023-02-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 750.83 | -21.13 | Unknown | Unknown | 8.32 | 763.64 | Unknown | 1544.87 | 750.83 | 794.04 | Yes | N/A | N/A | 2023-02-25 | 2023-03-28 | 32 | 22 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 32 | 22 | 1 | 1 | 33 | 23 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.94 | -11.6 | Unknown | Unknown | Unknown | 7.66 | 3981 | 656.37 | -3.94 | 660.31 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-05 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 723.54 | -12.44 | Unknown | Unknown | 7.58 | 728.4 | 3981 | 670.34 | 723.54 | -53.2 | Yes | N/A | N/A | 2023-08-07 | 2023-05-23 | Unknown | Unknown | 2023-05-23 | 2023-09-25 | 126 | 90 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2024-01-25 | 123 | 89 | Unknown | 2024-01-24 | Unknown | Unknown | 2024-01-25 | 2024-01-30 | 6 | 4 | 2024-01-30 | 2024-01-30 | 1 | 1 | 123 | 89 | 133 | 95 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | 236.25 | 236.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 291 | 210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | 2023-10-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 24543.8 | 1588.9 | Unknown | Unknown | -3699.6 | 26654.5 | 15942 | 24167.51 | 24543.8 | -376.29 | Yes | N/A | N/A | 2022-10-31 | 2023-02-01 | 94 | 68 | 2023-02-01 | Unknown | Unknown | Unknown | 2023-02-13 | 2023-07-11 | 58 | 43 | 2023-06-28 | 2023-07-12 | 5 | 5 | 2023-06-23 | 2023-10-25 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2024-02-16 | 115 | 83 | 2024-02-16 | 2024-02-16 | 1 | 1 | 277 | 200 | 121 | 89 | 398 | 289 | Steps 2,3,5,6,7 | 32 | 22 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-07 | 54 | 40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | -11.42 | -8.68 | Unknown | Unknown | Unknown | -2.74 | Unknown | 496.37 | -11.42 | 507.79 | Yes | N/A | N/A | 2023-08-04 | 2023-11-09 | 98 | 70 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-10-19 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-01-12 | 86 | 62 | 2024-01-12 | 2024-05-31 | 141 | 101 | 175 | 125 | 227 | 163 | 402 | 288 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 514.4 | -12.25 | Unknown | Unknown | Unknown | 526.65 | 3981 | 1271.42 | 514.4 | 757.02 | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-05-30 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-06-14 | 16 | 12 | 2023-06-14 | 2023-06-14 | 1 | 1 | 44 | 32 | 17 | 13 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -449 | -322 | No | 2023-12-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2024-03-22 | 2024-05-28 | IOU Designed & Installed | N/A | Yes | 105 | -5.37 | -4.35 | Unknown | Unknown | Unknown | -1.02 | 3981 | 501.14 | -5.37 | 506.51 | Yes | N/A | N/A | 2023-12-08 | 2024-03-20 | 104 | 74 | 2024-03-20 | 2024-03-22 | 3 | 3 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-05-28 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-19 | 23 | 17 | 2024-06-19 | 2024-06-19 | 1 | 1 | 172 | 122 | 27 | 21 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-28 | 490 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-12 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 958.26 | -43.82 | Unknown | Unknown | -677 | 1679.08 | 7085.32 | 1528.04 | 958.26 | 569.78 | Yes | N/A | N/A | 2022-10-12 | 2023-02-10 | 122 | 88 | 2023-02-10 | 2023-08-09 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-04-01 | 1 | 1 | 122 | 88 | 182 | 130 | 304 | 218 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 760 | 543 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20348.68 | -6.67 | Unknown | Unknown | Unknown | 20355.35 | 541850 | 25402.99 | 20348.68 | 5054.31 | Yes | N/A | N/A | 2023-03-20 | 2024-05-30 | 438 | 314 | 2024-05-30 | 2024-10-15 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-05-23 | 221 | 159 | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 659 | 473 | 140 | 100 | 799 | 573 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-22 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | -7.31 | -7.11 | Unknown | Unknown | Unknown | -0.2 | Unknown | 192.83 | -7.31 | 200.14 | Yes | N/A | N/A | 2024-04-15 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-23 | 78 | 56 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-05-29 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-04 | 7 | 5 | 2024-06-04 | 2024-06-04 | 1 | 1 | 7 | 5 | 86 | 62 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-10 | -184 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-05-30 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 734.32 | 239.9 | Unknown | 62.06 | Unknown | 432.36 | 3981 | 1935.77 | 734.32 | 1201.45 | Yes | N/A | N/A | 2023-03-31 | 2023-04-26 | 27 | 19 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-08-10 | 72 | 52 | Unknown | 2023-08-08 | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2023-08-10 | 1 | 1 | 99 | 71 | 2 | 2 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1086-F3 CYPRES PT PH2 | OC 1086-F3 CYPRES PT PH2 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -52 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 101213.98 | 3238.02 | Unknown | Unknown | 14156 | 83819.96 | Unknown | 57841.72 | 101213.98 | -43372.26 | Yes | N/A | N/A | 2024-01-05 | 2024-02-02 | 29 | 21 | 2024-02-02 | 2024-05-14 | 103 | 73 | 2024-03-08 | 2024-05-02 | 12 | 8 | 2024-03-13 | 2024-05-02 | 20 | 16 | 2024-05-28 | Unknown | Unknown | Unknown | 2024-05-28 | 2024-09-12 | 108 | 78 | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 41 | 29 | 232 | 168 | 273 | 197 | Steps 2,3,5,6,7 | 117 | 83 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 92 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-06-04 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 1661.13 | 354.78 | Unknown | Unknown | Unknown | 1306.35 | 3981 | 1499.84 | 1661.13 | -161.29 | Yes | N/A | N/A | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | 2024-06-28 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-24 | 21 | 15 | 2024-06-28 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-02 | 2 | 2 | 2024-07-02 | 2024-07-02 | 1 | 1 | 1 | 1 | 71 | 53 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | -114 | -82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-05 | 2022-08-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1183.43 | -23.57 | Unknown | Unknown | 3.43 | 1203.57 | 3981 | 525.88 | 1183.43 | -657.55 | Yes | N/A | N/A | 2022-08-05 | 2023-03-27 | 235 | 167 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2024-02-08 | 184 | 132 | 235 | 167 | 184 | 132 | 419 | 299 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | 253 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 23674.32 | 259 | Unknown | 32.69 | Unknown | 23382.63 | 142509 | 2648.74 | 23674.32 | -21025.58 | Yes | N/A | N/A | 2024-04-24 | 2024-06-13 | 51 | 37 | 2024-06-13 | 2024-06-17 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-10-02 | 108 | 78 | Unknown | 2024-10-30 | Unknown | Unknown | 2024-11-05 | 2024-11-13 | 9 | 7 | 2024-11-13 | 2024-11-09 | Unknown | Unknown | 159 | 115 | 14 | 10 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-17 | -298 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 649.49 | -32.03 | Unknown | Unknown | 5.63 | 675.89 | 25672.6 | 1279.01 | 649.49 | 629.52 | Yes | N/A | N/A | 2023-08-22 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-09-08 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-01 | 5 | 5 | 2023-09-08 | 2024-01-12 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-01-24 | Unknown | Unknown | 127 | 91 | 121 | 89 | 248 | 180 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | 40 | 29 | No | 2025-02-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-24 | 2025-03-28 | IOU Designed & Installed | N/A | Yes | 24 | 463.64 | -9.41 | Unknown | Unknown | Unknown | 473.05 | Unknown | 996.66 | 463.64 | 533.02 | Yes | N/A | N/A | 2025-02-28 | 2025-03-18 | 19 | 13 | 2025-03-18 | 2025-03-24 | 7 | 5 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-28 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-10 | 14 | 10 | 2025-04-10 | 2025-04-09 | Unknown | Unknown | 24 | 18 | 21 | 15 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-22 | 359 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2167.53 | 1570.33 | Unknown | 353.76 | -4820 | 728.38 | 0 | 4819.77 | -2167.53 | 6987.3 | Yes | N/A | N/A | 2023-07-06 | 2023-07-06 | 1 | 1 | 2023-07-06 | 2023-07-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | 3 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-16 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 521.03 | -10.45 | Unknown | Unknown | 64.89 | 466.59 | 0 | 656.47 | 521.03 | 135.44 | Yes | N/A | N/A | 2023-05-12 | 2023-05-16 | 5 | 3 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-04 | 21 | 15 | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-04 | 2025-04-10 | 555 | 397 | 2025-04-10 | 2025-04-10 | 1 | 1 | 26 | 18 | 556 | 398 | 582 | 416 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-27 | 2023-03-12 | IOU Designed & Installed | N/A | No | N/A | 2005.85 | 5357.13 | Unknown | 1485.28 | -7449 | 2612.44 | Unknown | 7449.28 | 2005.85 | 5443.43 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-12 | 2023-05-10 | 60 | 43 | 2023-05-10 | 2023-05-10 | 1 | 1 | 1 | 1 | 61 | 44 | 62 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-20 | 715 | 512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-25 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 69026.87 | 9698.31 | Unknown | Unknown | -21641.42 | 80969.98 | 28311.23 | 62605.88 | 69026.87 | -6420.99 | Yes | N/A | N/A | 2024-03-20 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-10-09 | 211 | 151 | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-06-20 | 2025-03-20 | 178 | 128 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-04 | 36 | 26 | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 1 | 426 | 306 | 427 | 307 | Steps 2,3,5,6,7 | 273 | 195 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-23 | 37 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-26 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 479.96 | -12.85 | Unknown | Unknown | -432.72 | 925.53 | Unknown | 664.58 | 479.96 | 184.62 | Yes | N/A | N/A | 2023-06-14 | 2023-06-30 | 17 | 13 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2024-04-09 | 201 | 143 | Unknown | 2024-04-05 | Unknown | Unknown | 2024-04-09 | 2024-04-29 | 21 | 15 | 2024-04-29 | 2024-04-29 | 1 | 1 | 218 | 156 | 23 | 17 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 765 | 548 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8894.75 | Unknown | Unknown | Unknown | Unknown | 8894.75 | 3661 | 812.32 | 8894.75 | -8082.43 | Yes | N/A | N/A | 2024-05-14 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-06-05 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2025-01-23 | 233 | 167 | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-19 | Unknown | Unknown | 233 | 167 | 24 | 18 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | -61 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-12-19 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1368.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2024-11-26 | 19 | 13 | 2024-11-26 | 2025-05-21 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-15 | 19 | 13 | 2025-05-21 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-27 | 22 | 16 | 2025-06-27 | 2025-06-25 | Unknown | Unknown | 19 | 13 | 218 | 156 | 237 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 5.74 | -5.1 | Unknown | Unknown | Unknown | 10.84 | Unknown | 307.58 | 5.74 | 301.84 | Yes | N/A | N/A | 2024-05-15 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-05-15 | 2 | 2 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-06-18 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-24 | 7 | 5 | 2024-06-24 | 2024-06-24 | 1 | 1 | 35 | 25 | 10 | 8 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -544 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2024-01-29 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 653.72 | -26.88 | Unknown | Unknown | Unknown | 680.6 | Unknown | 1014.83 | 653.72 | 361.11 | Yes | N/A | N/A | 2023-12-28 | 2024-01-29 | 33 | 23 | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | 2024-01-29 | 2024-03-04 | 36 | 26 | 2024-03-13 | 2024-03-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-03-25 | 13 | 9 | 2024-03-25 | 2024-03-25 | 1 | 1 | 34 | 24 | 51 | 37 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-04-18 | IOU Designed & Installed | N/A | No | N/A | -6.54 | -4.74 | Unknown | Unknown | Unknown | -1.8 | Unknown | 625.02 | -6.54 | 631.56 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-04-18 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-08-09 | 114 | 82 | 2023-08-09 | 2023-08-09 | 1 | 1 | 13 | 9 | 115 | 83 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 657.09 | -9.88 | Unknown | Unknown | Unknown | 666.97 | 3981 | 1078.78 | 657.09 | 421.69 | Yes | N/A | N/A | 2024-05-29 | 2024-06-06 | 9 | 7 | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-11 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-14 | 4 | 4 | 2024-06-14 | 2024-06-14 | 1 | 1 | 15 | 11 | 6 | 6 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 399 | 399 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 947 | 676 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2024-04-23 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 38284.5 | 5232.86 | Unknown | Unknown | -27755 | 60806.64 | 12971.95 | 70329.48 | 38284.5 | 32044.98 | Yes | N/A | N/A | 2023-09-20 | 2024-04-23 | 217 | 155 | 2024-04-23 | 2025-02-25 | 309 | 221 | 2025-02-13 | 2025-02-18 | 6 | 4 | 2024-07-31 | 2025-02-28 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-05-05 | 49 | 35 | 2025-05-05 | 2025-05-05 | 1 | 1 | 223 | 159 | 370 | 266 | 593 | 425 | Steps 2,3,5,6,7 | 214 | 152 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | 59 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1290.32 | 3572.55 | Unknown | 871.27 | -4650 | 1496.5 | 0 | 4650.34 | 1290.32 | 3360.02 | Yes | N/A | N/A | 2023-05-31 | 2023-05-25 | Unknown | Unknown | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | -105 | -76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4193.96 | -34.51 | Unknown | Unknown | 234.7 | 3993.77 | 7962 | 1277.69 | 4193.96 | -2916.27 | Yes | N/A | N/A | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | 2024-02-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-19 | 22 | 16 | 2024-02-27 | 2024-10-10 | 227 | 163 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2024-10-16 | Unknown | Unknown | 228 | 164 | 38 | 28 | 266 | 192 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | -382 | -275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -512.28 | -11.09 | Unknown | Unknown | -1523.42 | 1022.23 | Unknown | 1523.7 | -512.28 | 2035.98 | Yes | N/A | N/A | 2023-07-03 | 2023-07-11 | 9 | 7 | 2023-07-11 | 2023-07-27 | 17 | 13 | 2023-07-27 | 2023-09-29 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 74 | 54 | 18 | 14 | 92 | 68 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -425 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 446.53 | Unknown | Unknown | Unknown | 3.82 | 442.71 | 3941 | 326.25 | 446.53 | -120.28 | Yes | N/A | N/A | 2024-09-24 | 2025-03-20 | 178 | 128 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-04 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-29 | 26 | 18 | 2025-04-29 | 2025-04-28 | Unknown | Unknown | 194 | 140 | 27 | 19 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11198.58 | Unknown | Unknown | Unknown | Unknown | 11198.58 | 431982 | 31423.32 | 11198.58 | 20224.74 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | 2023-08-08 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2024-09-09 | 399 | 285 | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-15 | 1 | 1 | 400 | 286 | 79 | 57 | 479 | 343 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 31.25 | Unknown | Unknown | Unknown | Unknown | 31.25 | 3981 | 2109.63 | 31.25 | 2078.38 | Yes | N/A | N/A | 2025-02-19 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-19 | 2 | 2 | 2025-02-19 | Unknown | Unknown | Unknown | 2025-02-20 | 2025-02-26 | 7 | 5 | 2025-02-19 | 2025-02-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-10 | 19 | 13 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2 | 2 | 29 | 21 | 31 | 23 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 284.1 | 284.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -522 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 1832.08 | 644.05 | Unknown | Unknown | Unknown | 1188.03 | 3981 | 1277.36 | 1832.08 | -554.72 | Yes | N/A | N/A | 2023-07-07 | 2023-07-06 | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-10-23 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-10-27 | 5 | 5 | 2023-10-27 | 2023-10-27 | 1 | 1 | 109 | 77 | 6 | 6 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -593 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 451.27 | Unknown | Unknown | Unknown | 8.57 | 442.7 | 3981 | 1231.32 | 451.27 | 780.05 | Yes | N/A | N/A | 2025-03-04 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-11 | 14 | 10 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-06-09 | 91 | 65 | Unknown | 2025-05-23 | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 91 | 65 | 16 | 12 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-21 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 131.78 | -1.88 | Unknown | Unknown | Unknown | 133.66 | Unknown | 1523.16 | 131.78 | 1391.38 | Yes | N/A | N/A | 2024-06-04 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-06-21 | 51 | 37 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-29 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-09-03 | 37 | 27 | 2024-09-03 | 2024-09-03 | 1 | 1 | 39 | 27 | 89 | 65 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | -197 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 2334.73 | 679.56 | Unknown | 386.03 | Unknown | 1269.14 | Unknown | 783.8 | 2334.73 | -1550.93 | Yes | N/A | N/A | 2023-11-17 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-11-17 | 94 | 68 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-12-05 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-01-18 | 45 | 33 | 2024-01-18 | 2024-01-18 | 1 | 1 | 19 | 13 | 140 | 102 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -114 | -82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 406.61 | -31 | Unknown | Unknown | Unknown | 437.61 | 15924 | 1022.98 | 406.61 | 616.37 | Yes | N/A | N/A | 2023-02-06 | 2023-03-24 | 47 | 35 | 2023-03-24 | 2023-09-26 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-09-30 | 11 | 8 | 2023-09-26 | 2024-04-30 | 218 | 156 | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-02 | Unknown | Unknown | 265 | 191 | 198 | 141 | 463 | 332 | Steps 2,3,5,6,7 | 4 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 1122.37 | 435.85 | Unknown | Unknown | Unknown | 686.52 | 3941 | 153.49 | 1122.37 | -968.88 | Yes | N/A | N/A | 2023-12-27 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-01-18 | 38 | 28 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-06-05 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-10 | 6 | 4 | 2024-06-10 | 2024-06-10 | 1 | 1 | 140 | 100 | 45 | 33 | 185 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -361 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -14.85 | -12.08 | Unknown | Unknown | Unknown | -2.77 | Unknown | 372.29 | -14.85 | 387.14 | Yes | N/A | N/A | 2023-07-13 | 2023-08-11 | 30 | 22 | 2023-08-11 | 2023-08-11 | 1 | 1 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-04-24 | Unknown | Unknown | 30 | 22 | 1 | 1 | 31 | 23 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 430 | 307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | -691.73 | 7169.28 | Unknown | Unknown | -12538 | 4676.99 | Unknown | 12537.55 | -691.73 | 13229.28 | Yes | N/A | N/A | 2024-06-25 | 2024-07-01 | 7 | 5 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-14 | 3 | 1 | 2024-07-14 | 2024-07-14 | 1 | 0 | 7 | 5 | 4 | 1 | 11 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-01 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 1070.88 | -16.71 | Unknown | Unknown | 8.35 | 1079.24 | 3981 | 379.73 | 1070.88 | -691.15 | Yes | N/A | N/A | 2023-08-29 | 2023-09-01 | 4 | 4 | 2023-09-01 | 2025-03-06 | 553 | 395 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-10-10 | 40 | 28 | Unknown | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-10-12 | 3 | 3 | 2023-10-12 | 2023-10-12 | 1 | 1 | 44 | 32 | 557 | 399 | 601 | 431 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-11 | -242 | -174 | No | 2024-03-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | 2025-01-27 | IOU Designed & Installed | N/A | Yes | 283 | -24 | 257.08 | Unknown | Unknown | -1032 | 750.92 | 3981 | 1375.75 | -24 | 1399.75 | Yes | N/A | N/A | 2024-03-15 | 2024-12-23 | 284 | 202 | 2024-12-23 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-02-07 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-27 | 41 | 29 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-01-27 | 2025-02-11 | 16 | 12 | 2025-02-11 | 2025-02-11 | 1 | 1 | 378 | 270 | 17 | 13 | 395 | 283 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -662 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 53.11 | Unknown | Unknown | Unknown | Unknown | 53.11 | Unknown | 1399 | 53.11 | 1345.89 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-08-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-13 | 8 | 6 | 2024-08-13 | 2024-08-13 | 1 | 1 | 44 | 32 | 10 | 8 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 22.99 | Unknown | Unknown | Unknown | Unknown | 22.99 | 3981 | 1771.62 | 22.99 | 1748.63 | Yes | N/A | N/A | 2025-01-24 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-24 | 10 | 8 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-18 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-20 | 3 | 3 | 2025-02-20 | 2025-02-20 | 1 | 1 | 23 | 17 | 14 | 12 | 37 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-18 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-07 | 2022-09-07 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 636.07 | -14.91 | Unknown | Unknown | -558.4 | 1209.38 | Unknown | 730.08 | 636.07 | 94.01 | Yes | N/A | N/A | 2022-09-07 | 2023-02-02 | 149 | 107 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-07-25 | 96 | 68 | Unknown | 2023-07-19 | Unknown | Unknown | 2023-07-25 | 2023-09-01 | 39 | 29 | 2023-09-01 | 2023-09-01 | 1 | 1 | 245 | 175 | 40 | 30 | 285 | 205 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-05-07 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 2371.15 | 490.64 | Unknown | 15.54 | Unknown | 1864.97 | 3981 | 936.51 | 2371.15 | -1434.64 | Yes | N/A | N/A | 2024-04-12 | 2024-04-25 | 14 | 10 | 2024-04-25 | 2024-05-07 | 13 | 9 | 2024-05-07 | Unknown | Unknown | Unknown | 2024-05-08 | 2024-09-30 | 35 | 25 | 2024-05-07 | 2024-09-03 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-08 | 36 | 26 | 2024-10-08 | 2024-10-08 | 1 | 1 | 134 | 96 | 85 | 61 | 219 | 157 | Steps 2,3,5,6,7 | 146 | 104 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -386 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-10 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 2084.14 | 502.72 | Unknown | 95.68 | Unknown | 1485.74 | Unknown | 1043.66 | 2084.14 | -1040.48 | Yes | N/A | N/A | 2024-05-09 | 2024-05-10 | 2 | 2 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2025-03-04 | 299 | 213 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-03-04 | 1 | 1 | 301 | 215 | 3 | 3 | 304 | 218 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-19 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | -1597.91 | Unknown | Unknown | Unknown | -1622 | 24.09 | Unknown | 1622.14 | -1597.91 | 3220.05 | Yes | N/A | N/A | 2024-07-29 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-08-19 | 148 | 106 | 2024-08-19 | 2024-08-30 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-19 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-14 | 26 | 18 | 2024-10-14 | 2024-10-11 | Unknown | Unknown | 33 | 25 | 174 | 124 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -97 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 27.99 | Unknown | Unknown | Unknown | Unknown | 27.99 | 3981 | 866.38 | 27.99 | 838.39 | Yes | N/A | N/A | 2024-05-17 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-17 | 12 | 10 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-11-18 | 186 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-11-22 | 5 | 5 | 2024-11-22 | 2024-11-22 | 1 | 1 | 186 | 132 | 18 | 16 | 204 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-08 | -9 | -7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -13.76 | -9.98 | Unknown | Unknown | Unknown | -3.78 | 3981 | 464.78 | -13.76 | 478.54 | Yes | N/A | N/A | 2023-04-27 | 2023-04-27 | 1 | 1 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-06-29 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-12-19 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 893.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2023-12-19 | 62 | 44 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-11 | 24 | 18 | Unknown | 2024-01-03 | Unknown | Unknown | 2024-01-11 | 2024-01-16 | 6 | 4 | 2024-01-16 | 2024-01-16 | 1 | 1 | 24 | 18 | 69 | 49 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.09 | Unknown | Unknown | Unknown | Unknown | 30.09 | 3981 | 994.19 | 30.09 | 964.1 | Yes | N/A | N/A | 2023-10-31 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2024-06-20 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-24 | Unknown | Unknown | 14 | 10 | 324 | 232 | 338 | 242 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-08-19 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 10268.74 | Unknown | Unknown | Unknown | -1313.71 | 11582.45 | Unknown | 2164.71 | 10268.74 | -8104.03 | Yes | N/A | N/A | 2024-06-26 | 2024-08-19 | 55 | 39 | 2024-08-19 | 2024-09-04 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-11-12 | 69 | 49 | 2024-11-12 | 2024-11-12 | 1 | 1 | 55 | 39 | 87 | 63 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | Not available | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2023-03-28 | 352 | 252 | 2023-03-28 | 2023-09-21 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 352 | 252 | 179 | 129 | 531 | 381 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 385.05 | 385.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | -64 | -46 | No | 2023-03-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-04-20 | IOU Designed & Installed | N/A | Yes | 19 | -3.5 | -10.17 | Unknown | Unknown | Unknown | 6.67 | 3981 | 696 | -3.5 | 699.5 | Yes | N/A | N/A | 2023-03-10 | 2023-03-29 | 20 | 14 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-04-20 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-06-12 | 54 | 38 | 2023-06-12 | 2023-04-28 | Unknown | Unknown | 62 | 44 | 54 | 38 | 116 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | -8.78 | -9.21 | Unknown | Unknown | Unknown | 0.43 | 3885 | 163.83 | -8.78 | 172.61 | Yes | N/A | N/A | 2023-11-14 | 2024-02-23 | 102 | 74 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-07 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-03-20 | 14 | 10 | 2024-03-20 | 2024-03-20 | 1 | 1 | 116 | 84 | 16 | 12 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | -438 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-03 | 2022-11-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4309.3 | -22.33 | Unknown | Unknown | 24.28 | 4307.35 | 3885 | 517.74 | 4309.3 | -3791.56 | Yes | N/A | N/A | 2022-11-03 | 2023-02-10 | 100 | 72 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-04-24 | Unknown | Unknown | 100 | 72 | 0 | 0 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -434 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 2815.34 | 322.46 | Unknown | Unknown | 67.69 | 2425.19 | 3941 | 861.16 | 2815.34 | -1954.18 | Yes | N/A | N/A | 2024-03-11 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-05-13 | 161 | 115 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-09-12 | 123 | 89 | Unknown | 2024-08-15 | Unknown | Unknown | 2024-09-12 | 2024-09-12 | 1 | 1 | 2024-09-12 | 2024-09-12 | 1 | 1 | 123 | 89 | 163 | 117 | 286 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | 159 | 115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 409.69 | -8.23 | Unknown | Unknown | Unknown | 417.92 | 49559 | 1573.62 | 409.69 | 1163.93 | Yes | N/A | N/A | 2024-03-01 | 2024-03-04 | 4 | 2 | 2024-03-04 | 2025-02-19 | 353 | 253 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 11 | 7 | 353 | 253 | 364 | 260 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Dana Point | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 439 | 315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-08-21 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 10320.54 | 4130.2 | Unknown | 1261.03 | Unknown | 4929.31 | 0 | 3307.35 | 10320.54 | -7013.19 | Yes | N/A | N/A | 2023-04-06 | 2023-05-04 | 29 | 21 | 2023-05-04 | Unknown | Unknown | Unknown | 2023-08-28 | 2023-11-10 | 75 | 55 | 2023-12-13 | 2023-12-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2025-03-14 | 436 | 312 | 2025-03-14 | 2025-03-14 | 1 | 1 | 104 | 76 | 438 | 314 | 542 | 390 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | -402 | -287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-22 | 2023-06-05 | IOU Designed & Installed | N/A | No | N/A | 610.45 | -18.22 | Unknown | Unknown | Unknown | 628.67 | Unknown | 264.34 | 610.45 | -346.11 | Yes | N/A | N/A | 2023-05-19 | 2023-05-24 | 6 | 4 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-06-05 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-09-14 | 102 | 74 | 2023-09-14 | 2023-09-14 | 1 | 1 | 19 | 13 | 103 | 75 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | -626 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-08 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 1203.83 | 307.88 | Unknown | Unknown | Unknown | 895.95 | 3981 | 1895.3 | 1203.83 | 691.47 | Yes | N/A | N/A | 2025-04-07 | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-04-08 | 12 | 8 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-20 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-18 | 30 | 22 | 2025-06-18 | 2025-06-18 | 1 | 1 | 43 | 31 | 43 | 31 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-30 | 266 | 191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-21 | 2023-10-21 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 1355.91 | 168.74 | Unknown | 48.97 | 2.07 | 1136.13 | 0 | 1018.6 | 1355.91 | -337.31 | Yes | N/A | N/A | 2023-10-21 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-10-21 | 9 | 6 | 2023-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | 2024-11-22 | 399 | 285 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-01-21 | 61 | 43 | 2025-01-21 | 2025-01-21 | 1 | 1 | 399 | 285 | 71 | 50 | 470 | 335 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 64.37 | -13.16 | Unknown | Unknown | -699 | 776.53 | Unknown | 698.64 | 64.37 | 634.27 | Yes | N/A | N/A | 2024-01-03 | 2024-01-04 | 2 | 2 | 2024-01-04 | 2024-02-08 | 36 | 26 | 2024-01-26 | 2024-02-06 | 12 | 8 | 2024-01-18 | 2024-02-16 | 20 | 16 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-20 | 20 | 14 | 2024-05-20 | 2024-05-20 | 1 | 1 | 14 | 10 | 77 | 57 | 91 | 67 | Steps 2,3,5,6,7 | 40 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | -22 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 644.9 | -12.96 | Unknown | Unknown | Unknown | 657.86 | 7962 | 1446.07 | 644.9 | 801.17 | Yes | N/A | N/A | 2024-01-05 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2025-01-08 | 451 | 323 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-31 | 19 | 15 | 2025-01-08 | 2025-02-03 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-19 | Unknown | Unknown | 2025-04-19 | 2025-04-16 | Unknown | Unknown | 27 | 19 | 470 | 338 | 497 | 357 | Steps 2,3,5,6,7 | 23 | 17 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | 2022-04-07 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | -1397.1 | 960.44 | Unknown | 235.84 | -3030 | 436.62 | Unknown | 3029.98 | -1397.1 | 4427.08 | Yes | N/A | N/A | 2022-04-07 | 2023-03-28 | 356 | 254 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-12-11 | 48 | 34 | 2023-12-11 | 2023-12-11 | 1 | 1 | 356 | 254 | 49 | 35 | 405 | 289 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-10 | -103 | -74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-03-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 619.69 | -17.04 | Unknown | Unknown | 8.83 | 627.9 | 3981 | 552.11 | 619.69 | -67.58 | Yes | N/A | N/A | 2023-02-24 | 2023-03-04 | 9 | 6 | 2023-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-05-22 | 18 | 12 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2023-06-29 | Unknown | Unknown | 9 | 6 | 18 | 12 | 27 | 18 | Steps 2,3,5,6,7 | 77 | 55 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 375.5 | 375.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | -9 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-19 | IOU Designed & Installed | N/A | No | N/A | 3209.9 | Unknown | Unknown | Unknown | Unknown | 3209.9 | Unknown | 8716.79 | 3209.9 | 5506.89 | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | 2023-04-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-06-20 | 63 | 45 | 2023-06-20 | 2023-06-20 | 1 | 1 | 1 | 1 | 66 | 48 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1782.74 | -4.19 | Unknown | Unknown | -282.49 | 2069.42 | 0 | 266.52 | 1782.74 | -1516.22 | Yes | N/A | N/A | 2022-12-06 | 2023-01-31 | 57 | 41 | 2023-01-31 | 2023-03-14 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-06 | Unknown | Unknown | 57 | 41 | 43 | 31 | 100 | 72 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-22 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-30 | 2025-06-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1414.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | 2025-05-30 | 11 | 9 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-24 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 27 | 19 | 13 | 11 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-21 | -600 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2023-05-05 | IOU Designed & Installed | N/A | No | N/A | 367.82 | -12.89 | Unknown | Unknown | Unknown | 380.71 | 3891 | 898.47 | 367.82 | 530.65 | Yes | N/A | N/A | 2023-04-05 | 2023-04-05 | 1 | 1 | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-05-05 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-06-01 | 28 | 20 | 2023-06-01 | 2023-06-01 | 1 | 1 | 32 | 24 | 29 | 21 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | -95 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-17 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 71.08 | -5.4 | Unknown | Unknown | Unknown | 76.48 | 3241 | 1092.09 | 71.08 | 1021.01 | Yes | N/A | N/A | 2023-07-14 | 2023-07-17 | 4 | 2 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2023-09-22 | 2023-10-11 | 20 | 14 | 2023-10-11 | 2024-03-04 | 146 | 104 | 4 | 2 | 166 | 118 | 170 | 120 | Steps 2,3,5,6,7 | 571 | 407 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-25 | 645 | 462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-17 | 2022-09-20 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 9.45 | -8.43 | Unknown | Unknown | Unknown | 17.88 | 3241 | 827.83 | 9.45 | 818.38 | Yes | N/A | N/A | 2022-08-17 | 2024-03-22 | 584 | 418 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-20 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 12 | 8 | 2024-03-25 | 2024-05-31 | 68 | 50 | 584 | 418 | 80 | 58 | 664 | 476 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-07-27 | 1030 | 737 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-12 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 18528.87 | 276.33 | Unknown | Unknown | -5876 | 24128.54 | Unknown | 5875.56 | 18528.87 | -12653.31 | Yes | N/A | N/A | 2024-03-01 | 2024-04-15 | 46 | 32 | 2024-04-15 | 2024-04-25 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-05-07 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-22 | 20 | 14 | 2024-05-22 | 2024-05-22 | 1 | 1 | 46 | 32 | 66 | 48 | 112 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 1395.93 | Unknown | Unknown | Unknown | 10.1 | 1385.83 | 3981 | 1271.11 | 1395.93 | -124.82 | Yes | N/A | N/A | 2024-09-11 | 2024-09-26 | 16 | 12 | 2024-09-26 | 2024-10-04 | 9 | 7 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2025-02-04 | 124 | 88 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-02-04 | 2025-02-11 | 8 | 6 | 2025-02-11 | 2025-02-11 | 1 | 1 | 140 | 100 | 18 | 14 | 158 | 114 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -560 | -401 | No | 2024-11-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2024-12-19 | IOU Designed & Installed | N/A | Yes | 132 | 341.55 | -6.89 | Unknown | Unknown | Unknown | 348.44 | Unknown | 1066.51 | 341.55 | 724.96 | Yes | N/A | N/A | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-06 | 50 | 36 | 2025-02-06 | 2025-02-06 | 1 | 1 | 36 | 26 | 52 | 38 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-30 | 445 | 318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3369.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-24 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-29 | 2025-03-19 | 142 | 102 | 2025-03-19 | 2025-03-19 | 1 | 1 | 0 | 0 | 181 | 131 | 181 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-10 | -419 | -300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 25.19 | Unknown | Unknown | Unknown | Unknown | 25.19 | 3241 | 712.19 | 25.19 | 687 | Yes | N/A | N/A | 2023-12-08 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2023-12-08 | 23 | 17 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-17 | Unknown | Unknown | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | 52 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1759.53 | -35.9 | Unknown | Unknown | 170.83 | 1624.6 | 3981 | 953.69 | 1759.53 | -805.84 | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | 2023-09-28 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-16 | 7 | 5 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | 1 | 1 | 60 | 44 | 61 | 45 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-19 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 21.98 | Unknown | Unknown | Unknown | Unknown | 21.98 | 3981 | 1239.92 | 21.98 | 1217.94 | Yes | N/A | N/A | 2024-04-12 | 2024-04-15 | 4 | 2 | 2024-04-15 | 2024-04-19 | 5 | 5 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-09-03 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-11 | 9 | 7 | 2024-09-11 | 2024-09-11 | 1 | 1 | 142 | 100 | 15 | 13 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -591 | -422 | No | 2023-04-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | Yes | 44 | -9.16 | -8.37 | Unknown | Unknown | Unknown | -0.79 | Unknown | 153.75 | -9.16 | 162.91 | Yes | N/A | N/A | 2023-04-19 | 2023-06-02 | 45 | 33 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 45 | 33 | 1 | 1 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 649.72 | -4.32 | Unknown | Unknown | 13.57 | 640.47 | 3981 | 301.02 | 649.72 | -348.7 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | 2023-03-24 | 2023-03-29 | 6 | 4 | 2023-03-17 | 2023-04-17 | 28 | 20 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-04-26 | Unknown | Unknown | 7 | 5 | 28 | 20 | 35 | 25 | Steps 2,3,5,6,7 | 43 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -509 | -365 | No | 2024-01-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-04-30 | IOU Designed & Installed | N/A | Yes | 21 | 1413.89 | -14.76 | Unknown | Unknown | 1.86 | 1426.79 | 3981 | 2220.05 | 1413.89 | 806.16 | Yes | N/A | N/A | 2024-01-08 | 2024-01-30 | 23 | 17 | 2024-01-30 | 2024-02-01 | 3 | 3 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-04-30 | 90 | 64 | Unknown | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-05-13 | 14 | 10 | 2024-05-13 | 2024-05-13 | 1 | 1 | 113 | 81 | 18 | 14 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1377.42 | 348.98 | Unknown | Unknown | Unknown | 1028.44 | 3981 | 1434.91 | 1377.42 | 57.49 | Yes | N/A | N/A | 2025-04-25 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-25 | 2 | 2 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-16 | 22 | 16 | 2025-05-16 | 2025-05-16 | 1 | 1 | 1 | 1 | 25 | 19 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 246 | 246 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 427 | 306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 25.28 | Unknown | Unknown | Unknown | Unknown | 25.28 | 3981 | 2461.4 | 25.28 | 2436.12 | Yes | N/A | N/A | 2023-06-15 | 2024-07-17 | 399 | 285 | 2024-07-17 | 2024-08-13 | 28 | 20 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-01-31 | 1 | 1 | 399 | 285 | 29 | 21 | 428 | 306 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -592 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-24 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 88.28 | -1.25 | Unknown | Unknown | Unknown | 89.53 | Unknown | 1581.95 | 88.28 | 1493.67 | Yes | N/A | N/A | 2024-07-17 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-24 | 20 | 14 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-11-01 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-12 | 12 | 8 | 2024-11-12 | 2024-11-12 | 1 | 1 | 101 | 73 | 33 | 23 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-04 | -613 | -439 | No | 2024-07-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | Yes | 78 | 1990.58 | Unknown | Unknown | Unknown | Unknown | 1990.58 | 3981 | 1097.93 | 1990.58 | -892.65 | Yes | N/A | N/A | 2024-07-15 | 2024-09-27 | 75 | 55 | 2024-09-27 | 2024-10-01 | 5 | 3 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-10-29 | 1 | 1 | 75 | 55 | 6 | 4 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-09 | 2023-06-09 | IOU Designed & Installed | N/A | No | N/A | -8.8 | -6.37 | Unknown | Unknown | Unknown | -2.43 | Unknown | 479.76 | -8.8 | 488.56 | Yes | N/A | N/A | 2023-06-06 | 2023-06-08 | 3 | 3 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-06-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-06 | 28 | 20 | 2023-07-06 | 2023-07-06 | 1 | 1 | 4 | 4 | 29 | 21 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 1278.14 | 233.94 | Unknown | Unknown | Unknown | 1044.2 | 3981 | 1416.09 | 1278.14 | 137.95 | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-12-10 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-01-13 | 35 | 25 | 2025-01-13 | 2025-01-13 | 1 | 1 | 107 | 77 | 37 | 27 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -442 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-06-24 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 1173.39 | -24.19 | Unknown | Unknown | 57.25 | 1140.33 | 3981 | 1516.93 | 1173.39 | 343.54 | Yes | N/A | N/A | 2024-05-02 | 2024-06-04 | 34 | 24 | 2024-06-04 | 2024-07-16 | 43 | 31 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-06-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-12-18 | 178 | 128 | 2024-12-18 | 2024-12-18 | 1 | 1 | 35 | 25 | 222 | 160 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | 376 | 269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1011.12 | Unknown | Unknown | Unknown | Unknown | 1011.12 | 3981 | 1249.55 | 1011.12 | 238.43 | Yes | N/A | N/A | 2024-04-08 | 2024-06-05 | 59 | 43 | 2024-06-05 | 2025-01-24 | 234 | 168 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 59 | 43 | 235 | 169 | 294 | 212 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 825.5 | Unknown | Unknown | Unknown | Unknown | 825.5 | 3885 | 1517.72 | 825.5 | 692.22 | Yes | N/A | N/A | 2024-06-18 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-06-18 | 84 | 60 | 2024-06-18 | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-19 | 31 | 23 | 2024-06-18 | 2024-08-12 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-19 | 39 | 29 | 2024-09-19 | 2024-09-19 | 1 | 1 | 56 | 40 | 155 | 113 | 211 | 153 | Steps 2,3,5,6,7 | 31 | 23 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-04 | 101 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 135.48 | -15.09 | Unknown | Unknown | 16.05 | 134.52 | 3981 | 1288.69 | 135.48 | 1153.21 | Yes | N/A | N/A | 2023-06-27 | 2023-06-27 | 1 | 1 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2023-11-13 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 59.05 | 59.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -219 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -685.06 | -18.39 | Unknown | Unknown | -2646.42 | 1979.75 | Unknown | 4507.02 | -685.06 | 5192.08 | Yes | N/A | N/A | 2025-01-15 | 2025-01-22 | 8 | 6 | 2025-01-22 | 2025-04-10 | 79 | 57 | 2025-02-13 | 2025-03-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-23 | 14 | 10 | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-29 | Unknown | Unknown | 58 | 42 | 79 | 57 | 137 | 99 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 12.2 | -10.8 | Unknown | Unknown | Unknown | 23 | Unknown | 971.62 | 12.2 | 959.42 | Yes | N/A | N/A | 2024-04-24 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-04-24 | 28 | 20 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-04-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-14 | 20 | 14 | 2024-05-14 | 2024-05-14 | 1 | 1 | 2 | 2 | 49 | 35 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-27 | 198 | 141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 874.03 | -16.8 | Unknown | Unknown | Unknown | 890.83 | 0 | 688.59 | 874.03 | -185.44 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | 2024-07-19 | 495 | 355 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-12 | 25 | 17 | 2024-08-12 | 2024-08-12 | 1 | 1 | 496 | 356 | 26 | 18 | 522 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -420 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-07-19 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 3123.44 | 646.3 | Unknown | 148.52 | 38.49 | 2290.13 | 3981 | 1809.57 | 3123.44 | -1313.87 | Yes | N/A | N/A | 2024-03-19 | 2024-06-25 | 99 | 71 | 2024-06-25 | 2024-07-19 | 25 | 19 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-09-13 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-12-19 | 98 | 70 | 2024-12-19 | 2024-12-19 | 1 | 1 | 156 | 112 | 124 | 90 | 280 | 202 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 22.43 | Unknown | Unknown | Unknown | Unknown | 22.43 | 3981 | 1467.39 | 22.43 | 1444.96 | Yes | N/A | N/A | 2024-07-12 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-07-12 | 53 | 39 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 0 | 0 | 54 | 40 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | -78 | -57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | 2023-09-03 | IOU Designed & Installed | N/A | No | N/A | 3472.31 | 547.87 | Unknown | 1497.57 | 1.5 | 1425.37 | 3981 | 788.32 | 3472.31 | -2683.99 | Yes | N/A | N/A | 2023-02-10 | 2023-03-02 | 21 | 15 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-09-03 | 186 | 132 | Unknown | 2023-07-28 | Unknown | Unknown | 2023-09-03 | 2023-10-05 | 33 | 24 | 2023-10-05 | 2023-10-05 | 1 | 1 | 207 | 147 | 34 | 25 | 241 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-18 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 261.75 | -24.37 | Unknown | Unknown | 45.68 | 240.44 | 3981 | 2300.43 | 261.75 | 2038.68 | Yes | N/A | N/A | 2024-07-16 | 2024-07-24 | 9 | 7 | 2024-07-24 | 2024-08-13 | 21 | 15 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-14 | 2 | 2 | 9 | 7 | 23 | 17 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -614 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 515.97 | -9.69 | Unknown | Unknown | Unknown | 525.66 | 3981 | 1524.19 | 515.97 | 1008.22 | Yes | N/A | N/A | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-13 | 16 | 12 | 2024-10-24 | 2024-10-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-11 | 14 | 10 | 2024-11-11 | 2024-11-11 | 1 | 1 | 6 | 4 | 33 | 25 | 39 | 29 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-07 | 609 | 436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-11-11 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 13805.13 | -181.43 | Unknown | Unknown | -1979 | 15965.56 | 4630638.08 | 1978.52 | 13805.13 | -11826.61 | Yes | N/A | N/A | 2024-10-22 | 2024-11-11 | 21 | 15 | 2024-11-11 | 2024-11-26 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-08 | 17 | 13 | 2025-05-08 | 2025-05-08 | 1 | 1 | 21 | 15 | 34 | 26 | 55 | 41 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 286 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 5180 | 340.36 | Unknown | 16.62 | -15739 | 20562.02 | 1787 | 16650.13 | 5180 | 11470.13 | Yes | N/A | N/A | 2023-08-31 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-10-31 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 2023-10-31 | 2024-10-07 | 343 | 245 | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-10 | 2024-10-17 | 8 | 6 | 2024-10-17 | 2024-10-13 | Unknown | Unknown | 343 | 245 | 99 | 71 | 442 | 316 | Steps 2,3,5,6,7 | 335 | 239 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 915.62 | Unknown | Unknown | Unknown | 22.03 | 893.59 | Unknown | 611.73 | 915.62 | -303.89 | Yes | N/A | N/A | 2025-01-08 | 2025-02-14 | 38 | 28 | 2025-02-14 | 2025-02-25 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-02-25 | 2025-06-04 | 100 | 72 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-07-11 | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 138 | 100 | 30 | 22 | 168 | 122 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 28.1 | Unknown | Unknown | Unknown | Unknown | 28.1 | 3981 | 1678.58 | 28.1 | 1650.48 | Yes | N/A | N/A | 2024-12-13 | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-12-13 | 75 | 55 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-13 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-04 | 23 | 17 | 2025-02-04 | 2025-02-04 | 1 | 1 | 32 | 22 | 99 | 73 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1341.27 | -25.46 | Unknown | Unknown | 3.26 | 1363.47 | 3981 | 1769.78 | 1341.27 | 428.51 | Yes | N/A | N/A | 2025-01-16 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-16 | 7 | 5 | 2025-01-16 | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-13 | 17 | 13 | 2025-01-16 | 2025-01-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-04-09 | 79 | 57 | 2025-04-09 | 2025-04-09 | 1 | 1 | 6 | 4 | 104 | 76 | 110 | 80 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -352 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-28 | 2023-10-30 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 312.61 | 196.14 | Unknown | Unknown | Unknown | 116.47 | Unknown | 513.31 | 312.61 | 200.7 | Yes | N/A | N/A | 2023-10-28 | 2023-10-28 | 1 | 0 | 2023-10-28 | 2023-10-28 | 1 | 0 | 2023-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-05-17 | 201 | 145 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-28 | 43 | 31 | 2024-06-28 | 2024-06-28 | 1 | 1 | 202 | 145 | 45 | 32 | 247 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | -196 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1152.45 | -34.24 | Unknown | Unknown | 11.43 | 1175.26 | Unknown | 962.44 | 1152.45 | -190.01 | Yes | N/A | N/A | 2023-06-19 | 2023-06-19 | 1 | 1 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -551 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 933.88 | Unknown | Unknown | Unknown | Unknown | 933.88 | 3981 | 1155.13 | 933.88 | 221.25 | Yes | N/A | N/A | 2024-05-20 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-05-22 | 24 | 18 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-10-15 | 147 | 105 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-15 | 2024-10-18 | 4 | 4 | 2024-10-18 | 2024-10-18 | 1 | 1 | 147 | 105 | 29 | 23 | 176 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 420.49 | Unknown | Unknown | Unknown | 5 | 415.49 | 3981 | 1313.95 | 420.49 | 893.46 | Yes | N/A | N/A | 2024-10-09 | 2024-12-03 | 56 | 40 | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2024-12-26 | 22 | 16 | Unknown | 2025-01-23 | Unknown | Unknown | 2024-12-26 | 2025-02-03 | 40 | 28 | 2025-02-03 | 2025-02-03 | 1 | 1 | 78 | 56 | 42 | 30 | 120 | 86 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1660.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2025-03-07 | 110 | 80 | 2025-03-07 | 2025-03-27 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-21 | 15 | 11 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 110 | 80 | 37 | 27 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -207 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-01 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 32.77 | Unknown | Unknown | Unknown | Unknown | 32.77 | 3991 | 2060.38 | 32.77 | 2027.61 | Yes | N/A | N/A | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2025-02-05 | 524 | 374 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-07 | 3 | 3 | 2025-02-07 | 2025-02-06 | Unknown | Unknown | 525 | 375 | 3 | 3 | 528 | 378 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 2044.1 | 823.54 | Unknown | 592.69 | Unknown | 627.87 | Unknown | 265.75 | 2044.1 | -1778.35 | Yes | N/A | N/A | 2025-03-05 | 2025-03-06 | 2 | 2 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2 | 2 | 17 | 13 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 248.05 | 248.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | 90 | 65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-08-14 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 6584.7 | 1442.01 | Unknown | Unknown | Unknown | 5142.69 | 3981 | 392.38 | 6584.7 | -6192.32 | Yes | N/A | N/A | 2023-03-15 | 2023-08-10 | 149 | 107 | 2023-08-10 | 2023-10-27 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-06 | 4 | 4 | 2023-10-27 | 2024-01-04 | 70 | 50 | Unknown | 2023-12-14 | Unknown | Unknown | 2024-01-05 | 2024-01-31 | 27 | 19 | 2024-01-31 | 2024-06-04 | 126 | 90 | 219 | 157 | 236 | 170 | 455 | 327 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 786.65 | 251.99 | Unknown | Unknown | Unknown | 534.66 | 3981 | 1392.14 | 786.65 | 605.49 | Yes | N/A | N/A | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-24 | 30 | 22 | 2024-07-24 | 2024-07-24 | 1 | 1 | 9 | 7 | 32 | 24 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-20 | 884 | 633 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 46.17 | Unknown | Unknown | Unknown | Unknown | 46.17 | Unknown | 615.26 | 46.17 | 569.09 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-09-03 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | 1 | 1 | 35 | 25 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-05 | -170 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.56 | -5.31 | Unknown | Unknown | Unknown | -1.25 | 3981 | 163.83 | -6.56 | 170.39 | Yes | N/A | N/A | 2024-04-03 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-04 | 43 | 31 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-04-18 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 116.05 | 116.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-24 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 5.22 | Unknown | Unknown | Unknown | Unknown | 5.22 | 3981 | 999.88 | 5.22 | 994.66 | Yes | N/A | N/A | 2024-09-11 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-09-24 | 33 | 23 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-11-06 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-26 | 21 | 15 | 2024-11-26 | 2024-11-26 | 1 | 1 | 44 | 32 | 55 | 39 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-26 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 2431.48 | 904.05 | Unknown | 125.64 | -1087 | 2488.79 | 3981 | 2866.54 | 2431.48 | 435.06 | Yes | N/A | N/A | 2024-08-12 | 2024-08-26 | 15 | 11 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-09-06 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-10 | 35 | 25 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-10 | 2024-12-04 | 56 | 40 | 2024-12-04 | 2024-12-04 | 1 | 1 | 62 | 46 | 58 | 42 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-20 | -514 | -367 | No | 2025-01-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-02-07 | IOU Designed & Installed | N/A | Yes | 27 | 10.03 | Unknown | Unknown | Unknown | Unknown | 10.03 | 3961 | 1379.63 | 10.03 | 1369.6 | Yes | N/A | N/A | 2025-01-07 | 2025-01-31 | 25 | 19 | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-07 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-21 | 15 | 11 | 2025-02-21 | 2025-02-21 | 1 | 1 | 57 | 43 | 20 | 14 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | 30 | 21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | -786.58 | -17.26 | Unknown | Unknown | -806 | 36.68 | 0 | 1729.28 | -786.58 | 2515.86 | Yes | N/A | N/A | 2023-05-19 | 2023-05-25 | 7 | 5 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2024-04-11 | 297 | 213 | Unknown | 2024-04-10 | Unknown | Unknown | 2024-04-11 | 2024-04-15 | 5 | 3 | 2024-04-15 | 2024-04-15 | 1 | 1 | 304 | 218 | 6 | 4 | 310 | 222 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-07 | -423 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-06-06 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 2652.78 | -88.12 | Unknown | Unknown | -1607.58 | 4348.48 | Unknown | 1332.43 | 2652.78 | -1320.35 | Yes | N/A | N/A | 2023-05-08 | 2023-04-01 | Unknown | Unknown | 2023-04-01 | 2023-10-13 | 196 | 140 | 2023-10-13 | 2023-11-29 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-21 | 23 | 17 | Unknown | 2023-12-20 | Unknown | Unknown | 2023-12-21 | 2024-01-09 | 20 | 14 | 2024-01-09 | 2024-01-09 | 1 | 1 | 71 | 51 | 217 | 155 | 288 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -544 | -389 | No | 2024-03-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-25 | 2024-03-28 | IOU Designed & Installed | N/A | Yes | 91 | 2300.46 | 705.4 | Unknown | Unknown | Unknown | 1595.06 | Unknown | 1118.42 | 2300.46 | -1182.04 | Yes | N/A | N/A | 2024-03-06 | 2024-06-05 | 92 | 66 | 2024-06-05 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-28 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-07-16 | 111 | 79 | 2024-07-16 | 2024-07-16 | 1 | 1 | 96 | 70 | 112 | 80 | 208 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | EL CAJON | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -111 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | 2025-02-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 46828.49 | 16638.59 | Unknown | 2074.12 | -24350 | 52465.78 | 0 | 24350.33 | 46828.49 | -22478.16 | Yes | N/A | N/A | 2023-08-09 | 2023-12-11 | 125 | 89 | 2023-12-11 | 2024-05-29 | 171 | 123 | 2024-01-10 | 2024-12-09 | 40 | 28 | 2024-03-11 | 2025-01-13 | 91 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-08 | 2025-02-13 | 6 | 4 | 2025-02-13 | 2025-02-13 | 1 | 1 | 165 | 117 | 269 | 195 | 434 | 312 | Steps 2,3,5,6,7 | 413 | 295 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 592 | 423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 3844.16 | -76.35 | Unknown | Unknown | -15937.76 | 19858.27 | Unknown | 16213.39 | 3844.16 | 12369.23 | Yes | N/A | N/A | 2024-11-11 | 2024-11-13 | 3 | 3 | 2024-11-13 | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-25 | 10 | 4 | 2024-11-20 | 2024-11-27 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-28 | 153 | 109 | 2025-04-28 | 2025-04-28 | 1 | 1 | 13 | 7 | 159 | 115 | 172 | 122 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 30.66 | Unknown | Unknown | Unknown | Unknown | 30.66 | 3981 | 1504.62 | 30.66 | 1473.96 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-08-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-26 | 31 | 23 | 2024-09-26 | 2024-09-26 | 1 | 1 | 3 | 3 | 33 | 25 | 36 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -562 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-04-11 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 2358.43 | 735.15 | Unknown | 110.39 | Unknown | 1512.89 | Unknown | 980.74 | 2358.43 | -1377.69 | Yes | N/A | N/A | 2024-03-15 | 2024-03-22 | 8 | 6 | 2024-03-22 | 2024-04-11 | 21 | 15 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-19 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-21 | 3 | 3 | 2024-06-21 | 2024-06-21 | 1 | 1 | 78 | 56 | 25 | 19 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | -443 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.99 | -5.79 | Unknown | Unknown | Unknown | -2.2 | 3981 | 341 | -7.99 | 348.99 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | Applicant Design | Commercial | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | 559 | 400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-07 | 2021-10-07 | 2023-07-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 92069.18 | 10264.54 | Unknown | Unknown | 4111.79 | 77692.85 | 166621 | 42018.13 | 92069.18 | -50051.05 | Yes | N/A | N/A | 2021-10-07 | 2023-02-14 | 496 | 354 | 2023-02-14 | 2023-06-21 | 128 | 92 | 2023-03-22 | 2024-04-12 | 64 | 46 | 2023-06-22 | 2024-04-15 | 237 | 167 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2024-05-16 | 311 | 223 | 2024-05-16 | 2024-05-16 | 1 | 1 | 560 | 400 | 677 | 483 | 1237 | 883 | Steps 2,3,5,6,7 | 685 | 489 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -638 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-03 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1716.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-03-03 | 12 | 8 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-26 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-11 | 17 | 13 | 2025-04-11 | 2025-04-11 | 1 | 1 | 25 | 19 | 30 | 22 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-12 | -162 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 21.36 | Unknown | Unknown | Unknown | Unknown | 21.36 | Unknown | 1087.26 | 21.36 | 1065.9 | Yes | N/A | N/A | 2024-06-04 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-06-04 | 72 | 52 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-01 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-10-01 | 93 | 67 | 2024-10-01 | 2024-10-01 | 1 | 1 | 28 | 20 | 166 | 120 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 248.05 | 248.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-09-13 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 14328.55 | 2768.89 | Unknown | Unknown | -21464 | 33023.66 | Unknown | 21463.78 | 14328.55 | 7135.23 | Yes | N/A | N/A | 2023-05-11 | 2023-04-24 | Unknown | Unknown | 2023-04-24 | 2023-12-08 | 229 | 165 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-01-18 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-31 | 23 | 17 | 2024-01-31 | 2024-01-31 | 1 | 1 | 0 | 0 | 263 | 191 | 263 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 3.89 | -3.47 | Unknown | Unknown | Unknown | 7.36 | Unknown | 299.38 | 3.89 | 295.49 | Yes | N/A | N/A | 2024-04-11 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-04-11 | 63 | 45 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-12 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-04-25 | 14 | 10 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2 | 2 | 78 | 56 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 284 | 203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 2176.43 | 499.71 | Unknown | Unknown | Unknown | 1676.72 | 7962 | 1168.93 | 2176.43 | -1007.5 | Yes | N/A | N/A | 2024-02-26 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-03-08 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-07-11 | 126 | 90 | Unknown | 2024-06-21 | Unknown | Unknown | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | 2024-07-02 | 1 | 1 | 126 | 90 | 38 | 28 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.88 | -6.57 | Unknown | Unknown | Unknown | -1.31 | 3981 | 728.47 | -7.88 | 736.35 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-05-15 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | 1258 | 899 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 726.22 | -8 | Unknown | Unknown | 11.75 | 722.47 | 3981 | 470.21 | 726.22 | -256.01 | Yes | N/A | N/A | 2024-02-20 | 2024-02-21 | 2 | 2 | 2024-02-21 | 2024-03-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-05-09 | 66 | 48 | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-06-11 | Unknown | Unknown | 68 | 50 | 14 | 10 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-30 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 38.87 | Unknown | Unknown | Unknown | Unknown | 38.87 | 3981 | 1455.63 | 38.87 | 1416.76 | Yes | N/A | N/A | 2024-05-28 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-05-30 | 108 | 78 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-08-13 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-08 | 57 | 41 | 2024-10-08 | 2024-10-08 | 1 | 1 | 76 | 54 | 166 | 120 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1626.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-05-06 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-09 | 4 | 4 | 2025-05-09 | 2025-05-09 | 1 | 1 | 57 | 41 | 6 | 6 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1190 CMR PA10 WO3 (E) | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 607 | 435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 33790.37 | 5324.94 | Unknown | Unknown | Unknown | 28465.43 | 43382 | Not available | 33790.37 | Unknown | Yes | N/A | N/A | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | 2024-11-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-12-23 | 53 | 37 | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-16 | Unknown | Unknown | 54 | 38 | 2 | 2 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 148 | 107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2024-01-03 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 1019.13 | Unknown | Unknown | Unknown | Unknown | 1019.13 | 3981 | 1022.15 | 1019.13 | 3.02 | Yes | N/A | N/A | 2023-05-17 | 2023-12-20 | 218 | 156 | 2023-12-20 | 2024-02-01 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-13 | 42 | 30 | Unknown | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-03-28 | 10 | 8 | 2024-03-28 | 2024-03-28 | 1 | 1 | 260 | 186 | 55 | 41 | 315 | 227 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -360 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 5410.78 | -78.12 | Unknown | Unknown | 158.76 | 5330.14 | 3981 | 1211.46 | 5410.78 | -4199.32 | Yes | N/A | N/A | 2024-01-09 | 2024-03-07 | 59 | 43 | 2024-03-07 | 2024-03-15 | 9 | 7 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-10-11 | 211 | 151 | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-11 | 2024-10-28 | 18 | 12 | 2024-10-28 | 2024-10-28 | 1 | 1 | 270 | 194 | 28 | 20 | 298 | 214 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -613 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2025-01-10 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 54.34 | Unknown | Unknown | Unknown | Unknown | 54.34 | 3981 | 1846.19 | 54.34 | 1791.85 | Yes | N/A | N/A | 2024-11-18 | 2025-01-10 | 54 | 40 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-16 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-28 | 13 | 9 | 2025-01-28 | 2025-01-28 | 1 | 1 | 61 | 45 | 15 | 11 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 4845.59 | 2092.63 | Unknown | Unknown | 18.39 | 2734.57 | 3981 | 1867.13 | 4845.59 | -2978.46 | Yes | N/A | N/A | 2024-08-30 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-08-30 | 25 | 19 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-12-05 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2024-12-11 | 7 | 5 | 2024-12-11 | 2025-02-28 | 80 | 58 | 98 | 70 | 112 | 82 | 210 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-15 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 4.61 | -4.1 | Unknown | Unknown | Unknown | 8.71 | Unknown | 1120.67 | 4.61 | 1116.06 | Yes | N/A | N/A | 2024-04-08 | 2024-04-15 | 8 | 6 | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-14 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-07-09 | 57 | 41 | 2024-07-09 | 2024-07-09 | 1 | 1 | 38 | 28 | 59 | 43 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -306 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1536.68 | -6.04 | Unknown | Unknown | 4.21 | 1538.51 | 3981 | 1117.14 | 1536.68 | -419.54 | Yes | N/A | N/A | 2023-12-13 | 2024-06-11 | 182 | 130 | 2024-06-11 | 2024-06-13 | 3 | 3 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-30 | 1 | 1 | 182 | 130 | 4 | 4 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | -669 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 1673.12 | -33.05 | Unknown | Unknown | Unknown | 1706.17 | 3981 | 1934.82 | 1673.12 | 261.7 | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-24 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-26 | 34 | 24 | 2025-02-26 | 2025-02-26 | 1 | 1 | 19 | 15 | 36 | 26 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -628 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-19 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 33.99 | Unknown | Unknown | Unknown | Unknown | 33.99 | Unknown | 1446.69 | 33.99 | 1412.7 | Yes | N/A | N/A | 2024-09-04 | 2024-09-19 | 16 | 12 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-07 | 15 | 11 | 2024-09-19 | 2024-10-24 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-12 | 20 | 14 | 2024-11-12 | 2024-11-12 | 1 | 1 | 52 | 38 | 37 | 27 | 89 | 65 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -443 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-08-19 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 523.25 | 502.72 | Unknown | 138.51 | -1544 | 1426.02 | 3981 | 2191.02 | 523.25 | 1667.77 | Yes | N/A | N/A | 2024-05-28 | 2024-08-12 | 77 | 55 | 2024-08-12 | 2024-08-19 | 8 | 6 | 2024-08-19 | 2024-08-23 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2025-01-02 | 116 | 84 | Unknown | 2024-12-20 | Unknown | Unknown | 2025-01-02 | 2025-01-03 | 2 | 2 | 2025-01-03 | 2025-01-03 | 1 | 1 | 198 | 144 | 11 | 9 | 209 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 154 | 154 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | 838 | 599 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2023-05-08 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 106349.09 | 30161.18 | Unknown | 97.26 | 196.02 | 75894.63 | 72218 | 32856.34 | 106349.09 | -73492.75 | Yes | N/A | N/A | 2022-11-02 | 2023-04-17 | 167 | 119 | 2023-04-17 | 2024-06-12 | 423 | 303 | 2023-08-08 | 2023-08-11 | 4 | 4 | 2023-09-07 | 2023-11-29 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-12-20 | 176 | 126 | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | 2025-02-24 | 1 | 1 | 171 | 123 | 622 | 446 | 793 | 569 | Steps 2,3,5,6,7 | 309 | 221 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-10 | -370 | -265 | No | 2023-12-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-09-16 | IOU Designed & Installed | N/A | Yes | 70 | 16101.12 | 5078.57 | Unknown | 328.41 | 66.11 | 10628.03 | 3981 | 953.34 | 16101.12 | -15147.78 | Yes | N/A | N/A | 2023-12-11 | 2024-02-21 | 73 | 53 | 2024-02-21 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-09-16 | 279 | 199 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-16 | 2024-11-05 | 51 | 37 | 2024-11-05 | 2024-11-05 | 1 | 1 | 352 | 252 | 52 | 38 | 404 | 290 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 24.09 | Unknown | Unknown | Unknown | Unknown | 24.09 | 3981 | 1573.97 | 24.09 | 1549.88 | Yes | N/A | N/A | 2024-09-09 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-09 | 5 | 3 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-07 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-11-07 | 32 | 24 | 2024-11-07 | 2024-11-07 | 1 | 1 | 29 | 21 | 38 | 28 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 5711.53 | 1406.32 | Unknown | 1050.98 | Unknown | 3254.23 | Unknown | 568.18 | 5711.53 | -5143.35 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-19 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | 2023-12-19 | 1 | 1 | 6 | 4 | 2 | 2 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-27 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 52.69 | -17.42 | Unknown | Unknown | Unknown | 70.11 | 3981 | 662.98 | 52.69 | 610.29 | Yes | N/A | N/A | 2023-01-09 | 2023-02-24 | 47 | 35 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 47 | 35 | 1 | 1 | 48 | 36 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 712.86 | 306.13 | Unknown | Unknown | Unknown | 406.73 | 3981 | 2386.18 | 712.86 | 1673.32 | Yes | N/A | N/A | 2024-03-01 | 2024-01-12 | Unknown | Unknown | 2024-01-12 | 2024-03-01 | 50 | 36 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-04-11 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-06 | 26 | 18 | 2024-05-06 | 2024-05-06 | 1 | 1 | 42 | 30 | 77 | 55 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-10-08 | 991 | 708 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.89 | -5.6 | Unknown | Unknown | Unknown | 3.71 | Unknown | 271.63 | -1.89 | 273.52 | Yes | N/A | N/A | 2023-03-10 | 2023-03-09 | Unknown | Unknown | 2023-03-09 | 2023-03-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 0 | 0 | 7 | 5 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 87.05 | 87.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-30 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 0.54 | -14.24 | Unknown | Unknown | Unknown | 14.78 | 3981 | 958.38 | 0.54 | 957.84 | Yes | N/A | N/A | 2023-10-18 | 2023-10-25 | 8 | 6 | 2023-10-25 | 2023-10-30 | 6 | 4 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-09 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-15 | 7 | 5 | 2023-11-15 | 2023-11-15 | 1 | 1 | 19 | 15 | 14 | 10 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONSALL | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.51 | -10.97 | Unknown | Unknown | 5.25 | 7.23 | 3981 | 766.47 | 1.51 | 764.96 | Yes | N/A | N/A | 2023-05-10 | 2023-05-10 | 1 | 1 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | 141 | 102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-10-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 125.31 | Unknown | Unknown | Unknown | 16.78 | 108.53 | 3981 | 1739.79 | 125.31 | 1614.48 | Yes | N/A | N/A | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | -689 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 3.94 | Unknown | Unknown | Unknown | Unknown | 3.94 | 3981 | 118.25 | 3.94 | 114.31 | Yes | N/A | N/A | 2025-04-29 | 2025-05-01 | 3 | 3 | 2025-05-01 | 2025-05-02 | 2 | 2 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-05 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-20 | 16 | 12 | 2025-05-20 | 2025-05-20 | 1 | 1 | 7 | 5 | 19 | 15 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -454 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 0.41 | -11.78 | Unknown | Unknown | Unknown | 12.19 | 3241 | 777.76 | 0.41 | 777.35 | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2023-10-11 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-16 | 6 | 4 | 2023-10-16 | 2023-10-16 | 1 | 1 | 31 | 23 | 8 | 6 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-04 | -276 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 3778.14 | 667.4 | Unknown | Unknown | 1.97 | 3108.77 | 0 | 920.5 | 3778.14 | -2857.64 | Yes | N/A | N/A | 2023-11-20 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-11-20 | 90 | 64 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-07-23 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-11-01 | 102 | 74 | 2024-11-01 | 2024-11-01 | 1 | 1 | 247 | 177 | 193 | 139 | 440 | 316 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | 3052 | 3052 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-27 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 83.98 | -5.76 | Unknown | Unknown | -316.41 | 406.15 | Unknown | 281 | 83.98 | 197.02 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | 2023-02-21 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-03-27 | 35 | 25 | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-03-28 | Unknown | Unknown | 36 | 26 | 19 | 13 | 55 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -478 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.42 | -3.94 | Unknown | Unknown | Unknown | -1.48 | 3981 | 341 | -5.42 | 346.42 | Yes | N/A | N/A | 2023-02-27 | 2023-03-03 | 5 | 5 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-07-25 | 1 | 1 | 5 | 5 | 1 | 1 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 1780.87 | 428.77 | Unknown | Unknown | Unknown | 1352.1 | 3981 | 975.35 | 1780.87 | -805.52 | Yes | N/A | N/A | 2024-05-09 | 2024-05-09 | 1 | 1 | 2024-05-09 | 2024-05-09 | 1 | 1 | 2024-05-09 | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-23 | 15 | 11 | 2024-05-09 | 2024-05-24 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-05 | 13 | 9 | 2024-06-05 | 2024-06-05 | 1 | 1 | 17 | 13 | 30 | 22 | 47 | 35 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -366 | -263 | No | 2023-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | Yes | 227 | -5.59 | -10.95 | Unknown | Unknown | Unknown | 5.36 | 3241 | 1109.79 | -5.59 | 1115.38 | Yes | N/A | N/A | 2023-02-06 | 2023-09-21 | 228 | 164 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2023-10-11 | 1 | 1 | 228 | 164 | 1 | 1 | 229 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-16 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 5.63 | -5.02 | Unknown | Unknown | Unknown | 10.65 | Unknown | 1002.75 | 5.63 | 997.12 | Yes | N/A | N/A | 2024-04-03 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-04-16 | 47 | 33 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-05-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-23 | 11 | 9 | 2024-05-23 | 2024-05-23 | 1 | 1 | 28 | 20 | 59 | 43 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -657 | -470 | No | 2024-07-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-08-30 | IOU Designed & Installed | N/A | Yes | 42 | 5.64 | Unknown | Unknown | Unknown | Unknown | 5.64 | 3981 | 192.95 | 5.64 | 187.31 | Yes | N/A | N/A | 2024-07-23 | 2024-09-03 | 43 | 31 | 2024-09-03 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-30 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-12 | 14 | 10 | 2024-09-12 | 2024-09-12 | 1 | 1 | 51 | 37 | 15 | 11 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 128.05 | 128.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | 2 | 1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2025-03-25 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-09 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2025-03-27 | 512 | 366 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-02 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-11 | 22 | 16 | 2025-06-11 | 2025-06-02 | Unknown | Unknown | 37 | 27 | 534 | 382 | 571 | 409 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -685 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-28 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 1868.26 | 498.43 | Unknown | Unknown | Unknown | 1369.83 | Unknown | 1657.87 | 1868.26 | -210.39 | Yes | N/A | N/A | 2025-03-27 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-28 | 17 | 13 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-15 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-19 | 5 | 4 | 2025-04-19 | 2025-04-19 | 1 | 0 | 19 | 13 | 23 | 17 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-22 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-03-30 | IOU Designed & Installed | N/A | No | N/A | 460.91 | -15.43 | Unknown | Unknown | Unknown | 476.34 | Unknown | 363.72 | 460.91 | -97.19 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-03-30 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-06-12 | 75 | 53 | 2023-06-12 | 2023-06-12 | 1 | 1 | 23 | 17 | 76 | 54 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 47.1 | 47.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-10 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 80.75 | Unknown | Unknown | Unknown | Unknown | 80.75 | 11943 | 1743.18 | 80.75 | 1662.43 | Yes | N/A | N/A | 2024-10-07 | 2024-10-10 | 4 | 4 | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-20 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-01-21 | 63 | 45 | 2025-01-21 | 2025-01-21 | 1 | 1 | 46 | 34 | 65 | 47 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 2608.55 | Unknown | Unknown | Unknown | 28.56 | 2579.99 | 3981 | 1916.7 | 2608.55 | -691.85 | Yes | N/A | N/A | 2024-07-10 | 2024-09-18 | 71 | 51 | 2024-09-18 | 2024-12-19 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-04-03 | 107 | 77 | 2024-12-19 | 2025-06-11 | 175 | 125 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-05-22 | 2025-06-18 | 28 | 20 | 2025-06-18 | 2025-06-11 | Unknown | Unknown | 246 | 176 | 228 | 164 | 474 | 340 | Steps 2,3,5,6,7 | 105 | 75 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-02-23 | -345 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-27 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 6.17 | -5.48 | Unknown | Unknown | Unknown | 11.65 | Unknown | 308.87 | 6.17 | 302.7 | Yes | N/A | N/A | 2024-02-26 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-03-01 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-15 | 15 | 11 | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-05 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 79.51 | 1146.18 | Unknown | 412.72 | -2065 | 585.61 | Unknown | 2065.09 | 79.51 | 1985.58 | Yes | N/A | N/A | 2022-12-09 | 2023-08-03 | 238 | 170 | 2023-08-03 | 2023-08-28 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | 2023-10-04 | Unknown | Unknown | 238 | 170 | 27 | 19 | 265 | 189 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 87.57 | -13.49 | Unknown | Unknown | Unknown | 101.06 | 3981 | 895.13 | 87.57 | 807.56 | Yes | N/A | N/A | 2024-01-09 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-01-09 | 22 | 16 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-03-08 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-25 | 18 | 12 | 2024-03-25 | 2024-03-25 | 1 | 1 | 60 | 44 | 41 | 29 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-01-25 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 7.89 | -9.57 | Unknown | Unknown | Unknown | 17.46 | Unknown | 896.26 | 7.89 | 888.37 | Yes | N/A | N/A | 2023-12-21 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-01-25 | 94 | 68 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-01-30 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-21 | 23 | 17 | 2024-02-21 | 2024-02-21 | 1 | 1 | 6 | 4 | 118 | 86 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -443 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -275.75 | -27.59 | Unknown | Unknown | -354 | 105.84 | 3981 | 672.61 | -275.75 | 948.36 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-07-31 | 130 | 92 | Unknown | 2023-04-12 | Unknown | Unknown | 2023-07-31 | 2023-08-09 | 10 | 8 | 2023-08-09 | 2023-08-15 | 7 | 5 | 131 | 93 | 17 | 13 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 1137.5 | -21.9 | Unknown | Unknown | Unknown | 1159.4 | 3981 | 1376.77 | 1137.5 | 239.27 | Yes | N/A | N/A | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-08-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-11 | 15 | 11 | 2024-09-11 | 2024-09-11 | 1 | 1 | 8 | 6 | 17 | 13 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-11 | -133 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 18489.14 | Unknown | Unknown | Unknown | -456 | 18945.14 | 3891 | 1604.81 | 18489.14 | -16884.33 | Yes | N/A | N/A | 2024-03-11 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-04-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-09-27 | 171 | 123 | Unknown | 2024-10-16 | Unknown | Unknown | 2024-10-24 | 2024-11-05 | 13 | 9 | 2024-11-05 | 2024-10-29 | Unknown | Unknown | 171 | 123 | 48 | 34 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 28.35 | 28.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-30 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 307.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-04-30 | 2 | 2 | 2024-04-30 | 2024-10-21 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-31 | 32 | 24 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-04 | 13 | 9 | 2024-11-04 | 2024-11-04 | 1 | 1 | 2 | 2 | 221 | 159 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-05 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | Unknown | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 74.74 | -0.94 | Unknown | Unknown | Unknown | 75.68 | 3981 | 1526.33 | 74.74 | 1451.59 | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-10 | 36 | 26 | 2024-10-10 | 2024-10-10 | 1 | 1 | 15 | 11 | 38 | 28 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -547 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 1007.66 | Unknown | Unknown | Unknown | Unknown | 1007.66 | 3981 | 1205.55 | 1007.66 | 197.89 | Yes | N/A | N/A | 2024-11-19 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-11-19 | 5 | 3 | 2024-11-19 | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-12 | 23 | 17 | 2024-11-19 | 2025-03-18 | 120 | 86 | Unknown | 2025-03-17 | Unknown | Unknown | 2025-03-18 | 2025-03-28 | 11 | 9 | 2025-03-28 | 2025-03-28 | 1 | 1 | 120 | 86 | 40 | 30 | 160 | 116 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-02-03 | 1322 | 945 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 133.41 | -32.94 | Unknown | Unknown | -1629 | 1795.35 | 0 | 1574.6 | 133.41 | 1441.19 | Yes | N/A | N/A | 2023-03-20 | 2023-06-07 | 80 | 58 | 2023-06-07 | 2024-02-28 | 267 | 191 | 2023-06-19 | 2023-06-20 | 2 | 2 | 2023-06-07 | 2024-08-26 | 72 | 52 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | 82 | 60 | 340 | 244 | 422 | 304 | Steps 2,3,5,6,7 | 447 | 319 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 849.2 | 849.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-10 | 320 | 229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-12-19 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 43864.99 | 2532.17 | Unknown | 288.6 | 44.56 | 40999.66 | 267037 | 24351.7 | 43864.99 | -19513.29 | Yes | N/A | N/A | 2023-06-01 | 2023-07-26 | 56 | 40 | 2023-07-26 | 2024-05-23 | 303 | 217 | 2024-03-26 | 2024-04-09 | 15 | 11 | 2024-05-24 | 2024-07-18 | 39 | 29 | 2024-05-23 | 2958465 | Unknown | Unknown | 2024-08-05 | 2024-11-25 | 113 | 81 | 2025-01-02 | 2025-02-24 | 54 | 38 | 2025-02-24 | 2025-02-24 | 1 | 1 | 71 | 51 | 510 | 366 | 581 | 417 | Steps 2,3,5,6,7 | 114 | 82 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 548.62 | -16 | Unknown | Unknown | 36.62 | 528 | Unknown | 1001.21 | 548.62 | 452.59 | Yes | N/A | N/A | 2024-04-30 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-02 | 44 | 32 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-28 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2025-03-20 | 297 | 213 | 2025-03-20 | 2024-07-25 | Unknown | Unknown | 27 | 19 | 341 | 245 | 368 | 264 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 1559.81 | Unknown | Unknown | Unknown | 22.24 | 1537.57 | 3981 | 1158.4 | 1559.81 | -401.41 | Yes | N/A | N/A | 2024-08-29 | 2024-10-28 | 61 | 43 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-19 | 53 | 39 | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2025-01-08 | 21 | 15 | 2025-01-08 | 2025-01-08 | 1 | 1 | 114 | 82 | 23 | 17 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 96.49 | -0.63 | Unknown | Unknown | Unknown | 97.12 | 3981 | 1548.91 | 96.49 | 1452.42 | Yes | N/A | N/A | 2024-10-17 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-22 | 9 | 7 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-10-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-07 | 16 | 12 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2 | 2 | 26 | 20 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -34 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-20 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 1635.55 | Unknown | Unknown | Unknown | Unknown | 1635.55 | 3981 | 1040.48 | 1635.55 | -595.07 | Yes | N/A | N/A | 2024-06-14 | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-06-20 | 32 | 24 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-08-16 | 58 | 42 | Unknown | 2024-07-25 | Unknown | Unknown | 2024-08-16 | 2024-08-27 | 12 | 8 | 2024-08-27 | 2024-08-27 | 1 | 1 | 58 | 42 | 45 | 33 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -471 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -55.71 | -40.37 | Unknown | Unknown | Unknown | -15.34 | Unknown | 98.41 | -55.71 | 154.12 | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-06-05 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-09-22 | 1 | 1 | 0 | 0 | 15 | 11 | 15 | 11 | Steps 2,3,5,6,7 | 77 | 55 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -368 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-09 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 7199.69 | -4.14 | Unknown | Unknown | 35.46 | 7168.37 | 3981 | 1868.84 | 7199.69 | -5330.85 | Yes | N/A | N/A | 2024-09-06 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-12-06 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-02-06 | 29 | 21 | 2025-02-06 | 2025-01-28 | Unknown | Unknown | 15 | 11 | 129 | 93 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -374 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.12 | -15.28 | Unknown | Unknown | Unknown | 27.4 | 3981 | 645.66 | 12.12 | 633.54 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-01-24 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 3.86 | Unknown | Unknown | Unknown | Unknown | 3.86 | Unknown | 443.54 | 3.86 | 439.68 | Yes | N/A | N/A | 2024-06-21 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-06-21 | 8 | 6 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-10-10 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-22 | 13 | 9 | 2024-10-22 | 2024-10-22 | 1 | 1 | 112 | 80 | 22 | 16 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -423 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 2173.84 | 483.36 | Unknown | 120.93 | 3.16 | 1566.39 | 3981 | 2012.89 | 2173.84 | -160.95 | Yes | N/A | N/A | 2023-04-04 | 2023-09-29 | 179 | 129 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-12-07 | 70 | 50 | Unknown | 2023-11-16 | Unknown | Unknown | 2023-12-07 | 2023-12-12 | 6 | 4 | 2023-12-12 | 2023-12-12 | 1 | 1 | 249 | 179 | 8 | 6 | 257 | 185 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 97.1 | 97.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1492.64 | -7.97 | Unknown | Unknown | -1933 | 448.33 | Unknown | 1932.99 | -1492.64 | 3425.63 | Yes | N/A | N/A | 2024-10-30 | 2025-01-30 | 93 | 67 | 2025-01-30 | 2025-03-03 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-25 | 22 | 16 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-15 | 1 | 1 | 93 | 67 | 56 | 40 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-28 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 935.47 | 349.41 | Unknown | Unknown | Unknown | 586.06 | 3981 | 769.84 | 935.47 | -165.63 | Yes | N/A | N/A | 2023-06-16 | 2023-06-16 | 1 | 1 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-07 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-08 | 2 | 2 | 2023-08-08 | 2023-08-08 | 1 | 1 | 54 | 38 | 3 | 3 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | 335 | 240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1172.26 | -11.09 | Unknown | Unknown | -993.66 | 2177.01 | 0 | 1051.85 | 1172.26 | -120.41 | Yes | N/A | N/A | 2023-07-18 | 2023-06-23 | Unknown | Unknown | 2023-06-23 | 2024-03-21 | 273 | 195 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2025-04-11 | 16 | 12 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 0 | 0 | 290 | 208 | 290 | 208 | Steps 2,3,5,6,7 | 386 | 276 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-10 | 114 | 83 | No | 2024-06-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-07 | 2024-09-13 | IOU Designed & Installed | N/A | Yes | 105 | 1530.45 | 759.9 | Unknown | 70.33 | Unknown | 700.22 | 3961 | 283.53 | 1530.45 | -1246.92 | Yes | N/A | N/A | 2024-06-04 | 2024-09-13 | 102 | 74 | 2024-09-13 | 2024-09-17 | 5 | 3 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-09-13 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-02 | 20 | 14 | 2024-10-02 | 2024-10-02 | 1 | 1 | 188 | 136 | 26 | 18 | 214 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 316 | 227 | No | 2023-09-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-30 | 2023-09-30 | 2024-09-30 | IOU Designed & Installed | N/A | Yes | 354 | 3015.25 | 830.59 | Unknown | 217.08 | 77.02 | 1890.56 | 3281 | 958.81 | 3015.25 | -2056.44 | Yes | N/A | N/A | 2023-09-30 | 2024-09-18 | 355 | 253 | 2024-09-18 | 2023-09-30 | Unknown | Unknown | 2023-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-30 | 2024-09-30 | 367 | 261 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-01-16 | 109 | 79 | 2025-01-16 | 2024-11-12 | Unknown | Unknown | 722 | 514 | 109 | 79 | 831 | 593 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 290 | 209 | No | 2023-01-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | Yes | 377 | 504.59 | -8.86 | Unknown | Unknown | Unknown | 513.45 | 15924 | 1082.32 | 504.59 | 577.73 | Yes | N/A | N/A | 2023-01-25 | 2023-10-24 | 273 | 195 | 2023-10-24 | 2024-02-16 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-16 | Unknown | Unknown | 273 | 195 | 124 | 90 | 397 | 285 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -578 | -414 | No | 2024-12-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-04-18 | IOU Designed & Installed | N/A | Yes | 147 | 12967.01 | 2936.8 | Unknown | 621.88 | Unknown | 9408.33 | 3981 | 1260.28 | 12967.01 | -11706.73 | Yes | N/A | N/A | 2024-12-05 | 2025-05-01 | 148 | 106 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-04-18 | 135 | 97 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-18 | 2025-05-06 | 19 | 13 | 2025-05-06 | 2025-05-06 | 1 | 1 | 283 | 203 | 21 | 15 | 304 | 218 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 640 | 640 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 1568.39 | 588.42 | Unknown | Unknown | Unknown | 979.97 | 11823 | 619.85 | 1568.39 | -948.54 | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-10-19 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-25 | 7 | 5 | 2023-10-25 | 2023-10-25 | 1 | 1 | 33 | 25 | 9 | 7 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-20 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 416.83 | -7.5 | Unknown | Unknown | 3.21 | 421.12 | 3981 | 1442.19 | 416.83 | 1025.36 | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-10-31 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-03-04 | 125 | 89 | 2025-03-04 | 2025-03-04 | 1 | 1 | 5 | 5 | 127 | 91 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -555 | -398 | No | 2023-07-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-28 | 2023-09-27 | IOU Designed & Installed | N/A | Yes | 58 | 3034.29 | 992.88 | Unknown | 235.84 | Unknown | 1805.57 | 3961 | 1853.1 | 3034.29 | -1181.19 | Yes | N/A | N/A | 2023-07-19 | 2023-07-28 | 10 | 8 | 2023-07-28 | 2023-09-15 | 50 | 36 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-09-27 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-09-27 | 1 | 1 | 23 | 17 | 52 | 38 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.53 | Unknown | Unknown | Unknown | Unknown | 14.53 | Unknown | 307.58 | 14.53 | 293.05 | Yes | N/A | N/A | 2024-04-23 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-04-23 | 111 | 79 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-07-30 | 1 | 1 | 0 | 0 | 112 | 80 | 112 | 80 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 83.1 | 83.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-30 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 754.7 | -7.91 | Unknown | Unknown | Unknown | 762.61 | 3981 | 1096.15 | 754.7 | 341.45 | Yes | N/A | N/A | 2023-11-28 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2023-11-30 | 32 | 24 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-05-03 | 156 | 112 | Unknown | 2024-04-19 | Unknown | Unknown | 2024-05-03 | 2024-05-10 | 8 | 6 | 2024-05-10 | 2024-05-09 | Unknown | Unknown | 156 | 112 | 40 | 30 | 196 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-19 | -4 | -3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | -9.18 | -7.24 | Unknown | Unknown | Unknown | -1.94 | Unknown | 158.79 | -9.18 | 167.97 | Yes | N/A | N/A | 2023-05-23 | 2023-12-15 | 207 | 149 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-20 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-03-15 | 87 | 63 | 2024-03-15 | 2024-03-15 | 1 | 1 | 213 | 153 | 88 | 64 | 301 | 217 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -488 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2025-01-13 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 1678.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2025-01-13 | 62 | 44 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-04-08 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-17 | 10 | 8 | 2025-04-17 | 2025-04-15 | Unknown | Unknown | 148 | 106 | 10 | 8 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 20.25 | 20.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | -16 | -13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1778.43 | -22.08 | Unknown | Unknown | -3068 | 1311.65 | Unknown | 2457.75 | -1778.43 | 4236.18 | Yes | N/A | N/A | 2023-05-17 | 2023-07-25 | 70 | 50 | 2023-07-25 | 2023-08-22 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-16 | 9 | 7 | 2023-08-22 | 2024-03-22 | 214 | 154 | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-04-10 | 1 | 1 | 284 | 204 | 39 | 29 | 323 | 233 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-02 | 226 | 161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3443.19 | 7020.63 | Unknown | 1733.57 | -8142 | 2830.99 | 0 | 8141.53 | 3443.19 | 4698.34 | Yes | N/A | N/A | 2023-02-08 | 2023-04-20 | 72 | 52 | 2023-04-20 | 2023-05-16 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 72 | 52 | 28 | 20 | 100 | 72 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | 100 | 73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1114.97 | -22.41 | Unknown | Unknown | Unknown | 1137.38 | 3981 | 2129.86 | 1114.97 | 1014.89 | Yes | N/A | N/A | 2024-09-30 | 2024-10-02 | 3 | 3 | 2024-10-02 | 2024-10-10 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-11-01 | 30 | 22 | 2024-10-10 | 2025-04-03 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-25 | Unknown | Unknown | 179 | 129 | 39 | 29 | 218 | 158 | Steps 2,3,5,6,7 | 22 | 16 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 9 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-03 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 1231.28 | Unknown | Unknown | Unknown | Unknown | 1231.28 | Unknown | 1291.52 | 1231.28 | 60.24 | Yes | N/A | N/A | 2022-11-17 | 2023-09-26 | 314 | 224 | 2023-09-26 | 2023-09-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-24 | 14 | 10 | 2023-10-24 | 2023-10-24 | 1 | 1 | 314 | 224 | 16 | 12 | 330 | 236 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 1252.03 | -37.31 | Unknown | Unknown | Unknown | 1289.34 | 3981 | 1806.52 | 1252.03 | 554.49 | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-04-02 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-10 | 9 | 7 | 2025-04-10 | 2025-04-10 | 1 | 1 | 116 | 84 | 11 | 9 | 127 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 82.1 | 82.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -492 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-26 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 29.88 | Unknown | Unknown | Unknown | Unknown | 29.88 | Unknown | 1553.31 | 29.88 | 1523.43 | Yes | N/A | N/A | 2024-09-20 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-09-26 | 38 | 28 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-02-27 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-07 | 9 | 7 | 2025-03-07 | 2025-03-07 | 1 | 1 | 155 | 111 | 48 | 36 | 203 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-29 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 3502.78 | 924.74 | Unknown | 70.33 | Unknown | 2507.71 | Unknown | 1570.86 | 3502.78 | -1931.92 | Yes | N/A | N/A | 2024-07-09 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-29 | 55 | 39 | 2024-07-29 | 2024-09-04 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-07-31 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-10-02 | 64 | 46 | 2024-10-02 | 2024-10-02 | 1 | 1 | 41 | 31 | 120 | 86 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | 52 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1030.65 | -80.1 | Unknown | Unknown | -1257 | 2367.75 | 58681.65 | 4364.17 | 1030.65 | 3333.52 | Yes | N/A | N/A | 2023-07-28 | 2023-07-28 | 1 | 1 | 2023-07-28 | 2023-08-22 | 26 | 18 | 2023-08-02 | 2023-08-03 | 2 | 2 | 2023-08-03 | 2023-08-11 | 9 | 7 | 2023-08-22 | 2024-05-01 | 254 | 182 | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-13 | Unknown | Unknown | 257 | 185 | 35 | 25 | 292 | 210 | Steps 2,3,5,6,7 | 20 | 14 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -116 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1395.54 | 1691.14 | Unknown | 538.79 | -4468 | 842.53 | Unknown | 4468.32 | -1395.54 | 5863.86 | Yes | N/A | N/A | 2023-11-16 | 2023-11-17 | 2 | 2 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | 254 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 431.76 | Unknown | Unknown | Unknown | 9.76 | 422 | Unknown | 3637.61 | 431.76 | 3205.85 | Yes | N/A | N/A | 2024-01-02 | 2025-01-09 | 374 | 268 | 2025-01-09 | 2025-03-31 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-12-31 | 72 | 52 | 2025-03-31 | 2025-05-23 | 54 | 40 | Unknown | 2025-04-18 | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 428 | 308 | 156 | 112 | 584 | 420 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 234 | 234 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 783 | 560 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-13 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 3461.23 | 384.84 | Unknown | 354.25 | 85.84 | 2636.3 | 3981 | 1522.36 | 3461.23 | -1938.87 | Yes | N/A | N/A | 2023-08-30 | 2023-09-13 | 15 | 11 | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2025-05-06 | 602 | 430 | Unknown | 2025-03-21 | Unknown | Unknown | 2025-05-06 | 2025-05-22 | 17 | 13 | 2025-05-22 | 2025-05-22 | 1 | 1 | 617 | 441 | 19 | 15 | 636 | 456 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 34860.57 | 7352.52 | Unknown | Unknown | Unknown | 27508.05 | Unknown | 5808.53 | 34860.57 | -29052.04 | Yes | N/A | N/A | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-06 | 7 | 5 | 2023-11-30 | 2023-12-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-17 | 31 | 23 | 2024-01-17 | 2024-01-17 | 1 | 1 | 20 | 14 | 39 | 29 | 59 | 43 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | -116 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1325.18 | -24.66 | Unknown | Unknown | 4.25 | 1345.59 | 3981 | 1558.71 | 1325.18 | 233.53 | Yes | N/A | N/A | 2024-06-20 | 2024-07-31 | 42 | 30 | 2024-07-31 | 2024-08-22 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-30 | 31 | 23 | 2024-08-22 | 2024-11-26 | 97 | 69 | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-11-26 | Unknown | Unknown | 139 | 99 | 54 | 40 | 193 | 139 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 47 | 34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1004.92 | -6.77 | Unknown | Unknown | 14.92 | 996.77 | 1000 | 894.41 | 1004.92 | -110.51 | Yes | N/A | N/A | 2023-09-27 | 2023-10-20 | 24 | 18 | 2023-10-20 | 2023-10-24 | 5 | 3 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-06-17 | 1 | 1 | 24 | 18 | 6 | 4 | 30 | 22 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | 1119 | 800 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1315.08 | -23.56 | Unknown | Unknown | Unknown | 1338.64 | Unknown | 3963.82 | 1315.08 | 2648.74 | Yes | N/A | N/A | 2024-09-24 | 2024-10-10 | 17 | 13 | 2024-10-10 | 2024-11-11 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-08 | 30 | 22 | 2024-11-11 | 2025-01-23 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-23 | Unknown | Unknown | 91 | 67 | 63 | 45 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 688.63 | -13.2 | Unknown | Unknown | Unknown | 701.83 | 3981 | 1501.7 | 688.63 | 813.07 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-29 | 2 | 2 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-30 | 13 | 9 | 2024-09-30 | 2024-09-30 | 1 | 1 | 22 | 16 | 16 | 12 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-25 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 10207.13 | -116.21 | Unknown | Unknown | Unknown | 10323.34 | 19313 | 2564.35 | 10207.13 | -7642.78 | Yes | N/A | N/A | 2025-02-05 | 2025-01-29 | Unknown | Unknown | 2025-01-29 | 2025-02-07 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-06 | 28 | 20 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-17 | 2025-04-07 | 22 | 16 | 2025-04-07 | 2025-04-02 | Unknown | Unknown | 28 | 20 | 32 | 24 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | 203 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-19 | 2024-07-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 41867.84 | 9802.74 | Unknown | Unknown | 167.1 | 31898 | 599648 | 28957.99 | 41867.84 | -12909.85 | Yes | N/A | N/A | 2024-01-10 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2024-02-13 | 134 | 96 | 2023-10-10 | 2023-10-25 | 16 | 12 | 2024-02-06 | 2024-03-01 | 17 | 11 | 2024-02-13 | Unknown | Unknown | Unknown | 2024-04-03 | 2024-07-18 | 107 | 77 | 2024-07-29 | 2024-09-03 | 37 | 27 | 2024-09-03 | 2024-09-03 | 1 | 1 | 16 | 12 | 296 | 212 | 312 | 224 | Steps 2,3,5,6,7 | 143 | 103 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -552 | -395 | No | 2024-09-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2025-01-31 | IOU Designed & Installed | N/A | Yes | 108 | 2545.85 | 137.39 | Unknown | Unknown | 12.69 | 2395.77 | 3981 | 1369.35 | 2545.85 | -1176.5 | Yes | N/A | N/A | 2024-09-30 | 2025-01-16 | 109 | 79 | 2025-01-16 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2025-01-31 | 122 | 88 | Unknown | 2024-12-30 | Unknown | Unknown | 2025-01-31 | 2025-02-20 | 21 | 15 | 2025-02-20 | 2025-02-24 | 5 | 3 | 231 | 167 | 26 | 18 | 257 | 185 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -296 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 1416.06 | Unknown | Unknown | Unknown | 28.84 | 1387.22 | 3981 | 812.25 | 1416.06 | -603.81 | Yes | N/A | N/A | 2024-09-09 | 2024-11-10 | 63 | 45 | 2024-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-08 | 27 | 19 | Unknown | 2025-04-25 | Unknown | Unknown | 2025-01-08 | 2025-06-30 | 174 | 124 | 2025-06-30 | 2025-06-30 | 1 | 1 | 90 | 64 | 175 | 125 | 265 | 189 | Steps 2,3,5,6,7 | 107 | 77 | Unknown | Meeting | Not Available | N/A
| R29/R45 | UG | Applicant Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-05 | 427 | 306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-13 | 2023-04-18 | 2024-03-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 70141.78 | -229.2 | Unknown | Unknown | 1045.23 | 69325.75 | 0 | 14444.64 | 70141.78 | -55697.14 | Yes | N/A | N/A | 2022-10-13 | 2023-04-14 | 184 | 132 | 2023-04-14 | 2024-04-03 | 356 | 254 | 2023-05-25 | 2023-10-17 | 29 | 21 | 2023-07-05 | 2023-09-20 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | 2024-03-29 | 2024-09-04 | 160 | 114 | 2024-09-04 | 2024-09-04 | 1 | 1 | 213 | 153 | 521 | 373 | 734 | 526 | Steps 2,3,5,6,7 | 502 | 358 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 2029.05 | 457.31 | Unknown | Unknown | Unknown | 1571.74 | 3981 | 1962.61 | 2029.05 | -66.44 | Yes | N/A | N/A | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-01-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-19 | 44 | 32 | 2025-02-19 | 2025-02-19 | 1 | 1 | 10 | 8 | 46 | 34 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-12 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 1566.52 | 376.81 | Unknown | 32.17 | 1.94 | 1155.6 | 3981 | 840.38 | 1566.52 | -726.14 | Yes | N/A | N/A | 2024-03-07 | 2024-03-18 | 12 | 8 | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-03 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-09 | 7 | 5 | 2024-04-09 | 2024-04-09 | 1 | 1 | 28 | 20 | 10 | 8 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-26 | 72 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-25 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 442.03 | -30.39 | Unknown | Unknown | 22.09 | 450.33 | 3981 | 2670.51 | 442.03 | 2228.48 | Yes | N/A | N/A | 2023-02-22 | 2023-02-24 | 3 | 3 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-25 | 2023-07-19 | 145 | 103 | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-19 | 2023-10-06 | 80 | 58 | 2023-10-06 | 2023-10-06 | 1 | 1 | 148 | 106 | 81 | 59 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 151 | 151 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-04 | 986 | 705 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-04 | 2022-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 287.23 | -12.92 | Unknown | Unknown | -354 | 654.15 | 3981 | 760.72 | 287.23 | 473.49 | Yes | N/A | N/A | 2021-02-04 | 2023-02-07 | 734 | 524 | 2023-02-07 | Unknown | Unknown | Unknown | 2023-02-28 | 2023-04-17 | 49 | 35 | 2023-02-07 | 2024-11-06 | 592 | 424 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-11-14 | Unknown | Unknown | 783 | 559 | 592 | 424 | 1375 | 983 | Steps 2,3,5,6,7 | 434 | 310 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-03 | 569 | 408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1511.27 | -12.15 | Unknown | Unknown | -2802 | 1302.88 | Unknown | 2421.4 | -1511.27 | 3932.67 | Yes | N/A | N/A | 2024-02-29 | 2024-03-01 | 2 | 2 | 2024-03-01 | 2024-04-12 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1 | 1 | 2 | 2 | 44 | 32 | 46 | 34 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-28 | 1426 | 1019 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 340.58 | -12.44 | Unknown | Unknown | Unknown | 353.02 | 11851.63 | 469.38 | 340.58 | 128.8 | Yes | N/A | N/A | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | 2023-12-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-08 | 36 | 26 | Unknown | 2023-12-27 | Unknown | Unknown | 2024-01-22 | 2024-03-15 | 54 | 40 | 2024-03-15 | 2024-01-24 | Unknown | Unknown | 37 | 27 | 58 | 42 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-11-04 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 6006.97 | 1400.85 | Unknown | 757.17 | 19.8 | 3829.15 | 3981 | 1660.96 | 6006.97 | -4346.01 | Yes | N/A | N/A | 2024-10-24 | 2024-10-29 | 6 | 4 | 2024-10-29 | 2024-11-04 | 7 | 5 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-05 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-12-18 | 44 | 32 | 2024-12-18 | 2024-12-18 | 1 | 1 | 8 | 6 | 52 | 38 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 363.01 | -7.37 | Unknown | Unknown | Unknown | 370.38 | 54899 | 81.53 | 363.01 | -281.48 | Yes | N/A | N/A | 2024-03-06 | 2024-08-05 | 153 | 109 | 2024-08-05 | 2025-03-27 | 235 | 169 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-07-16 | 53 | 39 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-14 | 1 | 1 | 153 | 109 | 289 | 209 | 442 | 318 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -291 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 40.66 | Unknown | Unknown | Unknown | Unknown | 40.66 | 3981 | 1616.47 | 40.66 | 1575.81 | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-24 | 28 | 20 | 2025-03-24 | 2025-03-24 | 1 | 1 | 30 | 22 | 30 | 22 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 232 | 232 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | 264 | 189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-06 | 2023-01-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 23.57 | Unknown | Unknown | Unknown | Unknown | 23.57 | 3981 | 821.62 | 23.57 | 798.05 | Yes | N/A | N/A | 2023-01-06 | 2023-12-05 | 334 | 238 | 2023-12-05 | 2023-12-11 | 7 | 5 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-10-16 | 1 | 1 | 334 | 238 | 8 | 6 | 342 | 244 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | -3.92 | -6.48 | Unknown | Unknown | Unknown | 2.56 | Unknown | 148.7 | -3.92 | 152.62 | Yes | N/A | N/A | 2023-07-25 | 2023-08-29 | 36 | 26 | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-08-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-10-02 | 34 | 24 | 2023-10-02 | 2023-10-02 | 1 | 1 | 38 | 28 | 36 | 26 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -702 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 591.19 | 181.27 | Unknown | Unknown | Unknown | 409.92 | Unknown | 1458.15 | 591.19 | 866.96 | Yes | N/A | N/A | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-29 | 6 | 4 | 2024-07-29 | 2024-07-29 | 1 | 1 | 14 | 10 | 8 | 6 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | 2025-01-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 164211.85 | 22500.53 | Unknown | 55.44 | 790.44 | 140865.44 | 4111552 | 95728.97 | 164211.85 | -68482.88 | Yes | N/A | N/A | 2023-05-31 | 2023-09-26 | 119 | 85 | 2023-09-26 | 2024-02-23 | 151 | 109 | 2023-10-18 | 2023-11-09 | 23 | 17 | 2024-01-26 | 2024-02-02 | 8 | 6 | 2024-02-23 | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-14 | 7 | 5 | 2025-01-16 | 2025-03-11 | 55 | 39 | 2025-03-11 | 2025-03-11 | 1 | 1 | 142 | 102 | 222 | 160 | 364 | 262 | Steps 2,3,5,6,7 | 128 | 92 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1420.89 | Unknown | Unknown | Unknown | 12.87 | 1408.02 | 3981 | 1280.72 | 1420.89 | -140.17 | Yes | N/A | N/A | 2024-09-17 | 2024-09-16 | Unknown | Unknown | 2024-09-16 | 2024-10-09 | 24 | 18 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 0 | 0 | 25 | 19 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 158.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | 2023-11-29 | 3 | 3 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-19 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-19 | 32 | 24 | 2024-01-19 | 2024-01-19 | 1 | 1 | 21 | 15 | 36 | 28 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-03 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | -9.17 | -8.57 | Unknown | Unknown | Unknown | -0.6 | Unknown | 176.76 | -9.17 | 185.93 | Yes | N/A | N/A | 2024-03-27 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-04-16 | 54 | 38 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-09 | 23 | 17 | 2024-05-09 | 2024-05-09 | 1 | 1 | 2 | 2 | 78 | 56 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | Bonsall | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | 64 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-10-04 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 22710.74 | 6333.26 | Unknown | Unknown | 99.42 | 16278.06 | 45559 | 19275.03 | 22710.74 | -3435.71 | Yes | N/A | N/A | 2023-08-29 | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2024-03-20 | 216 | 154 | 2024-02-28 | 2024-03-05 | 7 | 5 | 2024-03-12 | 2024-11-12 | 246 | 176 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-06 | 22 | 16 | 2024-12-06 | 2024-12-06 | 1 | 1 | 7 | 5 | 485 | 347 | 492 | 352 | Steps 2,3,5,6,7 | 258 | 184 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-06 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-30 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 486.75 | Unknown | Unknown | Unknown | 5.52 | 481.23 | 3981 | 1173.35 | 486.75 | 686.6 | Yes | N/A | N/A | 2025-01-23 | 2025-02-07 | 16 | 12 | 2025-02-07 | 2025-02-13 | 7 | 5 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-19 | 35 | 25 | Unknown | 2025-02-18 | Unknown | Unknown | 2025-03-19 | 2025-04-14 | 27 | 19 | 2025-04-14 | 2025-04-14 | 1 | 1 | 51 | 37 | 35 | 25 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 1279.05 | 1279.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-04-29 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1713.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-07-05 | 66 | 48 | 2024-07-05 | 2024-07-11 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2025-03-12 | 241 | 173 | Unknown | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-21 | 10 | 8 | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 248 | 178 | 76 | 56 | 324 | 234 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-25 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 7.72 | Unknown | Unknown | Unknown | Unknown | 7.72 | Unknown | 192.95 | 7.72 | 185.23 | Yes | N/A | N/A | 2024-07-15 | 2024-08-06 | 23 | 17 | 2024-08-06 | 2024-08-26 | 21 | 15 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-10-04 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-30 | 27 | 19 | 2024-10-30 | 2024-10-29 | Unknown | Unknown | 63 | 47 | 48 | 34 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -238 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 824.65 | -19.04 | Unknown | Unknown | Unknown | 843.69 | Unknown | 832.35 | 824.65 | 7.7 | Yes | N/A | N/A | 2023-12-18 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2023-12-18 | 28 | 20 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-30 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-03-15 | 46 | 34 | 2024-03-15 | 2024-03-15 | 1 | 1 | 44 | 32 | 75 | 55 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | 211 | 152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-12 | 2022-09-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 478.84 | -9.62 | Unknown | Unknown | Unknown | 488.46 | 0 | 489.36 | 478.84 | 10.52 | Yes | N/A | N/A | 2022-09-12 | 2024-05-28 | 625 | 447 | 2024-05-28 | 2024-05-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | 625 | 447 | 3 | 3 | 628 | 450 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-20 | -440 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-20 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 180.79 | -12.89 | Unknown | Unknown | Unknown | 193.68 | Unknown | 1116.78 | 180.79 | 935.99 | Yes | N/A | N/A | 2023-11-13 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | 2023-11-20 | 112 | 80 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-04-22 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-06 | 15 | 11 | 2024-05-06 | 2024-05-06 | 1 | 1 | 155 | 111 | 128 | 92 | 283 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 626 | 447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-08 | 2025-01-25 | IOU Designed & Installed | N/A | No | N/A | 3687.96 | 10593.64 | Unknown | 193.78 | -14361 | 7261.54 | Unknown | 14361.31 | 3687.96 | 10673.35 | Yes | N/A | N/A | 2025-01-07 | 2025-01-08 | 2 | 2 | 2025-01-08 | 2025-01-23 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-25 | 2025-01-26 | 2 | 0 | 2025-01-26 | 2025-01-26 | 1 | 0 | 2 | 2 | 19 | 12 | 21 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 861.7 | 315.37 | Unknown | Unknown | Unknown | 546.33 | 3981 | 962.73 | 861.7 | 101.03 | Yes | N/A | N/A | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-09-11 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-14 | 4 | 4 | 2023-09-14 | 2023-09-14 | 1 | 1 | 29 | 21 | 6 | 6 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 504.07 | -31.35 | Unknown | Unknown | 56.01 | 479.41 | 3981 | 1635.24 | 504.07 | 1131.17 | Yes | N/A | N/A | 2024-12-02 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-12-02 | 49 | 35 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-04-07 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-21 | 15 | 11 | 2025-04-21 | 2025-04-21 | 1 | 1 | 127 | 91 | 65 | 47 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 661.05 | 661.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-16 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | -67.98 | 386.28 | Unknown | Unknown | -1984 | 1529.74 | Unknown | 1837.3 | -67.98 | 1905.28 | Yes | N/A | N/A | 2025-04-08 | 2025-04-16 | 9 | 7 | 2025-04-16 | 2025-04-16 | 1 | 1 | 2025-04-16 | 2025-04-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-22 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-30 | 39 | 29 | 2025-05-30 | 2025-05-30 | 1 | 1 | 17 | 13 | 41 | 31 | 58 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2023-08-15 | IOU Designed & Installed | N/A | No | N/A | 4057.45 | 1259.39 | Unknown | 530.64 | Unknown | 2267.42 | 3981 | 780.82 | 4057.45 | -3276.63 | Yes | N/A | N/A | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-08-15 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-08-23 | 9 | 7 | 2023-08-23 | 2023-08-23 | 1 | 1 | 83 | 59 | 10 | 8 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 396 | 283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2355.81 | -31.23 | Unknown | Unknown | 15.56 | 2371.48 | 36349.88 | 2894.03 | 2355.81 | 538.22 | Yes | N/A | N/A | 2023-06-07 | 2023-08-21 | 76 | 54 | 2023-08-21 | 2023-09-08 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2024-06-18 | 285 | 203 | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-08 | Unknown | Unknown | 361 | 257 | 19 | 15 | 380 | 272 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 84190 | 84190 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-01 | 107 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 9253.16 | 418.82 | Unknown | 22.48 | 8.51 | 8803.35 | 223457 | 15435.23 | 9253.16 | 6182.07 | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | 2024-06-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-08 | 21 | 15 | 2024-06-20 | 2025-04-09 | 294 | 210 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-16 | 2025-05-05 | 20 | 14 | 2025-05-05 | 2025-04-18 | Unknown | Unknown | 295 | 211 | 56 | 40 | 351 | 251 | Steps 2,3,5,6,7 | 292 | 208 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-27 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 1597.47 | 416.72 | Unknown | 135.71 | -1197 | 2242.04 | Unknown | 1196.64 | 1597.47 | -400.83 | Yes | N/A | N/A | 2025-01-22 | 2025-01-23 | 2 | 2 | 2025-01-23 | 2025-01-27 | 5 | 3 | 2025-01-27 | 2025-01-29 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-31 | 62 | 44 | Unknown | 2025-03-20 | Unknown | Unknown | 2025-03-31 | 2025-04-08 | 9 | 7 | 2025-04-08 | 2025-04-08 | 1 | 1 | 67 | 49 | 15 | 11 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-24 | -132 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1421.34 | 411.3 | Unknown | 206.36 | 12.46 | 791.22 | 3981 | 2026.62 | 1421.34 | 605.28 | Yes | N/A | N/A | 2023-08-04 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | 2023-09-12 | 43 | 31 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -143 | -104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | -9142.9 | Unknown | Unknown | Unknown | -25177.98 | 16035.08 | Unknown | 1242.68 | -9142.9 | 10385.58 | Yes | N/A | N/A | 2024-03-11 | 2024-08-26 | 169 | 121 | 2024-08-26 | 2024-09-09 | 15 | 11 | 2024-09-09 | 2024-10-29 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-02-04 | 97 | 69 | Unknown | 2025-01-13 | Unknown | Unknown | 2025-02-04 | 2025-05-05 | 91 | 65 | 2025-05-05 | 2025-05-05 | 1 | 1 | 317 | 227 | 107 | 77 | 424 | 304 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | -323 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | -1905.8 | 602.57 | Unknown | 302.6 | -3159 | 348.03 | Unknown | 3159.09 | -1905.8 | 5064.89 | Yes | N/A | N/A | 2023-07-25 | 2023-07-26 | 2 | 2 | 2023-07-26 | 2023-08-03 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2 | 2 | 11 | 9 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-13 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 2019.5 | 1097.67 | Unknown | Unknown | -1722 | 2643.83 | Unknown | 2510.39 | 2019.5 | 490.89 | Yes | N/A | N/A | 2025-02-28 | 2025-03-21 | 22 | 16 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-06-10 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-17 | 8 | 6 | 2025-06-17 | 2025-06-17 | 1 | 1 | 105 | 75 | 10 | 8 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 171.05 | 171.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | -40 | -29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 60.95 | Unknown | Unknown | Unknown | Unknown | 60.95 | 3981 | 1639.8 | 60.95 | 1578.85 | Yes | N/A | N/A | 2024-09-26 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-10-10 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-21 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-09 | 15 | 11 | 2024-12-09 | 2024-12-06 | Unknown | Unknown | 43 | 31 | 65 | 47 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 312 | 223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-06-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26305.86 | 1556.8 | Unknown | Unknown | 10.44 | 24738.62 | 38264 | 35707.35 | 26305.86 | 9401.49 | Yes | N/A | N/A | 2023-03-27 | 2024-01-26 | 306 | 220 | 2024-01-26 | 2024-04-29 | 95 | 67 | 2023-08-15 | 2024-08-21 | 93 | 67 | 2024-04-15 | 2024-09-03 | 51 | 37 | 2024-04-29 | 2024-08-06 | 100 | 72 | 2024-07-09 | 2024-08-13 | 36 | 26 | Unknown | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-09 | Unknown | Unknown | 499 | 359 | 182 | 130 | 681 | 489 | Steps 2,3,5,6,7 | 541 | 387 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 22216.48 | 3481.82 | Unknown | Unknown | Unknown | 18734.66 | Unknown | 4273.05 | 22216.48 | -17943.43 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-04-12 | 6 | 4 | 2023-04-07 | 2023-06-23 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-07-25 | 33 | 23 | 2023-07-25 | 2023-07-25 | 1 | 1 | 79 | 57 | 40 | 28 | 119 | 85 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-12 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 337.27 | -24.15 | Unknown | Unknown | Unknown | 361.42 | 3981 | 629.51 | 337.27 | 292.24 | Yes | N/A | N/A | 2024-01-22 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-01-31 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-03-19 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-04-11 | Unknown | Unknown | 49 | 35 | 97 | 69 | 146 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 65.5 | 65.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | -228 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-02-21 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 14.49 | -12.83 | Unknown | Unknown | Unknown | 27.32 | 3981 | 1584.44 | 14.49 | 1569.95 | Yes | N/A | N/A | 2024-01-11 | 2024-02-21 | 42 | 30 | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-05-09 | 79 | 57 | Unknown | 2024-05-08 | Unknown | Unknown | 2024-05-09 | 2024-05-17 | 9 | 7 | 2024-05-17 | 2024-05-16 | Unknown | Unknown | 121 | 87 | 10 | 8 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 189.11 | -3.4 | Unknown | Unknown | Unknown | 192.51 | Unknown | 488.99 | 189.11 | 299.88 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-07-10 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-18 | 28 | 20 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-09-03 | 1 | 1 | 3 | 3 | 99 | 71 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 382 | 273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 4097.2 | 1098.46 | Unknown | 117.05 | 15.62 | 2866.07 | 15924 | 4234.24 | 4097.2 | 137.04 | Yes | N/A | N/A | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | 2024-10-17 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-15 | 31 | 23 | 2024-10-17 | 2024-11-06 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-16 | 5 | 3 | 2024-12-16 | 2024-12-16 | 1 | 1 | 22 | 16 | 40 | 30 | 62 | 46 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -702 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-03 | 2024-08-03 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 668.31 | 218.6 | Unknown | Unknown | Unknown | 449.71 | 3981 | 1587.31 | 668.31 | 919 | Yes | N/A | N/A | 2024-08-03 | 2024-08-03 | 1 | 0 | 2024-08-03 | 2024-08-06 | 4 | 2 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | 2024-08-06 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-12 | 7 | 5 | 2024-08-12 | 2024-08-12 | 1 | 1 | 5 | 2 | 12 | 8 | 17 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-02 | 1072 | 767 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 85098.87 | 38119 | Unknown | Unknown | Unknown | 46979.87 | 1999410 | 40976.87 | 85098.87 | -44122 | Yes | N/A | N/A | 2024-12-30 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-09 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-10 | 3 | 3 | 2025-01-09 | 2025-03-17 | 68 | 48 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-05-16 | 2025-05-09 | Unknown | Unknown | 68 | 48 | 35 | 27 | 103 | 75 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | -360 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | -426.69 | -14.36 | Unknown | Unknown | -1132 | 719.67 | Unknown | 1016.86 | -426.69 | 1443.55 | Yes | N/A | N/A | 2024-07-26 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-07-26 | 59 | 43 | 2024-07-26 | 2024-08-23 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-23 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-10-01 | 40 | 28 | 2024-10-01 | 2024-10-01 | 1 | 1 | 30 | 22 | 100 | 72 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 262 | 187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-06 | 2023-01-06 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 1613.05 | -13.16 | Unknown | Unknown | 66.89 | 1559.32 | Unknown | 368.59 | 1613.05 | -1244.46 | Yes | N/A | N/A | 2023-01-06 | 2023-06-14 | 160 | 114 | 2023-06-14 | 2023-06-20 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2024-01-02 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-03-15 | 15 | 11 | 2024-03-15 | 2024-03-04 | Unknown | Unknown | 160 | 114 | 105 | 75 | 265 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -481 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-02-12 | 2024-02-14 | IOU Designed & Installed | N/A | No | N/A | 343 | -9.4 | Unknown | Unknown | Unknown | 352.4 | Unknown | 889.64 | 343 | 546.64 | Yes | N/A | N/A | 2023-12-13 | 2024-02-09 | 59 | 43 | 2024-02-09 | 2024-02-12 | 4 | 2 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-14 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-05-20 | 97 | 69 | 2024-05-20 | 2024-05-20 | 1 | 1 | 62 | 46 | 102 | 72 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | -75 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1963.73 | -8.26 | Unknown | Unknown | -2893.47 | 4865.46 | Unknown | 2785.28 | 1963.73 | 821.55 | Yes | N/A | N/A | 2024-10-02 | 2024-10-21 | 20 | 14 | 2024-10-21 | 2024-12-26 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-12 | 32 | 24 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-14 | 1 | 1 | 20 | 14 | 100 | 74 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | -30 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-07 | 2023-03-29 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 7184.81 | 272.1 | Unknown | Unknown | -1070 | 7982.71 | 7329 | 1709.69 | 7184.81 | -5475.12 | Yes | N/A | N/A | 2022-10-07 | 2023-08-30 | 328 | 234 | 2023-08-30 | 2023-10-10 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | 2024-05-30 | 2024-06-21 | 23 | 17 | 2024-06-21 | 2024-06-21 | 1 | 1 | 328 | 234 | 66 | 48 | 394 | 282 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-06 | 591 | 424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 6.38 | -4.92 | Unknown | Unknown | Unknown | 11.3 | Unknown | 444.8 | 6.38 | 438.42 | Yes | N/A | N/A | 2024-06-21 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2024-07-11 | 308 | 220 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-19 | 9 | 7 | 2024-07-19 | 2024-07-19 | 1 | 1 | 0 | 0 | 318 | 228 | 318 | 228 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | 16 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-10-16 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 3754.19 | 1228.7 | Unknown | 124.14 | 59.63 | 2341.72 | 3981 | 1158.5 | 3754.19 | -2595.69 | Yes | N/A | N/A | 2023-09-01 | 2023-10-03 | 33 | 23 | 2023-10-03 | 2023-10-16 | 14 | 10 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-11-17 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-02-29 | 105 | 75 | 2024-02-29 | 2024-02-29 | 1 | 1 | 66 | 48 | 120 | 86 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA, SAN DIEGO | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-13 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 32917.08 | 1226.41 | Unknown | Unknown | 49.16 | 31641.51 | Unknown | 30796.37 | 32917.08 | -2120.71 | Yes | N/A | N/A | 2024-07-30 | 2024-08-01 | 3 | 3 | 2024-08-01 | 2025-03-11 | 223 | 159 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-20 | 30 | 18 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-06-11 | 57 | 41 | 2025-06-11 | 2025-06-11 | 1 | 1 | 3 | 3 | 311 | 219 | 314 | 222 | Steps 2,3,5,6,7 | 9 | 7 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-09 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.06 | Unknown | Unknown | Unknown | Unknown | 7.06 | Unknown | 388.05 | 7.06 | 380.99 | Yes | N/A | N/A | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-25 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 3459.4 | 3459.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-08-19 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-24 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 67.67 | Unknown | Unknown | Unknown | -1274 | 1341.67 | Unknown | 1138.54 | 67.67 | 1070.87 | Yes | N/A | N/A | 2024-09-18 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-09 | 42 | 30 | 2024-10-09 | 2024-12-03 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-17 | 30 | 22 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-24 | 8 | 6 | 2025-01-24 | 2025-01-23 | Unknown | Unknown | 86 | 62 | 50 | 36 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | -234 | -168 | No | 2023-10-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-19 | 2024-11-20 | IOU Designed & Installed | N/A | Yes | 168 | 1801.35 | Unknown | Unknown | Unknown | 18.58 | 1782.77 | 3961 | 1164.61 | 1801.35 | -636.74 | Yes | N/A | N/A | 2023-10-13 | 2024-03-26 | 166 | 118 | 2024-03-26 | 2024-03-29 | 4 | 4 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-11-20 | 318 | 228 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-11-20 | 1 | 1 | 484 | 346 | 6 | 6 | 490 | 352 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | 15 | 12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1079.53 | -44.15 | Unknown | Unknown | Unknown | 1123.68 | 27449 | 656.74 | 1079.53 | -422.79 | Yes | N/A | N/A | 2024-03-29 | 2024-08-12 | 137 | 97 | 2024-08-12 | 2024-10-23 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-11-16 | 93 | 66 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 137 | 97 | 167 | 120 | 304 | 217 | Steps 2,3,5,6,7 | 24 | 17 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 65.4 | 65.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-30 | -447 | -320 | No | 2024-01-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-27 | 2024-04-18 | IOU Designed & Installed | N/A | Yes | 114 | 29122.7 | 8029.06 | Unknown | Unknown | -11526 | 32619.64 | 2336 | 25388.57 | 29122.7 | -3734.13 | Yes | N/A | N/A | 2023-11-21 | 2023-11-29 | 9 | 7 | 2023-11-29 | 2024-01-23 | 56 | 40 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-22 | 2024-04-10 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-05-09 | 22 | 16 | 2024-05-09 | 2024-05-09 | 1 | 1 | 10 | 8 | 159 | 115 | 169 | 123 | Steps 2,3,5,6,7 | 4 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | 136000 | 136000 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-05-31 | 751 | 538 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | 1858.33 | Unknown | Unknown | Unknown | Unknown | 1858.33 | 39341 | 3995.45 | 1858.33 | 2137.12 | Yes | N/A | N/A | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | 2024-12-05 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-05-22 | 169 | 121 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-19 | 2025-06-21 | 3 | 2 | 2025-06-21 | 2025-06-20 | Unknown | Unknown | 170 | 122 | 68 | 49 | 238 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 31200 | 31200 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-05-17 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-26 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 20.77 | Unknown | Unknown | Unknown | Unknown | 20.77 | Unknown | 1451.19 | 20.77 | 1430.42 | Yes | N/A | N/A | 2024-06-24 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-06-26 | 36 | 26 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-31 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-19 | 20 | 14 | 2024-08-19 | 2024-08-19 | 1 | 1 | 36 | 26 | 57 | 41 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -137 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 932.9 | -18.74 | Unknown | Unknown | Unknown | 951.64 | 19455 | 1879.23 | 932.9 | 946.33 | Yes | N/A | N/A | 2024-09-10 | 2024-11-22 | 74 | 54 | 2024-11-22 | 2024-11-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-09 | 46 | 34 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 74 | 54 | 53 | 39 | 127 | 93 | Steps 2,3,5,6,7 | 43 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CALTRANS-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | 300 | 215 | No | 2023-10-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | Yes | 147 | 19286.95 | Unknown | Unknown | Unknown | 33.29 | 19253.66 | 3981 | 796.12 | 19286.95 | -18490.83 | Yes | N/A | N/A | 2023-10-12 | 2024-03-07 | 148 | 106 | 2024-03-07 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2025-01-02 | 3 | 3 | 2023-10-26 | 2025-01-07 | 56 | 40 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-03-14 | 1 | 1 | 151 | 109 | 57 | 41 | 208 | 150 | Steps 2,3,5,6,7 | 873 | 623 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -164 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 219.65 | -3.65 | Unknown | Unknown | Unknown | 223.3 | Unknown | 560.1 | 219.65 | 340.45 | Yes | N/A | N/A | 2024-04-09 | 2024-04-09 | 1 | 1 | 2024-04-09 | 2024-04-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-08-27 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | Steps 2,3,5,6,7 | 128 | 92 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | 12 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-08 | 2025-06-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2458.84 | 1423.95 | Unknown | Unknown | -4241.09 | 5275.98 | Unknown | 4243.19 | 2458.84 | 1784.35 | Yes | N/A | N/A | 2024-10-07 | 2025-05-02 | 208 | 150 | 2025-05-02 | 2025-05-05 | 4 | 2 | 2025-01-27 | 2025-05-02 | 96 | 70 | 2025-03-05 | 2025-05-21 | 28 | 20 | 2025-06-03 | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | 2025-06-13 | 1 | 1 | 304 | 220 | 34 | 24 | 338 | 244 | Steps 2,3,5,6,7 | 156 | 112 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 84.1 | 84.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 451.01 | Unknown | Unknown | Unknown | 8.28 | 442.73 | 3981 | 1199.58 | 451.01 | 748.57 | Yes | N/A | N/A | 2025-02-18 | 2025-03-07 | 18 | 14 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-06-04 | 90 | 64 | Unknown | 2025-05-09 | Unknown | Unknown | 2025-06-04 | 2025-06-05 | 2 | 2 | 2025-06-05 | 2025-06-05 | 1 | 1 | 108 | 78 | 4 | 4 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -711 | -510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-03 | 2024-08-03 | 2024-08-07 | IOU Designed & Installed | N/A | No | N/A | 6.23 | Unknown | Unknown | Unknown | Unknown | 6.23 | 3981 | 1409.63 | 6.23 | 1403.4 | Yes | N/A | N/A | 2024-08-03 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-06 | 6 | 4 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | 2024-08-07 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-12 | 6 | 4 | 2024-08-12 | 2024-08-12 | 1 | 1 | 5 | 3 | 13 | 9 | 18 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 132.42 | Unknown | Unknown | Unknown | Unknown | 132.42 | 3241 | 1945.67 | 132.42 | 1813.25 | Yes | N/A | N/A | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-23 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-10 | 18 | 14 | 2024-10-10 | 2024-10-10 | 1 | 1 | 7 | 5 | 20 | 16 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -509 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-29 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | 4.37 | Unknown | Unknown | Unknown | Unknown | 4.37 | Unknown | 1361.38 | 4.37 | 1357.01 | Yes | N/A | N/A | 2024-10-01 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-10-29 | 42 | 30 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-03-25 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-14 | 21 | 15 | 2025-04-14 | 2025-04-14 | 1 | 1 | 148 | 106 | 64 | 46 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -353 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | -22.28 | -18.1 | Unknown | Unknown | Unknown | -4.18 | Unknown | 163.83 | -22.28 | 186.11 | Yes | N/A | N/A | 2024-01-31 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-01-31 | 2 | 2 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-12 | 11 | 7 | 2024-02-12 | 2024-02-12 | 1 | 1 | 3 | 3 | 14 | 10 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-12 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-10 | IOU Designed & Installed | N/A | No | N/A | 821.81 | -11.76 | Unknown | Unknown | 3.08 | 830.49 | Unknown | 555.58 | 821.81 | -266.23 | Yes | N/A | N/A | 2023-03-20 | 2023-03-31 | 12 | 10 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-04-10 | 11 | 7 | Unknown | 2023-04-06 | Unknown | Unknown | 2023-04-10 | 2023-06-12 | 64 | 46 | 2023-06-12 | 2023-06-12 | 1 | 1 | 23 | 17 | 65 | 47 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -53 | -39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-07-14 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 16943.15 | 352.45 | Unknown | Unknown | -681.71 | 17272.41 | 3981 | 2054.85 | 16943.15 | -14888.3 | Yes | N/A | N/A | 2023-04-18 | 2023-07-14 | 88 | 64 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2024-11-14 | 465 | 333 | Unknown | 2023-10-13 | Unknown | Unknown | 2024-11-14 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-11-19 | 237 | 169 | 553 | 397 | 237 | 169 | 790 | 566 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2025-01-30 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1736.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2025-01-30 | 50 | 36 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-04-29 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-06-09 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-20 | 12 | 10 | 2025-06-20 | 2025-06-20 | 1 | 1 | 182 | 130 | 14 | 12 | 196 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -328 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-04-10 | IOU Designed & Installed | N/A | No | N/A | 3120.52 | 1347.12 | Unknown | 1914.2 | -1156 | 1015.2 | Unknown | 2312.45 | 3120.52 | -808.07 | Yes | N/A | N/A | 2023-03-24 | 2023-03-28 | 5 | 3 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-04-13 | 4 | 4 | 2023-04-13 | 2023-04-13 | 1 | 1 | 5 | 3 | 5 | 5 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -617 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3785.75 | Unknown | Unknown | Unknown | 4.97 | 3780.78 | 3981 | 974.87 | 3785.75 | -2810.88 | Yes | N/A | N/A | 2025-01-07 | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2025-01-14 | 33 | 23 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1 | 1 | 0 | 0 | 34 | 24 | 34 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | -302 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 1260.43 | 502.72 | Unknown | 271.4 | -2014 | 2500.31 | Unknown | 1869.28 | 1260.43 | 608.85 | Yes | N/A | N/A | 2025-01-16 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-17 | 8 | 6 | 2025-01-17 | 2025-01-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-14 | 52 | 38 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-14 | 2025-03-18 | 5 | 3 | 2025-03-18 | 2025-03-18 | 1 | 1 | 58 | 42 | 14 | 10 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-01 | 1341 | 958 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12656.74 | -12.92 | Unknown | Unknown | -219.87 | 12889.53 | 2875 | 2094.41 | 12656.74 | -10562.33 | Yes | N/A | N/A | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | 2023-12-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-09-26 | 291 | 209 | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-02 | 1 | 1 | 292 | 210 | 23 | 17 | 315 | 227 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 1742.02 | Unknown | Unknown | Unknown | 24.47 | 1717.55 | 3981 | 1120.15 | 1742.02 | -621.87 | Yes | N/A | N/A | 2024-04-29 | 2024-07-15 | 78 | 56 | 2024-07-15 | 2024-07-17 | 3 | 3 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-10-24 | 100 | 72 | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-24 | 2024-11-01 | 9 | 7 | 2024-11-01 | 2024-11-01 | 1 | 1 | 178 | 128 | 13 | 11 | 191 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -555 | -396 | No | 2024-12-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-26 | 2025-04-17 | IOU Designed & Installed | N/A | Yes | 79 | 3908.13 | 808.74 | Unknown | 252.54 | -556 | 3402.85 | 3981 | 1878.6 | 3908.13 | -2029.53 | Yes | N/A | N/A | 2024-12-18 | 2025-02-20 | 65 | 47 | 2025-02-20 | 2025-03-07 | 16 | 12 | 2025-03-07 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-04-17 | 108 | 78 | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-17 | 2025-05-06 | 20 | 14 | 2025-05-06 | 2025-04-25 | Unknown | Unknown | 173 | 125 | 36 | 26 | 209 | 151 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-10 | -500 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-17 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | -6.1 | -11.97 | Unknown | Unknown | Unknown | 5.87 | Unknown | 928.64 | -6.1 | 934.74 | Yes | N/A | N/A | 2023-05-12 | 2023-05-17 | 6 | 4 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-09-19 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-10-27 | 39 | 29 | 2023-10-27 | 2023-10-27 | 1 | 1 | 132 | 94 | 40 | 30 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -507 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-02-08 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 2291.36 | 702.6 | Unknown | Unknown | Unknown | 1588.76 | 3981 | 1207.49 | 2291.36 | -1083.87 | Yes | N/A | N/A | 2024-01-09 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-02-12 | 62 | 44 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-06-28 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-18 | 21 | 15 | 2024-07-18 | 2024-07-18 | 1 | 1 | 142 | 102 | 84 | 60 | 226 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-21 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 802.08 | -12.99 | Unknown | Unknown | 6.65 | 808.42 | 3981 | 717.17 | 802.08 | -84.91 | Yes | N/A | N/A | 2023-12-01 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2024-01-18 | 114 | 82 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-04-09 | 83 | 59 | Unknown | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-04-29 | 21 | 15 | 2024-04-29 | 2024-04-29 | 1 | 1 | 83 | 59 | 136 | 98 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -655 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 522.58 | -9.54 | Unknown | Unknown | Unknown | 532.12 | 3981 | 1475.62 | 522.58 | 953.04 | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-19 | 15 | 11 | 2024-10-28 | 2024-11-20 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-30 | 41 | 29 | 2024-12-30 | 2024-12-30 | 1 | 1 | 25 | 19 | 58 | 42 | 83 | 61 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 742.05 | 742.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | -10.92 | -8.87 | Unknown | Unknown | Unknown | -2.05 | 3981 | 1154.6 | -10.92 | 1165.52 | Yes | N/A | N/A | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-03-12 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-21 | 10 | 8 | 2024-03-21 | 2024-03-20 | Unknown | Unknown | 48 | 34 | 11 | 9 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | -5.91 | -4.79 | Unknown | Unknown | Unknown | -1.12 | Unknown | 153.75 | -5.91 | 159.66 | Yes | N/A | N/A | 2023-06-01 | 2023-06-08 | 8 | 6 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-12-14 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-02-26 | 75 | 53 | 2024-02-26 | 2024-02-26 | 1 | 1 | 198 | 142 | 76 | 54 | 274 | 196 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | -234 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-09-23 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 126.97 | -2.19 | Unknown | Unknown | Unknown | 129.16 | 3981 | 1085.6 | 126.97 | 958.63 | Yes | N/A | N/A | 2024-08-02 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-09-23 | 102 | 72 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-01 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-07 | 7 | 5 | 2024-10-07 | 2024-10-04 | Unknown | Unknown | 9 | 7 | 109 | 77 | 118 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-20 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | -1721.76 | Unknown | Unknown | Unknown | -1788 | 66.24 | Unknown | 1787.89 | -1721.76 | 3509.65 | Yes | N/A | N/A | 2024-09-10 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-09-20 | 33 | 25 | 2024-09-20 | 2024-11-04 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2025-01-16 | 74 | 54 | Unknown | 2024-12-13 | Unknown | Unknown | 2025-01-16 | 2025-01-22 | 7 | 5 | 2025-01-22 | 2025-01-22 | 1 | 1 | 120 | 86 | 41 | 31 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-09 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 1719.1 | 507.87 | Unknown | 144.48 | Unknown | 1066.75 | 3981 | 994.19 | 1719.1 | -724.91 | Yes | N/A | N/A | 2023-10-31 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-12-04 | 124 | 88 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-24 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-01-30 | 7 | 5 | 2024-01-30 | 2024-01-29 | Unknown | Unknown | 52 | 38 | 131 | 93 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -465 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 701.29 | -13.07 | Unknown | Unknown | Unknown | 714.36 | 3981 | 1561.76 | 701.29 | 860.47 | Yes | N/A | N/A | 2024-07-03 | 2024-07-23 | 21 | 15 | 2024-07-23 | 2025-01-08 | 170 | 122 | 2024-09-21 | 2024-10-09 | 19 | 13 | 2024-09-10 | 2024-10-11 | 15 | 12 | 2025-01-08 | 2025-01-28 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-02-27 | Unknown | Unknown | 61 | 43 | 185 | 134 | 246 | 177 | Steps 2,3,5,6,7 | 138 | 98 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -653 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 48.17 | -12.64 | Unknown | Unknown | 1.28 | 59.53 | 3981 | 807.84 | 48.17 | 759.67 | Yes | N/A | N/A | 2024-02-05 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-02-05 | 19 | 13 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-15 | 39 | 29 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2 | 2 | 59 | 43 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1218.25 | 304.25 | Unknown | Unknown | Unknown | 914 | 3981 | 1630.64 | 1218.25 | 412.39 | Yes | N/A | N/A | 2024-10-31 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-31 | 8 | 6 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-01-21 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-02-07 | 18 | 14 | 2025-02-07 | 2025-02-07 | 1 | 1 | 83 | 59 | 27 | 21 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-12 | 184 | 133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13264.65 | Unknown | Unknown | Unknown | -267.15 | 13531.8 | 3981 | 3742.2 | 13264.65 | -9522.45 | Yes | N/A | N/A | 2023-03-31 | 2023-03-28 | Unknown | Unknown | 2023-03-28 | 2023-04-18 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-12-06 | 118 | 84 | 2023-04-18 | 2024-01-05 | 263 | 189 | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-01-12 | Unknown | Unknown | 263 | 189 | 140 | 100 | 403 | 289 | Steps 2,3,5,6,7 | 232 | 166 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | -548 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-11 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 31.75 | Unknown | Unknown | Unknown | Unknown | 31.75 | Unknown | 1072.03 | 31.75 | 1040.28 | Yes | N/A | N/A | 2024-04-02 | 2024-04-11 | 10 | 8 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-07-15 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-23 | 40 | 30 | 2024-08-23 | 2024-08-23 | 1 | 1 | 106 | 76 | 42 | 32 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-26 | -220 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.98 | -11.33 | Unknown | Unknown | Unknown | 20.31 | 3981 | 703.84 | 8.98 | 694.86 | Yes | N/A | N/A | 2022-11-29 | 2023-03-24 | 116 | 84 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-01-19 | Unknown | Unknown | 116 | 84 | 0 | 0 | 116 | 84 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -452 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 419.44 | -8.43 | Unknown | Unknown | Unknown | 427.87 | Unknown | 1273.08 | 419.44 | 853.64 | Yes | N/A | N/A | 2025-03-31 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-31 | 8 | 6 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-05-12 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-15 | 4 | 4 | 2025-05-15 | 2025-05-14 | Unknown | Unknown | 43 | 31 | 12 | 10 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | 268 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1076.31 | -16.97 | Unknown | Unknown | -1067.55 | 8.21 | 0 | 1729.5 | -1076.31 | 2805.81 | Yes | N/A | N/A | 2023-01-30 | 2023-02-28 | 30 | 22 | 2023-02-28 | 2023-03-17 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 30 | 22 | 19 | 14 | 49 | 36 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 371 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | -881.27 | -4.28 | Unknown | Unknown | -1156 | 279.01 | 3981 | 2539.49 | -881.27 | 3420.76 | Yes | N/A | N/A | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | 2024-01-17 | 9 | 7 | 2024-01-17 | 2024-05-21 | 126 | 90 | 2024-01-17 | 2024-08-07 | 47 | 33 | 2024-03-21 | 2024-07-12 | 114 | 82 | Unknown | 2024-09-04 | Unknown | Unknown | 2024-07-12 | 2024-09-11 | 62 | 44 | 2024-09-11 | 2024-09-06 | Unknown | Unknown | 241 | 173 | 118 | 84 | 359 | 257 | Steps 2,3,5,6,7 | 318 | 226 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 116 | 116 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-29 | -198 | -143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9842.79 | 226 | Unknown | Unknown | -12084.31 | 21701.1 | 3981 | 15449.45 | 9842.79 | 5606.66 | Yes | N/A | N/A | 2024-01-31 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-05-22 | 119 | 85 | 2024-02-13 | 2024-03-14 | 31 | 23 | 2024-03-14 | 2024-05-16 | 12 | 8 | 2024-05-22 | 2024-08-07 | 78 | 56 | 2024-05-28 | 2024-10-22 | 148 | 106 | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-11-12 | Unknown | Unknown | 109 | 79 | 279 | 199 | 388 | 278 | Steps 2,3,5,6,7 | 170 | 122 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -567 | -406 | No | 2024-07-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2024-11-06 | IOU Designed & Installed | N/A | Yes | 93 | 7064.31 | 1473 | Unknown | Unknown | 48.74 | 5542.57 | 3981 | 1386.38 | 7064.31 | -5677.93 | Yes | N/A | N/A | 2024-07-15 | 2024-10-14 | 92 | 66 | 2024-10-14 | 2024-10-16 | 3 | 3 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-11-06 | 91 | 65 | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-06 | 2024-11-22 | 17 | 13 | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 183 | 131 | 20 | 16 | 203 | 147 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 134.01 | -21.34 | Unknown | Unknown | Unknown | 155.35 | Unknown | 1209.32 | 134.01 | 1075.31 | Yes | N/A | N/A | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | 2024-02-09 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 1 | 1 | 24 | 18 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ESCONDIDO | N/A | 3000 | 3000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-15 | 183 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-07-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -325.99 | Unknown | Unknown | Unknown | -385 | 59.01 | 1192 | 803.93 | -325.99 | 1129.92 | Yes | N/A | N/A | 2024-06-21 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-08 | 40 | 28 | 2024-07-08 | 2024-08-16 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-03-17 | 1 | 1 | 40 | 30 | 41 | 29 | 81 | 59 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 18.61 | Unknown | Unknown | Unknown | Unknown | 18.61 | Unknown | 1518.74 | 18.61 | 1500.13 | Yes | N/A | N/A | 2024-07-11 | 2024-07-19 | 9 | 7 | 2024-07-19 | 2024-08-02 | 15 | 11 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-28 | 1 | 1 | 9 | 7 | 16 | 12 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-12-10 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 29.65 | Unknown | Unknown | Unknown | Unknown | 29.65 | 3981 | 1615.43 | 29.65 | 1585.78 | Yes | N/A | N/A | 2024-10-24 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-12-09 | 54 | 38 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-10 | 30 | 22 | 2025-01-10 | 2025-01-10 | 1 | 1 | 3 | 3 | 85 | 61 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | -440 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 4214.05 | Unknown | Unknown | Unknown | 62.21 | 4151.84 | 3981 | 1166.16 | 4214.05 | -3047.89 | Yes | N/A | N/A | 2024-07-03 | 2024-11-01 | 122 | 88 | 2024-11-01 | 2024-11-03 | 3 | 1 | 2024-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-03 | 2025-03-10 | 128 | 91 | Unknown | 2025-02-27 | Unknown | Unknown | 2025-03-10 | 2025-03-18 | 9 | 7 | 2025-03-18 | 2025-03-18 | 1 | 1 | 250 | 179 | 13 | 9 | 263 | 188 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | -213 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-05-13 | IOU Designed & Installed | N/A | No | N/A | -3.65 | -10.64 | Unknown | Unknown | Unknown | 6.99 | 3981 | 647.88 | -3.65 | 651.53 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | 2023-05-13 | 89 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-05-13 | 2023-06-12 | 31 | 21 | 2023-06-12 | 2023-06-12 | 1 | 1 | 90 | 65 | 32 | 22 | 122 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -401 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -19.32 | -14 | Unknown | Unknown | Unknown | -5.32 | 3981 | 341.75 | -19.32 | 361.07 | Yes | N/A | N/A | 2023-04-03 | 2023-04-03 | 1 | 1 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -529 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-10 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 30.69 | Unknown | Unknown | Unknown | Unknown | 30.69 | Unknown | 1493.67 | 30.69 | 1462.98 | Yes | N/A | N/A | 2024-06-03 | 2024-06-10 | 8 | 6 | 2024-06-10 | 2024-06-10 | 1 | 1 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-11-15 | 159 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-02 | 18 | 12 | 2024-12-02 | 2024-12-02 | 1 | 1 | 167 | 121 | 20 | 14 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -20 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 99.3 | Unknown | Unknown | Unknown | 5.9 | 93.4 | 3981 | 192.51 | 99.3 | 93.21 | Yes | N/A | N/A | 2024-06-24 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-08 | 56 | 40 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-01-28 | 205 | 147 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-12 | 44 | 32 | 2025-03-12 | 2025-03-12 | 1 | 1 | 205 | 147 | 101 | 73 | 306 | 220 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 256 | 183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-01 | 2022-11-01 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 1088.44 | 3382.02 | Unknown | 84.15 | -4020 | 1642.27 | Unknown | 2860.21 | 1088.44 | 1771.77 | Yes | N/A | N/A | 2022-11-01 | 2023-12-18 | 413 | 295 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-01 | 11 | 9 | 2024-02-01 | 2024-02-27 | 27 | 19 | 413 | 295 | 38 | 28 | 451 | 323 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 699 | 500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | -6081.58 | 2810.09 | Unknown | 169.12 | -9219 | 158.21 | Unknown | 9218.94 | -6081.58 | 15300.52 | Yes | N/A | N/A | 2024-11-07 | 2024-11-08 | 2 | 2 | 2024-11-08 | 2024-11-21 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-22 | 2025-01-27 | 67 | 47 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2 | 2 | 83 | 59 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -47 | -34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 28104.75 | 1944.18 | Unknown | Unknown | 1381.29 | 24779.28 | 7294069 | 90048.96 | 28104.75 | 61944.21 | Yes | N/A | N/A | 2023-01-10 | 2023-09-26 | 260 | 186 | 2023-09-26 | 2024-03-26 | 183 | 131 | 2023-10-13 | 2023-10-16 | 4 | 2 | 2024-01-26 | 2024-02-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-20 | 1 | 1 | Unknown | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2024-12-27 | 1 | 1 | 264 | 188 | 193 | 139 | 457 | 327 | Steps 2,3,5,6,7 | 165 | 117 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | -318 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 11.4 | -10.09 | Unknown | Unknown | Unknown | 21.49 | 3981 | 1025.84 | 11.4 | 1014.44 | Yes | N/A | N/A | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-04-09 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-05-13 | 35 | 25 | 2024-05-13 | 2024-05-09 | Unknown | Unknown | 84 | 60 | 36 | 26 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 26.75 | 26.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-29 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 76.65 | -0.63 | Unknown | Unknown | Unknown | 77.28 | 3981 | 1554.69 | 76.65 | 1478.04 | Yes | N/A | N/A | 2024-08-02 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-08-29 | 56 | 40 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-10-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-24 | 22 | 16 | 2024-10-24 | 2024-10-24 | 1 | 1 | 36 | 26 | 79 | 57 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 184.1 | 184.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2017.13 | Unknown | Unknown | Unknown | 1.74 | 2015.39 | 3981 | 2888.08 | 2017.13 | 870.95 | Yes | N/A | N/A | 2025-02-07 | 2025-02-27 | 21 | 15 | 2025-02-27 | 2025-03-03 | 5 | 3 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-21 | 1 | 1 | 21 | 15 | 6 | 4 | 27 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-10 | -371 | -266 | No | 2023-12-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-09-16 | IOU Designed & Installed | N/A | Yes | 245 | 11939.71 | 2700.29 | Unknown | 1230.05 | 89.07 | 7920.3 | 3981 | 934.69 | 11939.71 | -11005.02 | Yes | N/A | N/A | 2023-12-11 | 2024-08-15 | 249 | 179 | 2024-08-15 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-09-16 | 278 | 198 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-16 | 2024-11-04 | 50 | 36 | 2024-11-04 | 2024-11-04 | 1 | 1 | 527 | 377 | 51 | 37 | 578 | 414 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 1611.16 | -6.08 | Unknown | Unknown | 7.48 | 1609.76 | Unknown | 1100.24 | 1611.16 | -510.92 | Yes | N/A | N/A | 2024-10-22 | 2024-11-07 | 17 | 13 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2025-01-28 | 83 | 59 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-28 | 2025-02-25 | 29 | 21 | 2025-02-25 | 2025-02-25 | 1 | 1 | 100 | 72 | 31 | 23 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | 279 | 200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1134.58 | Unknown | Unknown | Unknown | Unknown | 1134.58 | Unknown | 5354.79 | 1134.58 | 4220.21 | Yes | N/A | N/A | 2024-09-30 | 2024-10-02 | 3 | 3 | 2024-10-02 | 2024-10-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-18 | 1 | 1 | 3 | 3 | 23 | 17 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 431 | 308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 7389.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-03-29 | 15 | 11 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-18 | -291 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 546.52 | -10.24 | Unknown | Unknown | Unknown | 556.76 | 7962 | 859.62 | 546.52 | 313.1 | Yes | N/A | N/A | 2024-01-31 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2024-02-29 | 127 | 91 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-10-31 | 1 | 1 | 0 | 0 | 128 | 92 | 128 | 92 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | -409 | -292 | No | 2023-07-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-22 | Unknown | 2024-11-22 | IOU Designed & Installed | N/A | Yes | 585 | 80.76 | -23.28 | Unknown | Unknown | 3.53 | 100.51 | Unknown | 1147.56 | 80.76 | 1066.8 | Yes | N/A | N/A | 2023-07-22 | 2025-02-27 | 587 | 419 | 2025-02-27 | 2023-07-22 | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | 2024-11-22 | 490 | 350 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-04-03 | 133 | 95 | 2025-04-03 | 2025-04-03 | 1 | 1 | 1077 | 769 | 134 | 96 | 1211 | 865 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | -690 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-20 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1421.52 | Unknown | Unknown | Unknown | 2.96 | 1418.56 | 3981 | 1225.94 | 1421.52 | -195.58 | Yes | N/A | N/A | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | 2025-03-21 | 3 | 3 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-25 | 36 | 26 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-25 | 2025-04-29 | 5 | 3 | 2025-04-29 | 2025-04-28 | Unknown | Unknown | 37 | 27 | 8 | 6 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 168.05 | 168.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -154 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-11 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 6595.42 | Unknown | Unknown | Unknown | -2835.62 | 9431.04 | Unknown | 2847.53 | 6595.42 | -3747.89 | Yes | N/A | N/A | 2024-01-05 | 2025-02-04 | 397 | 283 | 2025-02-04 | 2025-03-04 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-04 | 21 | 15 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | 2025-05-12 | 2025-06-02 | 22 | 16 | 2025-06-02 | 2025-06-02 | 1 | 1 | 397 | 283 | 73 | 53 | 470 | 336 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-10-15 | IOU Designed & Installed | N/A | No | N/A | -820.81 | 837.95 | Unknown | 188 | -2365 | 518.24 | Unknown | 2364.65 | -820.81 | 3185.46 | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-15 | 2023-10-18 | 4 | 3 | 2023-10-18 | 2023-10-18 | 1 | 1 | 1 | 1 | 5 | 4 | 6 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 192 | 138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | -4583.25 | 1341.78 | Unknown | Unknown | -6846 | 920.97 | 0 | 6846.26 | -4583.25 | 11429.51 | Yes | N/A | N/A | 2024-06-26 | 2023-04-12 | Unknown | Unknown | 2023-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-21 | Unknown | Unknown | 2024-09-21 | 2024-09-21 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.99 | Unknown | Unknown | Unknown | -1254.27 | 1247.28 | Unknown | 1263.22 | -6.99 | 1270.21 | Yes | N/A | N/A | 2024-07-15 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-08-16 | 66 | 48 | 2024-08-16 | 2024-11-08 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-23 | Unknown | Unknown | 85 | 61 | 66 | 48 | 151 | 109 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | -712 | -509 | No | 2024-06-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2024-06-25 | IOU Designed & Installed | N/A | Yes | 4 | 9.74 | -8.64 | Unknown | Unknown | Unknown | 18.38 | 3981 | 1840.21 | 9.74 | 1830.47 | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-06-24 | 5 | 3 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-25 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-02 | 8 | 6 | 2024-07-02 | 2024-07-02 | 1 | 1 | 7 | 5 | 14 | 10 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-23 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 750.96 | -10.98 | Unknown | Unknown | 2.12 | 759.82 | 3981 | 571.51 | 750.96 | -179.45 | Yes | N/A | N/A | 2024-04-16 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-05-20 | 60 | 42 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-29 | 10 | 8 | Unknown | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-06-13 | 16 | 12 | 2024-06-13 | 2024-06-13 | 1 | 1 | 10 | 8 | 77 | 55 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-06-13 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 33.6 | Unknown | Unknown | Unknown | Unknown | 33.6 | 3891 | 1705.15 | 33.6 | 1671.55 | Yes | N/A | N/A | 2024-03-12 | 2024-05-13 | 63 | 45 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-12 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-24 | 13 | 9 | 2024-07-24 | 2024-07-24 | 1 | 1 | 92 | 66 | 14 | 10 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -564 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 615.68 | 313.56 | Unknown | 68.61 | Unknown | 233.51 | 3981 | 192.51 | 615.68 | -423.17 | Yes | N/A | N/A | 2024-07-15 | 2024-07-24 | 10 | 8 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-09-13 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-23 | 41 | 29 | 2024-10-23 | 2024-11-05 | 14 | 10 | 62 | 46 | 56 | 40 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 434.05 | 434.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -447 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-21 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 995.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | 2024-03-21 | 8 | 6 | 2024-03-21 | Unknown | Unknown | Unknown | 2024-03-21 | 2024-03-27 | 7 | 5 | 2024-03-21 | 2024-06-20 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2025-08-11 | 418 | 298 | 2025-08-11 | 2024-06-28 | Unknown | Unknown | 93 | 67 | 433 | 309 | 526 | 376 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2024-03-22 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 5727.87 | Unknown | Unknown | Unknown | Unknown | 5727.87 | Unknown | 828.21 | 5727.87 | -4899.66 | Yes | N/A | N/A | 2022-08-11 | 2024-03-18 | 586 | 418 | 2024-03-18 | 2024-06-14 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-21 | 5 | 5 | 2024-06-21 | 2024-06-21 | 1 | 1 | 586 | 418 | 95 | 71 | 681 | 489 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -365 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | 2254.37 | 495.03 | Unknown | 197.39 | Unknown | 1561.95 | Unknown | 1164.74 | 2254.37 | -1089.63 | Yes | N/A | N/A | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-02-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-02-22 | 1 | 1 | 2024-02-22 | 2024-02-22 | 1 | 1 | 3 | 3 | 3 | 3 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-01-22 | 1477 | 1056 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-15 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | -1410.32 | Unknown | Unknown | Unknown | -5568 | 4157.68 | Unknown | 9856.95 | -1410.32 | 11267.27 | Yes | N/A | N/A | 2023-08-11 | 2023-08-15 | 5 | 3 | 2023-08-15 | 2023-11-07 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-09-07 | 22 | 16 | 2024-01-02 | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-10 | 9 | 7 | 2024-01-19 | 2024-02-07 | 20 | 14 | 2024-02-07 | 2024-02-07 | 1 | 1 | 5 | 3 | 137 | 99 | 142 | 102 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | 117 | 85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 873.82 | -81.77 | Unknown | Unknown | Unknown | 955.59 | 801864 | 8757.15 | 873.82 | 7883.33 | Yes | N/A | N/A | 2024-12-03 | 2025-02-13 | 73 | 53 | 2025-02-13 | 2025-03-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-07 | 16 | 12 | 2025-03-21 | 2025-03-20 | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-04-11 | Unknown | Unknown | 73 | 53 | 53 | 39 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 14.7 | 14.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -522 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 2044.46 | -11.16 | Unknown | Unknown | 39.72 | 2015.9 | 3981 | 1062.65 | 2044.46 | -981.81 | Yes | N/A | N/A | 2024-10-03 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-10-29 | 47 | 33 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-03-10 | 133 | 95 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-10 | 2025-03-25 | 16 | 12 | 2025-03-25 | 2025-03-25 | 1 | 1 | 133 | 95 | 64 | 46 | 197 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -641 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 1145.06 | -21.9 | Unknown | Unknown | Unknown | 1166.96 | 3981 | 1402.26 | 1145.06 | 257.2 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-23 | 35 | 25 | 2024-08-20 | 2024-09-12 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-09-23 | 12 | 8 | 2024-09-23 | 2024-09-23 | 1 | 1 | 25 | 19 | 49 | 35 | 74 | 54 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | SM 1108-E6 w. mission (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 256 | 183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2024-04-22 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 125707.58 | 21791.42 | Unknown | Unknown | 2141.13 | 101775.03 | 557601 | 95759.5 | 125707.58 | -29948.08 | Yes | N/A | N/A | 2023-11-20 | 2023-12-01 | 12 | 10 | 2023-12-01 | 2024-09-10 | 285 | 203 | 2024-03-12 | 2024-12-20 | 77 | 57 | 2024-05-30 | 2024-12-06 | 50 | 38 | 2024-09-30 | Unknown | Unknown | Unknown | 2024-09-30 | 2024-12-18 | 80 | 58 | 2025-01-08 | 2025-04-28 | 111 | 79 | 2025-04-28 | 2025-04-28 | 1 | 1 | 89 | 67 | 527 | 379 | 616 | 446 | Steps 2,3,5,6,7 | 453 | 325 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 172.87 | Unknown | Unknown | Unknown | Unknown | 172.87 | 3981 | 118.25 | 172.87 | -54.62 | Yes | N/A | N/A | 2025-05-12 | 2025-06-09 | 29 | 21 | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-23 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-25 | 3 | 3 | 2025-06-25 | 2025-06-25 | 1 | 1 | 44 | 32 | 5 | 5 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 870.82 | 575.75 | Unknown | Unknown | Unknown | 295.07 | Unknown | 190.13 | 870.82 | -680.69 | Yes | N/A | N/A | 2025-01-21 | 2025-02-19 | 30 | 22 | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-05-12 | 83 | 59 | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-12 | 2025-06-10 | 30 | 22 | 2025-06-10 | 2025-06-10 | 1 | 1 | 113 | 81 | 32 | 24 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.6 | -4.82 | Unknown | Unknown | Unknown | 3.22 | Unknown | 710.9 | -1.6 | 712.5 | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-05-04 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 4351 | 4351 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-07-24 | -149 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2024-12-26 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | -1748.81 | Unknown | Unknown | Unknown | -1787 | 38.19 | Unknown | 1643.83 | -1748.81 | 3392.64 | Yes | N/A | N/A | 2023-10-20 | 2024-11-15 | 393 | 281 | 2024-11-15 | 2025-02-21 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-02-20 | 43 | 31 | 2025-02-21 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-02-26 | 3 | 3 | 2025-02-26 | 2025-02-25 | Unknown | Unknown | 393 | 281 | 145 | 105 | 538 | 386 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 10.1 | 10.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -264 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-11-25 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 343.48 | -5.64 | Unknown | Unknown | Unknown | 349.12 | 3981 | 1568.7 | 343.48 | 1225.22 | Yes | N/A | N/A | 2024-10-04 | 2024-11-27 | 55 | 39 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-19 | 17 | 13 | 2024-11-27 | 2025-02-19 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-04 | 14 | 10 | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 140 | 100 | 32 | 24 | 172 | 124 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-28 | -183 | -132 | No | 2024-11-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-13 | 2025-04-10 | IOU Designed & Installed | N/A | Yes | 49 | 2463.81 | Unknown | Unknown | Unknown | 33.51 | 2430.3 | Unknown | 1493.93 | 2463.81 | -969.88 | Yes | N/A | N/A | 2024-11-11 | 2024-12-30 | 50 | 36 | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-04-10 | 105 | 75 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-04-10 | 2025-04-28 | 19 | 13 | 2025-04-28 | 2025-04-28 | 1 | 1 | 155 | 111 | 21 | 15 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | -16.3 | -14.08 | Unknown | Unknown | Unknown | -2.22 | Unknown | 1181.38 | -16.3 | 1197.68 | Yes | N/A | N/A | 2024-03-21 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-03-21 | 37 | 27 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-07-10 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-22 | 13 | 9 | 2024-07-22 | 2024-07-22 | 1 | 1 | 112 | 80 | 51 | 37 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 15.55 | 15.55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2025-01-31 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 46.09 | Unknown | Unknown | Unknown | Unknown | 46.09 | 3981 | 1575.16 | 46.09 | 1529.07 | Yes | N/A | N/A | 2024-11-22 | 2025-01-15 | 55 | 39 | 2025-01-15 | 2025-01-29 | 15 | 11 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-01-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-19 | 20 | 14 | 2025-02-19 | 2025-02-19 | 1 | 1 | 56 | 40 | 36 | 26 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | -351.82 | Unknown | Unknown | Unknown | -434 | 82.18 | 1700 | 1907.42 | -351.82 | 2259.24 | Yes | N/A | N/A | 2024-07-17 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-07-26 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-08-26 | 19 | 13 | 2024-08-26 | 2024-08-26 | 1 | 1 | 0 | 0 | 71 | 51 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | Pauma Valley | CALTRANS-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | 351 | 251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12096.44 | 157.12 | Unknown | Unknown | -2480 | 14419.32 | 0 | 2480.47 | 12096.44 | -9615.97 | Yes | N/A | N/A | 2023-10-12 | 2023-10-13 | 2 | 2 | 2023-10-13 | 2025-01-29 | 475 | 339 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-02-07 | 2024-09-10 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-03-17 | 1 | 1 | 3 | 3 | 508 | 364 | 511 | 367 | Steps 2,3,5,6,7 | 357 | 255 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 730.05 | 730.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-27 | -177 | -127 | No | 2023-12-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | Yes | 362 | 28.87 | Unknown | Unknown | Unknown | Unknown | 28.87 | Unknown | 1766.18 | 28.87 | 1737.31 | Yes | N/A | N/A | 2023-12-15 | 2024-12-06 | 358 | 256 | 2024-12-06 | 2024-12-11 | 6 | 4 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-03 | 1 | 1 | 358 | 256 | 7 | 5 | 365 | 261 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | -2038.86 | 894.52 | Unknown | 476.44 | -3860 | 450.18 | Unknown | 3859.66 | -2038.86 | 5898.52 | Yes | N/A | N/A | 2023-11-09 | 2023-11-13 | 5 | 3 | 2023-11-13 | 2023-12-12 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-11 | 2023-12-14 | 4 | 4 | 2023-12-14 | 2023-12-14 | 1 | 1 | 5 | 3 | 36 | 28 | 41 | 31 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -278 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 678.26 | -11.89 | Unknown | Unknown | Unknown | 690.15 | Unknown | 1323.62 | 678.26 | 645.36 | Yes | N/A | N/A | 2024-02-15 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-02-15 | 74 | 54 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-04-18 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-23 | 6 | 4 | 2024-04-23 | 2024-04-23 | 1 | 1 | 64 | 46 | 81 | 59 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -683 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 1123.02 | -21.9 | Unknown | Unknown | Unknown | 1144.92 | 3981 | 1485.54 | 1123.02 | 362.52 | Yes | N/A | N/A | 2024-10-10 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-10-10 | 22 | 16 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-29 | 15 | 11 | 2024-10-29 | 2024-10-29 | 1 | 1 | 6 | 4 | 38 | 28 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -526 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-11-14 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 60.76 | Unknown | Unknown | Unknown | Unknown | 60.76 | Unknown | 1660.24 | 60.76 | 1599.48 | Yes | N/A | N/A | 2024-09-09 | 2024-11-14 | 67 | 49 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-07 | 23 | 16 | 2025-01-08 | 2025-01-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-16 | 7 | 5 | 2025-01-16 | 2025-01-16 | 1 | 1 | 70 | 52 | 32 | 23 | 102 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 60 | 43 | No | 2022-06-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-24 | 2022-06-24 | 2023-05-30 | IOU Designed & Installed | N/A | Yes | 222 | 647.19 | 237.76 | Unknown | Unknown | Unknown | 409.43 | Unknown | 314 | 647.19 | -333.19 | Yes | N/A | N/A | 2022-06-24 | 2023-02-01 | 223 | 159 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-06-24 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | 2023-05-30 | 1 | 1 | 223 | 159 | 2 | 2 | 225 | 161 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 306 | 306 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-22 | 935 | 670 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 2129.61 | Unknown | Unknown | Unknown | Unknown | 2129.61 | 3981 | 454.63 | 2129.61 | -1674.98 | Yes | N/A | N/A | 2023-11-06 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-12-18 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-04-25 | 130 | 94 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-06-06 | 2024-06-17 | 12 | 8 | 2024-06-17 | 2024-06-14 | Unknown | Unknown | 130 | 94 | 107 | 75 | 237 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | -689 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 44.8 | Unknown | Unknown | Unknown | Unknown | 44.8 | 3981 | 1624.99 | 44.8 | 1580.19 | Yes | N/A | N/A | 2025-03-14 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-14 | 3 | 3 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-24 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-04-07 | 15 | 11 | 2025-04-07 | 2025-04-07 | 1 | 1 | 11 | 7 | 19 | 15 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | -170 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 6639.09 | 352.45 | Unknown | Unknown | Unknown | 6286.64 | 3981 | 735.88 | 6639.09 | -5903.21 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-08-03 | 177 | 127 | Unknown | 2023-07-31 | Unknown | Unknown | 2023-08-03 | 2023-08-16 | 14 | 10 | 2023-08-16 | 2023-08-22 | 7 | 5 | 178 | 128 | 21 | 15 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -311 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 41.52 | Unknown | Unknown | Unknown | Unknown | 41.52 | 3981 | 1650.2 | 41.52 | 1608.68 | Yes | N/A | N/A | 2024-12-03 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-12-03 | 8 | 6 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-03 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-16 | 14 | 10 | 2024-12-16 | 2024-12-16 | 1 | 1 | 1 | 1 | 23 | 17 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-01 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 1327.27 | 440.64 | Unknown | 90.7 | Unknown | 795.93 | Unknown | 1718.91 | 1327.27 | 391.64 | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-12 | 9 | 7 | 2023-12-12 | 2023-12-12 | 1 | 1 | 5 | 3 | 10 | 8 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | Unknown | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 81.79 | -11.96 | Unknown | Unknown | 27.96 | 65.79 | 3981 | 911.02 | 81.79 | 829.23 | Yes | N/A | N/A | 2023-08-24 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-08-29 | 112 | 80 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-10-12 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-09 | 29 | 21 | 2023-11-09 | 2023-11-09 | 1 | 1 | 45 | 33 | 142 | 102 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | 84 | 61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-07-29 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 14514.55 | 1285.34 | Unknown | Unknown | 4.61 | 13224.6 | Unknown | 14188.28 | 14514.55 | -326.27 | Yes | N/A | N/A | 2024-06-10 | 2024-06-26 | 17 | 13 | 2024-06-26 | 2025-01-29 | 218 | 156 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-12-23 | 39 | 27 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-10 | 13 | 9 | 2025-03-10 | 2025-03-10 | 1 | 1 | 17 | 13 | 271 | 193 | 288 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-10 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 28.14 | Unknown | Unknown | Unknown | Unknown | 28.14 | Unknown | 1634.63 | 28.14 | 1606.49 | Yes | N/A | N/A | 2024-10-08 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-10-10 | 64 | 46 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-12-03 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-01-14 | 43 | 31 | 2025-01-14 | 2025-01-14 | 1 | 1 | 55 | 39 | 108 | 78 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-03 | 721 | 516 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 58357.94 | 8467.44 | Unknown | 324.59 | -148.47 | 49714.38 | 276849 | 48080.88 | 58357.94 | -10277.06 | Yes | N/A | N/A | 2022-11-14 | 2023-02-10 | 89 | 65 | 2023-02-10 | 2023-08-16 | 188 | 134 | 2023-05-17 | 2023-05-22 | 6 | 4 | 2023-07-10 | 2023-08-16 | 7 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2025-02-19 | 197 | 141 | 2025-03-04 | 2025-03-24 | 21 | 15 | 2025-03-24 | 2025-03-24 | 1 | 1 | 95 | 69 | 414 | 298 | 509 | 367 | Steps 2,3,5,6,7 | 91 | 65 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | Encinitas | ENCINITAS | 436 | 436 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 339 | 243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-08-21 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 14975.85 | 447.9 | Unknown | Unknown | -6489 | 21016.95 | 3981 | 7661.98 | 14975.85 | -7313.87 | Yes | N/A | N/A | 2023-06-02 | 2023-07-01 | 30 | 21 | 2023-07-01 | 2023-11-13 | 136 | 96 | 2023-07-14 | 2024-08-01 | 9 | 7 | 2023-09-06 | 2023-11-14 | 39 | 29 | 2023-11-13 | Unknown | Unknown | Unknown | 2023-12-29 | 2024-07-15 | 200 | 142 | 2024-08-15 | 2024-09-04 | 21 | 15 | 2024-09-04 | 2024-09-04 | 1 | 1 | 39 | 28 | 397 | 283 | 436 | 311 | Steps 2,3,5,6,7 | 453 | 323 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2023-09-05 | IOU Designed & Installed | N/A | No | N/A | 1139.38 | -33.88 | Unknown | Unknown | Unknown | 1173.26 | 3885 | 814.37 | 1139.38 | -325.01 | Yes | N/A | N/A | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-21 | 22 | 16 | 2023-05-30 | 2023-09-05 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-08 | 4 | 4 | 2023-09-08 | 2023-09-08 | 1 | 1 | 100 | 72 | 27 | 21 | 127 | 93 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -164 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | 592.41 | -22.35 | Unknown | Unknown | Unknown | 614.76 | 3981 | 468.73 | 592.41 | -123.68 | Yes | N/A | N/A | 2023-04-17 | 2023-04-17 | 1 | 1 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2023-08-16 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-08-21 | 6 | 4 | 2023-08-21 | 2023-08-21 | 1 | 1 | 123 | 89 | 7 | 5 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-21 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | -1274.45 | -10.2 | Unknown | Unknown | -1782 | 517.75 | Unknown | 1647.76 | -1274.45 | 2922.21 | Yes | N/A | N/A | 2025-02-20 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-21 | 16 | 12 | 2025-02-21 | 2025-03-05 | 13 | 9 | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-21 | 2025-05-21 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-05-27 | 7 | 5 | 2025-05-27 | 2025-05-27 | 1 | 1 | 103 | 73 | 28 | 22 | 131 | 95 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 2551.51 | 422.95 | Unknown | 5.23 | 10.26 | 2113.07 | 3981 | 833.7 | 2551.51 | -1717.81 | Yes | N/A | N/A | 2024-04-02 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-04-05 | 58 | 42 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-07-03 | 90 | 64 | Unknown | 2024-06-11 | Unknown | Unknown | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | 2024-07-03 | 1 | 1 | 90 | 64 | 60 | 44 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-30 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-29 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | -207.78 | Unknown | Unknown | Unknown | -1402.01 | 1194.23 | Unknown | 1287.27 | -207.78 | 1495.05 | Yes | N/A | N/A | 2024-08-02 | 2024-08-12 | 11 | 7 | 2024-08-12 | 2024-09-05 | 25 | 19 | 2024-09-05 | 2024-10-09 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-11-19 | 61 | 43 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-19 | 2024-12-19 | 31 | 23 | 2024-12-19 | 2024-12-09 | Unknown | Unknown | 107 | 75 | 56 | 42 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -577 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1706.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-28 | 14 | 10 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-04-09 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-21 | 13 | 9 | 2025-04-21 | 2025-04-21 | 1 | 1 | 72 | 52 | 28 | 20 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-29 | -262 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-11-10 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 2993.27 | 1015.12 | Unknown | Unknown | 105.66 | 1872.49 | 3241 | 1391 | 2993.27 | -1602.27 | Yes | N/A | N/A | 2023-10-19 | 2023-11-10 | 23 | 17 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-11-09 | 359 | 256 | 2024-11-09 | 2024-11-09 | 1 | 0 | 31 | 23 | 361 | 257 | 392 | 280 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-07 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 29.88 | Unknown | Unknown | Unknown | Unknown | 29.88 | Unknown | 1600.61 | 29.88 | 1570.73 | Yes | N/A | N/A | 2025-02-04 | 2025-02-07 | 4 | 4 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-19 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-24 | 34 | 24 | 2025-03-24 | 2025-03-24 | 1 | 1 | 14 | 12 | 36 | 26 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-03 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 4.39 | Unknown | Unknown | Unknown | Unknown | 4.39 | Unknown | 1066.51 | 4.39 | 1062.12 | Yes | N/A | N/A | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-12-11 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-17 | 7 | 5 | 2024-12-17 | 2025-02-27 | 73 | 53 | 73 | 53 | 81 | 59 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | -156 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.64 | -1.91 | Unknown | Unknown | Unknown | 1.27 | Unknown | 217.6 | -0.64 | 218.24 | Yes | N/A | N/A | 2023-02-07 | 2023-02-10 | 4 | 4 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-08-16 | 1 | 1 | 4 | 4 | 1 | 1 | 5 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-26 | 1147 | 820 | No | 2020-11-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-14 | 2021-01-22 | Unknown | IOU Designed & Installed | N/A | Yes | 1266 | 82.01 | Unknown | Unknown | Unknown | Unknown | 82.01 | 93823 | 3590.18 | 82.01 | 3508.17 | Yes | N/A | N/A | 2020-07-14 | 2024-01-30 | 1296 | 926 | 2024-01-30 | 2024-04-25 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 1296 | 926 | 87 | 63 | 1383 | 989 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | -164.84 | -5.67 | Unknown | Unknown | -752 | 592.83 | 0 | 751.7 | -164.84 | 916.54 | Yes | N/A | N/A | 2023-10-18 | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-12-20 | 192 | 138 | 2023-12-20 | 2024-01-02 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-04-29 | 119 | 85 | Unknown | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-05-13 | 15 | 11 | 2024-05-13 | 2024-05-13 | 1 | 1 | 133 | 95 | 208 | 150 | 341 | 245 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 26 | 19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 0.73 | -11.85 | Unknown | Unknown | Unknown | 12.58 | 3981 | 557.95 | 0.73 | 557.22 | Yes | N/A | N/A | 2023-06-30 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-06-30 | 3 | 3 | 2023-06-30 | 2023-08-02 | 32 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-11-14 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-11-30 | 17 | 13 | 2023-11-30 | 2024-06-26 | 210 | 150 | 170 | 118 | 230 | 166 | 400 | 284 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-27 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 6.26 | -5.54 | Unknown | Unknown | Unknown | 11.8 | Unknown | 1026.98 | 6.26 | 1020.72 | Yes | N/A | N/A | 2024-03-20 | 2024-03-27 | 8 | 6 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-01 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-01 | 31 | 23 | 2024-05-01 | 2024-05-01 | 1 | 1 | 14 | 10 | 33 | 25 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 308 | 308 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-20 | 671 | 480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 15.88 | Unknown | Unknown | Unknown | Unknown | 15.88 | Unknown | 618.41 | 15.88 | 602.53 | Yes | N/A | N/A | 2024-10-30 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-11-19 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-21 | 2 | 2 | 2024-11-21 | 2024-11-21 | 1 | 1 | 0 | 0 | 30 | 22 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -669 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 1393.3 | 489.8 | Unknown | Unknown | Unknown | 903.5 | 3885 | 779.97 | 1393.3 | -613.33 | Yes | N/A | N/A | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | 2025-03-06 | 555 | 397 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-10-09 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-31 | 23 | 17 | 2023-10-31 | 2023-10-31 | 1 | 1 | 42 | 30 | 579 | 415 | 621 | 445 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 8018.55 | Unknown | Unknown | Unknown | Unknown | 8018.55 | Unknown | 540 | 8018.55 | -7478.55 | Yes | N/A | N/A | 2023-07-05 | 2023-07-06 | 2 | 2 | 2023-07-06 | 2023-07-28 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-17 | 12 | 8 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-23 | 23 | 17 | 2023-08-23 | 2023-08-23 | 1 | 1 | 2 | 2 | 59 | 43 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | -1171.21 | -0.31 | Unknown | Unknown | -1218 | 47.1 | Unknown | 986.74 | -1171.21 | 2157.95 | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-11-27 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-11-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-06 | 10 | 8 | 2024-12-06 | 2024-12-06 | 1 | 1 | 124 | 90 | 12 | 10 | 136 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | 85.05 | 85.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 1715.26 | 503.36 | Unknown | Unknown | -995.49 | 2207.39 | 3981 | 1235.42 | 1715.26 | -479.84 | Yes | N/A | N/A | 2024-08-28 | 2024-09-06 | 10 | 8 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | 2024-11-20 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-06-05 | 193 | 139 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | 2025-06-05 | 1 | 1 | 208 | 150 | 3 | 3 | 211 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 443 | 316 | No | 2022-01-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | 2022-01-19 | 2024-03-04 | IOU Designed & Installed | N/A | Yes | 688 | -4.4 | -3.57 | Unknown | Unknown | Unknown | -0.83 | Unknown | 507.77 | -4.4 | 512.17 | Yes | N/A | N/A | 2022-01-10 | 2023-11-01 | 661 | 473 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-01-19 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-18 | 15 | 11 | 2024-03-18 | 2024-03-18 | 1 | 1 | 661 | 473 | 16 | 12 | 677 | 485 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | Unknown | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 39.07 | -0.62 | Unknown | Unknown | Unknown | 39.69 | 3981 | 1686.98 | 39.07 | 1647.91 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2025-01-29 | 170 | 122 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2 | 2 | 172 | 124 | 174 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 1842.41 | -36.27 | Unknown | Unknown | Unknown | 1878.68 | 3981 | 2038.63 | 1842.41 | 196.22 | Yes | N/A | N/A | 2025-01-29 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-01-29 | 3 | 3 | 2025-01-29 | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-19 | 22 | 16 | 2025-01-29 | 2025-01-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-14 | 17 | 13 | 2025-02-14 | 2025-02-14 | 1 | 1 | 1 | 1 | 43 | 33 | 44 | 34 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-08 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | -9.89 | -8.05 | Unknown | Unknown | Unknown | -1.84 | Unknown | 499.18 | -9.89 | 509.07 | Yes | N/A | N/A | 2024-01-03 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2024-01-03 | 43 | 31 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-02-08 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-03-15 | 37 | 27 | 2024-03-15 | 2024-03-15 | 1 | 1 | 37 | 27 | 81 | 59 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | -90 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-10 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 192.35 | -17.42 | Unknown | Unknown | 9.23 | 200.54 | Unknown | 1025.36 | 192.35 | 833.01 | Yes | N/A | N/A | 2023-12-26 | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2024-01-10 | 92 | 66 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-05-10 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-07-01 | 53 | 37 | 2024-07-01 | 2024-07-01 | 1 | 1 | 122 | 88 | 146 | 104 | 268 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -58 | -43 | No | 2023-09-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | Yes | 197 | 14.7 | -13.06 | Unknown | Unknown | Unknown | 27.76 | 3981 | 895.48 | 14.7 | 880.78 | Yes | N/A | N/A | 2023-09-19 | 2024-04-25 | 220 | 158 | 2024-04-25 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-05-21 | 1 | 1 | 220 | 158 | 1 | 1 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | 64 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 893.36 | Unknown | Unknown | Unknown | 22.1 | 871.26 | 3981 | 1216.74 | 893.36 | 323.38 | Yes | N/A | N/A | 2023-08-28 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-08-31 | 72 | 52 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2024-07-23 | 328 | 234 | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-23 | 2024-08-09 | 18 | 14 | 2024-08-09 | 2024-08-23 | 15 | 11 | 328 | 234 | 105 | 77 | 433 | 311 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36.7 | 36.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 392.78 | Unknown | Unknown | Unknown | 4.98 | 387.8 | 3981 | 1114.43 | 392.78 | 721.65 | Yes | N/A | N/A | 2024-08-06 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-08-30 | 51 | 37 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-11-20 | 83 | 59 | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-12-13 | 24 | 18 | 2024-12-13 | 2024-12-13 | 1 | 1 | 83 | 59 | 76 | 56 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | 510.3 | 342.98 | Unknown | Unknown | Unknown | 167.32 | Unknown | 480.37 | 510.3 | -29.93 | Yes | N/A | N/A | 2023-08-18 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-08-18 | 95 | 69 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-09-14 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-18 | 5 | 3 | 2023-09-18 | 2023-09-18 | 1 | 1 | 28 | 20 | 101 | 73 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | -712 | -510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 33.64 | Unknown | Unknown | Unknown | Unknown | 33.64 | 3981 | 1695.63 | 33.64 | 1661.99 | Yes | N/A | N/A | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-10 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-15 | 6 | 4 | 2025-04-15 | 2025-04-14 | Unknown | Unknown | 12 | 10 | 7 | 5 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | -662 | -474 | No | 2025-04-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-22 | 2025-06-05 | IOU Designed & Installed | N/A | Yes | 24 | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1687.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-05-13 | 23 | 17 | 2025-05-13 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-06-05 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-17 | 13 | 9 | 2025-06-17 | 2025-06-17 | 1 | 1 | 68 | 50 | 14 | 10 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 100.4 | 100.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 1182.21 | Unknown | Unknown | Unknown | 32.47 | 1149.74 | 3981 | 493.68 | 1182.21 | -688.53 | Yes | N/A | N/A | 2023-12-05 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2023-12-19 | 36 | 26 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2025-03-06 | 444 | 318 | Unknown | 2025-02-06 | Unknown | Unknown | 2025-03-06 | 2025-03-10 | 5 | 3 | 2025-03-10 | 2025-03-10 | 1 | 1 | 444 | 318 | 42 | 30 | 486 | 348 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2105.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-02-27 | 35 | 25 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-06-18 | 104 | 74 | 2025-06-18 | 2025-06-18 | 1 | 1 | 9 | 7 | 140 | 100 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | 86 | 62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2022-10-21 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 1969.39 | Unknown | Unknown | Unknown | 47.94 | 1921.45 | 3981 | 886.05 | 1969.39 | -1083.34 | Yes | N/A | N/A | 2022-10-21 | 2023-12-05 | 411 | 293 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-09-11 | 281 | 201 | Unknown | 2024-08-14 | Unknown | Unknown | 2024-09-11 | 2024-09-17 | 7 | 5 | 2024-09-17 | 2024-09-17 | 1 | 1 | 692 | 494 | 8 | 6 | 700 | 500 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-11 | 642 | 459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 96.27 | 18.33 | Unknown | Unknown | 4.19 | 73.75 | 3981 | 585.17 | 96.27 | 488.9 | Yes | N/A | N/A | 2023-02-22 | 2023-02-15 | Unknown | Unknown | 2023-02-15 | 2023-03-30 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-03-09 | 9 | 7 | 2023-03-30 | 2023-08-18 | 142 | 102 | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2023-11-15 | Unknown | Unknown | 142 | 102 | 53 | 39 | 195 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -257 | -185 | No | 2023-02-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-12-29 | IOU Designed & Installed | N/A | Yes | 6 | -10.5 | -8.52 | Unknown | Unknown | Unknown | -1.98 | 3981 | 341 | -10.5 | 351.5 | Yes | N/A | N/A | 2023-02-23 | 2023-03-01 | 7 | 5 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-12-29 | 304 | 218 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-04-08 | 102 | 72 | 2024-04-08 | 2024-04-08 | 1 | 1 | 311 | 223 | 103 | 73 | 414 | 296 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | Applicant Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 3873.3 | 3873.3 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-28 | 232 | 167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | 2024-01-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 48109.26 | 7162.06 | Unknown | Unknown | 111.04 | 40836.16 | 51370 | 25143.91 | 48109.26 | -22965.35 | Yes | N/A | N/A | 2022-12-12 | 2023-03-07 | 86 | 62 | 2023-03-07 | 2023-09-06 | 184 | 132 | 2023-05-30 | 2023-09-01 | 45 | 31 | 2023-02-23 | 2023-09-11 | 64 | 46 | 2023-09-11 | Unknown | Unknown | Unknown | 2023-09-11 | 2024-01-05 | 117 | 85 | 2024-01-23 | 2024-02-15 | 24 | 18 | 2024-02-15 | 2024-02-15 | 1 | 1 | 131 | 93 | 390 | 282 | 521 | 375 | Steps 2,3,5,6,7 | 289 | 207 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-29 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | -9.86 | -8.02 | Unknown | Unknown | Unknown | -1.84 | 3981 | 1121.14 | -9.86 | 1131 | Yes | N/A | N/A | 2024-02-21 | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-02-29 | 56 | 40 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-08 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-04-16 | 40 | 28 | 2024-04-16 | 2024-04-16 | 1 | 1 | 9 | 7 | 97 | 69 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -659 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-06 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 3837.69 | 982.46 | Unknown | 82.25 | Unknown | 2772.98 | Unknown | 1846.17 | 3837.69 | -1991.52 | Yes | N/A | N/A | 2025-02-05 | 2025-02-06 | 2 | 2 | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-18 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-03-21 | 4 | 4 | 2025-03-21 | 2025-03-21 | 1 | 1 | 43 | 31 | 6 | 6 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-29 | 649 | 464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 851.23 | -56.57 | Unknown | Unknown | -1302.8 | 2210.6 | 7087.17 | 1489.3 | 851.23 | 638.07 | Yes | N/A | N/A | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | 2023-11-08 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-11-10 | 4 | 4 | 2023-11-08 | 2024-03-21 | 135 | 97 | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-05-08 | Unknown | Unknown | 136 | 98 | 27 | 21 | 163 | 119 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 8.05 | 8.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | -122 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 799.24 | -34.65 | Unknown | Unknown | Unknown | 833.89 | 3981 | 765.43 | 799.24 | -33.81 | Yes | N/A | N/A | 2023-08-17 | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-08-17 | 74 | 54 | 2023-08-17 | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-24 | 8 | 6 | 2023-08-17 | 2023-12-28 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-30 | 34 | 24 | 2024-01-30 | 2024-01-30 | 1 | 1 | 134 | 96 | 117 | 85 | 251 | 181 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | -324 | -231 | No | 2022-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-24 | 2022-01-24 | 2023-02-09 | IOU Designed & Installed | N/A | Yes | 372 | 653.55 | -7.04 | Unknown | Unknown | 16.07 | 644.52 | 3885 | 872.72 | 653.55 | 219.17 | Yes | N/A | N/A | 2022-01-24 | 2023-01-31 | 373 | 267 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | Unknown | Unknown | 2023-02-09 | 2023-03-01 | 21 | 15 | 2023-03-01 | 2023-02-10 | Unknown | Unknown | 373 | 267 | 21 | 15 | 394 | 282 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-30 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 699.57 | 179.08 | Unknown | Unknown | Unknown | 520.49 | 3981 | 1355.86 | 699.57 | 656.29 | Yes | N/A | N/A | 2024-05-17 | 2024-05-24 | 8 | 6 | 2024-05-24 | 2024-05-30 | 7 | 5 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-08 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-19 | 12 | 10 | 2024-07-19 | 2024-07-19 | 1 | 1 | 48 | 34 | 20 | 16 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1809.12 | 288.16 | Unknown | 184.28 | 14.9 | 1321.78 | 3981 | 2349.81 | 1809.12 | 540.69 | Yes | N/A | N/A | 2024-05-01 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-06-05 | 77 | 55 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-12 | 1 | 1 | 0 | 0 | 78 | 56 | 78 | 56 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -533 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 3.86 | -4.86 | Unknown | Unknown | Unknown | 8.72 | 3981 | 836.36 | 3.86 | 832.5 | Yes | N/A | N/A | 2023-10-10 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | 2023-10-10 | 2 | 2 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-12-04 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-03-01 | 89 | 65 | 2024-03-01 | 2024-03-01 | 1 | 1 | 56 | 40 | 92 | 68 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 340 | 340 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 1711.56 | 339.19 | Unknown | Unknown | -635.53 | 2007.9 | Unknown | 658.67 | 1711.56 | -1052.89 | Yes | N/A | N/A | 2023-07-17 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-08-11 | 134 | 96 | 2023-08-11 | 2023-08-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-31 | 72 | 52 | Unknown | 2023-10-18 | Unknown | Unknown | 2023-10-31 | 2023-11-14 | 15 | 11 | 2023-11-14 | 2023-11-14 | 1 | 1 | 87 | 63 | 150 | 108 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | -552 | -395 | No | 2025-01-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-05-07 | IOU Designed & Installed | N/A | Yes | 86 | 430.91 | Unknown | Unknown | Unknown | 11.19 | 419.72 | 3981 | 1276.05 | 430.91 | 845.14 | Yes | N/A | N/A | 2025-01-14 | 2025-04-07 | 84 | 60 | 2025-04-07 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-05-07 | 98 | 70 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-19 | 13 | 9 | 2025-05-19 | 2025-05-19 | 1 | 1 | 182 | 130 | 14 | 10 | 196 | 140 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -596 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-12 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | 7.56 | -6.74 | Unknown | Unknown | Unknown | 14.3 | 3981 | 1155.49 | 7.56 | 1147.93 | Yes | N/A | N/A | 2024-01-19 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-02-12 | 91 | 65 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-28 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-15 | 17 | 13 | 2024-03-15 | 2024-03-15 | 1 | 1 | 17 | 13 | 109 | 79 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 1129.92 | 1775.06 | Unknown | Unknown | -1646 | 1000.86 | Unknown | 1645.6 | 1129.92 | 515.68 | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-04 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 48.88 | -43.64 | Unknown | Unknown | Unknown | 92.52 | 3981 | 893.27 | 48.88 | 844.39 | Yes | N/A | N/A | 2023-12-11 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2023-12-11 | 40 | 28 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 41 | 29 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | 60 | 43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 12.38 | Unknown | Unknown | Unknown | Unknown | 12.38 | 3981 | 192.83 | 12.38 | 180.45 | Yes | N/A | N/A | 2023-11-29 | 2024-06-14 | 199 | 143 | 2024-06-14 | 2024-06-17 | 4 | 2 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-09-13 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-07 | 25 | 17 | 2024-10-07 | 2024-10-07 | 1 | 1 | 288 | 208 | 30 | 20 | 318 | 228 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 154 | 111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 2786.66 | 871.76 | Unknown | 309.73 | 4.21 | 1600.96 | 3981 | 1931.27 | 2786.66 | -855.39 | Yes | N/A | N/A | 2023-05-22 | 2023-06-02 | 12 | 10 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-10-30 | 151 | 107 | Unknown | 2023-10-23 | Unknown | Unknown | 2023-10-30 | 2023-11-02 | 4 | 4 | 2023-11-02 | 2023-11-02 | 1 | 1 | 163 | 117 | 5 | 5 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 249 | 179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | Unknown | 2023-08-31 | IOU Designed & Installed | N/A | No | N/A | -6 | -11.78 | Unknown | Unknown | Unknown | 5.78 | 3981 | 859.57 | -6 | 865.57 | Yes | N/A | N/A | 2023-04-04 | 2023-05-04 | 31 | 23 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-08-31 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-09-07 | 8 | 6 | 2023-09-07 | 2023-09-07 | 1 | 1 | 147 | 107 | 9 | 7 | 156 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 118.4 | 118.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -504 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-13 | 2024-10-13 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 2198.12 | 303.12 | Unknown | Unknown | Unknown | 1895 | 3981 | 1068.64 | 2198.12 | -1129.48 | Yes | N/A | N/A | 2024-10-13 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-10-13 | 26 | 18 | 2024-10-13 | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-28 | 12 | 8 | 2024-10-13 | 2025-03-14 | 153 | 110 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-14 | 2025-03-19 | 6 | 4 | 2025-03-19 | 2025-03-19 | 1 | 1 | 153 | 110 | 45 | 31 | 198 | 141 | Steps 2,3,5,6,7 | 15 | 10 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -398 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-12-08 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 0.39 | Unknown | Unknown | Unknown | 0.66 | -0.27 | 3981 | 1207.17 | 0.39 | 1206.78 | Yes | N/A | N/A | 2023-10-11 | 2023-12-08 | 59 | 43 | 2023-12-08 | 2023-12-08 | 1 | 1 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-06-04 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-06-24 | 102 | 72 | 127 | 91 | 103 | 73 | 230 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-22 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 582.25 | -11.7 | Unknown | Unknown | Unknown | 593.95 | 3981 | 1712.85 | 582.25 | 1130.6 | Yes | N/A | N/A | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-13 | 15 | 11 | 2025-05-13 | 2025-05-13 | 1 | 1 | 37 | 27 | 17 | 13 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-08 | 486 | 347 | No | 2022-12-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | Yes | 668 | -1010.52 | -10.7 | Unknown | Unknown | -1633 | 633.18 | Unknown | 1516.09 | -1010.52 | 2526.61 | Yes | N/A | N/A | 2022-12-13 | 2024-10-11 | 669 | 479 | 2024-10-11 | 2025-02-04 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-24 | 29 | 21 | 2025-02-04 | 2025-02-24 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 690 | 494 | 146 | 104 | 836 | 598 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | -959.79 | 1291.24 | Unknown | 280.85 | -3257 | 725.12 | Unknown | 3257.32 | -959.79 | 4217.11 | Yes | N/A | N/A | 2025-03-14 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-04-30 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -626 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 517.55 | -20.98 | Unknown | Unknown | Unknown | 538.53 | 3941 | 845 | 517.55 | 327.45 | Yes | N/A | N/A | 2024-05-16 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-16 | 44 | 32 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-05-24 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-13 | 21 | 15 | 2024-06-13 | 2024-06-13 | 1 | 1 | 9 | 7 | 66 | 48 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-25 | 2024-03-17 | IOU Designed & Installed | N/A | No | N/A | 1426.31 | 457.22 | Unknown | 49.67 | Unknown | 919.42 | Unknown | 1155.49 | 1426.31 | -270.82 | Yes | N/A | N/A | 2024-01-24 | 2024-01-25 | 2 | 2 | 2024-01-25 | 2024-01-26 | 2 | 2 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-03-17 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-03-17 | 2024-03-20 | 4 | 3 | 2024-03-20 | 2024-03-20 | 1 | 1 | 55 | 39 | 7 | 6 | 62 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -504 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 1804.56 | 551.03 | Unknown | Unknown | 16.5 | 1237.03 | 3981 | 1012.75 | 1804.56 | -791.81 | Yes | N/A | N/A | 2024-02-08 | 2023-11-10 | Unknown | Unknown | 2023-11-10 | 2024-02-08 | 91 | 65 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-05-13 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-06-28 | 47 | 35 | 2024-06-28 | 2024-05-31 | Unknown | Unknown | 96 | 68 | 138 | 100 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 103.98 | -1.5 | Unknown | Unknown | Unknown | 105.48 | 3981 | 1615.09 | 103.98 | 1511.11 | Yes | N/A | N/A | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-16 | 35 | 25 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2 | 2 | 37 | 27 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-30 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | -6.52 | -11.96 | Unknown | Unknown | Unknown | 5.44 | 3981 | 1151.95 | -6.52 | 1158.47 | Yes | N/A | N/A | 2024-05-20 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-05-20 | 46 | 32 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-25 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-03 | 9 | 7 | 2024-07-03 | 2024-07-03 | 1 | 1 | 37 | 27 | 56 | 40 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-07 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-29 | 2025-01-11 | IOU Designed & Installed | N/A | No | N/A | -4728.21 | 3422.48 | Unknown | Unknown | -9735 | 1584.31 | Unknown | 9734.5 | -4728.21 | 14462.71 | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-11 | 2025-01-21 | 11 | 7 | 2025-01-21 | 2025-01-21 | 1 | 1 | 1 | 1 | 12 | 8 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -396 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 806.47 | 122.45 | Unknown | Unknown | -595.8 | 1279.82 | 0 | 651.78 | 806.47 | -154.69 | Yes | N/A | N/A | 2023-10-19 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-11-15 | 94 | 68 | 2023-11-15 | 2023-11-29 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-04-11 | 135 | 97 | Unknown | 2024-07-03 | Unknown | Unknown | 2024-04-11 | 2024-07-03 | 84 | 60 | 2024-07-03 | 2024-07-03 | 1 | 1 | 150 | 108 | 179 | 129 | 329 | 237 | Steps 2,3,5,6,7 | 83 | 59 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1739.99 | 404.18 | Unknown | 182.28 | 39.72 | 1113.81 | 3981 | 680.23 | 1739.99 | -1059.76 | Yes | N/A | N/A | 2023-08-21 | 2023-06-23 | Unknown | Unknown | 2023-06-23 | 2023-08-10 | 49 | 35 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-02-29 | 1 | 1 | 0 | 0 | 50 | 36 | 50 | 36 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 166.05 | 166.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | 75 | 54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2024-05-14 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 3002.54 | 300.29 | Unknown | Unknown | -11572 | 14274.25 | 3981 | 14357.56 | 3002.54 | 11355.02 | Yes | N/A | N/A | 2023-12-19 | 2023-12-20 | 2 | 2 | 2023-12-20 | 2024-09-06 | 262 | 188 | 2024-05-15 | 2024-12-06 | 151 | 111 | 2024-09-04 | 2024-12-17 | 31 | 21 | 2024-09-06 | 2025-02-12 | 160 | 114 | 2024-12-03 | 2025-02-12 | 72 | 52 | 2025-02-24 | 2025-03-06 | 11 | 9 | 2025-03-06 | 2025-03-05 | Unknown | Unknown | 313 | 227 | 376 | 270 | 689 | 497 | Steps 2,3,5,6,7 | 380 | 272 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-11 | 427 | 306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 16.23 | -14.42 | Unknown | Unknown | Unknown | 30.65 | 3981 | 1170.64 | 16.23 | 1154.41 | Yes | N/A | N/A | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | 2024-03-15 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-10-16 | 196 | 140 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-06-11 | 89 | 63 | 2024-06-11 | 2024-06-11 | 1 | 1 | 1 | 1 | 353 | 253 | 354 | 254 | Steps 2,3,5,6,7 | 215 | 153 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 1518.24 | -29.32 | Unknown | Unknown | 6.53 | 1541.03 | 3941 | 1054.62 | 1518.24 | -463.62 | Yes | N/A | N/A | 2024-02-08 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2024-02-08 | 71 | 51 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-06-04 | 118 | 84 | Unknown | 2024-05-28 | Unknown | Unknown | 2024-06-04 | 2024-06-25 | 22 | 16 | 2024-06-25 | 2024-06-25 | 1 | 1 | 118 | 84 | 94 | 68 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | 75 | 54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-06-19 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 5829.11 | -18.36 | Unknown | Unknown | Unknown | 5847.47 | 0 | 2026.67 | 5829.11 | -3802.44 | Yes | N/A | N/A | 2023-04-18 | 2023-04-03 | Unknown | Unknown | 2023-04-03 | 2023-08-02 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-04-23 | 142 | 102 | 2024-04-23 | 2024-04-23 | 1 | 1 | 0 | 0 | 265 | 191 | 265 | 191 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1962.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2025-01-31 | 50 | 36 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-23 | 1 | 1 | 50 | 36 | 2 | 2 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 436.06 | -11.62 | Unknown | Unknown | 8.35 | 439.33 | 3981 | 572.83 | 436.06 | 136.77 | Yes | N/A | N/A | 2023-03-02 | 2023-03-17 | 16 | 12 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 90.05 | 90.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-30 | 152 | 109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 534.31 | -11.07 | Unknown | Unknown | 35.15 | 510.23 | 3981 | 302.4 | 534.31 | -231.91 | Yes | N/A | N/A | 2023-02-13 | 2023-02-14 | 2 | 2 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2023-05-01 | Unknown | Unknown | 2 | 2 | 0 | 0 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-02 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 619.77 | -11.97 | Unknown | Unknown | 7.54 | 624.2 | 3981 | 742.67 | 619.77 | 122.9 | Yes | N/A | N/A | 2023-05-31 | 2023-10-06 | 129 | 93 | 2023-10-06 | 2023-10-13 | 8 | 6 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-11-09 | 31 | 23 | Unknown | 2024-04-05 | Unknown | Unknown | 2023-11-09 | 2024-04-16 | 160 | 114 | 2024-04-16 | 2024-04-16 | 1 | 1 | 160 | 116 | 169 | 121 | 329 | 237 | Steps 2,3,5,6,7 | 148 | 106 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Pauma Valley | N/A | 440 | 440 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -11 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-06-01 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 38688.87 | 11322.94 | Unknown | 402.56 | 596.2 | 26367.17 | 123081 | 26728.1 | 38688.87 | -11960.77 | Yes | N/A | N/A | 2023-04-12 | 2023-04-28 | 17 | 13 | 2023-04-28 | 2023-08-08 | 103 | 73 | 2023-07-05 | 2023-08-01 | 28 | 20 | 2023-08-02 | 2023-09-26 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-03-05 | 120 | 86 | 2024-03-05 | 2024-03-05 | 1 | 1 | 45 | 33 | 280 | 200 | 325 | 233 | Steps 2,3,5,6,7 | 34 | 24 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 61.16 | -4.68 | Unknown | Unknown | Unknown | 65.84 | Unknown | 288.14 | 61.16 | 226.98 | Yes | N/A | N/A | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-19 | 16 | 12 | 2023-12-19 | 2023-12-19 | 1 | 1 | 5 | 3 | 18 | 14 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-20 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 3.92 | Unknown | Unknown | Unknown | Unknown | 3.92 | Unknown | 1449.68 | 3.92 | 1445.76 | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-07-16 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-07-31 | 16 | 12 | 2024-07-31 | 2024-07-31 | 1 | 1 | 56 | 40 | 18 | 14 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-08 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -16.8 | -12.19 | Unknown | Unknown | Unknown | -4.61 | Unknown | 98.41 | -16.8 | 115.21 | Yes | N/A | N/A | 2023-02-01 | 2023-02-03 | 3 | 3 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -91 | -66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.25 | Unknown | Unknown | Unknown | Unknown | -0.25 | Unknown | 52.54 | -0.25 | 52.79 | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-12-31 | 202 | 144 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-27 | 31 | 23 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-22 | 1 | 1 | 1 | 1 | 234 | 168 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-SOUTH of 56 | 1022 | 1022 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-03-29 | -31 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2024-04-20 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | -1251.55 | 467.18 | Unknown | Unknown | -10842 | 9123.27 | 3981 | 14823.39 | -1251.55 | 16074.94 | Yes | N/A | N/A | 2023-11-27 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-08-16 | 274 | 196 | 2024-04-12 | 2024-04-12 | 1 | 1 | 2024-04-29 | 2024-08-14 | 28 | 22 | 2024-08-16 | 2024-12-23 | 130 | 92 | 2024-09-12 | 2025-01-30 | 141 | 101 | 2025-02-10 | 2025-03-03 | 22 | 16 | 2025-03-03 | 2025-02-26 | Unknown | Unknown | 131 | 93 | 465 | 335 | 596 | 428 | Steps 2,3,5,6,7 | 228 | 162 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -411 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | -551.37 | 179.63 | Unknown | Unknown | -1964 | 1233 | Unknown | 1824.54 | -551.37 | 2375.91 | Yes | N/A | N/A | 2025-01-09 | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-01-09 | 7 | 5 | 2025-01-09 | 2025-02-19 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-21 | 25 | 19 | 2025-02-21 | 2025-02-21 | 1 | 1 | 43 | 31 | 33 | 25 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -526 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-11-13 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 1462.9 | 914.7 | Unknown | 118.74 | Unknown | 429.46 | Unknown | 144.47 | 1462.9 | -1318.43 | Yes | N/A | N/A | 2024-10-24 | 2024-11-13 | 21 | 15 | 2024-11-13 | 2024-11-22 | 10 | 8 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-04-22 | 152 | 108 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-02 | 11 | 9 | 2025-05-02 | 2025-05-02 | 1 | 1 | 173 | 123 | 22 | 18 | 195 | 141 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-16 | 9 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-19 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 401.27 | 288.16 | Unknown | Unknown | Unknown | 113.11 | 3981 | 482.43 | 401.27 | 81.16 | Yes | N/A | N/A | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | 2023-10-19 | 4 | 4 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-25 | 7 | 5 | 2023-10-25 | 2023-10-25 | 1 | 1 | 2 | 2 | 12 | 10 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1391.95 | -1.25 | Unknown | Unknown | 16.38 | 1376.82 | 3981 | 909.84 | 1391.95 | -482.11 | Yes | N/A | N/A | 2024-03-25 | 2024-07-16 | 114 | 82 | 2024-07-16 | 2024-07-23 | 8 | 6 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 114 | 82 | 9 | 7 | 123 | 89 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | -263 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 64.89 | -1.26 | Unknown | Unknown | Unknown | 66.15 | Unknown | 501.14 | 64.89 | 436.25 | Yes | N/A | N/A | 2024-02-05 | 2024-02-09 | 5 | 5 | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-04-10 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-09-06 | 150 | 108 | 2024-09-06 | 2024-09-05 | Unknown | Unknown | 67 | 49 | 151 | 109 | 218 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 36.99 | Unknown | Unknown | Unknown | Unknown | 36.99 | Unknown | 1603.61 | 36.99 | 1566.62 | Yes | N/A | N/A | 2024-08-16 | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-08-16 | 166 | 120 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-03 | 1 | 1 | 0 | 0 | 167 | 121 | 167 | 121 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | 86 | 61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 65.59 | Unknown | Unknown | Unknown | Unknown | 65.59 | 3981 | 142.53 | 65.59 | 76.94 | Yes | N/A | N/A | 2024-07-30 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-09-19 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-04-15 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 209 | 149 | 126 | 90 | 335 | 239 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -627 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-07 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 285.68 | -5.7 | Unknown | Unknown | Unknown | 291.38 | 3981 | 1775.34 | 285.68 | 1489.66 | Yes | N/A | N/A | 2024-12-16 | 2025-01-07 | 23 | 17 | 2025-01-07 | 2025-01-08 | 2 | 2 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-03-05 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-18 | 14 | 10 | 2025-03-18 | 2025-03-18 | 1 | 1 | 80 | 58 | 17 | 13 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | -2560 | -1829 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1232.06 | -18.83 | Unknown | Unknown | -395.11 | 1646 | Unknown | 416.15 | 1232.06 | -815.91 | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | 2023-09-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-12-18 | 81 | 57 | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2023-12-28 | Unknown | Unknown | 82 | 58 | 22 | 16 | 104 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-11-19 | -1032 | -739 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 50.85 | -0.62 | Unknown | Unknown | Unknown | 51.47 | Unknown | 1735.88 | 50.85 | 1685.03 | Yes | N/A | N/A | 2024-11-12 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-12 | 5 | 3 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-01-13 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-21 | 9 | 7 | 2025-01-21 | 2025-01-21 | 1 | 1 | 63 | 45 | 15 | 11 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 316 | 316 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-27 | 799 | 572 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 787.74 | -15.83 | Unknown | Unknown | Unknown | 803.57 | 207704 | 15179.85 | 787.74 | 14392.11 | Yes | N/A | N/A | 2024-01-26 | 2024-03-26 | 61 | 43 | 2024-03-26 | 2024-06-05 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-16 | 22 | 16 | 2024-06-05 | 2025-05-06 | 336 | 240 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-06-02 | 2025-06-03 | 2 | 2 | 2025-06-03 | 2025-06-03 | 1 | 1 | 397 | 283 | 97 | 71 | 494 | 354 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -470 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-11-04 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 4.03 | Unknown | Unknown | Unknown | Unknown | 4.03 | Unknown | 477.21 | 4.03 | 473.18 | Yes | N/A | N/A | 2024-10-23 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-10-23 | 2 | 2 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2025-01-30 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-19 | 21 | 15 | 2025-02-19 | 2025-02-19 | 1 | 1 | 88 | 64 | 24 | 18 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -589 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-04-27 | IOU Designed & Installed | N/A | No | N/A | 572.31 | 196.68 | Unknown | 77.89 | Unknown | 297.74 | Unknown | 722.58 | 572.31 | 150.27 | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | 2023-04-27 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-04-28 | 2 | 2 | 2023-04-28 | 2023-04-28 | 1 | 1 | 54 | 40 | 3 | 3 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -479 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 2229.25 | 491.61 | Unknown | 156.39 | 15.57 | 1565.68 | 3981 | 565.59 | 2229.25 | -1663.66 | Yes | N/A | N/A | 2023-01-05 | 2023-02-06 | 33 | 23 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2023-05-30 | 114 | 82 | Unknown | 2023-04-12 | Unknown | Unknown | 2023-05-30 | 2023-06-12 | 14 | 10 | 2023-06-12 | 2023-06-12 | 1 | 1 | 147 | 105 | 15 | 11 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | -179 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-09-12 | IOU Designed & Installed | N/A | No | N/A | 528.99 | -10.51 | Unknown | Unknown | Unknown | 539.5 | 3981 | 748.46 | 528.99 | 219.47 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-09-12 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2023-10-23 | 42 | 30 | 2023-10-23 | 2023-10-23 | 1 | 1 | 77 | 55 | 44 | 32 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 1285.25 | 253.74 | Unknown | Unknown | Unknown | 1031.51 | Unknown | 1552.51 | 1285.25 | 267.26 | Yes | N/A | N/A | 2024-09-05 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-09-24 | 70 | 50 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-08 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-24 | 17 | 13 | 2024-10-24 | 2024-10-24 | 1 | 1 | 15 | 11 | 88 | 64 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -67 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1400.03 | 189.69 | Unknown | Unknown | 75.02 | 1135.32 | 3981 | 572.68 | 1400.03 | -827.35 | Yes | N/A | N/A | 2024-01-25 | 2024-02-06 | 13 | 9 | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-10-18 | 256 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-21 | 4 | 2 | 2024-10-21 | 2024-10-21 | 1 | 1 | 269 | 193 | 6 | 4 | 275 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 566.17 | -13.03 | Unknown | Unknown | Unknown | 579.2 | Unknown | 965.91 | 566.17 | 399.74 | Yes | N/A | N/A | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-13 | 44 | 32 | 2024-06-13 | 2024-06-13 | 1 | 1 | 4 | 4 | 46 | 34 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 1941.63 | 606.36 | Unknown | Unknown | Unknown | 1335.27 | 3981 | 893.49 | 1941.63 | -1048.14 | Yes | N/A | N/A | 2024-04-23 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-31 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-06 | 7 | 5 | 2024-06-06 | 2024-06-06 | 1 | 1 | 39 | 29 | 8 | 6 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -677 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 1798.06 | 235.23 | Unknown | Unknown | Unknown | 1562.83 | 3981 | 1465.63 | 1798.06 | -332.43 | Yes | N/A | N/A | 2024-09-05 | 2024-08-30 | Unknown | Unknown | 2024-08-30 | 2024-09-05 | 7 | 5 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-09-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-07 | 33 | 23 | 2024-10-07 | 2024-10-07 | 1 | 1 | 1 | 1 | 41 | 29 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-03 | 62 | 45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | -8.29 | -22.87 | Unknown | Unknown | Unknown | 14.58 | 3981 | 872.01 | -8.29 | 880.3 | Yes | N/A | N/A | 2023-06-23 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-07-03 | 63 | 45 | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-07-20 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-21 | 2 | 2 | 2023-07-21 | 2023-10-04 | 76 | 54 | 18 | 14 | 141 | 101 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -494 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 0.47 | -6.11 | Unknown | Unknown | Unknown | 6.58 | 3241 | 635.88 | 0.47 | 635.41 | Yes | N/A | N/A | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-11-14 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-12-07 | 24 | 18 | 2023-12-07 | 2023-12-07 | 1 | 1 | 44 | 32 | 26 | 20 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -458 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-05-05 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 2828.39 | 925.1 | Unknown | 243.48 | Unknown | 1659.81 | 3981 | 932.72 | 2828.39 | -1895.67 | Yes | N/A | N/A | 2023-02-21 | 2023-05-05 | 74 | 54 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-08-30 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-06 | 8 | 6 | 2023-09-06 | 2023-09-06 | 1 | 1 | 192 | 138 | 9 | 7 | 201 | 145 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 143 | 143 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 8 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 2139.69 | 1521.34 | Unknown | Unknown | -11724 | 12342.35 | 3981 | 15454.38 | 2139.69 | 13314.69 | Yes | N/A | N/A | 2024-01-26 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-05-09 | 149 | 107 | 2024-02-21 | 2024-04-22 | 5 | 3 | 2024-05-02 | 2024-06-21 | 51 | 37 | 2024-05-09 | 2024-07-16 | 69 | 49 | 2024-05-13 | 2024-05-20 | 8 | 6 | 2024-07-01 | 2024-07-25 | 25 | 19 | 2024-07-25 | 2024-07-19 | Unknown | Unknown | 74 | 52 | 233 | 169 | 307 | 221 | Steps 2,3,5,6,7 | 185 | 133 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-08 | 6 | 5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | Unknown | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 497.52 | -22.44 | Unknown | Unknown | Unknown | 519.96 | 3885 | 591.79 | 497.52 | 94.27 | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-11-01 | 224 | 160 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-15 | 15 | 11 | 2023-11-15 | 2023-11-14 | Unknown | Unknown | 225 | 161 | 15 | 11 | 240 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 110 | 110 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | 72 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-13 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 9321.74 | 2207.42 | Unknown | Unknown | -1202 | 8316.32 | 3981 | 2244.73 | 9321.74 | -7077.01 | Yes | N/A | N/A | 2024-11-07 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-12-06 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-04-03 | 119 | 85 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-27 | 2025-04-21 | 26 | 18 | 2025-04-21 | 2025-04-14 | Unknown | Unknown | 119 | 85 | 163 | 117 | 282 | 202 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1499.32 | 382.05 | Unknown | Unknown | Unknown | 1117.27 | Unknown | 2191.25 | 1499.32 | 691.93 | Yes | N/A | N/A | 2025-04-16 | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-04-21 | 27 | 19 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-04-25 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-01 | 7 | 5 | 2025-05-01 | 2025-05-01 | 1 | 1 | 5 | 5 | 35 | 25 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 12.15 | 12.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 51.33 | -7.83 | Unknown | Unknown | Unknown | 59.16 | Unknown | 496.45 | 51.33 | 445.12 | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-08-07 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-09-13 | 38 | 28 | 2023-09-13 | 2023-09-13 | 1 | 1 | 26 | 18 | 40 | 30 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -485 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 756.68 | 192.82 | Unknown | Unknown | Unknown | 563.86 | 3981 | 1358.16 | 756.68 | 601.48 | Yes | N/A | N/A | 2024-08-29 | 2024-08-25 | Unknown | Unknown | 2024-08-25 | 2024-08-30 | 6 | 5 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2025-02-03 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-04-14 | 71 | 51 | 2025-04-14 | 2025-04-14 | 1 | 1 | 159 | 113 | 78 | 57 | 237 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-09-18 | IOU Designed & Installed | N/A | No | N/A | 0.61 | -8.2 | Unknown | Unknown | Unknown | 8.81 | Unknown | 941.92 | 0.61 | 941.31 | Yes | N/A | N/A | 2023-09-08 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-09-08 | 116 | 84 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-09-18 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-11-29 | 73 | 53 | 2023-11-29 | 2023-11-29 | 1 | 1 | 11 | 7 | 190 | 138 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -673 | -482 | No | 2024-11-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2024-11-15 | IOU Designed & Installed | N/A | Yes | 1 | 1004.86 | -20.4 | Unknown | Unknown | Unknown | 1025.26 | Unknown | 1544.6 | 1004.86 | 539.74 | Yes | N/A | N/A | 2024-11-06 | 2024-11-07 | 2 | 2 | 2024-11-07 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-12 | 7 | 5 | 2024-11-06 | 2024-11-15 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-04 | 20 | 14 | 2024-12-04 | 2024-12-04 | 1 | 1 | 12 | 10 | 28 | 20 | 40 | 30 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | 594.05 | 594.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-09-05 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | -2827.51 | 583.62 | Unknown | Unknown | -17574.37 | 14163.24 | 0 | 17581.52 | -2827.51 | 20409.03 | Yes | N/A | N/A | 2024-03-05 | 2024-04-23 | 50 | 36 | 2024-04-23 | 2025-02-05 | 289 | 207 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-12-04 | 2025-01-29 | 11 | 9 | 2025-02-05 | Unknown | Unknown | Unknown | 2025-02-21 | 2025-04-15 | 54 | 38 | 2025-04-22 | 2025-05-07 | 16 | 12 | 2025-05-07 | 2025-05-07 | 1 | 1 | 51 | 37 | 371 | 267 | 422 | 304 | Steps 2,3,5,6,7 | 90 | 64 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | 2025-06-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1390.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-13 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-16 | 4 | 2 | 2025-06-16 | 2025-06-16 | 1 | 1 | 12 | 10 | 6 | 4 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | MOUNT LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -333 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-11 | IOU Designed & Installed | N/A | No | N/A | 324.5 | 186.73 | Unknown | 21.85 | Unknown | 115.92 | Unknown | 690.19 | 324.5 | 365.69 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-04-11 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-04-18 | 8 | 6 | 2023-04-18 | 2023-04-18 | 1 | 1 | 24 | 18 | 9 | 7 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -404 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -259.4 | -3.44 | Unknown | Unknown | -513.81 | 257.85 | 3981 | 1364.29 | -259.4 | 1623.69 | Yes | N/A | N/A | 2024-04-02 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-04-02 | 9 | 7 | 2024-04-02 | 2024-05-08 | 37 | 27 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-02 | 1 | 1 | 37 | 27 | 11 | 9 | 48 | 36 | Steps 2,3,5,6,7 | 124 | 88 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 507.56 | -10.2 | Unknown | Unknown | Unknown | 517.76 | 3981 | 1643.26 | 507.56 | 1135.7 | Yes | N/A | N/A | 2025-02-05 | 2025-01-23 | Unknown | Unknown | 2025-01-23 | 2025-02-05 | 14 | 10 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-18 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-23 | 6 | 4 | 2025-04-23 | 2025-04-21 | Unknown | Unknown | 73 | 53 | 20 | 14 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-16 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 544.27 | 1998.62 | Unknown | 708.93 | -3118 | 954.72 | Unknown | 3117.84 | 544.27 | 2573.57 | Yes | N/A | N/A | 2023-11-21 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2023-12-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | 2023-12-29 | 2023-12-29 | 1 | 1 | 2023-12-06 | 2023-12-11 | 6 | 4 | 2023-12-11 | 2023-12-11 | 1 | 1 | 0 | 0 | 51 | 37 | 51 | 37 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 457.74 | -19.28 | Unknown | Unknown | Unknown | 477.02 | 3981 | 860.12 | 457.74 | 402.38 | Yes | N/A | N/A | 2023-12-07 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-12-18 | 83 | 59 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2023-12-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-08 | 12 | 8 | 2024-01-08 | 2024-01-08 | 1 | 1 | 10 | 8 | 96 | 68 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | -156 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.65 | -5.54 | Unknown | Unknown | Unknown | -2.11 | Unknown | 341 | -7.65 | 348.65 | Yes | N/A | N/A | 2023-02-28 | 2023-03-07 | 8 | 6 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -56 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.62 | -5.83 | Unknown | Unknown | 1.07 | -1.86 | Unknown | 495.15 | -6.62 | 501.77 | Yes | N/A | N/A | 2023-08-03 | 2023-08-21 | 19 | 13 | 2023-08-21 | 2023-08-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 19 | 13 | 3 | 3 | 22 | 16 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-13 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2420.2 | -8.71 | Unknown | Unknown | Unknown | 2428.91 | 3981 | 917.56 | 2420.2 | -1502.64 | Yes | N/A | N/A | 2023-01-13 | 2023-03-03 | 50 | 36 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 50 | 36 | 1 | 1 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | -383 | -275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-07-15 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 3161.39 | 1013.6 | Unknown | 53.2 | Unknown | 2094.59 | Unknown | 1572.78 | 3161.39 | -1588.61 | Yes | N/A | N/A | 2023-12-13 | 2024-07-15 | 216 | 154 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-31 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-05 | 6 | 4 | 2024-08-05 | 2024-08-05 | 1 | 1 | 233 | 167 | 8 | 6 | 241 | 173 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | ES 1110-F5 DIXON TL PH2 | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | 257 | 184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2025-06-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 81410.34 | 1510.08 | Unknown | Unknown | 14074.61 | 65825.65 | 0 | 47546.71 | 81410.34 | -33863.63 | Yes | N/A | N/A | 2023-06-01 | 2024-01-13 | 227 | 162 | 2024-01-13 | 2024-04-16 | 95 | 67 | 2024-02-07 | 2024-10-24 | 120 | 86 | 2024-02-07 | 2025-07-16 | 144 | 100 | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-03 | 2025-05-05 | 307 | 219 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 347 | 248 | 548 | 388 | 895 | 636 | Steps 2,3,5,6,7 | 707 | 505 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 146.1 | 146.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -653 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-25 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | -98.57 | Unknown | Unknown | Unknown | -140 | 41.43 | Unknown | 1691.91 | -98.57 | 1790.48 | Yes | N/A | N/A | 2024-11-20 | 2024-11-25 | 6 | 4 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2025-01-29 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-01-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-06 | 9 | 7 | 2025-02-06 | 2025-02-06 | 1 | 1 | 73 | 53 | 11 | 9 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | -410 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | 4630.72 | 1494.82 | Unknown | Unknown | -558.3 | 3694.2 | Unknown | 647.76 | 4630.72 | -3982.96 | Yes | N/A | N/A | 2023-02-06 | 2023-04-03 | 57 | 41 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | 2023-09-20 | 226 | 162 | Unknown | 2023-09-15 | Unknown | Unknown | 2023-09-20 | 2023-09-21 | 2 | 2 | 2023-09-21 | 2023-09-21 | 1 | 1 | 283 | 203 | 3 | 3 | 286 | 206 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-23 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 633.13 | -1.5 | Unknown | Unknown | Unknown | 634.63 | Unknown | 1059.42 | 633.13 | 426.29 | Yes | N/A | N/A | 2024-05-24 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-24 | 59 | 43 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-07-25 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-07 | 14 | 10 | 2024-08-07 | 2024-08-07 | 1 | 1 | 63 | 45 | 74 | 54 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 211 | 211 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | 389 | 279 | No | 2023-09-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | Yes | 439 | 1983.02 | -1.57 | Unknown | Unknown | 2.15 | 1982.44 | 3981 | 1364.93 | 1983.02 | -618.09 | Yes | N/A | N/A | 2023-09-07 | 2024-11-18 | 439 | 313 | 2024-11-18 | 2024-11-19 | 2 | 2 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 439 | 313 | 3 | 3 | 442 | 316 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | -850.48 | Unknown | Unknown | Unknown | -1235 | 384.52 | Unknown | 1235.36 | -850.48 | 2085.84 | Yes | N/A | N/A | 2024-06-18 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-08-28 | 98 | 70 | 2024-08-28 | 2024-09-09 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2025-01-06 | 120 | 86 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-01-06 | 2025-01-08 | 3 | 3 | 2025-01-08 | 2025-01-07 | Unknown | Unknown | 133 | 95 | 101 | 73 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -424 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 746.5 | -11.16 | Unknown | Unknown | -964.07 | 1721.73 | Unknown | 965.02 | 746.5 | 218.52 | Yes | N/A | N/A | 2023-12-13 | 2024-01-15 | 34 | 24 | 2024-01-15 | 2024-01-29 | 15 | 11 | 2024-01-29 | 2024-03-13 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-05-20 | 56 | 40 | Unknown | 2024-05-18 | Unknown | Unknown | 2024-05-20 | 2024-06-10 | 22 | 16 | 2024-06-10 | 2024-06-10 | 1 | 1 | 135 | 97 | 38 | 28 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | NCTD-Trolly South of 56, OCTA/METROLINK | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 342 | 245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-18 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 5972.06 | Unknown | Unknown | Unknown | -162 | 6134.06 | Unknown | 994.11 | 5972.06 | -4977.95 | Yes | N/A | N/A | 2024-01-17 | 2024-04-19 | 94 | 68 | 2024-04-19 | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-15 | 8 | 6 | 2024-02-01 | 2024-03-22 | 20 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-08 | 14 | 10 | 2024-05-08 | 2024-05-08 | 1 | 1 | 102 | 74 | 35 | 23 | 137 | 97 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 3092 | 3092 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-12-19 | 521 | 374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 805.29 | -16.18 | Unknown | Unknown | Unknown | 821.47 | 27867 | 1853.26 | 805.29 | 1047.97 | Yes | N/A | N/A | 2024-11-11 | 2025-04-09 | 150 | 108 | 2025-04-09 | 2025-04-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-22 | 13 | 9 | 2025-04-14 | 2025-04-25 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-23 | Unknown | Unknown | 162 | 118 | 19 | 13 | 181 | 131 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -488 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 603.39 | 185.02 | Unknown | Unknown | Unknown | 418.37 | Unknown | 1115.06 | 603.39 | 511.67 | Yes | N/A | N/A | 2024-03-06 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2024-04-01 | 132 | 94 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-07-11 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-15 | 5 | 3 | 2024-07-15 | 2024-07-15 | 1 | 1 | 102 | 74 | 138 | 98 | 240 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | -612 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-19 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | -253.74 | -5.36 | Unknown | Unknown | -251 | 2.62 | Unknown | 944.5 | -253.74 | 1198.24 | Yes | N/A | N/A | 2023-08-30 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-09-19 | 83 | 59 | 2023-09-19 | 2023-09-21 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-09-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-25 | 34 | 24 | 2023-10-25 | 2023-10-25 | 1 | 1 | 5 | 5 | 118 | 84 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -187 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-29 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 51.51 | Unknown | Unknown | Unknown | Unknown | 51.51 | Unknown | 1466.27 | 51.51 | 1414.76 | Yes | N/A | N/A | 2024-05-28 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-29 | 49 | 35 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-08-20 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-27 | 39 | 29 | 2024-09-27 | 2024-09-27 | 1 | 1 | 84 | 60 | 89 | 65 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-26 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | -12.63 | -10.26 | Unknown | Unknown | Unknown | -2.37 | 3981 | 1105.93 | -12.63 | 1118.56 | Yes | N/A | N/A | 2024-01-02 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2024-01-26 | 93 | 67 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-01-31 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-23 | 24 | 18 | 2024-02-23 | 2024-02-23 | 1 | 1 | 6 | 4 | 118 | 86 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 528 | 377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 6865.57 | 9225.76 | Unknown | 2475.37 | -11488 | 6652.44 | Unknown | 11488.29 | 6865.57 | 4622.72 | Yes | N/A | N/A | 2024-09-30 | 2024-10-16 | 17 | 13 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-20 | 5 | 3 | 2024-10-20 | 2024-10-20 | 1 | 0 | 17 | 13 | 6 | 3 | 23 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | -430 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 366.21 | -6.9 | Unknown | Unknown | Unknown | 373.11 | 3981 | 1651.35 | 366.21 | 1285.14 | Yes | N/A | N/A | 2024-10-04 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-10-04 | 157 | 113 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2025-01-07 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-06 | 31 | 23 | 2025-02-06 | 2025-02-05 | Unknown | Unknown | 96 | 68 | 188 | 136 | 284 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 416500 | 416500 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-01 | 417 | 299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 749.02 | -14.36 | Unknown | Unknown | Unknown | 763.38 | 3981 | 627.04 | 749.02 | -121.98 | Yes | N/A | N/A | 2023-12-26 | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2024-01-08 | 151 | 107 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 0 | 0 | 151 | 107 | 151 | 107 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-08-05 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 1794.08 | 554.6 | Unknown | 6.58 | Unknown | 1232.9 | Unknown | 1521.7 | 1794.08 | -272.38 | Yes | N/A | N/A | 2024-07-10 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-08-05 | 57 | 41 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-10-01 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-18 | 18 | 14 | 2024-10-18 | 2024-10-18 | 1 | 1 | 58 | 42 | 76 | 56 | 134 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-10 | 125 | 90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.81 | -16.83 | Unknown | Unknown | Unknown | 15.02 | 0 | 583.97 | -1.81 | 585.78 | Yes | N/A | N/A | 2023-02-22 | 2023-02-22 | 1 | 1 | 2023-02-22 | 2023-03-01 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56, LA MESA | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 21896.84 | 2415.8 | Unknown | 3972.01 | 390.02 | 15119.01 | 7882 | 1305.4 | 21896.84 | -20591.44 | Yes | N/A | N/A | 2024-01-09 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-01-12 | 31 | 23 | 2024-01-12 | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-16 | 25 | 17 | 2024-01-12 | 2025-03-10 | 424 | 302 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-05-16 | 68 | 50 | 2025-05-16 | 2025-05-16 | 1 | 1 | 424 | 302 | 125 | 91 | 549 | 393 | Steps 2,3,5,6,7 | 490 | 350 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-24 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 7323.68 | 1970.8 | Unknown | 460.39 | Unknown | 4892.49 | 3981 | 553.5 | 7323.68 | -6770.18 | Yes | N/A | N/A | 2024-07-02 | 2024-07-17 | 16 | 12 | 2024-07-17 | 2024-07-24 | 8 | 6 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-14 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-28 | 46 | 33 | 2024-09-28 | 2024-09-28 | 1 | 0 | 38 | 28 | 55 | 39 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 10.54 | Unknown | Unknown | Unknown | Unknown | 10.54 | Unknown | 186.52 | 10.54 | 175.98 | Yes | N/A | N/A | 2024-08-28 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-08-28 | 16 | 12 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-18 | 9 | 7 | 2024-09-18 | 2024-09-18 | 1 | 1 | 14 | 10 | 26 | 20 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 469.39 | -9.09 | Unknown | Unknown | Unknown | 478.48 | Unknown | 1248.49 | 469.39 | 779.1 | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-10-15 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-18 | 35 | 25 | 2024-11-18 | 2024-11-18 | 1 | 1 | 183 | 131 | 36 | 26 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | 19216 | 19216 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-08 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-04-18 | IOU Designed & Installed | N/A | No | N/A | 1825.84 | 680.16 | Unknown | 88.1 | Unknown | 1057.58 | 3981 | 651.01 | 1825.84 | -1174.83 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-04-18 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-04-19 | 2 | 2 | 2023-04-19 | 2023-04-19 | 1 | 1 | 30 | 22 | 3 | 3 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -124 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-10-09 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 3485.37 | 2352.16 | Unknown | 751.06 | -2350 | 2732.15 | Unknown | 2350.37 | 3485.37 | -1135 | Yes | N/A | N/A | 2024-09-04 | 2024-10-21 | 48 | 34 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-03 | 19 | 15 | 2025-01-03 | 2025-01-03 | 1 | 1 | 48 | 34 | 20 | 16 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-31 | 1165 | 832 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-06 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16.68 | Unknown | Unknown | Unknown | Unknown | 16.68 | 3991 | 505.34 | 16.68 | 488.66 | Yes | N/A | N/A | 2021-12-06 | 2023-02-08 | 430 | 308 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-03-10 | 1 | 1 | 430 | 308 | 1 | 1 | 431 | 309 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 569.28 | -22.45 | Unknown | Unknown | 5.03 | 586.7 | 3981 | 1207.66 | 569.28 | 638.38 | Yes | N/A | N/A | 2025-01-14 | 2025-01-24 | 11 | 9 | 2025-01-24 | 2025-01-27 | 4 | 2 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-13 | 46 | 34 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-13 | 2025-03-28 | 16 | 12 | 2025-03-28 | 2025-03-28 | 1 | 1 | 57 | 43 | 21 | 15 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Poway | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | 550 | 393 | No | 2021-03-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-24 | 2021-03-24 | 2023-10-17 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 334 | 56811.72 | 644.21 | Unknown | Unknown | 3071.46 | 53096.05 | Unknown | 37821.09 | 56811.72 | -18990.63 | Yes | N/A | N/A | 2021-03-24 | 2023-01-31 | 679 | 485 | 2023-01-31 | 2023-02-07 | 8 | 6 | 2022-09-23 | 2023-02-06 | 49 | 35 | 2023-02-01 | 2023-10-12 | 254 | 182 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | 2023-10-17 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2023-09-25 | 1 | 1 | 728 | 520 | 263 | 189 | 991 | 709 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15.35 | 15.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 932.31 | 378.69 | Unknown | Unknown | Unknown | 553.62 | 11943 | 1363.71 | 932.31 | 431.4 | Yes | N/A | N/A | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2024-03-26 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-16 | 22 | 16 | 2024-04-16 | 2024-04-16 | 1 | 1 | 185 | 133 | 24 | 18 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 2357.1 | 435.72 | Unknown | 54.23 | 32.54 | 1834.61 | Unknown | 772.55 | 2357.1 | -1584.55 | Yes | N/A | N/A | 2023-03-23 | 2023-08-03 | 134 | 96 | 2023-08-03 | 2023-08-03 | 1 | 1 | 2023-08-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-09-28 | 190 | 136 | Unknown | 2023-10-16 | Unknown | Unknown | 2023-09-28 | 2023-11-02 | 36 | 26 | 2023-11-02 | 2023-11-02 | 1 | 1 | 324 | 232 | 38 | 28 | 362 | 260 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-17 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 1245.38 | 303.12 | Unknown | 106.59 | Unknown | 835.67 | Unknown | 1233.84 | 1245.38 | -11.54 | Yes | N/A | N/A | 2024-10-10 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-10-17 | 57 | 41 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-07 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-25 | 19 | 13 | 2024-11-25 | 2024-11-25 | 1 | 1 | 22 | 16 | 77 | 55 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | -569 | -408 | No | 2023-02-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-06-09 | IOU Designed & Installed | N/A | Yes | 74 | 1826.27 | 232.94 | Unknown | Unknown | 23.11 | 1570.22 | 3885 | 421.65 | 1826.27 | -1404.62 | Yes | N/A | N/A | 2023-02-13 | 2023-04-28 | 75 | 55 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-06-09 | 93 | 67 | Unknown | 2023-06-08 | Unknown | Unknown | 2023-06-09 | 2023-06-12 | 4 | 2 | 2023-06-12 | 2023-06-12 | 1 | 1 | 168 | 122 | 5 | 3 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | 4.07 | -3.59 | Unknown | Unknown | Unknown | 7.66 | Unknown | 1297.45 | 4.07 | 1293.38 | Yes | N/A | N/A | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | 2024-02-28 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-04-03 | 35 | 25 | 2024-04-03 | 2024-04-03 | 1 | 1 | 1 | 1 | 66 | 48 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-12 | -186 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | -16.66 | -12.09 | Unknown | Unknown | Unknown | -4.57 | Unknown | 464.78 | -16.66 | 481.44 | Yes | N/A | N/A | 2023-06-13 | 2023-03-30 | Unknown | Unknown | 2023-03-30 | 2023-06-20 | 83 | 59 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-08-16 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-09-08 | 24 | 18 | 2023-09-08 | 2023-09-08 | 1 | 1 | 58 | 42 | 108 | 78 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 39.4 | 39.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-24 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-28 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 1.24 | -17.1 | Unknown | Unknown | Unknown | 18.34 | Unknown | 820.17 | 1.24 | 818.93 | Yes | N/A | N/A | 2023-09-25 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-09-28 | 51 | 37 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-16 | 36 | 26 | 2023-11-16 | 2023-11-16 | 1 | 1 | 15 | 11 | 88 | 64 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 53 | 38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2023-02-21 | IOU Designed & Installed | N/A | No | N/A | 435.28 | 236.04 | Unknown | 38.18 | Unknown | 161.06 | 3981 | 666.88 | 435.28 | 231.6 | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-02-21 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-02-22 | 2 | 2 | 2023-02-22 | 2023-02-22 | 1 | 1 | 23 | 17 | 3 | 3 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-29 | 342 | 245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | -3.93 | -11.61 | Unknown | Unknown | Unknown | 7.68 | Unknown | 929.81 | -3.93 | 933.74 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-06-26 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-07-06 | 11 | 9 | 2023-07-06 | 2023-07-06 | 1 | 1 | 90 | 64 | 12 | 10 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 225 | 225 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-09-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 981.96 | Unknown | Unknown | Unknown | Unknown | 981.96 | 3981 | 1396.94 | 981.96 | 414.98 | Yes | N/A | N/A | 2023-07-27 | 2023-09-05 | 41 | 29 | 2023-09-05 | 2023-09-05 | 1 | 1 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-04-28 | Unknown | Unknown | 41 | 29 | 1 | 1 | 42 | 30 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | -425 | -304 | No | 2024-05-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2025-02-19 | IOU Designed & Installed | N/A | Yes | 151 | 984 | Unknown | Unknown | Unknown | 2.88 | 981.12 | 3981 | 1237.55 | 984 | 253.55 | Yes | N/A | N/A | 2024-05-23 | 2024-10-19 | 150 | 107 | 2024-10-19 | 2024-10-21 | 3 | 1 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2025-02-19 | 122 | 88 | Unknown | 2024-11-20 | Unknown | Unknown | 2025-02-19 | 2025-02-26 | 8 | 6 | 2025-02-26 | 2025-02-25 | Unknown | Unknown | 272 | 195 | 11 | 7 | 283 | 202 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 302.67 | -9.75 | Unknown | Unknown | Unknown | 312.42 | 3981 | 838.69 | 302.67 | 536.02 | Yes | N/A | N/A | 2023-11-27 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-05 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-01-18 | 45 | 33 | 2024-01-18 | 2024-01-18 | 1 | 1 | 9 | 7 | 46 | 34 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-16 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 29.88 | Unknown | Unknown | Unknown | Unknown | 29.88 | 3981 | 1542.14 | 29.88 | 1512.26 | Yes | N/A | N/A | 2024-08-14 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-08-14 | 2 | 2 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | 244 | 175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 67.71 | Unknown | Unknown | Unknown | -341.59 | 409.3 | Unknown | 289.87 | 67.71 | 222.16 | Yes | N/A | N/A | 2023-01-30 | 2024-01-30 | 366 | 262 | 2024-01-30 | 2024-05-30 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-14 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-10-31 | Unknown | Unknown | 366 | 262 | 125 | 91 | 491 | 353 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 1150 | 1150 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-22 | 17 | 12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-28 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | -12.15 | -9.84 | Unknown | Unknown | Unknown | -2.31 | Unknown | 496.37 | -12.15 | 508.52 | Yes | N/A | N/A | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | 2023-07-28 | 12 | 10 | 2023-07-28 | 2024-03-21 | 238 | 170 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-10-10 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2024-04-08 | 182 | 130 | 2024-04-08 | 2024-04-08 | 1 | 1 | 314 | 224 | 195 | 141 | 509 | 365 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 1736.79 | Unknown | Unknown | Unknown | 8.98 | 1727.81 | Unknown | 1270.87 | 1736.79 | -465.92 | Yes | N/A | N/A | 2024-09-06 | 2024-10-30 | 55 | 39 | 2024-10-30 | 2024-12-02 | 34 | 24 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-01-17 | 47 | 35 | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-17 | 2025-02-04 | 19 | 13 | 2025-02-04 | 2025-02-04 | 1 | 1 | 102 | 74 | 54 | 38 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 297 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-27 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 18310.97 | Unknown | Unknown | Unknown | 95.96 | 18215.01 | 53153 | 8876.38 | 18310.97 | -9434.59 | Yes | N/A | N/A | 2022-09-23 | 2023-05-24 | 244 | 174 | 2023-05-24 | 2024-01-30 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-24 | 2024-11-21 | 59 | 43 | 2024-11-21 | 2024-10-07 | Unknown | Unknown | 244 | 174 | 311 | 223 | 555 | 397 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -31 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 490.52 | -12.13 | Unknown | Unknown | 10.08 | 492.57 | 3981 | 651.15 | 490.52 | 160.63 | Yes | N/A | N/A | 2023-06-27 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-07-13 | 105 | 75 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2024-01-31 | 203 | 145 | Unknown | 2024-01-23 | Unknown | Unknown | 2024-01-31 | 2024-02-14 | 15 | 11 | 2024-02-14 | 2024-02-14 | 1 | 1 | 203 | 145 | 121 | 87 | 324 | 232 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 76.46 | -9.12 | Unknown | Unknown | -647.93 | 733.51 | Unknown | 661.64 | 76.46 | 585.18 | Yes | N/A | N/A | 2023-07-07 | 2023-07-25 | 19 | 13 | 2023-07-25 | 2023-07-27 | 3 | 3 | 2023-07-27 | 2023-10-25 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-01-09 | 65 | 47 | Unknown | 2024-01-05 | Unknown | Unknown | 2024-01-09 | 2024-03-14 | 66 | 48 | 2024-03-14 | 2024-03-14 | 1 | 1 | 175 | 125 | 70 | 52 | 245 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-28 | 328 | 235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-18 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4845.97 | 728.65 | Unknown | 761.55 | Unknown | 3355.77 | 3981 | 625.26 | 4845.97 | -4220.71 | Yes | N/A | N/A | 2022-08-18 | 2023-12-01 | 471 | 337 | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-06-20 | Unknown | Unknown | 471 | 337 | 1 | 1 | 472 | 338 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 32.17 | Unknown | Unknown | Unknown | Unknown | 32.17 | Unknown | 1599.15 | 32.17 | 1566.98 | Yes | N/A | N/A | 2024-09-06 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2025-03-03 | 187 | 133 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-01 | 26 | 18 | 2024-10-01 | 2024-10-01 | 1 | 1 | 1 | 1 | 214 | 152 | 215 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 9.35 | Unknown | Unknown | Unknown | Unknown | 9.35 | 3981 | 190.44 | 9.35 | 181.09 | Yes | N/A | N/A | 2024-09-09 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2024-10-07 | 78 | 56 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-08 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-12-06 | 60 | 44 | 2024-12-06 | 2024-12-06 | 1 | 1 | 6 | 4 | 139 | 101 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-21 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-28 | 2023-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.18 | -6.52 | Unknown | Unknown | Unknown | 4.34 | 3981 | 666.85 | -2.18 | 669.03 | Yes | N/A | N/A | 2022-07-28 | 2023-02-21 | 209 | 149 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | 2023-06-13 | 2023-06-13 | 1 | 1 | 209 | 149 | 1 | 1 | 210 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -401 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | 14425.05 | 3649.3 | Unknown | Unknown | 12.04 | 10763.71 | 3981 | 1020.99 | 14425.05 | -13404.06 | Yes | N/A | N/A | 2025-04-07 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-04-08 | 19 | 13 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-06-17 | 72 | 52 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-17 | 2025-06-24 | 8 | 6 | 2025-06-24 | 2025-06-24 | 1 | 1 | 72 | 52 | 28 | 20 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 942 | 673 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-09 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 6237.25 | Unknown | Unknown | Unknown | 362.08 | 5875.17 | 2875.23 | 481.12 | 6237.25 | -5756.13 | Yes | N/A | N/A | 2023-10-02 | 2023-11-09 | 39 | 29 | 2023-11-09 | 2023-11-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-10-15 | 2023-10-24 | 10 | 7 | 2023-11-17 | 2024-10-17 | 336 | 240 | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-24 | 2025-04-01 | 160 | 114 | 2025-04-01 | 2025-04-01 | 1 | 1 | 375 | 269 | 180 | 129 | 555 | 398 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | EN 1167-D7 | ENCINITAS | 1296 | 1296 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-01-08 | 519 | 372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2024-02-06 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 8009.01 | 584.83 | Unknown | Unknown | 1021.52 | 6402.66 | 0 | 12565.28 | 8009.01 | 4556.27 | Yes | N/A | N/A | 2023-10-09 | 2023-07-05 | Unknown | Unknown | 2023-07-05 | 2024-10-17 | 471 | 337 | 2024-03-11 | 2024-10-07 | 40 | 28 | 2024-08-30 | 2024-10-24 | 43 | 31 | 2024-12-12 | Unknown | Unknown | Unknown | 2024-12-12 | 2025-05-07 | 147 | 105 | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | 2025-06-10 | 1 | 1 | 40 | 28 | 663 | 475 | 703 | 503 | Steps 2,3,5,6,7 | 258 | 184 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2024-07-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 7642.96 | 790.59 | Unknown | Unknown | -14184.42 | 21036.79 | Unknown | 16714.29 | 7642.96 | 9071.33 | Yes | N/A | N/A | 2023-06-01 | 2024-01-26 | 240 | 172 | 2024-01-26 | 2024-07-19 | 176 | 126 | 2024-02-21 | 2024-07-15 | 141 | 101 | 2024-02-27 | 2024-07-09 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-09-05 | 42 | 30 | 2024-09-05 | 2024-09-05 | 1 | 1 | 381 | 273 | 240 | 172 | 621 | 445 | Steps 2,3,5,6,7 | 288 | 206 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | -151 | -110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 515.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-04-23 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-07 | 25 | 17 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 132 | 94 | 132 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-05-16 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 19099.8 | Unknown | Unknown | Unknown | -9695 | 28794.8 | 0 | 9695.27 | 19099.8 | -9404.53 | Yes | N/A | N/A | 2023-04-06 | 2023-05-05 | 30 | 22 | 2023-05-05 | 2024-07-16 | 439 | 313 | 2023-08-04 | 2024-02-14 | 20 | 12 | 2023-07-26 | 2024-08-05 | 70 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-16 | 36 | 26 | 2024-10-16 | 2024-10-16 | 1 | 1 | 50 | 34 | 546 | 392 | 596 | 426 | Steps 2,3,5,6,7 | 550 | 392 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 1007.1 | 1007.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-07-12 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1765.27 | Unknown | Unknown | Unknown | 4.88 | 1760.39 | 3981 | 999.53 | 1765.27 | -765.74 | Yes | N/A | N/A | 2024-07-29 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-08-09 | 23 | 17 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-14 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-02 | -281 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2024-03-18 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 14176.14 | 38.34 | Unknown | Unknown | 0.61 | 14137.19 | 64188 | 1692 | 14176.14 | -12484.14 | Yes | N/A | N/A | 2023-05-18 | 2023-08-02 | 77 | 55 | 2023-08-02 | 2024-12-06 | 493 | 353 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-02-07 | 64 | 46 | Unknown | 2024-12-31 | Unknown | Unknown | 2025-01-27 | 2025-02-24 | 29 | 21 | 2025-02-24 | 2025-02-24 | 1 | 1 | 141 | 101 | 523 | 375 | 664 | 476 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1134.88 | -19.82 | Unknown | Unknown | Unknown | 1154.7 | 3981 | 3813.61 | 1134.88 | 2678.73 | Yes | N/A | N/A | 2024-08-06 | 2024-08-13 | 8 | 6 | 2024-08-13 | 2024-08-26 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-14 | 9 | 7 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-09-24 | 1 | 1 | 8 | 6 | 24 | 18 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | Carlsbad | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2024-08-30 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 132167.76 | 29288.38 | Unknown | Unknown | -50154.59 | 153033.97 | 0 | 56439.26 | 132167.76 | -75728.5 | Yes | N/A | N/A | 2023-10-26 | 2024-04-09 | 167 | 119 | 2024-04-09 | 2024-08-21 | 135 | 97 | 2024-06-07 | 2024-07-05 | 29 | 21 | 2024-06-26 | 2025-02-19 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2025-04-01 | 215 | 153 | 2025-04-01 | 2025-04-01 | 1 | 1 | 196 | 140 | 479 | 343 | 675 | 483 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -606 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-08 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 345.24 | Unknown | Unknown | Unknown | 4.57 | 340.67 | 3981 | 1098.48 | 345.24 | 753.24 | Yes | N/A | N/A | 2024-08-01 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-08-22 | 49 | 35 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-12 | 22 | 16 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-12 | 2024-10-21 | 40 | 28 | 2024-10-21 | 2024-10-21 | 1 | 1 | 22 | 16 | 90 | 64 | 112 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-16 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 684.26 | -12.92 | Unknown | Unknown | Unknown | 697.18 | Unknown | 1335.04 | 684.26 | 650.78 | Yes | N/A | N/A | 2024-05-15 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-05-16 | 38 | 28 | 2024-05-16 | Unknown | Unknown | Unknown | 2024-05-16 | 2024-06-21 | 37 | 27 | 2024-05-16 | 2024-07-22 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-06 | 16 | 12 | 2024-08-06 | 2024-08-06 | 1 | 1 | 68 | 48 | 92 | 68 | 160 | 116 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-17 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 20.85 | Unknown | Unknown | Unknown | Unknown | 20.85 | 3981 | 1846.19 | 20.85 | 1825.34 | Yes | N/A | N/A | 2025-01-10 | 2025-01-15 | 6 | 4 | 2025-01-15 | 2025-01-17 | 3 | 3 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-02-18 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-05 | 16 | 12 | 2025-03-05 | 2025-03-03 | Unknown | Unknown | 39 | 27 | 19 | 15 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 126.05 | 126.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -443 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-14 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | 2537.75 | 303.12 | Unknown | 314.55 | Unknown | 1920.08 | 3981 | 1330.05 | 2537.75 | -1207.7 | Yes | N/A | N/A | 2024-10-04 | 2024-12-11 | 69 | 49 | 2024-12-11 | 2025-01-17 | 38 | 28 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-04-28 | 102 | 72 | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-28 | 2025-05-15 | 18 | 14 | 2025-05-15 | 2025-05-15 | 1 | 1 | 171 | 121 | 57 | 43 | 228 | 164 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 32.39 | Unknown | Unknown | Unknown | Unknown | 32.39 | 3981 | 1353.12 | 32.39 | 1320.73 | Yes | N/A | N/A | 2025-06-03 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-03 | 7 | 5 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-18 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-26 | 9 | 7 | 2025-06-26 | 2025-06-26 | 1 | 1 | 16 | 12 | 17 | 13 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-17 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-09-08 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 4.72 | -4.15 | Unknown | Unknown | Unknown | 8.87 | 3981 | 618.09 | 4.72 | 613.37 | Yes | N/A | N/A | 2023-08-31 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | 2023-09-08 | 16 | 12 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2024-04-08 | 214 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-19 | 12 | 10 | 2024-04-19 | 2024-06-04 | 47 | 33 | 214 | 152 | 75 | 55 | 289 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 32.45 | 32.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -631 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-09-20 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 2623.19 | 530.19 | Unknown | 13.17 | 31.11 | 2048.72 | 3981 | 2225.14 | 2623.19 | -398.05 | Yes | N/A | N/A | 2024-08-09 | 2024-08-20 | 12 | 8 | 2024-08-20 | 2024-09-20 | 32 | 24 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-09-30 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-12-19 | 81 | 59 | 2024-12-19 | 2024-10-04 | Unknown | Unknown | 23 | 15 | 113 | 83 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 89 | 89 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -65 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 3985.45 | 509.4 | Unknown | 373.91 | 91.77 | 3010.37 | 3981 | 1255.81 | 3985.45 | -2729.64 | Yes | N/A | N/A | 2023-03-30 | 2023-09-21 | 176 | 126 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2024-10-23 | 398 | 284 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-23 | 2024-11-01 | 10 | 8 | 2024-11-01 | 2024-11-01 | 1 | 1 | 574 | 410 | 11 | 9 | 585 | 419 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 614.9 | -11.7 | Unknown | Unknown | Unknown | 626.6 | 3981 | 2057.68 | 614.9 | 1442.78 | Yes | N/A | N/A | 2024-12-03 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-03 | 20 | 14 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-27 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-10 | 15 | 11 | 2025-01-10 | 2025-01-10 | 1 | 1 | 25 | 19 | 36 | 26 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 2025.22 | -13.59 | Unknown | Unknown | 77.63 | 1961.18 | Unknown | 1112.37 | 2025.22 | -912.85 | Yes | N/A | N/A | 2024-01-24 | 2024-03-21 | 58 | 42 | 2024-03-21 | 2024-03-25 | 5 | 3 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-07-11 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-22 | 12 | 8 | 2024-07-22 | 2024-07-22 | 1 | 1 | 167 | 121 | 18 | 12 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-23 | 704 | 503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2233.47 | -14.9 | Unknown | Unknown | 38.13 | 2210.24 | 10791 | 461.83 | 2233.47 | -1771.64 | Yes | N/A | N/A | 2022-11-07 | 2023-06-19 | 225 | 161 | 2023-06-19 | 2023-12-26 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-06-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-27 | Unknown | Unknown | 225 | 161 | 199 | 143 | 424 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 126.75 | 126.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -528 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 482.71 | -25.8 | Unknown | Unknown | -801 | 1309.51 | 4148.48 | 1550.15 | 482.71 | 1067.44 | Yes | N/A | N/A | 2025-03-04 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2025-03-19 | 132 | 94 | 2025-03-19 | 2025-04-09 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 22 | 16 | 133 | 95 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | 44 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 971.97 | Unknown | Unknown | Unknown | 95.38 | 876.59 | 0 | 731.65 | 971.97 | -240.32 | Yes | N/A | N/A | 2024-05-06 | 2024-05-07 | 2 | 2 | 2024-05-07 | 2024-05-13 | 7 | 5 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-06-12 | 396 | 284 | Unknown | 2025-04-18 | Unknown | Unknown | 2025-06-12 | 2025-06-13 | 2 | 2 | 2025-06-13 | 2025-06-13 | 1 | 1 | 398 | 286 | 10 | 8 | 408 | 294 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -122 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 10341.26 | 2051.34 | Unknown | Unknown | 19.25 | 8270.67 | 3981 | Not available | 10341.26 | Unknown | Yes | N/A | N/A | 2024-01-24 | 2023-04-24 | Unknown | Unknown | 2023-04-24 | 2024-05-07 | 380 | 272 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-03 | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-06-14 | 37 | 27 | 2024-06-14 | 2024-06-03 | Unknown | Unknown | 0 | 0 | 417 | 299 | 417 | 299 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-10 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | -5.48 | -4.45 | Unknown | Unknown | Unknown | -1.03 | 3981 | 875.22 | -5.48 | 880.7 | Yes | N/A | N/A | 2024-04-08 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-12 | 44 | 32 | 2024-04-12 | 2024-04-17 | 6 | 4 | 2024-04-16 | 2024-04-30 | 15 | 11 | 2024-04-17 | 2024-04-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-13 | 27 | 19 | 2024-05-13 | 2024-05-13 | 1 | 1 | 7 | 5 | 87 | 63 | 94 | 68 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | -568 | -406 | No | 2024-10-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-12-27 | 2025-01-22 | IOU Designed & Installed | N/A | Yes | 8 | 1767.61 | -33.42 | Unknown | Unknown | 0.32 | 1800.71 | 3981 | 2072.76 | 1767.61 | 305.15 | Yes | N/A | N/A | 2024-10-23 | 2024-10-31 | 9 | 7 | 2024-10-31 | 2024-12-27 | 58 | 42 | 2024-12-27 | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-14 | 19 | 13 | 2024-12-27 | 2025-01-22 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-28 | 38 | 28 | 2025-02-28 | 2025-02-28 | 1 | 1 | 36 | 26 | 116 | 84 | 152 | 110 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 154 | 154 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | 137 | 98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 41.63 | Unknown | Unknown | Unknown | Unknown | 41.63 | 7962 | 794.97 | 41.63 | 753.34 | Yes | N/A | N/A | 2023-11-21 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2023-11-21 | 2 | 2 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-10-28 | 343 | 245 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-01 | 5 | 5 | 2024-11-01 | 2024-11-05 | 5 | 3 | 343 | 245 | 12 | 10 | 355 | 255 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-20 | 128 | 93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2023-04-19 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 1662.91 | 230.61 | Unknown | 117.92 | -1010 | 2324.38 | 3981 | 3364.05 | 1662.91 | 1701.14 | Yes | N/A | N/A | 2022-12-08 | 2023-04-18 | 132 | 94 | 2023-04-18 | 2023-06-07 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-09-21 | 107 | 77 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-10-23 | 2023-11-06 | 15 | 11 | 2023-11-06 | 2023-10-26 | Unknown | Unknown | 239 | 171 | 66 | 48 | 305 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-16 | -577 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -918.07 | 391.96 | Unknown | 50.09 | -1633 | 272.88 | Unknown | 1632.6 | -918.07 | 2550.67 | Yes | N/A | N/A | 2024-11-19 | 2024-12-04 | 16 | 12 | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2024-12-16 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 116.05 | 116.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -439 | -314 | No | 2022-12-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-05 | 2022-12-20 | 2023-07-19 | IOU Designed & Installed | N/A | Yes | 133 | 577.33 | -7.81 | Unknown | Unknown | 27.44 | 557.7 | 3981 | 897.84 | 577.33 | 320.51 | Yes | N/A | N/A | 2022-12-05 | 2023-04-17 | 134 | 96 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-22 | 2023-07-19 | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | 2023-07-19 | 1 | 1 | 134 | 96 | 2 | 2 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 14.31 | Unknown | Unknown | Unknown | Unknown | 14.31 | 3981 | 1631.84 | 14.31 | 1617.53 | Yes | N/A | N/A | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-02-14 | 25 | 19 | 2025-02-14 | 2025-02-14 | 1 | 1 | 38 | 28 | 27 | 21 | 65 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 43 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 506.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-13 | 3 | 3 | 2025-02-13 | 2025-03-03 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-03 | 19 | 13 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 3 | 3 | 39 | 27 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 1428.19 | 345.62 | Unknown | 80.58 | Unknown | 1001.99 | 3981 | 1601.07 | 1428.19 | 172.88 | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-17 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-25 | 9 | 7 | 2025-03-25 | 2025-03-25 | 1 | 1 | 19 | 13 | 11 | 9 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 226.39 | -19.71 | Unknown | Unknown | Unknown | 246.1 | Unknown | 955.19 | 226.39 | 728.8 | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-08-02 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 588.61 | Unknown | Unknown | Unknown | Unknown | 588.61 | 3981 | 1744.13 | 588.61 | 1155.52 | Yes | N/A | N/A | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | Unknown | Unknown | Unknown | 2025-02-03 | 2025-05-21 | 108 | 78 | 2025-02-03 | 2025-06-09 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-16 | 8 | 6 | 2025-06-16 | 2025-06-16 | 1 | 1 | 127 | 91 | 121 | 87 | 248 | 178 | Steps 2,3,5,6,7 | 107 | 77 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -135 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 694 | -18.25 | Unknown | Unknown | Unknown | 712.25 | 3981 | 909.18 | 694 | 215.18 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-11 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-18 | 69 | 49 | 2024-06-18 | 2024-06-18 | 1 | 1 | 38 | 28 | 71 | 51 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 243.05 | 243.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2246.21 | -30.92 | Unknown | Unknown | 5.35 | 2271.78 | 3981 | 1171.09 | 2246.21 | -1075.12 | Yes | N/A | N/A | 2024-03-08 | 2024-08-12 | 158 | 112 | 2024-08-12 | 2024-08-20 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-13 | 33 | 25 | 2024-08-20 | 2024-10-31 | 73 | 53 | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-10-31 | Unknown | Unknown | 231 | 165 | 42 | 32 | 273 | 197 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | WARNER SPRINGS | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 3505 | 966.72 | Unknown | 507.57 | Unknown | 2030.71 | 3981 | 917.58 | 3505 | -2587.42 | Yes | N/A | N/A | 2024-05-24 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-05-24 | 38 | 28 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-08-12 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-15 | 4 | 4 | 2024-08-15 | 2024-08-15 | 1 | 1 | 76 | 54 | 43 | 33 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -205 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -17.44 | -8.4 | Unknown | Unknown | Unknown | -9.04 | 0 | 239.23 | -17.44 | 256.67 | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-08-02 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-06-14 | 1 | 1 | 0 | 0 | 149 | 107 | 149 | 107 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -358 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 491.92 | -9.89 | Unknown | Unknown | Unknown | 501.81 | 3981 | 1037.07 | 491.92 | 545.15 | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-12 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-16 | 5 | 5 | 2025-05-16 | 2025-05-16 | 1 | 1 | 5 | 3 | 7 | 7 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -702 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-24 | Unknown | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 50.68 | Unknown | Unknown | Unknown | Unknown | 50.68 | 3981 | 1494.9 | 50.68 | 1444.22 | Yes | N/A | N/A | 2024-08-24 | 2024-08-24 | 1 | 0 | 2024-08-24 | 2024-08-24 | 1 | 0 | 2024-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-24 | 2024-08-27 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-12 | 17 | 13 | 2024-09-12 | 2024-09-12 | 1 | 1 | 5 | 2 | 19 | 14 | 24 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 472.05 | 472.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -492 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-09-05 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 235.39 | 90.63 | Unknown | Unknown | Unknown | 144.76 | 3981 | 1077.86 | 235.39 | 842.47 | Yes | N/A | N/A | 2023-08-15 | 2023-09-05 | 22 | 16 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-09-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-05 | 9 | 7 | 2023-10-05 | 2023-10-05 | 1 | 1 | 44 | 32 | 10 | 8 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | 64 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 37.84 | Unknown | Unknown | Unknown | Unknown | 37.84 | 0 | 893.07 | 37.84 | 855.23 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-20 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1942.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-03-13 | 35 | 25 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-04-23 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-15 | 23 | 17 | 2025-05-15 | 2025-05-15 | 1 | 1 | 42 | 30 | 59 | 43 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1032.43 | Unknown | Unknown | Unknown | Unknown | 1032.43 | 3981 | 1316.94 | 1032.43 | 284.51 | Yes | N/A | N/A | 2024-11-04 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2025-03-03 | 125 | 89 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-02-20 | 107 | 77 | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-20 | 2025-03-18 | 27 | 19 | 2025-03-18 | 2025-03-18 | 1 | 1 | 107 | 77 | 153 | 109 | 260 | 186 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-12-16 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 736.28 | -14.79 | Unknown | Unknown | Unknown | 751.07 | 3981 | 2062.47 | 736.28 | 1326.19 | Yes | N/A | N/A | 2024-10-22 | 2024-11-20 | 30 | 22 | 2024-11-20 | 2024-12-16 | 27 | 19 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-04-29 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-12 | 14 | 10 | 2025-05-12 | 2025-05-09 | Unknown | Unknown | 165 | 119 | 41 | 29 | 206 | 148 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.01 | 48.01 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -430 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-24 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 2.53 | -3.07 | Unknown | Unknown | Unknown | 5.6 | 3981 | 942.04 | 2.53 | 939.51 | Yes | N/A | N/A | 2023-12-26 | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2024-01-24 | 113 | 81 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-28 | 23 | 17 | 2024-02-28 | 2024-02-26 | Unknown | Unknown | 14 | 10 | 136 | 98 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 90.89 | -1.25 | Unknown | Unknown | Unknown | 92.14 | 3981 | 1549.07 | 90.89 | 1458.18 | Yes | N/A | N/A | 2024-11-05 | 2024-11-07 | 3 | 3 | 2024-11-07 | 2024-11-14 | 8 | 6 | 2024-11-14 | 2024-12-02 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-14 | 1 | 1 | 22 | 16 | 9 | 7 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-12 | 86 | 63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | 2025.55 | -16.11 | Unknown | Unknown | 28.99 | 2012.67 | 3981 | 1909.89 | 2025.55 | -115.66 | Yes | N/A | N/A | 2023-01-24 | 2023-03-07 | 43 | 31 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-07-07 | 123 | 89 | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-07 | 2023-07-07 | 1 | 1 | 2023-07-07 | 2023-07-07 | 1 | 1 | 166 | 120 | 2 | 2 | 168 | 122 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1239 | 886 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 135992.53 | 20146.69 | Unknown | Unknown | 21332.39 | 94513.45 | 0 | 124088.11 | 135992.53 | -11904.42 | Yes | N/A | N/A | 2024-01-05 | 2024-06-05 | 153 | 109 | 2024-06-05 | 2024-09-04 | 92 | 66 | 2024-06-25 | 2025-01-28 | 43 | 33 | 2024-07-11 | 2024-09-06 | 13 | 11 | 2024-09-10 | Unknown | Unknown | Unknown | 2024-09-10 | 2025-05-21 | 254 | 182 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-24 | 2025-06-24 | 1 | 1 | 196 | 142 | 360 | 260 | 556 | 402 | Steps 2,3,5,6,7 | 272 | 194 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -319 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1648.36 | 518.85 | Unknown | 72.09 | Unknown | 1057.42 | 3981 | 885.09 | 1648.36 | -763.27 | Yes | N/A | N/A | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-02-28 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2024-03-21 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 6934.8 | 256.6 | Unknown | Unknown | Unknown | 6678.2 | Unknown | 826.35 | 6934.8 | -6108.45 | Yes | N/A | N/A | 2022-08-11 | 2024-03-18 | 586 | 418 | 2024-03-18 | 2024-06-04 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-21 | 15 | 11 | 2024-06-21 | 2024-06-21 | 1 | 1 | 586 | 418 | 95 | 69 | 681 | 487 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-28 | -133 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-04 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 660.99 | -10.86 | Unknown | Unknown | 31.04 | 640.81 | 3981 | 694.31 | 660.99 | 33.32 | Yes | N/A | N/A | 2023-01-25 | 2023-02-04 | 11 | 8 | 2023-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-04 | 2024-05-31 | 483 | 345 | Unknown | 2024-05-17 | Unknown | Unknown | 2024-05-31 | 2024-06-17 | 18 | 12 | 2024-06-17 | 2024-06-17 | 1 | 1 | 494 | 353 | 19 | 13 | 513 | 366 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | 354.05 | 354.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 8.39 | -10.61 | Unknown | Unknown | Unknown | 19 | 3981 | 861.77 | 8.39 | 853.38 | Yes | N/A | N/A | 2023-12-08 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-12-08 | 44 | 32 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-12 | 24 | 18 | 2024-01-12 | 2024-01-12 | 1 | 1 | 13 | 9 | 69 | 51 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 213 | 152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8833.12 | 88.51 | Unknown | Unknown | -14571.7 | 5650.07 | Unknown | 17066.63 | -8833.12 | 25899.75 | Yes | N/A | N/A | 2023-11-22 | 2024-01-04 | 44 | 32 | 2024-01-04 | 2024-05-20 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-12 | 16 | 12 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-09-23 | 1 | 1 | 44 | 32 | 155 | 111 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | 253 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 47568.83 | 13509.96 | Unknown | Unknown | 72.04 | 33986.83 | 44286 | 23920.05 | 47568.83 | -23648.78 | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | 2024-03-08 | 148 | 106 | 2023-10-24 | 2023-12-18 | 56 | 40 | 2024-03-05 | 2025-02-05 | 9 | 7 | 2024-03-08 | 1999-12-31 | Unknown | Unknown | 2024-12-19 | 2025-02-07 | 51 | 37 | 2025-02-21 | 2025-03-12 | 20 | 14 | 2025-03-12 | 2025-03-03 | Unknown | Unknown | 57 | 41 | 228 | 164 | 285 | 205 | Steps 2,3,5,6,7 | 470 | 336 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-08 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-21 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 2061.49 | 582.92 | Unknown | 235.84 | Unknown | 1242.73 | 3981 | 828.14 | 2061.49 | -1233.35 | Yes | N/A | N/A | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2024-01-22 | 186 | 132 | Unknown | 2024-01-05 | Unknown | Unknown | 2024-01-22 | 2024-01-25 | 4 | 4 | 2024-01-25 | 2024-01-25 | 1 | 1 | 187 | 133 | 6 | 6 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 483.61 | Unknown | Unknown | Unknown | Unknown | 483.61 | 3981 | 803.04 | 483.61 | 319.43 | Yes | N/A | N/A | 2025-04-23 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-05-07 | 24 | 18 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 0 | 0 | 25 | 19 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 22.31 | Unknown | Unknown | Unknown | Unknown | 22.31 | 3981 | 1575.58 | 22.31 | 1553.27 | Yes | N/A | N/A | 2024-09-23 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-23 | 4 | 2 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-11-19 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-13 | 25 | 19 | 2024-12-13 | 2024-12-13 | 1 | 1 | 58 | 42 | 30 | 22 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 398.68 | -5.65 | Unknown | Unknown | 8.57 | 395.76 | Unknown | 498.48 | 398.68 | 99.8 | Yes | N/A | N/A | 2024-03-18 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-03-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-05-20 | 60 | 42 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2 | 2 | 62 | 44 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2024-02-06 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | -31420.07 | 2627.63 | Unknown | Unknown | -38064 | 4016.3 | 0 | 38064.31 | -31420.07 | 69484.38 | Yes | N/A | N/A | 2023-07-18 | 2024-04-25 | 283 | 203 | 2024-04-25 | 2025-03-28 | 338 | 242 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2025-04-22 | 86 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-13 | 2025-06-10 | 29 | 21 | 2025-06-10 | 2025-06-10 | 1 | 1 | 283 | 203 | 454 | 322 | 737 | 525 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | SAN DIEGO | POWAY, SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | 311 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-13 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 95.79 | Unknown | Unknown | Unknown | -321.67 | 417.46 | 0 | 345.13 | 95.79 | 249.34 | Yes | N/A | N/A | 2023-02-09 | 2023-02-10 | 2 | 2 | 2023-02-10 | 2023-06-06 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | 2023-06-09 | 117 | 85 | 2023-06-06 | 2024-12-12 | 556 | 398 | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-27 | 2025-01-07 | 12 | 8 | 2025-01-07 | 2025-01-06 | Unknown | Unknown | 558 | 400 | 246 | 176 | 804 | 576 | Steps 2,3,5,6,7 | 3 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | -360 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3120.21 | -58.87 | Unknown | Unknown | Unknown | 3179.08 | 3981 | 684.36 | 3120.21 | -2435.85 | Yes | N/A | N/A | 2023-10-18 | 2024-04-17 | 183 | 131 | 2024-04-17 | 2024-05-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-04 | 17 | 13 | 2024-05-16 | 2024-07-02 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-02 | Unknown | Unknown | 231 | 165 | 47 | 35 | 278 | 200 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-26 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 1022.09 | -18.85 | Unknown | Unknown | Unknown | 1040.94 | Unknown | 1666.5 | 1022.09 | 644.41 | Yes | N/A | N/A | 2024-07-05 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-07-05 | 9 | 7 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-08-27 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-02 | 37 | 27 | 2024-10-02 | 2024-10-02 | 1 | 1 | 54 | 38 | 47 | 35 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -52 | -39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 1746.36 | 553.63 | Unknown | 172.3 | Unknown | 1020.43 | Unknown | 270.36 | 1746.36 | -1476 | Yes | N/A | N/A | 2023-08-02 | 2023-08-04 | 3 | 3 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-01-04 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-09 | 6 | 4 | 2024-01-09 | 2024-01-09 | 1 | 1 | 157 | 113 | 8 | 6 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -493 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-10-20 | IOU Designed & Installed | N/A | No | N/A | 28765.88 | 3593.66 | Unknown | 198.56 | 156.86 | 24816.8 | Unknown | 1043.26 | 28765.88 | -27722.62 | Yes | N/A | N/A | 2024-05-07 | 2024-05-24 | 18 | 14 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-24 | 27 | 19 | 2024-05-29 | 2024-10-20 | 145 | 103 | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-20 | 2024-10-23 | 4 | 3 | 2024-10-23 | 2024-10-23 | 1 | 1 | 163 | 117 | 33 | 24 | 196 | 141 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -627 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 224.04 | -21.2 | Unknown | Unknown | Unknown | 245.24 | Unknown | 778.7 | 224.04 | 554.66 | Yes | N/A | N/A | 2024-04-01 | 2024-04-05 | 5 | 5 | 2024-04-05 | 2024-05-29 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-29 | 23 | 17 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-06-10 | 1 | 1 | 5 | 5 | 79 | 57 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-11 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 2173.16 | 809.28 | Unknown | Unknown | -479 | 1842.88 | 3981 | 2659.3 | 2173.16 | 486.14 | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | 2024-06-07 | 2 | 2 | 2024-06-07 | 2024-07-26 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-30 | 36 | 26 | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-30 | 2024-09-05 | 7 | 5 | 2024-09-05 | 2024-09-03 | Unknown | Unknown | 87 | 63 | 9 | 7 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -453 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 1206.76 | 253.74 | Unknown | Unknown | Unknown | 953.02 | 3981 | 1122.46 | 1206.76 | -84.3 | Yes | N/A | N/A | 2024-09-03 | 2024-09-19 | 17 | 13 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-22 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-10-24 | 3 | 3 | 2024-10-24 | 2024-10-24 | 1 | 1 | 51 | 37 | 5 | 5 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-09 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1058.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-05-05 | 1 | 1 | 2025-05-05 | 2025-05-09 | 5 | 5 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-27 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-09 | 14 | 10 | 2025-06-09 | 2025-06-09 | 1 | 1 | 20 | 14 | 20 | 16 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-13 | -447 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 773.4 | 482.64 | Unknown | 26.46 | Unknown | 264.3 | Unknown | 515.81 | 773.4 | -257.59 | Yes | N/A | N/A | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-12 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-05-23 | 164 | 118 | 2024-05-23 | 2024-05-23 | 1 | 1 | 3 | 3 | 166 | 120 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-03-12 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 33241.86 | 8880.99 | Unknown | Unknown | 309.51 | 24051.36 | 3981 | 1808.32 | 33241.86 | -31433.54 | Yes | N/A | N/A | 2025-01-02 | 2025-03-03 | 61 | 43 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-28 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-14 | 18 | 12 | 2025-04-14 | 2025-04-14 | 1 | 1 | 78 | 56 | 19 | 13 | 97 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 478.3 | Unknown | Unknown | Unknown | 3.19 | 475.11 | Unknown | 1320.54 | 478.3 | 842.24 | Yes | N/A | N/A | 2024-12-04 | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2025-01-10 | 50 | 36 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-06 | 28 | 20 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-06 | 2025-03-05 | 28 | 20 | 2025-03-05 | 2025-03-05 | 1 | 1 | 28 | 20 | 79 | 57 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | -211 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-15 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | 10753.63 | 2866.67 | Unknown | Unknown | -8431 | 16317.96 | Unknown | 8431.4 | 10753.63 | -2322.23 | Yes | N/A | N/A | 2023-05-04 | 2023-11-06 | 187 | 133 | 2023-11-06 | 2024-02-13 | 100 | 72 | 2023-08-16 | 2024-02-12 | 181 | 129 | 2023-09-07 | 2024-02-14 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-07 | 21 | 15 | 2024-03-07 | 2024-03-07 | 1 | 1 | 368 | 262 | 133 | 97 | 501 | 359 | Steps 2,3,5,6,7 | 339 | 241 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 187 | 134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 1099.98 | 412 | Unknown | Unknown | Unknown | 687.98 | 3981 | 848.75 | 1099.98 | -251.23 | Yes | N/A | N/A | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-11-17 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-12-04 | 18 | 12 | 2023-12-04 | 2023-12-04 | 1 | 1 | 40 | 30 | 20 | 14 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | -1329 | -950 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-25 | 2023-06-25 | 2023-09-12 | IOU Designed & Installed | N/A | No | N/A | 591.31 | 362.52 | Unknown | Unknown | Unknown | 228.79 | 23991 | 536.75 | 591.31 | -54.56 | Yes | N/A | N/A | 2023-06-25 | 2023-06-28 | 4 | 3 | 2023-06-28 | 2023-06-29 | 2 | 2 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-09-12 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2023-09-15 | 4 | 4 | 2023-09-15 | 2023-09-15 | 1 | 1 | 81 | 58 | 7 | 7 | 88 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-14 | 700 | 501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 4650.99 | Unknown | Unknown | Unknown | 207.1 | 4443.89 | 15018 | 8294.16 | 4650.99 | 3643.17 | Yes | N/A | N/A | 2023-10-13 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2024-02-16 | 171 | 123 | 2024-05-13 | 2024-06-27 | 19 | 15 | 2024-02-09 | 2024-06-27 | 114 | 82 | 2024-02-16 | 2025-02-11 | 362 | 258 | 2024-02-29 | 2025-02-21 | 359 | 257 | 2025-02-26 | 2025-03-17 | 20 | 14 | 2025-03-17 | 2025-03-14 | Unknown | Unknown | 381 | 273 | 664 | 476 | 1045 | 749 | Steps 2,3,5,6,7 | 619 | 441 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 603.33 | -16.97 | Unknown | Unknown | Unknown | 620.3 | Unknown | 872.08 | 603.33 | 268.75 | Yes | N/A | N/A | 2024-01-24 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-01-24 | 28 | 20 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-01-30 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-12 | 14 | 10 | 2024-02-12 | 2024-02-12 | 1 | 1 | 7 | 5 | 43 | 31 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 450.51 | -8.88 | Unknown | Unknown | Unknown | 459.39 | Unknown | 466.88 | 450.51 | 16.37 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-18 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-07 | 30 | 22 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | 2 | 2 | 80 | 58 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 178.15 | 178.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -239 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 993.92 | Unknown | Unknown | Unknown | Unknown | 993.92 | 3981 | 979.57 | 993.92 | -14.35 | Yes | N/A | N/A | 2023-08-28 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-01 | 417 | 298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-18 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | -8034.78 | -28.97 | Unknown | Unknown | -8444 | 438.19 | Unknown | 3372.88 | -8034.78 | 11407.66 | Yes | N/A | N/A | 2023-12-14 | 2023-12-18 | 5 | 3 | 2023-12-18 | 2023-12-26 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2023-12-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-22 | 21 | 15 | 2024-01-22 | 2024-01-22 | 1 | 1 | 5 | 3 | 32 | 24 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -565 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 2708.87 | 489.8 | Unknown | 138.51 | Unknown | 2080.56 | 3981 | 1487.75 | 2708.87 | -1221.12 | Yes | N/A | N/A | 2024-09-04 | 2024-10-10 | 37 | 27 | 2024-10-10 | 2024-10-29 | 20 | 14 | 2024-10-29 | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-23 | 14 | 10 | 2024-10-29 | 2024-11-19 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-30 | 42 | 30 | 2024-12-30 | 2024-12-30 | 1 | 1 | 59 | 43 | 77 | 55 | 136 | 98 | Steps 2,3,5,6,7 | 55 | 39 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -464 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-29 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 1371.49 | -6.74 | Unknown | Unknown | 9.53 | 1368.7 | 3961 | 1264.19 | 1371.49 | -107.3 | Yes | N/A | N/A | 2024-02-21 | 2024-04-12 | 52 | 38 | 2024-04-12 | 2024-05-31 | 50 | 36 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-08-27 | 89 | 63 | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-09-12 | 17 | 13 | 2024-09-12 | 2024-09-12 | 1 | 1 | 141 | 101 | 68 | 50 | 209 | 151 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2004.05 | 2004.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-02-28 | -446 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 120.27 | Unknown | Unknown | Unknown | 18.58 | 101.69 | 3981 | 1291.51 | 120.27 | 1171.24 | Yes | N/A | N/A | 2024-05-01 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-09 | 25 | 17 | 2024-12-09 | 2024-12-09 | 1 | 1 | 0 | 0 | 26 | 18 | 26 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 43.75 | 43.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -520 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 2098.81 | 449.9 | Unknown | Unknown | 14.83 | 1634.08 | Unknown | 441.71 | 2098.81 | -1657.1 | Yes | N/A | N/A | 2024-09-11 | 2024-10-07 | 27 | 19 | 2024-10-07 | 2024-10-07 | 1 | 1 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2025-01-30 | 119 | 85 | Unknown | 2024-12-09 | Unknown | Unknown | 2025-01-30 | 2025-01-31 | 2 | 2 | 2025-01-31 | 2025-01-31 | 1 | 1 | 146 | 104 | 4 | 4 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-11-05 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 1427.16 | Unknown | Unknown | Unknown | 13.66 | 1413.5 | 3981 | 1519.51 | 1427.16 | 92.35 | Yes | N/A | N/A | 2024-10-10 | 2024-11-04 | 26 | 18 | 2024-11-04 | 2024-11-27 | 24 | 18 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-24 | 149 | 107 | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-24 | 2025-05-05 | 12 | 8 | 2025-05-05 | 2025-05-02 | Unknown | Unknown | 175 | 125 | 36 | 26 | 211 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 25.7 | 25.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | 225 | 162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-28 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1955.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2025-03-27 | 213 | 153 | 2025-03-27 | 2025-04-08 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-18 | 34 | 24 | 2025-06-18 | 2025-06-13 | Unknown | Unknown | 213 | 153 | 47 | 33 | 260 | 186 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 48.4 | 48.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 884.2 | -12.49 | Unknown | Unknown | Unknown | 896.69 | 3981 | 1253.06 | 884.2 | 368.86 | Yes | N/A | N/A | 2025-02-18 | 2025-02-27 | 10 | 8 | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-27 | 1 | 1 | 10 | 8 | 2 | 2 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-07-06 | IOU Designed & Installed | N/A | No | N/A | 1579.26 | -40.79 | Unknown | Unknown | Unknown | 1620.05 | 3981 | 783.41 | 1579.26 | -795.85 | Yes | N/A | N/A | 2023-07-06 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-07-06 | 65 | 47 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-25 | 20 | 14 | 2023-07-25 | 2023-07-25 | 1 | 1 | 1 | 1 | 86 | 62 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | -685 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | -7.75 | -32.33 | Unknown | Unknown | Unknown | 24.58 | Unknown | 2221.71 | -7.75 | 2229.46 | Yes | N/A | N/A | 2025-03-11 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-03-11 | 28 | 20 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-20 | 8 | 6 | 2025-03-20 | 2025-03-20 | 1 | 1 | 3 | 3 | 37 | 27 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -453 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-08-04 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 3.3 | -6.16 | Unknown | Unknown | 3.08 | 6.38 | 3981 | 825.25 | 3.3 | 821.95 | Yes | N/A | N/A | 2023-07-19 | 2023-08-04 | 17 | 13 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-09-27 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-02-03 | 130 | 93 | 2024-02-03 | 2024-02-03 | 1 | 0 | 72 | 52 | 132 | 94 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 289 | 206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 245.63 | -16.81 | Unknown | Unknown | Unknown | 262.44 | Unknown | 744.77 | 245.63 | 499.14 | Yes | N/A | N/A | 2023-06-07 | 2023-06-07 | 1 | 1 | 2023-06-07 | 2023-07-14 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-06-14 | 8 | 6 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-16 | 1 | 1 | 1 | 1 | 47 | 35 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1979.95 | 370.15 | Unknown | Unknown | Unknown | 1609.8 | 3981 | 1666.77 | 1979.95 | -313.18 | Yes | N/A | N/A | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-02-03 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-03-17 | 43 | 31 | 2025-03-17 | 2025-03-17 | 1 | 1 | 65 | 47 | 45 | 33 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -145 | -105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2932.89 | 68.33 | Unknown | Unknown | 3.93 | 2860.63 | 3981 | 2460.46 | 2932.89 | -472.43 | Yes | N/A | N/A | 2024-07-02 | 2024-07-03 | 2 | 2 | 2024-07-03 | 2024-08-01 | 30 | 22 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-06 | 1 | 1 | 2 | 2 | 31 | 23 | 33 | 25 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | -6 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -54.98 | 1277.04 | Unknown | 530.64 | -2495 | 632.34 | 0 | 2495.38 | -54.98 | 2550.36 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-16 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Juan Capistrano | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -319 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2023-12-08 | IOU Designed & Installed | N/A | No | N/A | -6521.77 | 5829.97 | Unknown | Unknown | -14785 | 2433.26 | Unknown | 14784.91 | -6521.77 | 21306.68 | Yes | N/A | N/A | 2023-11-09 | 2023-11-13 | 5 | 3 | 2023-11-13 | 2023-12-11 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-08 | 2023-12-13 | 6 | 4 | 2023-12-13 | 2023-12-13 | 1 | 1 | 5 | 3 | 37 | 27 | 42 | 30 | Steps 2,3,5,6,7 | 3 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-05 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | -386.9 | -10.1 | Unknown | Unknown | -684 | 307.2 | Unknown | 683.84 | -386.9 | 1070.74 | Yes | N/A | N/A | 2023-11-29 | 2023-11-13 | Unknown | Unknown | 2023-11-13 | 2024-01-16 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-20 | 15 | 11 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-20 | 20 | 14 | 2024-05-20 | 2024-05-20 | 1 | 1 | 0 | 0 | 101 | 73 | 101 | 73 | Steps 2,3,5,6,7 | 35 | 25 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-04-12 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | -1067.8 | Unknown | Unknown | Unknown | -1145 | 77.2 | 3981 | 2533.16 | -1067.8 | 3600.96 | Yes | N/A | N/A | 2024-03-25 | 2024-04-12 | 19 | 15 | 2024-04-12 | 2024-04-12 | 1 | 1 | 2024-04-12 | 2024-07-08 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-10-17 | 115 | 83 | Unknown | 2024-10-07 | Unknown | Unknown | 2024-10-17 | 2024-10-22 | 6 | 4 | 2024-10-22 | 2024-10-22 | 1 | 1 | 222 | 160 | 8 | 6 | 230 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-21 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 997.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-02-20 | 22 | 16 | 2025-02-20 | 2025-02-21 | 2 | 2 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-17 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-17 | 32 | 24 | 2025-04-17 | 2025-04-17 | 1 | 1 | 47 | 33 | 35 | 27 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -473 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | 2023-08-14 | IOU Designed & Installed | N/A | No | N/A | 673.86 | 241.68 | Unknown | Unknown | Unknown | 432.18 | Unknown | 796.65 | 673.86 | 122.79 | Yes | N/A | N/A | 2023-05-09 | 2023-05-09 | 1 | 1 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-08-14 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-09-05 | 23 | 17 | 2023-09-05 | 2023-09-05 | 1 | 1 | 99 | 71 | 24 | 18 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 202.73 | 2129.49 | Unknown | 589.6 | -3442 | 925.64 | Unknown | 3441.93 | 202.73 | 3239.2 | Yes | N/A | N/A | 2022-06-22 | 2023-03-28 | 280 | 200 | 2023-03-28 | 2023-08-11 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 280 | 200 | 138 | 100 | 418 | 300 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 300 | 300 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -482 | -345 | No | 2023-01-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-26 | 2023-06-09 | IOU Designed & Installed | N/A | Yes | 77 | 1934.37 | 208.94 | Unknown | Unknown | Unknown | 1725.43 | Unknown | 1170.75 | 1934.37 | -763.62 | Yes | N/A | N/A | 2023-01-26 | 2023-04-13 | 78 | 56 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-26 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-06-12 | 4 | 2 | 2023-06-12 | 2023-06-12 | 1 | 1 | 78 | 56 | 5 | 3 | 83 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SD 1189-G3 | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-15 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2024-12-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 193859.36 | 30364.13 | Unknown | Unknown | 15061.83 | 148433.4 | 0 | 93782.43 | 193859.36 | -100076.93 | Yes | N/A | N/A | 2023-04-25 | 2023-07-31 | 98 | 70 | 2023-07-31 | 2023-12-18 | 141 | 101 | 2023-08-22 | 2024-01-12 | 54 | 40 | 2023-05-17 | 2023-12-27 | 52 | 38 | 2024-01-25 | Unknown | Unknown | Unknown | 2024-01-25 | 2024-12-04 | 315 | 225 | 2024-12-16 | 2025-03-03 | 78 | 56 | 2025-03-03 | 2025-03-03 | 1 | 1 | 152 | 110 | 587 | 421 | 739 | 531 | Steps 2,3,5,6,7 | 358 | 256 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | -482 | -345 | No | 2023-12-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-19 | 2024-04-30 | IOU Designed & Installed | N/A | Yes | 114 | -5.04 | -4.09 | Unknown | Unknown | Unknown | -0.95 | 3981 | 970.04 | -5.04 | 975.08 | Yes | N/A | N/A | 2023-12-20 | 2024-04-12 | 115 | 83 | 2024-04-12 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-04-30 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-06-05 | 37 | 27 | 2024-06-05 | 2024-06-05 | 1 | 1 | 218 | 156 | 38 | 28 | 256 | 184 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -653 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 674.12 | -8.2 | Unknown | Unknown | Unknown | 682.32 | Unknown | 909.99 | 674.12 | 235.87 | Yes | N/A | N/A | 2024-05-01 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-05-01 | 44 | 32 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-23 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-05-30 | 8 | 6 | 2024-05-30 | 2024-05-30 | 1 | 1 | 23 | 17 | 53 | 39 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -538 | -385 | No | 2024-02-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-29 | 2024-05-08 | IOU Designed & Installed | N/A | Yes | 62 | -12.48 | -10.13 | Unknown | Unknown | Unknown | -2.35 | Unknown | 820.13 | -12.48 | 832.61 | Yes | N/A | N/A | 2024-02-22 | 2024-04-24 | 63 | 45 | 2024-04-24 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-05-08 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-11 | 35 | 25 | 2024-06-11 | 2024-06-11 | 1 | 1 | 133 | 95 | 36 | 26 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | -355 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-19 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 20916.9 | 1466.12 | Unknown | Unknown | 26.33 | 19424.45 | Unknown | 17010.78 | 20916.9 | -3906.12 | Yes | N/A | N/A | 2024-07-17 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-11-06 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-11-07 | 22 | 16 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-03-12 | 58 | 42 | 2025-03-12 | 2025-03-12 | 1 | 1 | 0 | 0 | 248 | 178 | 248 | 178 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-11 | 469 | 336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-04-06 | IOU Designed & Installed | N/A | No | N/A | 4388.62 | -41.75 | Unknown | Unknown | Unknown | 4430.37 | Unknown | 1449.04 | 4388.62 | -2939.58 | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | 2023-03-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-03-23 | 10 | 8 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-05-26 | 51 | 37 | 2023-05-26 | 2023-05-26 | 1 | 1 | 1 | 1 | 64 | 48 | 65 | 49 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-24 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | -9.91 | -4.62 | Unknown | Unknown | 7.18 | -12.47 | Unknown | 158.51 | -9.91 | 168.42 | Yes | N/A | N/A | 2023-03-23 | 2023-03-22 | Unknown | Unknown | 2023-03-22 | 2023-06-29 | 100 | 72 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-11-20 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-29 | 10 | 8 | 2023-11-29 | 2023-11-29 | 1 | 1 | 145 | 103 | 111 | 81 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -302 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | -3218.58 | 582.92 | Unknown | 26.45 | -4231 | 403.05 | Unknown | 4230.66 | -3218.58 | 7449.24 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-25 | 4 | 4 | 2024-07-25 | 2024-07-25 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 291 | 208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.3 | Unknown | Unknown | Unknown | Unknown | -6.3 | Unknown | 2272.52 | -6.3 | 2278.82 | Yes | N/A | N/A | 2023-06-07 | 2023-07-27 | 51 | 37 | 2023-07-27 | 2023-08-15 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 51 | 37 | 21 | 15 | 72 | 52 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.1 | 48.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-29 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 27.4 | Unknown | Unknown | Unknown | Unknown | 27.4 | 3981 | 1666.5 | 27.4 | 1639.1 | Yes | N/A | N/A | 2024-03-28 | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2024-06-27 | 204 | 146 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-09-09 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-25 | 17 | 13 | 2024-09-25 | 2024-09-25 | 1 | 1 | 75 | 53 | 222 | 160 | 297 | 213 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-04-02 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 448.64 | Unknown | Unknown | Unknown | 5.68 | 442.96 | 3981 | 1232.19 | 448.64 | 783.55 | Yes | N/A | N/A | 2025-03-28 | 2025-04-04 | 8 | 6 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-05-05 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-06-04 | 31 | 23 | 2025-06-04 | 2025-06-04 | 1 | 1 | 40 | 28 | 33 | 25 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 133.15 | 133.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-07 | -536 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 1232.27 | 354.06 | Unknown | 233.67 | 38.24 | 606.3 | 3981 | 1543.61 | 1232.27 | 311.34 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2023-07-24 | 158 | 112 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2024-03-22 | 243 | 175 | 2024-03-22 | 2023-04-20 | Unknown | Unknown | 159 | 113 | 243 | 175 | 402 | 288 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -144 | -105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 10760.12 | Unknown | Unknown | Unknown | Unknown | 10760.12 | Unknown | 5702.94 | 10760.12 | -5057.18 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | 2024-05-06 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-29 | 2024-06-10 | 13 | 9 | 2024-06-10 | 2024-06-10 | 1 | 1 | 1 | 1 | 113 | 81 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | -171 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 314.85 | -11.23 | Unknown | Unknown | 8.63 | 317.45 | 3981 | 885.34 | 314.85 | 570.49 | Yes | N/A | N/A | 2023-10-11 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-10-18 | 44 | 32 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2024-01-22 | 97 | 69 | Unknown | 2024-01-23 | Unknown | Unknown | 2024-01-22 | 2024-02-13 | 23 | 17 | 2024-02-13 | 2024-02-13 | 1 | 1 | 97 | 69 | 68 | 50 | 165 | 119 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-05-31 | 920 | 659 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -279.86 | 2605.13 | Unknown | Unknown | -3947 | 1062.01 | Unknown | 3947.22 | -279.86 | 4227.08 | Yes | N/A | N/A | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-11 | 8 | 6 | 2023-12-11 | 2023-12-07 | Unknown | Unknown | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 194.15 | 194.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-04 | 692 | 495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-11-24 | IOU Designed & Installed | N/A | No | N/A | 1444.3 | 664.64 | Unknown | 713.45 | Unknown | 66.21 | 7962 | 297.76 | 1444.3 | -1146.54 | Yes | N/A | N/A | 2023-10-20 | 2023-11-20 | 32 | 22 | 2023-11-20 | 2023-12-05 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-11-14 | 346 | 248 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-11-24 | 2024-11-26 | 3 | 2 | 2024-11-26 | 2024-11-26 | 1 | 1 | 378 | 270 | 20 | 15 | 398 | 285 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10.4 | 10.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -632 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 23.35 | Unknown | Unknown | Unknown | Unknown | 23.35 | 3981 | 1776.05 | 23.35 | 1752.7 | Yes | N/A | N/A | 2024-08-07 | 2024-08-13 | 7 | 5 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-18 | 1 | 1 | 7 | 5 | 2 | 2 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -177 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 1511.27 | Unknown | Unknown | Unknown | Unknown | 1511.27 | 3981 | 2450.09 | 1511.27 | 938.82 | Yes | N/A | N/A | 2024-03-11 | 2024-06-17 | 99 | 71 | 2024-06-17 | 2024-08-13 | 58 | 42 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2025-05-22 | 283 | 203 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-22 | 2025-06-11 | 21 | 15 | 2025-06-11 | 2025-06-11 | 1 | 1 | 382 | 274 | 80 | 58 | 462 | 332 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 175.36 | 175.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-26 | 39 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-05-12 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 466.47 | -13.11 | Unknown | Unknown | 16.46 | 463.12 | 3981 | 609.28 | 466.47 | 142.81 | Yes | N/A | N/A | 2023-01-18 | 2023-05-12 | 115 | 83 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-10-11 | 153 | 109 | Unknown | 2023-11-20 | Unknown | Unknown | 2023-10-11 | 2023-12-05 | 56 | 40 | 2023-12-05 | 2023-12-04 | Unknown | Unknown | 268 | 192 | 56 | 40 | 324 | 232 | Steps 2,3,5,6,7 | 40 | 28 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -530 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-23 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 168.97 | 290.66 | Unknown | 124.32 | -1147 | 900.99 | Unknown | 1147.24 | 168.97 | 978.27 | Yes | N/A | N/A | 2024-07-18 | 2024-08-12 | 26 | 18 | 2024-08-12 | 2024-10-01 | 51 | 37 | 2024-10-01 | 2024-12-11 | 72 | 52 | 2024-08-13 | 2024-08-22 | 10 | 8 | 2024-12-11 | 2024-12-20 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-06 | 18 | 12 | 2025-01-06 | 2025-01-06 | 1 | 1 | 108 | 78 | 80 | 58 | 188 | 136 | Steps 2,3,5,6,7 | 120 | 86 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 578.09 | -11.7 | Unknown | Unknown | Unknown | 589.79 | 3981 | 1616.75 | 578.09 | 1038.66 | Yes | N/A | N/A | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-01-14 | 44 | 32 | 2025-01-14 | 2025-01-14 | 1 | 1 | 7 | 5 | 46 | 34 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 151.05 | 151.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 1275.18 | Unknown | Unknown | Unknown | 20.97 | 1254.21 | 3981 | 1436.78 | 1275.18 | 161.6 | Yes | N/A | N/A | 2024-06-06 | 2024-06-28 | 23 | 17 | 2024-06-28 | 2024-07-01 | 4 | 2 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-12-04 | 157 | 113 | Unknown | 2024-10-28 | Unknown | Unknown | 2024-12-04 | 2024-12-11 | 8 | 6 | 2024-12-11 | 2024-12-11 | 1 | 1 | 180 | 130 | 13 | 9 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 127.75 | 127.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -647 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-16 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | -1437.44 | Unknown | Unknown | Unknown | -1467 | 29.56 | Unknown | 1331.38 | -1437.44 | 2768.82 | Yes | N/A | N/A | 2024-09-05 | 2024-09-26 | 22 | 16 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | 2024-10-07 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-10 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-04 | 26 | 18 | 2024-11-04 | 2024-10-30 | Unknown | Unknown | 38 | 28 | 27 | 19 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-05 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | -9.19 | -7.44 | Unknown | Unknown | Unknown | -1.75 | 3981 | 1079.2 | -9.19 | 1088.39 | Yes | N/A | N/A | 2024-01-12 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-02-05 | 90 | 64 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-03-05 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-27 | 23 | 17 | 2024-03-27 | 2024-03-27 | 1 | 1 | 30 | 22 | 114 | 82 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -173 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 521.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2025-06-09 | 503 | 359 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 504 | 360 | 3 | 3 | 507 | 363 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-28 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 271.91 | -3.42 | Unknown | Unknown | Unknown | 275.33 | 3981 | 308.87 | 271.91 | 36.96 | Yes | N/A | N/A | 2024-02-21 | 2024-01-28 | Unknown | Unknown | 2024-01-28 | 2024-03-08 | 41 | 30 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-26 | 13 | 9 | 2024-03-26 | 2024-03-26 | 1 | 1 | 7 | 5 | 55 | 40 | 62 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-01 | 906 | 647 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1163.93 | -0.94 | Unknown | Unknown | 59.25 | 1105.62 | 18965 | 3084.29 | 1163.93 | 1920.36 | Yes | N/A | N/A | 2023-02-22 | 2023-03-06 | 13 | 9 | 2023-03-06 | 2023-03-08 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2024-04-19 | 12 | 10 | 2023-03-08 | 2024-08-20 | 532 | 380 | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-09-23 | Unknown | Unknown | 545 | 389 | 15 | 13 | 560 | 402 | Steps 2,3,5,6,7 | 408 | 292 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | 553 | 396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2024-02-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 11301.37 | 1000.59 | Unknown | Unknown | -10201.38 | 20502.16 | 2875.23 | 13046.42 | 11301.37 | 1745.05 | Yes | N/A | N/A | 2023-02-09 | 2023-03-15 | 35 | 25 | 2023-03-15 | 2023-09-14 | 184 | 132 | 2023-03-21 | 2023-06-21 | 93 | 67 | 2023-07-26 | 2024-01-31 | 14 | 10 | 2023-09-14 | 2024-05-10 | 240 | 172 | 2023-09-19 | 2024-01-25 | 129 | 93 | 2024-02-14 | 2024-03-04 | 20 | 14 | 2024-03-04 | 2024-05-10 | 68 | 50 | 368 | 264 | 415 | 299 | 783 | 563 | Steps 2,3,5,6,7 | 550 | 394 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 213 | 213 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 613 | 438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1954.04 | 507.48 | Unknown | Unknown | Unknown | 1446.56 | 3885 | 980.73 | 1954.04 | -973.31 | Yes | N/A | N/A | 2023-07-26 | 2023-08-08 | 14 | 10 | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2025-02-04 | 124 | 88 | 14 | 10 | 125 | 89 | 139 | 99 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | -438 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-30 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | -322.3 | 183.68 | Unknown | Unknown | -865 | 359.02 | Unknown | 865.19 | -322.3 | 1187.49 | Yes | N/A | N/A | 2023-06-19 | 2023-06-30 | 12 | 10 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2023-10-24 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-17 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-01-04 | 49 | 35 | 2024-01-04 | 2024-01-04 | 1 | 1 | 154 | 112 | 51 | 37 | 205 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | -21.96 | -17.31 | Unknown | Unknown | Unknown | -4.65 | Unknown | 515.81 | -21.96 | 537.77 | Yes | N/A | N/A | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2023-12-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-03-15 | 86 | 62 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2 | 2 | 88 | 64 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-08-03 | 2024-01-12 | IOU Designed & Installed | N/A | No | N/A | 728.97 | -11.09 | Unknown | Unknown | 4.72 | 735.34 | 3981 | 2080.81 | 728.97 | 1351.84 | Yes | N/A | N/A | 2023-07-07 | 2023-12-11 | 158 | 112 | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-12 | 33 | 25 | Unknown | 2024-01-09 | Unknown | Unknown | 2024-01-12 | 2024-03-15 | 64 | 46 | 2024-03-15 | 2024-03-15 | 1 | 1 | 191 | 137 | 66 | 48 | 257 | 185 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 229.05 | 229.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-02 | -87 | -62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-11 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | -8.45 | -6.67 | Unknown | Unknown | Unknown | -1.78 | Unknown | 496.37 | -8.45 | 504.82 | Yes | N/A | N/A | 2023-08-29 | 2023-09-11 | 14 | 10 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-12-26 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-03-07 | 73 | 53 | 2024-03-07 | 2024-03-07 | 1 | 1 | 121 | 87 | 75 | 55 | 196 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-10 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | 2023-06-12 | IOU Designed & Installed | N/A | No | N/A | 1557.79 | 582.35 | Unknown | Unknown | Unknown | 975.44 | 3981 | 871.71 | 1557.79 | -686.08 | Yes | N/A | N/A | 2023-05-09 | 2023-05-10 | 2 | 2 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | 2023-06-12 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-06-13 | 2 | 2 | 2023-06-13 | 2023-06-13 | 1 | 1 | 36 | 26 | 3 | 3 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -212 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | 8056.4 | 1601.57 | Unknown | 271.4 | 20.94 | 6162.49 | 3981 | 2367.53 | 8056.4 | -5688.87 | Yes | N/A | N/A | 2024-03-11 | 2024-04-25 | 46 | 34 | 2024-04-25 | 2024-06-06 | 43 | 31 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2025-03-21 | 289 | 207 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-21 | 2025-04-08 | 19 | 13 | 2025-04-08 | 2025-04-08 | 1 | 1 | 335 | 241 | 63 | 45 | 398 | 286 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -386.88 | -7.36 | Unknown | Unknown | Unknown | -379.52 | 25521.5 | 381.5 | -386.88 | 768.38 | Yes | N/A | N/A | 2024-04-17 | 2024-04-22 | 6 | 4 | 2024-04-22 | 2024-05-30 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-11-21 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-24 | 1 | 1 | 182 | 130 | 40 | 30 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-17 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-06 | 2024-04-19 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 818.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-06 | 2024-04-19 | 14 | 10 | 2024-04-19 | 2024-04-19 | 1 | 1 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-07-02 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2025-08-15 | 410 | 294 | 2025-08-15 | 2024-07-05 | Unknown | Unknown | 89 | 63 | 411 | 295 | 500 | 358 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -641 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 110.07 | 39.41 | Unknown | Unknown | Unknown | 70.66 | Unknown | 1046.02 | 110.07 | 935.95 | Yes | N/A | N/A | 2024-03-12 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-03-12 | 40 | 28 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-04-10 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-15 | 6 | 4 | 2024-04-15 | 2024-04-15 | 1 | 1 | 30 | 22 | 47 | 33 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-05 | 82 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1071.53 | -6.57 | Unknown | Unknown | -1072 | 7.04 | Unknown | 979.78 | -1071.53 | 2051.31 | Yes | N/A | N/A | 2023-07-18 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-09-21 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-10-12 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2023-10-26 | Unknown | Unknown | 22 | 16 | 71 | 51 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-09 | 451 | 324 | No | 2022-08-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2023-10-18 | IOU Designed & Installed | N/A | Yes | 399 | 415.58 | 254.76 | Unknown | Unknown | Unknown | 160.82 | 3885 | 347.69 | 415.58 | -67.89 | Yes | N/A | N/A | 2022-08-31 | 2023-10-04 | 400 | 286 | 2023-10-04 | 2023-10-04 | 1 | 1 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-09 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-11-03 | 17 | 13 | 2023-11-03 | 2023-11-03 | 1 | 1 | 400 | 286 | 19 | 15 | 419 | 301 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 679 | 679 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-05 | -132 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 432.97 | -8.7 | Unknown | Unknown | Unknown | 441.67 | Unknown | 4391.48 | 432.97 | 3958.51 | Yes | N/A | N/A | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | 2025-03-18 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -182 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | Unknown | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | 159.51 | -7.31 | Unknown | Unknown | 2.68 | 164.14 | 3981 | 1762.33 | 159.51 | 1602.82 | Yes | N/A | N/A | 2023-03-28 | 2023-05-04 | 38 | 28 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-06-28 | 93 | 67 | Unknown | 2023-06-27 | Unknown | Unknown | 2023-06-28 | 2023-07-07 | 10 | 8 | 2023-07-07 | 2023-07-07 | 1 | 1 | 131 | 95 | 11 | 9 | 142 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 1820.16 | -36.01 | Unknown | Unknown | Unknown | 1856.17 | 3981 | 1503.35 | 1820.16 | -316.81 | Yes | N/A | N/A | 2024-11-21 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2025-02-28 | 107 | 77 | 2025-02-28 | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-09 | 23 | 17 | 2024-11-21 | 2025-01-31 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-19 | 20 | 14 | 2025-02-19 | 2025-02-19 | 1 | 1 | 72 | 52 | 151 | 109 | 223 | 161 | Steps 2,3,5,6,7 | 49 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-08-29 | -1319 | -942 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | -5.4 | -3.92 | Unknown | Unknown | Unknown | -1.48 | 3981 | 465.36 | -5.4 | 470.76 | Yes | N/A | N/A | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-08-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2024-01-18 | 143 | 103 | 2024-01-18 | 2024-01-18 | 1 | 1 | 2 | 2 | 145 | 105 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 3145.14 | 804.36 | Unknown | Unknown | Unknown | 2340.78 | 3981 | 593.59 | 3145.14 | -2551.55 | Yes | N/A | N/A | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-05-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-09 | 13 | 9 | 2025-06-09 | 2025-06-09 | 1 | 1 | 11 | 9 | 15 | 11 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -302 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-31 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 16.84 | -15.03 | Unknown | Unknown | Unknown | 31.87 | 3981 | 1059.12 | 16.84 | 1042.28 | Yes | N/A | N/A | 2023-10-16 | 2023-11-01 | 17 | 13 | 2023-11-01 | 2023-11-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-11-30 | 31 | 23 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-14 | 23 | 17 | 2024-03-14 | 2024-03-14 | 1 | 1 | 17 | 13 | 57 | 43 | 74 | 56 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-21 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | 0.92 | -12.3 | Unknown | Unknown | Unknown | 13.22 | Unknown | 284.51 | 0.92 | 283.59 | Yes | N/A | N/A | 2023-11-20 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2023-11-21 | 33 | 23 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-12-05 | 15 | 11 | 2023-12-05 | 2023-12-05 | 1 | 1 | 1 | 1 | 49 | 35 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | -647 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-09 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 916.57 | -18.42 | Unknown | Unknown | Unknown | 934.99 | 3981 | 1986.27 | 916.57 | 1069.7 | Yes | N/A | N/A | 2025-04-02 | 2025-04-04 | 3 | 3 | 2025-04-04 | 2025-04-09 | 6 | 4 | 2025-04-09 | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-28 | 20 | 14 | 2025-04-09 | 2025-06-12 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | 2025-06-12 | 1 | 1 | 68 | 50 | 28 | 20 | 96 | 70 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-08 | 2025-03-08 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1832.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-08 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-10 | 14 | 10 | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-10 | 2025-04-09 | 31 | 23 | 2025-03-08 | 2025-04-11 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-19 | 39 | 27 | 2025-05-19 | 2025-05-19 | 1 | 1 | 35 | 25 | 85 | 61 | 120 | 86 | Steps 2,3,5,6,7 | 32 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -467 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 639.29 | -6.4 | Unknown | Unknown | 20.54 | 625.15 | 3981 | 531.96 | 639.29 | -107.33 | Yes | N/A | N/A | 2023-02-02 | 2023-03-27 | 54 | 38 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 54 | 38 | 1 | 1 | 55 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 555.31 | -28.08 | Unknown | Unknown | Unknown | 583.39 | Unknown | 2093.98 | 555.31 | 1538.67 | Yes | N/A | N/A | 2025-03-10 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-10 | 13 | 9 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-04-15 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-17 | 3 | 3 | 2025-04-17 | 2025-04-17 | 1 | 1 | 37 | 27 | 17 | 13 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 631.32 | -11.9 | Unknown | Unknown | Unknown | 643.22 | 3981 | 1570.86 | 631.32 | 939.54 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-30 | 35 | 25 | 2024-08-26 | 2024-09-12 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-10-08 | 27 | 19 | 2024-10-08 | 2024-10-08 | 1 | 1 | 19 | 15 | 64 | 46 | 83 | 61 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-04-24 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 74.68 | -1.5 | Unknown | Unknown | Unknown | 76.18 | 3981 | 1420.25 | 74.68 | 1345.57 | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-04-24 | 56 | 40 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-01 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-30 | 30 | 22 | 2025-05-30 | 2025-05-30 | 1 | 1 | 9 | 7 | 87 | 63 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 1469.12 | 647.35 | Unknown | Unknown | -742 | 1563.77 | 3981 | 2048.24 | 1469.12 | 579.12 | Yes | N/A | N/A | 2024-04-15 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-06-10 | 174 | 124 | 2024-06-10 | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-11 | 31 | 23 | 2024-07-03 | 2024-09-04 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-06 | 3 | 3 | 2024-09-06 | 2024-09-06 | 1 | 1 | 64 | 46 | 209 | 151 | 273 | 197 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 4860.32 | 1384.44 | Unknown | 351.74 | Unknown | 3124.14 | 3981 | 1197.75 | 4860.32 | -3662.57 | Yes | N/A | N/A | 2024-05-03 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-05-06 | 102 | 72 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-14 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-01 | 18 | 12 | 2024-07-01 | 2024-07-01 | 1 | 1 | 40 | 30 | 121 | 85 | 161 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-23 | IOU Designed & Installed | N/A | No | N/A | 486.86 | 243.32 | Unknown | 88.1 | Unknown | 155.44 | Unknown | 95.13 | 486.86 | -391.73 | Yes | N/A | N/A | 2023-03-08 | 2023-03-08 | 1 | 1 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-03-23 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-03-24 | 2 | 2 | 2023-03-24 | 2023-03-24 | 1 | 1 | 17 | 13 | 3 | 3 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 1044.05 | 1044.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-18 | -444 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-05-02 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 696.45 | -11.7 | Unknown | Unknown | 14.45 | 693.7 | 3981 | 809.18 | 696.45 | 112.73 | Yes | N/A | N/A | 2023-04-18 | 2023-05-22 | 35 | 25 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-10-31 | 163 | 117 | Unknown | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2023-11-02 | 3 | 3 | 2023-11-02 | 2023-11-01 | Unknown | Unknown | 198 | 142 | 3 | 3 | 201 | 145 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | -194 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 2061.68 | 605.65 | Unknown | 328.03 | 4.99 | 1123.01 | 3981 | 2156.31 | 2061.68 | 94.63 | Yes | N/A | N/A | 2023-08-29 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-10-19 | 79 | 57 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-01-04 | 78 | 56 | Unknown | 2023-11-07 | Unknown | Unknown | 2024-01-04 | 2024-01-08 | 5 | 3 | 2024-01-08 | 2024-01-08 | 1 | 1 | 78 | 56 | 85 | 61 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 6606 | 6606 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-24 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6882.41 | Unknown | Unknown | Unknown | Unknown | 6882.41 | 59715 | 7949.42 | 6882.41 | 1067.01 | Yes | N/A | N/A | 2023-04-19 | 2023-12-06 | 232 | 166 | 2023-12-06 | 2023-12-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2024-09-18 | 287 | 205 | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-20 | Unknown | Unknown | 519 | 371 | 2 | 2 | 521 | 373 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -154 | -110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-10-10 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | 770.13 | 532.63 | Unknown | Unknown | -809.43 | 1046.93 | 0 | 853.26 | 770.13 | 83.13 | Yes | N/A | N/A | 2023-09-21 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-10-10 | 111 | 79 | 2023-10-10 | 2023-11-28 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-11-30 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-11-09 | 346 | 247 | 2024-11-09 | 2024-11-09 | 1 | 0 | 53 | 39 | 458 | 326 | 511 | 365 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -255 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 341.63 | -0.63 | Unknown | Unknown | 19.14 | 323.12 | 3981 | 1687.5 | 341.63 | 1345.87 | Yes | N/A | N/A | 2024-03-13 | 2024-06-07 | 87 | 63 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-25 | Unknown | Unknown | 87 | 63 | 1 | 1 | 88 | 64 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | -2.06 | -5.34 | Unknown | Unknown | Unknown | 3.28 | Unknown | 186.4 | -2.06 | 188.46 | Yes | N/A | N/A | 2024-04-30 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-05-24 | 89 | 65 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-05-31 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-20 | 21 | 15 | 2024-06-20 | 2024-06-20 | 1 | 1 | 8 | 6 | 111 | 81 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 17208 | 17208 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-08-18 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 5.16 | -6.55 | Unknown | Unknown | Unknown | 11.71 | 3981 | 788.25 | 5.16 | 783.09 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-01-18 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-24 | 7 | 5 | 2024-01-24 | 2024-01-24 | 1 | 1 | 54 | 40 | 9 | 7 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-19 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 12983.65 | -17.09 | Unknown | Unknown | 17.44 | 12983.3 | 3981 | 873.21 | 12983.65 | -12110.44 | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | 2023-08-14 | 90 | 64 | 2023-05-22 | 2023-08-10 | 81 | 59 | 2023-05-22 | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-17 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-12-18 | 112 | 80 | 2023-12-18 | 2023-12-13 | Unknown | Unknown | 86 | 64 | 202 | 144 | 288 | 208 | Steps 2,3,5,6,7 | 164 | 118 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | -327 | -235 | No | 2024-04-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | Yes | 35 | 2962.37 | Unknown | Unknown | Unknown | 115.59 | 2846.78 | 3941 | 1205.92 | 2962.37 | -1756.45 | Yes | N/A | N/A | 2024-04-15 | 2024-05-20 | 36 | 26 | 2024-05-20 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-13 | Unknown | Unknown | 36 | 26 | 0 | 0 | 36 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-21 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 29.15 | Unknown | Unknown | Unknown | Unknown | 29.15 | Unknown | 1181.18 | 29.15 | 1152.03 | Yes | N/A | N/A | 2024-06-13 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-06-21 | 67 | 49 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-08-05 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-08 | 4 | 4 | 2024-08-08 | 2024-08-08 | 1 | 1 | 46 | 32 | 72 | 54 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -536 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | -5.62 | -5.99 | Unknown | Unknown | Unknown | 0.37 | 3981 | 153.75 | -5.62 | 159.37 | Yes | N/A | N/A | 2023-03-23 | 2023-06-15 | 85 | 61 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-07-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 121 | 87 | 2 | 2 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -408 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-16 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1603.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-20 | 31 | 23 | 2024-09-20 | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-22 | 33 | 23 | 2024-09-20 | 2025-06-23 | 277 | 197 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 277 | 197 | 67 | 49 | 344 | 246 | Steps 2,3,5,6,7 | 32 | 22 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 5.25 | Unknown | Unknown | Unknown | Unknown | 5.25 | Unknown | 1103.3 | 5.25 | 1098.05 | Yes | N/A | N/A | 2024-09-26 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-02 | Unknown | Unknown | 2024-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-10 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-14 | 36 | 26 | 2024-11-14 | 2024-11-14 | 1 | 1 | 15 | 11 | 37 | 27 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-12 | 374 | 268 | No | 2023-03-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-11-06 | IOU Designed & Installed | N/A | Yes | 229 | 865.49 | -41.28 | Unknown | Unknown | 55.25 | 851.52 | 3885 | 431.86 | 865.49 | -433.63 | Yes | N/A | N/A | 2023-03-01 | 2023-10-16 | 230 | 164 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2023-11-06 | 204 | 146 | Unknown | 2023-10-09 | Unknown | Unknown | 2023-11-06 | 2024-01-25 | 81 | 59 | 2024-01-25 | 2024-04-20 | 87 | 62 | 434 | 310 | 168 | 121 | 602 | 431 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -628 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-19 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 2.03 | Unknown | Unknown | Unknown | Unknown | 2.03 | Unknown | 139.57 | 2.03 | 137.54 | Yes | N/A | N/A | 2024-06-25 | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-07-19 | 61 | 45 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-19 | 26 | 18 | 2024-08-19 | 2024-08-19 | 1 | 1 | 7 | 5 | 88 | 64 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | -752 | -539 | No | 2023-03-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-12-04 | IOU Designed & Installed | N/A | Yes | 218 | 1333.91 | 499.8 | Unknown | Unknown | Unknown | 834.11 | 3241 | 777.38 | 1333.91 | -556.53 | Yes | N/A | N/A | 2023-03-28 | 2023-11-01 | 219 | 157 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-12-04 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-05 | 2 | 2 | 2023-12-05 | 2023-12-05 | 1 | 1 | 471 | 337 | 3 | 3 | 474 | 340 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-05 | 72 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-16 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | -925.95 | Unknown | Unknown | Unknown | 87.06 | -1013.01 | 3981 | 906.89 | -925.95 | 1832.84 | Yes | N/A | N/A | 2024-05-06 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-05-16 | 59 | 43 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-10-08 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-17 | 10 | 8 | 2024-10-17 | 2024-10-16 | Unknown | Unknown | 145 | 103 | 69 | 51 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | 187 | 134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2023-12-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 64.77 | Unknown | Unknown | Unknown | 21.48 | 43.29 | 3981 | 772.99 | 64.77 | 708.22 | Yes | N/A | N/A | 2023-12-28 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2023-12-28 | 56 | 40 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-02-27 | 73 | 53 | 0 | 0 | 129 | 93 | 129 | 93 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | -388 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -1100.06 | -12.47 | Unknown | Unknown | -1101 | 13.41 | 3981 | 1860.35 | -1100.06 | 2960.41 | Yes | N/A | N/A | 2023-05-09 | 2023-05-09 | 1 | 1 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-11-15 | 112 | 80 | Unknown | 2023-10-26 | Unknown | Unknown | 2023-11-15 | 2024-02-02 | 80 | 58 | 2024-02-02 | 2023-11-30 | Unknown | Unknown | 113 | 81 | 80 | 58 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-12 | 2022-10-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -675.22 | 1289.37 | Unknown | 284.25 | -2749 | 500.16 | Unknown | 2749.08 | -675.22 | 3424.3 | Yes | N/A | N/A | 2022-10-12 | 2023-05-17 | 218 | 156 | 2023-05-17 | 2023-07-17 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 218 | 156 | 63 | 45 | 281 | 201 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -471 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 1346.29 | -1.88 | Unknown | Unknown | 20.4 | 1327.77 | 3981 | 1330.6 | 1346.29 | -15.69 | Yes | N/A | N/A | 2024-05-15 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-05-24 | 39 | 29 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-09-24 | 124 | 88 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-24 | 2024-10-03 | 10 | 8 | 2024-10-03 | 2024-10-03 | 1 | 1 | 124 | 88 | 50 | 38 | 174 | 126 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 12000 | 12000 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-10-16 | -641 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1224.6 | Unknown | Unknown | Unknown | 8.16 | 1216.44 | 3981 | 1140.31 | 1224.6 | -84.29 | Yes | N/A | N/A | 2024-10-29 | 2024-11-06 | 9 | 7 | 2024-11-06 | 2024-11-07 | 2 | 2 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-13 | 1 | 1 | 9 | 7 | 3 | 3 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-31 | 861 | 616 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 792.12 | -8.41 | Unknown | Unknown | Unknown | 800.53 | 3981 | 638.41 | 792.12 | -153.71 | Yes | N/A | N/A | 2024-01-25 | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2024-04-05 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-05-13 | 39 | 27 | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-11 | 9 | 7 | 2024-06-11 | 2024-06-10 | Unknown | Unknown | 39 | 27 | 90 | 66 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 134 | 134 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-16 | 91 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 198.16 | -11.55 | Unknown | Unknown | 1.88 | 207.83 | 3981 | 647.76 | 198.16 | 449.6 | Yes | N/A | N/A | 2023-02-28 | 2023-04-03 | 35 | 25 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 35 | 25 | 1 | 1 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 2456.05 | 2456.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-23 | -534 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-20 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 2.72 | -3.42 | Unknown | Unknown | Unknown | 6.14 | Unknown | 288.14 | 2.72 | 285.42 | Yes | N/A | N/A | 2023-12-18 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2023-12-21 | 71 | 51 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-16 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-03-07 | 52 | 38 | 2024-03-07 | 2024-03-07 | 1 | 1 | 28 | 20 | 124 | 90 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-05 | 98 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 331.26 | -13.03 | Unknown | Unknown | -666.14 | 1010.43 | 0 | 670.34 | 331.26 | 339.08 | Yes | N/A | N/A | 2023-09-07 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-09-19 | 83 | 59 | 2023-09-19 | 2024-04-25 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-07-02 | 69 | 49 | Unknown | 2024-06-27 | Unknown | Unknown | 2024-07-02 | 2024-07-12 | 11 | 9 | 2024-07-12 | 2024-07-12 | 1 | 1 | 289 | 207 | 95 | 69 | 384 | 276 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | -7.18 | -5.83 | Unknown | Unknown | Unknown | -1.35 | Unknown | 158.79 | -7.18 | 165.97 | Yes | N/A | N/A | 2023-12-15 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-19 | 9 | 7 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-19 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-16 | 29 | 21 | 2024-02-16 | 2024-02-16 | 1 | 1 | 32 | 24 | 39 | 29 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 320.24 | -6.61 | Unknown | Unknown | Unknown | 326.85 | Unknown | 52.44 | 320.24 | -267.8 | Yes | N/A | N/A | 2025-02-27 | 2025-04-02 | 35 | 25 | 2025-04-02 | 2025-04-03 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-21 | 17 | 13 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 35 | 25 | 20 | 16 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | -154 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 353.62 | -26.13 | Unknown | Unknown | Unknown | 379.75 | 15924 | 1232.77 | 353.62 | 879.15 | Yes | N/A | N/A | 2023-11-10 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2024-02-02 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-14 | 2 | 2 | 2024-02-02 | 2024-02-28 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-28 | Unknown | Unknown | 27 | 19 | 112 | 82 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-13 | -516 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 162.64 | -3.57 | Unknown | Unknown | -671.61 | 837.82 | Unknown | 681.56 | 162.64 | 518.92 | Yes | N/A | N/A | 2023-11-01 | 2024-01-05 | 66 | 48 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-02-26 | 35 | 25 | Unknown | 2024-03-06 | Unknown | Unknown | 2024-02-26 | 2024-03-15 | 19 | 15 | 2024-03-15 | 2024-03-15 | 1 | 1 | 101 | 73 | 20 | 16 | 121 | 89 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | -332 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | -4.18 | -8.17 | Unknown | Unknown | Unknown | 3.99 | Unknown | 371.24 | -4.18 | 375.42 | Yes | N/A | N/A | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-28 | 22 | 16 | Unknown | 2023-08-25 | Unknown | Unknown | 2023-08-28 | 2023-08-30 | 3 | 3 | 2023-08-30 | 2023-08-30 | 1 | 1 | 23 | 17 | 5 | 5 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -292 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2024-01-08 | IOU Designed & Installed | N/A | No | N/A | -6.09 | -4.78 | Unknown | Unknown | Unknown | -1.31 | Unknown | 158.79 | -6.09 | 164.88 | Yes | N/A | N/A | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-08 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-03-04 | 57 | 41 | 2024-03-04 | 2024-03-04 | 1 | 1 | 5 | 3 | 59 | 43 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 242.9 | 242.9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | -204 | -147 | No | 2024-08-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-20 | 2024-09-12 | IOU Designed & Installed | N/A | Yes | 142 | 6104.76 | Unknown | Unknown | Unknown | 168.48 | 5936.28 | 3981 | 1118.97 | 6104.76 | -4985.79 | Yes | N/A | N/A | 2023-04-12 | 2024-08-14 | 491 | 351 | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-09-12 | 190 | 136 | Unknown | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-24 | 13 | 9 | 2024-09-24 | 2024-09-23 | Unknown | Unknown | 681 | 487 | 14 | 10 | 695 | 497 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Borrego Springs | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-03 | 466 | 333 | No | 2022-08-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2023-02-06 | 2023-03-30 | IOU Designed & Installed | N/A | Yes | 235 | 24279.98 | 4146.28 | Unknown | Unknown | -10244.84 | 30378.54 | Unknown | 10657.21 | 24279.98 | -13622.77 | Yes | N/A | N/A | 2022-08-11 | 2023-02-13 | 187 | 133 | 2023-02-13 | 2023-03-30 | 46 | 34 | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-21 | 2023-03-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-06-12 | 75 | 53 | 2023-06-12 | 2023-06-12 | 1 | 1 | 188 | 134 | 131 | 95 | 319 | 229 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 116 | 116 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | 142 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28.49 | Unknown | Unknown | Unknown | Unknown | 28.49 | 3981 | 805.4 | 28.49 | 776.91 | Yes | N/A | N/A | 2023-09-29 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-09-29 | 23 | 17 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-10-04 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | Applicant Design | Commercial | Underserved Community | El Cajon | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | -85 | -62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2024-02-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 33.12 | 126.15 | Unknown | 22.86 | Unknown | -115.89 | Unknown | 8817.8 | 33.12 | 8784.68 | Yes | N/A | N/A | 2023-10-31 | 2023-11-08 | 9 | 7 | 2023-11-08 | 2024-01-11 | 65 | 47 | 2023-12-19 | 2024-01-19 | 23 | 16 | 2023-12-14 | 2024-02-14 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-14 | 17 | 13 | 2024-03-14 | 2024-03-14 | 1 | 1 | 32 | 23 | 123 | 89 | 155 | 112 | Steps 2,3,5,6,7 | 59 | 43 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | 488 | 349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-06-09 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 1294.12 | 244.9 | Unknown | Unknown | 41.36 | 1007.86 | 3981 | 449.67 | 1294.12 | -844.45 | Yes | N/A | N/A | 2023-02-07 | 2023-06-09 | 123 | 89 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2024-05-17 | 344 | 246 | Unknown | 2024-02-05 | Unknown | Unknown | 2024-05-17 | 2024-05-29 | 13 | 9 | 2024-05-29 | 2024-05-29 | 1 | 1 | 467 | 335 | 14 | 10 | 481 | 345 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3463.66 | 916.53 | Unknown | 101.61 | 3.4 | 2442.12 | 3981 | 2321.17 | 3463.66 | -1142.49 | Yes | N/A | N/A | 2024-03-06 | 2024-03-12 | 7 | 5 | 2024-03-12 | 2024-03-19 | 8 | 6 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-05-23 | 1 | 1 | 7 | 5 | 9 | 7 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | -724 | -519 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 35.24 | Unknown | Unknown | Unknown | Unknown | 35.24 | 3981 | 1244.48 | 35.24 | 1209.24 | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-21 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-25 | 5 | 3 | 2025-02-25 | 2025-02-25 | 1 | 1 | 5 | 5 | 7 | 5 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 457.05 | 457.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -76 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | 679.37 | -12.84 | Unknown | Unknown | Unknown | 692.21 | 3941 | 819.88 | 679.37 | 140.51 | Yes | N/A | N/A | 2024-02-22 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-02-22 | 7 | 5 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-07 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-01 | 26 | 18 | 2024-04-01 | 2024-05-31 | 61 | 45 | 15 | 11 | 94 | 68 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-24 | -583 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-06 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 35.44 | Unknown | Unknown | Unknown | Unknown | 35.44 | Unknown | 1450.73 | 35.44 | 1415.29 | Yes | N/A | N/A | 2024-08-29 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-06 | 30 | 22 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-08 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-18 | 11 | 9 | 2024-10-18 | 2024-10-18 | 1 | 1 | 33 | 23 | 42 | 32 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -448 | -321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-08-13 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 33.37 | Unknown | Unknown | Unknown | Unknown | 33.37 | 3981 | 1483.23 | 33.37 | 1449.86 | Yes | N/A | N/A | 2024-07-08 | 2024-08-08 | 32 | 24 | 2024-08-08 | 2024-08-13 | 6 | 4 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2025-01-28 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-28 | 32 | 24 | 2025-02-28 | 2025-02-27 | Unknown | Unknown | 201 | 145 | 38 | 28 | 239 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DANA POINT | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-04 | 2023-05-12 | IOU Designed & Installed | N/A | No | N/A | 1109.97 | 354.06 | Unknown | 134.04 | Unknown | 621.87 | 3981 | 1013.81 | 1109.97 | -96.16 | Yes | N/A | N/A | 2023-05-02 | 2023-05-05 | 4 | 4 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-05-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-05-15 | 4 | 2 | 2023-05-15 | 2023-05-15 | 1 | 1 | 12 | 10 | 5 | 3 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-06 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | 1798.58 | 346.38 | Unknown | 37.78 | Unknown | 1414.42 | 3981 | 1001.53 | 1798.58 | -797.05 | Yes | N/A | N/A | 2023-08-04 | 2023-08-06 | 3 | 1 | 2023-08-06 | 2023-08-06 | 1 | 0 | 2023-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-06 | 2023-08-22 | 17 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-08-25 | 4 | 4 | 2023-08-25 | 2023-08-25 | 1 | 1 | 20 | 13 | 6 | 5 | 26 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2025-03-20 | IOU Designed & Installed | N/A | No | N/A | 24194.41 | 4228.25 | Unknown | 857.11 | 116.02 | 18993.03 | 7922 | 1159.52 | 24194.41 | -23034.89 | Yes | N/A | N/A | 2024-08-08 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-09-26 | 135 | 97 | 2024-09-26 | 2025-03-05 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-03-20 | 176 | 126 | Unknown | 2025-01-29 | Unknown | Unknown | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-03-20 | 1 | 1 | 337 | 241 | 137 | 99 | 474 | 340 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | 26 | 19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-06-30 | IOU Designed & Installed | N/A | No | N/A | 2600.99 | 407.7 | Unknown | 100.44 | 97.22 | 1995.63 | 23886 | 5101.38 | 2600.99 | 2500.39 | Yes | N/A | N/A | 2024-10-17 | 2024-10-25 | 9 | 7 | 2024-10-25 | 2025-05-13 | 201 | 143 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2025-03-06 | 42 | 30 | 2025-05-13 | 2025-06-30 | 49 | 35 | Unknown | 2025-06-13 | Unknown | Unknown | 2025-06-30 | 2025-07-01 | 2 | 2 | 2025-07-01 | 2025-06-30 | Unknown | Unknown | 58 | 42 | 245 | 175 | 303 | 217 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | 68 | 49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | -1502.95 | 372.38 | Unknown | 60.1 | -2177 | 241.57 | Unknown | 2176.91 | -1502.95 | 3679.86 | Yes | N/A | N/A | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-01-21 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2024-12-31 | 5 | 3 | 2024-12-31 | 2024-12-31 | 1 | 1 | 1 | 1 | 57 | 41 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 468.7 | -12.11 | Unknown | Unknown | Unknown | 480.81 | 3981 | 725.33 | 468.7 | 256.63 | Yes | N/A | N/A | 2023-09-29 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-10-13 | 95 | 69 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-29 | 48 | 34 | Unknown | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2023-12-14 | 16 | 12 | 2023-12-14 | 2023-12-05 | Unknown | Unknown | 48 | 34 | 111 | 81 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-22 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 9.04 | -6.96 | Unknown | Unknown | Unknown | 16 | 3981 | 1045.59 | 9.04 | 1036.55 | Yes | N/A | N/A | 2024-05-09 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-05-22 | 35 | 25 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-27 | 37 | 27 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-06-27 | 2024-07-22 | 26 | 18 | 2024-07-22 | 2024-07-22 | 1 | 1 | 37 | 27 | 62 | 44 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Juan Capistrano | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | -6099.05 | 1946.66 | Unknown | 808.62 | -10130 | 1275.67 | Unknown | 10130.15 | -6099.05 | 16229.2 | Yes | N/A | N/A | 2024-01-05 | 2024-01-08 | 4 | 2 | 2024-01-08 | 2024-03-27 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-29 | 2024-04-12 | 15 | 11 | 2024-04-12 | 2024-04-12 | 1 | 1 | 4 | 2 | 97 | 71 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 411.05 | 411.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-13 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 1499.24 | 382.05 | Unknown | Unknown | Unknown | 1117.19 | 3981 | 3258.53 | 1499.24 | 1759.29 | Yes | N/A | N/A | 2024-12-09 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-17 | 27 | 19 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-24 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 129 | 93 | 29 | 21 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 120.05 | -1.88 | Unknown | Unknown | Unknown | 121.93 | 3981 | 1853.67 | 120.05 | 1733.62 | Yes | N/A | N/A | 2025-02-21 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-04-03 | 42 | 30 | 2025-04-03 | 2025-04-03 | 1 | 1 | 1 | 1 | 47 | 35 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 986.64 | -27.15 | Unknown | Unknown | Unknown | 1013.79 | 3981 | 940.76 | 986.64 | -45.88 | Yes | N/A | N/A | 2024-04-08 | 2024-04-08 | 1 | 1 | 2024-04-08 | 2024-04-08 | 1 | 1 | 2024-04-08 | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-22 | 14 | 10 | 2024-04-08 | 2024-04-15 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-07 | 23 | 17 | 2024-05-07 | 2024-05-06 | Unknown | Unknown | 9 | 7 | 38 | 28 | 47 | 35 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-05-22 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1143.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-05-16 | 2025-05-22 | 7 | 5 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-09 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-24 | 16 | 12 | 2025-06-24 | 2025-06-24 | 1 | 1 | 37 | 27 | 24 | 18 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 769.58 | -24.13 | Unknown | Unknown | Unknown | 793.71 | 3941 | 928.91 | 769.58 | 159.33 | Yes | N/A | N/A | 2024-02-13 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-02-13 | 26 | 18 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-06-26 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-22 | 27 | 19 | 2024-07-22 | 2024-07-22 | 1 | 1 | 135 | 97 | 54 | 38 | 189 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-05 | 576 | 413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-11-02 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.43 | -7.5 | Unknown | Unknown | Unknown | 15.93 | 3981 | 787.72 | 8.43 | 779.29 | Yes | N/A | N/A | 2021-11-02 | 2023-08-18 | 655 | 469 | 2023-08-18 | 2024-03-01 | 197 | 141 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-03 | 1 | 1 | 655 | 469 | 198 | 142 | 853 | 611 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-03 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 1306.2 | 377.04 | Unknown | Unknown | Unknown | 929.16 | 3981 | 1616.94 | 1306.2 | 310.74 | Yes | N/A | N/A | 2024-09-06 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-06 | 3 | 3 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-10 | 5 | 3 | 2024-09-10 | 2024-09-10 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | -775 | -554 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | 396.82 | -10.06 | Unknown | Unknown | Unknown | 406.88 | 3981 | 817.46 | 396.82 | 420.64 | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-11-15 | 52 | 38 | 2023-11-15 | 2023-11-15 | 1 | 1 | 16 | 12 | 54 | 40 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | -145 | -104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-05-15 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | -11.21 | -8.13 | Unknown | Unknown | Unknown | -3.08 | Unknown | 495.75 | -11.21 | 506.96 | Yes | N/A | N/A | 2023-03-20 | 2023-05-15 | 57 | 41 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-08-09 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-09-15 | 38 | 28 | 2023-09-15 | 2023-09-15 | 1 | 1 | 144 | 104 | 39 | 29 | 183 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-27 | 303 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1524.55 | -74.3 | Unknown | Unknown | -2584 | 1133.75 | 0 | 2079.59 | -1524.55 | 3604.14 | Yes | N/A | N/A | 2024-05-07 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-16 | 15 | 11 | 2024-05-09 | 2024-05-13 | 5 | 3 | 2024-05-08 | 2024-06-07 | 28 | 22 | 2024-05-16 | 2025-02-28 | 289 | 207 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-26 | Unknown | Unknown | 294 | 210 | 43 | 33 | 337 | 243 | Steps 2,3,5,6,7 | 34 | 24 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 103.72 | 103.72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 923.37 | -15.68 | Unknown | Unknown | 134.33 | 804.72 | 3981 | 655.72 | 923.37 | -267.65 | Yes | N/A | N/A | 2023-08-08 | 2023-09-06 | 30 | 22 | 2023-09-06 | 2023-09-07 | 2 | 2 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-11-13 | 68 | 48 | Unknown | 2023-10-31 | Unknown | Unknown | 2023-11-13 | 2024-10-10 | 333 | 239 | 2024-10-10 | 2023-11-20 | Unknown | Unknown | 98 | 70 | 335 | 241 | 433 | 311 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-12 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 1387.61 | -38.78 | Unknown | Unknown | Unknown | 1426.39 | Unknown | 752.08 | 1387.61 | -635.53 | Yes | N/A | N/A | 2023-06-07 | 2023-06-12 | 6 | 4 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-06-19 | 8 | 6 | 2023-06-12 | 2023-07-17 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-20 | 4 | 4 | 2023-07-20 | 2023-07-20 | 1 | 1 | 42 | 30 | 13 | 11 | 55 | 41 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -352 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 3744.76 | 1250.78 | Unknown | 86.76 | Unknown | 2407.22 | Unknown | 943.97 | 3744.76 | -2800.79 | Yes | N/A | N/A | 2023-12-14 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2023-12-14 | 2 | 2 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2023-12-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-19 | 5 | 3 | 2023-12-19 | 2023-12-19 | 1 | 1 | 2 | 2 | 8 | 6 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 13.35 | 13.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-25 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-18 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 2039.98 | 767.56 | Unknown | Unknown | Unknown | 1272.42 | 3981 | 634.1 | 2039.98 | -1405.88 | Yes | N/A | N/A | 2023-09-15 | 2023-09-18 | 4 | 2 | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-10-13 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-17 | 5 | 3 | 2023-10-17 | 2023-10-17 | 1 | 1 | 30 | 22 | 7 | 5 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 24.4 | 24.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-06 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | -23.43 | -15.17 | Unknown | Unknown | Unknown | -8.26 | 3981 | 1749.59 | -23.43 | 1773.02 | Yes | N/A | N/A | 2025-02-28 | 2025-03-07 | 8 | 6 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-05-30 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-14 | 16 | 11 | 2025-06-14 | 2025-06-14 | 1 | 0 | 93 | 67 | 18 | 12 | 111 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-31 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1536.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-12-23 | 35 | 25 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-23 | 2 | 2 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-01-23 | 1 | 1 | 35 | 25 | 4 | 4 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | -471 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 379.09 | -7.33 | Unknown | Unknown | Unknown | 386.42 | 3981 | 1293.1 | 379.09 | 914.01 | Yes | N/A | N/A | 2024-03-28 | 2024-08-27 | 153 | 109 | 2024-08-27 | 2024-10-10 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-16 | 29 | 21 | 2024-10-10 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2024-10-24 | Unknown | Unknown | 153 | 109 | 74 | 54 | 227 | 163 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 1245.05 | 1245.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-04-24 | -663 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-27 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2485.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-20 | 13 | 9 | 2025-05-20 | 2025-05-27 | 8 | 6 | 2025-05-27 | 2025-06-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-23 | 22 | 16 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-06-23 | 2025-06-30 | 8 | 6 | 2025-06-30 | 2025-06-30 | 1 | 1 | 42 | 30 | 17 | 13 | 59 | 43 | Steps 2,3,5,6,7 | 4 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.63 | -7.7 | Unknown | Unknown | Unknown | 5.07 | Unknown | 966.53 | -2.63 | 969.16 | Yes | N/A | N/A | 2023-01-31 | 2023-02-01 | 2 | 2 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-04-06 | Unknown | Unknown | 2 | 2 | 0 | 0 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 496 | 355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 267.06 | Unknown | Unknown | Unknown | Unknown | 267.06 | Unknown | 499.14 | 267.06 | 232.08 | Yes | N/A | N/A | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | 2024-12-11 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-11 | 24 | 18 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-02-07 | 59 | 43 | 2025-02-07 | 2025-02-07 | 1 | 1 | 1 | 1 | 111 | 81 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | 177 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-19 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 28.51 | Unknown | Unknown | Unknown | Unknown | 28.51 | 3981 | 993.59 | 28.51 | 965.08 | Yes | N/A | N/A | 2024-06-12 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-06-19 | 85 | 61 | 2024-06-19 | 2024-06-26 | 3 | 3 | 2024-06-26 | 2024-07-27 | 32 | 23 | 2024-06-19 | 2024-07-22 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-09-12 | 53 | 39 | 2024-09-12 | 2024-09-09 | Unknown | Unknown | 37 | 27 | 170 | 123 | 207 | 150 | Steps 2,3,5,6,7 | 38 | 27 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-18 | 127 | 92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-05-30 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | -14050.27 | -61.16 | Unknown | Unknown | -19384 | 5394.89 | 0 | 23444.64 | -14050.27 | 37494.91 | Yes | N/A | N/A | 2023-04-06 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2024-01-09 | 328 | 234 | 2023-08-30 | 2023-10-11 | 43 | 31 | 2023-09-07 | 2024-04-24 | 22 | 16 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-24 | 18 | 14 | 2024-05-24 | 2024-05-24 | 1 | 1 | 43 | 31 | 369 | 265 | 412 | 296 | Steps 2,3,5,6,7 | 272 | 194 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-05 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 593.69 | 362.52 | Unknown | Unknown | Unknown | 231.17 | Unknown | 158.14 | 593.69 | -435.55 | Yes | N/A | N/A | 2023-11-06 | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-11-16 | 156 | 112 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-05 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-07 | 3 | 3 | 2023-12-07 | 2023-12-07 | 1 | 1 | 20 | 14 | 160 | 116 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2534.71 | 2093.49 | Unknown | 172.37 | -705 | 973.85 | Unknown | 705.14 | 2534.71 | -1829.57 | Yes | N/A | N/A | 2024-05-15 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 255 | 255 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-29 | -420 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1101.03 | -8.4 | Unknown | Unknown | 10.66 | 1098.77 | 3981 | 661.64 | 1101.03 | -439.39 | Yes | N/A | N/A | 2023-06-26 | 2023-04-25 | Unknown | Unknown | 2023-04-25 | 2023-07-28 | 95 | 69 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-04 | Unknown | Unknown | 0 | 0 | 95 | 69 | 95 | 69 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-06-07 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 1148.79 | 183.23 | Unknown | Unknown | 19.67 | 945.89 | 3981 | 1323.53 | 1148.79 | 174.74 | Yes | N/A | N/A | 2024-05-17 | 2024-06-06 | 21 | 15 | 2024-06-06 | 2024-06-07 | 2 | 2 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-08-01 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2025-01-13 | 166 | 118 | 2025-01-13 | 2025-01-13 | 1 | 1 | 77 | 55 | 169 | 121 | 246 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | -311 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | -7.59 | -14.75 | Unknown | Unknown | Unknown | 7.16 | 3941 | 741.43 | -7.59 | 749.02 | Yes | N/A | N/A | 2023-07-17 | 2023-06-23 | Unknown | Unknown | 2023-06-23 | 2023-07-17 | 25 | 17 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-08-02 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-08-16 | 15 | 11 | 2023-08-16 | 2023-08-16 | 1 | 1 | 17 | 13 | 41 | 29 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -379 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-10 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 728.88 | Unknown | Unknown | Unknown | Unknown | 728.88 | 3981 | 724.23 | 728.88 | -4.65 | Yes | N/A | N/A | 2024-07-02 | 2024-07-09 | 8 | 6 | 2024-07-09 | 2024-07-10 | 2 | 2 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-10-10 | 93 | 67 | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-10 | 2024-10-25 | 16 | 12 | 2024-10-25 | 2024-10-23 | Unknown | Unknown | 101 | 73 | 18 | 14 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | -93 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-13 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 704.69 | -11.61 | Unknown | Unknown | 10.18 | 706.12 | 3961 | 971.87 | 704.69 | 267.18 | Yes | N/A | N/A | 2023-06-09 | 2023-09-14 | 98 | 70 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-12-21 | 99 | 71 | Unknown | 2023-12-07 | Unknown | Unknown | 2023-12-21 | 2023-12-28 | 8 | 6 | 2023-12-28 | 2023-12-28 | 1 | 1 | 197 | 141 | 10 | 8 | 207 | 149 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | -139 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 400.73 | -6.69 | Unknown | Unknown | Unknown | 407.42 | 23886 | 1767.48 | 400.73 | 1366.75 | Yes | N/A | N/A | 2024-08-16 | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-09-04 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-18 | 1 | 1 | 0 | 0 | 79 | 57 | 79 | 57 | Steps 2,3,5,6,7 | 61 | 43 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 113.4 | 113.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-29 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.11 | Unknown | Unknown | Unknown | Unknown | 6.11 | 3981 | 1452.23 | 6.11 | 1446.12 | Yes | N/A | N/A | 2024-08-29 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-08-30 | 33 | 25 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-10-23 | 1 | 1 | 0 | 0 | 34 | 26 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | 115 | 82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-31 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 24537.13 | 4562.23 | Unknown | Unknown | -2850.39 | 22825.29 | 3981 | 11447.75 | 24537.13 | -13089.38 | Yes | N/A | N/A | 2024-01-30 | 2024-02-12 | 14 | 10 | 2024-02-12 | 2024-12-06 | 299 | 215 | 2024-06-26 | 2024-07-24 | 29 | 21 | 2024-11-26 | 2024-12-09 | 14 | 10 | 2024-12-06 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-13 | 43 | 31 | 2025-02-13 | 2025-01-14 | Unknown | Unknown | 43 | 31 | 356 | 256 | 399 | 287 | Steps 2,3,5,6,7 | 166 | 118 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | La Mesa | La Mesa | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 624 | 446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-27 | 2024-01-09 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 22636.32 | 1266.39 | Unknown | Unknown | -6482.29 | 27852.22 | Unknown | 6490.69 | 22636.32 | -16145.63 | Yes | N/A | N/A | 2022-01-27 | 2024-03-12 | 776 | 554 | 2024-03-12 | 2024-03-21 | 10 | 8 | 2024-02-26 | 2024-03-06 | 8 | 6 | 2024-02-14 | 2024-03-28 | 31 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-09-16 | 95 | 67 | 2024-09-16 | 2024-09-16 | 1 | 1 | 784 | 560 | 137 | 97 | 921 | 657 | Steps 2,3,5,6,7 | 45 | 33 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15.05 | 15.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-04-09 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 1176.66 | 236.85 | Unknown | Unknown | 2.02 | 937.79 | Unknown | 1093.83 | 1176.66 | -82.83 | Yes | N/A | N/A | 2024-03-29 | 2024-01-08 | Unknown | Unknown | 2024-01-08 | 2024-04-09 | 93 | 67 | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-05-06 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-13 | 39 | 29 | 2024-06-13 | 2024-06-13 | 1 | 1 | 28 | 20 | 133 | 97 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | 67 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-20 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 749.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-10-21 | 23 | 16 | 2023-10-21 | 2023-10-21 | 1 | 0 | 2023-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | 2025-06-19 | 608 | 434 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-23 | 5 | 3 | 2025-06-23 | 2025-06-23 | 1 | 1 | 631 | 450 | 7 | 4 | 638 | 454 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-14 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-10 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -8.97 | -6.5 | Unknown | Unknown | Unknown | -2.47 | Unknown | 483.84 | -8.97 | 492.81 | Yes | N/A | N/A | 2023-04-06 | 2023-04-07 | 2 | 2 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-07-27 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-01 | 6 | 4 | 2023-08-01 | 2023-08-01 | 1 | 1 | 111 | 81 | 7 | 5 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 328.22 | Unknown | Unknown | Unknown | 9.24 | 318.98 | Unknown | 792.14 | 328.22 | 463.92 | Yes | N/A | N/A | 2024-03-25 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-04 | 52 | 38 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-09-20 | 170 | 122 | Unknown | 2024-09-19 | Unknown | Unknown | 2024-09-20 | 2024-09-25 | 6 | 4 | 2024-09-25 | 2024-09-25 | 1 | 1 | 170 | 122 | 59 | 43 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -632 | -453 | No | 2024-11-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-26 | 2024-12-20 | IOU Designed & Installed | N/A | Yes | 25 | 30.7 | Unknown | Unknown | Unknown | Unknown | 30.7 | 3981 | 1727.03 | 30.7 | 1696.33 | Yes | N/A | N/A | 2024-11-01 | 2024-11-26 | 26 | 18 | 2024-11-26 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-20 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-13 | 25 | 17 | 2025-01-13 | 2025-01-08 | Unknown | Unknown | 45 | 33 | 25 | 17 | 70 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -296 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 1525.19 | 513.58 | Unknown | 27.02 | Unknown | 984.59 | 3941 | 605.95 | 1525.19 | -919.24 | Yes | N/A | N/A | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2024-08-08 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-15 | 8 | 6 | 2024-08-15 | 2024-08-09 | Unknown | Unknown | 324 | 232 | 8 | 6 | 332 | 238 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | Alpine | COUNTY OF SAN DIEGO-SOUTH of 56 | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | 228 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-04-11 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 85060.79 | 11842.18 | Unknown | Unknown | -21211.97 | 94430.58 | 8812 | 29460.17 | 85060.79 | -55600.62 | Yes | N/A | N/A | 2024-02-28 | 2024-10-11 | 227 | 163 | 2024-10-11 | Unknown | Unknown | Unknown | 2024-04-30 | 2024-08-01 | 18 | 14 | 2024-07-16 | 2024-09-19 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-02-13 | 176 | 126 | 2025-02-13 | 2025-02-13 | 1 | 1 | 245 | 177 | 222 | 160 | 467 | 337 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -56 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1266.96 | Unknown | Unknown | Unknown | Unknown | 1266.96 | 3981 | 2556.16 | 1266.96 | 1289.2 | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-07-01 | 19 | 13 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 1 | 1 | 20 | 14 | 21 | 15 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -171 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 684.91 | 3371.52 | Unknown | 361.04 | -4613 | 1565.35 | Unknown | 4613.35 | 684.91 | 3928.44 | Yes | N/A | N/A | 2024-03-28 | 2024-03-29 | 2 | 2 | 2024-03-29 | 2024-08-16 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-16 | 1 | 1 | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 2 | 2 | 143 | 103 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-16 | 1176 | 841 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-10-20 | Unknown | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 1763.06 | 253.36 | Unknown | 75.48 | Unknown | 1434.22 | 3981 | 668.16 | 1763.06 | -1094.9 | Yes | N/A | N/A | 2020-10-20 | 2023-04-03 | 896 | 640 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2024-12-04 | 612 | 438 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-05 | 2 | 2 | 2024-12-05 | 2024-12-05 | 1 | 1 | 1508 | 1078 | 3 | 3 | 1511 | 1081 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | -208 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 8.41 | Unknown | Unknown | Unknown | Unknown | 8.41 | 3981 | 1582.69 | 8.41 | 1574.28 | Yes | N/A | N/A | 2024-05-29 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-05-29 | 37 | 27 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-09-13 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-20 | 8 | 6 | 2024-09-20 | 2024-09-26 | 7 | 5 | 108 | 78 | 52 | 38 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 131.72 | -1.5 | Unknown | Unknown | Unknown | 133.22 | 3981 | 1570.22 | 131.72 | 1438.5 | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-03-17 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-19 | 3 | 3 | 2025-03-19 | 2025-03-19 | 1 | 1 | 89 | 63 | 5 | 5 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | -290 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | -997.86 | 466.28 | Unknown | 101.26 | -2098 | 532.6 | Unknown | 620.6 | -997.86 | 1618.46 | Yes | N/A | N/A | 2023-07-19 | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-08-02 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-07 | 5 | 3 | 2023-08-07 | 2023-08-07 | 1 | 1 | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-21 | 258 | 185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 824.58 | 244.9 | Unknown | 55.15 | Unknown | 524.53 | 3941 | 500.35 | 824.58 | -324.23 | Yes | N/A | N/A | 2024-01-19 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-27 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-05 | 8 | 6 | 2024-03-05 | 2024-03-05 | 1 | 1 | 40 | 28 | 9 | 7 | 49 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 12.15 | 12.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -396 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 516.94 | 41.83 | Unknown | Unknown | Unknown | 475.11 | 10920 | 1505.08 | 516.94 | 988.14 | Yes | N/A | N/A | 2025-04-08 | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-28 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-22 | 15 | 11 | 2025-04-28 | 2025-04-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-07 | Unknown | Unknown | 1 | 1 | 40 | 28 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -606 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 1494.85 | 379.03 | Unknown | Unknown | -462 | 1577.82 | Unknown | 319.57 | 1494.85 | -1175.28 | Yes | N/A | N/A | 2025-02-20 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-02-20 | 31 | 23 | 2025-02-20 | 2025-02-25 | 6 | 4 | 2025-02-28 | 2025-03-13 | 14 | 10 | 2025-02-25 | 2025-04-08 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-12 | 35 | 25 | 2025-05-12 | 2025-05-12 | 1 | 1 | 49 | 35 | 81 | 59 | 130 | 94 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-10 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-28 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 9.62 | -8.54 | Unknown | Unknown | Unknown | 18.16 | 0 | 911.77 | 9.62 | 902.15 | Yes | N/A | N/A | 2023-08-04 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-08-16 | 92 | 66 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2024-06-13 | 291 | 209 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-25 | 13 | 9 | 2024-06-25 | 2024-06-25 | 1 | 1 | 291 | 209 | 106 | 76 | 397 | 285 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-31 | -43 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 32.31 | Unknown | Unknown | Unknown | Unknown | 32.31 | 3981 | 955.53 | 32.31 | 923.22 | Yes | N/A | N/A | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-18 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | -368 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 515.61 | Unknown | Unknown | Unknown | 14.18 | 501.43 | 3981 | 755.54 | 515.61 | 239.93 | Yes | N/A | N/A | 2024-03-27 | 2024-04-25 | 30 | 22 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-23 | 2025-01-23 | 1 | 1 | 30 | 22 | 2 | 2 | 32 | 24 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 1072.11 | Unknown | Unknown | Unknown | 4.02 | 1068.09 | 3981 | 1322.91 | 1072.11 | 250.8 | Yes | N/A | N/A | 2024-07-16 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-07-19 | 80 | 58 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-10-14 | 88 | 62 | Unknown | 2024-10-11 | Unknown | Unknown | 2024-10-14 | 2024-10-31 | 18 | 14 | 2024-10-31 | 2024-10-31 | 1 | 1 | 88 | 62 | 99 | 73 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | -191.09 | Unknown | Unknown | Unknown | -1265.81 | 1074.72 | 3981 | 2914.14 | -191.09 | 3105.23 | Yes | N/A | N/A | 2024-07-18 | 2024-08-28 | 42 | 30 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2025-06-12 | 289 | 207 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-06-25 | 91 | 65 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-06-25 | 2025-06-27 | 3 | 3 | 2025-06-27 | 2025-06-27 | 1 | 1 | 422 | 302 | 5 | 5 | 427 | 307 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | 129 | 129 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | Unknown | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 1312.29 | -25.4 | Unknown | Unknown | Unknown | 1337.69 | 3981 | 1752.37 | 1312.29 | 440.08 | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-29 | 7 | 5 | 2024-08-23 | 2024-09-26 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-11 | 16 | 12 | 2024-10-11 | 2024-10-11 | 1 | 1 | 36 | 26 | 25 | 19 | 61 | 45 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-25 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 35.21 | Unknown | Unknown | Unknown | Unknown | 35.21 | Unknown | 1494.48 | 35.21 | 1459.27 | Yes | N/A | N/A | 2024-11-11 | 2024-11-12 | 2 | 2 | 2024-11-12 | 2024-11-25 | 14 | 10 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-02-24 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | 2025-02-27 | 1 | 1 | 94 | 68 | 19 | 15 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -635 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 46.07 | Unknown | Unknown | Unknown | Unknown | 46.07 | 3981 | 1548.49 | 46.07 | 1502.42 | Yes | N/A | N/A | 2024-12-09 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-09 | 4 | 2 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-02-24 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-10 | 15 | 11 | 2025-03-10 | 2025-03-10 | 1 | 1 | 78 | 56 | 20 | 14 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | Unknown | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 65.7 | -0.94 | Unknown | Unknown | Unknown | 66.64 | 3981 | 1834.73 | 65.7 | 1769.03 | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-03 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-15 | 13 | 9 | 2024-10-15 | 2024-10-15 | 1 | 1 | 25 | 19 | 15 | 11 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 45.35 | 45.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 4058.78 | Unknown | Unknown | Unknown | 68.24 | 3990.54 | 3981 | 1146.68 | 4058.78 | -2912.1 | Yes | N/A | N/A | 2024-06-11 | 2024-08-22 | 73 | 53 | 2024-08-22 | 2024-08-23 | 2 | 2 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-12-19 | 119 | 85 | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-19 | 2025-01-06 | 19 | 13 | 2025-01-06 | 2025-01-03 | Unknown | Unknown | 192 | 138 | 21 | 15 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -529 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-13 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 24.09 | -21.41 | Unknown | Unknown | Unknown | 45.5 | Unknown | 838.1 | 24.09 | 814.01 | Yes | N/A | N/A | 2024-03-08 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-03-13 | 55 | 39 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-16 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-04-17 | 3 | 3 | 35 | 25 | 58 | 42 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | 1611.19 | Unknown | 1611.19 | Yes | N/A | N/A | 2024-08-12 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-12 | 4 | 2 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-16 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-12 | 28 | 20 | 2024-09-12 | 2024-09-12 | 1 | 1 | 5 | 5 | 33 | 23 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | 22 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 739.2 | 199.45 | Unknown | Unknown | 34.41 | 505.34 | 3981 | 587.44 | 739.2 | -151.76 | Yes | N/A | N/A | 2023-03-01 | 2023-03-10 | 10 | 8 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-08-03 | 147 | 105 | Unknown | 2024-01-31 | Unknown | Unknown | 2023-08-03 | 2024-01-31 | 182 | 130 | 2024-01-31 | 2024-01-31 | 1 | 1 | 157 | 113 | 183 | 131 | 340 | 244 | Steps 2,3,5,6,7 | 181 | 129 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-04-06 | -59 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -79.76 | -22.63 | Unknown | Unknown | -549.03 | 491.9 | Unknown | 584.37 | -79.76 | 664.13 | Yes | N/A | N/A | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | 2023-07-21 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-12-13 | 146 | 104 | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-07 | Unknown | Unknown | 147 | 105 | 53 | 39 | 200 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 122.05 | 122.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-11 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 2304.51 | 606.24 | Unknown | 35.96 | Unknown | 1662.31 | Unknown | 1787.18 | 2304.51 | -517.33 | Yes | N/A | N/A | 2024-10-10 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2025-03-03 | 146 | 104 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-10-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-04 | 7 | 5 | 2024-11-04 | 2024-11-04 | 1 | 1 | 6 | 4 | 154 | 110 | 160 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-11 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | -1190.09 | Unknown | Unknown | Unknown | -1197 | 6.91 | Unknown | 1197.21 | -1190.09 | 2387.3 | Yes | N/A | N/A | 2024-11-08 | 2024-11-09 | 2 | 1 | 2024-11-09 | 2024-11-15 | 7 | 5 | 2024-11-15 | 2024-12-23 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-02 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-13 | 12 | 8 | 2025-01-13 | 2025-02-27 | 46 | 34 | 52 | 37 | 65 | 47 | 117 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 796.69 | 90.6 | Unknown | Unknown | Unknown | 706.09 | 3981 | 1676.31 | 796.69 | 879.62 | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-03-19 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-09 | 22 | 16 | 2025-04-09 | 2025-04-09 | 1 | 1 | 64 | 46 | 24 | 18 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-08 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | 69.79 | -11.17 | Unknown | Unknown | 0.31 | 80.65 | 3981 | 957.59 | 69.79 | 887.8 | Yes | N/A | N/A | 2024-01-04 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2024-01-08 | 118 | 84 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-02-13 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-15 | 32 | 24 | 2024-03-15 | 2024-03-15 | 1 | 1 | 37 | 27 | 151 | 109 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | -708 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 134.87 | -12.25 | Unknown | Unknown | Unknown | 147.12 | Unknown | 952.51 | 134.87 | 817.64 | Yes | N/A | N/A | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-10 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-17 | 8 | 6 | 2024-05-17 | 2024-05-17 | 1 | 1 | 11 | 9 | 10 | 8 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 1047.94 | Unknown | Unknown | Unknown | 7.92 | 1040.02 | 3961 | 1427.65 | 1047.94 | 379.71 | Yes | N/A | N/A | 2024-05-09 | 2024-07-01 | 54 | 38 | 2024-07-01 | 2024-07-17 | 17 | 13 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-10-08 | 84 | 60 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-10-08 | 2024-10-18 | 11 | 9 | 2024-10-18 | 2024-10-18 | 1 | 1 | 138 | 98 | 29 | 23 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -459 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-05-03 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 710.81 | 945.67 | Unknown | Unknown | -2381 | 2146.14 | Unknown | 2380.77 | 710.81 | 1669.96 | Yes | N/A | N/A | 2024-04-18 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-09-10 | 223 | 159 | 2024-09-10 | 2024-09-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-10-16 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-21 | 6 | 4 | 2024-10-21 | 2024-10-21 | 1 | 1 | 154 | 110 | 230 | 164 | 384 | 274 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-24 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 28.99 | Unknown | Unknown | Unknown | Unknown | 28.99 | 3981 | 1574.53 | 28.99 | 1545.54 | Yes | N/A | N/A | 2024-09-20 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-24 | 35 | 25 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-12-04 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-26 | 23 | 17 | 2024-12-26 | 2024-12-26 | 1 | 1 | 72 | 52 | 59 | 43 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-14 | 381 | 272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-08-07 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 445.51 | -23.76 | Unknown | Unknown | Unknown | 469.27 | 3981 | 1087.97 | 445.51 | 642.46 | Yes | N/A | N/A | 2023-02-16 | 2023-07-28 | 163 | 117 | 2023-07-28 | 2023-08-14 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-01-30 | 86 | 62 | 2024-01-30 | 2024-01-30 | 1 | 1 | 163 | 117 | 105 | 75 | 268 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 160.05 | 160.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -316 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 10651.54 | 1432.8 | Unknown | Unknown | Unknown | 9218.74 | Unknown | 4144.7 | 10651.54 | -6506.84 | Yes | N/A | N/A | 2024-07-19 | 2024-07-29 | 11 | 7 | 2024-07-29 | 2024-11-06 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-10-26 | 2024-11-11 | 17 | 11 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-05-02 | 2025-05-02 | 1 | 1 | 11 | 7 | 120 | 86 | 131 | 93 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 91 | 91 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-20 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-08-29 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 17092.29 | 8249.08 | Unknown | Unknown | -13444 | 22287.21 | 5953 | 22996.66 | 17092.29 | 5904.37 | Yes | N/A | N/A | 2023-01-20 | 2023-08-21 | 214 | 152 | 2023-08-21 | 2023-11-03 | 75 | 55 | 2023-08-29 | 2023-08-30 | 2 | 2 | 2023-11-06 | 2023-12-01 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-11 | 27 | 19 | 2023-12-27 | 2024-01-12 | 17 | 13 | 2024-01-12 | 2024-01-09 | Unknown | Unknown | 216 | 154 | 124 | 92 | 340 | 246 | Steps 2,3,5,6,7 | 66 | 48 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 86.38 | -0.94 | Unknown | Unknown | Unknown | 87.32 | 3981 | 1683.03 | 86.38 | 1596.65 | Yes | N/A | N/A | 2024-10-15 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-15 | 6 | 4 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-12-09 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-01-09 | 32 | 24 | 2025-01-09 | 2025-01-09 | 1 | 1 | 56 | 40 | 39 | 29 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-03 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | -9.4 | -8.1 | Unknown | Unknown | Unknown | -1.3 | 3981 | 983.86 | -9.4 | 993.26 | Yes | N/A | N/A | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-11 | 3 | 3 | 2024-07-11 | 2024-07-11 | 1 | 1 | 3 | 3 | 5 | 5 | 8 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-29 | -366 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-23 | 2022-12-01 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 4655.33 | 723.36 | Unknown | 81.68 | 42.1 | 3808.19 | Unknown | 623.05 | 4655.33 | -4032.28 | Yes | N/A | N/A | 2022-11-23 | 2023-04-24 | 153 | 109 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-07-27 | 95 | 69 | Unknown | 2023-08-01 | Unknown | Unknown | 2023-07-27 | 2023-08-29 | 34 | 24 | 2023-08-29 | 2023-08-29 | 1 | 1 | 248 | 178 | 35 | 25 | 283 | 203 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | COUNTY OF SAN DIEGO-NORTH of 56 | 115.15 | 115.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | -97 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | -911.96 | 2461.17 | Unknown | Unknown | -12605 | 9231.87 | 2778.97 | 15384.3 | -911.96 | 16296.26 | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2024-02-08 | 59 | 43 | 2023-12-20 | 2023-12-21 | 2 | 2 | 2024-01-17 | 2024-02-21 | 22 | 16 | 2024-02-08 | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-25 | 32 | 22 | 2024-04-04 | 2024-04-15 | 12 | 8 | 2024-04-15 | 2024-04-15 | 1 | 1 | 3 | 3 | 126 | 90 | 129 | 93 | Steps 2,3,5,6,7 | 63 | 45 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -444 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-08-11 | IOU Designed & Installed | N/A | No | N/A | 949.22 | -15.71 | Unknown | Unknown | 14.75 | 950.18 | 3981 | 645.55 | 949.22 | -303.67 | Yes | N/A | N/A | 2023-02-28 | 2023-07-10 | 133 | 95 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-08-11 | 120 | 86 | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-11 | 2023-09-20 | 41 | 29 | 2023-09-20 | 2023-09-20 | 1 | 1 | 253 | 181 | 43 | 31 | 296 | 212 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | -32 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 116 | -6.14 | Unknown | Unknown | 5.86 | 116.28 | 7962 | 2291.08 | 116 | 2175.08 | Yes | N/A | N/A | 2024-01-17 | 2024-02-24 | 39 | 28 | 2024-02-24 | 2024-08-27 | 186 | 132 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 39 | 28 | 187 | 133 | 226 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26.05 | 26.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-26 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | -3.73 | -15.54 | Unknown | Unknown | Unknown | 11.81 | 3981 | 1636.32 | -3.73 | 1640.05 | Yes | N/A | N/A | 2024-11-06 | 2024-11-25 | 20 | 14 | 2024-11-25 | 2024-11-27 | 3 | 3 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-01 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-04 | 4 | 4 | 2025-04-04 | 2025-04-04 | 1 | 1 | 146 | 104 | 8 | 8 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-20 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1098.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-05-21 | 22 | 16 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-22 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-10 | 20 | 14 | 2025-06-10 | 2025-06-10 | 1 | 1 | 3 | 3 | 43 | 31 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 632 | 451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 467882 | 13354.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | 2024-07-17 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-03-24 | 251 | 179 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-06-10 | 2025-06-23 | 14 | 10 | 2025-06-23 | 2025-06-23 | 1 | 1 | 252 | 180 | 60 | 44 | 312 | 224 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -804 | -575 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-10 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 619.81 | -9.26 | Unknown | Unknown | 6.22 | 622.85 | 3981 | 637.18 | 619.81 | 17.37 | Yes | N/A | N/A | 2023-04-07 | 2023-04-27 | 21 | 15 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-07-17 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-09-19 | 65 | 47 | 2023-09-19 | 2023-09-19 | 1 | 1 | 103 | 73 | 66 | 48 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -250 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1710.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-02-19 | 13 | 9 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-04-25 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-05 | 11 | 7 | 2025-05-05 | 2025-05-05 | 1 | 1 | 66 | 48 | 25 | 17 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | DEL MAR | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-23 | 186 | 133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | 569.03 | -19.72 | Unknown | Unknown | Unknown | 588.75 | 3981 | 1003.03 | 569.03 | 434 | Yes | N/A | N/A | 2023-02-27 | 2023-02-28 | 2 | 2 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-08-04 | 156 | 112 | Unknown | 2023-06-21 | Unknown | Unknown | 2023-08-04 | 2023-08-28 | 25 | 17 | 2023-08-28 | 2023-08-28 | 1 | 1 | 158 | 114 | 26 | 18 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 2370 | 1695 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-27 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 504.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-27 | 25 | 19 | 2024-12-27 | 2025-03-12 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-12-29 | 2025-01-24 | 27 | 20 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-27 | 3 | 3 | 2025-06-27 | 2025-06-27 | 1 | 1 | 25 | 19 | 107 | 78 | 132 | 97 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Fallbrook | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | -30 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 10309.22 | 2849.34 | Unknown | Unknown | -2787 | 10246.88 | 3103 | 9500.42 | 10309.22 | -808.8 | Yes | N/A | N/A | 2023-03-29 | 2023-08-30 | 155 | 111 | 2023-08-30 | 2024-05-24 | 269 | 193 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2024-05-17 | 221 | 159 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-21 | 23 | 17 | 2024-06-21 | 2024-06-21 | 1 | 1 | 155 | 111 | 514 | 370 | 669 | 481 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-26 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 6.84 | -6.05 | Unknown | Unknown | Unknown | 12.89 | Unknown | 958.86 | 6.84 | 952.02 | Yes | N/A | N/A | 2024-01-25 | 2024-02-26 | 33 | 23 | 2024-02-26 | 2024-03-04 | 8 | 6 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-22 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-15 | 25 | 17 | 2024-04-15 | 2024-04-15 | 1 | 1 | 59 | 43 | 34 | 24 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | Vista | VISTA | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 28 | 21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 2247.34 | -12.92 | Unknown | Unknown | Unknown | 2260.26 | 0 | 5511.13 | 2247.34 | 3263.79 | Yes | N/A | N/A | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | Unknown | Unknown | Unknown | 2024-11-27 | 2025-01-30 | 22 | 16 | 2024-11-19 | 2024-11-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-29 | 66 | 48 | 2025-01-29 | 2025-01-29 | 1 | 1 | 8 | 6 | 90 | 66 | 98 | 72 | Steps 2,3,5,6,7 | 72 | 52 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-07 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 797.63 | Unknown | Unknown | Unknown | -1221 | 2018.63 | Unknown | 1220.59 | 797.63 | 422.96 | Yes | N/A | N/A | 2025-02-27 | 2025-03-06 | 8 | 6 | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-07 | 2025-04-03 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-05-16 | 44 | 32 | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-16 | 2025-05-21 | 6 | 4 | 2025-05-21 | 2025-05-21 | 1 | 1 | 80 | 58 | 9 | 7 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-24 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 20.27 | Unknown | Unknown | Unknown | Unknown | 20.27 | 3948 | 2926.71 | 20.27 | 2906.44 | Yes | N/A | N/A | 2024-09-10 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-09-24 | 30 | 22 | 2024-09-24 | 2025-01-09 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-12-30 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-01-14 | 16 | 12 | 2025-01-14 | 2025-01-14 | 1 | 1 | 206 | 148 | 47 | 35 | 253 | 183 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 508 | 363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2024-01-10 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 25140.53 | -26.1 | Unknown | Unknown | Unknown | 25166.63 | 3981 | 1930.61 | 25140.53 | -23209.92 | Yes | N/A | N/A | 2023-11-30 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2024-04-05 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-04-05 | 2024-07-11 | 98 | 70 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-18 | 2024-11-26 | 40 | 28 | 2024-11-26 | 2024-11-20 | Unknown | Unknown | 98 | 70 | 197 | 141 | 295 | 211 | Steps 2,3,5,6,7 | 164 | 116 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | 41 | 30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | -5822.32 | 62.06 | Unknown | Unknown | -10344 | 4459.62 | Unknown | 9468.79 | -5822.32 | 15291.11 | Yes | N/A | N/A | 2024-09-06 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2025-04-08 | 217 | 155 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2024-10-04 | 2025-04-09 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-05-02 | 2025-06-10 | 40 | 28 | 2025-06-10 | 2025-06-10 | 1 | 1 | 1 | 1 | 329 | 235 | 330 | 236 | Steps 2,3,5,6,7 | 186 | 132 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | -58 | -42 | No | 2023-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-06-10 | IOU Designed & Installed | N/A | Yes | 148 | 534.53 | -7.54 | Unknown | Unknown | Unknown | 542.07 | 3981 | 781.84 | 534.53 | 247.31 | Yes | N/A | N/A | 2023-10-17 | 2024-03-13 | 149 | 107 | 2024-03-13 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-17 | 2023-10-25 | 9 | 7 | 2023-10-17 | 2024-06-10 | 238 | 170 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-20 | 11 | 9 | 2024-06-20 | 2024-06-20 | 1 | 1 | 387 | 277 | 21 | 17 | 408 | 294 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 99 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.21 | Unknown | Unknown | Unknown | Unknown | -0.21 | Unknown | 52.54 | -0.21 | 52.75 | Yes | N/A | N/A | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | 2024-10-17 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1 | 1 | 1 | 1 | 18 | 14 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 867.08 | -16.41 | Unknown | Unknown | Unknown | 883.49 | 3981 | 1018.57 | 867.08 | 151.49 | Yes | N/A | N/A | 2024-03-07 | 2024-03-27 | 21 | 15 | 2024-03-27 | 2024-03-29 | 3 | 3 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-17 | Unknown | Unknown | 21 | 15 | 3 | 3 | 24 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -131 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-25 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 7395.69 | 2798.45 | Unknown | 542.35 | -636 | 4690.89 | Unknown | 1634.34 | 7395.69 | -5761.35 | Yes | N/A | N/A | 2023-05-19 | 2023-05-25 | 7 | 5 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-11-06 | 140 | 100 | Unknown | 2023-10-06 | Unknown | Unknown | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-06 | 1 | 1 | 147 | 105 | 2 | 2 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | VALLEY CENTER | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-12 | 1397 | 998 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-19 | 2021-04-26 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 207624.19 | 1340.5 | Unknown | Unknown | 3671.32 | 202612.37 | 0 | 66937.3 | 207624.19 | -140686.89 | Yes | N/A | N/A | 2021-04-19 | 2023-04-03 | 715 | 511 | 2023-04-03 | 2024-07-03 | 458 | 328 | 2022-12-29 | 2024-05-10 | 2 | 2 | 2024-07-16 | 2024-07-25 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-01-30 | 162 | 116 | 2024-08-13 | 2025-04-09 | 240 | 172 | 2025-04-09 | 2025-04-09 | 1 | 1 | 717 | 513 | 871 | 625 | 1588 | 1138 | Steps 2,3,5,6,7 | 170 | 122 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | 511.08 | 183.68 | Unknown | Unknown | Unknown | 327.4 | Unknown | 911.02 | 511.08 | 399.94 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-12-14 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-01-03 | 21 | 15 | 2024-01-03 | 2024-01-03 | 1 | 1 | 37 | 27 | 23 | 17 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | -586 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 454.75 | Unknown | Unknown | Unknown | 12.46 | 442.29 | 3981 | 1504.87 | 454.75 | 1050.12 | Yes | N/A | N/A | 2025-02-07 | 2025-02-26 | 20 | 14 | 2025-02-26 | 2025-02-28 | 3 | 3 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-05-29 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-09 | 12 | 8 | 2025-06-09 | 2025-06-09 | 1 | 1 | 111 | 79 | 16 | 12 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -437 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 3339.23 | Unknown | Unknown | Unknown | 109.42 | 3229.81 | 3981 | 1336.34 | 3339.23 | -2002.89 | Yes | N/A | N/A | 2024-08-02 | 2024-08-12 | 11 | 7 | 2024-08-12 | 2024-08-12 | 1 | 1 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2025-04-17 | 246 | 176 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-17 | 2025-04-29 | 13 | 9 | 2025-04-29 | 2025-04-29 | 1 | 1 | 257 | 183 | 15 | 11 | 272 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 32.1 | 32.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | -123 | -88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 107.64 | Unknown | Unknown | Unknown | 55.37 | 52.27 | 3981 | 1048.24 | 107.64 | 940.6 | Yes | N/A | N/A | 2023-03-21 | 2023-04-06 | 17 | 13 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-09-26 | Unknown | Unknown | 17 | 13 | 0 | 0 | 17 | 13 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | -333 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 313.56 | 183.68 | Unknown | Unknown | Unknown | 129.88 | Unknown | 513.31 | 313.56 | 199.75 | Yes | N/A | N/A | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-12-27 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-04 | 9 | 7 | 2024-01-04 | 2024-01-04 | 1 | 1 | 45 | 33 | 11 | 9 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -262 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-19 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 2270.13 | 483.41 | Unknown | Unknown | Unknown | 1786.72 | 3981 | 1020.54 | 2270.13 | -1249.59 | Yes | N/A | N/A | 2024-04-10 | 2024-04-30 | 21 | 15 | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-06-04 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-06 | 3 | 3 | 2024-06-06 | 2024-06-06 | 1 | 1 | 57 | 41 | 6 | 6 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-28 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2023-05-31 | IOU Designed & Installed | N/A | No | N/A | -2.06 | -6.05 | Unknown | Unknown | Unknown | 3.99 | 3981 | 814.37 | -2.06 | 816.43 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-05-31 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-08 | 9 | 7 | 2023-06-08 | 2023-06-08 | 1 | 1 | 14 | 10 | 10 | 8 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 229 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-10 | 2022-11-10 | 2024-04-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 37872.66 | 23269.47 | Unknown | 29.69 | -85210 | 99783.5 | 0 | 82101.58 | 37872.66 | 44228.92 | Yes | N/A | N/A | 2022-11-10 | 2023-02-21 | 104 | 74 | 2023-02-21 | 2023-08-14 | 175 | 125 | 2023-04-04 | 2023-12-05 | 23 | 17 | 2023-08-14 | 2023-09-01 | 19 | 15 | 2023-08-23 | Unknown | Unknown | Unknown | 2023-08-23 | 2024-03-12 | 203 | 145 | 2024-04-05 | 2024-04-30 | 26 | 18 | 2024-04-30 | 2024-04-30 | 1 | 1 | 127 | 91 | 424 | 304 | 551 | 395 | Steps 2,3,5,6,7 | 254 | 182 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -529 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -24.93 | -12.47 | Unknown | Unknown | Unknown | -12.46 | Unknown | 154.79 | -24.93 | 179.72 | Yes | N/A | N/A | 2023-04-11 | 2023-04-21 | 11 | 9 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-08-30 | 1 | 1 | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 2171.2 | 2171.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-06 | 379 | 272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 364.66 | -7.33 | Unknown | Unknown | Unknown | 371.99 | Unknown | 654.52 | 364.66 | 289.86 | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-04-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-05-30 | 52 | 38 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 1 | 1 | 61 | 45 | 62 | 46 | Steps 2,3,5,6,7 | 44 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-02-10 | IOU Designed & Installed | N/A | No | N/A | -6.39 | -18.7 | Unknown | Unknown | Unknown | 12.31 | 3981 | 643.13 | -6.39 | 649.52 | Yes | N/A | N/A | 2023-02-07 | 2023-02-08 | 2 | 2 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-02-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-04-18 | 68 | 48 | 2023-04-18 | 2023-04-18 | 1 | 1 | 5 | 5 | 69 | 49 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -471 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-11 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 1920.02 | Unknown | Unknown | Unknown | 19.9 | 1900.12 | 3981 | 1202.13 | 1920.02 | -717.89 | Yes | N/A | N/A | 2024-10-11 | 2025-02-06 | 119 | 85 | 2025-02-06 | 2025-02-11 | 6 | 4 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-05-02 | 81 | 59 | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-02 | 2025-05-13 | 12 | 8 | 2025-05-13 | 2025-05-13 | 1 | 1 | 200 | 144 | 19 | 13 | 219 | 157 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | -980 | -701 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -52.43 | -5.44 | Unknown | Unknown | Unknown | -46.99 | Unknown | 2032.22 | -52.43 | 2084.65 | Yes | N/A | N/A | 2023-01-09 | 2023-02-13 | 36 | 26 | 2023-02-13 | 2023-02-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-04-26 | Unknown | Unknown | 36 | 26 | 16 | 12 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 322676.25 | 322676.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-07-17 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-05-07 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 52809.49 | 8374.41 | Unknown | Unknown | -10564.46 | 54999.54 | 3981 | 28043.14 | 52809.49 | -24766.35 | Yes | N/A | N/A | 2024-04-09 | 2024-04-09 | 1 | 1 | 2024-04-09 | 2024-06-07 | 60 | 44 | 2024-05-08 | 2024-06-07 | 4 | 3 | 2024-05-31 | 2024-07-15 | 14 | 10 | 2024-06-07 | 2024-07-26 | 50 | 36 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-23 | 2024-09-30 | 70 | 50 | 2024-09-30 | 2024-08-28 | Unknown | Unknown | 55 | 40 | 145 | 105 | 200 | 145 | Steps 2,3,5,6,7 | 99 | 71 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-12 | 509 | 365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-23 | 2023-05-16 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 27212.91 | 2037.07 | Unknown | 20.1 | Unknown | 25155.74 | 553391 | 35057.97 | 27212.91 | 7845.06 | Yes | N/A | N/A | 2022-05-23 | 2023-04-03 | 316 | 226 | 2023-04-03 | 2024-05-01 | 395 | 283 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | 2024-05-02 | 2024-05-06 | 5 | 3 | 2024-05-06 | 2024-05-04 | Unknown | Unknown | 316 | 226 | 400 | 286 | 716 | 512 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.67 | Unknown | Unknown | Unknown | Unknown | -0.67 | 17710.6 | 98.17 | -0.67 | 98.84 | Yes | N/A | N/A | 2023-11-21 | 2023-11-13 | Unknown | Unknown | 2023-11-13 | 2024-02-02 | 82 | 60 | 2023-12-05 | 2023-12-12 | 8 | 6 | 2023-12-12 | 2023-12-18 | 7 | 5 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-12-04 | 1 | 1 | 8 | 6 | 90 | 66 | 98 | 72 | Steps 2,3,5,6,7 | 59 | 43 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-13 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 1087.05 | 382.14 | Unknown | Unknown | Unknown | 704.91 | 3241 | 1806.68 | 1087.05 | 719.63 | Yes | N/A | N/A | 2023-09-29 | 2023-10-13 | 15 | 11 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-19 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-11-03 | 16 | 12 | 2023-11-03 | 2023-11-03 | 1 | 1 | 22 | 16 | 18 | 14 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1054.93 | Unknown | Unknown | Unknown | 22.47 | 1032.46 | 3981 | 856.86 | 1054.93 | -198.07 | Yes | N/A | N/A | 2024-06-28 | 2024-08-13 | 47 | 33 | 2024-08-13 | 2024-08-29 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-13 | 32 | 24 | 2024-08-29 | 2024-10-28 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-10-29 | Unknown | Unknown | 108 | 76 | 49 | 37 | 157 | 113 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | -144 | -105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3148.09 | -86.11 | Unknown | Unknown | 12.72 | 3221.48 | 3981 | 1011.56 | 3148.09 | -2136.53 | Yes | N/A | N/A | 2023-06-30 | 2023-08-08 | 40 | 28 | 2023-08-08 | 2023-12-01 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-28 | 9 | 7 | 2023-12-01 | 2023-12-05 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2023-12-18 | Unknown | Unknown | 45 | 31 | 125 | 91 | 170 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-01 | 802 | 574 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 29693.68 | 595.35 | Unknown | Unknown | Unknown | 29098.33 | 276059 | 7167.45 | 29693.68 | -22526.23 | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | 2023-04-17 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2024-06-18 | 429 | 307 | Unknown | 2024-06-13 | Unknown | Unknown | 2024-06-21 | 2024-07-23 | 33 | 23 | 2024-07-23 | 2024-07-11 | Unknown | Unknown | 430 | 308 | 55 | 39 | 485 | 347 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | -493 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 938.97 | 277.85 | Unknown | Unknown | 1.12 | 660 | 3981 | 994.15 | 938.97 | 55.18 | Yes | N/A | N/A | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | 2024-01-19 | 30 | 22 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-19 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-03-15 | 57 | 41 | 2024-03-15 | 2024-03-06 | Unknown | Unknown | 31 | 23 | 87 | 63 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 609 | -11.4 | Unknown | Unknown | 2.81 | 617.59 | 3241 | 1469.51 | 609 | 860.51 | Yes | N/A | N/A | 2024-07-18 | 2024-08-01 | 15 | 11 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-30 | 1 | 1 | 15 | 11 | 2 | 2 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -458 | -329 | No | 2022-12-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | 2022-12-16 | 2023-04-06 | IOU Designed & Installed | N/A | Yes | 49 | -4.78 | -3.46 | Unknown | Unknown | Unknown | -1.32 | Unknown | 343.5 | -4.78 | 348.28 | Yes | N/A | N/A | 2022-12-16 | 2023-02-03 | 50 | 36 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-22 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-08-08 | 125 | 89 | 2023-08-08 | 2023-08-08 | 1 | 1 | 50 | 36 | 126 | 90 | 176 | 126 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-04-27 | IOU Designed & Installed | N/A | No | N/A | -8.52 | -6.19 | Unknown | Unknown | Unknown | -2.33 | Unknown | 154.79 | -8.52 | 163.31 | Yes | N/A | N/A | 2023-03-24 | 2023-04-06 | 14 | 10 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-08-08 | 104 | 74 | 2023-08-08 | 2023-08-08 | 1 | 1 | 36 | 26 | 105 | 75 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -120 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 18.49 | -5.02 | Unknown | Unknown | 18.15 | 5.36 | 3981 | 827.4 | 18.49 | 808.91 | Yes | N/A | N/A | 2023-03-31 | 2023-04-21 | 22 | 16 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-08 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 833.33 | Unknown | Unknown | Unknown | 8.14 | 825.19 | 3981 | 1053.14 | 833.33 | 219.81 | Yes | N/A | N/A | 2024-12-17 | 2025-01-27 | 42 | 30 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-04-24 | 88 | 64 | Unknown | 2025-03-31 | Unknown | Unknown | 2025-04-24 | 2025-04-28 | 5 | 3 | 2025-04-28 | 2025-04-28 | 1 | 1 | 130 | 94 | 7 | 5 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-05 | 2022-01-05 | 2023-05-31 | IOU Designed & Installed | N/A | No | N/A | 41424.21 | 11034.53 | Unknown | 27.08 | Unknown | 30362.6 | 412521 | 36714.88 | 41424.21 | -4709.33 | Yes | N/A | N/A | 2022-01-05 | 2023-04-10 | 461 | 329 | 2023-04-10 | 2023-04-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-04-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | Unknown | Unknown | 2023-05-31 | 2023-06-21 | 22 | 16 | 2023-06-21 | 2023-06-19 | Unknown | Unknown | 461 | 329 | 45 | 33 | 506 | 362 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-19 | -282 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-21 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 1293.8 | -24.99 | Unknown | Unknown | Unknown | 1318.79 | 3981 | 1885.05 | 1293.8 | 591.25 | Yes | N/A | N/A | 2024-10-14 | 2024-10-14 | 1 | 1 | 2024-10-14 | 2024-10-21 | 8 | 6 | 2024-10-21 | Unknown | Unknown | Unknown | 2024-10-22 | 2024-12-06 | 46 | 34 | 2024-10-21 | 2024-12-16 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-10 | 26 | 20 | 2025-01-10 | 2025-01-10 | 1 | 1 | 58 | 42 | 81 | 61 | 139 | 103 | Steps 2,3,5,6,7 | 46 | 34 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 55200 | 55200 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-05-21 | 333 | 239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-23 | 2022-08-24 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 11.17 | -9.92 | Unknown | Unknown | Unknown | 21.09 | 3885 | 810.01 | 11.17 | 798.84 | Yes | N/A | N/A | 2022-08-23 | 2023-10-13 | 417 | 299 | 2023-10-13 | 2023-10-27 | 15 | 11 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-24 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-04-24 | 13 | 9 | 2024-04-24 | 2024-04-18 | Unknown | Unknown | 417 | 299 | 28 | 20 | 445 | 319 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 24.2 | 24.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -368 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-21 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 1172.05 | 238.82 | Unknown | Unknown | Unknown | 933.23 | 3885 | 870.81 | 1172.05 | -301.24 | Yes | N/A | N/A | 2023-09-14 | 2023-09-21 | 8 | 6 | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2024-06-05 | 259 | 185 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-10 | 6 | 4 | 2024-06-10 | 2024-06-10 | 1 | 1 | 267 | 191 | 8 | 6 | 275 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 447.38 | Unknown | Unknown | Unknown | 4.65 | 442.73 | 3981 | 897.84 | 447.38 | 450.46 | Yes | N/A | N/A | 2025-02-24 | 2025-03-07 | 12 | 10 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-01 | 1 | 1 | 12 | 10 | 2 | 2 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 1065.19 | 731.4 | Unknown | Unknown | Unknown | 333.79 | Unknown | 480.37 | 1065.19 | -584.82 | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-10-05 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-10 | 6 | 4 | 2023-10-10 | 2023-10-10 | 1 | 1 | 52 | 38 | 8 | 6 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-10 | 809 | 578 | No | 2020-08-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-08-28 | 2020-10-27 | 2023-08-28 | IOU Designed & Installed | N/A | Yes | 1067 | 49375.95 | 7657.49 | Unknown | Unknown | 10.58 | 41707.88 | 53069 | 27139.28 | 49375.95 | -22236.67 | Yes | N/A | N/A | 2020-08-28 | 2023-04-25 | 971 | 693 | 2023-04-25 | 2023-08-22 | 120 | 86 | 2023-06-09 | 2023-06-11 | 3 | 1 | 2021-03-04 | 2023-08-24 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-27 | 31 | 23 | 2023-09-27 | 2023-09-27 | 1 | 1 | 974 | 694 | 231 | 167 | 1205 | 861 | Steps 2,3,5,6,7 | 74 | 52 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -387 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 1705.89 | 444.05 | Unknown | Unknown | Unknown | 1261.84 | 15924 | 1565.45 | 1705.89 | -140.44 | Yes | N/A | N/A | 2024-09-20 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2025-01-22 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-04 | 14 | 10 | 2025-02-04 | 2025-02-04 | 1 | 1 | 122 | 88 | 15 | 11 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-02 | -375 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-05-06 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 1221.16 | -17.93 | Unknown | Unknown | 6.15 | 1232.94 | 3981 | 959.7 | 1221.16 | -261.46 | Yes | N/A | N/A | 2024-04-26 | 2024-05-03 | 8 | 6 | 2024-05-03 | 2024-05-06 | 4 | 2 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2025-05-21 | 381 | 273 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-05-28 | 8 | 6 | 2025-05-28 | 2025-05-23 | Unknown | Unknown | 389 | 279 | 12 | 8 | 401 | 287 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | 750.43 | 529.37 | Unknown | Unknown | -1317.05 | 1538.11 | 0 | 1730.5 | 750.43 | 980.07 | Yes | N/A | N/A | 2023-02-13 | 2023-04-10 | 57 | 41 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2024-02-29 | 323 | 231 | Unknown | 2024-02-08 | Unknown | Unknown | 2024-02-29 | 2024-03-01 | 2 | 2 | 2024-03-01 | 2024-03-01 | 1 | 1 | 380 | 272 | 3 | 3 | 383 | 275 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-24 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | -289.76 | 382.05 | Unknown | 115.64 | -1915 | 1127.55 | Unknown | 1914.37 | -289.76 | 2204.13 | Yes | N/A | N/A | 2024-12-19 | 2025-01-23 | 36 | 26 | 2025-01-23 | 2025-01-24 | 2 | 2 | 2025-01-24 | 2025-04-14 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-04-22 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | 2025-04-22 | Unknown | Unknown | 206 | 146 | 5 | 5 | 211 | 151 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 287.05 | 287.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -64 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 321.38 | -12.06 | Unknown | Unknown | Unknown | 333.44 | 3941 | 156.93 | 321.38 | -164.45 | Yes | N/A | N/A | 2024-05-08 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-20 | 20 | 14 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-03 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-13 | 11 | 9 | 2024-06-13 | 2024-06-12 | Unknown | Unknown | 15 | 11 | 31 | 23 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3941 | 1382.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-05-28 | Unknown | Unknown | 2024-05-28 | 2024-07-02 | 36 | 26 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-10-10 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-15 | 6 | 4 | 2024-10-15 | 2024-10-15 | 1 | 1 | 101 | 73 | 43 | 31 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | -668 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-25 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 891.99 | Unknown | Unknown | Unknown | 4.81 | 887.18 | 3981 | 1204.78 | 891.99 | 312.79 | Yes | N/A | N/A | 2025-02-20 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-28 | 23 | 17 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-17 | 18 | 12 | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-17 | 2025-04-01 | 16 | 12 | 2025-04-01 | 2025-04-01 | 1 | 1 | 18 | 12 | 40 | 30 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 89 | 64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2024-07-12 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 53.64 | Unknown | Unknown | Unknown | Unknown | 53.64 | 3981 | 284.29 | 53.64 | 230.65 | Yes | N/A | N/A | 2023-07-28 | 2024-07-03 | 342 | 244 | 2024-07-03 | 2024-07-12 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-10-08 | 89 | 63 | Unknown | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-10-09 | 17 | 13 | 2024-10-09 | 2024-10-08 | Unknown | Unknown | 431 | 307 | 27 | 21 | 458 | 328 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-18 | -467 | -334 | No | 2023-05-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-26 | 2023-11-03 | IOU Designed & Installed | N/A | Yes | 131 | -9 | -6.61 | Unknown | Unknown | Unknown | -2.39 | Unknown | 371.82 | -9 | 380.82 | Yes | N/A | N/A | 2023-05-25 | 2023-10-03 | 132 | 94 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-11-03 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-09 | 7 | 5 | 2023-11-09 | 2023-11-09 | 1 | 1 | 294 | 210 | 8 | 6 | 302 | 216 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | Carlsbad | CARLSBAD | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-05 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-12 | 2022-11-16 | 2023-03-02 | IOU Designed & Installed | N/A | No | N/A | 8351.91 | Unknown | Unknown | Unknown | -256 | 8607.91 | Unknown | 2418.15 | 8351.91 | -5933.76 | Yes | N/A | N/A | 2022-11-12 | 2023-03-20 | 129 | 91 | 2023-03-20 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-27 | 2023-02-21 | 6 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-05-19 | 79 | 57 | 2023-05-19 | 2023-05-19 | 1 | 1 | 129 | 91 | 86 | 60 | 215 | 151 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 4.33 | -5.46 | Unknown | Unknown | Unknown | 9.79 | Unknown | 288.14 | 4.33 | 283.81 | Yes | N/A | N/A | 2023-12-18 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-12-28 | 105 | 75 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2023-12-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-18 | 22 | 16 | 2024-01-18 | 2024-01-18 | 1 | 1 | 1 | 1 | 128 | 92 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | -7.66 | -7.2 | Unknown | Unknown | Unknown | -0.46 | Unknown | 438.07 | -7.66 | 445.73 | Yes | N/A | N/A | 2023-06-09 | 2023-07-18 | 40 | 28 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-10-18 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-25 | 8 | 6 | 2023-10-25 | 2023-10-25 | 1 | 1 | 133 | 95 | 9 | 7 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -456 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2025-03-21 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2998.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2025-02-26 | 120 | 86 | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | 2025-03-25 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-06-16 | 78 | 56 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-06-16 | 2025-06-18 | 3 | 3 | 2025-06-18 | 2025-06-18 | 1 | 1 | 226 | 162 | 5 | 5 | 231 | 167 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | DANA POINT | 17.4 | 17.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-13 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 22633.14 | 5330.64 | Unknown | Unknown | 37.67 | 17264.83 | Unknown | 12874.41 | 22633.14 | -9758.73 | Yes | N/A | N/A | 2024-05-13 | 2024-05-20 | 8 | 6 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-17 | 2024-11-07 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-01-03 | 26 | 20 | 2025-01-03 | 2025-01-03 | 1 | 1 | 8 | 6 | 46 | 34 | 54 | 40 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | -2218.82 | Unknown | Unknown | Unknown | -3145 | 926.18 | Unknown | 3144.9 | -2218.82 | 5363.72 | Yes | N/A | N/A | 2024-12-12 | 2024-12-17 | 6 | 4 | 2024-12-17 | 2024-12-23 | 7 | 5 | 2024-12-23 | 2024-12-27 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-02-18 | 54 | 38 | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-03-06 | 2025-03-06 | 1 | 1 | 65 | 47 | 25 | 19 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -444 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 54.46 | -17.4 | Unknown | Unknown | Unknown | 71.86 | Unknown | 1032.15 | 54.46 | 977.69 | Yes | N/A | N/A | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | 2025-02-10 | 68 | 48 | 2024-12-18 | 2024-12-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-12 | 29 | 21 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2 | 2 | 98 | 70 | 100 | 72 | Steps 2,3,5,6,7 | 54 | 38 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2023-09-15 | IOU Designed & Installed | N/A | No | N/A | 1269.36 | -35.6 | Unknown | Unknown | Unknown | 1304.96 | Unknown | 301.02 | 1269.36 | -968.34 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-06-07 | 36 | 26 | 2023-05-03 | 2023-09-15 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-10-13 | 29 | 21 | 2023-10-13 | 2023-10-13 | 1 | 1 | 137 | 99 | 66 | 48 | 203 | 147 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -183 | -132 | No | 2023-07-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2024-05-08 | IOU Designed & Installed | N/A | Yes | 55 | 7116.45 | -23.44 | Unknown | Unknown | 237.12 | 6902.77 | 3981 | 756.43 | 7116.45 | -6360.02 | Yes | N/A | N/A | 2023-07-14 | 2023-09-07 | 56 | 40 | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | Unknown | Unknown | Unknown | 2023-07-14 | 2024-04-15 | 5 | 3 | 2023-08-25 | 2024-05-08 | 258 | 184 | Unknown | 2024-05-07 | Unknown | Unknown | 2024-05-08 | 2024-06-04 | 28 | 20 | 2024-06-04 | 2024-06-05 | 2 | 2 | 314 | 224 | 36 | 26 | 350 | 250 | Steps 2,3,5,6,7 | 234 | 166 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | -213 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 208.52 | -4.16 | Unknown | Unknown | 8.79 | 203.89 | 3981 | 396.09 | 208.52 | 187.57 | Yes | N/A | N/A | 2023-03-15 | 2023-03-20 | 6 | 4 | 2023-03-20 | 2023-04-17 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-05-23 | Unknown | Unknown | 6 | 4 | 29 | 21 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-27 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 36.88 | Unknown | Unknown | Unknown | Unknown | 36.88 | Unknown | 1746.08 | 36.88 | 1709.2 | Yes | N/A | N/A | 2024-12-17 | 2024-12-18 | 2 | 2 | 2024-12-18 | 2024-12-27 | 10 | 8 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-08 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-16 | 9 | 7 | 2025-01-16 | 2025-01-16 | 1 | 1 | 15 | 11 | 20 | 16 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 508.05 | 508.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 21.48 | Unknown | Unknown | Unknown | Unknown | 21.48 | 3961 | 1392.35 | 21.48 | 1370.87 | Yes | N/A | N/A | 2025-02-12 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-12 | 22 | 16 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-24 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-05 | 10 | 8 | 2025-03-05 | 2025-03-05 | 1 | 1 | 12 | 8 | 33 | 25 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-03 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 493.05 | 306.13 | Unknown | Unknown | Unknown | 186.92 | Unknown | 148.7 | 493.05 | -344.35 | Yes | N/A | N/A | 2023-08-15 | 2023-09-01 | 18 | 14 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2024-01-03 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-01-09 | 7 | 5 | 2024-01-09 | 2024-01-09 | 1 | 1 | 143 | 103 | 9 | 7 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-23 | -920 | -657 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.83 | -23 | Unknown | Unknown | Unknown | 15.17 | 3981 | 983.22 | -7.83 | 991.05 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 14.85 | 14.85 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -205 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16.13 | Unknown | Unknown | Unknown | Unknown | 16.13 | Unknown | 196.69 | 16.13 | 180.56 | Yes | N/A | N/A | 2025-01-23 | 2025-02-04 | 13 | 9 | 2025-02-04 | 2025-02-06 | 3 | 3 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 13 | 9 | 4 | 4 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 179.05 | 179.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-21 | 406 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2023-03-14 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 5912.98 | Unknown | Unknown | Unknown | Unknown | 5912.98 | 3981 | 2423.13 | 5912.98 | -3489.85 | Yes | N/A | N/A | 2022-11-08 | 2023-03-14 | 127 | 91 | 2023-03-14 | 2023-05-09 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-05-09 | 2024-03-19 | 316 | 226 | Unknown | 2024-04-02 | Unknown | Unknown | 2024-04-09 | 2024-05-07 | 29 | 21 | 2024-05-07 | 2024-04-30 | Unknown | Unknown | 443 | 317 | 87 | 63 | 530 | 380 | Steps 2,3,5,6,7 | 125 | 89 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-26 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 133.41 | -1.88 | Unknown | Unknown | Unknown | 135.29 | Unknown | 1541.05 | 133.41 | 1407.64 | Yes | N/A | N/A | 2024-09-23 | 2024-09-26 | 4 | 4 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-02-06 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-26 | 21 | 15 | 2025-02-26 | 2025-02-26 | 1 | 1 | 138 | 100 | 23 | 17 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 170011.35 | 170011.35 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-05 | -571 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-22 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | 2408.89 | -20.08 | Unknown | Unknown | 22.23 | 2406.74 | 7962 | 1096.58 | 2408.89 | -1312.31 | Yes | N/A | N/A | 2024-02-06 | 2024-03-01 | 25 | 19 | 2024-03-01 | 2024-03-01 | 1 | 1 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-04-26 | 57 | 41 | Unknown | 2024-04-25 | Unknown | Unknown | 2024-04-26 | 2024-06-11 | 47 | 33 | 2024-06-11 | 2024-05-13 | Unknown | Unknown | 82 | 60 | 48 | 34 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -416 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 909.07 | -5.85 | Unknown | Unknown | 21.53 | 893.39 | 3981 | 685.99 | 909.07 | -223.08 | Yes | N/A | N/A | 2023-02-15 | 2023-04-10 | 55 | 39 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-10-10 | 187 | 133 | Unknown | 2023-10-09 | Unknown | Unknown | 2023-10-10 | 2023-10-23 | 14 | 10 | 2023-10-23 | 2023-10-23 | 1 | 1 | 242 | 172 | 15 | 11 | 257 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 482.18 | Unknown | Unknown | Unknown | 3.43 | 478.75 | Unknown | 1493.93 | 482.18 | 1011.75 | Yes | N/A | N/A | 2024-12-20 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2025-01-24 | 44 | 32 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-11 | 19 | 13 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-02-11 | 2025-03-06 | 24 | 18 | 2025-03-06 | 2025-03-06 | 1 | 1 | 19 | 13 | 69 | 51 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-14 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 428.69 | -6.45 | Unknown | Unknown | Unknown | 435.14 | 3981 | 411.76 | 428.69 | -16.93 | Yes | N/A | N/A | 2022-09-21 | 2023-05-08 | 230 | 164 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-07-06 | 1 | 1 | 230 | 164 | 1 | 1 | 231 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -427 | -306 | No | 2023-02-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | Yes | 62 | -13.1 | -9.5 | Unknown | Unknown | Unknown | -3.6 | Unknown | 311.78 | -13.1 | 324.88 | Yes | N/A | N/A | 2023-02-08 | 2023-04-11 | 63 | 45 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 63 | 45 | 1 | 1 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | 104 | 75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 1649.87 | Unknown | Unknown | Unknown | 34.72 | 1615.15 | 3885 | 1087.2 | 1649.87 | -562.67 | Yes | N/A | N/A | 2023-08-25 | 2024-05-21 | 271 | 193 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | 2024-09-06 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-08-19 | 91 | 65 | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-19 | 2024-10-02 | 45 | 33 | 2024-10-02 | 2024-10-02 | 1 | 1 | 471 | 337 | 47 | 35 | 518 | 372 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | -170 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | -12.11 | -10.81 | Unknown | Unknown | Unknown | -1.3 | Unknown | 153.49 | -12.11 | 165.6 | Yes | N/A | N/A | 2023-10-27 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2024-01-03 | 107 | 77 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-01-23 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-03-15 | 53 | 39 | 2024-03-15 | 2024-03-15 | 1 | 1 | 21 | 15 | 161 | 117 | 182 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | -268 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-02-03 | 2023-03-31 | IOU Designed & Installed | N/A | No | N/A | 752.13 | 248.3 | Unknown | 88.1 | Unknown | 415.73 | Unknown | 217.6 | 752.13 | -534.53 | Yes | N/A | N/A | 2023-01-19 | 2023-02-03 | 16 | 12 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-03-31 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-04-03 | 4 | 2 | 2023-04-03 | 2023-04-03 | 1 | 1 | 73 | 53 | 5 | 3 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-12 | 667 | 476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-06 | 2021-05-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2748.14 | Unknown | Unknown | Unknown | -2749 | 0.86 | Unknown | 2876.01 | -2748.14 | 5624.15 | Yes | N/A | N/A | 2021-05-06 | 2023-06-28 | 784 | 560 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 784 | 560 | 1 | 1 | 785 | 561 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 29185 | 29185 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-12-01 | 221 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-26 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 8.59 | -6.62 | Unknown | Unknown | Unknown | 15.21 | 15924 | 717.38 | 8.59 | 708.79 | Yes | N/A | N/A | 2023-07-25 | 2023-07-26 | 2 | 2 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-03 | 9 | 7 | 2023-07-26 | 2024-06-28 | 339 | 243 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-09 | 12 | 8 | 2024-07-09 | 2024-07-09 | 1 | 1 | 341 | 245 | 22 | 16 | 363 | 261 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -368 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-16 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 12211.41 | -127.25 | Unknown | Unknown | Unknown | 12338.66 | Unknown | 6313.02 | 12211.41 | -5898.39 | Yes | N/A | N/A | 2024-05-07 | 2024-05-29 | 23 | 17 | 2024-05-29 | 2024-07-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-22 | 35 | 23 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-16 | 28 | 20 | 2024-09-16 | 2024-09-16 | 1 | 1 | 23 | 17 | 100 | 70 | 123 | 87 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | 328 | 235 | No | 2023-09-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2024-09-16 | 2024-10-31 | IOU Designed & Installed | N/A | Yes | 366 | 62.72 | -0.63 | Unknown | Unknown | Unknown | 63.35 | Unknown | 1424.59 | 62.72 | 1361.87 | Yes | N/A | N/A | 2023-09-19 | 2024-09-19 | 367 | 263 | 2024-09-19 | 2024-09-16 | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-31 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-13 | 14 | 10 | 2024-11-13 | 2024-11-08 | Unknown | Unknown | 410 | 294 | 14 | 10 | 424 | 304 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -571 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 8359.24 | -82.95 | Unknown | Unknown | Unknown | 8442.19 | 3981 | 1333.01 | 8359.24 | -7026.23 | Yes | N/A | N/A | 2024-08-06 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-08-06 | 9 | 7 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-10-21 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-05 | 16 | 12 | 2024-11-05 | 2024-10-28 | Unknown | Unknown | 77 | 55 | 25 | 19 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -212 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 17921.23 | Unknown | Unknown | Unknown | Unknown | 17921.23 | 8241 | 2188.27 | 17921.23 | -15732.96 | Yes | N/A | N/A | 2024-09-25 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-12-26 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-29 | 22 | 16 | 2025-01-29 | 2025-01-29 | 1 | 1 | 0 | 0 | 118 | 86 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | -149 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 7505.15 | 1982.81 | Unknown | 959.3 | Unknown | 4563.04 | Unknown | 770 | 7505.15 | -6735.15 | Yes | N/A | N/A | 2023-06-27 | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-06-27 | 55 | 39 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-10-24 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-22 | 30 | 22 | 2023-11-22 | 2023-11-22 | 1 | 1 | 120 | 86 | 86 | 62 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 336.25 | -13.61 | Unknown | Unknown | Unknown | 349.86 | Unknown | 960.75 | 336.25 | 624.5 | Yes | N/A | N/A | 2024-01-18 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2024-01-18 | 133 | 95 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-03-15 | 52 | 38 | 2024-03-15 | 2024-03-15 | 1 | 1 | 7 | 5 | 186 | 134 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | 25 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 6776.33 | Unknown | Unknown | Unknown | Unknown | 6776.33 | 3981 | 1369.07 | 6776.33 | -5407.26 | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-08-13 | 20 | 14 | 2024-08-13 | 2024-08-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-06 | 16 | 12 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2 | 2 | 37 | 27 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4290 | 4290 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-05-13 | 458 | 327 | No | 2021-07-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-09 | 2021-07-15 | Unknown | IOU Designed & Installed | N/A | Yes | 626 | -8.86 | -6.43 | Unknown | Unknown | Unknown | -2.43 | Unknown | 467.9 | -8.86 | 476.76 | Yes | N/A | N/A | 2021-07-09 | 2023-03-27 | 627 | 447 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 627 | 447 | 1 | 1 | 628 | 448 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | -669 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1696.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-06-03 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-10 | 8 | 6 | 2025-06-10 | 2025-06-10 | 1 | 1 | 51 | 37 | 10 | 8 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-03-22 | IOU Designed & Installed | N/A | No | N/A | -9.42 | -6.83 | Unknown | Unknown | Unknown | -2.59 | Unknown | 934 | -9.42 | 943.42 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-03-22 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-05-18 | 58 | 42 | 2023-05-18 | 2023-05-18 | 1 | 1 | 37 | 27 | 59 | 43 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 671.05 | 671.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -513 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 978.01 | 359.3 | Unknown | Unknown | Unknown | 618.71 | 3981 | 400.91 | 978.01 | -577.1 | Yes | N/A | N/A | 2024-03-14 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2024-03-18 | 110 | 78 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-04-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-05-03 | 31 | 23 | 2024-05-03 | 2024-05-03 | 1 | 1 | 21 | 15 | 142 | 102 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | -530 | -379 | No | 2024-10-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-31 | 2025-03-04 | IOU Designed & Installed | N/A | Yes | 128 | 57.3 | Unknown | Unknown | Unknown | Unknown | 57.3 | 3981 | 3306.07 | 57.3 | 3248.77 | Yes | N/A | N/A | 2024-10-07 | 2025-02-10 | 127 | 91 | 2025-02-10 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2025-02-12 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-03-04 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-12 | 9 | 7 | 2025-03-12 | 2025-03-11 | Unknown | Unknown | 357 | 255 | 9 | 7 | 366 | 262 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1527 | 1092 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 736.47 | -13.14 | Unknown | Unknown | 1.98 | 747.63 | Unknown | 2645.95 | 736.47 | 1909.48 | Yes | N/A | N/A | 2023-11-28 | 2024-08-15 | 262 | 188 | 2024-08-15 | 2024-09-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-21 | 36 | 26 | 2024-09-05 | 2025-02-24 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-07 | 1 | 1 | 435 | 311 | 59 | 43 | 494 | 354 | Steps 2,3,5,6,7 | 138 | 98 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-22 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 0.36 | -5.02 | Unknown | Unknown | Unknown | 5.38 | 3981 | 882.47 | 0.36 | 882.11 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-12-18 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-21 | 35 | 25 | 2024-01-21 | 2023-12-20 | Unknown | Unknown | 41 | 29 | 36 | 26 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -333 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1270.54 | Unknown | Unknown | Unknown | 13.56 | 1256.98 | 3981 | 1667.92 | 1270.54 | 397.38 | Yes | N/A | N/A | 2024-06-17 | 2024-09-23 | 99 | 71 | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | 99 | 71 | 2 | 2 | 101 | 73 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-04 | -165 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-21 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 688.89 | -10.47 | Unknown | Unknown | 9.98 | 689.38 | 3941 | 627.67 | 688.89 | -61.22 | Yes | N/A | N/A | 2023-07-21 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-08-02 | 84 | 60 | 2023-08-02 | 2023-08-30 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-31 | 72 | 52 | Unknown | 2023-10-27 | Unknown | Unknown | 2023-10-31 | 2023-11-21 | 22 | 16 | 2023-11-21 | 2023-11-21 | 1 | 1 | 101 | 73 | 107 | 77 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-14 | 798 | 571 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-30 | 2022-06-30 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 3636.18 | 493.36 | Unknown | 82.65 | 180.54 | 2879.63 | 3885 | 323.12 | 3636.18 | -3313.06 | Yes | N/A | N/A | 2022-06-30 | 2025-03-10 | 985 | 703 | 2025-03-10 | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2022-07-11 | 2024-08-06 | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | 2024-08-06 | 2024-08-20 | 15 | 11 | 2024-08-20 | 2024-08-20 | 1 | 1 | 986 | 704 | 16 | 12 | 1002 | 716 | Steps 2,3,5,6,7 | 216 | 154 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.18 | -3.53 | Unknown | Unknown | Unknown | 2.35 | Unknown | 217.6 | -1.18 | 218.78 | Yes | N/A | N/A | 2022-12-28 | 2023-02-07 | 42 | 30 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-05-04 | 1 | 1 | 42 | 30 | 1 | 1 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 21 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-06-08 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 29725.92 | 10614.86 | Unknown | Unknown | 58.09 | 19052.97 | 162086 | 11945.76 | 29725.92 | -17780.16 | Yes | N/A | N/A | 2023-04-04 | 2023-04-04 | 1 | 1 | 2023-04-04 | 2023-11-28 | 239 | 171 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2958465 | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | 2024-06-11 | 2024-07-22 | 42 | 30 | 2024-07-22 | 2024-07-22 | 1 | 1 | 1 | 1 | 282 | 202 | 283 | 203 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -246 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 1152.39 | 315.3 | Unknown | Unknown | 60.13 | 776.96 | 7962 | 655.33 | 1152.39 | -497.06 | Yes | N/A | N/A | 2023-10-26 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-10-26 | 10 | 8 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2025-01-07 | 440 | 314 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-04-11 | 95 | 69 | 2025-04-11 | 2024-09-13 | Unknown | Unknown | 440 | 314 | 105 | 77 | 545 | 391 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -349 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 416.65 | -8.37 | Unknown | Unknown | Unknown | 425.02 | 7962 | 1676.55 | 416.65 | 1259.9 | Yes | N/A | N/A | 2025-02-27 | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2025-03-31 | 158 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-14 | 16 | 12 | 2025-03-31 | 2025-05-05 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 36 | 26 | 174 | 124 | 210 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | -535 | -382 | No | 2024-11-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-27 | 2025-02-28 | IOU Designed & Installed | N/A | Yes | 38 | -6.49 | -27.05 | Unknown | Unknown | Unknown | 20.56 | 3981 | 1603.66 | -6.49 | 1610.15 | Yes | N/A | N/A | 2024-11-01 | 2024-12-03 | 33 | 23 | 2024-12-03 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-02-28 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-27 | 28 | 20 | 2025-03-27 | 2025-03-27 | 1 | 1 | 127 | 91 | 29 | 21 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 967.05 | 967.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-31 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 3014.89 | 208.36 | Unknown | 406.7 | 47.29 | 2352.54 | 3981 | 1842.82 | 3014.89 | -1172.07 | Yes | N/A | N/A | 2024-07-24 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-08-23 | 85 | 61 | 2024-08-23 | 2024-09-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-12-17 | 117 | 83 | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-17 | 2024-12-19 | 3 | 3 | 2024-12-19 | 2024-12-19 | 1 | 1 | 131 | 93 | 89 | 65 | 220 | 158 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -317 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 3548.24 | 724.66 | Unknown | Unknown | 102.84 | 2720.74 | 3241 | 1040.16 | 3548.24 | -2508.08 | Yes | N/A | N/A | 2024-02-02 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2024-02-02 | 178 | 128 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-08-01 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-09-27 | 58 | 42 | 2024-09-27 | 2024-09-26 | Unknown | Unknown | 182 | 130 | 236 | 170 | 418 | 300 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | LA JOLLA | SAN DIEGO | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -82 | -59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3042.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2025-01-22 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-24 | 27 | 19 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-10 | 2 | 2 | 2025-06-10 | 2025-06-10 | 1 | 1 | 0 | 0 | 109 | 79 | 109 | 79 | Steps 2,3,5,6,7 | 33 | 23 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2028-08-31 | -1365 | -976 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-11-21 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 7694.8 | 2283.33 | Unknown | Unknown | Unknown | 5411.47 | 3981 | 616.97 | 7694.8 | -7077.83 | Yes | N/A | N/A | 2023-08-22 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2024-01-22 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-08-14 | 206 | 148 | Unknown | 2024-10-31 | Unknown | Unknown | 2024-11-05 | 2024-12-06 | 32 | 24 | 2024-12-06 | 2024-12-05 | Unknown | Unknown | 206 | 148 | 205 | 147 | 411 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -75 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 2412.47 | 254.7 | Unknown | 56.75 | 30.18 | 2070.84 | 3981 | 1057.67 | 2412.47 | -1354.8 | Yes | N/A | N/A | 2024-03-07 | 2024-04-22 | 47 | 33 | 2024-04-22 | 2024-06-04 | 44 | 32 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2025-04-09 | 310 | 222 | Unknown | 2025-03-28 | Unknown | Unknown | 2025-04-09 | 2025-04-21 | 13 | 9 | 2025-04-21 | 2025-04-21 | 1 | 1 | 357 | 255 | 58 | 42 | 415 | 297 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -544 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2024-02-08 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 1466.25 | 19.17 | Unknown | Unknown | Unknown | 1447.08 | Unknown | 558.25 | 1466.25 | -908 | Yes | N/A | N/A | 2023-11-29 | 2024-01-09 | 42 | 30 | 2024-01-09 | 2024-05-06 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-05-03 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-20 | 14 | 10 | 2024-05-20 | 2024-05-20 | 1 | 1 | 42 | 30 | 149 | 107 | 191 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-11 | 253 | 182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 61112.32 | 11591.92 | Unknown | Unknown | 5054.25 | 44466.15 | 0 | 12421.33 | 61112.32 | -48690.99 | Yes | N/A | N/A | 2023-01-12 | 2023-07-11 | 181 | 129 | 2023-07-11 | 2023-09-20 | 72 | 52 | 2023-07-17 | 2024-06-04 | 59 | 41 | 2023-09-20 | 2023-10-02 | 13 | 9 | 2024-07-29 | Unknown | Unknown | Unknown | 2024-07-29 | 2025-01-06 | 162 | 116 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 240 | 170 | 248 | 178 | 488 | 348 | Steps 2,3,5,6,7 | 323 | 231 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 940 | 673 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 144038.46 | 6635.42 | Unknown | Unknown | 26935.33 | 110467.71 | 0 | 100561.37 | 144038.46 | -43477.09 | Yes | N/A | N/A | 2022-09-01 | 2023-07-26 | 329 | 235 | 2023-07-26 | 2023-10-06 | 73 | 53 | 2023-08-10 | 2024-04-08 | 22 | 16 | 2023-08-10 | 2023-10-17 | 22 | 16 | 2023-10-11 | Unknown | Unknown | Unknown | 2023-10-11 | 2024-04-03 | 176 | 126 | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-08-29 | 1 | 1 | 351 | 251 | 272 | 196 | 623 | 447 | Steps 2,3,5,6,7 | 305 | 217 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 87.4 | 87.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | -9.74 | -7.14 | Unknown | Unknown | Unknown | -2.6 | Unknown | 497.98 | -9.74 | 507.72 | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-10-06 | 25 | 19 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-23 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-11-08 | 17 | 13 | 2023-11-08 | 2023-11-08 | 1 | 1 | 19 | 13 | 43 | 33 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | 299 | 214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 551.72 | -11.09 | Unknown | Unknown | Unknown | 562.81 | 17193 | 1867.4 | 551.72 | 1315.68 | Yes | N/A | N/A | 2024-01-10 | 2024-02-13 | 35 | 25 | 2024-02-13 | 2024-05-31 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-12 | 18 | 14 | 2024-05-31 | 2025-03-25 | 299 | 213 | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 334 | 238 | 128 | 94 | 462 | 332 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -429 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.16 | -17.67 | Unknown | Unknown | Unknown | 18.83 | 3981 | 642.02 | 1.16 | 640.86 | Yes | N/A | N/A | 2023-03-20 | 2023-03-30 | 11 | 9 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2023-12-21 | 1 | 1 | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-29 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 1893.46 | 24.11 | Unknown | Unknown | 0.99 | 1868.36 | 3981 | 1490.81 | 1893.46 | -402.65 | Yes | N/A | N/A | 2025-04-28 | 2025-04-29 | 2 | 2 | 2025-04-29 | 2025-06-10 | 43 | 31 | 2025-06-10 | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-05-08 | 2025-06-10 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-11 | 2 | 2 | 2025-06-11 | 2025-06-11 | 1 | 1 | 36 | 26 | 64 | 48 | 100 | 74 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | Unknown | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 611.48 | -11.7 | Unknown | Unknown | Unknown | 623.18 | 3981 | 1431.4 | 611.48 | 819.92 | Yes | N/A | N/A | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-26 | 39 | 29 | 2024-08-19 | 2024-09-13 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-20 | 8 | 6 | 2024-09-20 | 2024-09-23 | 4 | 2 | 27 | 21 | 52 | 38 | 79 | 59 | Steps 2,3,5,6,7 | 38 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | -603 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-10-10 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 882.06 | 441.81 | Unknown | 176.88 | Unknown | 263.37 | Unknown | 514.57 | 882.06 | -367.49 | Yes | N/A | N/A | 2023-09-27 | 2023-10-10 | 14 | 10 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-11-03 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | 2023-11-03 | 1 | 1 | 39 | 29 | 3 | 3 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-09 | -565 | -404 | No | 2024-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-22 | 2024-05-21 | IOU Designed & Installed | N/A | Yes | 59 | 2925.97 | -6.54 | Unknown | Unknown | 4.48 | 2928.03 | 3981 | 767.8 | 2925.97 | -2158.17 | Yes | N/A | N/A | 2024-02-06 | 2024-04-04 | 59 | 43 | 2024-04-04 | 2024-04-05 | 2 | 2 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-05-21 | 76 | 54 | Unknown | 2024-05-16 | Unknown | Unknown | 2024-05-21 | 2024-05-23 | 3 | 3 | 2024-05-23 | 2024-05-23 | 1 | 1 | 135 | 97 | 6 | 6 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -507 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 1044.99 | 367.35 | Unknown | Unknown | Unknown | 677.64 | 3981 | 1501.91 | 1044.99 | 456.92 | Yes | N/A | N/A | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-10-18 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-24 | 7 | 5 | 2023-10-24 | 2023-10-24 | 1 | 1 | 37 | 27 | 9 | 7 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15.35 | 15.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-09-25 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 2987.35 | 855.19 | Unknown | 471.68 | 59.34 | 1601.14 | 11943 | 569.87 | 2987.35 | -2417.48 | Yes | N/A | N/A | 2023-06-12 | 2023-09-22 | 103 | 75 | 2023-09-22 | 2023-09-22 | 1 | 1 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2024-03-26 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-18 | 24 | 18 | 2024-04-18 | 2024-04-18 | 1 | 1 | 287 | 207 | 26 | 20 | 313 | 227 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 922 | 922 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -498 | -357 | No | 2024-09-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-03-21 | IOU Designed & Installed | N/A | Yes | 156 | 2318.15 | -61.75 | Unknown | Unknown | Unknown | 2379.9 | 3981 | 1589.1 | 2318.15 | -729.05 | Yes | N/A | N/A | 2024-09-17 | 2025-02-20 | 157 | 113 | 2025-02-20 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2025-03-21 | 186 | 134 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-09 | 20 | 14 | 2025-04-09 | 2025-04-08 | Unknown | Unknown | 343 | 247 | 20 | 14 | 363 | 261 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 130 | 130 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | 17 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 276.56 | -3.68 | Unknown | Unknown | 1.07 | 279.17 | 7962 | 1683.55 | 276.56 | 1406.99 | Yes | N/A | N/A | 2024-10-25 | 2024-10-25 | 1 | 1 | 2024-10-25 | 2024-10-31 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-26 | 33 | 23 | 2024-10-31 | 2024-11-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-01-17 | Unknown | Unknown | 9 | 7 | 40 | 28 | 49 | 35 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-23 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 324.28 | -14.85 | Unknown | Unknown | -479 | 818.13 | 3981 | 1631.85 | 324.28 | 1307.57 | Yes | N/A | N/A | 2024-04-29 | 2024-06-11 | 44 | 32 | 2024-06-11 | 2024-06-12 | 2 | 2 | 2024-06-12 | 2024-08-26 | 76 | 54 | 2024-05-01 | 2024-06-06 | 37 | 27 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 120 | 86 | 40 | 30 | 160 | 116 | Steps 2,3,5,6,7 | 117 | 83 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | 444.43 | Unknown | Unknown | Unknown | 1.53 | 442.9 | 3981 | 2576.65 | 444.43 | 2132.22 | Yes | N/A | N/A | 2025-03-20 | 2025-05-01 | 43 | 31 | 2025-05-01 | 2025-05-05 | 5 | 3 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-06-25 | 52 | 38 | Unknown | 2025-06-17 | Unknown | Unknown | 2025-06-25 | 2025-06-26 | 2 | 2 | 2025-06-26 | 2025-06-26 | 1 | 1 | 95 | 69 | 8 | 6 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community,Tribal Community | PV 1052-f7 | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | 351 | 251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-12-13 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 32989.45 | 3188.57 | Unknown | Unknown | -14723.53 | 44524.41 | 0 | 26996.9 | 32989.45 | -5992.55 | Yes | N/A | N/A | 2023-10-12 | 2023-10-13 | 2 | 2 | 2023-10-13 | 2024-09-17 | 341 | 243 | 2024-01-08 | 2024-08-16 | 3 | 3 | 2024-02-07 | 2024-09-23 | 25 | 19 | 2024-09-17 | Unknown | Unknown | Unknown | 2024-10-03 | 2025-01-21 | 111 | 79 | 2025-02-05 | 2025-03-17 | 41 | 29 | 2025-03-17 | 2025-03-17 | 1 | 1 | 5 | 5 | 519 | 371 | 524 | 376 | Steps 2,3,5,6,7 | 450 | 322 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3787 | 3787 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-08-20 | 347 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-09-14 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 32.47 | -11.09 | Unknown | Unknown | 32.05 | 11.51 | 3941 | 661.04 | 32.47 | 628.57 | Yes | N/A | N/A | 2023-08-01 | 2023-09-14 | 45 | 33 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | 2023-09-18 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-27 | 14 | 10 | Unknown | 2023-09-26 | Unknown | Unknown | 2023-09-27 | 2024-07-26 | 304 | 218 | 2024-07-26 | 2024-08-01 | 7 | 5 | 64 | 46 | 312 | 224 | 376 | 270 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -513 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-12-29 | IOU Designed & Installed | N/A | No | N/A | 1151.27 | 709.34 | Unknown | 65.07 | Unknown | 376.86 | 3961 | 158.79 | 1151.27 | -992.48 | Yes | N/A | N/A | 2023-10-13 | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-12-28 | 154 | 110 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2023-12-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-01-09 | 12 | 8 | 2024-01-09 | 2024-01-09 | 1 | 1 | 2 | 2 | 167 | 119 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1485 | 1062 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-10 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 19254.34 | 6223.35 | Unknown | 692.89 | Unknown | 12338.1 | Unknown | 2843.22 | 19254.34 | -16411.12 | Yes | N/A | N/A | 2023-08-09 | 2023-10-10 | 63 | 45 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | 2024-01-18 | 2024-01-24 | 7 | 5 | 2024-01-24 | 2024-01-24 | 1 | 1 | 63 | 45 | 8 | 6 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -20 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 35020.55 | 327.76 | Unknown | 49.18 | Unknown | 34643.61 | 2113167 | 19316.05 | 35020.55 | -15704.5 | Yes | N/A | N/A | 2023-12-13 | 2024-04-02 | 112 | 80 | 2024-04-02 | 2024-05-16 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2025-03-11 | 300 | 214 | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-16 | 2025-02-24 | 40 | 28 | 2025-02-24 | 2025-01-23 | Unknown | Unknown | 412 | 294 | 85 | 61 | 497 | 355 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | -6.07 | -10.09 | Unknown | Unknown | -825.04 | 829.06 | Unknown | 825.8 | -6.07 | 831.87 | Yes | N/A | N/A | 2024-01-19 | 2024-02-08 | 21 | 15 | 2024-02-08 | 2024-02-09 | 2 | 2 | 2024-02-09 | 2024-02-20 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-04 | 14 | 10 | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 12 | 10 | 2024-03-15 | 2024-03-15 | 1 | 1 | 47 | 33 | 15 | 13 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1181.01 | 1499.3 | Unknown | 469.17 | -1424 | 636.54 | Unknown | 1423.67 | 1181.01 | 242.66 | Yes | N/A | N/A | 2023-06-20 | 2023-06-22 | 3 | 3 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 9.89 | Unknown | Unknown | Unknown | Unknown | 9.89 | Unknown | 1855.26 | 9.89 | 1845.37 | Yes | N/A | N/A | 2024-06-06 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-06-06 | 9 | 7 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-23 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-25 | 3 | 3 | 2024-07-25 | 2024-07-25 | 1 | 1 | 48 | 34 | 13 | 11 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-29 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 5.82 | Unknown | Unknown | Unknown | Unknown | 5.82 | 3981 | 1143.81 | 5.82 | 1137.99 | Yes | N/A | N/A | 2024-04-17 | 2024-04-29 | 13 | 9 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-07-17 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-05 | 20 | 14 | 2024-08-05 | 2024-08-05 | 1 | 1 | 93 | 67 | 22 | 16 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2024-06-06 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | -9594.39 | 1393.8 | Unknown | 621.56 | -12501 | 891.25 | Unknown | 12500.76 | -9594.39 | 22095.15 | Yes | N/A | N/A | 2023-09-19 | 2024-06-13 | 269 | 193 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-23 | 40 | 28 | 2024-07-23 | 2024-06-19 | Unknown | Unknown | 269 | 193 | 40 | 28 | 309 | 221 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | -669 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-07 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 886.03 | 533.76 | Unknown | Unknown | Unknown | 352.27 | Unknown | 118.25 | 886.03 | -767.78 | Yes | N/A | N/A | 2025-05-06 | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-07 | 7 | 5 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-27 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-04 | 9 | 7 | 2025-06-04 | 2025-06-04 | 1 | 1 | 21 | 15 | 17 | 13 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-18 | -109 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -974.1 | Unknown | Unknown | Unknown | -1110 | 135.9 | 0 | 1109.76 | -974.1 | 2083.86 | Yes | N/A | N/A | 2023-11-10 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-12-05 | 99 | 71 | 2023-12-05 | 2023-12-14 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-01 | 1 | 1 | 10 | 8 | 100 | 72 | 110 | 80 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-03 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8898.91 | Unknown | Unknown | Unknown | 2.83 | 8896.08 | 3981 | 2093.23 | 8898.91 | -6805.68 | Yes | N/A | N/A | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 49.31 | Unknown | Unknown | Unknown | Unknown | 49.31 | Unknown | 1677.69 | 49.31 | 1628.38 | Yes | N/A | N/A | 2024-06-25 | 2024-08-07 | 44 | 32 | 2024-08-07 | 2024-09-06 | 31 | 23 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-11-01 | 1 | 1 | 44 | 32 | 32 | 24 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Underserved Community | Escondido | N/A | 160 | 160 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 305 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-01-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 51547.24 | 2409.48 | Unknown | Unknown | 133.41 | 49004.35 | 47365 | Not available | 51547.24 | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-02 | 6 | 4 | 2023-10-02 | 2023-10-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-01-31 | 16 | 12 | 2024-01-31 | 2024-01-31 | 1 | 1 | 6 | 4 | 32 | 24 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-11-07 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 10.52 | Unknown | Unknown | Unknown | Unknown | 10.52 | Unknown | 1576.54 | 10.52 | 1566.02 | Yes | N/A | N/A | 2024-10-30 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-11-07 | 24 | 18 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-21 | 14 | 10 | 2024-11-21 | 2024-11-21 | 1 | 1 | 2 | 2 | 39 | 29 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 822.77 | -12.16 | Unknown | Unknown | Unknown | 834.93 | 8703 | 518.49 | 822.77 | -304.28 | Yes | N/A | N/A | 2023-12-26 | 2023-12-26 | 1 | 1 | 2023-12-26 | 2023-12-29 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-11-08 | 316 | 226 | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 317 | 227 | 4 | 4 | 321 | 231 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-20 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 78.25 | -0.31 | Unknown | Unknown | Unknown | 78.56 | Unknown | 1706.51 | 78.25 | 1628.26 | Yes | N/A | N/A | 2024-12-19 | 2024-12-08 | Unknown | Unknown | 2024-12-08 | 2024-12-20 | 13 | 10 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-29 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-18 | 21 | 15 | 2025-02-18 | 2025-02-18 | 1 | 1 | 41 | 29 | 35 | 26 | 76 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-09 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 3032.79 | 489.8 | Unknown | 286.15 | Unknown | 2256.84 | 3981 | 992.53 | 3032.79 | -2040.26 | Yes | N/A | N/A | 2024-05-07 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-09 | 37 | 27 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-06 | 29 | 21 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-06 | 2024-06-11 | 6 | 4 | 2024-06-11 | 2024-06-11 | 1 | 1 | 29 | 21 | 44 | 32 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-16 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 726.87 | Unknown | Unknown | Unknown | Unknown | 726.87 | 3981 | 1080.07 | 726.87 | 353.2 | Yes | N/A | N/A | 2024-07-01 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-07-16 | 47 | 33 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-09-11 | 58 | 42 | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-11 | 2024-09-23 | 13 | 9 | 2024-09-23 | 2024-09-23 | 1 | 1 | 58 | 42 | 61 | 43 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-12 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 1492.78 | 364.96 | Unknown | 53.64 | Unknown | 1074.18 | Unknown | 1480.23 | 1492.78 | -12.55 | Yes | N/A | N/A | 2024-07-08 | 2024-07-12 | 5 | 5 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2025-01-24 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-27 | 4 | 2 | 2025-01-27 | 2025-01-27 | 1 | 1 | 202 | 146 | 6 | 4 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-22 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-11 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 1466.95 | Unknown | Unknown | Unknown | 11.37 | 1455.58 | 3981 | 1098.48 | 1466.95 | -368.47 | Yes | N/A | N/A | 2024-08-01 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-08-11 | 42 | 30 | 2024-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-11 | 2025-06-23 | 317 | 226 | Unknown | 2025-06-13 | Unknown | Unknown | 2025-06-23 | 2025-06-27 | 5 | 5 | 2025-06-27 | 2025-06-27 | 1 | 1 | 317 | 226 | 48 | 36 | 365 | 262 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | -152 | -109 | No | 2023-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2024-02-28 | IOU Designed & Installed | N/A | Yes | 243 | 5067.52 | -31.61 | Unknown | Unknown | 25.24 | 5073.89 | 3241 | 1873.63 | 5067.52 | -3193.89 | Yes | N/A | N/A | 2023-02-15 | 2023-10-16 | 244 | 174 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2024-02-28 | 286 | 204 | Unknown | 2024-02-16 | Unknown | Unknown | 2024-02-28 | 2024-04-23 | 56 | 40 | 2024-04-23 | 2024-04-16 | Unknown | Unknown | 530 | 378 | 56 | 40 | 586 | 418 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 24.05 | 24.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 275.72 | -6.88 | Unknown | Unknown | 1.81 | 280.79 | 3981 | 2214.7 | 275.72 | 1938.98 | Yes | N/A | N/A | 2024-01-09 | 2024-01-24 | 16 | 12 | 2024-01-24 | 2024-02-01 | 9 | 7 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-05-10 | 100 | 72 | Unknown | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-05-22 | 13 | 9 | 2024-05-22 | 2024-05-22 | 1 | 1 | 116 | 84 | 23 | 17 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 22.13 | -19.65 | Unknown | Unknown | Unknown | 41.78 | 3241 | 887.91 | 22.13 | 865.78 | Yes | N/A | N/A | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-13 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-03 | 22 | 16 | 2024-04-03 | 2024-04-03 | 1 | 1 | 32 | 24 | 24 | 18 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Rancho Santa Fe | N/A | 2382 | 2382 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-15 | -198 | -143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 14868.56 | 3301.84 | Unknown | Unknown | 31.14 | 11535.58 | 2947.03 | 11362.57 | 14868.56 | -3505.99 | Yes | N/A | N/A | 2023-04-28 | 2023-03-24 | Unknown | Unknown | 2023-03-24 | 2023-07-10 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-17 | 8 | 6 | 2023-07-10 | Unknown | Unknown | Unknown | 2023-08-02 | 2024-04-23 | 266 | 190 | 2024-04-25 | 2024-05-01 | 7 | 5 | 2024-05-01 | 2024-05-01 | 1 | 1 | 0 | 0 | 391 | 279 | 391 | 279 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 107.75 | 107.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -170 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-09-08 | 2023-12-08 | IOU Designed & Installed | N/A | No | N/A | 2819.2 | 928.6 | Unknown | 211.63 | Unknown | 1678.97 | 3981 | 1734.28 | 2819.2 | -1084.92 | Yes | N/A | N/A | 2023-08-25 | 2023-09-08 | 15 | 11 | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-12-08 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-12 | 5 | 3 | 2023-12-12 | 2024-12-12 | 367 | 263 | 107 | 77 | 373 | 267 | 480 | 344 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-24 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 679.94 | 232.94 | Unknown | 41.6 | Unknown | 405.4 | Unknown | 783.58 | 679.94 | 103.64 | Yes | N/A | N/A | 2023-04-21 | 2023-04-25 | 5 | 3 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-06-23 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-26 | 4 | 2 | 2023-06-26 | 2023-06-26 | 1 | 1 | 65 | 47 | 5 | 3 | 70 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -613 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-27 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 93.21 | -15.4 | Unknown | Unknown | 0.45 | 108.16 | 3981 | 1024.22 | 93.21 | 931.01 | Yes | N/A | N/A | 2024-03-14 | 2024-03-25 | 12 | 8 | 2024-03-25 | 2024-03-27 | 3 | 3 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-05 | 56 | 40 | 2024-06-05 | 2024-05-06 | Unknown | Unknown | 28 | 20 | 59 | 43 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-06 | 648 | 463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1079.3 | 1891.66 | Unknown | 526.05 | -4271 | 773.99 | 0 | 4270.94 | -1079.3 | 5350.24 | Yes | N/A | N/A | 2023-06-01 | 2023-06-02 | 2 | 2 | 2023-06-02 | 2023-06-19 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2 | 2 | 19 | 13 | 21 | 15 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -467 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6283.26 | 310.52 | Unknown | Unknown | Unknown | 5972.74 | Unknown | 13773.45 | 6283.26 | 7490.19 | Yes | N/A | N/A | 2023-03-01 | 2023-08-11 | 164 | 118 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-08-21 | 11 | 7 | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2023-10-04 | 1 | 1 | 164 | 118 | 12 | 8 | 176 | 126 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | RA 1171-H1 | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-04 | 225 | 162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-11-06 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 16731.94 | 4738.92 | Unknown | Unknown | 26.01 | 11967.01 | 54898 | 23730.13 | 16731.94 | 6998.19 | Yes | N/A | N/A | 2023-09-05 | 2023-09-22 | 18 | 14 | 2023-09-22 | 2024-03-06 | 167 | 119 | 2024-01-23 | 2024-02-22 | 10 | 8 | 2024-02-23 | 2024-10-18 | 7 | 5 | 2024-03-21 | Unknown | Unknown | Unknown | 2024-03-21 | 2025-02-20 | 337 | 241 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-04-17 | 1 | 1 | 28 | 22 | 513 | 367 | 541 | 389 | Steps 2,3,5,6,7 | 254 | 182 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-23 | -846 | -605 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -14.35 | -10.39 | Unknown | Unknown | Unknown | -3.96 | Unknown | 364.52 | -14.35 | 378.87 | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | 325 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 11.85 | -10.49 | Unknown | Unknown | Unknown | 22.34 | 3941 | 746.85 | 11.85 | 735 | Yes | N/A | N/A | 2023-07-27 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-07-27 | 4 | 4 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2024-04-19 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-05-17 | 29 | 21 | 2024-05-17 | 2024-05-20 | 4 | 2 | 268 | 192 | 37 | 27 | 305 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -95 | -69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-05-06 | 2025-06-14 | IOU Designed & Installed | N/A | No | N/A | 1197.38 | Unknown | Unknown | Unknown | 1.34 | 1196.04 | 3981 | 1606.22 | 1197.38 | 408.84 | Yes | N/A | N/A | 2024-01-30 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-09-27 | 344 | 246 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-18 | 31 | 23 | 2024-09-27 | 2025-03-25 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-06-14 | 2025-06-17 | 4 | 2 | 2025-06-17 | 2025-06-17 | 1 | 1 | 180 | 128 | 380 | 272 | 560 | 400 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-27 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 1009.93 | 513.16 | Unknown | 161.3 | Unknown | 335.47 | 3981 | 625.16 | 1009.93 | -384.77 | Yes | N/A | N/A | 2023-07-19 | 2023-07-27 | 9 | 7 | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-10-13 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-25 | 13 | 9 | 2023-10-25 | 2023-10-25 | 1 | 1 | 88 | 64 | 15 | 11 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -854 | -611 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -26.19 | -13.1 | Unknown | Unknown | Unknown | -13.09 | Unknown | 341 | -26.19 | 367.19 | Yes | N/A | N/A | 2023-03-13 | 2023-03-13 | 1 | 1 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 197 | 197 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | 22 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-29 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 6806.58 | -1.1 | Unknown | Unknown | -268 | 7075.68 | 0 | 268.33 | 6806.58 | -6538.25 | Yes | N/A | N/A | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-05-31 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-01 | 26 | 18 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2025-02-24 | 267 | 191 | 2025-02-24 | 2025-02-24 | 1 | 1 | 1 | 1 | 388 | 278 | 389 | 279 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-21 | -1316 | -941 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 248.96 | -12.62 | Unknown | Unknown | Unknown | 261.58 | 0 | 545.51 | 248.96 | 296.55 | Yes | N/A | N/A | 2023-04-10 | 2023-04-10 | 1 | 1 | 2023-04-10 | 2023-04-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | 8994 | 8994 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-01 | -423 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-07-31 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 14.78 | Unknown | Unknown | Unknown | Unknown | 14.78 | Unknown | 449.58 | 14.78 | 434.8 | Yes | N/A | N/A | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | 2024-08-21 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-15 | 15 | 11 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-04 | 10 | 8 | 2024-09-04 | 2024-09-04 | 1 | 1 | 1 | 1 | 83 | 61 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | VALLEY CENTER | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -83 | -60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-29 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 10170.72 | Unknown | Unknown | Unknown | Unknown | 10170.72 | 3981 | 945.17 | 10170.72 | -9225.55 | Yes | N/A | N/A | 2024-01-25 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2024-03-08 | 297 | 213 | 2024-02-29 | 2024-03-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-07-11 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-27 | 44 | 32 | 2024-08-27 | 2024-08-05 | Unknown | Unknown | 128 | 92 | 341 | 245 | 469 | 337 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-04 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 836.1 | Unknown | Unknown | Unknown | Unknown | 836.1 | 3981 | 1179.63 | 836.1 | 343.53 | Yes | N/A | N/A | 2024-06-20 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-06-20 | 3 | 3 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-11-25 | 1 | 1 | 0 | 0 | 4 | 4 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-11 | -436 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 19.69 | Unknown | Unknown | Unknown | Unknown | 19.69 | Unknown | 990.9 | 19.69 | 971.21 | Yes | N/A | N/A | 2024-02-09 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-09 | 99 | 71 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-07-26 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-01 | 7 | 5 | 2024-08-01 | 2024-08-01 | 1 | 1 | 169 | 121 | 107 | 77 | 276 | 198 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | -88 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 553.61 | -8.43 | Unknown | Unknown | -729.17 | 1291.21 | Unknown | 751.7 | 553.61 | 198.09 | Yes | N/A | N/A | 2023-09-29 | 2023-12-01 | 64 | 46 | 2023-12-01 | 2023-12-04 | 4 | 2 | 2023-12-04 | 2024-01-12 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-03-14 | 63 | 45 | Unknown | 2024-03-12 | Unknown | Unknown | 2024-03-14 | 2024-04-02 | 20 | 14 | 2024-04-02 | 2024-04-02 | 1 | 1 | 167 | 121 | 25 | 17 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-07-07 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | -1109.98 | -17.63 | Unknown | Unknown | -1101 | 8.65 | 7704.36 | 2252.68 | -1109.98 | 3362.66 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-07-07 | 17 | 13 | 2023-07-07 | 2023-08-08 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-09-11 | 35 | 25 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-11 | 2023-09-15 | 5 | 5 | 2023-09-15 | 2023-09-15 | 1 | 1 | 69 | 49 | 23 | 19 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-15 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 1013.16 | 1717.57 | Unknown | Unknown | -5303.56 | 4599.15 | Unknown | 5304.33 | 1013.16 | 4291.17 | Yes | N/A | N/A | 2025-04-02 | 2025-04-08 | 7 | 5 | 2025-04-08 | 2025-05-28 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-05-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | 2025-06-05 | 1 | 1 | 8 | 6 | 53 | 39 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 3466.16 | 822.43 | Unknown | Unknown | Unknown | 2643.73 | 3981 | 1634.89 | 3466.16 | -1831.27 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-12-02 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2024-12-02 | 1 | 1 | 29 | 21 | 3 | 3 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | -626 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-22 | 2024-03-22 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | -7.54 | -11.78 | Unknown | Unknown | Unknown | 4.24 | 3981 | 1231.14 | -7.54 | 1238.68 | Yes | N/A | N/A | 2024-03-22 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-03-22 | 38 | 28 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-15 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-22 | 38 | 28 | 2024-05-22 | 2024-05-22 | 1 | 1 | 25 | 17 | 77 | 57 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA HILLS | COUNTY OF ORANGE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-16 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 493.11 | Unknown | Unknown | Unknown | Unknown | 493.11 | Unknown | 444.8 | 493.11 | -48.31 | Yes | N/A | N/A | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-07-23 | 7 | 5 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-21 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | 243 | 174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-30 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | -217.05 | 224.92 | Unknown | Unknown | -1575 | 1133.03 | 0 | 1821.97 | -217.05 | 2039.02 | Yes | N/A | N/A | 2024-04-29 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-12-06 | 290 | 208 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-12-06 | 44 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-21 | 20 | 14 | 2025-05-21 | 2025-05-21 | 1 | 1 | 0 | 0 | 355 | 253 | 355 | 253 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | Unknown | Unknown | IOU Designed & Installed | N/A | No | N/A | 105.54 | Unknown | Unknown | Unknown | Unknown | 105.54 | 3981 | 1635.65 | 105.54 | 1530.11 | Yes | N/A | N/A | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-25 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-12 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 2056 | -39.51 | Unknown | Unknown | Unknown | 2095.51 | Unknown | 1526.94 | 2056 | -529.06 | Yes | N/A | N/A | 2024-07-24 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-08-12 | 60 | 42 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2025-02-11 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-18 | 36 | 26 | 2025-03-18 | 2025-03-18 | 1 | 1 | 184 | 132 | 97 | 69 | 281 | 201 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-16 | 564 | 403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 423.2 | -7.37 | Unknown | Unknown | Unknown | 430.57 | 3981 | 1593.74 | 423.2 | 1170.54 | Yes | N/A | N/A | 2022-07-29 | 2024-01-04 | 525 | 375 | 2024-01-04 | 2024-08-13 | 223 | 159 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-12 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-09-30 | Unknown | Unknown | 525 | 375 | 232 | 166 | 757 | 541 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | 707 | 506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-03-07 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 11122.73 | 272.1 | Unknown | Unknown | -770 | 11620.63 | 7605 | 1038.29 | 11122.73 | -10084.44 | Yes | N/A | N/A | 2023-01-10 | 2023-02-22 | 44 | 32 | 2023-02-22 | 2024-01-11 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | 2024-08-29 | 2024-10-10 | 43 | 31 | 2024-10-10 | 2024-10-08 | Unknown | Unknown | 44 | 32 | 367 | 263 | 411 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.2 | Unknown | Unknown | Unknown | Unknown | 12.2 | 3981 | 105.08 | 12.2 | 92.88 | Yes | N/A | N/A | 2024-12-13 | 2024-12-20 | 8 | 6 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-09 | 1 | 1 | 8 | 6 | 2 | 2 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | -303 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 248.14 | -5.21 | Unknown | Unknown | Unknown | 253.35 | 3241 | 683.36 | 248.14 | 435.22 | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-14 | 5 | 3 | 2023-08-14 | 2023-08-14 | 1 | 1 | 2 | 2 | 7 | 5 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | 218 | 157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 1098.62 | Unknown | Unknown | Unknown | 36.27 | 1062.35 | 3981 | 1001.91 | 1098.62 | -96.71 | Yes | N/A | N/A | 2024-03-13 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-06-04 | 125 | 89 | 2024-05-31 | 2024-05-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-10-14 | 133 | 95 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-14 | 2024-10-21 | 8 | 6 | 2024-10-21 | 2024-10-18 | Unknown | Unknown | 134 | 96 | 133 | 95 | 267 | 191 | Steps 2,3,5,6,7 | 4 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-04 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 1272.36 | 737.67 | Unknown | 24.17 | Unknown | 510.52 | Unknown | 192.83 | 1272.36 | -1079.53 | Yes | N/A | N/A | 2024-06-03 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-06-04 | 20 | 14 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-02 | 26 | 18 | 2024-07-02 | 2024-07-02 | 1 | 1 | 4 | 4 | 47 | 33 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-24 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | Unknown | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 626.19 | -11.7 | Unknown | Unknown | Unknown | 637.89 | 3981 | 1554.46 | 626.19 | 928.27 | Yes | N/A | N/A | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-25 | 28 | 20 | 2024-08-29 | 2024-10-14 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-23 | 10 | 8 | 2024-10-23 | 2024-10-23 | 1 | 1 | 48 | 34 | 40 | 30 | 88 | 64 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 89 | 89 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-15 | 370 | 265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2024-03-29 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 44.98 | Unknown | Unknown | Unknown | Unknown | 44.98 | Unknown | 912.77 | 44.98 | 867.79 | Yes | N/A | N/A | 2023-10-25 | 2024-03-28 | 156 | 112 | 2024-03-28 | 2024-03-29 | 2 | 2 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-08-15 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-19 | 5 | 3 | 2024-08-19 | 2024-08-19 | 1 | 1 | 296 | 212 | 8 | 6 | 304 | 218 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -253 | -182 | No | 2024-04-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-08 | 2025-06-18 | IOU Designed & Installed | N/A | Yes | 387 | 1472.8 | 774.73 | Unknown | Unknown | -1523 | 2221.07 | Unknown | 1390.21 | 1472.8 | -82.59 | Yes | N/A | N/A | 2024-04-03 | 2025-04-25 | 388 | 278 | 2025-04-25 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2025-05-16 | 374 | 268 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-06-18 | 407 | 291 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 1169 | 837 | 2 | 2 | 1171 | 839 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -372 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 215.54 | 128.54 | Unknown | Unknown | Unknown | 87 | Unknown | 709.65 | 215.54 | 494.11 | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-14 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-05 | 20 | 14 | 2025-03-05 | 2025-03-05 | 1 | 1 | 4 | 4 | 22 | 16 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1129.25 | -14.21 | Unknown | Unknown | -424.57 | 1568.03 | 0 | 456.31 | 1129.25 | -672.94 | Yes | N/A | N/A | 2023-04-21 | 2023-04-21 | 1 | 1 | 2023-04-21 | 2023-10-11 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2025-04-17 | 555 | 397 | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 556 | 398 | 174 | 124 | 730 | 522 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-08 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 4595.97 | 1152.04 | Unknown | 74.46 | 11.4 | 3358.07 | 3981 | 1248.72 | 4595.97 | -3347.25 | Yes | N/A | N/A | 2024-05-03 | 2024-05-16 | 14 | 10 | 2024-05-16 | 2024-06-07 | 23 | 17 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-11-19 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-02 | 14 | 10 | 2024-12-02 | 2024-12-02 | 1 | 1 | 180 | 128 | 38 | 28 | 218 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -239 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 19.49 | Unknown | Unknown | Unknown | Unknown | 19.49 | 0 | 958.48 | 19.49 | 938.99 | Yes | N/A | N/A | 2023-11-13 | 2023-08-27 | Unknown | Unknown | 2023-08-27 | 2023-11-21 | 87 | 62 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-20 | 1 | 1 | 0 | 0 | 88 | 63 | 88 | 63 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | -21 | -16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2023-05-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1070.06 | -14.15 | Unknown | Unknown | -1086 | 30.09 | 7866 | 1831.75 | -1070.06 | 2901.81 | Yes | N/A | N/A | 2022-11-08 | 2023-05-09 | 183 | 131 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-04-04 | 1 | 1 | 183 | 131 | 1 | 1 | 184 | 132 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -415 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-21 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 2208.84 | 445.08 | Unknown | Unknown | Unknown | 1763.76 | Unknown | 599.43 | 2208.84 | -1609.41 | Yes | N/A | N/A | 2024-05-20 | 2024-05-21 | 2 | 2 | 2024-05-21 | 2024-06-07 | 18 | 14 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2025-01-14 | 239 | 171 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-01-14 | 1 | 1 | 241 | 173 | 20 | 16 | 261 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -617 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-03 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1780.67 | 321.36 | Unknown | Unknown | Unknown | 1459.31 | 0 | 311.78 | 1780.67 | -1468.89 | Yes | N/A | N/A | 2025-01-03 | 2024-01-07 | Unknown | Unknown | 2024-01-07 | 2025-01-07 | 367 | 262 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-01-31 | 11 | 9 | 2025-01-31 | 2025-01-31 | 1 | 1 | 15 | 11 | 379 | 272 | 394 | 283 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | -360 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 41.58 | Unknown | Unknown | Unknown | Unknown | 41.58 | Unknown | 1548.43 | 41.58 | 1506.85 | Yes | N/A | N/A | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-04 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-08 | 5 | 3 | 2024-10-08 | 2024-10-08 | 1 | 1 | 3 | 3 | 6 | 4 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 229 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2025-02-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 23920.3 | 4569.06 | Unknown | Unknown | -1820.24 | 21171.48 | 425432 | 33755.15 | 23920.3 | 9834.85 | Yes | N/A | N/A | 2023-10-20 | 2024-07-09 | 264 | 188 | 2024-07-09 | 2024-11-18 | 133 | 95 | 2024-07-17 | 2024-10-25 | 48 | 36 | 2024-10-08 | 2024-11-21 | 38 | 28 | 2024-11-18 | Unknown | Unknown | Unknown | 2024-12-13 | 2025-02-14 | 64 | 46 | 2025-02-25 | 2025-03-18 | 22 | 16 | 2025-03-18 | 2025-03-18 | 1 | 1 | 312 | 224 | 258 | 186 | 570 | 410 | Steps 2,3,5,6,7 | 144 | 104 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 4797.92 | 985.49 | Unknown | 275.23 | 72.28 | 3464.92 | 3981 | 799 | 4797.92 | -3998.92 | Yes | N/A | N/A | 2024-01-26 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-02-22 | 116 | 84 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-11-27 | 280 | 200 | Unknown | 2024-11-21 | Unknown | Unknown | 2024-11-27 | 2024-12-05 | 9 | 7 | 2024-12-05 | 2024-12-05 | 1 | 1 | 280 | 200 | 126 | 92 | 406 | 292 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-05 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2025-01-09 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 1434.57 | Unknown | Unknown | Unknown | 51.2 | 1383.37 | 7882 | 813 | 1434.57 | -621.57 | Yes | N/A | N/A | 2024-11-22 | 2025-02-04 | 75 | 53 | 2025-02-04 | 2025-02-06 | 3 | 3 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-05-28 | 112 | 80 | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-28 | 2025-06-23 | 27 | 19 | 2025-06-23 | 2025-06-23 | 1 | 1 | 187 | 133 | 31 | 23 | 218 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -74 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-07-17 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 4589.01 | 1448.65 | Unknown | 333.66 | Unknown | 2806.7 | 3981 | 2317.81 | 4589.01 | -2271.2 | Yes | N/A | N/A | 2023-05-03 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | 2023-08-10 | 120 | 86 | 2023-08-23 | 2025-03-06 | 287 | 207 | 2023-08-08 | 2024-12-03 | 127 | 93 | 2023-08-10 | 2024-10-02 | 420 | 300 | Unknown | 2024-11-21 | Unknown | Unknown | 2024-12-13 | 2024-12-16 | 4 | 2 | 2024-12-16 | 2024-12-16 | 1 | 1 | 707 | 507 | 252 | 182 | 959 | 689 | Steps 2,3,5,6,7 | 1057 | 755 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | 140 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-09-15 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 3466.21 | -4.21 | Unknown | Unknown | -274 | 3744.42 | Unknown | 274.43 | 3466.21 | -3191.78 | Yes | N/A | N/A | 2023-05-15 | 2023-09-08 | 117 | 85 | 2023-09-08 | 2024-03-12 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-22 | 9 | 7 | 2024-05-22 | 2024-05-22 | 1 | 1 | 117 | 85 | 197 | 141 | 314 | 226 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-28 | -397 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1460.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-09-20 | 8 | 6 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-01 | 15 | 11 | 2024-09-20 | 2025-06-26 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-06-26 | 1 | 1 | 2025-06-26 | 2025-06-26 | 1 | 1 | 288 | 206 | 18 | 14 | 306 | 220 | Steps 2,3,5,6,7 | 11 | 7 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | COUNTY OF SAN DIEGO-NORTH of 56, SAN DIEGO | 180 | 180 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-11 | -460 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 21418.09 | -197.16 | Unknown | Unknown | 93.13 | 21522.12 | Unknown | 3465.16 | 21418.09 | -17952.93 | Yes | N/A | N/A | 2024-03-26 | 2024-03-26 | 1 | 1 | 2024-03-26 | 2024-05-31 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-05-09 | 16 | 10 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-07-08 | 36 | 26 | 2024-07-08 | 2024-07-08 | 1 | 1 | 1 | 1 | 120 | 86 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 2421.08 | -48.65 | Unknown | Unknown | Unknown | 2469.73 | Unknown | 2038.18 | 2421.08 | -382.9 | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-22 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-01 | 10 | 8 | 2025-05-01 | 2025-05-01 | 1 | 1 | 28 | 20 | 12 | 10 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | -350 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 519.04 | -22.34 | Unknown | Unknown | Unknown | 541.38 | Unknown | 895.14 | 519.04 | 376.1 | Yes | N/A | N/A | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | 2024-04-11 | 2 | 2 | 2024-04-11 | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-03 | 22 | 16 | 2024-04-11 | 2024-04-18 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-23 | 6 | 4 | 2024-04-23 | 2024-04-23 | 1 | 1 | 9 | 7 | 31 | 23 | 40 | 30 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | -572 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-06-09 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1032.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-05-27 | 42 | 30 | 2025-05-27 | 2025-06-09 | 14 | 10 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-19 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-24 | 6 | 4 | 2025-06-24 | 2025-06-23 | Unknown | Unknown | 53 | 39 | 20 | 14 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-29 | -600 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 969.83 | 619.75 | Unknown | Unknown | Unknown | 350.08 | Unknown | 158.51 | 969.83 | -811.32 | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-11-22 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-07 | 16 | 12 | 2023-12-07 | 2023-12-07 | 1 | 1 | 56 | 40 | 18 | 14 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2015.43 | -15.21 | Unknown | Unknown | 6.81 | 2023.83 | 26839 | 4445.42 | 2015.43 | 2429.99 | Yes | N/A | N/A | 2024-10-29 | 2025-01-06 | 70 | 50 | 2025-01-06 | 2025-01-21 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-20 | 23 | 17 | 2025-01-21 | 2025-02-14 | 25 | 19 | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 95 | 69 | 40 | 30 | 135 | 99 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 51.7 | 51.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -470 | -337 | No | 2023-12-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-02-21 | IOU Designed & Installed | N/A | Yes | 84 | 886.28 | -38.96 | Unknown | Unknown | Unknown | 925.24 | 11943 | 1325.4 | 886.28 | 439.12 | Yes | N/A | N/A | 2023-12-05 | 2024-02-27 | 85 | 61 | 2024-02-27 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-02-21 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-15 | 24 | 18 | 2024-03-15 | 2024-03-06 | Unknown | Unknown | 161 | 115 | 24 | 18 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -861 | -616 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.8 | -8.14 | Unknown | Unknown | Unknown | 5.34 | Unknown | 744.74 | -2.8 | 747.54 | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 2.03 | 2.03 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | 97 | 70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-08 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 1451.21 | 470.75 | Unknown | Unknown | Unknown | 980.46 | 3981 | 1560.66 | 1451.21 | 109.45 | Yes | N/A | N/A | 2024-07-02 | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-07-08 | 74 | 52 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-25 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-07-30 | 6 | 4 | 2024-07-30 | 2024-07-30 | 1 | 1 | 18 | 14 | 81 | 57 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -547 | -391 | No | 2023-12-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2024-01-22 | 2024-02-28 | IOU Designed & Installed | N/A | Yes | 49 | -15.84 | -12.82 | Unknown | Unknown | Unknown | -3.02 | 3981 | 501.14 | -15.84 | 516.98 | Yes | N/A | N/A | 2023-12-08 | 2024-01-23 | 47 | 33 | 2024-01-23 | 2024-01-26 | 4 | 4 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-28 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-15 | 17 | 13 | 2024-03-15 | 2024-03-15 | 1 | 1 | 81 | 57 | 22 | 18 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-28 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -13.01 | -9.44 | Unknown | Unknown | Unknown | -3.57 | Unknown | 98.41 | -13.01 | 111.42 | Yes | N/A | N/A | 2023-01-09 | 2023-02-27 | 50 | 36 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | 2023-06-07 | 2023-06-07 | 1 | 1 | 50 | 36 | 1 | 1 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-07 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2268.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | 2025-04-08 | 27 | 19 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-13 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-05-22 | 10 | 8 | 2025-05-22 | 2025-05-22 | 1 | 1 | 37 | 27 | 38 | 28 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-23 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 929.16 | Unknown | Unknown | Unknown | 7.36 | 921.8 | 3981 | 747.62 | 929.16 | -181.54 | Yes | N/A | N/A | 2024-04-16 | 2024-05-20 | 35 | 25 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-11 | 53 | 39 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-07-11 | 2024-07-29 | 19 | 13 | 2024-07-29 | 2024-07-24 | Unknown | Unknown | 88 | 64 | 20 | 14 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 19.45 | 19.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -380 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-05-23 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 4346.57 | 1462.53 | Unknown | 169.65 | -895 | 3609.39 | Unknown | 773.87 | 4346.57 | -3572.7 | Yes | N/A | N/A | 2024-03-11 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-07-24 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-26 | 34 | 24 | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-19 | 2024-09-24 | 6 | 4 | 2024-09-24 | 2024-09-24 | 1 | 1 | 34 | 24 | 177 | 127 | 211 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-21 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 31.23 | Unknown | Unknown | Unknown | Unknown | 31.23 | 3981 | 2103.45 | 31.23 | 2072.22 | Yes | N/A | N/A | 2024-06-18 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-08-12 | 180 | 128 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-17 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-27 | 11 | 9 | 2024-09-27 | 2024-09-30 | 4 | 2 | 37 | 27 | 195 | 139 | 232 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | -697 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-02 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 481.37 | -9.67 | Unknown | Unknown | Unknown | 491.04 | 3981 | 1224.04 | 481.37 | 742.67 | Yes | N/A | N/A | 2025-05-02 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-05-02 | 4 | 4 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-15 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-19 | 5 | 3 | 2025-05-19 | 2025-05-19 | 1 | 1 | 14 | 10 | 10 | 8 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | -723 | -518 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 74.16 | Unknown | Unknown | Unknown | Unknown | 74.16 | Unknown | 1832.47 | 74.16 | 1758.31 | Yes | N/A | N/A | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-01-27 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-05 | 10 | 8 | 2025-02-05 | 2025-02-05 | 1 | 1 | 6 | 4 | 12 | 10 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -474 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-21 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | -1690.61 | Unknown | Unknown | Unknown | -1731 | 40.39 | Unknown | 1599.97 | -1690.61 | 3290.58 | Yes | N/A | N/A | 2024-10-18 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-21 | 8 | 6 | 2024-10-21 | 2024-10-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2025-01-13 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-03-10 | 57 | 41 | 2025-03-10 | 2025-03-07 | Unknown | Unknown | 86 | 62 | 65 | 47 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | 1081 | 773 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 1665.08 | 305.5 | Unknown | 120.99 | 24.45 | 1214.14 | 0 | 1269.87 | 1665.08 | -395.21 | Yes | N/A | N/A | 2024-01-05 | 2024-02-05 | 32 | 22 | 2024-02-05 | 2024-02-07 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-01 | 14 | 10 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-29 | 1 | 1 | 32 | 22 | 19 | 15 | 51 | 37 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-03 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 20.28 | Unknown | Unknown | Unknown | Unknown | 20.28 | Unknown | 1575.05 | 20.28 | 1554.77 | Yes | N/A | N/A | 2024-07-02 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-07-03 | 99 | 71 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-23 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-05 | 14 | 10 | 2024-09-05 | 2024-09-05 | 1 | 1 | 52 | 38 | 114 | 82 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 2242.24 | 513.63 | Unknown | Unknown | 18.54 | 1710.07 | 3981 | 231.09 | 2242.24 | -2011.15 | Yes | N/A | N/A | 2023-10-17 | 2024-02-13 | 120 | 86 | 2024-02-13 | 2024-02-23 | 11 | 9 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-04-23 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-25 | 3 | 3 | 2024-04-25 | 2024-04-25 | 1 | 1 | 183 | 131 | 15 | 13 | 198 | 144 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -318 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | -2422.43 | 654.4 | Unknown | 12.57 | -3428 | 338.6 | Unknown | 3427.98 | -2422.43 | 5850.41 | Yes | N/A | N/A | 2024-02-15 | 2024-02-16 | 2 | 2 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-02-21 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | La Jolla | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-14 | 111 | 80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | 4697.73 | -40.98 | Unknown | Unknown | Unknown | 4738.71 | 250 | 245.36 | 4697.73 | -4452.37 | Yes | N/A | N/A | 2023-08-23 | 2023-08-23 | 1 | 1 | 2023-08-23 | 2023-09-11 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-03 | 20 | 14 | 2023-10-03 | 2023-10-03 | 1 | 1 | 1 | 1 | 42 | 30 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -541 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | -370.14 | -1.25 | Unknown | Unknown | -486 | 117.11 | 3981 | 2896.17 | -370.14 | 3266.31 | Yes | N/A | N/A | 2024-08-15 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-15 | 4 | 4 | 2024-08-15 | 2024-09-23 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-11-21 | 60 | 44 | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-21 | 2024-12-06 | 16 | 12 | 2024-12-06 | 2024-12-06 | 1 | 1 | 100 | 72 | 21 | 17 | 121 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1425.1 | 1425.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-15 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 2300.2 | 239.56 | Unknown | Unknown | -7304 | 9364.64 | 3981 | 9624.79 | 2300.2 | 7324.59 | Yes | N/A | N/A | 2023-03-20 | 2023-03-17 | Unknown | Unknown | 2023-03-17 | 2023-04-20 | 35 | 25 | 2023-03-21 | 2023-04-20 | 3 | 3 | 2023-04-21 | 2023-05-31 | 11 | 7 | 2023-04-20 | 2023-04-25 | 6 | 4 | 2023-05-02 | 2023-09-20 | 142 | 102 | 2023-09-21 | 2023-10-04 | 14 | 10 | 2023-10-04 | 2023-10-04 | 1 | 1 | 9 | 7 | 203 | 145 | 212 | 152 | Steps 2,3,5,6,7 | 71 | 51 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-19 | -430 | -309 | No | 2023-01-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2022-11-08 | 2023-05-04 | IOU Designed & Installed | N/A | Yes | 56 | 4519.44 | Unknown | Unknown | Unknown | 122.78 | 4396.66 | 3981 | 831.59 | 4519.44 | -3687.85 | Yes | N/A | N/A | 2022-11-08 | 2023-03-03 | 116 | 84 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-05-04 | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | 2023-05-04 | 2023-08-14 | 103 | 73 | 2023-08-14 | 2023-05-16 | Unknown | Unknown | 116 | 84 | 103 | 73 | 219 | 157 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -390 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-06 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 634.93 | -12.76 | Unknown | Unknown | Unknown | 647.69 | 3981 | 750.33 | 634.93 | 115.4 | Yes | N/A | N/A | 2025-01-02 | 2024-12-31 | Unknown | Unknown | 2024-12-31 | 2025-01-06 | 7 | 5 | 2025-01-06 | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-16 | 11 | 9 | 2025-03-18 | 2025-03-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-03-28 | 11 | 9 | 2025-03-28 | 2025-03-28 | 1 | 1 | 1 | 1 | 30 | 24 | 31 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-02 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-19 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 823.61 | Unknown | Unknown | Unknown | Unknown | 823.61 | 3981 | 1165.63 | 823.61 | 342.02 | Yes | N/A | N/A | 2024-06-25 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-19 | 45 | 33 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-09-09 | 53 | 37 | Unknown | 2024-09-06 | Unknown | Unknown | 2024-09-09 | 2024-09-25 | 17 | 13 | 2024-09-25 | 2024-09-25 | 1 | 1 | 53 | 37 | 63 | 47 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 2.89 | -2.55 | Unknown | Unknown | Unknown | 5.44 | Unknown | 435.21 | 2.89 | 432.32 | Yes | N/A | N/A | 2024-05-21 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-05-21 | 28 | 20 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-23 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-05-28 | 6 | 4 | 2024-05-28 | 2024-05-28 | 1 | 1 | 3 | 3 | 35 | 25 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | 187 | 134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 50.41 | Unknown | Unknown | Unknown | Unknown | 50.41 | 3981 | 766.47 | 50.41 | 716.06 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-08-20 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 240 | 240 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-07-01 | IOU Designed & Installed | N/A | No | N/A | 244.16 | -13.02 | Unknown | Unknown | Unknown | 257.18 | Unknown | 815.52 | 244.16 | 571.36 | Yes | N/A | N/A | 2023-03-24 | 2023-03-29 | 6 | 4 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-07-01 | 95 | 68 | Unknown | Unknown | Unknown | Unknown | 2023-07-01 | 2023-07-27 | 27 | 19 | 2023-07-27 | 2023-07-27 | 1 | 1 | 101 | 72 | 28 | 20 | 129 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 141 | 141 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | -459 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 383.19 | -6.22 | Unknown | Unknown | Unknown | 389.41 | Unknown | 957.21 | 383.19 | 574.02 | Yes | N/A | N/A | 2024-02-12 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2024-02-12 | 174 | 124 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-04-05 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-05-21 | 47 | 33 | 2024-05-21 | 2024-05-21 | 1 | 1 | 54 | 40 | 222 | 158 | 276 | 198 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -318 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-05-13 | 2025-05-26 | IOU Designed & Installed | N/A | No | N/A | 2005.64 | 4558.32 | Unknown | Unknown | -4456 | 1903.32 | Unknown | 4456.38 | 2005.64 | 2450.74 | Yes | N/A | N/A | 2025-04-30 | 2025-05-07 | 8 | 6 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-26 | 2025-06-10 | 16 | 12 | 2025-06-10 | 2025-06-10 | 1 | 1 | 8 | 6 | 17 | 13 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-24 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 1298.65 | 329.69 | Unknown | Unknown | Unknown | 968.96 | 3981 | 1421.86 | 1298.65 | 123.21 | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-12-16 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-12-16 | 2024-12-16 | 1 | 1 | 196 | 140 | 3 | 3 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 109 | 109 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-18 | 508 | 365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10642.05 | Unknown | Unknown | Unknown | Unknown | 10642.05 | 3981 | 2572.66 | 10642.05 | -8069.39 | Yes | N/A | N/A | 2023-01-03 | 2023-05-23 | 141 | 101 | 2023-05-23 | 2023-10-24 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2025-01-13 | 448 | 320 | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-07 | Unknown | Unknown | 589 | 421 | 155 | 111 | 744 | 532 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 70.1 | 70.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 150 | 109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-01-19 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | 5045 | 241.68 | Unknown | Unknown | 269.89 | 4533.43 | 3981 | 829.55 | 5045 | -4215.45 | Yes | N/A | N/A | 2023-01-19 | 2023-03-07 | 48 | 34 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-09-25 | 203 | 145 | Unknown | 2023-09-14 | Unknown | Unknown | 2023-09-25 | 2023-09-28 | 4 | 4 | 2023-09-28 | 2023-09-28 | 1 | 1 | 251 | 179 | 5 | 5 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -648 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 1292.28 | -41.02 | Unknown | Unknown | Unknown | 1333.3 | Unknown | 861.62 | 1292.28 | -430.66 | Yes | N/A | N/A | 2024-03-26 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-03-26 | 33 | 23 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-17 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-08 | 22 | 16 | 2024-05-08 | 2024-05-08 | 1 | 1 | 23 | 17 | 56 | 40 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.07 | -9.03 | Unknown | Unknown | Unknown | 5.96 | 3885 | 695.07 | -3.07 | 698.14 | Yes | N/A | N/A | 2023-01-18 | 2023-02-14 | 28 | 20 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-03-31 | Unknown | Unknown | 28 | 20 | 0 | 0 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | 460 | 329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 48.01 | -11.64 | Unknown | Unknown | 54 | 5.65 | 3981 | 776.65 | 48.01 | 728.64 | Yes | N/A | N/A | 2023-07-10 | 2023-07-13 | 4 | 4 | 2023-07-13 | 2023-07-17 | 5 | 3 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | 2025-06-05 | 2025-06-05 | 1 | 1 | 4 | 4 | 6 | 4 | 10 | 8 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 108.4 | 108.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -472 | -337 | No | 2024-09-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | 2025-03-24 | IOU Designed & Installed | N/A | Yes | 167 | -3.63 | -15.13 | Unknown | Unknown | Unknown | 11.5 | 3981 | 1464.81 | -3.63 | 1468.44 | Yes | N/A | N/A | 2024-09-11 | 2025-02-24 | 167 | 119 | 2025-02-24 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-03-24 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-28 | 5 | 5 | 2025-03-28 | 2025-03-27 | Unknown | Unknown | 362 | 258 | 5 | 5 | 367 | 263 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | -208 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-26 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | 862.98 | -5.68 | Unknown | Unknown | Unknown | 868.66 | 3981 | 1043.15 | 862.98 | 180.17 | Yes | N/A | N/A | 2023-05-23 | 2023-05-26 | 4 | 4 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-07-07 | 43 | 31 | Unknown | 2023-07-24 | Unknown | Unknown | 2023-07-07 | 2023-07-24 | 18 | 12 | 2023-07-24 | 2023-07-24 | 1 | 1 | 47 | 35 | 19 | 13 | 66 | 48 | Steps 2,3,5,6,7 | 17 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-24 | -540 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | -2.9 | -4.45 | Unknown | Unknown | Unknown | 1.55 | Unknown | 163.83 | -2.9 | 166.73 | Yes | N/A | N/A | 2023-11-14 | 2024-02-09 | 88 | 64 | 2024-02-09 | 2024-02-26 | 18 | 12 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-13 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-02 | 21 | 15 | 2024-04-02 | 2024-03-02 | Unknown | Unknown | 105 | 77 | 39 | 27 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 1382.3 | Unknown | Unknown | Unknown | 39.21 | 1343.09 | 3981 | 665.13 | 1382.3 | -717.17 | Yes | N/A | N/A | 2023-11-29 | 2024-01-11 | 44 | 32 | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-08-08 | 211 | 151 | Unknown | 2024-07-31 | Unknown | Unknown | 2024-08-08 | 2024-08-19 | 12 | 8 | 2024-08-19 | 2024-08-19 | 1 | 1 | 255 | 183 | 14 | 10 | 269 | 193 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SOUTH LAGUNA | SOUTH LAGUNA | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | 401 | 286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2232.1 | 254.67 | Unknown | 119.48 | 43.64 | 1814.31 | 3981 | 574.93 | 2232.1 | -1657.17 | Yes | N/A | N/A | 2023-09-01 | 2023-12-11 | 102 | 72 | 2023-12-11 | 2024-01-02 | 23 | 17 | 2024-01-02 | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-01 | 36 | 26 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-21 | 1 | 1 | 102 | 72 | 60 | 44 | 162 | 116 | Steps 2,3,5,6,7 | 485 | 347 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 1843.41 | 406.6 | Unknown | Unknown | Unknown | 1436.81 | Unknown | 1763.19 | 1843.41 | -80.22 | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-19 | 9 | 7 | 2025-02-19 | 2025-02-19 | 1 | 1 | 14 | 10 | 11 | 9 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-25 | -215 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-06 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | -8.31 | -6 | Unknown | Unknown | Unknown | -2.31 | Unknown | 153.75 | -8.31 | 162.06 | Yes | N/A | N/A | 2023-05-24 | 2023-06-06 | 14 | 10 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-07-19 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-07-25 | 7 | 5 | 2023-07-25 | 2023-07-25 | 1 | 1 | 58 | 42 | 8 | 6 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Rancho Santa Fe | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -785.37 | 1382.6 | Unknown | 179.82 | -3074 | 726.21 | Unknown | 3073.53 | -785.37 | 3858.9 | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 33.44 | Unknown | Unknown | Unknown | Unknown | 33.44 | Unknown | 1002.75 | 33.44 | 969.31 | Yes | N/A | N/A | 2024-03-13 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-04-15 | 67 | 47 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 0 | 0 | 68 | 48 | 68 | 48 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -606 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 103.31 | Unknown | Unknown | Unknown | 10.41 | 92.9 | Unknown | 1400.41 | 103.31 | 1297.1 | Yes | N/A | N/A | 2025-01-27 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-27 | 19 | 13 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-28 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-22 | 26 | 18 | 2025-04-22 | 2025-04-22 | 1 | 1 | 61 | 45 | 46 | 32 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -386 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 838.47 | 378.69 | Unknown | 176.88 | Unknown | 282.9 | Unknown | 424.95 | 838.47 | -413.52 | Yes | N/A | N/A | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2024-02-06 | 257 | 183 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-07 | 2 | 2 | 2024-02-07 | 2024-02-07 | 1 | 1 | 258 | 184 | 3 | 3 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 111 | 80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1076.03 | 112.08 | Unknown | Unknown | Unknown | 963.95 | 3981 | 565.48 | 1076.03 | -510.55 | Yes | N/A | N/A | 2023-12-19 | 2024-01-12 | 25 | 19 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-03-20 | 1 | 1 | 25 | 19 | 2 | 2 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-30 | 351 | 252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-06-02 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 14084.51 | 570.36 | Unknown | Unknown | -950 | 14464.15 | 3981 | 3005.01 | 14084.51 | -11079.5 | Yes | N/A | N/A | 2023-03-24 | 2023-06-08 | 77 | 55 | 2023-06-08 | 2023-07-28 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-09-19 | 8 | 6 | 2023-07-28 | 2024-09-04 | 405 | 289 | Unknown | 2024-09-17 | Unknown | Unknown | 2024-10-14 | 2024-10-23 | 10 | 8 | 2024-10-23 | 2024-10-15 | Unknown | Unknown | 482 | 344 | 69 | 51 | 551 | 395 | Steps 2,3,5,6,7 | 53 | 37 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-22 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | 2928.88 | Unknown | Unknown | Unknown | 13.27 | 2915.61 | 3981 | 837.21 | 2928.88 | -2091.67 | Yes | N/A | N/A | 2024-10-15 | 2024-10-30 | 16 | 12 | 2024-10-30 | 2024-11-06 | 8 | 6 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-06-06 | 213 | 153 | Unknown | 2025-06-05 | Unknown | Unknown | 2025-06-06 | 2025-06-10 | 5 | 3 | 2025-06-10 | 2025-06-10 | 1 | 1 | 229 | 165 | 14 | 10 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -546 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | -131.72 | Unknown | Unknown | Unknown | -1061.44 | 929.72 | Unknown | 1069.23 | -131.72 | 1200.95 | Yes | N/A | N/A | 2024-04-30 | 2024-06-17 | 49 | 35 | 2024-06-17 | 2024-06-20 | 4 | 4 | 2024-06-20 | 2024-07-26 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-12 | 18 | 12 | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-09-28 | 48 | 35 | 2024-09-28 | 2024-09-28 | 1 | 0 | 104 | 74 | 53 | 39 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-06 | -243 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 295.56 | -7.85 | Unknown | Unknown | Unknown | 303.41 | 3981 | 788.65 | 295.56 | 493.09 | Yes | N/A | N/A | 2023-10-05 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-10-05 | 38 | 28 | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-06 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-12-07 | 32 | 24 | 2023-12-07 | 2023-12-07 | 1 | 1 | 33 | 23 | 71 | 53 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 181.92 | -13.92 | Unknown | Unknown | Unknown | 195.84 | 7962 | 977.61 | 181.92 | 795.69 | Yes | N/A | N/A | 2023-12-15 | 2024-01-02 | 19 | 13 | 2024-01-02 | 2024-01-04 | 3 | 3 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-03-20 | 1 | 1 | 19 | 13 | 4 | 4 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | -418 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 27.97 | Unknown | Unknown | Unknown | Unknown | 27.97 | 3885 | 672.85 | 27.97 | 644.88 | Yes | N/A | N/A | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-10-11 | 52 | 38 | Unknown | 2024-09-16 | Unknown | Unknown | 2024-10-11 | 2024-10-16 | 6 | 4 | 2024-10-16 | 2024-10-16 | 1 | 1 | 53 | 39 | 8 | 6 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -855 | -611 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 953.32 | 614.34 | Unknown | Unknown | Unknown | 338.98 | 3241 | 554.66 | 953.32 | -398.66 | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2024-09-17 | 470 | 336 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-11 | 25 | 19 | 2024-10-11 | 2024-10-11 | 1 | 1 | 471 | 337 | 26 | 20 | 497 | 357 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 1665.32 | 298.27 | Unknown | Unknown | Unknown | 1367.05 | 3981 | 2133.39 | 1665.32 | 468.07 | Yes | N/A | N/A | 2025-03-07 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-03-07 | 22 | 16 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-04-16 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-21 | 6 | 4 | 2025-04-21 | 2025-04-21 | 1 | 1 | 41 | 29 | 29 | 21 | 70 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | -527 | -376 | No | 2024-05-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-09-09 | IOU Designed & Installed | N/A | Yes | 109 | 919.68 | 614.1 | Unknown | Unknown | Unknown | 305.58 | Unknown | 1312.69 | 919.68 | 393.01 | Yes | N/A | N/A | 2024-05-23 | 2024-09-09 | 110 | 78 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-09-09 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-27 | 19 | 15 | 2024-09-27 | 2024-09-27 | 1 | 1 | 220 | 156 | 21 | 17 | 241 | 173 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-23 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 29.84 | -13.55 | Unknown | Unknown | Unknown | 43.39 | Unknown | 1048.84 | 29.84 | 1019 | Yes | N/A | N/A | 2024-02-15 | 2024-02-21 | 7 | 5 | 2024-02-21 | 2024-02-23 | 3 | 3 | 2024-02-23 | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-11 | 18 | 12 | 2024-02-23 | 2024-03-21 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-03-28 | 8 | 6 | 2024-03-28 | 2024-03-28 | 1 | 1 | 35 | 25 | 30 | 22 | 65 | 47 | Steps 2,3,5,6,7 | 17 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-14 | 662 | 473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-02 | 2023-08-25 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 9258.69 | 2454.86 | Unknown | Unknown | -1092.16 | 7895.99 | 3981 | 1873.97 | 9258.69 | -7384.72 | Yes | N/A | N/A | 2021-04-02 | 2023-08-14 | 865 | 617 | 2023-08-14 | 2023-09-12 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-19 | 2023-11-14 | 27 | 19 | 2023-11-14 | 2023-11-07 | Unknown | Unknown | 865 | 617 | 57 | 41 | 922 | 658 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | -389 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-29 | 2023-04-29 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | 259.09 | -13.1 | Unknown | Unknown | 7.53 | 264.66 | Unknown | 806.69 | 259.09 | 547.6 | Yes | N/A | N/A | 2023-04-29 | 2023-04-29 | 1 | 0 | 2023-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-29 | 2023-07-07 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-12-07 | 154 | 110 | 2023-12-07 | 2023-12-07 | 1 | 1 | 71 | 50 | 155 | 111 | 226 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 508.01 | -9.6 | Unknown | Unknown | Unknown | 517.61 | 0 | 1731.53 | 508.01 | 1223.52 | Yes | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | 2023-09-11 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-01 | 5 | 5 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | 1 | 1 | 24 | 18 | 25 | 19 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56, DEL MAR | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-08-08 | -130 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 539.99 | 4931.25 | Unknown | Unknown | -29631 | 25239.74 | Unknown | 29113.62 | 539.99 | 28573.63 | Yes | N/A | N/A | 2024-08-08 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-11-06 | 128 | 92 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-10-03 | 2024-11-13 | 36 | 26 | 2024-11-06 | 2025-02-19 | 106 | 76 | 2024-11-19 | 2025-02-27 | 101 | 73 | 2025-03-05 | 2025-04-04 | 31 | 23 | 2025-04-04 | 2025-03-31 | Unknown | Unknown | 107 | 77 | 296 | 214 | 403 | 291 | Steps 2,3,5,6,7 | 147 | 105 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -619 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 2451.57 | 1452.27 | Unknown | Unknown | Unknown | 999.3 | Unknown | 186.52 | 2451.57 | -2265.05 | Yes | N/A | N/A | 2024-08-22 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-09-16 | 67 | 47 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-02 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-29 | 28 | 20 | 2024-10-29 | 2024-10-29 | 1 | 1 | 17 | 13 | 96 | 68 | 113 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -173 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-18 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | -851.42 | 252.46 | Unknown | 23.73 | -1655 | 527.39 | Unknown | 1556.33 | -851.42 | 2407.75 | Yes | N/A | N/A | 2023-07-17 | 2023-07-18 | 2 | 2 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-26 | 9 | 7 | 2024-03-28 | 2024-03-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-01 | 5 | 3 | 2024-04-01 | 2024-04-01 | 1 | 1 | 3 | 3 | 15 | 11 | 18 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 240.53 | -4.6 | Unknown | Unknown | Unknown | 245.13 | Unknown | 468.05 | 240.53 | 227.52 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-27 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-05-18 | 2024-06-14 | 28 | 20 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-01 | 1 | 1 | 2 | 2 | 87 | 63 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -81 | -58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 982.7 | Unknown | Unknown | Unknown | Unknown | 982.7 | 3981 | 2397.28 | 982.7 | 1414.58 | Yes | N/A | N/A | 2024-04-11 | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-09-06 | 187 | 135 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1 | 1 | 0 | 0 | 188 | 136 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41.4 | 41.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | 1700.48 | 291.46 | Unknown | 76.23 | 6.59 | 1326.2 | 3981 | 1056.92 | 1700.48 | -643.56 | Yes | N/A | N/A | 2023-04-12 | 2023-04-27 | 16 | 12 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2024-02-22 | 120 | 86 | Unknown | 2024-01-25 | Unknown | Unknown | 2024-02-22 | 2024-02-29 | 8 | 6 | 2024-02-29 | 2024-02-29 | 1 | 1 | 136 | 98 | 9 | 7 | 145 | 105 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -558 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-11 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 851.73 | Unknown | Unknown | Unknown | 7.18 | 844.55 | 3981 | 1146.68 | 851.73 | 294.95 | Yes | N/A | N/A | 2024-08-01 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-08-11 | 48 | 34 | 2024-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-11 | 2024-11-12 | 94 | 67 | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-12 | 2024-12-02 | 21 | 15 | 2024-12-02 | 2024-11-25 | Unknown | Unknown | 94 | 67 | 69 | 49 | 163 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-19 | 250 | 179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | -15.77 | -10.22 | Unknown | Unknown | Unknown | -5.55 | 0 | 884.08 | -15.77 | 899.85 | Yes | N/A | N/A | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | 2025-02-07 | 337 | 241 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2025-03-17 | 375 | 267 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-26 | 10 | 8 | 2025-03-26 | 2025-03-26 | 1 | 1 | 713 | 509 | 12 | 10 | 725 | 519 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 555.05 | 555.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-03-01 | IOU Designed & Installed | N/A | No | N/A | -10.8 | -7.81 | Unknown | Unknown | Unknown | -2.99 | 3981 | 341 | -10.8 | 351.8 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-03-01 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-05-18 | 79 | 57 | 2023-05-18 | 2023-05-18 | 1 | 1 | 10 | 8 | 80 | 58 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -227 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-03-10 | IOU Designed & Installed | N/A | No | N/A | 1040.63 | -6.64 | Unknown | Unknown | Unknown | 1047.27 | Unknown | 216 | 1040.63 | -824.63 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-03-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-06-19 | 102 | 72 | 2023-06-19 | 2023-06-19 | 1 | 1 | 3 | 3 | 103 | 73 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -380 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-01-19 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 7.77 | -6.9 | Unknown | Unknown | Unknown | 14.67 | 3981 | 824.56 | 7.77 | 816.79 | Yes | N/A | N/A | 2023-12-27 | 2024-01-17 | 22 | 16 | 2024-01-17 | 2024-01-19 | 3 | 3 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-05-10 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-29 | 20 | 14 | 2024-05-29 | 2024-05-28 | Unknown | Unknown | 135 | 97 | 23 | 17 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 117.69 | -1.5 | Unknown | Unknown | Unknown | 119.19 | 3981 | 1359.92 | 117.69 | 1242.23 | Yes | N/A | N/A | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-09-25 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-04 | 10 | 8 | 2024-10-04 | 2024-10-04 | 1 | 1 | 65 | 47 | 12 | 10 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 1937.14 | 443.79 | Unknown | 117.92 | 7.17 | 1368.26 | 3981 | 969.1 | 1937.14 | -968.04 | Yes | N/A | N/A | 2023-06-05 | 2023-06-09 | 5 | 5 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-19 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-08-17 | 30 | 22 | 2023-08-17 | 2023-08-17 | 1 | 1 | 46 | 34 | 31 | 23 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 578 | 413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 667.56 | -16.3 | Unknown | Unknown | 74.2 | 609.66 | 0 | 573.27 | 667.56 | -94.29 | Yes | N/A | N/A | 2023-10-06 | 2023-10-09 | 4 | 2 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-29 | Unknown | Unknown | 2024-09-29 | 2024-09-29 | 1 | 0 | 4 | 2 | 1 | 0 | 5 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-16 | -58 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 7876.27 | -3.24 | Unknown | Unknown | 2.48 | 7877.03 | 3981 | 525.59 | 7876.27 | -7350.68 | Yes | N/A | N/A | 2023-12-13 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-01-11 | 31 | 23 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-04-17 | 98 | 70 | Unknown | 2024-04-11 | Unknown | Unknown | 2024-04-17 | 2024-04-22 | 6 | 4 | 2024-04-22 | 2024-04-19 | Unknown | Unknown | 98 | 70 | 37 | 27 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 446.66 | -14.39 | Unknown | Unknown | 6.46 | 454.59 | 3981 | 1688.22 | 446.66 | 1241.56 | Yes | N/A | N/A | 2023-09-25 | 2024-02-27 | 156 | 112 | 2024-02-27 | 2024-03-11 | 14 | 10 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-05-20 | 71 | 51 | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-20 | 2024-06-19 | 31 | 23 | 2024-06-19 | 2024-06-19 | 1 | 1 | 227 | 163 | 46 | 34 | 273 | 197 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -36 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-04 | 2023-11-09 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 503.29 | -9.1 | Unknown | Unknown | 28.26 | 484.13 | 3981 | 1109.76 | 503.29 | 606.47 | Yes | N/A | N/A | 2023-11-04 | 2023-11-28 | 25 | 17 | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-04-19 | 144 | 104 | Unknown | 2024-04-13 | Unknown | Unknown | 2024-04-19 | 2024-05-01 | 13 | 9 | 2024-05-01 | 2024-05-01 | 1 | 1 | 169 | 121 | 15 | 11 | 184 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1013.54 | -20.24 | Unknown | Unknown | Unknown | 1033.78 | Unknown | 466.88 | 1013.54 | -546.66 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-17 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-05 | 27 | 19 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-12 | 1 | 1 | 2 | 2 | 76 | 54 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 26.22 | Unknown | Unknown | Unknown | Unknown | 26.22 | Unknown | 1497.75 | 26.22 | 1471.53 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | 2024-06-26 | 2 | 2 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-09 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-06 | 29 | 21 | 2024-08-06 | 2024-08-06 | 1 | 1 | 15 | 11 | 32 | 24 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | -457 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | 1480.19 | Unknown | Unknown | Unknown | 2.87 | 1477.32 | 3981 | 1208.59 | 1480.19 | -271.6 | Yes | N/A | N/A | 2024-09-27 | 2025-01-17 | 113 | 81 | 2025-01-17 | 2025-01-21 | 5 | 3 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-03-07 | 46 | 34 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-07 | 2025-03-21 | 15 | 11 | 2025-03-21 | 2025-03-21 | 1 | 1 | 159 | 115 | 21 | 15 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | 84 | 61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 15244.59 | Unknown | Unknown | Unknown | -1645 | 16889.59 | 7962 | 6295.38 | 15244.59 | -8949.21 | Yes | N/A | N/A | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | 2024-03-20 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-15 | 20 | 14 | 2024-03-20 | 2024-04-29 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-05-13 | 50 | 36 | 2024-05-13 | 2024-05-02 | Unknown | Unknown | 42 | 30 | 127 | 91 | 169 | 121 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | -275 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-06-13 | IOU Designed & Installed | N/A | No | N/A | -5.15 | -3.74 | Unknown | Unknown | Unknown | -1.41 | Unknown | 479.76 | -5.15 | 484.91 | Yes | N/A | N/A | 2023-06-08 | 2023-06-08 | 1 | 1 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-06-13 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-06-30 | 18 | 14 | 2023-06-30 | 2023-06-30 | 1 | 1 | 7 | 5 | 19 | 15 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | -690 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 32.39 | Unknown | Unknown | Unknown | Unknown | 32.39 | Unknown | 1510.52 | 32.39 | 1478.13 | Yes | N/A | N/A | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-12 | 16 | 12 | 2025-05-28 | 2025-06-12 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-24 | 13 | 9 | 2025-06-24 | 2025-06-24 | 1 | 1 | 17 | 13 | 31 | 23 | 48 | 36 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -49 | -36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-05 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | -1031.91 | Unknown | Unknown | Unknown | -2082 | 1050.09 | Unknown | 2081.6 | -1031.91 | 3113.51 | Yes | N/A | N/A | 2024-08-02 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-08-05 | 41 | 29 | 2024-08-05 | 2024-08-27 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-02-07 | 100 | 72 | Unknown | 2025-01-13 | Unknown | Unknown | 2025-02-07 | 2025-02-11 | 5 | 3 | 2025-02-11 | 2025-02-11 | 1 | 1 | 123 | 89 | 47 | 33 | 170 | 122 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-11 | -568 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 1395.34 | 240.76 | Unknown | 36.6 | Unknown | 1117.98 | Unknown | 848.51 | 1395.34 | -546.83 | Yes | N/A | N/A | 2024-02-12 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-02-12 | 91 | 65 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-15 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-03-22 | 37 | 27 | 2024-03-22 | 2024-03-22 | 1 | 1 | 4 | 4 | 129 | 93 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -240 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-02 | 2023-09-21 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 10992.93 | -85.78 | Unknown | Unknown | Unknown | 11078.71 | 3981 | 811.79 | 10992.93 | -10181.14 | Yes | N/A | N/A | 2022-12-02 | 2023-09-26 | 299 | 213 | 2023-09-26 | 2023-10-19 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-15 | 29 | 21 | 2024-02-15 | 2024-02-09 | Unknown | Unknown | 299 | 213 | 53 | 39 | 352 | 252 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | -379 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-26 | 2023-11-26 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 560.25 | Unknown | Unknown | Unknown | -639.4 | 1199.65 | Unknown | 680.09 | 560.25 | 119.84 | Yes | N/A | N/A | 2023-11-26 | 2023-12-18 | 23 | 16 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2024-05-07 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-07-29 | 202 | 144 | Unknown | 2025-03-18 | Unknown | Unknown | 2024-07-29 | 2024-07-31 | 3 | 3 | 2024-07-31 | 2024-07-31 | 1 | 1 | 367 | 262 | 5 | 5 | 372 | 267 | Steps 2,3,5,6,7 | 232 | 166 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 359 | 359 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 2310.17 | 695.08 | Unknown | 201.51 | 9.79 | 1403.79 | 3981 | 599.91 | 2310.17 | -1710.26 | Yes | N/A | N/A | 2023-02-23 | 2023-04-03 | 40 | 28 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-08-10 | 130 | 94 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-16 | 7 | 5 | 2023-08-16 | 2023-08-16 | 1 | 1 | 170 | 122 | 8 | 6 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-06 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-02-14 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1698.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-02-13 | 18 | 14 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-06-12 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-16 | 5 | 3 | 2025-06-16 | 2025-06-16 | 1 | 1 | 119 | 85 | 24 | 18 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 144 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-11-03 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 713.45 | -29.71 | Unknown | Unknown | Unknown | 743.16 | 2781 | 888.53 | 713.45 | 175.08 | Yes | N/A | N/A | 2023-10-09 | 2023-11-03 | 26 | 20 | 2023-11-03 | 2025-03-06 | 490 | 350 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2024-04-29 | 179 | 127 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-06 | 8 | 6 | 2024-05-06 | 2024-05-07 | 2 | 2 | 205 | 147 | 500 | 358 | 705 | 505 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | -689 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 1215.56 | -25.09 | Unknown | Unknown | Unknown | 1240.65 | 3981 | 1990.34 | 1215.56 | 774.78 | Yes | N/A | N/A | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | 2025-04-21 | 2025-05-15 | 25 | 19 | 2025-04-17 | 2025-05-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-22 | 7 | 5 | 2025-05-22 | 2025-05-22 | 1 | 1 | 31 | 23 | 34 | 26 | 65 | 49 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-28 | -923 | -660 | No | 2024-11-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | 2025-04-16 | IOU Designed & Installed | N/A | Yes | 127 | 74.73 | -1.5 | Unknown | Unknown | Unknown | 76.23 | 7962 | 4521.33 | 74.73 | 4446.6 | Yes | N/A | N/A | 2024-11-26 | 2025-04-02 | 128 | 92 | 2025-04-02 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-04-16 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-21 | 6 | 4 | 2025-04-21 | 2025-04-18 | Unknown | Unknown | 270 | 194 | 6 | 4 | 276 | 198 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 712.14 | Unknown | Unknown | Unknown | -1149.91 | 1862.05 | Unknown | 1150.65 | 712.14 | 438.51 | Yes | N/A | N/A | 2024-10-17 | 2024-10-24 | 8 | 6 | 2024-10-24 | 2024-11-08 | 16 | 12 | 2024-11-08 | 2024-11-27 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-01-07 | 42 | 30 | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-07 | 2025-01-15 | 9 | 7 | 2025-01-15 | 2025-01-14 | Unknown | Unknown | 70 | 50 | 25 | 19 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -502 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-19 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 1053.65 | Unknown | Unknown | Unknown | 12.08 | 1041.57 | 3961 | 1156.32 | 1053.65 | 102.67 | Yes | N/A | N/A | 2024-04-02 | 2024-08-16 | 137 | 99 | 2024-08-16 | 2024-08-23 | 8 | 6 | 2024-08-23 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-20 | 29 | 21 | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-20 | 2024-10-07 | 18 | 12 | 2024-10-07 | 2024-10-07 | 1 | 1 | 166 | 120 | 27 | 19 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | 472.94 | Unknown | Unknown | Unknown | Unknown | 472.94 | 3981 | 1163.79 | 472.94 | 690.85 | Yes | N/A | N/A | 2024-12-13 | 2024-12-22 | 10 | 6 | 2024-12-22 | 2025-02-28 | 69 | 50 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-06-20 | 149 | 107 | Unknown | 2025-05-22 | Unknown | Unknown | 2025-06-20 | 2025-06-21 | 2 | 1 | 2025-06-21 | 2025-06-21 | 1 | 0 | 159 | 113 | 72 | 51 | 231 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | SD 1189-H1 JUNIPERS PH8 (E) | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-08-22 | 496 | 355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2025-02-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 7572.63 | Unknown | Unknown | Unknown | Unknown | 7572.63 | 3981 | Not available | 7572.63 | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-06-20 | 52 | 38 | 2024-06-20 | 2024-07-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2025-07-15 | 378 | 270 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-30 | 1 | 1 | 430 | 308 | 15 | 11 | 445 | 319 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 2.35 | 2.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 570.94 | Unknown | Unknown | Unknown | 9.83 | 561.11 | 3981 | 2458.85 | 570.94 | 1887.91 | Yes | N/A | N/A | 2024-08-22 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-09-04 | 70 | 50 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-13 | 1 | 1 | 0 | 0 | 71 | 51 | 71 | 51 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 1218.9 | -15.26 | Unknown | Unknown | 13.92 | 1220.24 | 3981 | 807.5 | 1218.9 | -411.4 | Yes | N/A | N/A | 2023-06-13 | 2023-08-08 | 57 | 41 | 2023-08-08 | Unknown | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-12-11 | 48 | 34 | Unknown | 2023-11-22 | Unknown | Unknown | 2023-12-11 | 2023-12-13 | 3 | 3 | 2023-12-13 | 2023-12-13 | 1 | 1 | 106 | 76 | 4 | 4 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 150 | 150 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -323 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 1391.36 | 184.09 | Unknown | Unknown | -519 | 1726.27 | 0 | 1790.14 | 1391.36 | 398.78 | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2025-02-07 | 276 | 198 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-04-11 | 339 | 243 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-11 | 1 | 1 | 616 | 442 | 3 | 3 | 619 | 445 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.5 | 13.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -365 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-16 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2993.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-08-16 | 32 | 24 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2025-06-25 | 314 | 224 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-26 | 2 | 2 | 2025-06-26 | 2025-06-26 | 1 | 1 | 314 | 224 | 35 | 27 | 349 | 251 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-13 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 961.61 | Unknown | Unknown | Unknown | 2.55 | 959.06 | 3961 | 1304.13 | 961.61 | 342.52 | Yes | N/A | N/A | 2024-06-07 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-07-01 | 63 | 45 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-08-02 | 33 | 25 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-02 | 2024-08-27 | 26 | 18 | 2024-08-27 | 2024-08-27 | 1 | 1 | 33 | 25 | 90 | 64 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -96 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2767.99 | 857.28 | Unknown | 165.45 | -4319 | 528.28 | Unknown | 4318.73 | -2767.99 | 7086.72 | Yes | N/A | N/A | 2023-04-06 | 2023-04-10 | 5 | 3 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | 39 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 29264.66 | 11993.15 | Unknown | Unknown | Unknown | 17271.51 | 29816 | 18220.22 | 29264.66 | -11044.44 | Yes | N/A | N/A | 2024-10-07 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2025-01-23 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-25 | 34 | 24 | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-25 | Unknown | Unknown | 34 | 24 | 135 | 97 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 179 | 179 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 266 | 191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-09-15 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 35425.27 | 9108.9 | Unknown | Unknown | -14760.66 | 41077.03 | 0 | 14158.39 | 35425.27 | -21266.88 | Yes | N/A | N/A | 2023-05-18 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-11-27 | 201 | 143 | 2023-06-12 | 2023-06-28 | 17 | 13 | 2023-10-20 | 2024-04-03 | 104 | 74 | 2024-01-25 | Unknown | Unknown | Unknown | 2024-01-25 | 2025-02-28 | 401 | 287 | 2024-05-17 | 2024-06-04 | 19 | 13 | 2024-06-04 | 2024-06-04 | 1 | 1 | 17 | 13 | 726 | 518 | 743 | 531 | Steps 2,3,5,6,7 | 524 | 374 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | -136 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-11 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 898.5 | Unknown | Unknown | Unknown | 12.21 | 886.29 | 3981 | 2773.5 | 898.5 | 1875 | Yes | N/A | N/A | 2024-12-06 | 2025-01-09 | 35 | 25 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-06-05 | 148 | 106 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-06-05 | 2025-06-07 | 3 | 2 | 2025-06-07 | 2025-06-07 | 1 | 0 | 183 | 131 | 5 | 3 | 188 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 1013.48 | -19.99 | Unknown | Unknown | Unknown | 1033.47 | Unknown | 927.58 | 1013.48 | -85.9 | Yes | N/A | N/A | 2024-02-15 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-02-15 | 22 | 16 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-03-05 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-27 | 23 | 17 | 2024-03-27 | 2024-03-27 | 1 | 1 | 20 | 14 | 46 | 34 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -376 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 63.83 | -1.26 | Unknown | Unknown | Unknown | 65.09 | 0 | 1543.86 | 63.83 | 1480.03 | Yes | N/A | N/A | 2024-07-30 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-07-30 | 260 | 186 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-27 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-23 | 27 | 19 | 2024-10-23 | 2024-10-23 | 1 | 1 | 60 | 44 | 288 | 206 | 348 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-26 | -229 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 395.17 | 128.3 | Unknown | Unknown | Unknown | 266.87 | 3981 | 2530.81 | 395.17 | 2135.64 | Yes | N/A | N/A | 2024-05-30 | 2024-06-07 | 9 | 7 | 2024-06-07 | 2024-06-10 | 4 | 2 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-09 | 1 | 1 | 9 | 7 | 5 | 3 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -672 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 696.6 | -14.01 | Unknown | Unknown | Unknown | 710.61 | 3981 | 1670.23 | 696.6 | 973.63 | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-21 | 53 | 39 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2 | 2 | 55 | 41 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | 73843.24 | 73843.24 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-23 | 274 | 196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 71396.78 | 15013.53 | Unknown | Unknown | 1572.01 | 54811.24 | 121504 | 39025.23 | 71396.78 | -32371.55 | Yes | N/A | N/A | 2023-03-14 | 2023-10-06 | 207 | 149 | 2023-10-06 | 2024-05-17 | 225 | 161 | 2023-10-16 | 2024-05-17 | 130 | 94 | 2024-05-20 | 2024-10-04 | 138 | 100 | 2024-05-23 | Unknown | Unknown | Unknown | 2024-05-23 | 2025-02-26 | 280 | 200 | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 337 | 243 | 644 | 462 | 981 | 705 | Steps 2,3,5,6,7 | 348 | 250 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Tribal Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | -271 | -194 | No | 2024-03-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | 2024-05-10 | IOU Designed & Installed | N/A | Yes | 55 | -3.47 | -6.68 | Unknown | Unknown | Unknown | 3.21 | Unknown | 163.83 | -3.47 | 167.3 | Yes | N/A | N/A | 2024-03-13 | 2024-05-07 | 56 | 40 | 2024-05-07 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-05-10 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-24 | 15 | 11 | 2024-05-24 | 2024-05-31 | 8 | 6 | 88 | 64 | 23 | 17 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-30 | 295 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.97 | -7.69 | Unknown | Unknown | Unknown | 3.72 | 3981 | 812.39 | -3.97 | 816.36 | Yes | N/A | N/A | 2022-11-07 | 2023-01-31 | 86 | 62 | 2023-01-31 | 2023-02-10 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2023-11-21 | 22 | 16 | 86 | 62 | 33 | 25 | 119 | 87 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 77.68 | Unknown | Unknown | Unknown | Unknown | 77.68 | 3981 | 2571.07 | 77.68 | 2493.39 | Yes | N/A | N/A | 2025-05-29 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-29 | 21 | 15 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-10 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-17 | 8 | 6 | 2025-06-17 | 2025-06-17 | 1 | 1 | 13 | 9 | 30 | 22 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 612.4 | 612.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -278 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-05-23 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 4355.73 | 1005.44 | Unknown | 182.88 | 21.36 | 3146.05 | 3981 | 1091.19 | 4355.73 | -3264.54 | Yes | N/A | N/A | 2024-01-04 | 2024-06-04 | 153 | 109 | 2024-06-04 | 2024-06-04 | 1 | 1 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-11-27 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-09 | 13 | 9 | 2024-12-09 | 2024-12-09 | 1 | 1 | 329 | 235 | 15 | 11 | 344 | 246 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | -7.34 | -6.69 | Unknown | Unknown | Unknown | -0.65 | Unknown | 158.14 | -7.34 | 165.48 | Yes | N/A | N/A | 2023-11-13 | 2023-11-22 | 10 | 8 | 2023-11-22 | 2023-11-22 | 1 | 1 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-11-30 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-26 | 27 | 19 | 2023-12-26 | 2023-12-26 | 1 | 1 | 19 | 15 | 29 | 21 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-05 | 578 | 415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.1 | Unknown | Unknown | Unknown | Unknown | 6.1 | 0 | 1865.12 | 6.1 | 1859.02 | Yes | N/A | N/A | 2023-12-06 | 2023-12-08 | 3 | 3 | 2023-12-08 | 2023-12-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-01-03 | 1 | 1 | 3 | 3 | 23 | 17 | 26 | 20 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-23 | 506 | 361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -362.97 | -17.57 | Unknown | Unknown | -354 | 8.6 | 7530 | 998.58 | -362.97 | 1361.55 | Yes | N/A | N/A | 2022-08-01 | 2023-02-23 | 207 | 149 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2023-09-11 | Unknown | Unknown | 207 | 149 | 0 | 0 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1189-H1 JUNIPERS PH5 | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-08-22 | 482 | 345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 17979.07 | Unknown | Unknown | Unknown | 647.9 | 17331.17 | 3981 | Not available | 17979.07 | Unknown | Yes | N/A | N/A | 2024-01-09 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | 2024-05-07 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | 2024-07-25 | 2024-12-16 | 145 | 103 | 2024-12-16 | 2024-12-16 | 1 | 1 | 0 | 0 | 292 | 208 | 292 | 208 | Steps 2,3,5,6,7 | 75 | 53 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | 599.18 | 349.41 | Unknown | 52 | Unknown | 197.77 | Unknown | 45.46 | 599.18 | -553.72 | Yes | N/A | N/A | 2023-02-21 | 2023-03-23 | 31 | 23 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-06-28 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-06-29 | 2 | 2 | 2023-06-29 | 2023-06-29 | 1 | 1 | 129 | 93 | 3 | 3 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | -6.75 | -4.95 | Unknown | Unknown | Unknown | -1.8 | Unknown | 484.71 | -6.75 | 491.46 | Yes | N/A | N/A | 2023-09-29 | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-09-29 | 75 | 55 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-09 | 36 | 26 | 2023-11-09 | 2023-11-09 | 1 | 1 | 7 | 5 | 112 | 82 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 128.05 | 128.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -346 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-30 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 856.39 | Unknown | Unknown | Unknown | Unknown | 856.39 | 3981 | 1188.83 | 856.39 | 332.44 | Yes | N/A | N/A | 2024-05-13 | 2024-05-30 | 18 | 14 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-09-05 | 99 | 71 | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-05 | 2024-09-10 | 6 | 4 | 2024-09-10 | 2024-09-09 | Unknown | Unknown | 117 | 85 | 7 | 5 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -416 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 911.18 | Unknown | Unknown | Unknown | 71.44 | 839.74 | Unknown | 429.88 | 911.18 | -481.3 | Yes | N/A | N/A | 2023-03-28 | 2023-04-04 | 8 | 6 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2024-01-23 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-24 | 2 | 2 | 2024-01-24 | 2024-01-24 | 1 | 1 | 303 | 217 | 3 | 3 | 306 | 220 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-10 | -488 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 0.69 | -9.29 | Unknown | Unknown | Unknown | 9.98 | Unknown | 973.07 | 0.69 | 972.38 | Yes | N/A | N/A | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-12-12 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-08 | 28 | 20 | 2024-01-08 | 2024-01-08 | 1 | 1 | 86 | 62 | 30 | 22 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-02 | 227 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2023-03-17 | 2023-08-14 | IOU Designed & Installed | N/A | No | N/A | 436.4 | -3.24 | Unknown | Unknown | 7.19 | 432.45 | 3981 | 659.55 | 436.4 | 223.15 | Yes | N/A | N/A | 2022-06-23 | 2023-03-17 | 268 | 192 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | 2023-08-14 | 151 | 107 | Unknown | 2023-07-05 | Unknown | Unknown | 2023-08-14 | 2023-08-21 | 8 | 6 | 2023-08-21 | 2023-08-17 | Unknown | Unknown | 419 | 299 | 8 | 6 | 427 | 305 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-01-24 | 1150 | 822 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-14 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 52.92 | -6.79 | Unknown | Unknown | Unknown | 59.71 | Unknown | 297.38 | 52.92 | 244.46 | Yes | N/A | N/A | 2022-01-14 | 2023-08-03 | 567 | 405 | 2023-08-03 | 2024-01-31 | 182 | 130 | 2023-08-24 | 2023-09-14 | 22 | 16 | 2023-08-03 | 2024-02-02 | 30 | 22 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-03-19 | 1 | 1 | 589 | 421 | 213 | 153 | 802 | 574 | Steps 2,3,5,6,7 | 204 | 146 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -411 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-08-01 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 5518.38 | 294.92 | Unknown | Unknown | -258.19 | 5481.65 | Unknown | 1817.65 | 5518.38 | -3700.73 | Yes | N/A | N/A | 2024-04-23 | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-08-01 | 141 | 101 | 2024-08-01 | 2024-10-25 | 86 | 62 | 2024-08-30 | 2024-11-14 | 20 | 14 | 2024-08-01 | 2024-11-14 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-06 | 23 | 17 | 2024-12-06 | 2024-12-05 | Unknown | Unknown | 192 | 138 | 184 | 132 | 376 | 270 | Steps 2,3,5,6,7 | 161 | 115 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-03 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 196.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-03 | 8 | 6 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-06-17 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-30 | 14 | 10 | 2025-06-30 | 2025-06-30 | 1 | 1 | 84 | 60 | 16 | 12 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Residential | Underserved Community | El Cajon | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | 151 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-08-28 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 101216.64 | 16307.53 | Unknown | 1344.44 | 2982.55 | 80582.12 | 222034 | 45725.51 | 101216.64 | -55491.13 | Yes | N/A | N/A | 2023-07-13 | 2023-08-17 | 36 | 26 | 2023-08-17 | 2024-03-29 | 226 | 162 | 2024-01-02 | 2024-08-23 | 11 | 8 | 2024-03-11 | 2025-02-03 | 71 | 51 | 2024-08-05 | Unknown | Unknown | Unknown | 2024-08-05 | 2024-12-06 | 124 | 90 | 2024-10-09 | 2024-12-16 | 69 | 49 | 2024-12-16 | 2024-12-16 | 1 | 1 | 47 | 34 | 491 | 353 | 538 | 387 | Steps 2,3,5,6,7 | 492 | 354 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 918.23 | -8.71 | Unknown | Unknown | 9.62 | 917.32 | 3981 | 529.38 | 918.23 | -388.85 | Yes | N/A | N/A | 2023-12-11 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2024-01-03 | 35 | 25 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-03-14 | 72 | 52 | Unknown | 2024-03-26 | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 12 | 8 | 2024-03-25 | 2024-03-27 | 3 | 3 | 72 | 52 | 50 | 36 | 122 | 88 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-20 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 0.44 | -12.16 | Unknown | Unknown | Unknown | 12.6 | 3981 | 830.8 | 0.44 | 830.36 | Yes | N/A | N/A | 2023-09-12 | 2023-03-03 | Unknown | Unknown | 2023-03-03 | 2023-09-20 | 202 | 144 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-10-02 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2024-01-24 | 115 | 83 | 2024-01-24 | 2024-01-24 | 1 | 1 | 13 | 9 | 318 | 228 | 331 | 237 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA16 PH2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 438 | 315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-04-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 160373.95 | 33100.55 | Unknown | Unknown | 17832.76 | 109440.64 | 0 | 61291.56 | 160373.95 | -99082.39 | Yes | N/A | N/A | 2022-04-27 | 2023-04-05 | 344 | 246 | 2023-04-05 | 2023-09-15 | 164 | 118 | 2023-05-10 | 2024-04-08 | 291 | 208 | 2023-08-25 | 2024-04-23 | 242 | 170 | 2023-09-19 | Unknown | Unknown | Unknown | 2023-09-19 | 2024-04-22 | 217 | 155 | 2024-04-24 | 2024-05-31 | 38 | 28 | 2024-05-31 | 2024-05-31 | 1 | 1 | 635 | 454 | 662 | 472 | 1297 | 926 | Steps 2,3,5,6,7 | 572 | 408 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 2429 | 2429 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-01-13 | 202 | 145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-02 | 2023-02-14 | 2023-03-24 | IOU Designed & Installed | N/A | No | N/A | 30435.13 | 10707.81 | Unknown | Unknown | Unknown | 19727.32 | 348008 | 3591.68 | 30435.13 | -26843.45 | Yes | N/A | N/A | 2022-06-02 | 2023-03-13 | 285 | 203 | 2023-03-13 | 2023-03-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-08-03 | 133 | 95 | 2023-08-03 | 2023-08-03 | 1 | 1 | 285 | 203 | 138 | 100 | 423 | 303 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 389 | 389 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 11.38 | -10.11 | Unknown | Unknown | Unknown | 21.49 | 3941 | 852.4 | 11.38 | 841.02 | Yes | N/A | N/A | 2024-03-19 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-19 | 42 | 30 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-15 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-30 | 16 | 12 | 2024-04-30 | 2024-04-30 | 1 | 1 | 28 | 20 | 59 | 43 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | -1128.33 | 3137.8 | Unknown | 837.66 | -6453 | 1349.21 | Unknown | 6452.6 | -1128.33 | 7580.93 | Yes | N/A | N/A | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-11-07 | 56 | 40 | 2023-11-07 | 2023-11-07 | 1 | 1 | 1 | 1 | 57 | 41 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | -159 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 23.12 | -20.55 | Unknown | Unknown | Unknown | 43.67 | 3941 | 866.53 | 23.12 | 843.41 | Yes | N/A | N/A | 2023-12-19 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2023-12-19 | 43 | 31 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-05-13 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-20 | 8 | 6 | 2024-05-20 | 2024-05-20 | 1 | 1 | 147 | 105 | 52 | 38 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | -222 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-03-08 | 2023-03-10 | IOU Designed & Installed | N/A | No | N/A | 607.91 | 278.36 | Unknown | 117 | Unknown | 212.55 | Unknown | 363.72 | 607.91 | -244.19 | Yes | N/A | N/A | 2023-02-21 | 2023-03-08 | 16 | 12 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-03-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-06-22 | 105 | 75 | 2023-06-22 | 2023-06-22 | 1 | 1 | 19 | 15 | 106 | 76 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-10 | -318 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-27 | IOU Designed & Installed | N/A | No | N/A | 2245.18 | 1753.43 | Unknown | 809.56 | -1619 | 1301.19 | Unknown | 1618.52 | 2245.18 | -626.66 | Yes | N/A | N/A | 2023-02-28 | 2023-03-01 | 2 | 2 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2023-03-29 | 3 | 3 | 2023-03-29 | 2023-03-29 | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 60.34 | Unknown | Unknown | Unknown | Unknown | 60.34 | 3981 | 1558.07 | 60.34 | 1497.73 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-14 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-24 | 42 | 30 | 2024-09-24 | 2024-09-24 | 1 | 1 | 3 | 3 | 44 | 32 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 5672.05 | 5672.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-10 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -117.55 | -24.81 | Unknown | Unknown | -1436 | 1343.26 | Unknown | 1191.14 | -117.55 | 1308.69 | Yes | N/A | N/A | 2024-07-30 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-11-14 | 274 | 196 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-09-05 | 31 | 23 | 2024-11-14 | 2024-12-17 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-27 | Unknown | Unknown | 34 | 24 | 305 | 219 | 339 | 243 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-05 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | 23383.3 | -205.08 | Unknown | Unknown | 28.36 | 23560.02 | Unknown | 4980.09 | 23383.3 | -18403.21 | Yes | N/A | N/A | 2023-04-12 | 2023-04-18 | 7 | 5 | 2023-04-18 | 2023-06-29 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-18 | 9 | 7 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-09-06 | 29 | 21 | 2023-09-06 | 2023-09-06 | 1 | 1 | 7 | 5 | 112 | 82 | 119 | 87 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | -7.34 | -8.06 | Unknown | Unknown | Unknown | 0.72 | Unknown | 158.37 | -7.34 | 165.71 | Yes | N/A | N/A | 2024-01-23 | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-02-09 | 36 | 26 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-29 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-18 | 19 | 13 | 2024-03-18 | 2024-03-18 | 1 | 1 | 21 | 15 | 56 | 40 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -690 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 147.23 | -2.19 | Unknown | Unknown | Unknown | 149.42 | 3981 | 1588.64 | 147.23 | 1441.41 | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-24 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-12 | 17 | 13 | 2025-03-12 | 2025-03-12 | 1 | 1 | 19 | 13 | 19 | 15 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -374 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20.28 | Unknown | Unknown | Unknown | Unknown | 20.28 | 0 | 1058.41 | 20.28 | 1038.13 | Yes | N/A | N/A | 2024-03-20 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | 2024-03-20 | 115 | 83 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-10-23 | 1 | 1 | 0 | 0 | 116 | 84 | 116 | 84 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-06 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 98.76 | -1.26 | Unknown | Unknown | Unknown | 100.02 | Unknown | 1408.24 | 98.76 | 1309.48 | Yes | N/A | N/A | 2024-05-29 | 2024-06-06 | 9 | 7 | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-19 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-01 | 14 | 10 | 2024-08-01 | 2024-08-01 | 1 | 1 | 52 | 38 | 16 | 12 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 443.5 | 443.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | -284 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-10-17 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 144442.96 | 36191.76 | Unknown | Unknown | 225.38 | 108025.82 | Unknown | 59634.02 | 144442.96 | -84808.94 | Yes | N/A | N/A | 2024-04-26 | 2024-10-07 | 165 | 117 | 2024-10-07 | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-02 | 2025-03-20 | 48 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-05-06 | 36 | 26 | 2025-05-06 | 2025-05-06 | 1 | 1 | 166 | 118 | 85 | 63 | 251 | 181 | Steps 2,3,5,6,7 | 9 | 7 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 100 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 3810.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-10 | 182 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-24 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 10865.53 | 29.76 | Unknown | Unknown | 59.79 | 10775.98 | 45372 | 3206.65 | 10865.53 | -7658.88 | Yes | N/A | N/A | 2023-05-17 | 2023-05-22 | 6 | 4 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | 2024-01-03 | 2024-01-09 | 7 | 5 | 2024-01-09 | 2024-01-08 | Unknown | Unknown | 6 | 4 | 7 | 5 | 13 | 9 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 1203.29 | -8.57 | Unknown | Unknown | 3.75 | 1208.11 | Unknown | 613.57 | 1203.29 | -589.72 | Yes | N/A | N/A | 2023-03-17 | 2023-05-19 | 64 | 46 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-06-02 | 15 | 11 | 2023-05-19 | 2023-07-26 | 69 | 49 | Unknown | 2023-07-25 | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-07-26 | 1 | 1 | 133 | 95 | 17 | 13 | 150 | 108 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 CMR PA10 WO4 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 649 | 465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-30 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 37122.52 | 442.37 | Unknown | Unknown | Unknown | 36680.15 | 50111 | Not available | 37122.52 | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-24 | 3 | 3 | 2024-10-24 | 2024-10-30 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-03-10 | 132 | 94 | Unknown | 2025-03-13 | Unknown | Unknown | 2024-12-18 | 2024-12-30 | 13 | 9 | 2024-12-30 | 2024-12-28 | Unknown | Unknown | 135 | 97 | 20 | 14 | 155 | 111 | Steps 2,3,5,6,7 | 85 | 61 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -653 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-18 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 1321.69 | -25.7 | Unknown | Unknown | Unknown | 1347.39 | Unknown | 1733.21 | 1321.69 | 411.52 | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | 2024-12-18 | 30 | 22 | 2024-12-18 | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-26 | 8 | 6 | 2024-12-18 | 2025-01-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-24 | 9 | 7 | 2025-01-24 | 2025-01-24 | 1 | 1 | 31 | 23 | 48 | 36 | 79 | 59 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 315 | 226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-05 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 491.07 | -10.2 | Unknown | Unknown | Unknown | 501.27 | 3241 | 885.93 | 491.07 | 394.86 | Yes | N/A | N/A | 2024-04-03 | 2024-04-05 | 3 | 3 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | 2024-09-17 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-06-19 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-10-09 | 113 | 81 | 2024-10-09 | 2024-10-10 | 2 | 2 | 245 | 175 | 116 | 84 | 361 | 259 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 90 | 90 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -339 | -244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 6408.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-05 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-27 | 23 | 17 | 2025-05-27 | 2025-05-27 | 1 | 1 | 13 | 9 | 24 | 18 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | -513 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-05-01 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | -94.52 | Unknown | Unknown | Unknown | -1122.73 | 1028.21 | Unknown | 1130.33 | -94.52 | 1224.85 | Yes | N/A | N/A | 2024-04-24 | 2024-05-21 | 28 | 20 | 2024-05-21 | 2024-05-30 | 10 | 8 | 2024-05-30 | 2024-06-10 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-10-02 | 115 | 83 | Unknown | 2024-09-25 | Unknown | Unknown | 2024-10-02 | 2024-10-24 | 23 | 17 | 2024-10-24 | 2024-10-24 | 1 | 1 | 155 | 111 | 34 | 26 | 189 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-02-10 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | -4.4 | -18.46 | Unknown | Unknown | Unknown | 14.06 | Unknown | 1600.11 | -4.4 | 1604.51 | Yes | N/A | N/A | 2025-01-02 | 2025-01-31 | 30 | 22 | 2025-01-31 | 2025-02-10 | 11 | 7 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-24 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-04-07 | 15 | 11 | 2025-04-07 | 2025-04-07 | 1 | 1 | 72 | 52 | 27 | 19 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | -177 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-30 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 1780.93 | 320.75 | Unknown | 30.16 | Unknown | 1430.02 | 7222 | 153.87 | 1780.93 | -1627.06 | Yes | N/A | N/A | 2023-06-20 | 2023-06-30 | 11 | 9 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-18 | 15 | 11 | 2023-12-18 | 2023-12-18 | 1 | 1 | 11 | 9 | 16 | 12 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -565 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 38.07 | Unknown | Unknown | Unknown | 2.36 | 35.71 | Unknown | 1616.98 | 38.07 | 1578.91 | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-07 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2025-01-13 | 68 | 48 | 2025-01-13 | 2025-01-13 | 1 | 1 | 17 | 13 | 70 | 50 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 270.05 | 270.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | 114 | 83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.17 | Unknown | Unknown | Unknown | Unknown | -0.17 | Unknown | 19703.08 | -0.17 | 19703.25 | Yes | N/A | N/A | 2024-04-30 | 2024-05-09 | 10 | 8 | 2024-05-09 | 2024-09-19 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-11-07 | 30 | 22 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1 | 1 | 10 | 8 | 165 | 119 | 175 | 127 | Steps 2,3,5,6,7 | 49 | 35 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 81 | 58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | 2022-05-31 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 3979.87 | 4249.09 | Unknown | 685.19 | -2749 | 1794.59 | Unknown | 2749.08 | 3979.87 | -1230.79 | Yes | N/A | N/A | 2022-05-02 | 2023-05-19 | 383 | 275 | 2023-05-19 | 2023-05-20 | 2 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | 2023-06-06 | Unknown | Unknown | 383 | 275 | 3 | 2 | 386 | 277 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | -362 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1417.3 | 808.24 | Unknown | 245.44 | Unknown | 363.62 | 3241 | 1086.86 | 1417.3 | -330.44 | Yes | N/A | N/A | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2025-04-01 | 299 | 213 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-03 | 3 | 3 | 2025-04-03 | 2025-04-03 | 1 | 1 | 300 | 214 | 5 | 5 | 305 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 49.05 | 49.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -514 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-24 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1320.64 | 671.48 | Unknown | 46.77 | -1277 | 1879.39 | Unknown | 1134.09 | 1320.64 | -186.55 | Yes | N/A | N/A | 2025-01-15 | 2025-01-24 | 10 | 8 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-02-04 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-03 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-04 | 2 | 2 | 2025-02-04 | 2025-06-10 | 127 | 91 | 26 | 18 | 130 | 94 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 219 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3751.14 | Unknown | Unknown | Unknown | Unknown | 3751.14 | 77937 | 10822.19 | 3751.14 | 7071.05 | Yes | N/A | N/A | 2023-09-21 | 2023-09-18 | Unknown | Unknown | 2023-09-18 | 2023-11-30 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-10-14 | 320 | 228 | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | 2024-06-07 | 2024-06-07 | 1 | 1 | 320 | 228 | 75 | 55 | 395 | 283 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 701.37 | -13.59 | Unknown | Unknown | Unknown | 714.96 | Unknown | 52.54 | 701.37 | -648.83 | Yes | N/A | N/A | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | 2025-01-29 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-19 | 30 | 22 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 1 | 149 | 107 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-03 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 298.66 | -4.5 | Unknown | Unknown | Unknown | 303.16 | Unknown | 3567.13 | 298.66 | 3268.47 | Yes | N/A | N/A | 2024-12-02 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-12-05 | 21 | 15 | 2024-12-05 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-17 | 4 | 4 | 2024-12-05 | 2025-02-25 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-24 | 28 | 20 | 2025-03-24 | 2025-03-24 | 1 | 1 | 83 | 59 | 54 | 40 | 137 | 99 | Steps 2,3,5,6,7 | 43 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 1142.05 | 1142.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-03 | 31 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.2 | -7.49 | Unknown | Unknown | Unknown | -1.71 | Unknown | 464.78 | -9.2 | 473.98 | Yes | N/A | N/A | 2023-05-11 | 2023-06-01 | 22 | 16 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-03 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -521 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.43 | -3.93 | Unknown | Unknown | Unknown | -1.5 | Unknown | 154.79 | -5.43 | 160.22 | Yes | N/A | N/A | 2023-03-23 | 2023-04-04 | 13 | 9 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-06-14 | 1 | 1 | 13 | 9 | 1 | 1 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 122 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 1284.22 | 444.91 | Unknown | Unknown | 18.65 | 820.66 | 3981 | 1414.29 | 1284.22 | 130.07 | Yes | N/A | N/A | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-11-29 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-02-06 | 70 | 50 | 2024-02-06 | 2023-12-01 | Unknown | Unknown | 127 | 91 | 70 | 50 | 197 | 141 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 92.1 | 92.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -9 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | -363.25 | Unknown | Unknown | Unknown | -434 | 70.75 | Unknown | 433.51 | -363.25 | 796.76 | Yes | N/A | N/A | 2024-12-05 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-12-05 | 9 | 7 | 2024-12-05 | 2024-12-13 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-22 | 41 | 29 | 2025-01-22 | 2025-01-22 | 1 | 1 | 10 | 8 | 51 | 37 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2273.27 | 2273.27 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-27 | -59 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 593.45 | -48.77 | Unknown | Unknown | Unknown | 642.22 | 99525 | 834.21 | 593.45 | 240.76 | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | 2023-05-09 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-11-20 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2023-12-30 | Unknown | Unknown | 197 | 141 | 16 | 12 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -304 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | -914.79 | 2016.62 | Unknown | 513.38 | -4278 | 833.21 | Unknown | 3786.63 | -914.79 | 4701.42 | Yes | N/A | N/A | 2023-09-08 | 2023-09-13 | 6 | 4 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-07 | 27 | 19 | 2023-11-07 | 2023-11-07 | 1 | 1 | 6 | 4 | 28 | 20 | 34 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 1113.15 | -6.36 | Unknown | Unknown | 23.14 | 1096.37 | 3981 | 783.78 | 1113.15 | -329.37 | Yes | N/A | N/A | 2024-01-09 | 2024-03-07 | 59 | 43 | 2024-03-07 | 2025-03-06 | 365 | 261 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-29 | 54 | 38 | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-29 | 2024-05-15 | 17 | 13 | 2024-05-15 | 2024-05-14 | Unknown | Unknown | 113 | 81 | 382 | 274 | 495 | 355 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-17 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 883.32 | -14.05 | Unknown | Unknown | -522.12 | 1419.49 | Unknown | 534.97 | 883.32 | -348.35 | Yes | N/A | N/A | 2023-02-23 | 2023-03-22 | 28 | 20 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2023-08-07 | 1 | 1 | 28 | 20 | 1 | 1 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -453 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 64171.1 | 5517.85 | Unknown | Unknown | 1078.84 | 57574.41 | 3981 | 2320.88 | 64171.1 | -61850.22 | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | 2024-09-23 | 7 | 5 | 2025-02-12 | 2025-02-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-11-26 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-15 | 140 | 100 | 2025-04-15 | 2025-04-11 | Unknown | Unknown | 67 | 49 | 147 | 105 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1467.27 | -0.63 | Unknown | Unknown | -1596 | 129.36 | Unknown | 1595.77 | -1467.27 | 3063.04 | Yes | N/A | N/A | 2025-01-17 | 2025-01-18 | 2 | 1 | 2025-01-18 | 2025-02-03 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-19 | 22 | 16 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-07 | 1 | 1 | 2 | 1 | 40 | 28 | 42 | 29 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | 232 | 167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20518.2 | 14571.51 | Unknown | 2272.77 | -6328 | 10001.92 | Unknown | 6328.44 | 20518.2 | -14189.76 | Yes | N/A | N/A | 2024-02-09 | 2024-04-26 | 78 | 56 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2024-12-05 | 1 | 1 | 78 | 56 | 1 | 1 | 79 | 57 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -408 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-01-19 | 2024-03-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 409912.82 | 76738.7 | Unknown | 961.94 | 8888.92 | 323323.26 | 651254 | 189323.15 | 409912.82 | -220589.67 | Yes | N/A | N/A | 2023-01-19 | 2023-07-31 | 194 | 138 | 2023-07-31 | 2023-10-23 | 85 | 61 | 2023-08-30 | 2024-08-05 | 61 | 43 | 2023-03-31 | 2025-02-26 | 136 | 102 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-11-20 | 360 | 258 | 2024-03-22 | 2025-03-12 | 356 | 254 | 2025-03-12 | 2024-12-20 | Unknown | Unknown | 255 | 181 | 937 | 675 | 1192 | 856 | Steps 2,3,5,6,7 | 790 | 562 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 232.15 | 232.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 427 | 306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1419.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-16 | 2024-03-05 | 142 | 102 | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | 2025-08-20 | 2025-01-31 | Unknown | Unknown | 142 | 102 | 1 | 1 | 143 | 103 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1105.12 | Unknown | Unknown | Unknown | 11.78 | 1093.34 | 3981 | 1221.84 | 1105.12 | 116.72 | Yes | N/A | N/A | 2024-08-14 | 2024-09-19 | 37 | 27 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-18 | 30 | 22 | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-18 | 2024-11-04 | 18 | 12 | 2024-11-04 | 2024-10-31 | Unknown | Unknown | 67 | 49 | 19 | 13 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-22 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 37.94 | Unknown | Unknown | Unknown | Unknown | 37.94 | Unknown | 1487.88 | 37.94 | 1449.94 | Yes | N/A | N/A | 2024-04-30 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-05-22 | 44 | 32 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-07-11 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-31 | 21 | 15 | 2024-07-31 | 2024-07-31 | 1 | 1 | 51 | 37 | 66 | 48 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -619 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 371.25 | Unknown | Unknown | Unknown | 1.2 | 370.05 | Unknown | 1092.74 | 371.25 | 721.49 | Yes | N/A | N/A | 2024-09-11 | 2024-09-30 | 20 | 14 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-07 | 31 | 23 | 2024-11-07 | 2024-11-07 | 1 | 1 | 25 | 17 | 33 | 25 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -409 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-05 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 673.71 | -10.92 | Unknown | Unknown | 5.59 | 679.04 | 3981 | 2018.81 | 673.71 | 1345.1 | Yes | N/A | N/A | 2023-03-22 | 2023-04-14 | 24 | 18 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-12-18 | 249 | 177 | Unknown | 2023-11-17 | Unknown | Unknown | 2023-12-18 | 2023-12-27 | 10 | 8 | 2023-12-27 | 2023-12-27 | 1 | 1 | 273 | 195 | 11 | 9 | 284 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -109 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3902.6 | 1391.18 | Unknown | 338.76 | -6545 | 912.46 | Unknown | 6545.09 | -3902.6 | 10447.69 | Yes | N/A | N/A | 2024-02-12 | 2024-02-14 | 3 | 3 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-02-26 | 14 | 10 | Unknown | 2024-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 3 | 3 | 15 | 11 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 1862 | 1862 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-08 | 37 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 35.33 | Unknown | Unknown | Unknown | Unknown | 35.33 | 3941 | 949.46 | 35.33 | 914.13 | Yes | N/A | N/A | 2024-05-07 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-05-07 | 99 | 71 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-14 | Unknown | Unknown | 0 | 0 | 99 | 71 | 99 | 71 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2034-08-03 | -4012 | -2867 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | 740.14 | -27.29 | Unknown | Unknown | Unknown | 767.43 | 3981 | 824.56 | 740.14 | 84.42 | Yes | N/A | N/A | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-09 | 2 | 2 | 2023-08-09 | 2023-08-09 | 1 | 1 | 3 | 3 | 4 | 4 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -182 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 941.81 | -28.37 | Unknown | Unknown | Unknown | 970.18 | Unknown | 833.52 | 941.81 | -108.29 | Yes | N/A | N/A | 2023-12-15 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-12-15 | 74 | 54 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-02 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-02-01 | 31 | 23 | 2024-02-01 | 2024-02-01 | 1 | 1 | 19 | 13 | 106 | 78 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | -215 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2175.93 | Unknown | Unknown | Unknown | 3.88 | 2172.05 | 3981 | 1051.21 | 2175.93 | -1124.72 | Yes | N/A | N/A | 2024-06-27 | 2024-08-05 | 40 | 28 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 40 | 28 | 2 | 2 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 1857.06 | -36.65 | Unknown | Unknown | Unknown | 1893.71 | Unknown | 1769.85 | 1857.06 | -87.21 | Yes | N/A | N/A | 2024-11-20 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-20 | 13 | 9 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-05 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-24 | 51 | 37 | 2025-01-24 | 2025-01-24 | 1 | 1 | 16 | 12 | 65 | 47 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 4031.25 | 4031.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-03 | 79 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2761.35 | -8.58 | Unknown | Unknown | 60.59 | 2709.34 | 19905 | 1434.18 | 2761.35 | -1327.17 | Yes | N/A | N/A | 2023-08-09 | 2023-08-29 | 21 | 15 | 2023-08-29 | 2023-10-05 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-17 | 13 | 9 | 2023-10-05 | 2024-10-09 | 371 | 265 | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-10-21 | Unknown | Unknown | 392 | 280 | 51 | 37 | 443 | 317 | Steps 2,3,5,6,7 | 12 | 8 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-30 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 784.15 | 294.21 | Unknown | Unknown | Unknown | 489.94 | 3885 | 904.75 | 784.15 | 120.6 | Yes | N/A | N/A | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-11-08 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-07 | 30 | 22 | 2023-12-07 | 2023-12-07 | 1 | 1 | 65 | 47 | 32 | 24 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 361.39 | Unknown | Unknown | Unknown | 4.77 | 356.62 | Unknown | 1160.82 | 361.39 | 799.43 | Yes | N/A | N/A | 2024-07-10 | 2024-07-18 | 9 | 7 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-20 | 34 | 24 | Unknown | 2024-08-14 | Unknown | Unknown | 2024-08-20 | 2024-09-04 | 16 | 12 | 2024-09-04 | 2024-09-04 | 1 | 1 | 43 | 31 | 18 | 14 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | Applicant Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-01 | 811 | 580 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-11 | 2022-02-11 | 2024-02-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 94089.87 | 15777.55 | Unknown | Unknown | 3263.66 | 75048.66 | 21267.57 | 29777.16 | 94089.87 | -64312.71 | Yes | N/A | N/A | 2022-02-11 | 2023-07-10 | 515 | 367 | 2023-07-10 | 2024-01-17 | 192 | 138 | 2023-07-18 | 2024-01-11 | 56 | 40 | 2023-08-31 | 2024-01-31 | 137 | 97 | 2024-01-24 | Unknown | Unknown | Unknown | 2024-01-24 | 2024-07-18 | 177 | 127 | 2024-02-01 | 2024-08-20 | 202 | 144 | 2024-08-20 | 2024-08-20 | 1 | 1 | 571 | 407 | 709 | 507 | 1280 | 914 | Steps 2,3,5,6,7 | 491 | 351 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -214 | -155 | No | 2025-01-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | 2025-02-25 | IOU Designed & Installed | N/A | Yes | 62 | 206.79 | Unknown | Unknown | Unknown | -1217.26 | 1424.05 | Unknown | 1226.81 | 206.79 | 1020.02 | Yes | N/A | N/A | 2025-01-23 | 2025-03-25 | 62 | 44 | 2025-03-25 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-03-28 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-25 | 14 | 10 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-02-25 | 2025-06-09 | 105 | 75 | 2025-06-09 | 2025-06-09 | 1 | 1 | 121 | 87 | 106 | 76 | 227 | 163 | Steps 2,3,5,6,7 | 85 | 61 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -508 | -364 | No | 2024-09-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-03-04 | IOU Designed & Installed | N/A | Yes | 63 | 1279.16 | -11.87 | Unknown | Unknown | 19.33 | 1271.7 | 3981 | 1442.94 | 1279.16 | 163.78 | Yes | N/A | N/A | 2024-09-10 | 2024-11-12 | 64 | 46 | 2024-11-12 | 2024-10-04 | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-03-04 | 149 | 107 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-03-04 | 2025-03-26 | 23 | 17 | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 213 | 153 | 23 | 17 | 236 | 170 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-20 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | -406.53 | Unknown | Unknown | Unknown | -536 | 129.47 | Unknown | 2031.41 | -406.53 | 2437.94 | Yes | N/A | N/A | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | 2025-02-25 | 7 | 5 | 2025-02-25 | 2025-04-16 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-25 | 8 | 6 | 2025-06-25 | 2025-06-25 | 1 | 1 | 73 | 53 | 16 | 12 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | SPRING VALLEY | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -378 | -271 | No | 2024-12-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-02-24 | IOU Designed & Installed | N/A | Yes | 53 | 1044.03 | -20.4 | Unknown | Unknown | Unknown | 1064.43 | 3241 | 1783.6 | 1044.03 | 739.57 | Yes | N/A | N/A | 2024-12-19 | 2025-02-07 | 51 | 37 | 2025-02-07 | 2025-02-10 | 4 | 2 | 2025-02-10 | 2025-03-24 | 41 | 29 | 2025-03-24 | 2025-03-31 | 8 | 6 | 2024-12-20 | 2025-02-24 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | 2025-05-16 | 79 | 57 | 159 | 113 | 95 | 69 | 254 | 182 | Steps 2,3,5,6,7 | 101 | 71 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-06 | 306 | 219 | No | 2022-09-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | 2023-02-15 | IOU Designed & Installed | N/A | Yes | 167 | 22.86 | -14.97 | Unknown | Unknown | 5.42 | 32.41 | Unknown | 608.12 | 22.86 | 585.26 | Yes | N/A | N/A | 2022-09-13 | 2023-02-27 | 168 | 120 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-13 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-06-08 | 114 | 82 | 2023-06-08 | 2023-06-08 | 1 | 1 | 168 | 120 | 115 | 83 | 283 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | -569 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-15 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1736.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2025-01-15 | 21 | 15 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-05-20 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-27 | 8 | 6 | 2025-05-27 | 2025-05-22 | Unknown | Unknown | 126 | 90 | 29 | 21 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-17 | -698 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1139.38 | -21.9 | Unknown | Unknown | Unknown | 1161.28 | 3981 | 1576.21 | 1139.38 | 436.83 | Yes | N/A | N/A | 2024-11-20 | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-20 | 3 | 3 | 2024-11-20 | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-10 | 21 | 15 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | 0 | 0 | 25 | 19 | 25 | 19 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 48745.69 | 951.48 | Unknown | Unknown | 917.36 | 46876.85 | Unknown | 22666.88 | 48745.69 | -26078.81 | Yes | N/A | N/A | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | 2024-12-06 | 143 | 103 | 2024-08-27 | 2024-09-12 | 17 | 13 | 2024-08-13 | 2024-11-12 | 42 | 30 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-09 | 114 | 82 | 2025-04-09 | 2025-04-09 | 1 | 1 | 18 | 14 | 300 | 216 | 318 | 230 | Steps 2,3,5,6,7 | 131 | 95 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-02 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1832.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-02 | 16 | 12 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-06-09 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-20 | 12 | 10 | 2025-06-20 | 2025-06-20 | 1 | 1 | 39 | 27 | 29 | 23 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-18 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 1263 | 440.81 | Unknown | Unknown | Unknown | 822.19 | 3981 | 1471.32 | 1263 | 208.32 | Yes | N/A | N/A | 2024-06-13 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-18 | 69 | 49 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-18 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-16 | 30 | 22 | 2024-08-16 | 2024-08-15 | Unknown | Unknown | 31 | 23 | 99 | 71 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -537 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-09-19 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 0.66 | -8.99 | Unknown | Unknown | Unknown | 9.65 | Unknown | 932.32 | 0.66 | 931.66 | Yes | N/A | N/A | 2023-08-31 | 2023-09-19 | 20 | 14 | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-12-05 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-11 | 7 | 5 | 2023-12-11 | 2023-12-11 | 1 | 1 | 98 | 70 | 9 | 7 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -296 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | -400.17 | 409.4 | Unknown | Unknown | -1742 | 932.43 | Unknown | 1623.06 | -400.17 | 2023.23 | Yes | N/A | N/A | 2024-08-07 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-10-07 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-08 | 2 | 2 | 2024-10-08 | 2024-10-08 | 1 | 1 | 57 | 41 | 3 | 3 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | 104 | 75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-08-15 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 186.1 | Unknown | Unknown | Unknown | -1091 | 1277.1 | Unknown | 1090.55 | 186.1 | 904.45 | Yes | N/A | N/A | 2024-07-18 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-08-15 | 32 | 24 | 2024-08-15 | 2024-08-21 | 7 | 5 | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | 2024-10-09 | 50 | 36 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-09 | 2024-10-11 | 3 | 3 | 2024-10-11 | 2024-10-11 | 1 | 1 | 57 | 41 | 37 | 29 | 94 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -159 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.8 | Unknown | Unknown | Unknown | Unknown | 6.8 | 0 | 203.23 | 6.8 | 196.43 | Yes | N/A | N/A | 2024-01-08 | 2024-01-18 | 11 | 9 | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 11 | 9 | 2 | 2 | 13 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -520 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-18 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1628.56 | Unknown | Unknown | Unknown | 29.6 | 1598.96 | 3981 | 953.62 | 1628.56 | -674.94 | Yes | N/A | N/A | 2024-06-14 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-06-24 | 49 | 35 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-10-18 | 109 | 79 | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-18 | 2024-10-31 | 14 | 10 | 2024-10-31 | 2024-10-24 | Unknown | Unknown | 109 | 79 | 63 | 45 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | 8 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-17 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 1137.92 | -7.56 | Unknown | Unknown | 16.07 | 1129.41 | 3981 | 760.44 | 1137.92 | -377.48 | Yes | N/A | N/A | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-05-20 | 173 | 123 | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-20 | 2024-05-24 | 5 | 5 | 2024-05-24 | 2024-05-25 | 2 | 1 | 174 | 124 | 7 | 6 | 181 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 251.66 | -2.19 | Unknown | Unknown | 3.74 | 250.11 | 3981 | 186.52 | 251.66 | -65.14 | Yes | N/A | N/A | 2024-08-22 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-09-10 | 70 | 50 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-23 | 44 | 32 | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-23 | 2024-11-21 | 30 | 22 | 2024-11-21 | 2024-11-21 | 1 | 1 | 44 | 32 | 101 | 73 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9512 | 9512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-04-03 | 393 | 282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 523.33 | -10.49 | Unknown | Unknown | 0.88 | 532.94 | 7962 | 1080 | 523.33 | 556.67 | Yes | N/A | N/A | 2024-06-14 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2024-07-10 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2025-04-03 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-01 | Unknown | Unknown | 268 | 192 | 324 | 232 | 592 | 424 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 2522.87 | 520.33 | Unknown | Unknown | Unknown | 2002.54 | Unknown | 1262.46 | 2522.87 | -1260.41 | Yes | N/A | N/A | 2024-01-30 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2024-01-30 | 98 | 70 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-04-17 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-06 | 20 | 14 | 2024-05-06 | 2024-05-06 | 1 | 1 | 79 | 57 | 119 | 85 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-05 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 926.65 | Unknown | Unknown | Unknown | Unknown | 926.65 | 3981 | 1169.31 | 926.65 | 242.66 | Yes | N/A | N/A | 2024-08-21 | 2024-09-09 | 20 | 14 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2025-03-05 | 178 | 128 | Unknown | 2025-02-05 | Unknown | Unknown | 2025-03-05 | 2025-03-11 | 7 | 5 | 2025-03-11 | 2025-03-11 | 1 | 1 | 198 | 142 | 9 | 7 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 758.21 | -22.43 | Unknown | Unknown | 10.88 | 769.76 | 3981 | 981.61 | 758.21 | 223.4 | Yes | N/A | N/A | 2022-11-28 | 2023-04-18 | 142 | 102 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-05-05 | 18 | 14 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-09-14 | 1 | 1 | 142 | 102 | 19 | 15 | 161 | 117 | Steps 2,3,5,6,7 | 18 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -205 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 610 | -8.31 | Unknown | Unknown | 20.28 | 598.03 | 2875.23 | 582.04 | 610 | -27.96 | Yes | N/A | N/A | 2023-10-26 | 2023-10-27 | 2 | 2 | 2023-10-27 | 2023-11-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-12-28 | 57 | 41 | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-16 | Unknown | Unknown | 59 | 43 | 7 | 5 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -683 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 526.85 | -10.2 | Unknown | Unknown | Unknown | 537.05 | 3981 | 1472.98 | 526.85 | 946.13 | Yes | N/A | N/A | 2024-10-09 | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-09 | 3 | 3 | 2024-10-09 | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-24 | 15 | 11 | 2024-10-09 | 2024-10-29 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-18 | 21 | 15 | 2024-11-18 | 2024-11-18 | 1 | 1 | 21 | 15 | 40 | 30 | 61 | 45 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-31 | 610 | 437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 754.64 | -23.13 | Unknown | Unknown | -276.6 | 1054.37 | Unknown | 222.67 | 754.64 | -531.97 | Yes | N/A | N/A | 2024-04-04 | 2024-04-12 | 9 | 7 | 2024-04-12 | 2024-04-16 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-02 | 1 | 1 | 9 | 7 | 6 | 4 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | -56 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | -770.49 | Unknown | Unknown | Unknown | -803 | 32.51 | Unknown | 803.38 | -770.49 | 1573.87 | Yes | N/A | N/A | 2024-05-20 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-07-22 | 111 | 79 | 2024-07-22 | 2024-11-25 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2025-01-09 | 128 | 92 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-01-09 | 2025-01-23 | 15 | 11 | 2025-01-23 | 2025-01-23 | 1 | 1 | 255 | 183 | 127 | 91 | 382 | 274 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-16 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 1286.03 | Unknown | Unknown | Unknown | 12.76 | 1273.27 | 3981 | 1384.24 | 1286.03 | 98.21 | Yes | N/A | N/A | 2024-01-02 | 2024-06-10 | 161 | 115 | 2024-06-10 | 2024-06-13 | 4 | 4 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2025-06-05 | 358 | 256 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-06-05 | 2025-06-06 | 2 | 2 | 2025-06-06 | 2025-06-06 | 1 | 1 | 519 | 371 | 7 | 7 | 526 | 378 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 242.35 | 242.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | -332 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 11163.01 | -49.3 | Unknown | Unknown | Unknown | 11212.31 | Unknown | 5317.05 | 11163.01 | -5845.96 | Yes | N/A | N/A | 2024-07-23 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-11-05 | 28 | 20 | 2024-11-05 | 2024-11-05 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 448.36 | -9.21 | Unknown | Unknown | Unknown | 457.57 | 3981 | 1641.25 | 448.36 | 1192.89 | Yes | N/A | N/A | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-04-17 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-12 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-05-20 | 70 | 50 | 2025-05-20 | 2025-05-20 | 1 | 1 | 91 | 65 | 72 | 52 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-07 | 407 | 292 | No | 2023-03-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | Yes | 317 | 13.01 | -11.6 | Unknown | Unknown | Unknown | 24.61 | 3981 | 858.12 | 13.01 | 845.11 | Yes | N/A | N/A | 2023-03-30 | 2024-02-08 | 316 | 226 | 2024-02-08 | 2024-02-10 | 3 | 2 | 2024-02-10 | Unknown | Unknown | Unknown | 2023-06-09 | 2023-06-23 | 15 | 11 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-03-20 | 15 | 11 | 316 | 226 | 33 | 24 | 349 | 250 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-13 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 4.84 | Unknown | Unknown | Unknown | Unknown | 4.84 | 3961 | 192.51 | 4.84 | 187.67 | Yes | N/A | N/A | 2024-06-07 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-16 | 64 | 46 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-10-16 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-05 | 21 | 15 | 2024-11-05 | 2024-11-05 | 1 | 1 | 93 | 67 | 86 | 62 | 179 | 129 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-28 | 682 | 489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-09 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -992.78 | -15.28 | Unknown | Unknown | -1010 | 32.5 | 3981 | 1432.27 | -992.78 | 2425.05 | Yes | N/A | N/A | 2021-08-09 | 2023-04-18 | 618 | 442 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-05-10 | Unknown | Unknown | 618 | 442 | 0 | 0 | 618 | 442 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 64 | 46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-05 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 9399.25 | -102.42 | Unknown | Unknown | Unknown | 9501.67 | Unknown | 3241.7 | 9399.25 | -6157.55 | Yes | N/A | N/A | 2022-11-17 | 2023-05-05 | 170 | 122 | 2023-05-05 | 2023-10-19 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-18 | 22 | 16 | 2023-12-18 | 2023-12-18 | 1 | 1 | 170 | 122 | 191 | 137 | 361 | 259 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA HILLS | LAGUNA HILLS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-02 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 243.48 | Unknown | Unknown | Unknown | Unknown | 243.48 | Unknown | 444.8 | 243.48 | 201.32 | Yes | N/A | N/A | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-09 | 25 | 19 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-21 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2615179 | 2615179 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-09-05 | 609 | 436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-15 | 2023-03-22 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 253348.24 | 96600.27 | Unknown | Unknown | -49371.1 | 206119.07 | 1796263.82 | 232456.07 | 253348.24 | -20892.17 | Yes | N/A | N/A | 2022-06-15 | 2024-03-19 | 644 | 460 | 2024-03-19 | 2024-06-05 | 79 | 57 | 2023-11-13 | 2024-08-29 | 20 | 16 | 2024-01-26 | 2024-05-22 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2025-05-19 | 197 | 141 | 2025-02-05 | 2025-05-06 | 91 | 65 | 2025-05-06 | 2025-05-06 | 1 | 1 | 664 | 476 | 400 | 288 | 1064 | 764 | Steps 2,3,5,6,7 | 524 | 374 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 904.05 | 904.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | -46 | -34 | No | 2022-09-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-09-28 | Unknown | IOU Designed & Installed | N/A | Yes | 527 | 603.35 | -15.91 | Unknown | Unknown | 3.47 | 615.79 | 3981 | 1222.59 | 603.35 | 619.24 | Yes | N/A | N/A | 2022-09-28 | 2024-03-01 | 521 | 373 | 2024-03-01 | 2024-03-08 | 8 | 6 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-29 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-06-04 | Unknown | Unknown | 521 | 373 | 8 | 6 | 529 | 379 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-29 | -11 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 1049.86 | 109.72 | Unknown | Unknown | 72.03 | 868.11 | 3981 | 688.99 | 1049.86 | -360.87 | Yes | N/A | N/A | 2024-07-16 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-08-16 | 50 | 36 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2025-06-18 | 307 | 219 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 307 | 219 | 52 | 38 | 359 | 257 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | -572 | -410 | No | 2025-02-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-25 | 2025-06-03 | IOU Designed & Installed | N/A | Yes | 65 | 9006.18 | 2400.43 | Unknown | Unknown | Unknown | 6605.75 | Unknown | 1762.3 | 9006.18 | -7243.88 | Yes | N/A | N/A | 2025-02-24 | 2025-04-30 | 66 | 48 | 2025-04-30 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-06-03 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-09 | 7 | 5 | 2025-06-09 | 2025-06-09 | 1 | 1 | 165 | 119 | 8 | 6 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -662 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 45.9 | Unknown | Unknown | Unknown | Unknown | 45.9 | 3981 | 1824.54 | 45.9 | 1778.64 | Yes | N/A | N/A | 2025-01-13 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-13 | 4 | 2 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-15 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-26 | 43 | 31 | 2025-02-26 | 2025-02-26 | 1 | 1 | 3 | 3 | 48 | 34 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 282.19 | -11.09 | Unknown | Unknown | 1.66 | 291.62 | 3961 | 985.82 | 282.19 | 703.63 | Yes | N/A | N/A | 2024-01-18 | 2023-10-23 | Unknown | Unknown | 2023-10-23 | 2024-03-22 | 152 | 110 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-03-25 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-19 | 26 | 20 | 2024-04-19 | 2024-04-19 | 1 | 1 | 4 | 2 | 179 | 131 | 183 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 100 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1876.68 | 1091.32 | Unknown | 154.56 | -3811 | 688.44 | 0 | 3810.62 | -1876.68 | 5687.3 | Yes | N/A | N/A | 2023-04-12 | 2023-04-06 | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -306 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | -8411.67 | -52.06 | Unknown | Unknown | -9356 | 996.39 | Unknown | 9356.37 | -8411.67 | 17768.04 | Yes | N/A | N/A | 2024-07-02 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-07-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-01 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2025-02-28 | 183 | 131 | 2025-02-28 | 2025-02-28 | 1 | 1 | 0 | 0 | 223 | 161 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -711 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 30.17 | Unknown | Unknown | Unknown | Unknown | 30.17 | 3981 | 1363.03 | 30.17 | 1332.86 | Yes | N/A | N/A | 2024-09-13 | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-13 | 2 | 2 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-23 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-25 | 3 | 3 | 2024-09-25 | 2024-09-25 | 1 | 1 | 11 | 7 | 6 | 6 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-12-23 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 201.21 | -2.82 | Unknown | Unknown | 0.31 | 203.72 | 3981 | 1559.37 | 201.21 | 1358.16 | Yes | N/A | N/A | 2024-11-13 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-12-23 | 54 | 38 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-29 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-05 | 36 | 26 | 2025-03-05 | 2025-03-05 | 1 | 1 | 38 | 28 | 91 | 65 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 899.05 | 899.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | 486.78 | Unknown | Unknown | Unknown | 1.41 | 485.37 | 3981 | 2500.34 | 486.78 | 2013.56 | Yes | N/A | N/A | 2025-04-18 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-30 | 21 | 15 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-06-17 | 49 | 35 | Unknown | 2025-05-23 | Unknown | Unknown | 2025-06-17 | 2025-06-18 | 2 | 2 | 2025-06-18 | 2025-06-18 | 1 | 1 | 49 | 35 | 24 | 18 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | 11.75 | 11.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-28 | 244 | 175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-08-14 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 9511.38 | 2425.45 | Unknown | 929.53 | -6750.43 | 12906.83 | 3379.36 | 16478.42 | 9511.38 | 6967.04 | Yes | N/A | N/A | 2023-06-08 | 2023-08-14 | 68 | 48 | 2023-08-14 | 2024-02-14 | 185 | 133 | 2023-10-03 | 2024-02-13 | 132 | 96 | 2023-12-12 | 2024-02-15 | 7 | 7 | 2024-07-18 | Unknown | Unknown | Unknown | 2024-07-18 | 2024-12-19 | 155 | 111 | 2025-01-07 | 2025-01-27 | 21 | 15 | 2025-01-27 | 2025-01-27 | 1 | 1 | 200 | 144 | 369 | 267 | 569 | 411 | Steps 2,3,5,6,7 | 197 | 141 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -459 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -11.14 | -8.06 | Unknown | Unknown | Unknown | -3.08 | Unknown | 98.41 | -11.14 | 109.55 | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2023-10-04 | 1 | 1 | 0 | 0 | 14 | 10 | 14 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 17750.12 | 13.26 | Unknown | Unknown | 2.07 | 17734.79 | Unknown | 5052.18 | 17750.12 | -12697.94 | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | Unknown | Unknown | 2023-07-03 | 2023-07-03 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 275.05 | -4.69 | Unknown | Unknown | 0.17 | 279.57 | 3981 | 1874.23 | 275.05 | 1599.18 | Yes | N/A | N/A | 2024-12-17 | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2024-12-17 | 2 | 2 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-23 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-03-24 | 61 | 43 | 2025-03-24 | 2025-03-24 | 1 | 1 | 38 | 28 | 64 | 46 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-10 | 2024-05-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1007.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-27 | 2024-05-30 | 4 | 4 | 2024-05-30 | 2024-05-30 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | -21.78 | -17.69 | Unknown | Unknown | Unknown | -4.09 | Unknown | 958.77 | -21.78 | 980.55 | Yes | N/A | N/A | 2024-02-02 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-02-02 | 17 | 13 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 36 | 26 | 2024-03-15 | 2024-03-15 | 1 | 1 | 8 | 6 | 54 | 40 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 456.8 | Unknown | Unknown | Unknown | 7.74 | 449.06 | 3981 | 3170.32 | 456.8 | 2713.52 | Yes | N/A | N/A | 2024-12-03 | 2024-12-17 | 15 | 11 | 2024-12-17 | 2024-12-23 | 7 | 5 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1 | 1 | 15 | 11 | 8 | 6 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -235 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 1506.94 | -49.66 | Unknown | Unknown | 4.23 | 1552.37 | 3981 | 1123.38 | 1506.94 | -383.56 | Yes | N/A | N/A | 2024-04-24 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-04-24 | 49 | 35 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-04-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-07-01 | 69 | 49 | 2024-07-01 | 2024-07-01 | 1 | 1 | 1 | 1 | 119 | 85 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 197 | 197 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | 12 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-29 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 5731.38 | -2.35 | Unknown | Unknown | -1057.26 | 6790.99 | 0 | 951.2 | 5731.38 | -4780.18 | Yes | N/A | N/A | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-05-31 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-11-20 | 190 | 136 | 2024-05-31 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2025-02-24 | 267 | 191 | 2025-02-24 | 2025-02-14 | Unknown | Unknown | 1 | 1 | 551 | 395 | 552 | 396 | Steps 2,3,5,6,7 | 173 | 123 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -666 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 7.38 | Unknown | Unknown | Unknown | Unknown | 7.38 | Unknown | 192.95 | 7.38 | 185.57 | Yes | N/A | N/A | 2024-08-28 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-05 | 16 | 12 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-09-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-16 | 41 | 29 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2 | 2 | 58 | 42 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-04 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-07-22 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 28.38 | Unknown | Unknown | Unknown | Unknown | 28.38 | 3981 | 1604.54 | 28.38 | 1576.16 | Yes | N/A | N/A | 2024-06-17 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-22 | 70 | 50 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-11-26 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-11 | 16 | 12 | 2024-12-11 | 2024-12-11 | 1 | 1 | 128 | 92 | 87 | 63 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-04-01 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | 12.03 | -12.9 | Unknown | Unknown | Unknown | 24.93 | 3981 | 1056.41 | 12.03 | 1044.38 | Yes | N/A | N/A | 2024-03-18 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-04-01 | 18 | 12 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-15 | 44 | 32 | 2024-05-15 | 2024-05-15 | 1 | 1 | 2 | 2 | 63 | 45 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-08 | -50 | -36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1114.52 | -35.39 | Unknown | Unknown | Unknown | 1149.91 | 26990 | 445.64 | 1114.52 | -668.88 | Yes | N/A | N/A | 2023-06-15 | 2023-06-21 | 7 | 5 | 2023-06-21 | 2024-01-23 | 217 | 155 | 2023-07-21 | 2023-11-10 | 113 | 81 | 2023-06-21 | 2024-01-30 | 113 | 81 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | 2024-04-19 | 2024-04-19 | 1 | 1 | 120 | 86 | 331 | 237 | 451 | 323 | Steps 2,3,5,6,7 | 335 | 239 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 PA8 WO3 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 587 | 420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 9047.49 | -51.76 | Unknown | Unknown | 65.04 | 9034.21 | 50111 | Not available | 9047.49 | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2024-10-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-04-21 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2025-01-06 | 74 | 52 | 2025-01-06 | 2024-10-27 | Unknown | Unknown | 188 | 134 | 76 | 54 | 264 | 188 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2203.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2024-12-03 | 34 | 24 | 2024-12-03 | 2025-05-05 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-25 | 29 | 21 | 2025-05-05 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-05-29 | Unknown | Unknown | 34 | 24 | 183 | 131 | 217 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | SANTA YSABEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-30 | 43 | 32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-29 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 6948.72 | 19.17 | Unknown | Unknown | 1.39 | 6928.16 | 14805 | 776.08 | 6948.72 | -6172.64 | Yes | N/A | N/A | 2024-01-22 | 2024-01-29 | 8 | 6 | 2024-01-29 | 2024-06-07 | 131 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-17 | 8 | 6 | 2024-06-17 | 2024-06-12 | Unknown | Unknown | 8 | 6 | 139 | 101 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-11 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 26.27 | Unknown | Unknown | Unknown | Unknown | 26.27 | 3981 | 1422.83 | 26.27 | 1396.56 | Yes | N/A | N/A | 2024-07-10 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-10 | 22 | 16 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-09-11 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-13 | 3 | 3 | 2024-09-13 | 2024-09-13 | 1 | 1 | 63 | 45 | 26 | 20 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-12 | 3 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 150.19 | 1333.24 | Unknown | 110.29 | -1922 | 628.66 | Unknown | 1922.07 | 150.19 | 1771.88 | Yes | N/A | N/A | 2023-08-30 | 2023-10-31 | 63 | 45 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 63 | 45 | 1 | 1 | 64 | 46 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | 3000 | 3000 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-15 | -215 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-24 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 1914.55 | Unknown | Unknown | Unknown | 69.13 | 1845.42 | 1192.8 | 797.52 | 1914.55 | -1117.03 | Yes | N/A | N/A | 2024-06-19 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-06-28 | 36 | 26 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2025-01-30 | 217 | 155 | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-30 | 2025-02-13 | 15 | 11 | 2025-02-13 | 2025-02-12 | Unknown | Unknown | 217 | 155 | 51 | 37 | 268 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-21 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 543.92 | -10.2 | Unknown | Unknown | Unknown | 554.12 | Unknown | 1537.87 | 543.92 | 993.95 | Yes | N/A | N/A | 2024-11-20 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-11-21 | 15 | 11 | 2024-11-21 | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-09 | 18 | 12 | 2024-11-21 | 2024-12-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-20 | 10 | 8 | 2024-12-20 | 2024-12-20 | 1 | 1 | 21 | 15 | 44 | 32 | 65 | 47 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | -695 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 454.3 | -12.08 | Unknown | 164.18 | Unknown | 302.2 | 3981 | 1404.34 | 454.3 | 950.04 | Yes | N/A | N/A | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-29 | 8 | 6 | 2024-07-17 | 2024-07-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-15 | 17 | 13 | 2024-08-15 | 2024-08-15 | 1 | 1 | 15 | 11 | 27 | 21 | 42 | 32 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 680.99 | Unknown | Unknown | Unknown | -1180.68 | 1861.67 | Unknown | 1202.91 | 680.99 | 521.92 | Yes | N/A | N/A | 2024-12-12 | 2025-02-06 | 57 | 41 | 2025-02-06 | 2025-02-10 | 5 | 3 | 2025-02-10 | 2025-04-02 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-05-06 | 35 | 25 | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-06 | 2025-05-13 | 8 | 6 | 2025-05-13 | 2025-05-13 | 1 | 1 | 144 | 104 | 14 | 10 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 515.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-30 | 2 | 2 | 2025-01-30 | 2025-03-03 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 2 | 2 | 34 | 24 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 210.05 | 210.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | 46 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 962.29 | -7.85 | Unknown | Unknown | 24.33 | 945.81 | 3981 | 938.31 | 962.29 | -23.98 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2024-01-25 | 136 | 98 | Unknown | 2024-01-22 | Unknown | Unknown | 2024-01-25 | 2024-02-12 | 19 | 13 | 2024-02-12 | 2024-02-12 | 1 | 1 | 137 | 99 | 20 | 14 | 157 | 113 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 828.05 | 828.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -354 | -253 | No | 2024-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-28 | 2024-11-25 | IOU Designed & Installed | N/A | Yes | 273 | 1046.83 | Unknown | Unknown | Unknown | 38.62 | 1008.21 | 3981 | 1098.97 | 1046.83 | 52.14 | Yes | N/A | N/A | 2024-02-15 | 2024-11-14 | 274 | 196 | 2024-11-14 | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-08-20 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-11-25 | 225 | 161 | Unknown | 2024-10-02 | Unknown | Unknown | 2024-11-25 | 2024-12-12 | 18 | 14 | 2024-12-12 | 2024-12-11 | Unknown | Unknown | 627 | 449 | 18 | 14 | 645 | 463 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-20 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-09-06 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 5.57 | Unknown | Unknown | Unknown | Unknown | 5.57 | Unknown | 1326.24 | 5.57 | 1320.67 | Yes | N/A | N/A | 2024-08-09 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-09-06 | 43 | 31 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-08 | 26 | 18 | 2024-10-08 | 2024-10-08 | 1 | 1 | 8 | 6 | 70 | 50 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 70.35 | 70.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 3211.41 | 276.12 | Unknown | Unknown | 19.82 | 2915.47 | 3981 | 1760.97 | 3211.41 | -1450.44 | Yes | N/A | N/A | 2024-06-28 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-28 | 68 | 50 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-08-28 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-10-01 | 35 | 25 | 2024-10-01 | 2024-10-01 | 1 | 1 | 62 | 44 | 104 | 76 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -66 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-11-20 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | -1709.31 | -0.94 | Unknown | Unknown | -1789 | 80.63 | Unknown | 1789.05 | -1709.31 | 3498.36 | Yes | N/A | N/A | 2024-10-15 | 2024-11-11 | 28 | 20 | 2024-11-11 | 2024-11-19 | 9 | 7 | 2024-11-19 | 2025-02-06 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-06 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-01 | 27 | 19 | 2025-04-01 | 2025-03-27 | Unknown | Unknown | 137 | 99 | 36 | 26 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-05-15 | 324 | 233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2024-03-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 11600.07 | 227.22 | Unknown | Unknown | -6933.59 | 18306.44 | Unknown | 15362.41 | 11600.07 | 3762.34 | Yes | N/A | N/A | 2023-11-29 | 2024-01-12 | 45 | 33 | 2024-01-12 | 2024-03-04 | 53 | 37 | 2024-01-18 | 2024-01-23 | 6 | 4 | 2024-01-23 | 2024-03-15 | 34 | 26 | 2024-03-04 | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-20 | 2024-04-03 | 15 | 11 | 2024-04-03 | 2024-04-03 | 1 | 1 | 51 | 37 | 104 | 76 | 155 | 113 | Steps 2,3,5,6,7 | 57 | 41 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LADERA RANCH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-01 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | -7339.01 | 5533.72 | Unknown | 140.35 | -15600 | 2586.92 | Unknown | 15599.57 | -7339.01 | 22938.58 | Yes | N/A | N/A | 2024-07-30 | 2024-08-05 | 7 | 5 | 2024-08-05 | 2024-11-06 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2958465 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-12-04 | 48 | 34 | 2024-12-04 | 2024-12-04 | 1 | 1 | 7 | 5 | 143 | 103 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -208 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -406.32 | 757.95 | Unknown | 89.96 | -1780 | 525.77 | Unknown | 1779.88 | -406.32 | 2186.2 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-07 | -170 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 683.5 | -11.13 | Unknown | Unknown | 4.65 | 689.98 | Unknown | 1044.9 | 683.5 | 361.4 | Yes | N/A | N/A | 2023-06-19 | 2023-05-01 | Unknown | Unknown | 2023-05-01 | 2023-07-05 | 66 | 48 | 2023-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2023-09-29 | 87 | 63 | Unknown | 2023-09-27 | Unknown | Unknown | 2023-09-29 | 2023-10-20 | 22 | 16 | 2023-10-20 | 2023-10-20 | 1 | 1 | 87 | 63 | 89 | 65 | 176 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -205 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1714.9 | 1520.3 | Unknown | 295.84 | -4124 | 592.96 | Unknown | 4123.6 | -1714.9 | 5838.5 | Yes | N/A | N/A | 2023-05-30 | 2023-06-07 | 9 | 7 | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Tecate | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1932.35 | 1967.5 | Unknown | Unknown | -1149 | 1113.85 | 0 | 1148.95 | 1932.35 | -783.4 | Yes | N/A | N/A | 2023-05-03 | 2023-05-05 | 3 | 3 | 2023-05-05 | 2023-05-08 | 4 | 2 | 2023-05-05 | 2023-05-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 4 | 4 | 5 | 3 | 9 | 7 | Steps 2,3,5,6,7 | 3 | 1 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-04 | -475 | -340 | No | 2024-04-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2024-08-15 | IOU Designed & Installed | N/A | Yes | 65 | 799.31 | 186.96 | Unknown | 36.96 | Unknown | 575.39 | 3941 | 1075.67 | 799.31 | 276.36 | Yes | N/A | N/A | 2024-04-03 | 2024-06-07 | 66 | 48 | 2024-06-07 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-08-15 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-10-21 | 68 | 48 | 2024-10-21 | 2024-10-17 | Unknown | Unknown | 201 | 145 | 68 | 48 | 269 | 193 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-10 | -115 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -163.99 | Unknown | Unknown | Unknown | -1084.68 | 920.69 | 3981 | 1165.84 | -163.99 | 1329.83 | Yes | N/A | N/A | 2024-02-07 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-02-09 | 5 | 5 | 2024-02-09 | 2024-11-01 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-15 | 1 | 1 | 267 | 191 | 6 | 6 | 273 | 197 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | -304 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-14 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 1535.1 | Unknown | Unknown | Unknown | Unknown | 1535.1 | 3981 | 447.95 | 1535.1 | -1087.15 | Yes | N/A | N/A | 2024-05-13 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-05-14 | 6 | 4 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2025-01-31 | 263 | 189 | Unknown | 2025-01-29 | Unknown | Unknown | 2025-01-31 | 2025-02-07 | 8 | 6 | 2025-02-07 | 2025-02-07 | 1 | 1 | 263 | 189 | 15 | 11 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-07-31 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 263.86 | Unknown | Unknown | Unknown | Unknown | 263.86 | Unknown | 449.58 | 263.86 | 185.72 | Yes | N/A | N/A | 2024-07-31 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-16 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-23 | 8 | 6 | 2024-08-23 | 2024-08-23 | 1 | 1 | 11 | 9 | 9 | 7 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | JAMUL | COUNTY OF SAN DIEGO-SOUTH of 56 | 134.1 | 134.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 871 | 623 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-11-28 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 22352.87 | 2210.23 | Unknown | Unknown | -17818.27 | 37960.91 | 5861 | 40139.36 | 22352.87 | 17786.49 | Yes | N/A | N/A | 2023-01-19 | 2023-10-25 | 280 | 200 | 2023-10-25 | Unknown | Unknown | Unknown | 2024-01-26 | 2024-05-22 | 74 | 54 | 2024-02-09 | 2025-01-09 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-06-24 | 99 | 71 | 2025-06-24 | 2025-06-21 | Unknown | Unknown | 354 | 254 | 111 | 81 | 465 | 335 | Steps 2,3,5,6,7 | 103 | 73 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -609.81 | -27.81 | Unknown | Unknown | -1109 | 527 | 3981 | 1847.88 | -609.81 | 2457.69 | Yes | N/A | N/A | 2023-08-11 | 2023-08-11 | 1 | 1 | 2023-08-11 | 2023-08-11 | 1 | 1 | 2023-08-11 | 2023-09-12 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-03-19 | Unknown | Unknown | 34 | 24 | 1 | 1 | 35 | 25 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | 39 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 851.81 | -16.62 | Unknown | Unknown | 18 | 850.43 | 3981 | 666.23 | 851.81 | -185.58 | Yes | N/A | N/A | 2023-03-30 | 2023-05-31 | 63 | 45 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2024-04-09 | 315 | 225 | Unknown | 2024-03-27 | Unknown | Unknown | 2024-04-09 | 2024-04-11 | 3 | 3 | 2024-04-11 | 2024-04-11 | 1 | 1 | 378 | 270 | 4 | 4 | 382 | 274 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -392 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-03-04 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | 1133.66 | 307.05 | Unknown | Unknown | 1.18 | 825.43 | 3981 | 1255.49 | 1133.66 | 121.83 | Yes | N/A | N/A | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | 2024-03-07 | 14 | 10 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-04-02 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-09-16 | 168 | 120 | 2024-09-16 | 2024-09-16 | 1 | 1 | 31 | 23 | 183 | 131 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -290 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-23 | 2024-04-14 | IOU Designed & Installed | N/A | No | N/A | 5640.91 | Unknown | Unknown | Unknown | Unknown | 5640.91 | Unknown | 1875.49 | 5640.91 | -3765.42 | Yes | N/A | N/A | 2024-02-22 | 2024-02-22 | 1 | 1 | 2024-02-22 | 2024-04-05 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-14 | 2024-04-22 | 9 | 6 | 2024-04-22 | 2024-04-22 | 1 | 1 | 1 | 1 | 54 | 39 | 55 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 24.1 | 24.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -591 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | -2020.17 | -18.15 | Unknown | Unknown | -3351 | 1348.98 | Unknown | 3350.61 | -2020.17 | 5370.78 | Yes | N/A | N/A | 2024-12-05 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-22 | 21 | 15 | 2024-12-22 | 2024-12-31 | 10 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-03-17 | 75 | 53 | Unknown | 2025-03-14 | Unknown | Unknown | 2025-03-17 | 2025-04-02 | 17 | 13 | 2025-04-02 | 2025-04-02 | 1 | 1 | 85 | 60 | 39 | 29 | 124 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Agricultural | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-07 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 20.77 | -18.46 | Unknown | Unknown | Unknown | 39.23 | 3981 | 609.43 | 20.77 | 588.66 | Yes | N/A | N/A | 2024-02-05 | 2024-01-08 | Unknown | Unknown | 2024-01-08 | 2024-02-06 | 30 | 22 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-22 | 8 | 6 | 2024-03-22 | 2024-03-21 | Unknown | Unknown | 38 | 28 | 38 | 28 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | 170 | 121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 18.65 | Unknown | Unknown | Unknown | Unknown | 18.65 | 0 | 149.62 | 18.65 | 130.97 | Yes | N/A | N/A | 2023-04-03 | 2023-04-10 | 8 | 6 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2024-08-21 | 500 | 358 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-26 | 6 | 4 | 2024-08-26 | 2024-08-26 | 1 | 1 | 508 | 364 | 7 | 5 | 515 | 369 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 74.7 | -1.5 | Unknown | Unknown | Unknown | 76.2 | 3981 | 1031.47 | 74.7 | 956.77 | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-12 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-21 | 10 | 8 | 2025-05-21 | 2025-05-21 | 1 | 1 | 8 | 6 | 12 | 10 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-04 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1804.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-04 | 5 | 5 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-05-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-04-25 | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1 | 1 | 48 | 36 | 2 | 2 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 334.21 | Unknown | Unknown | Unknown | 2.3 | 331.91 | 3981 | 1114.43 | 334.21 | 780.22 | Yes | N/A | N/A | 2024-07-22 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-07-30 | 43 | 31 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-04 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-23 | 20 | 14 | 2024-09-23 | 2024-09-23 | 1 | 1 | 37 | 27 | 64 | 46 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -255 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 177.61 | 1324.79 | Unknown | Unknown | -1763 | 615.82 | Unknown | 1762.72 | 177.61 | 1585.11 | Yes | N/A | N/A | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 364 | 364 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.08 | -3.15 | Unknown | Unknown | Unknown | 2.07 | 3981 | 1013.81 | -1.08 | 1014.89 | Yes | N/A | N/A | 2023-05-10 | 2023-05-10 | 1 | 1 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -526 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-04 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 5608.44 | 1576.58 | Unknown | 471.92 | -1103 | 4662.94 | 3981 | 1907.46 | 5608.44 | -3700.98 | Yes | N/A | N/A | 2024-10-03 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-10-03 | 50 | 36 | 2024-10-03 | 2025-02-06 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-11-19 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-02-28 | 102 | 74 | 2025-02-28 | 2025-02-28 | 1 | 1 | 174 | 124 | 153 | 111 | 327 | 235 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 6658.83 | 1386.46 | Unknown | 653.73 | Unknown | 4618.64 | 3981 | 1253.54 | 6658.83 | -5405.29 | Yes | N/A | N/A | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-02-10 | 1 | 1 | 9 | 7 | 3 | 3 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-20 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 296.82 | -25.86 | Unknown | Unknown | Unknown | 322.68 | Unknown | 1603.8 | 296.82 | 1306.98 | Yes | N/A | N/A | 2024-11-19 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-20 | 34 | 24 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-03-31 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-03 | 4 | 4 | 2025-04-03 | 2025-04-03 | 1 | 1 | 132 | 94 | 39 | 29 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-29 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-03-06 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2000.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-03-06 | 23 | 17 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-29 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-06 | 8 | 6 | 2025-05-06 | 2025-05-06 | 1 | 1 | 55 | 39 | 32 | 24 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | -726 | -520 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 664.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-25 | 2 | 2 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-28 | 4 | 2 | 2025-04-28 | 2025-04-28 | 1 | 1 | 1 | 1 | 7 | 5 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | -162 | -117 | No | 2023-02-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-08-11 | IOU Designed & Installed | N/A | Yes | 85 | -14.43 | -10.45 | Unknown | Unknown | Unknown | -3.98 | 3961 | 341 | -14.43 | 355.43 | Yes | N/A | N/A | 2023-02-08 | 2023-05-04 | 86 | 62 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-08-11 | 185 | 133 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-08-21 | 11 | 7 | 2023-08-21 | 2023-08-21 | 1 | 1 | 271 | 195 | 12 | 8 | 283 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 49937.68 | 17634.74 | Unknown | Unknown | -113250 | 145552.94 | 0 | 133354.01 | 49937.68 | 83416.33 | Yes | N/A | N/A | 2023-12-08 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2024-10-30 | 338 | 242 | 2024-05-01 | 2024-05-02 | 2 | 2 | 2024-04-01 | 2024-11-05 | 20 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-06 | 1 | 1 | 2 | 2 | 359 | 259 | 361 | 261 | Steps 2,3,5,6,7 | 213 | 153 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | -704 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 115.06 | -1.57 | Unknown | Unknown | Unknown | 116.63 | 3981 | 1775.91 | 115.06 | 1660.85 | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-03 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-11 | 9 | 7 | 2025-02-11 | 2025-02-11 | 1 | 1 | 12 | 8 | 11 | 9 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20.14 | Unknown | Unknown | Unknown | Unknown | 20.14 | 3981 | 1009.05 | 20.14 | 988.91 | Yes | N/A | N/A | 2023-09-11 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-09-12 | 22 | 16 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-01 | 995 | 712 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | 2022-02-04 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 42263.59 | 805.06 | Unknown | Unknown | 4327.1 | 37131.43 | 59113 | 23992.61 | 42263.59 | -18270.98 | Yes | N/A | N/A | 2022-02-04 | 2023-05-02 | 453 | 323 | 2023-05-02 | 2024-08-29 | 486 | 348 | 2023-05-17 | 2024-06-28 | 37 | 26 | 2023-04-24 | 2024-09-23 | 26 | 20 | 2024-09-17 | Unknown | Unknown | Unknown | 2024-09-17 | 2025-05-06 | 232 | 166 | Unknown | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-23 | 1 | 1 | 490 | 349 | 745 | 535 | 1235 | 884 | Steps 2,3,5,6,7 | 907 | 649 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 14 | 11 | No | 2022-08-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-25 | 2022-08-25 | 2023-05-01 | IOU Designed & Installed | N/A | Yes | 189 | 13463.2 | 3335.15 | Unknown | Unknown | -4759.32 | 14887.37 | 3981 | 12604.96 | 13463.2 | -858.24 | Yes | N/A | N/A | 2022-08-25 | 2023-03-02 | 190 | 136 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-04-25 | 15 | 11 | 2023-02-14 | 2023-05-01 | 77 | 55 | Unknown | 2023-03-31 | Unknown | Unknown | 2023-05-01 | 2023-08-14 | 106 | 76 | 2023-08-14 | 2023-05-15 | Unknown | Unknown | 267 | 191 | 121 | 87 | 388 | 278 | Steps 2,3,5,6,7 | 70 | 50 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.35 | 13.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-07-10 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 917.04 | Unknown | Unknown | Unknown | Unknown | 917.04 | 3981 | 1150.99 | 917.04 | 233.95 | Yes | N/A | N/A | 2024-04-01 | 2024-07-10 | 101 | 73 | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-10-23 | 106 | 76 | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-23 | 2024-11-05 | 14 | 10 | 2024-11-05 | 2024-11-05 | 1 | 1 | 207 | 149 | 16 | 12 | 223 | 161 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 50107.63 | 19475.1 | Unknown | Unknown | 20.56 | 30611.97 | Unknown | 10726.12 | 50107.63 | -39381.51 | Yes | N/A | N/A | 2024-05-02 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-08-29 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-07-07 | 2024-08-22 | 40 | 29 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 0 | 0 | 202 | 145 | 202 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -492 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-12-12 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | -442.28 | Unknown | Unknown | Unknown | -520 | 77.72 | Unknown | 1837.4 | -442.28 | 2279.68 | Yes | N/A | N/A | 2024-11-12 | 2024-12-05 | 24 | 18 | 2024-12-05 | 2024-12-13 | 9 | 7 | 2024-12-13 | 2025-03-03 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-06-02 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-12 | 11 | 9 | 2025-06-12 | 2025-06-12 | 1 | 1 | 197 | 141 | 21 | 17 | 218 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-16 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 678.16 | Unknown | Unknown | Unknown | 9.42 | 668.74 | 3981 | 1308.41 | 678.16 | 630.25 | Yes | N/A | N/A | 2025-01-10 | 2025-02-10 | 32 | 22 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-26 | 45 | 33 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-04-09 | 15 | 11 | 2025-04-09 | 2025-04-09 | 1 | 1 | 77 | 55 | 17 | 13 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | -660 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-09 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 3156.31 | 820.98 | Unknown | Unknown | Unknown | 2335.33 | 3981 | 1109.59 | 3156.31 | -2046.72 | Yes | N/A | N/A | 2025-05-01 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-05-09 | 24 | 18 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-15 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-12 | 29 | 21 | 2025-06-12 | 2025-06-12 | 1 | 1 | 7 | 5 | 54 | 40 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -847 | -606 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-25 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | 20600.92 | 2533.84 | Unknown | 766.48 | -2989.75 | 20290.35 | Unknown | 2995.41 | 20600.92 | -17605.51 | Yes | N/A | N/A | 2023-04-20 | 2023-05-10 | 21 | 15 | 2023-05-10 | 2023-06-05 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-09-06 | 48 | 34 | 2023-09-06 | 2023-09-06 | 1 | 1 | 21 | 15 | 76 | 54 | 97 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTA YSABEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | 2023-07-02 | IOU Designed & Installed | N/A | No | N/A | 1462.9 | 465.88 | Unknown | 178.72 | Unknown | 818.3 | Unknown | 816.29 | 1462.9 | -646.61 | Yes | N/A | N/A | 2023-06-22 | 2023-06-22 | 1 | 1 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-07-02 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-07-02 | 2023-07-05 | 4 | 3 | 2023-07-05 | 2023-07-05 | 1 | 1 | 12 | 8 | 5 | 4 | 17 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -618 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 208.54 | -10.13 | Unknown | Unknown | Unknown | 218.67 | Unknown | 890.68 | 208.54 | 682.14 | Yes | N/A | N/A | 2023-06-07 | 2023-06-13 | 7 | 5 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-07-19 | 36 | 26 | Unknown | 2023-07-03 | Unknown | Unknown | 2023-07-19 | 2023-07-20 | 2 | 2 | 2023-07-20 | 2023-07-20 | 1 | 1 | 43 | 31 | 3 | 3 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -257 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-24 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 1900.04 | 546.56 | Unknown | 149.13 | Unknown | 1204.35 | 3981 | 1057.04 | 1900.04 | -843 | Yes | N/A | N/A | 2024-01-22 | 2024-03-15 | 54 | 40 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-10 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-23 | 44 | 32 | 2024-05-23 | 2024-11-25 | 187 | 133 | 81 | 59 | 232 | 166 | 313 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | -590 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1190.1 | -29.38 | Unknown | Unknown | Unknown | 1219.48 | 3981 | 499.96 | 1190.1 | -690.14 | Yes | N/A | N/A | 2023-03-31 | 2023-04-13 | 14 | 10 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-07-07 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-15 | 290 | 209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2024-01-19 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 62839.79 | 13445.96 | Unknown | Unknown | -23864 | 73257.83 | 11888 | 49499.17 | 62839.79 | -13340.62 | Yes | N/A | N/A | 2023-11-01 | 2023-11-13 | 13 | 9 | 2023-11-13 | 2024-08-08 | 270 | 194 | 2024-02-15 | 2024-09-30 | 122 | 88 | 2024-07-16 | 2024-09-20 | 67 | 49 | 2024-08-08 | 2024-10-21 | 75 | 53 | 2024-08-16 | 2024-09-27 | 43 | 31 | 2024-10-10 | 2024-11-05 | 27 | 19 | 2024-11-05 | 2024-10-31 | Unknown | Unknown | 210 | 150 | 407 | 293 | 617 | 443 | Steps 2,3,5,6,7 | 360 | 256 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | -238 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 376 | Unknown | Unknown | Unknown | 7.44 | 368.56 | 3941 | 2826.96 | 376 | 2450.96 | Yes | N/A | N/A | 2024-05-29 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-11 | 51 | 37 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-08-21 | 72 | 52 | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-21 | 2024-08-28 | 8 | 6 | 2024-08-28 | 2024-08-27 | Unknown | Unknown | 72 | 52 | 59 | 43 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 163 | 118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1475.07 | -38.38 | Unknown | Unknown | Unknown | 1513.45 | 3981 | 704.77 | 1475.07 | -770.3 | Yes | N/A | N/A | 2023-10-12 | 2023-10-13 | 2 | 2 | 2023-10-13 | 2023-10-16 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-11-02 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-01-10 | Unknown | Unknown | 20 | 16 | 4 | 2 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 186.05 | 186.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1039.1 | Unknown | Unknown | Unknown | -1061 | 21.9 | 6481 | 2065.73 | -1039.1 | 3104.83 | Yes | N/A | N/A | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-10-28 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 801 | 574 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9002.41 | Unknown | Unknown | Unknown | -1336 | 10338.41 | Unknown | 757.94 | 9002.41 | -8244.47 | Yes | N/A | N/A | 2024-07-23 | 2024-08-02 | 11 | 9 | 2024-08-02 | 2025-03-05 | 216 | 154 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2024-12-31 | Unknown | Unknown | 2025-03-05 | 2025-04-14 | 41 | 29 | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-29 | 24 | 18 | 11 | 9 | 281 | 201 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 30.1 | 30.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-06 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 502.53 | Unknown | Unknown | Unknown | Unknown | 502.53 | 7962 | 1994.1 | 502.53 | 1491.57 | Yes | N/A | N/A | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-10-02 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-12 | 32 | 24 | 2024-10-02 | 2025-06-05 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 2 | 2 | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 247 | 177 | 97 | 71 | 344 | 248 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 0.15 | -3.57 | Unknown | Unknown | Unknown | 3.72 | Unknown | 867.82 | 0.15 | 867.67 | Yes | N/A | N/A | 2023-06-05 | 2023-06-05 | 1 | 1 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-10-12 | 130 | 94 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-17 | 37 | 27 | 2023-11-17 | 2023-11-17 | 1 | 1 | 131 | 95 | 38 | 28 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.56 | -3.3 | Unknown | Unknown | Unknown | -1.26 | 3981 | 363.72 | -4.56 | 368.28 | Yes | N/A | N/A | 2023-02-21 | 2023-02-21 | 1 | 1 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-26 | 37 | 28 | No | 2023-08-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-03 | 2023-08-07 | IOU Designed & Installed | N/A | Yes | 15 | 1313.08 | -30.39 | Unknown | Unknown | 29.31 | 1314.16 | 3961 | 465.33 | 1313.08 | -847.75 | Yes | N/A | N/A | 2023-08-02 | 2023-08-17 | 16 | 12 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-07 | 5 | 3 | Unknown | 2023-09-01 | Unknown | Unknown | 2023-08-07 | 2023-11-09 | 95 | 69 | 2023-11-09 | 2023-09-01 | Unknown | Unknown | 21 | 15 | 96 | 70 | 117 | 85 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -3 | -4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-06-22 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 129891.1 | 3228.8 | Unknown | 32.44 | 590.04 | 126039.82 | 0 | 99696.22 | 129891.1 | -30194.88 | Yes | N/A | N/A | 2023-05-12 | 2023-06-22 | 42 | 30 | 2023-06-22 | 2023-10-10 | 111 | 79 | 2023-07-31 | 2024-03-21 | 187 | 135 | 2023-10-20 | 2023-11-06 | 18 | 12 | 2023-10-10 | 2024-05-29 | 233 | 167 | 2024-04-24 | 2024-06-07 | 45 | 33 | 2024-04-10 | 2024-07-22 | 104 | 74 | 2024-07-22 | 2024-07-22 | 1 | 1 | 462 | 332 | 279 | 199 | 741 | 531 | Steps 2,3,5,6,7 | 344 | 246 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-07 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 14.7 | Unknown | Unknown | Unknown | Unknown | 14.7 | Unknown | 1066.51 | 14.7 | 1051.81 | Yes | N/A | N/A | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-01-13 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-23 | 11 | 9 | 2025-01-23 | 2025-01-15 | Unknown | Unknown | 90 | 64 | 12 | 10 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-06-07 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 409.2 | -7.81 | Unknown | Unknown | Unknown | 417.01 | 3981 | 1554.56 | 409.2 | 1145.36 | Yes | N/A | N/A | 2024-05-06 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-06-07 | 59 | 43 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-07 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-25 | 19 | 13 | 2024-06-25 | 2024-06-25 | 1 | 1 | 1 | 1 | 79 | 57 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-19 | 972 | 695 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-16 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 2906.42 | Unknown | Unknown | Unknown | 125.7 | 2780.72 | 3981 | 2543.26 | 2906.42 | -363.16 | Yes | N/A | N/A | 2023-03-14 | 2023-03-16 | 3 | 3 | 2023-03-16 | 2023-05-17 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-05-17 | 2024-03-20 | 309 | 221 | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-05-31 | 46 | 34 | 2024-05-31 | 2024-04-17 | Unknown | Unknown | 312 | 224 | 110 | 80 | 422 | 304 | Steps 2,3,5,6,7 | 75 | 53 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-02 | -91 | -66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 92.44 | -0.63 | Unknown | Unknown | Unknown | 93.07 | 3981 | 1630.03 | 92.44 | 1537.59 | Yes | N/A | N/A | 2023-09-05 | 2024-05-22 | 261 | 187 | 2024-05-22 | 2024-11-14 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-12-13 | 32 | 24 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-03 | 1 | 1 | 261 | 187 | 210 | 152 | 471 | 339 | Steps 2,3,5,6,7 | 29 | 21 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-21 | IOU Designed & Installed | N/A | No | N/A | 59.1 | -13.07 | Unknown | Unknown | Unknown | 72.17 | 3981 | 781.1 | 59.1 | 722 | Yes | N/A | N/A | 2023-02-15 | 2023-02-16 | 2 | 2 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2023-02-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-05-18 | 87 | 63 | 2023-05-18 | 2023-05-18 | 1 | 1 | 8 | 6 | 88 | 64 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -403 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 1045.81 | Unknown | Unknown | Unknown | Unknown | 1045.81 | 3981 | 1126.92 | 1045.81 | 81.11 | Yes | N/A | N/A | 2024-09-25 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-09-25 | 30 | 22 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-03-04 | 160 | 114 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-03-04 | 2025-03-18 | 15 | 11 | 2025-03-18 | 2025-03-17 | Unknown | Unknown | 160 | 114 | 45 | 33 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 207.05 | 207.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-20 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 254.46 | -11.71 | Unknown | Unknown | 8.95 | 257.22 | 3981 | 1594.81 | 254.46 | 1340.35 | Yes | N/A | N/A | 2023-06-15 | 2023-04-06 | Unknown | Unknown | 2023-04-06 | 2023-11-16 | 225 | 161 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-04-03 | 140 | 100 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-03 | 2024-04-23 | 21 | 15 | 2024-04-23 | 2024-04-12 | Unknown | Unknown | 140 | 100 | 246 | 176 | 386 | 276 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 541 | 388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-10-20 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 29099.43 | 8165.79 | Unknown | 1026.91 | Unknown | 19906.73 | 3981 | Not available | 29099.43 | Unknown | Yes | N/A | N/A | 2023-09-14 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | 2024-07-25 | 2024-08-07 | 14 | 10 | 2024-08-07 | 2024-07-26 | Unknown | Unknown | 0 | 0 | 14 | 10 | 14 | 10 | Steps 2,3,5,6,7 | 105 | 75 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | 295 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 599.89 | 409.84 | Unknown | Unknown | Unknown | 190.05 | 0 | 311.78 | 599.89 | -288.11 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2025-06-03 | 847 | 605 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 848 | 606 | 2 | 2 | 850 | 608 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | -466 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-09 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 1170.47 | 376.26 | Unknown | 58.16 | Unknown | 736.05 | Unknown | 1015.11 | 1170.47 | -155.36 | Yes | N/A | N/A | 2023-11-08 | 2023-11-09 | 2 | 2 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-12-04 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-29 | 57 | 41 | 2024-01-29 | 2024-01-29 | 1 | 1 | 28 | 20 | 59 | 43 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -276 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2025-01-03 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 823.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-12-19 | 275 | 197 | 2024-12-19 | 2025-01-03 | 16 | 12 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-05-07 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-09 | 3 | 3 | 2025-05-09 | 2025-05-08 | Unknown | Unknown | 400 | 286 | 19 | 15 | 419 | 301 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -15 | -12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1833.81 | 246.68 | Unknown | 40.84 | 0.97 | 1545.32 | 3981 | 2322.56 | 1833.81 | 488.75 | Yes | N/A | N/A | 2023-09-29 | 2024-05-16 | 231 | 165 | 2024-05-16 | 2024-05-29 | 14 | 10 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-08-22 | 1 | 1 | 231 | 165 | 15 | 11 | 246 | 176 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | 78 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 825.42 | -11.95 | Unknown | Unknown | 31.5 | 805.87 | 3981 | 899.03 | 825.42 | 73.61 | Yes | N/A | N/A | 2023-02-07 | 2023-03-30 | 52 | 38 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2024-01-25 | 302 | 216 | Unknown | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-02-28 | 35 | 25 | 2024-02-28 | 2024-02-28 | 1 | 1 | 354 | 254 | 36 | 26 | 390 | 280 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-16 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 1934.96 | 342.42 | Unknown | Unknown | Unknown | 1592.54 | Unknown | 274.65 | 1934.96 | -1660.31 | Yes | N/A | N/A | 2023-09-13 | 2023-10-08 | 26 | 18 | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-08 | 2023-10-13 | 6 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-19 | 7 | 5 | 2023-10-19 | 2023-10-19 | 1 | 1 | 32 | 23 | 9 | 6 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-14 | -522 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 1258.38 | 260.55 | Unknown | Unknown | Unknown | 997.83 | 3981 | 1520.73 | 1258.38 | 262.35 | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-03-05 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-04-10 | 37 | 27 | 2025-04-10 | 2025-04-10 | 1 | 1 | 114 | 82 | 39 | 29 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -488 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-23 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 2073.37 | 502.72 | Unknown | 90.62 | Unknown | 1480.03 | 3981 | 1592.56 | 2073.37 | -480.81 | Yes | N/A | N/A | 2025-01-21 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-23 | 14 | 10 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-06-10 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-06-17 | 107 | 77 | 139 | 99 | 121 | 87 | 260 | 186 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -208 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-09-26 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 45.76 | Unknown | Unknown | Unknown | 13.54 | 32.22 | 3981 | 744.93 | 45.76 | 699.17 | Yes | N/A | N/A | 2024-04-29 | 2024-09-26 | 151 | 109 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-03-05 | 161 | 115 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-03-05 | 2025-08-11 | 160 | 114 | 2025-08-11 | 2025-03-10 | Unknown | Unknown | 312 | 224 | 161 | 115 | 473 | 339 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 2000.84 | 523.17 | Unknown | 234.7 | Unknown | 1242.97 | 3981 | 348.64 | 2000.84 | -1652.2 | Yes | N/A | N/A | 2023-09-18 | 2023-09-19 | 2 | 2 | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-29 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-04 | 6 | 4 | 2023-10-04 | 2023-10-04 | 1 | 1 | 13 | 11 | 8 | 6 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-22 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 13.37 | -11.86 | Unknown | Unknown | Unknown | 25.23 | 3981 | 1978.17 | 13.37 | 1964.8 | Yes | N/A | N/A | 2024-01-25 | 2024-02-14 | 21 | 15 | 2024-02-14 | 2024-02-22 | 9 | 7 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-05-07 | 76 | 54 | Unknown | 2024-04-29 | Unknown | Unknown | 2024-05-07 | 2024-05-17 | 11 | 9 | 2024-05-17 | 2024-05-17 | 1 | 1 | 97 | 69 | 21 | 17 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 508 | 363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2024-01-10 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | -7.57 | -18.2 | Unknown | Unknown | 29.27 | -18.64 | 3981 | 1006.83 | -7.57 | 1014.4 | Yes | N/A | N/A | 2023-11-30 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2024-04-05 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-07-11 | 98 | 70 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-18 | 2025-05-08 | 203 | 145 | 2025-05-08 | 2024-11-20 | Unknown | Unknown | 98 | 70 | 359 | 257 | 457 | 327 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-25 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | -623.92 | 1372 | Unknown | 78.02 | -2758 | 684.06 | Unknown | 2758.22 | -623.92 | 3382.14 | Yes | N/A | N/A | 2025-02-20 | 2025-02-25 | 6 | 4 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-03-24 | 1 | 1 | 6 | 4 | 2 | 2 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 161 | 161 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-01 | 493 | 354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 294.95 | -39.07 | Unknown | Unknown | 29.96 | 304.06 | 3981 | 783.36 | 294.95 | 488.41 | Yes | N/A | N/A | 2023-03-15 | 2023-03-21 | 7 | 5 | 2023-03-21 | 2023-03-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-06-07 | 72 | 52 | Unknown | 2023-05-30 | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2023-07-07 | Unknown | Unknown | 79 | 57 | 8 | 6 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-21 | -133 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.2 | Unknown | Unknown | Unknown | Unknown | -0.2 | Unknown | Not available | -0.2 | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-10-03 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 0 | 0 | 53 | 39 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 1893.43 | 544.78 | Unknown | 316.32 | Unknown | 1032.33 | Unknown | 606.39 | 1893.43 | -1287.04 | Yes | N/A | N/A | 2023-10-04 | 2023-10-05 | 2 | 2 | 2023-10-05 | 2023-10-19 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-10 | 2 | 2 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2 | 2 | 18 | 14 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 468.76 | -17.16 | Unknown | Unknown | 2.33 | 483.59 | 3981 | 737.9 | 468.76 | 269.14 | Yes | N/A | N/A | 2024-01-10 | 2024-02-12 | 34 | 24 | 2024-02-12 | 2024-02-22 | 11 | 9 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-02-26 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-15 | 19 | 15 | 2024-03-15 | 2024-03-07 | Unknown | Unknown | 39 | 27 | 30 | 24 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | Santee | Santee | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-27 | 75 | 54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2025-02-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2638.56 | 838.54 | Unknown | 412.87 | -1204 | 2591.15 | Unknown | 1203.53 | 2638.56 | -1435.03 | Yes | N/A | N/A | 2024-08-16 | 2024-10-18 | 64 | 46 | 2024-10-18 | 2025-01-16 | 91 | 65 | 2024-10-10 | 2024-10-30 | 21 | 15 | 2024-10-30 | 2025-01-22 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-02-10 | 1 | 1 | 85 | 61 | 178 | 128 | 263 | 189 | Steps 2,3,5,6,7 | 98 | 70 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -100 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -18.84 | -15.29 | Unknown | Unknown | Unknown | -3.55 | 3981 | 158.51 | -18.84 | 177.35 | Yes | N/A | N/A | 2023-10-16 | 2023-10-19 | 4 | 4 | 2023-10-19 | 2023-10-19 | 1 | 1 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-06-19 | 1 | 1 | 4 | 4 | 2 | 2 | 6 | 6 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 160 | 115 | No | 2023-06-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-19 | 2023-12-27 | IOU Designed & Installed | N/A | Yes | 119 | 2749.23 | 358.96 | Unknown | Unknown | 5.75 | 2384.52 | 3981 | 969.22 | 2749.23 | -1780.01 | Yes | N/A | N/A | 2023-06-13 | 2023-10-10 | 120 | 86 | 2023-10-10 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-12-27 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-11 | 16 | 12 | 2024-01-11 | 2024-01-08 | Unknown | Unknown | 312 | 224 | 16 | 12 | 328 | 236 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -627 | -448 | No | 2024-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-04-30 | IOU Designed & Installed | N/A | Yes | 11 | 20.62 | -17.92 | Unknown | Unknown | Unknown | 38.54 | 3981 | 1001.92 | 20.62 | 981.3 | Yes | N/A | N/A | 2024-03-21 | 2024-04-01 | 12 | 8 | 2024-04-01 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-30 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-15 | 16 | 12 | 2024-05-15 | 2024-05-15 | 1 | 1 | 53 | 37 | 17 | 13 | 70 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-19 | -522 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | 1460.3 | Unknown | Unknown | Unknown | 5.73 | 1454.57 | 3981 | 1416.13 | 1460.3 | -44.17 | Yes | N/A | N/A | 2025-03-12 | 2025-03-20 | 9 | 7 | 2025-03-20 | 2025-03-29 | 10 | 7 | 2025-03-20 | 2025-03-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-29 | 2025-05-13 | 46 | 32 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-13 | 2025-05-15 | 3 | 3 | 2025-05-15 | 2025-05-15 | 1 | 1 | 57 | 41 | 14 | 11 | 71 | 52 | Steps 2,3,5,6,7 | 9 | 6 | Meeting | Meeting | Not Available | N/A
| R15 | Both | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | EL CAJON | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -75 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | 2025-03-21 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2461.4 | 7072.05 | Unknown | 1266.3 | -23765 | 17888.05 | 0 | 23765.15 | 2461.4 | 21303.75 | Yes | N/A | N/A | 2023-08-10 | 2024-01-24 | 168 | 120 | 2024-01-24 | 2024-06-05 | 134 | 96 | 2024-02-09 | 2024-04-30 | 39 | 27 | 2024-03-26 | 2025-02-12 | 77 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 207 | 147 | 213 | 154 | 420 | 301 | Steps 2,3,5,6,7 | 152 | 108 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -691 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 201.26 | -3 | Unknown | Unknown | Unknown | 204.26 | Unknown | 1550.26 | 201.26 | 1349 | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-09-24 | 2 | 2 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-26 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-15 | 20 | 14 | 2024-10-15 | 2024-10-15 | 1 | 1 | 4 | 4 | 23 | 17 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 48.3 | -0.94 | Unknown | Unknown | Unknown | 49.24 | 3981 | 1687.06 | 48.3 | 1638.76 | Yes | N/A | N/A | 2024-10-24 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-10-24 | 8 | 6 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-07 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-22 | 16 | 12 | 2024-11-22 | 2024-11-22 | 1 | 1 | 15 | 11 | 25 | 19 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 186 | 186 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -582 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 1462.36 | Unknown | Unknown | Unknown | 8.48 | 1453.88 | 3981 | 1402.05 | 1462.36 | -60.31 | Yes | N/A | N/A | 2025-02-28 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-12 | 16 | 12 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-05-06 | 56 | 40 | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-06-06 | 32 | 24 | 2025-06-06 | 2025-06-06 | 1 | 1 | 56 | 40 | 49 | 37 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 1022.76 | 3013.06 | Unknown | 1031.8 | -4278 | 1255.9 | Unknown | 4277.83 | 1022.76 | 3255.07 | Yes | N/A | N/A | 2023-09-06 | 2023-09-12 | 7 | 5 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-07 | 34 | 24 | 2023-11-07 | 2023-11-07 | 1 | 1 | 7 | 5 | 35 | 25 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 27.35 | 27.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 293.55 | Unknown | Unknown | Unknown | 16.23 | 277.32 | 3941 | 158.37 | 293.55 | -135.18 | Yes | N/A | N/A | 2024-03-26 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-03-26 | 47 | 33 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-10-08 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-31 | 24 | 18 | 2024-10-31 | 2024-10-20 | Unknown | Unknown | 197 | 141 | 71 | 51 | 268 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -452 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-03-01 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 1551.68 | Unknown | Unknown | Unknown | 14.62 | 1537.06 | 3981 | 774.05 | 1551.68 | -777.63 | Yes | N/A | N/A | 2024-02-15 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-03-01 | 65 | 47 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-09-06 | 189 | 135 | Unknown | 2024-07-25 | Unknown | Unknown | 2024-09-06 | 2024-09-23 | 18 | 12 | 2024-09-23 | 2024-09-23 | 1 | 1 | 189 | 135 | 84 | 60 | 273 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -54 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1472.27 | 2438.97 | Unknown | 648.56 | -2672 | 1056.74 | Unknown | 2281.05 | 1472.27 | 808.78 | Yes | N/A | N/A | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | 199 | 144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2181.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-18 | 17 | 13 | 2025-04-18 | 2025-05-01 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-06-18 | 49 | 35 | Unknown | 2025-06-06 | Unknown | Unknown | 2025-06-18 | 2025-06-20 | 3 | 3 | 2025-06-20 | 2025-06-19 | Unknown | Unknown | 63 | 45 | 20 | 16 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 136.28 | -2.19 | Unknown | Unknown | Unknown | 138.47 | 3981 | 754.25 | 136.28 | 617.97 | Yes | N/A | N/A | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-08-22 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-13 | 23 | 17 | 2024-09-13 | 2024-09-13 | 1 | 1 | 100 | 72 | 25 | 19 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 697 | 498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-07-28 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 102475.45 | 5937.72 | Unknown | 23.59 | -38203.77 | 134717.91 | 0 | 42281.74 | 102475.45 | -60193.71 | Yes | N/A | N/A | 2023-06-09 | 2023-07-26 | 48 | 34 | 2023-07-26 | 2024-07-24 | 365 | 261 | 2024-06-04 | 2024-06-10 | 7 | 5 | 2023-09-13 | 2024-08-09 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2025-04-07 | 216 | 154 | 2025-04-07 | 2025-04-07 | 1 | 1 | 55 | 39 | 606 | 434 | 661 | 473 | Steps 2,3,5,6,7 | 321 | 229 | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 774 | 774 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | 229 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-06-08 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 128248.56 | 3576.76 | Unknown | 225.45 | 881.98 | 123564.37 | 0 | 72861.34 | 128248.56 | -55387.22 | Yes | N/A | N/A | 2023-05-18 | 2023-09-29 | 135 | 97 | 2023-09-29 | 2024-02-20 | 145 | 103 | 2023-11-15 | 2024-12-05 | 24 | 18 | 2023-12-22 | 2025-01-21 | 36 | 22 | 2024-02-20 | 2024-10-25 | 249 | 179 | 2024-09-12 | 2024-10-29 | 48 | 34 | 2024-08-28 | 2024-12-30 | 125 | 89 | 2024-12-30 | 2024-12-30 | 1 | 1 | 408 | 294 | 355 | 249 | 763 | 543 | Steps 2,3,5,6,7 | 887 | 633 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-21 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | -1516.24 | 1949.03 | Unknown | Unknown | -4353 | 887.73 | Unknown | 4353.2 | -1516.24 | 5869.44 | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | 2024-09-11 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-07-10 | 2024-09-11 | 64 | 46 | 2024-09-11 | 2024-09-11 | 1 | 1 | 1 | 1 | 165 | 119 | 166 | 120 | Steps 2,3,5,6,7 | 63 | 45 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | 254 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 2234.85 | 118.13 | Unknown | Unknown | 55.43 | 2061.29 | Unknown | 728.1 | 2234.85 | -1506.75 | Yes | N/A | N/A | 2024-01-02 | 2024-12-19 | 353 | 253 | 2024-12-19 | 2025-01-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-12-12 | 53 | 39 | 2025-01-10 | 2025-05-23 | 134 | 96 | Unknown | 2025-04-14 | Unknown | Unknown | 2025-06-04 | 2025-06-09 | 6 | 4 | 2025-06-09 | 2025-06-09 | 1 | 1 | 487 | 349 | 83 | 61 | 570 | 410 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA HILLS | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-03 | 171 | 122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 15146.63 | 475.77 | Unknown | Unknown | 61.86 | 14609 | 8164 | 789.33 | 15146.63 | -14357.3 | Yes | N/A | N/A | 2023-03-20 | 2023-06-29 | 102 | 74 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | 2024-10-14 | 2024-10-22 | 9 | 7 | 2024-10-22 | 2024-10-21 | Unknown | Unknown | 102 | 74 | 9 | 7 | 111 | 81 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -562 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 1774.92 | -50.54 | Unknown | Unknown | Unknown | 1825.46 | Unknown | 1579.01 | 1774.92 | -195.91 | Yes | N/A | N/A | 2024-11-21 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-12-02 | 13 | 9 | 2024-12-02 | Unknown | Unknown | Unknown | 2024-12-02 | 2025-03-11 | 100 | 72 | 2024-12-02 | 2025-03-12 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-04-10 | 30 | 22 | 2025-04-10 | 2025-04-10 | 1 | 1 | 101 | 73 | 144 | 104 | 245 | 177 | Steps 2,3,5,6,7 | 99 | 71 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 484575.05 | 484575.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-16 | 364 | 261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-05-10 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 12965.49 | 517.83 | Unknown | Unknown | 105.52 | 12342.14 | 35712 | 16510.12 | 12965.49 | 3544.63 | Yes | N/A | N/A | 2023-03-27 | 2023-07-31 | 127 | 91 | 2023-07-31 | 2024-02-21 | 206 | 148 | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-12-12 | 2024-02-26 | 15 | 11 | 2024-02-21 | 2024-10-18 | 241 | 173 | 2024-04-24 | 2024-08-20 | 119 | 85 | 2024-10-31 | 2024-12-26 | 57 | 41 | 2024-12-26 | 2024-11-14 | Unknown | Unknown | 369 | 265 | 397 | 285 | 766 | 550 | Steps 2,3,5,6,7 | 302 | 216 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -571 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-01-22 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 3.44 | -4.18 | Unknown | Unknown | Unknown | 7.62 | Unknown | 297.38 | 3.44 | 293.94 | Yes | N/A | N/A | 2023-12-21 | 2024-01-07 | 18 | 12 | 2024-01-07 | 2024-01-19 | 13 | 10 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-05 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-14 | 10 | 8 | 2024-02-14 | 2024-02-14 | 1 | 1 | 33 | 23 | 24 | 19 | 57 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 1047.13 | -20.4 | Unknown | Unknown | Unknown | 1067.53 | 3981 | 1402.26 | 1047.13 | 355.13 | Yes | N/A | N/A | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-15 | 7 | 5 | 2024-08-09 | 2024-09-20 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-25 | 36 | 26 | 2024-10-25 | 2024-10-25 | 1 | 1 | 44 | 32 | 45 | 33 | 89 | 65 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11.49 | Unknown | Unknown | Unknown | Unknown | 11.49 | 3981 | 192.83 | 11.49 | 181.34 | Yes | N/A | N/A | 2024-05-16 | 2024-06-07 | 23 | 17 | 2024-06-07 | 2024-06-10 | 4 | 2 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-01-30 | 1 | 1 | 23 | 17 | 5 | 3 | 28 | 20 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | COUNTY OF ORANGE | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-26 | 283 | 202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 17645.43 | Unknown | Unknown | Unknown | Unknown | 17645.43 | 38320 | 1524.05 | 17645.43 | -16121.38 | Yes | N/A | N/A | 2023-08-01 | 2024-02-29 | 213 | 153 | 2024-02-29 | 2024-04-10 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2024-06-17 | 53 | 34 | 2024-04-10 | 2025-01-23 | 289 | 207 | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 502 | 360 | 96 | 65 | 598 | 425 | Steps 2,3,5,6,7 | 68 | 48 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -470 | -337 | No | 2022-04-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | 2022-04-27 | Unknown | IOU Designed & Installed | N/A | Yes | 304 | 69.99 | -12.41 | Unknown | Unknown | 76.3 | 6.1 | 3885 | 779.72 | 69.99 | 709.73 | Yes | N/A | N/A | 2022-04-26 | 2023-02-24 | 305 | 219 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2023-09-18 | Unknown | Unknown | 305 | 219 | 0 | 0 | 305 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 11500 | 11500 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-04-01 | -470 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1249.82 | Unknown | Unknown | Unknown | 13.8 | 1236.02 | 3981 | 1149.59 | 1249.82 | -100.23 | Yes | N/A | N/A | 2024-05-20 | 2024-06-21 | 33 | 25 | 2024-06-21 | 2024-06-24 | 4 | 2 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 33 | 25 | 5 | 3 | 38 | 28 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -667 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 524.6 | -9.61 | Unknown | Unknown | Unknown | 534.21 | 3981 | 1570.86 | 524.6 | 1046.26 | Yes | N/A | N/A | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-09 | 31 | 23 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-10-31 | 1 | 1 | 1 | 1 | 33 | 25 | 34 | 26 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 3821.79 | Unknown | Unknown | Unknown | 135.54 | 3686.25 | 3981 | 1596.38 | 3821.79 | -2225.41 | Yes | N/A | N/A | 2024-04-11 | 2024-08-27 | 139 | 99 | 2024-08-27 | 2024-08-28 | 2 | 2 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2025-03-06 | 191 | 137 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-06 | 2025-03-21 | 16 | 12 | 2025-03-21 | 2025-03-21 | 1 | 1 | 330 | 236 | 19 | 15 | 349 | 251 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 390 | 390 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | -129 | -94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5546.95 | 901.8 | Unknown | Unknown | 14.22 | 4630.93 | 3981 | 942.26 | 5546.95 | -4604.69 | Yes | N/A | N/A | 2024-07-15 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-26 | 22 | 16 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-18 | 1 | 1 | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11493 | 11493 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-11 | -464 | -333 | No | 2022-09-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-28 | 2023-03-13 | IOU Designed & Installed | N/A | Yes | 182 | 242.87 | -12.05 | Unknown | Unknown | 24.45 | 230.47 | 3981 | 1008.87 | 242.87 | 766 | Yes | N/A | N/A | 2022-09-27 | 2023-03-29 | 184 | 132 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-28 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | 2023-11-07 | 240 | 172 | 2023-11-07 | 2023-04-04 | Unknown | Unknown | 184 | 132 | 240 | 172 | 424 | 304 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -438 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-08-28 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1187.9 | Unknown | Unknown | Unknown | 5 | 1182.9 | 3981 | 1122.44 | 1187.9 | -65.46 | Yes | N/A | N/A | 2024-02-29 | 2024-09-13 | 198 | 142 | 2024-09-13 | 2024-09-13 | 1 | 1 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-29 | 47 | 33 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-29 | 2024-11-05 | 8 | 6 | 2024-11-05 | 2024-11-04 | Unknown | Unknown | 245 | 175 | 9 | 7 | 254 | 182 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 2572.05 | 2572.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-08-02 | -514 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-18 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 1022.7 | Unknown | Unknown | Unknown | -1027 | 2049.7 | Unknown | 903.3 | 1022.7 | -119.4 | Yes | N/A | N/A | 2024-09-17 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-09-18 | 37 | 27 | 2024-09-18 | 2024-11-21 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-02-26 | 93 | 67 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-26 | 2025-03-06 | 9 | 7 | 2025-03-06 | 2025-03-06 | 1 | 1 | 158 | 114 | 47 | 35 | 205 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -454 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 2035.03 | Unknown | Unknown | Unknown | 20.28 | 2014.75 | 3981 | 1341.68 | 2035.03 | -693.35 | Yes | N/A | N/A | 2024-10-07 | 2024-10-11 | 5 | 5 | 2024-10-11 | 2024-10-22 | 12 | 8 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2025-05-06 | 197 | 141 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-05-06 | 2025-05-30 | 25 | 19 | 2025-05-30 | 2025-05-30 | 1 | 1 | 202 | 146 | 38 | 28 | 240 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 852 | 852 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 444 | 318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-24 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 26.53 | Unknown | Unknown | Unknown | Unknown | 26.53 | 3981 | 1136.41 | 26.53 | 1109.88 | Yes | N/A | N/A | 2024-10-14 | 2024-10-24 | 11 | 9 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-03-10 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-20 | 11 | 9 | 2025-03-20 | 2025-03-19 | Unknown | Unknown | 149 | 107 | 12 | 10 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | 651 | 651 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | 254 | 183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8519.9 | Unknown | Unknown | Unknown | -196 | 8715.9 | Unknown | 392.46 | 8519.9 | -8127.44 | Yes | N/A | N/A | 2024-05-06 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-24 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-07-03 | 1 | 1 | 0 | 0 | 29 | 21 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 2543.1 | 2543.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-03-25 | -294 | -211 | No | 2024-07-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2025-06-02 | IOU Designed & Installed | N/A | Yes | 292 | 1333.01 | -8.27 | Unknown | Unknown | 28.44 | 1312.84 | 3981 | 1451.16 | 1333.01 | 118.15 | Yes | N/A | N/A | 2024-07-25 | 2025-04-21 | 271 | 193 | 2025-04-21 | 2025-05-13 | 23 | 17 | 2025-05-13 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2025-06-02 | 313 | 223 | Unknown | 2025-05-15 | Unknown | Unknown | 2025-06-02 | 2025-06-04 | 3 | 3 | 2025-06-04 | 2025-06-04 | 1 | 1 | 584 | 416 | 27 | 21 | 611 | 437 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -268 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-03 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | -178.78 | 252.46 | Unknown | Unknown | -957 | 525.76 | 0 | 957.27 | -178.78 | 1136.05 | Yes | N/A | N/A | 2023-04-26 | 2023-05-03 | 8 | 6 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2024-04-02 | 236 | 168 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-03 | 2 | 2 | 2024-04-03 | 2024-04-03 | 1 | 1 | 244 | 174 | 3 | 3 | 247 | 177 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 143 | 143 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 21.44 | Unknown | Unknown | Unknown | Unknown | 21.44 | 3981 | 603.96 | 21.44 | 582.52 | Yes | N/A | N/A | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-08-19 | 82 | 58 | Unknown | 2024-06-06 | Unknown | Unknown | 2024-08-19 | 2024-08-30 | 12 | 10 | 2024-08-30 | 2024-08-30 | 1 | 1 | 83 | 59 | 14 | 12 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 149.1 | 149.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -394 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 32124.19 | 2754.09 | Unknown | Unknown | 24.88 | 29345.22 | 3981 | 1852.19 | 32124.19 | -30272 | Yes | N/A | N/A | 2024-11-27 | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2025-04-03 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-11 | 9 | 7 | 2025-04-03 | 2025-04-04 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-05-06 | 22 | 16 | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 2 | 2 | 209 | 151 | 211 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | 149 | 106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 236.93 | 2803.06 | Unknown | 214.66 | -3976 | 1195.21 | 0 | 3976.09 | 236.93 | 3739.16 | Yes | N/A | N/A | 2023-02-22 | 2023-03-06 | 13 | 9 | 2023-03-06 | 2023-03-08 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 13 | 9 | 4 | 4 | 17 | 13 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 689.83 | -46.48 | Unknown | Unknown | Unknown | 736.31 | Unknown | 941.85 | 689.83 | 252.02 | Yes | N/A | N/A | 2024-03-07 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-03-07 | 10 | 8 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-11 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-29 | 19 | 13 | 2024-04-29 | 2024-04-29 | 1 | 1 | 36 | 26 | 30 | 22 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -561 | -401 | No | 2023-03-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-05-26 | IOU Designed & Installed | N/A | Yes | 31 | 1396.07 | 239.56 | Unknown | 89.36 | Unknown | 1067.15 | 3885 | 715.04 | 1396.07 | -681.03 | Yes | N/A | N/A | 2023-03-24 | 2023-04-24 | 32 | 22 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-05-26 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | 2023-05-26 | 1 | 1 | 96 | 68 | 2 | 2 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-11-10 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 0.8 | -11.28 | Unknown | Unknown | Unknown | 12.08 | 3981 | 812.14 | 0.8 | 811.34 | Yes | N/A | N/A | 2023-10-05 | 2023-11-07 | 34 | 24 | 2023-11-07 | 2023-11-10 | 4 | 4 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-12-20 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-05 | 17 | 13 | 2024-01-05 | 2024-01-04 | Unknown | Unknown | 75 | 53 | 21 | 17 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 1279.94 | -25.71 | Unknown | Unknown | Unknown | 1305.65 | 3981 | 1893.35 | 1279.94 | 613.41 | Yes | N/A | N/A | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-26 | 41 | 29 | 2025-02-13 | 2025-04-04 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-17 | 14 | 10 | 2025-04-17 | 2025-04-17 | 1 | 1 | 52 | 38 | 57 | 41 | 109 | 79 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 293.05 | 293.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 1795.06 | 543.79 | Unknown | 47.31 | Unknown | 1203.96 | Unknown | 1315.49 | 1795.06 | -479.57 | Yes | N/A | N/A | 2024-04-03 | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2024-04-08 | 124 | 88 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-07-18 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-22 | 5 | 3 | 2024-07-22 | 2024-07-22 | 1 | 1 | 102 | 74 | 130 | 92 | 232 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -543 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-09-25 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | -445.85 | Unknown | Unknown | Unknown | -516 | 70.15 | 3981 | 3442.81 | -445.85 | 3888.66 | Yes | N/A | N/A | 2024-05-29 | 2024-08-29 | 93 | 67 | 2024-08-29 | 2024-10-09 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-24 | 16 | 12 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-11-05 | 13 | 9 | 2024-11-05 | 2024-11-04 | Unknown | Unknown | 109 | 79 | 55 | 39 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.4 | -10 | Unknown | Unknown | Unknown | 6.6 | 3981 | 940.08 | -3.4 | 943.48 | Yes | N/A | N/A | 2023-03-28 | 2023-04-07 | 11 | 9 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-01 | -442 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-22 | 2025-06-13 | IOU Designed & Installed | N/A | No | N/A | 1402.69 | Unknown | Unknown | Unknown | 25.24 | 1377.45 | 7962 | 1383.27 | 1402.69 | -19.42 | Yes | N/A | N/A | 2024-11-11 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-12-20 | 44 | 32 | 2024-12-20 | 2025-04-21 | 123 | 87 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-06-13 | 176 | 126 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-06-13 | 2025-06-16 | 4 | 2 | 2025-06-16 | 2025-06-16 | 1 | 1 | 299 | 213 | 49 | 35 | 348 | 248 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 198 | 198 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -521 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-08-14 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 11876.06 | 706.44 | Unknown | Unknown | -10611.12 | 21780.74 | 3981 | 14653.04 | 11876.06 | 2776.98 | Yes | N/A | N/A | 2023-05-03 | 2023-06-27 | 56 | 40 | 2023-06-27 | 2024-04-12 | 291 | 209 | 2023-10-04 | 2024-05-06 | 45 | 33 | 2023-11-27 | 2024-06-28 | 42 | 32 | 2024-04-12 | 2024-05-06 | 25 | 17 | 2024-04-17 | 2024-05-20 | 34 | 24 | 2024-06-18 | 2024-07-19 | 32 | 24 | 2024-07-19 | 2024-07-17 | Unknown | Unknown | 126 | 90 | 399 | 289 | 525 | 379 | Steps 2,3,5,6,7 | 448 | 320 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-09-30 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | -1385.06 | 44.75 | Unknown | Unknown | -1485 | 55.19 | Unknown | 1613.89 | -1385.06 | 2998.95 | Yes | N/A | N/A | 2024-06-05 | 2024-07-22 | 48 | 34 | 2024-07-22 | 2024-09-30 | 71 | 51 | 2024-09-30 | 2025-04-22 | 205 | 147 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-22 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 258 | 184 | 74 | 54 | 332 | 238 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | 102 | 73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1221.43 | -22.39 | Unknown | Unknown | Unknown | 1243.82 | 7962 | 949.68 | 1221.43 | -271.75 | Yes | N/A | N/A | 2024-02-16 | 2024-03-06 | 20 | 14 | 2024-03-06 | 2025-01-24 | 325 | 233 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2025-01-29 | 15 | 11 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 20 | 14 | 341 | 245 | 361 | 259 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 21.36 | Unknown | Unknown | Unknown | Unknown | 21.36 | Unknown | 1619.94 | 21.36 | 1598.58 | Yes | N/A | N/A | 2024-08-12 | 2024-09-06 | 26 | 20 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-10-21 | 1 | 1 | 26 | 20 | 2 | 2 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | -921.28 | -1.56 | Unknown | Unknown | -1442 | 522.28 | Unknown | 1441.57 | -921.28 | 2362.85 | Yes | N/A | N/A | 2025-02-10 | 2025-03-24 | 43 | 31 | 2025-03-24 | 2025-03-25 | 2 | 2 | 2025-03-25 | 2025-04-16 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-06-04 | 50 | 36 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-04 | 2025-06-12 | 9 | 7 | 2025-06-12 | 2025-06-12 | 1 | 1 | 116 | 84 | 12 | 10 | 128 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 273 | 273 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-18 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-25 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 14.3 | -12.68 | Unknown | Unknown | Unknown | 26.98 | Unknown | 960.08 | 14.3 | 945.78 | Yes | N/A | N/A | 2024-04-23 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | 2024-04-25 | 52 | 38 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-17 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-29 | 13 | 9 | 2024-05-29 | 2024-05-29 | 1 | 1 | 23 | 17 | 66 | 48 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 115.2 | 115.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | -474 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2022-11-08 | 2023-03-31 | IOU Designed & Installed | N/A | No | N/A | 4913.88 | 121.66 | Unknown | 50.62 | 22.46 | 4719.14 | Unknown | 1516.71 | 4913.88 | -3397.17 | Yes | N/A | N/A | 2022-11-08 | 2023-01-31 | 85 | 61 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-03-31 | 60 | 44 | Unknown | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-04-10 | 11 | 7 | 2023-04-10 | 2023-04-10 | 1 | 1 | 145 | 105 | 12 | 8 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 594.05 | 594.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -165 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 3964.56 | Unknown | Unknown | Unknown | -1159 | 5123.56 | Unknown | 1007.76 | 3964.56 | -2956.8 | Yes | N/A | N/A | 2024-11-19 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2025-04-15 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-22 | 8 | 6 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-22 | 2025-05-07 | 16 | 12 | 2025-05-07 | 2025-05-05 | Unknown | Unknown | 8 | 6 | 261 | 187 | 269 | 193 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-10 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 16365.89 | 909.34 | Unknown | 91.61 | -14438.81 | 29803.75 | Unknown | 11093.14 | 16365.89 | -5272.75 | Yes | N/A | N/A | 2024-11-08 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-12-17 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-05-05 | 89 | 63 | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 131 | 93 | 131 | 93 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-28 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | -1698.21 | Unknown | Unknown | Unknown | -1731 | 32.79 | Unknown | 1660.01 | -1698.21 | 3358.22 | Yes | N/A | N/A | 2025-01-27 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-28 | 15 | 11 | 2025-01-28 | 2025-02-19 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-25 | 7 | 5 | 2025-02-25 | 2025-02-28 | 4 | 4 | 24 | 18 | 26 | 20 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | SAN DIEGO | 126.1 | 126.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-02 | 196 | 141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-27 | 2024-04-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1799.92 | 60.89 | Unknown | Unknown | 6.67 | 1732.36 | 7962 | 968.58 | 1799.92 | -831.34 | Yes | N/A | N/A | 2024-04-27 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-05-08 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-07-12 | 66 | 48 | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 66 | 48 | 58 | 42 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -398 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 569.99 | 367.35 | Unknown | Unknown | Unknown | 202.64 | 26990 | 320.3 | 569.99 | -249.69 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-12-04 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-08 | 5 | 5 | 2023-12-08 | 2023-12-08 | 1 | 1 | 160 | 114 | 7 | 7 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-10 | 202 | 145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-06-12 | 2023-11-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 998.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-22 | 2023-06-09 | 19 | 15 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-11-23 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | 2023-11-23 | 2023-11-28 | 6 | 4 | 2023-11-28 | 2023-11-28 | 1 | 1 | 184 | 134 | 7 | 5 | 191 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -521 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.6 | -6.96 | Unknown | Unknown | Unknown | -2.64 | 3885 | 517.21 | -9.6 | 526.81 | Yes | N/A | N/A | 2023-03-24 | 2023-04-16 | 24 | 16 | 2023-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 24 | 16 | 1 | 1 | 25 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 116804 | 116804 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-04-02 | 124 | 90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-06-05 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 4764.46 | -43.36 | Unknown | Unknown | Unknown | 4807.82 | 3981 | 680.99 | 4764.46 | -4083.47 | Yes | N/A | N/A | 2023-04-24 | 2023-06-05 | 43 | 31 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-07-26 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-16 | 22 | 16 | 2023-08-16 | 2023-08-04 | Unknown | Unknown | 95 | 69 | 22 | 16 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-02 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2024-01-11 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 5536.94 | 1662.26 | Unknown | 536.8 | Unknown | 3337.88 | Unknown | 896.69 | 5536.94 | -4640.25 | Yes | N/A | N/A | 2023-12-07 | 2023-09-18 | Unknown | Unknown | 2023-09-18 | 2024-01-11 | 116 | 84 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-01-23 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-04-10 | 79 | 57 | 2024-04-10 | 2024-04-10 | 1 | 1 | 13 | 9 | 196 | 142 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 6.44 | Unknown | Unknown | Unknown | Unknown | 6.44 | 3981 | 197.01 | 6.44 | 190.57 | Yes | N/A | N/A | 2024-10-31 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-12-23 | 62 | 44 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2024-12-26 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-14 | 20 | 14 | 2025-01-14 | 2025-01-14 | 1 | 1 | 4 | 4 | 83 | 59 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 42.29 | Unknown | Unknown | Unknown | Unknown | 42.29 | Unknown | 1954.9 | 42.29 | 1912.61 | Yes | N/A | N/A | 2025-02-13 | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-02-13 | 32 | 24 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-26 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-19 | 22 | 16 | 2025-03-19 | 2025-03-19 | 1 | 1 | 14 | 10 | 55 | 41 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | Unknown | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 7.07 | -6.23 | Unknown | Unknown | Unknown | 13.3 | 3981 | 1025.78 | 7.07 | 1018.71 | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-15 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-18 | 4 | 4 | 2024-04-18 | 2024-04-18 | 1 | 1 | 13 | 9 | 6 | 6 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -449 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 767.53 | 439.96 | Unknown | Unknown | Unknown | 327.57 | 3981 | 526.48 | 767.53 | -241.05 | Yes | N/A | N/A | 2024-01-16 | 2023-11-13 | Unknown | Unknown | 2023-11-13 | 2024-02-12 | 92 | 66 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-15 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-25 | 42 | 30 | 2024-04-25 | 2024-04-25 | 1 | 1 | 33 | 25 | 135 | 97 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-05 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 488.59 | -8.01 | Unknown | Unknown | 6.09 | 490.51 | Unknown | 1460.16 | 488.59 | 971.57 | Yes | N/A | N/A | 2024-07-24 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-08-12 | 61 | 43 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2025-02-11 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-11 | 29 | 21 | 2025-03-11 | 2025-03-11 | 1 | 1 | 184 | 132 | 91 | 65 | 275 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-28 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.11 | Unknown | Unknown | Unknown | Unknown | 30.11 | 3981 | 743.25 | 30.11 | 713.14 | Yes | N/A | N/A | 2024-03-01 | 2024-04-11 | 42 | 30 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-08-22 | 1 | 1 | 42 | 30 | 2 | 2 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-11-17 | 2024-02-23 | IOU Designed & Installed | N/A | No | N/A | 6650.78 | 1969.08 | Unknown | 21.53 | Unknown | 4660.17 | 7962 | 1107.01 | 6650.78 | -5543.77 | Yes | N/A | N/A | 2023-10-13 | 2023-11-15 | 34 | 24 | 2023-11-15 | 2023-12-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-28 | 12 | 8 | 2023-12-20 | 2024-01-11 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-02-26 | 4 | 2 | 2024-02-26 | 2024-02-26 | 1 | 1 | 57 | 41 | 53 | 37 | 110 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -583 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-01 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 985.56 | 356.64 | Unknown | Unknown | Unknown | 628.92 | Unknown | 783.58 | 985.56 | -201.98 | Yes | N/A | N/A | 2023-04-26 | 2023-05-01 | 6 | 4 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-07-19 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-07-20 | 2 | 2 | 2023-07-20 | 2023-07-20 | 1 | 1 | 86 | 62 | 3 | 3 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 201 | 144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | 11.23 | -10.04 | Unknown | Unknown | Unknown | 21.27 | 3981 | 1873.41 | 11.23 | 1862.18 | Yes | N/A | N/A | 2023-10-02 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-10-02 | 35 | 25 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2024-02-28 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-19 | 21 | 15 | 2024-03-19 | 2024-03-19 | 1 | 1 | 150 | 108 | 57 | 41 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -670 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 1411.77 | -27.82 | Unknown | Unknown | Unknown | 1439.59 | 3981 | 1761.55 | 1411.77 | 349.78 | Yes | N/A | N/A | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-26 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-23 | 28 | 20 | 2024-12-23 | 2024-12-23 | 1 | 1 | 8 | 6 | 30 | 22 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-18 | -355 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-20 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 6000.24 | 1969.33 | Unknown | Unknown | Unknown | 4030.91 | 3981 | 988.72 | 6000.24 | -5011.52 | Yes | N/A | N/A | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | 2025-05-20 | 2 | 2 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-28 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | 2025-05-28 | 1 | 1 | 10 | 8 | 4 | 4 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-18 | -684 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-14 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 945.75 | -19.01 | Unknown | Unknown | Unknown | 964.76 | Unknown | 1498.56 | 945.75 | 552.81 | Yes | N/A | N/A | 2025-05-09 | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-14 | 10 | 8 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-16 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-03 | 19 | 13 | 2025-06-03 | 2025-06-03 | 1 | 1 | 3 | 3 | 30 | 22 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.65 | -7.84 | Unknown | Unknown | Unknown | -1.81 | 3981 | 154.79 | -9.65 | 164.44 | Yes | N/A | N/A | 2023-03-29 | 2023-04-17 | 20 | 14 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-06-29 | 1 | 1 | 20 | 14 | 1 | 1 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-20 | 2024-01-20 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 894.88 | 253.43 | Unknown | Unknown | Unknown | 641.45 | 3981 | 1119.34 | 894.88 | 224.46 | Yes | N/A | N/A | 2024-01-20 | 2024-01-20 | 1 | 0 | 2024-01-20 | 2024-01-20 | 1 | 0 | 2024-01-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-20 | 2024-10-01 | 256 | 182 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-07 | 7 | 5 | 2024-10-07 | 2024-10-07 | 1 | 1 | 257 | 182 | 9 | 6 | 266 | 188 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | -6.52 | -5.29 | Unknown | Unknown | Unknown | -1.23 | 3981 | 902.02 | -6.52 | 908.54 | Yes | N/A | N/A | 2023-12-21 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-12-21 | 121 | 87 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-02-28 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-15 | 17 | 13 | 2024-03-15 | 2024-03-15 | 1 | 1 | 70 | 50 | 139 | 101 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 119.1 | 119.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-21 | 2023-06-15 | IOU Designed & Installed | N/A | No | N/A | 634.13 | 232.94 | Unknown | Unknown | Unknown | 401.19 | Unknown | 845.06 | 634.13 | 210.93 | Yes | N/A | N/A | 2023-02-17 | 2023-02-21 | 5 | 3 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | 2023-06-15 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-06-16 | 2 | 2 | 2023-06-16 | 2023-06-16 | 1 | 1 | 119 | 85 | 3 | 3 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 154.1 | 154.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 1124.81 | 404.44 | Unknown | 43.38 | Unknown | 676.99 | Unknown | 270.38 | 1124.81 | -854.43 | Yes | N/A | N/A | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-10-12 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-26 | 15 | 11 | 2023-10-26 | 2023-10-26 | 1 | 1 | 93 | 67 | 17 | 13 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Rancho Santa fe | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-16 | 292 | 209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-12-15 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 5330.45 | 272.1 | Unknown | Unknown | -1743.08 | 6801.43 | 556 | 4959.52 | 5330.45 | -370.93 | Yes | N/A | N/A | 2023-09-01 | 2024-01-11 | 133 | 95 | 2024-01-11 | 2024-04-24 | 105 | 75 | 2023-09-05 | 2024-03-22 | 3 | 3 | 2024-04-09 | 2024-04-11 | 3 | 3 | 2024-05-13 | Unknown | Unknown | Unknown | 2024-05-13 | 2024-07-16 | 65 | 47 | 2024-07-23 | 2024-09-03 | 43 | 31 | 2024-09-03 | 2024-09-03 | 1 | 1 | 136 | 98 | 217 | 157 | 353 | 255 | Steps 2,3,5,6,7 | 232 | 166 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 14.1 | 14.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -480 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 897.03 | Unknown | Unknown | Unknown | 11.66 | 885.37 | 3981 | 2968.82 | 897.03 | 2071.79 | Yes | N/A | N/A | 2024-12-17 | 2025-03-24 | 98 | 70 | 2025-03-24 | 2025-04-01 | 9 | 7 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-06-11 | 72 | 52 | Unknown | 2025-05-14 | Unknown | Unknown | 2025-06-11 | 2025-06-17 | 7 | 5 | 2025-06-17 | 2025-06-17 | 1 | 1 | 170 | 122 | 17 | 13 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-15 | 358 | 257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-19 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 17658.37 | 470.59 | Unknown | Unknown | 134.94 | 17052.84 | 133153 | 34375.02 | 17658.37 | 16716.65 | Yes | N/A | N/A | 2023-04-12 | 2023-05-19 | 38 | 28 | 2023-05-19 | 2023-12-18 | 214 | 152 | 2023-10-12 | 2023-10-16 | 5 | 3 | 2023-12-05 | 2024-01-04 | 31 | 23 | 2023-12-18 | Unknown | Unknown | Unknown | 2024-01-03 | 2024-04-15 | 104 | 74 | 2024-04-18 | 2024-05-07 | 20 | 14 | 2024-05-07 | 2024-05-07 | 1 | 1 | 43 | 31 | 370 | 264 | 413 | 295 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | Dulzura | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 301 | 216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5218.9 | 78.56 | Unknown | Unknown | -5935 | 637.54 | 2803 | 14673.93 | -5218.9 | 19892.83 | Yes | N/A | N/A | 2022-12-07 | 2023-02-17 | 73 | 53 | 2023-02-17 | 2023-09-19 | 215 | 153 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-09-27 | 1 | 1 | 73 | 53 | 226 | 162 | 299 | 215 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | 150 | 107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7165.37 | 1447.72 | Unknown | 406.3 | Unknown | 5311.35 | Unknown | 917.9 | 7165.37 | -6247.47 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | 2024-06-27 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1 | 1 | 1 | 1 | 88 | 64 | 89 | 65 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 535 | 382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 6215.42 | 9567.88 | Unknown | 912.71 | -11488 | 7222.83 | Unknown | 11488.29 | 6215.42 | 5272.87 | Yes | N/A | N/A | 2024-10-08 | 2024-10-11 | 4 | 4 | 2024-10-11 | 2024-10-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-10-27 | 3 | 1 | 2024-10-27 | 2024-10-27 | 1 | 0 | 4 | 4 | 19 | 12 | 23 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -309 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2023-07-06 | IOU Designed & Installed | N/A | No | N/A | 5592.25 | 1730.24 | Unknown | 795.45 | 3.03 | 3063.53 | Unknown | 936.41 | 5592.25 | -4655.84 | Yes | N/A | N/A | 2023-05-25 | 2023-05-25 | 1 | 1 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-07-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-07 | 2 | 2 | 2023-07-07 | 2023-07-07 | 1 | 1 | 44 | 32 | 3 | 3 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 689.15 | 689.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -220 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 47460.22 | 6642.04 | Unknown | Unknown | 28.13 | 40790.05 | 71636 | 56587.12 | 47460.22 | 9126.9 | Yes | N/A | N/A | 2024-07-02 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2025-01-16 | 252 | 180 | 2024-09-03 | 2024-09-03 | 1 | 1 | 2025-02-06 | 2025-06-25 | 25 | 17 | 2025-01-16 | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-21 | 46 | 34 | 2025-02-25 | 2025-04-24 | 59 | 43 | 2025-04-24 | 2025-04-24 | 1 | 1 | 1 | 1 | 383 | 275 | 384 | 276 | Steps 2,3,5,6,7 | 319 | 229 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-22 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-24 | 2023-09-24 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 191.94 | 48.55 | Unknown | Unknown | 0.35 | 143.04 | 3981 | 708.83 | 191.94 | 516.89 | Yes | N/A | N/A | 2023-09-24 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-10-27 | 122 | 88 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-06 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-12-12 | 37 | 27 | 2023-12-12 | 2023-12-12 | 1 | 1 | 11 | 7 | 160 | 116 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -178 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 26990 | 344.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-01 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 3273.98 | Unknown | Unknown | Unknown | Unknown | 3273.98 | Unknown | 1100.98 | 3273.98 | -2173 | Yes | N/A | N/A | 2024-07-30 | 2024-08-12 | 14 | 10 | 2024-08-12 | 2024-09-11 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-11-18 | 55 | 39 | 2024-11-18 | 2024-11-18 | 1 | 1 | 14 | 10 | 87 | 63 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 15.12 | -13.43 | Unknown | Unknown | Unknown | 28.55 | Unknown | 1444.6 | 15.12 | 1429.48 | Yes | N/A | N/A | 2024-05-23 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-28 | 70 | 50 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-18 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-20 | 3 | 3 | 2024-06-20 | 2024-06-20 | 1 | 1 | 22 | 16 | 74 | 54 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 268.05 | 268.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 1283.04 | 316.44 | Unknown | 89.32 | 7.42 | 869.86 | 3981 | 1194.41 | 1283.04 | -88.63 | Yes | N/A | N/A | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-11-06 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-12-03 | 28 | 20 | 2024-12-03 | 2024-12-03 | 1 | 1 | 45 | 33 | 30 | 22 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -600 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 1441.18 | -0.94 | Unknown | Unknown | 4.69 | 1437.43 | 3981 | 1400.71 | 1441.18 | -40.47 | Yes | N/A | N/A | 2024-10-07 | 2024-10-29 | 23 | 17 | 2024-10-29 | 2024-11-08 | 11 | 9 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2025-01-23 | 77 | 55 | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-23 | 2025-01-28 | 6 | 4 | 2025-01-28 | 2025-01-28 | 1 | 1 | 100 | 72 | 18 | 14 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -383 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 586.63 | -7.87 | Unknown | Unknown | 0.76 | 593.74 | 3981 | 1215.49 | 586.63 | 628.86 | Yes | N/A | N/A | 2023-10-12 | 2023-08-17 | Unknown | Unknown | 2023-08-17 | 2023-11-28 | 104 | 74 | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-05-16 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-07-03 | 49 | 35 | 2024-07-03 | 2024-07-03 | 1 | 1 | 171 | 123 | 154 | 110 | 325 | 233 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 378.1 | 378.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-29 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 635.25 | -11.38 | Unknown | Unknown | 6.83 | 639.8 | 3981 | 1055.79 | 635.25 | 420.54 | Yes | N/A | N/A | 2023-12-14 | 2023-12-03 | Unknown | Unknown | 2023-12-03 | 2023-12-18 | 16 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-04-09 | 42 | 30 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | 2024-04-18 | 2024-04-24 | 7 | 5 | 2024-04-24 | 2024-04-24 | 1 | 1 | 0 | 0 | 66 | 47 | 66 | 47 | Steps 2,3,5,6,7 | 113 | 81 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 192.15 | 192.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-05-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 804.12 | -14.94 | Unknown | Unknown | Unknown | 819.06 | 11943 | 5214.64 | 804.12 | 4410.52 | Yes | N/A | N/A | 2024-04-26 | 2024-05-28 | 33 | 23 | 2024-05-28 | 2024-05-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-24 | 27 | 19 | 2024-05-29 | 2024-09-19 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-02 | Unknown | Unknown | 147 | 105 | 29 | 21 | 176 | 126 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-24 | -169 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 327.11 | 72.04 | Unknown | 48.69 | 4.84 | 201.54 | 3981 | 1384.85 | 327.11 | 1057.74 | Yes | N/A | N/A | 2024-07-02 | 2024-08-28 | 58 | 42 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 58 | 42 | 2 | 2 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -528 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | -112.65 | -47.81 | Unknown | Unknown | -1647 | 1582.16 | Unknown | 1511.39 | -112.65 | 1624.04 | Yes | N/A | N/A | 2024-10-09 | 2024-10-14 | 6 | 4 | 2024-10-14 | 2024-11-25 | 43 | 31 | 2024-11-25 | 2025-01-16 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-02-18 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-28 | 39 | 29 | 2025-03-28 | 2025-03-27 | Unknown | Unknown | 93 | 67 | 82 | 60 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-06 | 604 | 433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 13112.58 | Unknown | Unknown | Unknown | 1396.34 | 11716.24 | 8164 | 3203.33 | 13112.58 | -9909.25 | Yes | N/A | N/A | 2023-04-19 | 2023-04-25 | 7 | 5 | 2023-04-25 | 2023-08-14 | 112 | 80 | 2024-07-16 | 2024-07-19 | 4 | 4 | 2023-08-04 | 2024-07-31 | 32 | 22 | 2023-08-14 | 2024-06-24 | 316 | 226 | 2024-01-30 | 2024-06-05 | 128 | 92 | 2024-06-27 | 2024-08-09 | 44 | 32 | 2024-08-09 | 2024-08-01 | Unknown | Unknown | 327 | 235 | 316 | 226 | 643 | 461 | Steps 2,3,5,6,7 | 848 | 606 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 123 | 123 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-20 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 803.65 | -39.86 | Unknown | Unknown | Unknown | 843.51 | 15924 | 1058.68 | 803.65 | 255.03 | Yes | N/A | N/A | 2023-11-30 | 2023-12-04 | 5 | 3 | 2023-12-04 | 2023-12-20 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-12 | 13 | 9 | 2023-12-20 | 2024-03-21 | 93 | 67 | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-02 | Unknown | Unknown | 98 | 70 | 30 | 22 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-08 | 2023-10-09 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | -7.25 | -7.38 | Unknown | Unknown | Unknown | 0.13 | 3941 | 152.86 | -7.25 | 160.11 | Yes | N/A | N/A | 2023-10-08 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-11-21 | 111 | 79 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-03-14 | 108 | 78 | 2024-03-14 | 2024-03-14 | 1 | 1 | 8 | 6 | 220 | 158 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 544.33 | -6.79 | Unknown | Unknown | Unknown | 551.12 | 3981 | 708.83 | 544.33 | 164.5 | Yes | N/A | N/A | 2023-10-27 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-11-17 | 102 | 74 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-01-30 | 75 | 53 | Unknown | 2024-01-29 | Unknown | Unknown | 2024-01-30 | 2024-02-28 | 30 | 22 | 2024-02-28 | 2024-02-28 | 1 | 1 | 75 | 53 | 133 | 97 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | 271 | 194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 518.37 | -9.44 | Unknown | Unknown | Unknown | 527.81 | 3981 | 1029.82 | 518.37 | 511.45 | Yes | N/A | N/A | 2024-04-12 | 2024-04-18 | 7 | 5 | 2024-04-18 | 2024-05-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-05-15 | 28 | 20 | 2024-05-17 | 2024-08-26 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-08 | Unknown | Unknown | 109 | 77 | 58 | 42 | 167 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-30 | 540 | 387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 441.5 | -11.14 | Unknown | Unknown | 14.37 | 438.27 | 7962 | 571.14 | 441.5 | 129.64 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | 2023-02-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-05-03 | 83 | 59 | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-06-23 | Unknown | Unknown | 84 | 60 | 8 | 6 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA9 PH4 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 673 | 482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | 2024-10-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 104904.15 | 28149.92 | Unknown | Unknown | 5651.27 | 71102.96 | 0 | 31713.29 | 104904.15 | -73190.86 | Yes | N/A | N/A | 2022-04-27 | 2023-04-18 | 357 | 255 | 2023-04-18 | 2023-10-12 | 178 | 128 | 2023-05-23 | 2024-04-08 | 24 | 16 | 2023-10-12 | 2023-10-25 | 14 | 10 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-22 | 349 | 249 | 2024-10-23 | 2025-01-21 | 91 | 65 | 2025-01-21 | 2025-01-21 | 1 | 1 | 381 | 271 | 633 | 453 | 1014 | 724 | Steps 2,3,5,6,7 | 321 | 229 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | -690 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 1725.14 | 381.42 | Unknown | 169.96 | Unknown | 1173.76 | 3981 | 1608.36 | 1725.14 | -116.78 | Yes | N/A | N/A | 2025-03-25 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-25 | 5 | 3 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-07 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-15 | 9 | 7 | 2025-04-15 | 2025-04-15 | 1 | 1 | 14 | 10 | 15 | 11 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 127.05 | 127.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 788.23 | 241.68 | Unknown | Unknown | Unknown | 546.55 | 3981 | 756.73 | 788.23 | -31.5 | Yes | N/A | N/A | 2024-03-27 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-03-27 | 92 | 66 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-07-22 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-13 | 23 | 17 | 2024-08-13 | 2024-08-13 | 1 | 1 | 118 | 84 | 116 | 84 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 1395.25 | Unknown | Unknown | Unknown | 18.25 | 1377 | 3941 | 1082.18 | 1395.25 | -313.07 | Yes | N/A | N/A | 2024-04-18 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-06-11 | 112 | 80 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-08-05 | 56 | 40 | Unknown | 2024-07-29 | Unknown | Unknown | 2024-08-05 | 2024-09-09 | 36 | 26 | 2024-09-09 | 2024-09-09 | 1 | 1 | 56 | 40 | 149 | 107 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-20 | 873 | 624 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -200.88 | -6.92 | Unknown | Unknown | -584 | 390.04 | Unknown | 511.25 | -200.88 | 712.13 | Yes | N/A | N/A | 2025-01-03 | 2025-01-10 | 8 | 6 | 2025-01-10 | 2025-02-05 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-29 | 20 | 14 | 2025-02-05 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-11 | Unknown | Unknown | 8 | 6 | 47 | 33 | 55 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1281 | 1281 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-06-07 | -568 | -406 | No | 2023-09-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-10-16 | 2023-11-15 | IOU Designed & Installed | N/A | Yes | 42 | 2864.23 | 890.41 | Unknown | 281.98 | Unknown | 1691.84 | 3981 | 994.1 | 2864.23 | -1870.13 | Yes | N/A | N/A | 2023-09-06 | 2023-10-18 | 43 | 31 | 2023-10-18 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-11-15 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-11-17 | 3 | 3 | 2023-11-17 | 2023-11-17 | 1 | 1 | 74 | 54 | 4 | 4 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 820.97 | -12.66 | Unknown | Unknown | Unknown | 833.63 | 3981 | 766.01 | 820.97 | -54.96 | Yes | N/A | N/A | 2024-02-28 | 2024-03-25 | 27 | 19 | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-05-03 | 40 | 30 | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-17 | 15 | 11 | 2024-05-17 | 2024-05-17 | 1 | 1 | 67 | 49 | 17 | 13 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -372 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-07-05 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 33.42 | Unknown | Unknown | Unknown | Unknown | 33.42 | 3707 | 1022.83 | 33.42 | 989.41 | Yes | N/A | N/A | 2024-05-21 | 2024-06-04 | 15 | 11 | 2024-06-04 | 2024-07-05 | 32 | 24 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-12-20 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-22 | 34 | 24 | 2025-01-22 | 2025-01-22 | 1 | 1 | 184 | 132 | 67 | 49 | 251 | 181 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-09-11 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 0.37 | -10.32 | Unknown | Unknown | Unknown | 10.69 | 3981 | 879.54 | 0.37 | 879.17 | Yes | N/A | N/A | 2023-05-01 | 2023-09-11 | 134 | 96 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-27 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-08 | 13 | 9 | 2023-11-08 | 2023-11-06 | Unknown | Unknown | 181 | 131 | 14 | 10 | 195 | 141 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 123 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 7.03 | -8.86 | Unknown | Unknown | Unknown | 15.89 | 3981 | 738.54 | 7.03 | 731.51 | Yes | N/A | N/A | 2023-09-19 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-09-19 | 5 | 3 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-12-28 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-03 | 7 | 5 | 2024-01-03 | 2024-01-02 | Unknown | Unknown | 101 | 73 | 12 | 8 | 113 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12011 | 12011 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-21 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-12 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 696.47 | 239.04 | Unknown | Unknown | Unknown | 457.43 | 3981 | 838.69 | 696.47 | 142.22 | Yes | N/A | N/A | 2024-04-12 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-04-12 | 107 | 77 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-04-22 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-04-24 | 3 | 3 | 2024-04-24 | 2024-04-24 | 1 | 1 | 11 | 7 | 111 | 81 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-26 | 1119 | 800 | No | 2020-10-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-14 | 2021-02-12 | Unknown | IOU Designed & Installed | N/A | Yes | 1288 | 20315 | 1125.84 | Unknown | Unknown | 26.84 | 19162.32 | 89716 | 19588.19 | 20315 | -726.81 | Yes | N/A | N/A | 2020-07-14 | 2024-01-30 | 1296 | 926 | 2024-01-30 | 2024-04-25 | 87 | 63 | 2021-12-14 | 2024-01-26 | 2 | 2 | 2024-04-26 | 2024-04-29 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-21 | 36 | 26 | Unknown | 2024-07-19 | Unknown | Unknown | 2024-07-19 | 2024-07-19 | 1 | 1 | 1298 | 928 | 128 | 92 | 1426 | 1020 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -324 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 67.86 | -11.08 | Unknown | Unknown | Unknown | 78.94 | 3981 | 158.37 | 67.86 | 90.51 | Yes | N/A | N/A | 2024-02-22 | 2024-02-22 | 1 | 1 | 2024-02-22 | 2024-02-26 | 5 | 3 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-02-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-26 | 29 | 21 | 2024-03-26 | 2024-03-26 | 1 | 1 | 3 | 3 | 35 | 25 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | MISSION VIEJO | N/A | 212 | 212 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-04 | -19 | -14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | 2059.95 | Unknown | Unknown | Unknown | Unknown | 2059.95 | Unknown | 1630.9 | 2059.95 | -429.05 | Yes | N/A | N/A | 2023-06-01 | 2023-06-01 | 1 | 1 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-15 | 9 | 7 | 2023-09-15 | 2023-09-15 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-29 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 2629.53 | 547.33 | Unknown | Unknown | Unknown | 2082.2 | 3981 | 1416.09 | 2629.53 | -1213.44 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-10-28 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-02 | 36 | 26 | 2024-12-02 | 2024-12-02 | 1 | 1 | 62 | 44 | 38 | 28 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-09-30 | 1350 | 965 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2024-03-28 | 2024-06-08 | IOU Designed & Installed | N/A | No | N/A | -990.57 | 2230.88 | Unknown | 431.12 | -4742 | 1089.43 | Unknown | 4742.38 | -990.57 | 5732.95 | Yes | N/A | N/A | 2023-02-02 | 2024-03-05 | 398 | 284 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-08 | 2024-06-11 | 4 | 2 | 2024-06-11 | 2024-06-11 | 1 | 1 | 398 | 284 | 5 | 3 | 403 | 287 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 358 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-08-23 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 503330.32 | 186110.69 | Unknown | 23459.97 | -232815.77 | 526575.43 | 0 | 254955.44 | 503330.32 | -248374.88 | Yes | N/A | N/A | 2023-07-27 | 2023-08-15 | 20 | 14 | 2023-08-15 | 2024-01-25 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-18 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-11-23 | 304 | 217 | 2024-11-23 | 2024-11-23 | 1 | 0 | 20 | 14 | 478 | 342 | 498 | 356 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-20 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 992.89 | 355.92 | Unknown | Unknown | Unknown | 636.97 | 3981 | 957.49 | 992.89 | -35.4 | Yes | N/A | N/A | 2023-10-05 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-10-20 | 99 | 71 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-11-22 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-11-28 | 7 | 5 | 2023-11-28 | 2023-11-28 | 1 | 1 | 34 | 24 | 107 | 77 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | -17 | -12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-30 | 2023-09-12 | IOU Designed & Installed | N/A | No | N/A | 10179.28 | 4263.62 | Unknown | Unknown | -5541 | 11456.66 | Unknown | 4779.16 | 10179.28 | -5400.12 | Yes | N/A | N/A | 2023-06-29 | 2023-06-30 | 2 | 2 | 2023-06-30 | 2023-07-21 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-03 | 1 | 1 | 2023-07-21 | 2958465 | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | 2023-09-12 | 2023-09-13 | 2 | 2 | 2023-09-13 | 2023-09-14 | 2 | 2 | 2 | 2 | 27 | 21 | 29 | 23 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | -381 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-27 | Unknown | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 1763.82 | -6.02 | Unknown | Unknown | 16.97 | 1752.87 | 3885 | 1746.1 | 1763.82 | -17.72 | Yes | N/A | N/A | 2022-12-27 | 2023-02-01 | 37 | 27 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-27 | 2023-07-20 | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | 2023-07-20 | 2023-07-25 | 6 | 4 | 2023-07-25 | 2023-07-25 | 1 | 1 | 37 | 27 | 7 | 5 | 44 | 32 | Steps 2,3,5,6,7 | 601 | 429 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-09 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.88 | -4.78 | Unknown | Unknown | Unknown | -1.1 | Unknown | 1651.91 | -5.88 | 1657.79 | Yes | N/A | N/A | 2023-08-08 | 2024-02-07 | 184 | 132 | 2024-02-07 | 2025-03-06 | 394 | 282 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-06 | 1 | 1 | 184 | 132 | 395 | 283 | 579 | 415 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-17 | 2023-12-17 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 338.52 | -9.8 | Unknown | Unknown | Unknown | 348.32 | Unknown | 945.39 | 338.52 | 606.87 | Yes | N/A | N/A | 2023-12-17 | 2023-12-17 | 1 | 0 | 2023-12-17 | 2023-12-17 | 1 | 0 | 2023-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-17 | 2023-12-21 | 5 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-24 | 35 | 25 | 2024-01-24 | 2024-01-24 | 1 | 1 | 6 | 4 | 37 | 26 | 43 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | Carlsbad | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -323 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 2452.18 | 223.84 | Unknown | Unknown | Unknown | 2228.34 | Unknown | 4617.1 | 2452.18 | 2164.92 | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-11-01 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2024-02-23 | 115 | 83 | 2024-02-23 | 2024-02-23 | 1 | 1 | 93 | 67 | 116 | 84 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | -613 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-07-24 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 4.29 | Unknown | Unknown | Unknown | Unknown | 4.29 | Unknown | 1049.43 | 4.29 | 1045.14 | Yes | N/A | N/A | 2024-06-30 | 2024-06-30 | 1 | 0 | 2024-06-30 | 2024-06-30 | 1 | 0 | 2024-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-12 | 19 | 13 | 2024-08-12 | 2024-08-12 | 1 | 1 | 3 | 2 | 21 | 14 | 24 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 72.06 | -10.42 | Unknown | Unknown | Unknown | 82.48 | Unknown | 1186.5 | 72.06 | 1114.44 | Yes | N/A | N/A | 2024-03-13 | 2024-03-13 | 1 | 1 | 2024-03-13 | 2024-03-13 | 1 | 1 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-08 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-11 | 4 | 4 | 2024-04-11 | 2024-04-11 | 1 | 1 | 28 | 20 | 6 | 6 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-06-08 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -6.11 | -4.43 | Unknown | Unknown | Unknown | -1.68 | 3981 | 464.78 | -6.11 | 470.89 | Yes | N/A | N/A | 2023-05-01 | 2023-06-08 | 39 | 29 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-07-27 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-14 | 19 | 13 | 2023-08-14 | 2023-08-14 | 1 | 1 | 89 | 65 | 20 | 14 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 194.1 | 194.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 1695.42 | 305.87 | Unknown | 160.02 | 8.28 | 1221.25 | 7962 | 1684.3 | 1695.42 | -11.12 | Yes | N/A | N/A | 2023-10-25 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2024-01-08 | 119 | 85 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-03-14 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-18 | 5 | 3 | 2024-03-18 | 2024-03-18 | 1 | 1 | 67 | 49 | 125 | 89 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | 109 | 79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 197.38 | -33.55 | Unknown | Unknown | -1553 | 1783.93 | Unknown | 1329.35 | 197.38 | 1131.97 | Yes | N/A | N/A | 2024-09-09 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-10-03 | 37 | 27 | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-09-09 | 2025-04-17 | 81 | 59 | 2024-10-03 | 2024-10-15 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-19 | Unknown | Unknown | 15 | 11 | 118 | 86 | 133 | 97 | Steps 2,3,5,6,7 | 235 | 169 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -670 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 3495.78 | 671.25 | Unknown | 26.6 | Unknown | 2797.93 | 3981 | 1577.13 | 3495.78 | -1918.65 | Yes | N/A | N/A | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-04 | 8 | 6 | 2024-05-28 | 2024-06-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-22 | 28 | 20 | 2024-07-22 | 2024-07-22 | 1 | 1 | 30 | 22 | 38 | 28 | 68 | 50 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | -184 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1847.05 | 2742.06 | Unknown | Unknown | -2079 | 1183.99 | Unknown | 2078.54 | 1847.05 | 231.49 | Yes | N/A | N/A | 2023-11-01 | 2023-10-04 | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-12 | -2 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | 2022-10-25 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 6954.88 | -6.88 | Unknown | Unknown | -316.29 | 7278.05 | Unknown | 525.14 | 6954.88 | -6429.74 | Yes | N/A | N/A | 2022-10-25 | 2023-03-23 | 150 | 108 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-08-10 | 126 | 90 | Unknown | 2023-05-17 | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2023-08-10 | 1 | 1 | 276 | 198 | 2 | 2 | 278 | 200 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 470 | 470 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-01 | 572 | 409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-06 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 606.36 | Unknown | Unknown | Unknown | 8.38 | 597.98 | 3981 | 627.81 | 606.36 | 21.45 | Yes | N/A | N/A | 2023-10-05 | 2023-10-05 | 1 | 1 | 2023-10-05 | 2023-10-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-07 | 26 | 18 | 2023-10-20 | 2024-03-14 | 147 | 105 | Unknown | 2024-03-08 | Unknown | Unknown | 2024-03-20 | 2024-03-28 | 9 | 7 | 2024-03-28 | 2024-03-26 | Unknown | Unknown | 148 | 106 | 51 | 37 | 199 | 143 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-14 | -339 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | -4018.75 | 2210.21 | Unknown | 976.14 | -9867 | 2661.9 | Unknown | 9867.41 | -4018.75 | 13886.16 | Yes | N/A | N/A | 2023-09-14 | 2023-09-16 | 3 | 2 | 2023-09-16 | 2023-10-11 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-10 | 2023-10-11 | 2 | 2 | 2023-10-11 | 2023-10-11 | 1 | 1 | 3 | 2 | 30 | 22 | 33 | 24 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 1605 | 1605 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-06-01 | 480 | 343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | 2023-02-02 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 8070.69 | 2169.06 | Unknown | 1022.11 | 204.39 | 4675.13 | 19905 | 1754.77 | 8070.69 | -6315.92 | Yes | N/A | N/A | 2022-06-21 | 2023-03-13 | 266 | 190 | 2023-03-13 | 2023-05-30 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-09-23 | 1 | 1 | 266 | 190 | 81 | 59 | 347 | 249 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 583.96 | 183.68 | Unknown | Unknown | Unknown | 400.28 | 3981 | 987.89 | 583.96 | 403.93 | Yes | N/A | N/A | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-05-22 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-05-23 | 2 | 2 | 2024-05-23 | 2024-05-23 | 1 | 1 | 106 | 76 | 4 | 4 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | PAUMA VALLEY | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-08-20 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 18737.06 | 1395.42 | Unknown | 595.45 | Unknown | 16746.19 | 3981 | 2030.64 | 18737.06 | -16706.42 | Yes | N/A | N/A | 2024-07-15 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-08-20 | 91 | 65 | 2024-08-20 | 2024-11-11 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-11 | 6 | 4 | 2024-11-11 | 2024-11-11 | 1 | 1 | 85 | 61 | 98 | 70 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-11-24 | 1403 | 1003 | No | 2021-11-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-11-19 | 2021-11-19 | Unknown | IOU Designed & Installed | N/A | Yes | 521 | -13.15 | -9.52 | Unknown | Unknown | Unknown | -3.63 | 13818 | 558.3 | -13.15 | 571.45 | Yes | N/A | N/A | 2021-11-19 | 2023-04-24 | 522 | 372 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-09-27 | 1 | 1 | 522 | 372 | 1 | 1 | 523 | 373 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 130 | 94 | No | 2023-08-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | 2024-09-27 | IOU Designed & Installed | N/A | Yes | 403 | 661.79 | -11.86 | Unknown | Unknown | Unknown | 673.65 | 3241 | 789.67 | 661.79 | 127.88 | Yes | N/A | N/A | 2023-08-04 | 2024-09-10 | 404 | 288 | 2024-09-10 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-09-27 | 421 | 301 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-17 | 21 | 15 | 2024-10-17 | 2024-10-17 | 1 | 1 | 825 | 589 | 22 | 16 | 847 | 605 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 237.1 | 237.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 358 | 257 | No | 2024-05-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2025-04-24 | IOU Designed & Installed | N/A | Yes | 183 | 3099.85 | 525.12 | Unknown | 660.11 | 25.46 | 1889.16 | 7962 | 2044.62 | 3099.85 | -1055.23 | Yes | N/A | N/A | 2024-05-23 | 2024-11-22 | 184 | 132 | 2024-11-22 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2025-04-24 | 315 | 225 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 499 | 357 | 2 | 2 | 501 | 359 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | Unknown | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 1234.51 | -24.78 | Unknown | Unknown | Unknown | 1259.29 | 3981 | 1609.49 | 1234.51 | 374.98 | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-12 | 20 | 14 | 2024-10-23 | 2024-11-13 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-25 | 13 | 9 | 2024-11-25 | 2024-11-25 | 1 | 1 | 23 | 17 | 35 | 25 | 58 | 42 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -423 | -304 | No | 2024-07-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-22 | 2025-02-28 | IOU Designed & Installed | N/A | Yes | 181 | 1249.64 | Unknown | Unknown | Unknown | 14.9 | 1234.74 | 3981 | 989.29 | 1249.64 | -260.35 | Yes | N/A | N/A | 2024-07-09 | 2024-12-20 | 165 | 119 | 2024-12-20 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2025-02-28 | 194 | 140 | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-28 | 2025-03-24 | 25 | 17 | 2025-03-24 | 2025-03-24 | 1 | 1 | 359 | 259 | 26 | 18 | 385 | 277 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 32.23 | Unknown | Unknown | Unknown | Unknown | 32.23 | 3981 | 1661.87 | 32.23 | 1629.64 | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-17 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-02-11 | 26 | 18 | 2025-02-11 | 2025-02-11 | 1 | 1 | 12 | 10 | 28 | 20 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-09 | -611 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-06-07 | IOU Designed & Installed | N/A | No | N/A | 3236.45 | 1168.58 | Unknown | 380.32 | 14.11 | 1673.44 | 3981 | 154.79 | 3236.45 | -3081.66 | Yes | N/A | N/A | 2023-03-02 | 2023-04-07 | 37 | 27 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-06-07 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-07-07 | 31 | 23 | 2023-07-07 | 2023-07-07 | 1 | 1 | 99 | 71 | 32 | 24 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 425.79 | -19.56 | Unknown | Unknown | Unknown | 445.35 | 3981 | 1596.26 | 425.79 | 1170.47 | Yes | N/A | N/A | 2024-05-02 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-20 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-09 | 20 | 14 | 2024-07-09 | 2024-07-09 | 1 | 1 | 50 | 36 | 21 | 15 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-06 | 2024-07-06 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 11.48 | Unknown | Unknown | Unknown | Unknown | 11.48 | Unknown | 186.09 | 11.48 | 174.61 | Yes | N/A | N/A | 2024-07-06 | 2024-07-24 | 19 | 13 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-22 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-25 | 35 | 25 | 2024-09-25 | 2024-09-25 | 1 | 1 | 49 | 35 | 37 | 27 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.67 | -27.24 | Unknown | Unknown | Unknown | 57.91 | 3981 | 977.22 | 30.67 | 946.55 | Yes | N/A | N/A | 2024-04-01 | 2024-04-11 | 11 | 9 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-02-08 | Unknown | Unknown | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | 643.05 | 643.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-13 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 4266.14 | 984.36 | Unknown | 1503.06 | Unknown | 1778.72 | Unknown | 714.45 | 4266.14 | -3551.69 | Yes | N/A | N/A | 2023-12-12 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2023-12-12 | 15 | 11 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-19 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | 2023-12-20 | 2 | 2 | 7 | 5 | 18 | 14 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-23 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 52.92 | -17.62 | Unknown | Unknown | 52.21 | 18.33 | 3981 | 840.4 | 52.92 | 787.48 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-10-16 | 193 | 137 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-07-26 | 285 | 205 | 2024-07-26 | 2023-11-22 | Unknown | Unknown | 194 | 138 | 285 | 205 | 479 | 343 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-22 | 323 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | Unknown | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 569.92 | -34.02 | Unknown | Unknown | Unknown | 603.94 | 3885 | 625.02 | 569.92 | 55.1 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-11-16 | 282 | 202 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-11 | 26 | 18 | 2023-12-11 | 2023-12-11 | 1 | 1 | 283 | 203 | 27 | 19 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 183.1 | 183.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -164 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 76.06 | Unknown | Unknown | Unknown | Unknown | 76.06 | 3981 | 2032.17 | 76.06 | 1956.11 | Yes | N/A | N/A | 2023-12-07 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2024-01-23 | 120 | 86 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 0 | 0 | 121 | 87 | 121 | 87 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | 399 | 286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-22 | 2024-09-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 46340.92 | 11338.76 | Unknown | Unknown | 581.53 | 34420.63 | 44897 | 30951.71 | 46340.92 | -15389.21 | Yes | N/A | N/A | 2023-01-25 | 2023-03-30 | 65 | 47 | 2023-03-30 | 2023-04-25 | 27 | 19 | 2023-04-11 | 2023-09-11 | 86 | 62 | 2023-04-13 | 2024-01-02 | 49 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2024-08-06 | 307 | 219 | 2024-09-09 | 2024-12-06 | 89 | 65 | 2024-12-06 | 2024-12-06 | 1 | 1 | 151 | 109 | 473 | 338 | 624 | 447 | Steps 2,3,5,6,7 | 165 | 117 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | 193 | 138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -191.17 | Unknown | Unknown | Unknown | 59.28 | -250.45 | 3981 | 754.76 | -191.17 | 945.93 | Yes | N/A | N/A | 2023-06-02 | 2023-07-22 | 51 | 36 | 2023-07-22 | 2023-07-22 | 1 | 0 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-01 | 1 | 1 | 51 | 36 | 2 | 1 | 53 | 37 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 147 | 147 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | -463 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 0.27 | -3.93 | Unknown | Unknown | Unknown | 4.2 | 3885 | 627.38 | 0.27 | 627.11 | Yes | N/A | N/A | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-12-11 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-04 | 25 | 19 | 2024-01-04 | 2023-12-13 | Unknown | Unknown | 65 | 47 | 26 | 20 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -536 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-16 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 1454.9 | Unknown | Unknown | Unknown | 17.17 | 1437.73 | 3981 | 984.62 | 1454.9 | -470.28 | Yes | N/A | N/A | 2024-09-27 | 2024-10-11 | 15 | 11 | 2024-10-11 | 2024-10-21 | 11 | 7 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2025-02-27 | 130 | 94 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-02-27 | 2025-03-18 | 20 | 14 | 2025-03-18 | 2025-03-18 | 1 | 1 | 145 | 105 | 32 | 22 | 177 | 127 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 29.05 | 29.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | 56 | 41 | No | 2023-11-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2024-10-28 | 2025-06-25 | IOU Designed & Installed | N/A | Yes | 563 | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 858.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2025-05-29 | 564 | 404 | 2025-05-29 | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2025-05-28 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-26 | 2 | 2 | 2025-06-26 | 2025-06-26 | 1 | 1 | 806 | 578 | 3 | 3 | 809 | 581 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-05 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 1808.97 | Unknown | Unknown | Unknown | Unknown | 1808.97 | 3981 | 325.03 | 1808.97 | -1483.94 | Yes | N/A | N/A | 2024-12-03 | 2025-01-22 | 51 | 37 | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-10 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-26 | 17 | 13 | 2025-02-26 | 2025-02-21 | Unknown | Unknown | 71 | 51 | 18 | 14 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -661 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 591.19 | 181.27 | Unknown | Unknown | Unknown | 409.92 | 3981 | 1443.92 | 591.19 | 852.73 | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-24 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-29 | 6 | 4 | 2024-07-29 | 2024-07-29 | 1 | 1 | 36 | 26 | 8 | 6 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 157 | 157 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | -28 | -21 | No | 2023-08-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | Yes | 187 | 387.29 | -12.84 | Unknown | Unknown | Unknown | 400.13 | 3981 | 2269.19 | 387.29 | 1881.9 | Yes | N/A | N/A | 2023-08-18 | 2024-02-21 | 188 | 134 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-04-18 | 1 | 1 | 188 | 134 | 1 | 1 | 189 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -572 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 1636 | -31.94 | Unknown | Unknown | Unknown | 1667.94 | 3981 | 1641.81 | 1636 | 5.81 | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | Unknown | Unknown | Unknown | 2024-10-30 | 2025-01-29 | 92 | 66 | 2024-10-29 | 2025-01-31 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-03-17 | 46 | 32 | 2025-03-17 | 2025-03-17 | 1 | 1 | 96 | 70 | 140 | 100 | 236 | 170 | Steps 2,3,5,6,7 | 92 | 66 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 1730.44 | 2938.07 | Unknown | 559.88 | -3198 | 1430.49 | Unknown | 3198.24 | 1730.44 | 1467.8 | Yes | N/A | N/A | 2023-07-06 | 2023-07-06 | 1 | 1 | 2023-07-06 | 2023-07-26 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-07-28 | 3 | 3 | 2023-07-28 | 2023-07-28 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-03 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | 908.15 | Unknown | Unknown | Unknown | Unknown | 908.15 | 3981 | 918.72 | 908.15 | 10.57 | Yes | N/A | N/A | 2024-12-16 | 2025-01-03 | 19 | 15 | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-04-14 | 102 | 72 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-04-14 | 2025-05-22 | 39 | 29 | 2025-05-22 | 2025-05-22 | 1 | 1 | 121 | 87 | 41 | 31 | 162 | 118 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | -211 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-06-09 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | -811.81 | -13.8 | Unknown | Unknown | -1086 | 287.99 | 7710.44 | 2042.13 | -811.81 | 2853.94 | Yes | N/A | N/A | 2023-05-17 | 2023-06-09 | 24 | 18 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | 2023-07-28 | 2023-08-08 | 12 | 8 | 2023-08-08 | 2023-08-04 | Unknown | Unknown | 24 | 18 | 12 | 8 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 10.35 | 10.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -144 | -104 | No | 2024-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-08-01 | IOU Designed & Installed | N/A | Yes | 97 | 17.8 | Unknown | Unknown | Unknown | Unknown | 17.8 | Unknown | 1148.84 | 17.8 | 1131.04 | Yes | N/A | N/A | 2024-03-21 | 2024-06-26 | 98 | 70 | 2024-06-26 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-08-01 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-26 | 26 | 18 | 2024-08-26 | 2024-09-10 | 16 | 12 | 232 | 166 | 42 | 30 | 274 | 196 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | SD 1189-G3 PS. Montril (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-15 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2025-05-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 33078.48 | 9480.24 | Unknown | Unknown | Unknown | 23598.24 | 77019 | Not available | 33078.48 | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-03-21 | 1 | 1 | 2024-03-21 | 2024-03-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2025-07-15 | 475 | 339 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 476 | 340 | 9 | 7 | 485 | 347 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -529 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 12.06 | -10.68 | Unknown | Unknown | Unknown | 22.74 | Unknown | 1016.3 | 12.06 | 1004.24 | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-06-27 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-08 | 12 | 8 | 2024-07-08 | 2024-07-08 | 1 | 1 | 60 | 44 | 14 | 10 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132.1 | 132.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 1506.35 | 224.88 | Unknown | Unknown | Unknown | 1281.47 | 7962 | 1009.05 | 1506.35 | -497.3 | Yes | N/A | N/A | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-11-01 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-28 | 28 | 20 | 2023-11-28 | 2023-11-28 | 1 | 1 | 43 | 31 | 30 | 22 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -285 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 4682.28 | 825.68 | Unknown | 382.41 | 1.9 | 3472.29 | 3981 | 2379.92 | 4682.28 | -2302.36 | Yes | N/A | N/A | 2024-07-24 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-08-19 | 41 | 29 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-20 | 33 | 25 | Unknown | 2024-08-30 | Unknown | Unknown | 2024-09-20 | 2024-09-23 | 4 | 2 | 2024-09-23 | 2024-09-23 | 1 | 1 | 33 | 25 | 46 | 32 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-07 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2671.76 | -37.21 | Unknown | Unknown | 21.41 | 2687.56 | 3981 | 1533.58 | 2671.76 | -1138.18 | Yes | N/A | N/A | 2023-04-03 | 2023-04-06 | 4 | 4 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-04-19 | 13 | 9 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1 | 1 | 4 | 4 | 14 | 10 | 18 | 14 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 422 | 303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-18 | 2022-03-18 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -19928.7 | 9677.47 | Unknown | Unknown | -43961 | 14354.83 | 0 | 47499.62 | -19928.7 | 67428.32 | Yes | N/A | N/A | 2022-03-18 | 2023-06-25 | 465 | 331 | 2023-06-25 | 2024-09-10 | 444 | 317 | 2023-08-25 | 2023-10-12 | 49 | 35 | 2024-09-04 | 2025-01-09 | -99 | -75 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | 2025-06-27 | 2025-06-27 | 1 | 1 | 514 | 366 | 346 | 243 | 860 | 609 | Steps 2,3,5,6,7 | 382 | 272 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | -557 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 7.39 | -5.71 | Unknown | Unknown | Unknown | 13.1 | 3241 | 938.68 | 7.39 | 931.29 | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-06-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-07-11 | 39 | 29 | 2024-07-11 | 2024-07-11 | 1 | 1 | 37 | 27 | 41 | 31 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | 2024-01-22 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 4280.92 | -3.42 | Unknown | Unknown | 5.26 | 4279.08 | Unknown | 904.29 | 4280.92 | -3376.63 | Yes | N/A | N/A | 2023-12-29 | 2024-01-03 | 6 | 4 | 2024-01-03 | 2024-07-19 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-08-23 | 213 | 153 | 2024-08-23 | 2024-08-23 | 1 | 1 | 6 | 4 | 413 | 297 | 419 | 301 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-29 | 309 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 1517.31 | 367.95 | Unknown | Unknown | Unknown | 1149.36 | 3981 | 932.55 | 1517.31 | -584.76 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-08-01 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-04 | 4 | 4 | 2023-08-04 | 2023-08-04 | 1 | 1 | 154 | 110 | 5 | 5 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -278 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-07 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 17.57 | -15.56 | Unknown | Unknown | Unknown | 33.13 | Unknown | 2718.16 | 17.57 | 2700.59 | Yes | N/A | N/A | 2024-05-06 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-07 | 49 | 35 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-29 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-14 | 17 | 13 | 2024-06-14 | 2024-06-14 | 1 | 1 | 23 | 17 | 67 | 49 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-25 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 17156.32 | -5.11 | Unknown | Unknown | -1307 | 18468.43 | Unknown | 1307.02 | 17156.32 | -15849.3 | Yes | N/A | N/A | 2023-10-18 | 2023-10-19 | 2 | 2 | 2023-10-19 | 2023-11-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | 2024-01-16 | 2024-02-27 | 43 | 31 | 2024-02-27 | 2024-02-27 | 1 | 1 | 2 | 2 | 67 | 49 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 1124544 | 1124544 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-23 | -409 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-05-24 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 5150.86 | 1489.13 | Unknown | 318.72 | 18.08 | 3324.93 | 3981 | 2545.94 | 5150.86 | -2604.92 | Yes | N/A | N/A | 2023-03-09 | 2023-05-10 | 63 | 45 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-12-18 | 180 | 128 | Unknown | 2024-01-03 | Unknown | Unknown | 2023-12-18 | 2024-01-11 | 25 | 19 | 2024-01-11 | 2024-01-11 | 1 | 1 | 243 | 173 | 26 | 20 | 269 | 193 | Steps 2,3,5,6,7 | 16 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-06 | 1567 | 1120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 19086.19 | Unknown | Unknown | Unknown | Unknown | 19086.19 | Unknown | 6520.42 | 19086.19 | -12565.77 | Yes | N/A | N/A | 2025-02-06 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-10 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-20 | 3 | 3 | 2025-02-20 | 2025-02-20 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 80.1 | 80.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-20 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | -1209.01 | Unknown | Unknown | Unknown | -1233 | 23.99 | Unknown | 980.39 | -1209.01 | 2189.4 | Yes | N/A | N/A | 2024-11-18 | 2024-11-20 | 3 | 3 | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-12-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-16 | 5 | 3 | 2024-12-16 | 2025-01-16 | 32 | 24 | 28 | 22 | 38 | 28 | 66 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | -6.11 | -4.43 | Unknown | Unknown | Unknown | -1.68 | Unknown | 761.29 | -6.11 | 767.4 | Yes | N/A | N/A | 2023-07-05 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-07-05 | 64 | 46 | 2023-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2023-07-19 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-08-03 | 16 | 12 | 2023-08-03 | 2023-08-03 | 1 | 1 | 15 | 11 | 81 | 59 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | -230 | -165 | No | 2023-10-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2023-12-04 | IOU Designed & Installed | N/A | Yes | 453 | 864.59 | -16.58 | Unknown | Unknown | 3.51 | 877.66 | Unknown | 840.7 | 864.59 | -23.89 | Yes | N/A | N/A | 2023-10-27 | 2025-01-22 | 454 | 324 | 2025-01-22 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-02 | 4 | 4 | 2023-10-27 | 2023-12-04 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2025-01-27 | 421 | 301 | 2025-01-27 | 2025-01-27 | 1 | 1 | 493 | 351 | 426 | 306 | 919 | 657 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -354 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 385.54 | Unknown | Unknown | Unknown | 17.51 | 368.03 | 0 | 1174.46 | 385.54 | 788.92 | Yes | N/A | N/A | 2024-10-07 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-10-15 | 176 | 126 | 2024-10-15 | 2025-04-23 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2025-01-30 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-04-29 | 90 | 64 | 2025-04-29 | 2025-04-29 | 1 | 1 | 300 | 216 | 267 | 191 | 567 | 407 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | 80 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -940.94 | 2017.93 | Unknown | 253.76 | -3986 | 773.37 | 0 | 3986.03 | -940.94 | 4926.97 | Yes | N/A | N/A | 2023-05-12 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-06-02 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -715 | -512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 7.77 | Unknown | Unknown | Unknown | Unknown | 7.77 | Unknown | 1560.9 | 7.77 | 1553.13 | Yes | N/A | N/A | 2024-11-19 | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-19 | 2 | 2 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-11-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-05 | 10 | 8 | 2024-12-05 | 2024-11-27 | Unknown | Unknown | 8 | 6 | 12 | 10 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 320.2 | -2.73 | Unknown | Unknown | 23.55 | 299.38 | Unknown | 1019.95 | 320.2 | 699.75 | Yes | N/A | N/A | 2024-01-08 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2024-01-12 | 100 | 72 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-05-28 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-03 | 7 | 5 | 2024-06-03 | 2024-06-03 | 1 | 1 | 138 | 98 | 108 | 78 | 246 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -540 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2025-01-31 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 196.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2025-01-14 | 40 | 28 | 2025-01-14 | 2025-01-31 | 18 | 14 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-05-05 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-30 | 26 | 20 | 2025-05-30 | 2025-05-30 | 1 | 1 | 135 | 95 | 45 | 35 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -668 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 24.16 | Unknown | Unknown | Unknown | Unknown | 24.16 | 3981 | 1561.26 | 24.16 | 1537.1 | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-21 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-19 | 29 | 21 | 2024-12-19 | 2024-12-19 | 1 | 1 | 19 | 15 | 31 | 23 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 3004.05 | 3004.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-06-21 | -478 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 4.15 | -5.19 | Unknown | Unknown | Unknown | 9.34 | Unknown | 794.97 | 4.15 | 790.82 | Yes | N/A | N/A | 2023-10-06 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2023-11-08 | 97 | 69 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-19 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-02-29 | 73 | 53 | 2024-02-29 | 2024-02-29 | 1 | 1 | 42 | 30 | 171 | 123 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2024-03-21 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 2505.75 | Unknown | Unknown | Unknown | Unknown | 2505.75 | Unknown | 891.41 | 2505.75 | -1614.34 | Yes | N/A | N/A | 2022-08-11 | 2024-03-18 | 586 | 418 | 2024-03-18 | 2024-06-04 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-21 | 15 | 11 | 2024-06-21 | 2024-06-21 | 1 | 1 | 586 | 418 | 95 | 69 | 681 | 487 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 861 | 616 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 61900.7 | Unknown | Unknown | Unknown | 211.39 | 61689.31 | 621970 | 30234.92 | 61900.7 | -31665.78 | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-10-06 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2024-12-10 | 432 | 308 | Unknown | 2024-10-23 | Unknown | Unknown | 2024-12-19 | 2025-02-06 | 50 | 36 | 2025-02-06 | 2025-01-10 | Unknown | Unknown | 433 | 309 | 135 | 97 | 568 | 406 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -446 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 409.91 | -12.06 | Unknown | Unknown | 11.67 | 410.3 | 3981 | 534.97 | 409.91 | 125.06 | Yes | N/A | N/A | 2023-01-05 | 2023-03-01 | 56 | 40 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 56 | 40 | 1 | 1 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-28 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 1611.77 | 435.63 | Unknown | 170.7 | Unknown | 1005.44 | 3981 | 951.6 | 1611.77 | -660.17 | Yes | N/A | N/A | 2023-12-21 | 2023-12-28 | 8 | 6 | 2023-12-28 | 2023-12-28 | 1 | 1 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-01-31 | 7 | 5 | 2024-01-31 | 2024-01-31 | 1 | 1 | 37 | 27 | 9 | 7 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -507 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 283.79 | Unknown | Unknown | Unknown | -1070.02 | 1353.81 | Unknown | 1072.15 | 283.79 | 788.36 | Yes | N/A | N/A | 2024-04-30 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-07-16 | 140 | 100 | 2024-07-16 | 2024-08-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-24 | 37 | 27 | Unknown | 2025-03-21 | Unknown | Unknown | 2024-09-24 | 2024-10-02 | 9 | 7 | 2024-10-02 | 2024-10-02 | 1 | 1 | 72 | 52 | 150 | 108 | 222 | 160 | Steps 2,3,5,6,7 | 178 | 128 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | -30 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1208.48 | 509.56 | Unknown | 116.32 | -3155 | 1320.64 | Unknown | 3155.38 | -1208.48 | 4363.86 | Yes | N/A | N/A | 2023-05-04 | 2023-05-04 | 1 | 1 | 2023-05-04 | Unknown | Unknown | Unknown | 2023-05-12 | 2023-05-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-26 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 13.18 | Unknown | Unknown | Unknown | Unknown | 13.18 | Unknown | 186.52 | 13.18 | 173.34 | Yes | N/A | N/A | 2024-07-18 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-08-06 | 68 | 48 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-22 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-12 | 22 | 16 | 2024-09-12 | 2024-09-12 | 1 | 1 | 17 | 13 | 91 | 65 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 9225.77 | 2390.61 | Unknown | Unknown | Unknown | 6835.16 | 3981 | 2562.25 | 9225.77 | -6663.52 | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-13 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-05-29 | 78 | 56 | 2025-05-29 | 2025-05-29 | 1 | 1 | 3 | 3 | 80 | 58 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 20.73 | Unknown | Unknown | Unknown | Unknown | 20.73 | 3981 | 1434.75 | 20.73 | 1414.02 | Yes | N/A | N/A | 2024-06-17 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-06-17 | 42 | 30 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-24 | 15 | 11 | 2024-07-24 | 2024-08-12 | 20 | 14 | 24 | 18 | 77 | 55 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OC 1086-F2 Cypress pt PH1 WO1 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 2609.9 | -71.89 | Unknown | Unknown | Unknown | 2681.79 | 3981 | Not available | 2609.9 | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-05-30 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2025-04-18 | 324 | 232 | Unknown | 2025-02-28 | Unknown | Unknown | 2024-09-26 | 2024-09-30 | 5 | 3 | 2024-09-30 | 2024-09-30 | 1 | 1 | 324 | 232 | 72 | 52 | 396 | 284 | Steps 2,3,5,6,7 | 155 | 111 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 612.05 | 612.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | 278 | 200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 14.33 | -18.12 | Unknown | Unknown | Unknown | 32.45 | 3981 | 833.52 | 14.33 | 819.19 | Yes | N/A | N/A | 2023-11-28 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-11-28 | 34 | 24 | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-01-04 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-12 | 9 | 7 | 2024-01-12 | 2024-07-27 | 198 | 141 | 38 | 28 | 241 | 172 | 279 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 144 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | 414.28 | 126.23 | Unknown | 79.86 | Unknown | 208.19 | 3981 | 1582.75 | 414.28 | 1168.47 | Yes | N/A | N/A | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-22 | 2 | 2 | 2023-11-22 | 2023-11-22 | 1 | 1 | 3 | 3 | 4 | 4 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | -453 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 610.65 | -17.73 | Unknown | Unknown | Unknown | 628.38 | 3981 | 808.11 | 610.65 | 197.46 | Yes | N/A | N/A | 2022-11-28 | 2023-04-14 | 138 | 100 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-05-16 | 26 | 18 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 138 | 100 | 27 | 19 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | -685 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 127.58 | -0.94 | Unknown | Unknown | Unknown | 128.52 | 3981 | 2805.5 | 127.58 | 2677.92 | Yes | N/A | N/A | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-15 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-13 | 30 | 22 | 2025-06-13 | 2025-06-13 | 1 | 1 | 17 | 13 | 32 | 24 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 130 | 93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-21 | 2023-03-27 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 510.31 | -12.06 | Unknown | Unknown | Unknown | 522.37 | 3885 | 773.48 | 510.31 | 263.17 | Yes | N/A | N/A | 2022-07-21 | 2023-03-27 | 250 | 178 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2023-08-10 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-09-18 | 40 | 28 | 2023-09-18 | 2023-09-18 | 1 | 1 | 387 | 277 | 41 | 29 | 428 | 306 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 36.75 | 36.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-31 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 2033.73 | 480.61 | Unknown | Unknown | Unknown | 1553.12 | 3981 | 1645.82 | 2033.73 | -387.91 | Yes | N/A | N/A | 2024-05-29 | 2024-05-30 | 2 | 2 | 2024-05-30 | 2024-05-31 | 2 | 2 | 2024-05-31 | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-10 | 11 | 7 | 2024-05-31 | 2024-06-25 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-18 | 24 | 18 | 2024-07-18 | 2024-07-18 | 1 | 1 | 28 | 20 | 38 | 28 | 66 | 48 | Steps 2,3,5,6,7 | 10 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | -452 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 3.86 | Unknown | Unknown | Unknown | Unknown | 3.86 | Unknown | 384.31 | 3.86 | 380.45 | Yes | N/A | N/A | 2024-04-05 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | 2024-04-05 | 8 | 6 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-12 | 3 | 3 | 2024-09-12 | 2024-09-12 | 1 | 1 | 5 | 3 | 12 | 10 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-10-24 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 506.83 | -10.75 | Unknown | Unknown | 15.97 | 501.61 | 3885 | 418.8 | 506.83 | -88.03 | Yes | N/A | N/A | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | 2023-10-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-03-15 | 71 | 51 | 2024-03-15 | 2024-03-15 | 1 | 1 | 1 | 1 | 74 | 54 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Escondido | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 4667.32 | Unknown | Unknown | Unknown | 926 | 3741.32 | 5913 | 3007.17 | 4667.32 | -1660.15 | Yes | N/A | N/A | 2023-05-23 | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2024-03-08 | 296 | 212 | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-08 | 2024-03-12 | 5 | 3 | 2024-03-19 | Unknown | Unknown | Unknown | 2024-03-19 | 2024-06-04 | 78 | 56 | 2024-06-06 | 2024-06-14 | 9 | 7 | 2024-06-14 | 2024-06-14 | 1 | 1 | 1 | 1 | 389 | 279 | 390 | 280 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DESCANSO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 1769.23 | 894.29 | Unknown | 114.9 | -1134.99 | 1895.03 | 7531.04 | 1847.5 | 1769.23 | 78.27 | Yes | N/A | N/A | 2023-10-30 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2023-10-31 | 5 | 3 | 2023-10-31 | 2023-11-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-12-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-26 | 39 | 29 | 2024-01-26 | 2024-01-26 | 1 | 1 | 53 | 39 | 45 | 33 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | -123 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.17 | -9.35 | Unknown | Unknown | Unknown | 6.18 | Unknown | 776.51 | -3.17 | 779.68 | Yes | N/A | N/A | 2023-02-24 | 2023-03-17 | 22 | 16 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -103 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 697.52 | -14.02 | Unknown | Unknown | 13.32 | 698.22 | 3981 | 632.15 | 697.52 | -65.37 | Yes | N/A | N/A | 2023-06-07 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-06-28 | 90 | 64 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-11-27 | 153 | 109 | Unknown | 2023-11-13 | Unknown | Unknown | 2023-11-27 | 2023-12-04 | 8 | 6 | 2023-12-04 | 2023-12-04 | 1 | 1 | 153 | 109 | 99 | 71 | 252 | 180 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -482 | -345 | No | 2024-06-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-09-27 | IOU Designed & Installed | N/A | Yes | 128 | 42.74 | Unknown | Unknown | Unknown | 2.18 | 40.56 | 3981 | 1200.52 | 42.74 | 1157.78 | Yes | N/A | N/A | 2024-06-04 | 2024-10-10 | 129 | 93 | 2024-10-10 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-09-27 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-11-20 | 55 | 39 | 2024-11-20 | 2024-11-14 | Unknown | Unknown | 245 | 177 | 55 | 39 | 300 | 216 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-16 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 785.93 | -15.3 | Unknown | Unknown | Unknown | 801.23 | 7962 | 1498.1 | 785.93 | 712.17 | Yes | N/A | N/A | 2024-08-28 | 2024-09-11 | 15 | 11 | 2024-09-11 | 2024-09-16 | 6 | 4 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-12-20 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-08 | 20 | 14 | 2025-01-08 | 2024-12-20 | Unknown | Unknown | 111 | 81 | 26 | 18 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 66.75 | 66.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | 108 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-11-06 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 3637.44 | 600.93 | Unknown | 1220.22 | -1202 | 3018.29 | 3981 | 2379.22 | 3637.44 | -1258.22 | Yes | N/A | N/A | 2023-10-09 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2023-11-06 | 39 | 27 | 2023-11-06 | 2024-11-08 | 369 | 265 | 2023-11-08 | 2023-11-10 | 3 | 3 | 2024-11-08 | 2024-12-13 | 36 | 26 | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2024-12-18 | 6 | 4 | 2024-12-18 | 2024-12-18 | 1 | 1 | 405 | 291 | 49 | 35 | 454 | 326 | Steps 2,3,5,6,7 | 366 | 262 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 18 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-09 | 2024-03-16 | IOU Designed & Installed | N/A | No | N/A | 2933.11 | 766.02 | Unknown | 232.98 | Unknown | 1934.11 | 3981 | 1094.93 | 2933.11 | -1838.18 | Yes | N/A | N/A | 2023-08-08 | 2023-08-17 | 10 | 8 | 2023-08-17 | 2023-08-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-23 | 7 | 5 | 2023-08-30 | 2023-09-29 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-03-16 | 2024-03-19 | 4 | 2 | 2024-03-19 | 2024-03-19 | 1 | 1 | 41 | 31 | 26 | 18 | 67 | 49 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-07-11 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 15.89 | Unknown | Unknown | Unknown | Unknown | 15.89 | 3981 | 1519.31 | 15.89 | 1503.42 | Yes | N/A | N/A | 2024-06-19 | 2024-07-11 | 23 | 17 | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-10-01 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-10 | 10 | 8 | 2024-10-10 | 2024-10-10 | 1 | 1 | 106 | 76 | 12 | 10 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | -280 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-02-24 | IOU Designed & Installed | N/A | No | N/A | -2.13 | -6.27 | Unknown | Unknown | Unknown | 4.14 | Unknown | 871.76 | -2.13 | 873.89 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-02-24 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-03-17 | 22 | 16 | 2023-03-17 | 2023-03-17 | 1 | 1 | 23 | 17 | 23 | 17 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 420.81 | -8.16 | Unknown | Unknown | Unknown | 428.97 | 54899 | 81.53 | 420.81 | -339.28 | Yes | N/A | N/A | 2024-03-06 | 2024-08-08 | 156 | 112 | 2024-08-08 | 2024-08-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-06-19 | 45 | 33 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-21 | 1 | 1 | 156 | 112 | 59 | 43 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -252 | -181 | No | 2024-01-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | Yes | 318 | 7.53 | Unknown | Unknown | Unknown | Unknown | 7.53 | 3981 | 1921.6 | 7.53 | 1914.07 | Yes | N/A | N/A | 2024-01-12 | 2024-11-21 | 315 | 225 | 2024-11-21 | 2024-11-25 | 5 | 3 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-02-27 | Unknown | Unknown | 315 | 225 | 5 | 3 | 320 | 228 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-04-19 | IOU Designed & Installed | N/A | No | N/A | 204.96 | -29.82 | Unknown | Unknown | 19.37 | 215.41 | Unknown | 1844.15 | 204.96 | 1639.19 | Yes | N/A | N/A | 2023-03-06 | 2023-03-29 | 24 | 18 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-04-19 | 22 | 16 | Unknown | 2023-08-31 | Unknown | Unknown | 2023-04-19 | 2023-10-12 | 177 | 127 | 2023-10-12 | 2023-10-12 | 1 | 1 | 46 | 34 | 178 | 128 | 224 | 162 | Steps 2,3,5,6,7 | 134 | 96 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | 122 | 87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 996 | 281.44 | Unknown | 51.83 | 24.13 | 638.6 | 3981 | 2437.85 | 996 | 1441.85 | Yes | N/A | N/A | 2024-02-29 | 2024-08-21 | 175 | 125 | 2024-08-21 | 2024-08-22 | 2 | 2 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-06-02 | 285 | 203 | Unknown | 2025-05-28 | Unknown | Unknown | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | 2025-06-02 | 1 | 1 | 460 | 328 | 4 | 4 | 464 | 332 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -579 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 777.01 | -14.7 | Unknown | Unknown | Unknown | 791.71 | 3981 | 1916.43 | 777.01 | 1139.42 | Yes | N/A | N/A | 2024-08-08 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-08-08 | 30 | 22 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-10-15 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-28 | 14 | 10 | 2024-10-28 | 2024-10-28 | 1 | 1 | 69 | 49 | 45 | 33 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -555 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-06-16 | IOU Designed & Installed | N/A | No | N/A | -21.6 | -15.65 | Unknown | Unknown | Unknown | -5.95 | 3981 | 909.82 | -21.6 | 931.42 | Yes | N/A | N/A | 2023-03-23 | 2023-06-12 | 82 | 58 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-06-16 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-29 | 14 | 10 | 2023-06-29 | 2023-06-29 | 1 | 1 | 87 | 63 | 15 | 11 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | -97 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-31 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 86106.6 | 7277.96 | Unknown | Unknown | 92.68 | 78735.96 | 0 | 37166.42 | 86106.6 | -48940.18 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-12-11 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-02-14 | 51 | 37 | 2025-02-14 | 2025-02-14 | 1 | 1 | 1 | 1 | 78 | 58 | 79 | 59 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-31 | 597 | 428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-19 | 2022-09-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.57 | -7.61 | Unknown | Unknown | Unknown | 16.18 | 3885 | 642.83 | 8.57 | 634.26 | Yes | N/A | N/A | 2022-05-19 | 2023-08-11 | 450 | 322 | 2023-08-11 | 2023-09-21 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2024-04-03 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-06-19 | 1 | 1 | 646 | 462 | 43 | 31 | 689 | 493 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-20 | -444 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-24 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 829.21 | Unknown | Unknown | Unknown | Unknown | 829.21 | 3981 | 1105.77 | 829.21 | 276.56 | Yes | N/A | N/A | 2024-04-01 | 2024-04-24 | 24 | 18 | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-07-16 | 83 | 59 | Unknown | 2024-07-12 | Unknown | Unknown | 2024-07-16 | 2024-08-02 | 18 | 14 | 2024-08-02 | 2024-08-02 | 1 | 1 | 107 | 77 | 20 | 16 | 127 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -408 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 2601.27 | Unknown | Unknown | Unknown | Unknown | 2601.27 | Unknown | 1062.34 | 2601.27 | -1538.93 | Yes | N/A | N/A | 2023-10-13 | 2023-10-31 | 19 | 13 | 2023-10-31 | 2023-11-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-01-04 | 37 | 27 | 2024-01-04 | 2024-01-04 | 1 | 1 | 19 | 13 | 41 | 31 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | Unknown | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 49.28 | Unknown | Unknown | Unknown | Unknown | 49.28 | 3981 | 1483.79 | 49.28 | 1434.51 | Yes | N/A | N/A | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-30 | 31 | 23 | 2024-07-30 | 2024-09-10 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-19 | 10 | 8 | 2024-09-19 | 2024-09-19 | 1 | 1 | 44 | 32 | 43 | 33 | 87 | 65 | Steps 2,3,5,6,7 | 31 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 896.5 | 896.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -444 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 1984.45 | -8.72 | Unknown | Unknown | 61.76 | 1931.41 | 3981 | 1331.28 | 1984.45 | -653.17 | Yes | N/A | N/A | 2023-12-14 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2024-02-16 | 143 | 103 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-06-28 | 134 | 96 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-06-28 | 2024-07-02 | 5 | 3 | 2024-07-02 | 2024-07-01 | Unknown | Unknown | 134 | 96 | 148 | 106 | 282 | 202 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -510 | -365 | No | 2024-05-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-06-06 | 2024-10-22 | IOU Designed & Installed | N/A | Yes | 112 | 8828.77 | 2284.27 | Unknown | 332.87 | Unknown | 6211.63 | 3981 | 1551.16 | 8828.77 | -7277.61 | Yes | N/A | N/A | 2024-05-30 | 2024-09-19 | 113 | 81 | 2024-09-19 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-10-22 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-21 | 31 | 23 | 2024-11-21 | 2024-11-21 | 1 | 1 | 252 | 180 | 32 | 24 | 284 | 204 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -619 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-08-02 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 258.01 | -4.69 | Unknown | Unknown | Unknown | 262.7 | Unknown | 1504.62 | 258.01 | 1246.61 | Yes | N/A | N/A | 2024-07-09 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-08-02 | 61 | 45 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-09-09 | 35 | 25 | 2024-09-09 | 2024-09-09 | 1 | 1 | 5 | 3 | 97 | 71 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-25 | 3 | 3 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-21 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-19 | 30 | 22 | 2024-11-19 | 2024-11-19 | 1 | 1 | 30 | 22 | 32 | 24 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 1264.88 | 800.69 | Unknown | Unknown | Unknown | 464.19 | Unknown | 496.37 | 1264.88 | -768.51 | Yes | N/A | N/A | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-02 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-11-29 | 59 | 43 | 2023-11-29 | 2023-11-29 | 1 | 1 | 44 | 32 | 61 | 45 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | 41 | 30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 10958.58 | -5.94 | Unknown | Unknown | 392 | 10572.52 | 3981 | 603.53 | 10958.58 | -10355.05 | Yes | N/A | N/A | 2023-04-11 | 2023-05-19 | 39 | 29 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2025-03-14 | 522 | 374 | 2025-03-14 | 2025-03-14 | 1 | 1 | 39 | 29 | 523 | 375 | 562 | 404 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-05 | 2023-08-20 | 2023-08-21 | IOU Designed & Installed | N/A | No | N/A | -3.64 | -7.09 | Unknown | Unknown | Unknown | 3.45 | 3241 | 823.31 | -3.64 | 826.95 | Yes | N/A | N/A | 2023-08-05 | 2023-08-20 | 16 | 10 | 2023-08-20 | 2023-08-20 | 1 | 0 | 2023-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-20 | 2023-08-21 | 2 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-03 | 44 | 32 | 2023-10-03 | 2023-10-03 | 1 | 1 | 18 | 11 | 46 | 33 | 64 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | 180 | 129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2772.19 | -54.02 | Unknown | Unknown | Unknown | 2826.21 | 7962 | 1051.53 | 2772.19 | -1720.66 | Yes | N/A | N/A | 2023-06-28 | 2024-03-07 | 254 | 182 | 2024-03-07 | 2024-03-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-05 | 6 | 4 | 2024-03-19 | 2024-06-18 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-09-30 | 60 | 42 | 346 | 248 | 79 | 55 | 425 | 303 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 7.47 | Unknown | Unknown | Unknown | Unknown | 7.47 | 3981 | 197.01 | 7.47 | 189.54 | Yes | N/A | N/A | 2024-08-29 | 2024-10-03 | 36 | 26 | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-11 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-06 | 27 | 19 | 2024-11-06 | 2024-11-06 | 1 | 1 | 45 | 33 | 29 | 21 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-08-14 | 1674 | 1197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.36 | -14.96 | Unknown | Unknown | Unknown | 27.32 | Unknown | 466.94 | 12.36 | 454.58 | Yes | N/A | N/A | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | 2024-01-02 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-02-20 | 27 | 19 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 190 | 136 | 191 | 137 | Steps 2,3,5,6,7 | 49 | 35 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 24.5 | 24.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | -632 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-26 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 2087.07 | 533.76 | Unknown | Unknown | Unknown | 1553.31 | Unknown | 1880.16 | 2087.07 | -206.91 | Yes | N/A | N/A | 2025-03-21 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | 2025-03-26 | 14 | 10 | 2025-03-26 | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-22 | 27 | 19 | 2025-03-27 | 2025-05-22 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-05 | 15 | 11 | 2025-06-05 | 2025-06-05 | 1 | 1 | 57 | 41 | 57 | 41 | 114 | 82 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -430 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-01 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 1343.43 | -3.45 | Unknown | Unknown | Unknown | 1346.88 | Unknown | 341.38 | 1343.43 | -1002.05 | Yes | N/A | N/A | 2024-04-03 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-05-01 | 69 | 49 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-12-13 | 177 | 127 | 2024-12-13 | 2024-12-13 | 1 | 1 | 51 | 37 | 247 | 177 | 298 | 214 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | -620 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 1349.59 | Unknown | Unknown | Unknown | 13.28 | 1336.31 | 3981 | 1448.41 | 1349.59 | 98.82 | Yes | N/A | N/A | 2025-03-17 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-19 | 15 | 11 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-05-05 | 48 | 34 | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-05 | 2025-05-07 | 3 | 3 | 2025-05-07 | 2025-05-07 | 1 | 1 | 48 | 34 | 19 | 15 | 67 | 49 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | 200 | 143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | 788.8 | -15.42 | Unknown | Unknown | 143.05 | 661.17 | 3981 | 1056.55 | 788.8 | 267.75 | Yes | N/A | N/A | 2023-02-24 | 2023-03-10 | 15 | 11 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-08-04 | 148 | 106 | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-04 | 2024-11-12 | 467 | 333 | 2024-11-12 | 2024-11-12 | 1 | 1 | 163 | 117 | 468 | 334 | 631 | 451 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 9521.65 | Unknown | Unknown | Unknown | -495.58 | 10017.23 | Unknown | 511.8 | 9521.65 | -9009.85 | Yes | N/A | N/A | 2023-03-09 | 2023-03-24 | 16 | 12 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-10-13 | 51 | 37 | Unknown | 2023-10-12 | Unknown | Unknown | 2023-10-13 | 2023-10-23 | 11 | 7 | 2023-10-23 | 2023-10-23 | 1 | 1 | 67 | 49 | 12 | 8 | 79 | 57 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 165 | 118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-19 | 2022-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -755.17 | 1202.94 | Unknown | 312.76 | -2749 | 478.13 | Unknown | 2749.08 | -755.17 | 3504.25 | Yes | N/A | N/A | 2022-04-19 | 2023-05-25 | 402 | 288 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-08-29 | Unknown | Unknown | 402 | 288 | 0 | 0 | 402 | 288 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -516 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-09-23 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | -1611.28 | Unknown | Unknown | Unknown | -1648 | 36.72 | Unknown | 1647.69 | -1611.28 | 3258.97 | Yes | N/A | N/A | 2024-08-01 | 2024-09-23 | 54 | 38 | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-09-30 | 8 | 6 | 2024-09-24 | 2024-10-04 | 11 | 9 | 2025-01-21 | 2025-01-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-20 | 24 | 18 | 2025-02-20 | 2025-02-11 | Unknown | Unknown | 70 | 50 | 36 | 28 | 106 | 78 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 1352.32 | Unknown | Unknown | Unknown | 32.61 | 1319.71 | 0 | 794.48 | 1352.32 | -557.84 | Yes | N/A | N/A | 2024-09-23 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-09-30 | 120 | 86 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-05-29 | 242 | 174 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | 2025-05-29 | 1 | 1 | 242 | 174 | 122 | 88 | 364 | 262 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 2434.47 | 743.71 | Unknown | 110.28 | 12.4 | 1568.08 | 3981 | 372.84 | 2434.47 | -2061.63 | Yes | N/A | N/A | 2023-05-22 | 2023-05-22 | 1 | 1 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2024-03-11 | 295 | 211 | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-11 | 2024-04-02 | 23 | 17 | 2024-04-02 | 2024-03-29 | Unknown | Unknown | 296 | 212 | 23 | 17 | 319 | 229 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-01 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 7.15 | -6.4 | Unknown | Unknown | Unknown | 13.55 | Unknown | 958.86 | 7.15 | 951.71 | Yes | N/A | N/A | 2024-01-19 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-02-01 | 80 | 58 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-28 | 28 | 20 | 2024-02-28 | 2024-02-28 | 1 | 1 | 1 | 1 | 109 | 79 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 644 | 461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-03-31 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 1796.32 | Unknown | Unknown | Unknown | 35.13 | 1761.19 | 294486 | 28616.6 | 1796.32 | 26820.28 | Yes | N/A | N/A | 2023-01-18 | 2023-03-02 | 44 | 32 | 2023-03-02 | 2023-06-22 | 113 | 81 | 2023-04-05 | 2024-01-07 | 209 | 149 | 2023-04-25 | 2025-05-02 | 91 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-05-16 | 184 | 132 | 2025-06-02 | 2025-06-18 | 17 | 13 | 2025-06-18 | 2025-06-17 | Unknown | Unknown | 253 | 181 | 405 | 293 | 658 | 474 | Steps 2,3,5,6,7 | 335 | 239 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4000 | 4000 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-14 | -898 | -643 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 381.95 | 237.76 | Unknown | Unknown | Unknown | 144.19 | Unknown | 95.13 | 381.95 | -286.82 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-05-30 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-05-31 | 2 | 2 | 2023-05-31 | 2023-05-31 | 1 | 1 | 70 | 50 | 3 | 3 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -540 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-13 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 29.04 | -25.83 | Unknown | Unknown | Unknown | 54.87 | 3241 | 882.23 | 29.04 | 853.19 | Yes | N/A | N/A | 2024-02-05 | 2024-02-13 | 9 | 7 | 2024-02-13 | 2024-02-13 | 1 | 1 | 2024-02-13 | 2024-03-25 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-01 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-04-09 | 40 | 28 | 2024-04-09 | 2024-05-31 | 53 | 39 | 69 | 51 | 94 | 68 | 163 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 184.05 | 184.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-04-26 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 25717.36 | 10671.66 | Unknown | Unknown | -9244.32 | 24290.02 | 3981 | 13070.93 | 25717.36 | -12646.43 | Yes | N/A | N/A | 2023-01-31 | 2023-08-09 | 191 | 137 | 2023-08-09 | 2023-11-06 | 90 | 64 | 2023-08-22 | 2023-10-03 | 43 | 31 | 2023-11-06 | 2023-12-01 | 26 | 20 | 2023-11-06 | 2023-12-19 | 44 | 32 | 2023-11-27 | 2023-12-14 | 18 | 14 | 2023-12-18 | 2024-01-05 | 19 | 15 | 2024-01-05 | 2024-01-03 | Unknown | Unknown | 278 | 200 | 153 | 113 | 431 | 313 | Steps 2,3,5,6,7 | 123 | 89 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CAMPO | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -545 | -390 | No | 2025-02-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | 2025-06-13 | IOU Designed & Installed | N/A | Yes | 6 | 3126.03 | 842.36 | Unknown | Unknown | Unknown | 2283.67 | 3241 | 2419.64 | 3126.03 | -706.39 | Yes | N/A | N/A | 2025-02-07 | 2025-02-13 | 7 | 5 | 2025-02-13 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-02-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-06-13 | 123 | 89 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | 2025-06-13 | 1 | 1 | 135 | 97 | 2 | 2 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 93.3 | -1.88 | Unknown | Unknown | Unknown | 95.18 | 3981 | 1798.21 | 93.3 | 1704.91 | Yes | N/A | N/A | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-21 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-03 | 14 | 10 | 2025-06-03 | 2025-06-03 | 1 | 1 | 36 | 26 | 16 | 12 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | -165 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -484.71 | 2092.02 | Unknown | 360.04 | -3782 | 845.23 | Unknown | 3782.39 | -484.71 | 4267.1 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | 2023-09-05 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 1 | 1 | 170 | 122 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-08-13 | 1687 | 1206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | -191.73 | -28.95 | Unknown | Unknown | -155 | -7.78 | Unknown | 1454.9 | -191.73 | 1646.63 | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-11-21 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2024-03-26 | 100 | 72 | 2024-03-26 | 2024-03-26 | 1 | 1 | 1 | 1 | 157 | 113 | 158 | 114 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-29 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 695.93 | -26.36 | Unknown | Unknown | -616 | 1338.29 | Unknown | 1880.65 | 695.93 | 1184.72 | Yes | N/A | N/A | 2025-01-22 | 2025-01-29 | 8 | 6 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-02-07 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-04-09 | 62 | 44 | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-09 | 2025-04-29 | 21 | 15 | 2025-04-29 | 2025-04-28 | Unknown | Unknown | 80 | 58 | 22 | 16 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-05 | 476 | 341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 203.2 | -3.58 | Unknown | Unknown | 17.08 | 189.7 | 3991 | 338.54 | 203.2 | 135.34 | Yes | N/A | N/A | 2022-04-26 | 2023-02-03 | 284 | 204 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-04-25 | Unknown | Unknown | 284 | 204 | 0 | 0 | 284 | 204 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-12-05 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | 217.68 | -54.34 | Unknown | Unknown | -1156 | 1428.02 | 3981 | 2099.11 | 217.68 | 1881.43 | Yes | N/A | N/A | 2023-10-27 | 2023-12-04 | 39 | 27 | 2023-12-04 | 2023-12-05 | 2 | 2 | 2023-12-05 | 2023-12-13 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-11 | 30 | 22 | Unknown | 2024-01-09 | Unknown | Unknown | 2024-01-11 | 2024-03-07 | 57 | 41 | 2024-03-07 | 2024-03-07 | 1 | 1 | 78 | 56 | 60 | 44 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56, VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 818.75 | -25.81 | Unknown | Unknown | Unknown | 844.56 | Unknown | 838.24 | 818.75 | 19.49 | Yes | N/A | N/A | 2024-02-20 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-02-26 | 32 | 22 | 2024-02-26 | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-11 | 18 | 12 | 2024-02-26 | 2024-03-13 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-03-21 | 9 | 7 | 2024-03-21 | 2024-03-21 | 1 | 1 | 17 | 13 | 60 | 42 | 77 | 55 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 4864.38 | 1808.96 | Unknown | 102.22 | -2352 | 5305.2 | Unknown | 2352.26 | 4864.38 | -2512.12 | Yes | N/A | N/A | 2024-11-19 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-19 | 7 | 5 | 2024-11-19 | 2025-01-21 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-14 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-23 | 41 | 29 | 2025-04-23 | 2025-04-23 | 1 | 1 | 116 | 84 | 49 | 35 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 28.35 | 28.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1352.94 | -8.54 | Unknown | Unknown | Unknown | 1361.48 | 7962 | 946.83 | 1352.94 | -406.11 | Yes | N/A | N/A | 2024-04-29 | 2024-04-30 | 2 | 2 | 2024-04-30 | 2024-05-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-31 | 32 | 24 | 2024-05-02 | 2025-01-31 | 275 | 197 | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 277 | 199 | 35 | 27 | 312 | 226 | Steps 2,3,5,6,7 | 29 | 21 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-05 | 318 | 227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 11.89 | -10.61 | Unknown | Unknown | Unknown | 22.5 | 3981 | 612.17 | 11.89 | 600.28 | Yes | N/A | N/A | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-03-14 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-20 | 7 | 5 | 2024-03-20 | 2024-03-18 | Unknown | Unknown | 65 | 47 | 8 | 6 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-01 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 473.12 | -9.51 | Unknown | Unknown | Unknown | 482.63 | Unknown | 1095.91 | 473.12 | 622.79 | Yes | N/A | N/A | 2025-04-28 | 2025-05-01 | 4 | 4 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-27 | 26 | 18 | 2025-05-27 | 2025-05-27 | 1 | 1 | 6 | 6 | 28 | 20 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-19 | -363 | -260 | No | 2022-10-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-10-05 | Unknown | IOU Designed & Installed | N/A | Yes | 215 | 903.74 | 405.12 | Unknown | 230.28 | Unknown | 268.34 | 3885 | 348.88 | 903.74 | -554.86 | Yes | N/A | N/A | 2022-09-27 | 2023-05-08 | 224 | 160 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 224 | 160 | 1 | 1 | 225 | 161 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67.79 | 67.79 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-01 | -615 | -440 | No | 2025-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-28 | 2025-04-15 | IOU Designed & Installed | N/A | Yes | 39 | 93.32 | -1.88 | Unknown | Unknown | Unknown | 95.2 | 3981 | 2095.33 | 93.32 | 2002.01 | Yes | N/A | N/A | 2025-03-21 | 2025-05-13 | 54 | 38 | 2025-05-13 | 2025-03-28 | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-15 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-05-28 | 44 | 32 | 2025-05-28 | 2025-05-27 | Unknown | Unknown | 73 | 51 | 44 | 32 | 117 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -375 | -270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 321.95 | Unknown | Unknown | Unknown | -1134 | 1455.95 | Unknown | 1141.52 | 321.95 | 819.57 | Yes | N/A | N/A | 2024-01-23 | 2024-03-25 | 63 | 45 | 2024-03-25 | 2024-03-28 | 4 | 4 | 2024-03-28 | 2024-08-15 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-04 | 1 | 1 | 204 | 146 | 5 | 5 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -708 | -507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 87.04 | Unknown | Unknown | Unknown | Unknown | 87.04 | 7962 | 2149.5 | 87.04 | 2062.46 | Yes | N/A | N/A | 2024-09-09 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-10 | 6 | 4 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 0 | 0 | 7 | 5 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 642.8 | -11.7 | Unknown | Unknown | Unknown | 654.5 | 3981 | 1392.72 | 642.8 | 749.92 | Yes | N/A | N/A | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-21 | 49 | 35 | 2024-09-03 | 2024-10-03 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-29 | 27 | 19 | 2024-10-29 | 2024-10-29 | 1 | 1 | 32 | 24 | 78 | 56 | 110 | 80 | Steps 2,3,5,6,7 | 48 | 34 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-04 | 989 | 706 | No | 2023-06-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2024-04-14 | IOU Designed & Installed | N/A | Yes | 250 | 7764.54 | 350.69 | Unknown | Unknown | -8754 | 16167.85 | 3324.72 | 8066.35 | 7764.54 | 301.81 | Yes | N/A | N/A | 2023-06-08 | 2023-12-15 | 191 | 137 | 2023-12-15 | 2023-07-06 | Unknown | Unknown | 2024-03-27 | 2024-04-02 | 7 | 5 | 2023-06-30 | 2023-07-05 | 6 | 4 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-04-05 | 10 | 8 | 2024-04-14 | 2024-05-20 | 37 | 26 | 2024-05-20 | 2024-05-20 | 1 | 1 | 199 | 143 | 54 | 39 | 253 | 182 | Steps 2,3,5,6,7 | 277 | 197 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-07 | -627 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-26 | 2023-08-26 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | 2028 | 573.39 | Unknown | Unknown | Unknown | 1454.61 | Unknown | 871.39 | 2028 | -1156.61 | Yes | N/A | N/A | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2023-09-14 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-19 | 6 | 4 | 2023-09-19 | 2023-09-19 | 1 | 1 | 21 | 14 | 8 | 5 | 29 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-02 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-17 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | -104.23 | -19.99 | Unknown | Unknown | -1108 | 1023.76 | Unknown | 1123.04 | -104.23 | 1227.27 | Yes | N/A | N/A | 2024-12-12 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-17 | 12 | 8 | 2024-12-17 | 2024-12-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-03-28 | 88 | 64 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-28 | 2025-04-02 | 6 | 4 | 2025-04-02 | 2025-04-02 | 1 | 1 | 103 | 75 | 19 | 13 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 179 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-07 | 2022-06-07 | 2024-05-21 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 108052.04 | 11939.65 | Unknown | Unknown | 15258.46 | 80853.93 | 0 | 95910.04 | 108052.04 | -12142 | Yes | N/A | N/A | 2022-06-07 | 2023-06-09 | 368 | 264 | 2023-06-09 | 2023-10-09 | 123 | 87 | 2023-08-28 | 2024-06-25 | 45 | 33 | 2023-10-09 | 2023-10-16 | 8 | 6 | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-17 | 2024-05-20 | 217 | 155 | 2024-05-21 | 2024-06-14 | 25 | 19 | 2024-06-14 | 2024-06-14 | 1 | 1 | 413 | 297 | 374 | 268 | 787 | 565 | Steps 2,3,5,6,7 | 302 | 216 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-30 | 77 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 4196.79 | 954.69 | Unknown | 548.5 | Unknown | 2693.6 | 3941 | 773.51 | 4196.79 | -3423.28 | Yes | N/A | N/A | 2024-05-10 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-10 | 45 | 33 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-10-01 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-14 | 14 | 10 | 2024-10-14 | 2024-10-15 | 2 | 2 | 145 | 103 | 61 | 45 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -394 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-06 | 2024-07-06 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 28.52 | Unknown | Unknown | Unknown | Unknown | 28.52 | 3981 | 1614.71 | 28.52 | 1586.19 | Yes | N/A | N/A | 2024-07-06 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-07-06 | 88 | 63 | 2024-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-06 | 2024-08-21 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-27 | 7 | 5 | 2024-08-27 | 2025-03-07 | 193 | 139 | 47 | 33 | 288 | 207 | 335 | 240 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-21 | -801 | -572 | No | 2023-02-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-07-12 | IOU Designed & Installed | N/A | Yes | 100 | 574.75 | 323.84 | Unknown | 89.36 | Unknown | 161.55 | Unknown | 351.99 | 574.75 | -222.76 | Yes | N/A | N/A | 2023-02-13 | 2023-05-24 | 101 | 73 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | 2023-07-12 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2023-07-13 | 2 | 2 | 2023-07-13 | 2023-07-13 | 1 | 1 | 251 | 181 | 3 | 3 | 254 | 184 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 957.97 | -22.77 | Unknown | Unknown | 67.67 | 913.07 | 3981 | 782.17 | 957.97 | -175.8 | Yes | N/A | N/A | 2024-02-16 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-03-04 | 54 | 38 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 55 | 39 | 55 | 39 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2273.27 | 2273.27 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-27 | -25 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1213.69 | -26.85 | Unknown | Unknown | Unknown | 1240.54 | Unknown | 227.98 | 1213.69 | -985.71 | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | 2023-11-15 | 206 | 148 | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-05-08 | 6 | 4 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-02 | 1 | 1 | 1 | 1 | 213 | 153 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -606 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 137.31 | -8.47 | Unknown | Unknown | Unknown | 145.78 | 3981 | 908.03 | 137.31 | 770.72 | Yes | N/A | N/A | 2023-09-28 | 2023-07-05 | Unknown | Unknown | 2023-07-05 | 2023-10-09 | 97 | 69 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-18 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-24 | 7 | 5 | 2023-10-24 | 2023-10-24 | 1 | 1 | 10 | 8 | 105 | 75 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -497 | -356 | No | 2023-02-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | Yes | 20 | 0.02 | Unknown | Unknown | Unknown | Unknown | 0.02 | Unknown | 341 | 0.02 | 340.98 | Yes | N/A | N/A | 2023-02-24 | 2023-03-16 | 21 | 15 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 521 | 373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 887.31 | -49.55 | Unknown | Unknown | 345.7 | 591.16 | 115132 | Not available | 887.31 | Unknown | Yes | N/A | N/A | 2022-04-28 | 2023-02-02 | 281 | 201 | 2023-02-02 | 2023-03-22 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 281 | 201 | 50 | 35 | 331 | 236 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | LAGUNA NIGUEL | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 237.74 | Unknown | Unknown | Unknown | Unknown | 237.74 | Unknown | 444.8 | 237.74 | 207.06 | Yes | N/A | N/A | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-11-12 | 124 | 88 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-21 | 1 | 1 | 1 | 1 | 125 | 89 | 126 | 90 | Steps 2,3,5,6,7 | 111 | 79 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-07 | -336 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 196.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-21 | 11 | 7 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-04-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-06 | 15 | 11 | 2025-05-06 | 2025-05-06 | 1 | 1 | 2 | 2 | 27 | 19 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -504 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-25 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 659.06 | 190.31 | Unknown | Unknown | Unknown | 468.75 | Unknown | 1509.18 | 659.06 | 850.12 | Yes | N/A | N/A | 2024-07-19 | 2024-07-25 | 7 | 5 | 2024-07-25 | 2024-07-30 | 6 | 4 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-09-10 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-12 | 3 | 3 | 2024-09-12 | 2024-09-12 | 1 | 1 | 55 | 39 | 10 | 8 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-25 | -327 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 10.64 | Unknown | Unknown | Unknown | Unknown | 10.64 | 3981 | 186.09 | 10.64 | 175.45 | Yes | N/A | N/A | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | 2024-07-03 | 2 | 2 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-01 | 16 | 12 | 2024-08-01 | 2024-08-02 | 2 | 2 | 16 | 12 | 20 | 16 | 36 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-27 | -101 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-09 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 12.54 | -9.02 | Unknown | Unknown | 0.23 | 21.33 | 3981 | 931.53 | 12.54 | 918.99 | Yes | N/A | N/A | 2023-02-07 | 2023-02-21 | 15 | 11 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-08-07 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-18 | 12 | 10 | 2023-08-18 | 2023-08-18 | 1 | 1 | 183 | 131 | 13 | 11 | 196 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | -57 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 43715.82 | 9721.93 | Unknown | 527.78 | 185.54 | 33280.57 | 482445 | 24669.71 | 43715.82 | -19046.11 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | 2023-04-07 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-04-06 | 10 | 8 | 2023-04-07 | 2958465 | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | 2024-06-07 | 2024-07-25 | 49 | 35 | 2024-07-25 | 2024-07-10 | Unknown | Unknown | 1 | 1 | 77 | 57 | 78 | 58 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -352 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | -3.92 | -3.18 | Unknown | Unknown | Unknown | -0.74 | Unknown | 104.94 | -3.92 | 108.86 | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-02-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-15 | 24 | 18 | 2024-03-15 | 2024-02-26 | Unknown | Unknown | 8 | 6 | 25 | 19 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1225.56 | -7.65 | Unknown | Unknown | 4.58 | 1228.63 | 3981 | 829.38 | 1225.56 | -396.18 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-03-31 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Bonsall | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -290 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-07-10 | IOU Designed & Installed | N/A | No | N/A | 5461.82 | 4656.26 | Unknown | Unknown | -8904 | 9709.56 | Unknown | 8903.66 | 5461.82 | 3441.84 | Yes | N/A | N/A | 2023-06-08 | 2023-06-08 | 1 | 1 | 2023-06-08 | 2023-07-07 | 30 | 22 | 2023-06-12 | 2023-07-05 | 24 | 18 | 2023-07-07 | 2023-07-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-08-21 | 43 | 31 | 2023-08-21 | 2023-08-21 | 1 | 1 | 25 | 19 | 89 | 65 | 114 | 84 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-18 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | -16.96 | -12.3 | Unknown | Unknown | Unknown | -4.66 | Unknown | 425.49 | -16.96 | 442.45 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-10-02 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-12-04 | 64 | 46 | 2023-12-04 | 2023-12-04 | 1 | 1 | 64 | 46 | 66 | 48 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-08 | 853 | 610 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | 3070.36 | -29.14 | Unknown | Unknown | -2265 | 5364.5 | Unknown | 1811.91 | 3070.36 | -1258.45 | Yes | N/A | N/A | 2023-03-15 | 2023-03-14 | Unknown | Unknown | 2023-03-14 | 2023-05-26 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | Unknown | 2023-06-07 | 2023-06-23 | 17 | 13 | 2023-06-26 | 2023-10-09 | 106 | 76 | 2023-10-09 | 2023-10-09 | 1 | 1 | 0 | 0 | 198 | 144 | 198 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Clemente | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | -287 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-12 | 2024-08-31 | IOU Designed & Installed | N/A | No | N/A | -4921.25 | 1736.16 | Unknown | Unknown | -7849 | 1191.59 | Unknown | 7849.37 | -4921.25 | 12770.62 | Yes | N/A | N/A | 2024-07-24 | 2024-08-12 | 20 | 14 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-31 | 2024-09-03 | 4 | 2 | 2024-09-03 | 2024-09-03 | 1 | 1 | 20 | 14 | 5 | 3 | 25 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 34 | 25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | 754.96 | -17.44 | Unknown | Unknown | Unknown | 772.4 | 3981 | 1030.83 | 754.96 | 275.87 | Yes | N/A | N/A | 2023-12-06 | 2023-12-06 | 1 | 1 | 2023-12-06 | 2023-12-06 | 1 | 1 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-02-28 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-15 | 17 | 13 | 2024-03-15 | 2024-03-06 | Unknown | Unknown | 86 | 62 | 18 | 14 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 46.75 | 46.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -522 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-02-23 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 142.78 | -11.74 | Unknown | Unknown | -769.58 | 924.1 | Unknown | 775.84 | 142.78 | 633.06 | Yes | N/A | N/A | 2024-01-16 | 2024-04-16 | 92 | 66 | 2024-04-16 | 2024-04-22 | 7 | 5 | 2024-04-22 | 2024-06-03 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-11 | 22 | 16 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-07-11 | 2024-07-16 | 6 | 4 | 2024-07-16 | 2024-07-16 | 1 | 1 | 157 | 113 | 14 | 10 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-19 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 2244.28 | 377.04 | Unknown | 153.59 | -1363.18 | 3076.83 | Unknown | 1388.22 | 2244.28 | -856.06 | Yes | N/A | N/A | 2024-06-13 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-06-28 | 44 | 32 | 2024-06-28 | 2024-08-05 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-09-19 | 46 | 34 | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-19 | 2024-10-10 | 22 | 16 | 2024-10-10 | 2024-10-10 | 1 | 1 | 85 | 61 | 67 | 49 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -514 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-05 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 823.36 | -10.4 | Unknown | Unknown | 18.61 | 815.15 | 3981 | 641.78 | 823.36 | -181.58 | Yes | N/A | N/A | 2023-09-05 | 2023-09-12 | 8 | 6 | 2023-09-12 | 2023-11-07 | 57 | 41 | 2023-11-07 | 2023-12-18 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-04 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-21 | 49 | 35 | 2024-01-21 | 2023-12-20 | Unknown | Unknown | 77 | 55 | 106 | 76 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 3085.3 | Unknown | Unknown | Unknown | 25.9 | 3059.4 | 3941 | 1114.32 | 3085.3 | -1970.98 | Yes | N/A | N/A | 2024-08-26 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-09-06 | 37 | 27 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-02-19 | 167 | 119 | Unknown | 2025-01-22 | Unknown | Unknown | 2025-02-19 | 2025-02-26 | 8 | 6 | 2025-02-26 | 2025-02-26 | 1 | 1 | 167 | 119 | 46 | 34 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 76.15 | 76.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -250 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-04-25 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 1874.15 | -37.15 | Unknown | Unknown | Unknown | 1911.3 | 7962 | 1798.53 | 1874.15 | -75.62 | Yes | N/A | N/A | 2024-03-19 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-04-26 | 130 | 94 | 2024-04-26 | 2024-10-31 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2025-03-12 | 321 | 229 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-24 | 13 | 9 | 2025-03-24 | 2025-03-24 | 1 | 1 | 510 | 364 | 144 | 104 | 654 | 468 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 151 | 151 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-12 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 932.53 | -4.96 | Unknown | Unknown | 33.66 | 903.83 | 3981 | 749.77 | 932.53 | -182.76 | Yes | N/A | N/A | 2023-03-06 | 2023-07-28 | 145 | 105 | 2023-07-28 | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-12-05 | 131 | 93 | Unknown | 2023-11-07 | Unknown | Unknown | 2023-12-05 | 2023-12-19 | 15 | 11 | 2023-12-19 | 2023-12-19 | 1 | 1 | 277 | 199 | 16 | 12 | 293 | 211 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | 433 | 310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-26 | 2023-12-04 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 11264.88 | -20.79 | Unknown | Unknown | -8520.44 | 19806.11 | Unknown | 7978.59 | 11264.88 | -3286.29 | Yes | N/A | N/A | 2023-09-20 | 2023-10-05 | 16 | 12 | 2023-10-05 | 2023-11-02 | 29 | 21 | 2023-10-09 | 2023-10-11 | 3 | 3 | 2023-10-18 | 2023-11-08 | 14 | 10 | 2023-11-14 | Unknown | Unknown | Unknown | 2023-11-14 | 2023-11-21 | 8 | 6 | 2023-12-04 | 2024-01-11 | 39 | 29 | 2024-01-11 | 2024-01-11 | 1 | 1 | 19 | 15 | 91 | 67 | 110 | 82 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-20 | 575 | 412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-21 | 2021-10-21 | 2024-06-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 810328.97 | 238988.69 | Unknown | 48.48 | 21773.92 | 549517.88 | 3338256 | 324449.66 | 810328.97 | -485879.31 | Yes | N/A | N/A | 2021-10-21 | 2023-03-30 | 526 | 376 | 2023-03-30 | 2023-11-03 | 219 | 157 | 2023-04-14 | 2024-06-14 | 44 | 32 | 2023-11-03 | 2024-06-18 | 229 | 163 | 2023-11-03 | 2023-12-26 | 54 | 38 | 2023-11-16 | 2024-05-08 | 175 | 125 | 2024-06-20 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-05-17 | 1 | 1 | 624 | 446 | 624 | 446 | 1248 | 892 | Steps 2,3,5,6,7 | 695 | 495 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 234 | 167 | No | 2023-01-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | 2023-01-19 | IOU Designed & Installed | N/A | Yes | 66 | 868.74 | Unknown | Unknown | Unknown | 34.07 | 834.67 | 3981 | 587.44 | 868.74 | -281.3 | Yes | N/A | N/A | 2023-01-03 | 2023-03-10 | 67 | 49 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-01-19 | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | 2023-01-19 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-05 | 1 | 1 | 67 | 49 | 1 | 1 | 68 | 50 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | -461 | -330 | No | 2023-12-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-07-09 | IOU Designed & Installed | N/A | Yes | 48 | 1014.93 | Unknown | Unknown | Unknown | 34.59 | 980.34 | 3981 | 930.84 | 1014.93 | -84.09 | Yes | N/A | N/A | 2023-12-27 | 2024-02-13 | 49 | 35 | 2024-02-13 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-07-09 | 188 | 134 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-07-09 | 2024-07-24 | 16 | 12 | 2024-07-24 | 2024-08-09 | 17 | 13 | 237 | 169 | 33 | 25 | 270 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | -31 | -24 | No | 2021-10-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-13 | 2021-10-26 | 2022-07-07 | IOU Designed & Installed | N/A | Yes | 583 | 5079.14 | -6.05 | Unknown | Unknown | 297.34 | 4787.85 | 3981 | 1055.87 | 5079.14 | -4023.27 | Yes | N/A | N/A | 2021-10-13 | 2023-05-19 | 584 | 418 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-10-26 | 2022-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-07-07 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-08-01 | Unknown | Unknown | 584 | 418 | 0 | 0 | 584 | 418 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | -528 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 61.45 | -0.94 | Unknown | Unknown | Unknown | 62.39 | 1000 | 192.51 | 61.45 | 131.06 | Yes | N/A | N/A | 2024-07-15 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-07-15 | 25 | 17 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-11-04 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-13 | 10 | 8 | 2024-11-13 | 2024-11-13 | 1 | 1 | 113 | 81 | 36 | 26 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 2014.25 | 2014.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | -15 | -12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 2347.09 | -11.93 | Unknown | Unknown | 47.45 | 2311.57 | 3981 | 1389.22 | 2347.09 | -957.87 | Yes | N/A | N/A | 2024-03-14 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-05-01 | 113 | 81 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-07-16 | 77 | 55 | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-16 | 2024-07-18 | 3 | 3 | 2024-07-18 | 2024-07-17 | Unknown | Unknown | 77 | 55 | 116 | 84 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -304 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6693.54 | 157.13 | Unknown | Unknown | -1696 | 8232.41 | Unknown | 1910.93 | 6693.54 | -4782.61 | Yes | N/A | N/A | 2023-01-11 | 2023-05-12 | 122 | 88 | 2023-05-12 | 2024-02-02 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-07-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-02-16 | 1 | 1 | 122 | 88 | 270 | 194 | 392 | 282 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -108 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | -4.91 | -19.39 | Unknown | Unknown | 5.08 | 9.4 | 4000 | 1867.2 | -4.91 | 1872.11 | Yes | N/A | N/A | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2023-08-29 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-29 | 16 | 12 | 2023-08-29 | 2023-09-22 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2024-01-24 | 119 | 85 | 2024-01-24 | 2024-01-24 | 1 | 1 | 26 | 20 | 156 | 112 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 40.56 | Unknown | Unknown | Unknown | Unknown | 40.56 | Unknown | 1430.79 | 40.56 | 1390.23 | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-09-19 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-08 | 20 | 14 | 2024-10-08 | 2024-10-08 | 1 | 1 | 121 | 87 | 22 | 16 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-02 | 965 | 690 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-11 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 643.32 | -16.09 | Unknown | Unknown | 20.6 | 638.81 | 3981 | 1005.58 | 643.32 | 362.26 | Yes | N/A | N/A | 2021-10-11 | 2023-05-04 | 571 | 409 | 2023-05-04 | 2023-05-26 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-07-25 | Unknown | Unknown | 571 | 409 | 23 | 17 | 594 | 426 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-04-01 | 1427 | 1020 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-10 | 2022-11-10 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 28938.38 | 7408.63 | Unknown | Unknown | -14855 | 36384.75 | 0 | 25003.3 | 28938.38 | -3935.08 | Yes | N/A | N/A | 2022-11-10 | 2023-01-31 | 83 | 59 | 2023-01-31 | 2024-01-03 | 338 | 242 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2024-02-02 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-27 | 23 | 17 | 2024-02-27 | 2024-02-27 | 1 | 1 | 83 | 59 | 475 | 341 | 558 | 400 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-15 | 369 | 264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 1351.34 | 218.8 | Unknown | Unknown | 109.2 | 1023.34 | 3981 | 830.34 | 1351.34 | -521 | Yes | N/A | N/A | 2023-07-28 | 2023-08-23 | 27 | 19 | 2023-08-23 | 2023-08-23 | 1 | 1 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2024-05-28 | 280 | 200 | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-28 | 2024-06-19 | 23 | 17 | 2024-06-19 | 2024-06-18 | Unknown | Unknown | 307 | 219 | 24 | 18 | 331 | 237 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -528 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-03-29 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 11.2 | -9.94 | Unknown | Unknown | Unknown | 21.14 | Unknown | 1112.37 | 11.2 | 1101.17 | Yes | N/A | N/A | 2024-02-16 | 2024-03-27 | 41 | 29 | 2024-03-27 | 2024-03-29 | 3 | 3 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-06-17 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-01 | 15 | 11 | 2024-07-01 | 2024-07-01 | 1 | 1 | 122 | 86 | 19 | 15 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-25 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 985.87 | -0.94 | Unknown | Unknown | Unknown | 986.81 | 3981 | 1273.69 | 985.87 | 287.82 | Yes | N/A | N/A | 2024-06-18 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-10-04 | 129 | 93 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-10-11 | 108 | 78 | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-11 | 2024-10-24 | 14 | 10 | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 108 | 78 | 143 | 103 | 251 | 181 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-25 | -151 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-09-15 | IOU Designed & Installed | N/A | No | N/A | 799.05 | 414.7 | Unknown | 113.34 | Unknown | 271.01 | Unknown | 153.83 | 799.05 | -645.22 | Yes | N/A | N/A | 2023-07-17 | 2023-09-07 | 53 | 39 | 2023-09-07 | 2023-09-11 | 5 | 3 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-15 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-10-26 | 42 | 30 | 2023-10-26 | 2023-10-26 | 1 | 1 | 58 | 44 | 48 | 34 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | 204 | 147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 7 | Unknown | Unknown | Unknown | Unknown | 7 | 0 | 483.84 | 7 | 476.84 | Yes | N/A | N/A | 2023-04-19 | 2023-04-19 | 1 | 1 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2024-08-28 | 498 | 356 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-12 | 16 | 12 | 2024-09-12 | 2024-09-12 | 1 | 1 | 499 | 357 | 17 | 13 | 516 | 370 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-30 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 747.08 | 28.24 | Unknown | 5.37 | Unknown | 713.47 | Unknown | 1485.17 | 747.08 | 738.09 | Yes | N/A | N/A | 2024-05-06 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-06-18 | 71 | 51 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-18 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-28 | 11 | 9 | 2024-06-28 | 2024-06-27 | Unknown | Unknown | 20 | 14 | 82 | 60 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 169 | 169 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-23 | -557 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | -7.25 | -5.89 | Unknown | Unknown | Unknown | -1.36 | Unknown | 517.29 | -7.25 | 524.54 | Yes | N/A | N/A | 2024-02-27 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2024-02-27 | 82 | 58 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-14 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-05-15 | 63 | 45 | 2024-05-15 | 2024-05-15 | 1 | 1 | 17 | 13 | 146 | 104 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | -221 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-05-20 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 882.5 | Unknown | Unknown | Unknown | Unknown | 882.5 | 3981 | 1157.99 | 882.5 | 275.49 | Yes | N/A | N/A | 2023-11-28 | 2024-05-20 | 175 | 125 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-11-13 | 178 | 128 | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-13 | 2024-12-03 | 21 | 15 | 2024-12-03 | 2024-12-03 | 1 | 1 | 353 | 253 | 23 | 17 | 376 | 270 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 652 | 652 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -320 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-08 | 2023-10-08 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 30.79 | -4.52 | Unknown | Unknown | Unknown | 35.31 | 3885 | 1091.09 | 30.79 | 1060.3 | Yes | N/A | N/A | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-08 | 2024-06-27 | 264 | 189 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-08-20 | 55 | 39 | 2024-08-20 | 2024-08-19 | Unknown | Unknown | 265 | 189 | 56 | 39 | 321 | 228 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-28 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 905.39 | Unknown | Unknown | Unknown | 12.32 | 893.07 | 3981 | 800.33 | 905.39 | -105.06 | Yes | N/A | N/A | 2024-02-15 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-04-04 | 86 | 62 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-07-10 | 98 | 70 | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-10 | 2024-07-24 | 15 | 11 | 2024-07-24 | 2024-07-23 | Unknown | Unknown | 98 | 70 | 101 | 73 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1665.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-06-03 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-04 | 2 | 2 | 2025-06-04 | 2025-06-04 | 1 | 1 | 87 | 63 | 4 | 4 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-05-06 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 20.26 | Unknown | Unknown | Unknown | Unknown | 20.26 | Unknown | 1352.4 | 20.26 | 1332.14 | Yes | N/A | N/A | 2024-04-23 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-05-06 | 46 | 32 | 2024-05-06 | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-16 | 10 | 8 | 2024-05-06 | 2024-10-03 | 151 | 109 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-18 | 16 | 12 | 2024-10-18 | 2024-10-18 | 1 | 1 | 151 | 109 | 73 | 53 | 224 | 162 | Steps 2,3,5,6,7 | 10 | 8 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 263.2 | 263.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-10-18 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 3564.59 | Unknown | Unknown | Unknown | 307.23 | 3257.36 | 3981 | 795.93 | 3564.59 | -2768.66 | Yes | N/A | N/A | 2023-09-13 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-11-10 | 124 | 90 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-08-12 | 277 | 197 | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-12 | 2024-08-23 | 12 | 10 | 2024-08-23 | 2024-08-23 | 1 | 1 | 277 | 197 | 137 | 101 | 414 | 298 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -275 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-10 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | -956.09 | 1710.39 | Unknown | 190.61 | -3622 | 764.91 | Unknown | 3621.79 | -956.09 | 4577.88 | Yes | N/A | N/A | 2024-07-02 | 2024-07-10 | 9 | 7 | 2024-07-10 | 2024-09-11 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-07-30 | 2024-09-11 | 44 | 32 | 2024-09-11 | 2024-09-11 | 1 | 1 | 9 | 7 | 110 | 80 | 119 | 87 | Steps 2,3,5,6,7 | 43 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 14.28 | -12.64 | Unknown | Unknown | Unknown | 26.92 | 3981 | 1159.74 | 14.28 | 1145.46 | Yes | N/A | N/A | 2024-02-28 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-02-29 | 17 | 13 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-22 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-03-29 | 8 | 6 | 2024-03-29 | 2024-03-29 | 1 | 1 | 24 | 18 | 26 | 20 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-08 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-10 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1.66 | Unknown | Unknown | Unknown | Unknown | 1.66 | 3981 | 1668.57 | 1.66 | 1666.91 | Yes | N/A | N/A | 2024-12-16 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2025-01-10 | 33 | 25 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-21 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-01-30 | 10 | 8 | 2025-01-30 | 2025-01-30 | 1 | 1 | 12 | 8 | 44 | 34 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -498 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | -186.34 | -23.01 | Unknown | Unknown | -158 | -5.33 | Unknown | 158.14 | -186.34 | 344.48 | Yes | N/A | N/A | 2023-09-15 | 2023-10-10 | 26 | 18 | 2023-10-10 | 2023-12-05 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 38 | 28 | 2024-03-15 | 2024-03-15 | 1 | 1 | 26 | 18 | 96 | 70 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-09-23 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 12.32 | Unknown | Unknown | Unknown | Unknown | 12.32 | 3961 | 1485.16 | 12.32 | 1472.84 | Yes | N/A | N/A | 2024-08-13 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2024-09-23 | 64 | 46 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-18 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-25 | 8 | 6 | 2024-10-25 | 2024-10-25 | 1 | 1 | 25 | 19 | 73 | 53 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 654 | 654 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -488 | -349 | No | 2024-09-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-04-11 | IOU Designed & Installed | N/A | Yes | 177 | 1376.79 | Unknown | Unknown | Unknown | 16.26 | 1360.53 | 3981 | 1377.66 | 1376.79 | 0.87 | Yes | N/A | N/A | 2024-09-17 | 2025-03-13 | 178 | 128 | 2025-03-13 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 2024-09-26 | 2025-04-11 | 198 | 142 | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-15 | 5 | 3 | 2025-04-15 | 2025-04-15 | 1 | 1 | 376 | 270 | 7 | 5 | 383 | 275 | Steps 2,3,5,6,7 | 174 | 124 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | -11.28 | -9.75 | Unknown | Unknown | Unknown | -1.53 | 3941 | 1420.52 | -11.28 | 1431.8 | Yes | N/A | N/A | 2024-05-23 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-23 | 43 | 31 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-06 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-03 | 28 | 20 | 2024-07-03 | 2024-07-03 | 1 | 1 | 15 | 11 | 72 | 52 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-20 | -139 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1671.82 | -68.16 | Unknown | Unknown | 225.05 | 1514.93 | 6804 | 769.92 | 1671.82 | -901.9 | Yes | N/A | N/A | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | 2023-09-20 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-09-19 | 7 | 5 | 2023-09-20 | 2023-09-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 2 | 2 | 29 | 20 | 31 | 22 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | 224 | 161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 1083.76 | -20.4 | Unknown | Unknown | 19.12 | 1085.04 | 0 | 1631.09 | 1083.76 | 547.33 | Yes | N/A | N/A | 2023-09-22 | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-09-22 | 103 | 75 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2024-08-26 | 340 | 242 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2025-01-16 | 144 | 104 | 2025-01-16 | 2025-01-16 | 1 | 1 | 340 | 242 | 248 | 180 | 588 | 422 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | -212 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-20 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | -23.39 | -16.96 | Unknown | Unknown | Unknown | -6.43 | Unknown | 496.45 | -23.39 | 519.84 | Yes | N/A | N/A | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | 2023-07-20 | 4 | 4 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-08-16 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-08-25 | 10 | 8 | 2023-08-25 | 2023-08-25 | 1 | 1 | 29 | 21 | 15 | 13 | 44 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 182.05 | 182.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-12 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 448.64 | Unknown | Unknown | Unknown | 5.68 | 442.96 | 3981 | 844.22 | 448.64 | 395.58 | Yes | N/A | N/A | 2025-03-06 | 2025-04-03 | 29 | 21 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-06-03 | 62 | 44 | Unknown | 2025-04-28 | Unknown | Unknown | 2025-06-03 | 2025-06-02 | Unknown | Unknown | 2025-06-02 | 2025-06-02 | 1 | 1 | 91 | 65 | 2 | 2 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-08-07 | IOU Designed & Installed | N/A | No | N/A | 1433.77 | Unknown | Unknown | Unknown | Unknown | 1433.77 | Unknown | 767.41 | 1433.77 | -666.36 | Yes | N/A | N/A | 2024-07-02 | 2024-07-05 | 4 | 4 | 2024-07-05 | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-12 | 2 | 2 | 2024-07-08 | 2024-08-06 | 30 | 22 | 2024-07-24 | 2024-08-07 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-16 | 10 | 8 | 2024-08-16 | 2024-08-16 | 1 | 1 | 21 | 17 | 41 | 31 | 62 | 48 | Steps 2,3,5,6,7 | 17 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | -144 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 599.15 | 165.68 | Unknown | 88.44 | 4.66 | 340.37 | 3981 | 1990.01 | 599.15 | 1390.86 | Yes | N/A | N/A | 2023-08-22 | 2023-08-25 | 4 | 4 | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-02-07 | 1 | 1 | 4 | 4 | 2 | 2 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-20 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 1680.02 | 250.75 | Unknown | 93.04 | Unknown | 1336.23 | 3981 | 1373.07 | 1680.02 | -306.95 | Yes | N/A | N/A | 2024-06-14 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-07-08 | 62 | 44 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-05 | 15 | 11 | 2024-08-05 | 2024-08-05 | 1 | 1 | 15 | 11 | 78 | 56 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LADERA RANCH | N/A | 162 | 162 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | 134 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-09-13 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 122984.13 | 37110.82 | Unknown | 184.07 | 240.15 | 85449.09 | 334323 | 14765.98 | 122984.13 | -108218.15 | Yes | N/A | N/A | 2023-08-09 | 2023-08-10 | 2 | 2 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | 2024-11-14 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-08 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-24 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 42.33 | Unknown | Unknown | Unknown | Unknown | 42.33 | 3981 | 1442.22 | 42.33 | 1399.89 | Yes | N/A | N/A | 2024-06-04 | 2024-06-04 | 1 | 1 | 2024-06-04 | 2024-06-04 | 1 | 1 | 2024-06-04 | Unknown | Unknown | Unknown | 2024-06-05 | 2024-07-03 | 29 | 21 | 2024-06-04 | 2024-09-09 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-15 | 37 | 27 | 2024-10-15 | 2024-10-15 | 1 | 1 | 99 | 71 | 68 | 50 | 167 | 121 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | -9.68 | -7.85 | Unknown | Unknown | Unknown | -1.83 | Unknown | 515.81 | -9.68 | 525.49 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2023-12-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-03-15 | 88 | 64 | 2024-03-15 | 2024-03-15 | 1 | 1 | 3 | 3 | 90 | 66 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 100 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 3810.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | 2468.11 | Unknown | Unknown | Unknown | 12.04 | 2456.07 | 3981 | 1428.16 | 2468.11 | -1039.95 | Yes | N/A | N/A | 2025-01-21 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-22 | 14 | 10 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-06-19 | 149 | 107 | Unknown | 2025-06-16 | Unknown | Unknown | 2025-06-19 | 2025-06-30 | 12 | 8 | 2025-06-30 | 2025-06-30 | 1 | 1 | 149 | 107 | 27 | 19 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 108.52 | Unknown | Unknown | Unknown | Unknown | 108.52 | 3981 | 1839.17 | 108.52 | 1730.65 | Yes | N/A | N/A | 2024-08-05 | 2024-08-09 | 5 | 5 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-30 | 1 | 1 | 5 | 5 | 2 | 2 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | -222 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 13518.02 | 3122.15 | Unknown | 1114.34 | 4.04 | 9277.49 | 3981 | 2349.81 | 13518.02 | -11168.21 | Yes | N/A | N/A | 2024-06-05 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-24 | 21 | 15 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-09-13 | 82 | 60 | Unknown | 2024-08-26 | Unknown | Unknown | 2024-09-13 | 2024-09-16 | 4 | 2 | 2024-09-16 | 2024-09-16 | 1 | 1 | 82 | 60 | 26 | 18 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 515.23 | -18.9 | Unknown | Unknown | Unknown | 534.13 | 3981 | 1191.53 | 515.23 | 676.3 | Yes | N/A | N/A | 2024-05-01 | 2024-05-09 | 9 | 7 | 2024-05-09 | 2024-05-17 | 9 | 7 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-06-24 | 1 | 1 | 9 | 7 | 10 | 8 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Spring Valley | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-16 | 515 | 370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 1161.18 | 1189.53 | Unknown | 510.67 | -5661 | 5121.98 | Unknown | 5660.88 | 1161.18 | 4499.7 | Yes | N/A | N/A | 2024-11-21 | 2024-12-10 | 20 | 14 | 2024-12-10 | 2025-01-06 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-07 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-22 | 2025-03-14 | 52 | 38 | 2025-03-14 | 2025-03-14 | 1 | 1 | 20 | 14 | 97 | 71 | 117 | 85 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-05-23 | IOU Designed & Installed | N/A | No | N/A | -174.03 | -12.64 | Unknown | Unknown | -370 | 208.61 | Unknown | 580.44 | -174.03 | 754.47 | Yes | N/A | N/A | 2023-02-02 | 2023-02-09 | 8 | 6 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-05-23 | 75 | 53 | Unknown | 2023-05-25 | Unknown | Unknown | 2023-05-23 | 2023-06-12 | 21 | 15 | 2023-06-12 | 2023-06-12 | 1 | 1 | 83 | 59 | 22 | 16 | 105 | 75 | Steps 2,3,5,6,7 | 2 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | -620 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1626.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-31 | 18 | 14 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-04-22 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-30 | 9 | 7 | 2025-04-30 | 2025-04-30 | 1 | 1 | 82 | 58 | 28 | 22 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 33.35 | 33.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 135 | 98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-09 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 416.27 | -12.13 | Unknown | Unknown | 18.1 | 410.3 | 3981 | 1007.23 | 416.27 | 590.96 | Yes | N/A | N/A | 2023-02-07 | 2023-04-03 | 56 | 40 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-07-19 | 108 | 78 | Unknown | 2025-03-05 | Unknown | Unknown | 2023-07-19 | 2023-09-13 | 57 | 41 | 2023-09-13 | 2023-09-13 | 1 | 1 | 164 | 118 | 58 | 42 | 222 | 160 | Steps 2,3,5,6,7 | 595 | 425 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-09-09 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 431.25 | -8.78 | Unknown | Unknown | Unknown | 440.03 | Unknown | 1837.58 | 431.25 | 1406.33 | Yes | N/A | N/A | 2024-08-09 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-09-09 | 61 | 43 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-25 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-12 | 19 | 13 | 2024-11-12 | 2024-11-12 | 1 | 1 | 47 | 35 | 81 | 57 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | 32 | 24 | No | 2022-09-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-27 | 2024-07-30 | IOU Designed & Installed | N/A | Yes | 567 | 203.78 | 120.84 | Unknown | Unknown | Unknown | 82.94 | Unknown | 463.66 | 203.78 | 259.88 | Yes | N/A | N/A | 2022-09-27 | 2024-07-17 | 660 | 472 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-27 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-01 | 3 | 3 | 2024-08-01 | 2024-08-01 | 1 | 1 | 660 | 472 | 4 | 4 | 664 | 476 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | ALPINE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-01-31 | 498 | 357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-24 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 30198.43 | 8486.86 | Unknown | Unknown | -914 | 22625.57 | 23817 | 7537.12 | 30198.43 | -22661.31 | Yes | N/A | N/A | 2023-02-01 | 2023-02-24 | 24 | 18 | 2023-02-24 | 2023-10-24 | 243 | 173 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2024-09-16 | 329 | 235 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-06-12 | 2025-06-13 | 2 | 2 | 2025-06-13 | 2025-06-12 | Unknown | Unknown | 353 | 253 | 245 | 175 | 598 | 428 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -75 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-04-27 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 390.29 | -12.37 | Unknown | Unknown | 9.41 | 393.25 | 3981 | 646.79 | 390.29 | 256.5 | Yes | N/A | N/A | 2023-03-29 | 2023-05-01 | 34 | 24 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-11-13 | 197 | 141 | Unknown | 2023-08-03 | Unknown | Unknown | 2023-11-13 | 2023-11-17 | 5 | 5 | 2023-11-17 | 2023-11-17 | 1 | 1 | 231 | 165 | 6 | 6 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 37.1 | 37.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-15 | -455 | -326 | No | 2024-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | 2025-06-13 | IOU Designed & Installed | N/A | Yes | 214 | 2014.59 | 356.76 | Unknown | Unknown | -1644.63 | 3302.46 | Unknown | 1392.71 | 2014.59 | -621.88 | Yes | N/A | N/A | 2024-10-17 | 2025-05-19 | 215 | 153 | 2025-05-19 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-19 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-13 | 26 | 20 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-13 | 2025-06-17 | 5 | 3 | 2025-06-17 | 2025-06-17 | 1 | 1 | 252 | 180 | 6 | 4 | 258 | 184 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | 161 | 116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 1955.19 | 483.36 | Unknown | 36.42 | 14.62 | 1420.79 | 3981 | 718.62 | 1955.19 | -1236.57 | Yes | N/A | N/A | 2023-06-20 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-07-06 | 98 | 70 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2024-08-14 | 406 | 290 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-22 | 9 | 7 | 2024-08-22 | 2024-08-22 | 1 | 1 | 406 | 290 | 108 | 78 | 514 | 368 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -565 | -405 | No | 2025-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2025-02-06 | 2025-03-04 | IOU Designed & Installed | N/A | Yes | 12 | 503.33 | -10.2 | Unknown | Unknown | Unknown | 513.53 | Unknown | 1626.88 | 503.33 | 1123.55 | Yes | N/A | N/A | 2024-12-09 | 2025-02-18 | 72 | 52 | 2025-02-18 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-27 | 9 | 7 | 2025-02-06 | 2025-03-04 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-24 | 21 | 15 | 2025-03-24 | 2025-03-24 | 1 | 1 | 99 | 71 | 31 | 23 | 130 | 94 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 338 | 243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -779.71 | -18.52 | Unknown | Unknown | -798 | 36.81 | Unknown | 798.34 | -779.71 | 1578.05 | Yes | N/A | N/A | 2025-01-21 | 2025-01-24 | 4 | 4 | 2025-01-24 | 2025-02-28 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 4 | 4 | 37 | 27 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-08-03 | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | 9706.27 | 2961.82 | Unknown | 1097.03 | 434.38 | 5213.04 | 3981 | 1011.61 | 9706.27 | -8694.66 | Yes | N/A | N/A | 2023-06-30 | 2023-08-05 | 37 | 26 | 2023-08-05 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-09-13 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2024-10-10 | 394 | 282 | 2024-10-10 | 2024-10-10 | 1 | 1 | 68 | 49 | 395 | 283 | 463 | 332 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Jamul | COUNTY OF SAN DIEGO-SOUTH of 56 | 383.05 | 383.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | 36 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 36465.75 | 5500.78 | Unknown | Unknown | -12432.2 | 43397.17 | 2384 | 28454.64 | 36465.75 | -8011.11 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-10-09 | 83 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-02-04 | 75 | 53 | 2025-02-04 | 2025-02-04 | 1 | 1 | 1 | 1 | 159 | 111 | 160 | 112 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -585 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-27 | 2023-10-26 | IOU Designed & Installed | N/A | No | N/A | -252.26 | 185.4 | Unknown | 32.54 | -814 | 343.8 | Unknown | 814.34 | -252.26 | 1066.6 | Yes | N/A | N/A | 2023-08-30 | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-09-27 | 108 | 78 | 2023-09-27 | 2023-10-13 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-01 | 7 | 5 | 2023-11-01 | 2023-11-01 | 1 | 1 | 25 | 19 | 116 | 84 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-29 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 12.92 | -11.47 | Unknown | Unknown | Unknown | 24.39 | Unknown | 1198.92 | 12.92 | 1186 | Yes | N/A | N/A | 2024-02-09 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-09 | 99 | 71 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-05-13 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-15 | 3 | 3 | 2024-05-15 | 2024-05-15 | 1 | 1 | 95 | 67 | 103 | 75 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONSALL | BONSALL | 140 | 140 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -438 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-04-20 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 725.05 | -24.16 | Unknown | Unknown | 119.75 | 629.46 | 3981 | 643.13 | 725.05 | -81.92 | Yes | N/A | N/A | 2023-04-13 | 2023-04-20 | 8 | 6 | 2023-04-20 | Unknown | Unknown | Unknown | 2023-04-24 | 2023-05-03 | 10 | 8 | 2023-04-21 | 2023-04-24 | 4 | 2 | 2023-04-21 | 2023-10-02 | 165 | 117 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2024-11-12 | 408 | 292 | 2024-11-12 | 2023-10-03 | Unknown | Unknown | 183 | 131 | 412 | 294 | 595 | 425 | Steps 2,3,5,6,7 | 15 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 11.57 | -14.03 | Unknown | Unknown | Unknown | 25.6 | Unknown | 830.39 | 11.57 | 818.82 | Yes | N/A | N/A | 2024-01-18 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2024-01-18 | 101 | 73 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-03-15 | 52 | 38 | 2024-03-15 | 2024-03-29 | 15 | 11 | 7 | 5 | 168 | 122 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | 618.02 | -13.41 | Unknown | Unknown | Unknown | 631.43 | 3241 | 905.01 | 618.02 | 286.99 | Yes | N/A | N/A | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2024-07-05 | 254 | 182 | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-07-15 | 11 | 7 | 2024-07-15 | 2024-07-09 | Unknown | Unknown | 255 | 183 | 12 | 8 | 267 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | PINE VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-11 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1152.73 | 17.01 | Unknown | Unknown | -1183 | 13.26 | Unknown | 1182.6 | -1152.73 | 2335.33 | Yes | N/A | N/A | 2023-10-04 | 2023-10-02 | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-04-11 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | -1.63 | -4.86 | Unknown | Unknown | Unknown | 3.23 | 3981 | 558.72 | -1.63 | 560.35 | Yes | N/A | N/A | 2023-03-27 | 2023-04-11 | 16 | 12 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-07-18 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 115 | 83 | 2 | 2 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-14 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 1930.13 | 612.25 | Unknown | Unknown | Unknown | 1317.88 | Unknown | 1020.73 | 1930.13 | -909.4 | Yes | N/A | N/A | 2024-04-25 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-25 | 59 | 43 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-03 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-04 | 2 | 2 | 2024-06-04 | 2024-06-04 | 1 | 1 | 40 | 28 | 62 | 46 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-22 | 649 | 464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-18 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -344.23 | -13.02 | Unknown | Unknown | -355 | 23.79 | 7185.13 | 1254.6 | -344.23 | 1598.83 | Yes | N/A | N/A | 2021-05-18 | 2023-03-28 | 680 | 486 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-01-31 | 1 | 1 | 680 | 486 | 1 | 1 | 681 | 487 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | -152 | -109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 2529.61 | 561.84 | Unknown | 128.24 | 4.46 | 1835.07 | 3981 | 1959.91 | 2529.61 | -569.7 | Yes | N/A | N/A | 2023-03-06 | 2023-05-01 | 57 | 41 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-07-18 | 79 | 57 | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-18 | 2023-08-01 | 15 | 11 | 2023-08-01 | 2023-08-01 | 1 | 1 | 136 | 98 | 16 | 12 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-09 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | -9.29 | -38.78 | Unknown | Unknown | Unknown | 29.49 | 3981 | 1633.45 | -9.29 | 1642.74 | Yes | N/A | N/A | 2025-03-12 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-03-12 | 29 | 21 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-03 | 16 | 12 | 2025-04-03 | 2025-04-03 | 1 | 1 | 8 | 6 | 46 | 34 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-31 | 1392 | 995 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-03 | 2022-08-03 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 17100.85 | 714.76 | Unknown | Unknown | 26.77 | 16359.32 | Unknown | 8491.63 | 17100.85 | -8609.22 | Yes | N/A | N/A | 2022-08-03 | 2023-06-12 | 314 | 224 | 2023-06-12 | 2023-07-20 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-07-19 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-08-23 | 31 | 23 | 2023-08-23 | 2023-08-23 | 1 | 1 | 314 | 224 | 156 | 114 | 470 | 338 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | 86 | 62 | No | 2023-11-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | 2024-09-13 | IOU Designed & Installed | N/A | Yes | 201 | 11.87 | Unknown | Unknown | Unknown | Unknown | 11.87 | 3981 | 895.61 | 11.87 | 883.74 | Yes | N/A | N/A | 2023-11-17 | 2024-06-05 | 202 | 144 | 2024-06-05 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-09-13 | 302 | 216 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-20 | 8 | 6 | 2024-09-20 | 2024-10-01 | 12 | 8 | 504 | 360 | 20 | 14 | 524 | 374 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | 867.22 | 318.65 | Unknown | Unknown | Unknown | 548.57 | Unknown | 424.95 | 867.22 | -442.27 | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-06-26 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-06-27 | 2 | 2 | 2023-06-27 | 2023-06-27 | 1 | 1 | 42 | 30 | 3 | 3 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-27 | 261 | 188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 330.77 | -8.71 | Unknown | Unknown | Unknown | 339.48 | 2781 | 897.19 | 330.77 | 566.42 | Yes | N/A | N/A | 2023-05-24 | 2023-06-09 | 17 | 13 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 17 | 13 | 1 | 1 | 18 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 446.39 | Unknown | Unknown | Unknown | 3.48 | 442.91 | 15924 | 2890.97 | 446.39 | 2444.58 | Yes | N/A | N/A | 2025-03-20 | 2025-04-01 | 13 | 9 | 2025-04-01 | 2025-04-08 | 8 | 6 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-06-09 | 63 | 45 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-06-09 | 2025-06-10 | 2 | 2 | 2025-06-10 | 2025-06-10 | 1 | 1 | 76 | 54 | 11 | 9 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 216 | 155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 4486.22 | 4122.01 | Unknown | 2126.05 | -4020 | 2258.16 | Unknown | 8274.14 | 4486.22 | 3787.92 | Yes | N/A | N/A | 2023-10-10 | 2024-01-09 | 92 | 66 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-01-25 | 4 | 4 | 2024-01-25 | 2024-01-25 | 1 | 1 | 92 | 66 | 5 | 5 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -613 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | IOU Designed & Installed | N/A | No | N/A | -9.6 | -6.96 | Unknown | Unknown | Unknown | -2.64 | 3981 | 748.03 | -9.6 | 757.63 | Yes | N/A | N/A | 2023-02-02 | 2023-02-02 | 1 | 1 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-02-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-05-30 | 118 | 84 | 2023-05-30 | 2023-05-30 | 1 | 1 | 2 | 2 | 119 | 85 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 306 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -5.2 | -21.76 | Unknown | Unknown | Unknown | 16.56 | 3981 | 1174.73 | -5.2 | 1179.93 | Yes | N/A | N/A | 2024-01-03 | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-01-04 | 7 | 5 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2025-03-31 | 453 | 323 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-04 | 5 | 5 | 2025-04-04 | 2025-04-03 | Unknown | Unknown | 453 | 323 | 12 | 10 | 465 | 333 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | -691 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-12 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 618.07 | -11.7 | Unknown | Unknown | Unknown | 629.77 | Unknown | 1741.22 | 618.07 | 1123.15 | Yes | N/A | N/A | 2025-02-10 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-02-12 | 16 | 12 | 2025-02-12 | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-05 | 13 | 9 | 2025-02-12 | 2025-02-13 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-04 | 20 | 14 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2 | 2 | 50 | 36 | 52 | 38 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-11 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 62.21 | -1.25 | Unknown | Unknown | Unknown | 63.46 | Unknown | 1574.75 | 62.21 | 1512.54 | Yes | N/A | N/A | 2025-04-08 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-11 | 18 | 14 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-12 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 32 | 22 | 20 | 16 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-16 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 91.92 | -9.16 | Unknown | Unknown | Unknown | 101.08 | Unknown | 972.44 | 91.92 | 880.52 | Yes | N/A | N/A | 2023-11-13 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-11-16 | 140 | 100 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2023-12-18 | 1 | 1 | 0 | 0 | 141 | 101 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | -340 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 59.24 | Unknown | Unknown | Unknown | Unknown | 59.24 | Unknown | 3221.97 | 59.24 | 3162.73 | Yes | N/A | N/A | 2024-09-09 | 2024-09-19 | 11 | 9 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-10 | 1 | 1 | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 1196.27 | -35.1 | Unknown | Unknown | Unknown | 1231.37 | Unknown | 1171.25 | 1196.27 | -25.02 | Yes | N/A | N/A | 2024-01-10 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2024-01-11 | 92 | 66 | 2024-01-11 | Unknown | Unknown | Unknown | 2024-01-11 | 2024-01-29 | 19 | 13 | 2024-01-11 | 2024-02-07 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 38 | 28 | 2024-03-15 | 2024-03-15 | 1 | 1 | 28 | 20 | 150 | 108 | 178 | 128 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 455 | 455 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | 244 | 175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12802.81 | 4118.75 | Unknown | Unknown | 364.48 | 8319.58 | 7962 | 8479.21 | 12802.81 | -4323.6 | Yes | N/A | N/A | 2023-05-24 | 2023-02-03 | Unknown | Unknown | 2023-02-03 | 2023-08-07 | 186 | 132 | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-07-18 | 8 | 6 | 2023-08-07 | 2024-07-22 | 351 | 251 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-06 | 4 | 2 | 351 | 251 | 198 | 140 | 549 | 391 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-21 | -355 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-23 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 777.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | 2025-04-23 | 2 | 2 | 2025-04-23 | Unknown | Unknown | Unknown | 2025-04-23 | 2025-04-29 | 7 | 5 | 2025-04-23 | 2025-04-24 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-01 | 8 | 6 | 2025-05-01 | 2025-05-01 | 1 | 1 | 3 | 3 | 18 | 14 | 21 | 17 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 230.15 | 230.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-27 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1133.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-20 | 15 | 11 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-30 | 11 | 9 | Unknown | 2025-05-29 | Unknown | Unknown | 2025-05-30 | 2025-06-26 | 28 | 20 | 2025-06-26 | 2025-06-26 | 1 | 1 | 11 | 9 | 44 | 32 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 110 | 79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8489.67 | 4681.5 | Unknown | 3712.18 | -2522 | 2617.99 | 0 | 2521.54 | 8489.67 | -5968.13 | Yes | N/A | N/A | 2023-03-22 | 2023-04-13 | 23 | 17 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-07-01 | 1 | 1 | 23 | 17 | 1 | 1 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 265.05 | 265.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-11-11 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | -4.93 | -20.61 | Unknown | Unknown | Unknown | 15.68 | 3981 | 1534.53 | -4.93 | 1539.46 | Yes | N/A | N/A | 2024-10-14 | 2024-11-08 | 26 | 20 | 2024-11-08 | 2024-11-11 | 4 | 2 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-03-27 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-03 | 8 | 6 | 2025-04-03 | 2025-04-03 | 1 | 1 | 163 | 119 | 13 | 9 | 176 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-02-01 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | -1160.91 | -19.37 | Unknown | Unknown | -1183 | 41.46 | 3981 | 2335.03 | -1160.91 | 3495.94 | Yes | N/A | N/A | 2024-01-30 | 2024-02-01 | 3 | 3 | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-06-12 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-02 | 20 | 14 | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-02 | 2024-07-22 | 21 | 15 | 2024-07-22 | 2024-07-22 | 1 | 1 | 156 | 112 | 23 | 17 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -394 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-06-03 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 36.69 | Unknown | Unknown | Unknown | Unknown | 36.69 | 3981 | 1483.6 | 36.69 | 1446.91 | Yes | N/A | N/A | 2024-03-07 | 2024-06-03 | 89 | 63 | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-08-14 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-10-15 | 63 | 45 | 2024-10-15 | 2024-10-09 | Unknown | Unknown | 162 | 116 | 64 | 46 | 226 | 162 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -96 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-11-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2167.15 | 2667.93 | Unknown | 1591.92 | -3336 | 1243.3 | Unknown | 3336.21 | 2167.15 | 1169.06 | Yes | N/A | N/A | 2023-10-23 | 2023-11-07 | 16 | 12 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-29 | -362 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 653.12 | -26.19 | Unknown | Unknown | Unknown | 679.31 | Unknown | 929.55 | 653.12 | 276.43 | Yes | N/A | N/A | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-09 | 11 | 9 | 2024-04-29 | 2024-05-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-07 | 7 | 5 | 2024-05-07 | 2024-05-02 | Unknown | Unknown | 4 | 4 | 19 | 15 | 23 | 19 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2025-03-24 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | -953.04 | -18.42 | Unknown | Unknown | -1870 | 935.38 | Unknown | 1723.1 | -953.04 | 2676.14 | Yes | N/A | N/A | 2024-11-19 | 2025-03-24 | 126 | 90 | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-05-12 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-13 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-05-22 | 10 | 8 | 2025-05-22 | 2025-05-20 | Unknown | Unknown | 178 | 128 | 11 | 9 | 189 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -634 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-09 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 4.63 | -5.62 | Unknown | Unknown | Unknown | 10.25 | Unknown | 287.46 | 4.63 | 282.83 | Yes | N/A | N/A | 2024-02-08 | 2024-02-09 | 2 | 2 | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-20 | 12 | 8 | 2024-02-20 | 2024-02-20 | 1 | 1 | 3 | 3 | 14 | 10 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 1366.87 | 380.61 | Unknown | Unknown | Unknown | 986.26 | 3981 | 1683.03 | 1366.87 | 316.16 | Yes | N/A | N/A | 2024-10-17 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-10-17 | 74 | 54 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-12-16 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-12-16 | 2024-12-16 | 1 | 1 | 61 | 43 | 76 | 56 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 33104 | 33104 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-07 | 151 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-22 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | -476.94 | 225.77 | Unknown | 40.33 | -1491 | 747.96 | Unknown | 1281.5 | -476.94 | 1758.44 | Yes | N/A | N/A | 2025-01-07 | 2025-01-21 | 15 | 11 | 2025-01-21 | 2025-01-23 | 3 | 3 | 2025-01-23 | 2025-03-31 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-03 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-07 | 5 | 3 | 2025-04-07 | 2025-04-07 | 1 | 1 | 87 | 63 | 9 | 7 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1199.21 | -0.94 | Unknown | Unknown | 7.43 | 1192.72 | 3981 | 2948.53 | 1199.21 | 1749.32 | Yes | N/A | N/A | 2023-09-29 | 2024-10-18 | 386 | 276 | 2024-10-18 | 2025-01-08 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-19 | 33 | 23 | 2025-01-08 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-01-30 | Unknown | Unknown | 386 | 276 | 116 | 82 | 502 | 358 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | -626 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-06-08 | IOU Designed & Installed | N/A | No | N/A | 14.78 | -12.24 | Unknown | Unknown | Unknown | 27.02 | 3981 | 1129.27 | 14.78 | 1114.49 | Yes | N/A | N/A | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-22 | 23 | 17 | 2024-04-29 | 2024-06-08 | 41 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-06-08 | 2024-07-25 | 48 | 34 | 2024-07-25 | 2024-07-25 | 1 | 1 | 42 | 31 | 73 | 53 | 115 | 84 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2024-10-26 | IOU Designed & Installed | N/A | No | N/A | -1392.38 | 618.98 | Unknown | 265.86 | -2721 | 443.78 | Unknown | 2721 | -1392.38 | 4113.38 | Yes | N/A | N/A | 2024-08-16 | 2024-10-01 | 47 | 33 | 2024-10-01 | 2024-10-15 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-26 | 2024-10-29 | 4 | 2 | 2024-10-29 | 2024-10-29 | 1 | 1 | 47 | 33 | 20 | 14 | 67 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | -341 | -244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 4.72 | -3.64 | Unknown | Unknown | Unknown | 8.36 | Unknown | 571.46 | 4.72 | 566.74 | Yes | N/A | N/A | 2024-06-27 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-06-27 | 2 | 2 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-12 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-17 | 6 | 4 | 2024-07-17 | 2024-07-17 | 1 | 1 | 16 | 12 | 9 | 7 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-14 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | -5.87 | -5.31 | Unknown | Unknown | Unknown | -0.56 | 3981 | 153.83 | -5.87 | 159.7 | Yes | N/A | N/A | 2023-08-31 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2023-09-15 | 113 | 81 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-12-19 | 96 | 68 | Unknown | 2023-12-07 | Unknown | Unknown | 2023-12-19 | 2023-12-20 | 2 | 2 | 2023-12-20 | 2023-12-20 | 1 | 1 | 96 | 68 | 116 | 84 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 2392.79 | -52.99 | Unknown | Unknown | 125.11 | 2320.67 | 0 | 939.41 | 2392.79 | -1453.38 | Yes | N/A | N/A | 2024-04-24 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-24 | 59 | 43 | 2024-04-24 | 2024-11-22 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-23 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2025-03-06 | 288 | 206 | 2025-03-06 | 2025-03-06 | 1 | 1 | 243 | 175 | 348 | 250 | 591 | 425 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-26 | 148 | 107 | No | 2024-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | Yes | 127 | 412.42 | -9.27 | Unknown | Unknown | Unknown | 421.69 | 3941 | 828.92 | 412.42 | 416.5 | Yes | N/A | N/A | 2024-02-15 | 2024-06-21 | 128 | 92 | 2024-06-21 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-07-23 | 8 | 6 | 128 | 92 | 8 | 6 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-19 | -102 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 741.11 | 205.83 | Unknown | 117.92 | 4.46 | 412.9 | 3981 | 2105.74 | 741.11 | 1364.63 | Yes | N/A | N/A | 2023-08-18 | 2023-10-05 | 49 | 35 | 2023-10-05 | 2023-10-16 | 12 | 8 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-02-07 | 1 | 1 | 49 | 35 | 13 | 9 | 62 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 21.4 | 21.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -506 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | -110.49 | Unknown | Unknown | Unknown | -119 | 8.51 | Unknown | 3336.08 | -110.49 | 3446.57 | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2025-02-13 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-19 | 7 | 5 | 2025-02-19 | 2025-02-27 | 9 | 7 | 177 | 127 | 17 | 13 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 118.05 | 118.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-02 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-23 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 641.23 | -12.92 | Unknown | Unknown | Unknown | 654.15 | 3981 | 1413.11 | 641.23 | 771.88 | Yes | N/A | N/A | 2024-08-16 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-01 | 9 | 7 | 2024-08-26 | 2024-09-11 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-08 | 28 | 20 | 2024-10-08 | 2024-10-09 | 2 | 2 | 17 | 13 | 39 | 29 | 56 | 42 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 25.89 | Unknown | Unknown | Unknown | Unknown | 25.89 | Unknown | 1580.45 | 25.89 | 1554.56 | Yes | N/A | N/A | 2024-11-26 | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2024-11-26 | 33 | 23 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-02-05 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-10 | 34 | 24 | 2025-03-10 | 2025-03-10 | 1 | 1 | 72 | 52 | 68 | 48 | 140 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -522 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.56 | -10.48 | Unknown | Unknown | Unknown | 6.92 | 3981 | 723.25 | -3.56 | 726.81 | Yes | N/A | N/A | 2023-01-31 | 2023-02-09 | 10 | 8 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 10 | 8 | 1 | 1 | 11 | 9 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-26 | -334 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 744.13 | Unknown | Unknown | Unknown | Unknown | 744.13 | 3981 | 1239.55 | 744.13 | 495.42 | Yes | N/A | N/A | 2024-09-03 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-09-04 | 7 | 5 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-20 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-09-26 | 7 | 5 | 2024-09-26 | 2024-09-26 | 1 | 1 | 17 | 13 | 15 | 11 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 386 | 277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 56.28 | Unknown | Unknown | Unknown | Unknown | 56.28 | 3981 | 1143.65 | 56.28 | 1087.37 | Yes | N/A | N/A | 2022-11-14 | 2023-07-24 | 253 | 181 | 2023-07-24 | 2023-08-14 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2024-08-26 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | 253 | 181 | 53 | 39 | 306 | 220 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-23 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 8.6 | Unknown | Unknown | Unknown | Unknown | 8.6 | Unknown | 1476.63 | 8.6 | 1468.03 | Yes | N/A | N/A | 2024-08-21 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-09-23 | 46 | 32 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-12-31 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-07 | 8 | 6 | 2025-01-07 | 2025-01-03 | Unknown | Unknown | 100 | 72 | 54 | 38 | 154 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -374 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-01-08 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 385.54 | -18.21 | Unknown | Unknown | Unknown | 403.75 | 3981 | 916.41 | 385.54 | 530.87 | Yes | N/A | N/A | 2023-10-16 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2024-01-08 | 179 | 127 | 2024-01-08 | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-16 | 7 | 5 | 2024-01-08 | 2024-02-01 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-06-05 | 126 | 90 | 2024-06-05 | 2024-06-05 | 1 | 1 | 25 | 19 | 313 | 223 | 338 | 242 | Steps 2,3,5,6,7 | 129 | 93 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -513 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-03-08 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | -11.99 | -9.72 | Unknown | Unknown | Unknown | -2.27 | 3981 | 1000.64 | -11.99 | 1012.63 | Yes | N/A | N/A | 2024-01-25 | 2024-03-04 | 40 | 28 | 2024-03-04 | 2024-03-08 | 5 | 5 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-05-30 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-13 | 15 | 11 | 2024-06-13 | 2024-06-13 | 1 | 1 | 124 | 88 | 21 | 17 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-18 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-28 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | 33.04 | -4.56 | Unknown | Unknown | -288 | 325.6 | Unknown | 288.14 | 33.04 | 255.1 | Yes | N/A | N/A | 2023-12-20 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2024-01-09 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-03-07 | 58 | 42 | 2024-03-07 | 2024-03-07 | 1 | 1 | 0 | 0 | 130 | 94 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | 4722 | 4722 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-07-20 | 21 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.98 | -8.81 | Unknown | Unknown | Unknown | 5.83 | Unknown | 216.32 | -2.98 | 219.3 | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | 2023-04-24 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1 | 1 | 1 | 1 | 29 | 21 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-15 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | 1000.28 | -6.36 | Unknown | Unknown | 43.39 | 963.25 | 3981 | 988.3 | 1000.28 | -11.98 | Yes | N/A | N/A | 2023-11-13 | 2023-11-16 | 4 | 4 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-02-16 | 93 | 67 | Unknown | 2024-01-24 | Unknown | Unknown | 2024-02-16 | 2024-03-14 | 28 | 20 | 2024-03-14 | 2024-03-06 | Unknown | Unknown | 97 | 71 | 29 | 21 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 913.5 | Unknown | Unknown | Unknown | Unknown | 913.5 | 3981 | 1180.79 | 913.5 | 267.29 | Yes | N/A | N/A | 2025-01-10 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2025-01-14 | 16 | 12 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-03-06 | 52 | 38 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-06 | 2025-03-26 | 21 | 15 | 2025-03-26 | 2025-03-26 | 1 | 1 | 52 | 38 | 38 | 28 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -492 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-10 | 2023-06-07 | IOU Designed & Installed | N/A | No | N/A | 635.43 | 255.6 | Unknown | Unknown | Unknown | 379.83 | 3981 | 1333.96 | 635.43 | 698.53 | Yes | N/A | N/A | 2023-02-09 | 2023-02-09 | 1 | 1 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-06-07 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-06-08 | 2 | 2 | 2023-06-08 | 2023-06-08 | 1 | 1 | 119 | 85 | 3 | 3 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 61 | 44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | Unknown | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 30.12 | Unknown | Unknown | Unknown | Unknown | 30.12 | 3981 | 840.87 | 30.12 | 810.75 | Yes | N/A | N/A | 2023-09-07 | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2023-09-07 | 94 | 68 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2024-07-19 | 317 | 227 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-01 | 14 | 10 | 2024-08-01 | 2024-08-01 | 1 | 1 | 317 | 227 | 109 | 79 | 426 | 306 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2434.4 | Unknown | Unknown | Unknown | Unknown | 2434.4 | 3981 | 790.08 | 2434.4 | -1644.32 | Yes | N/A | N/A | 2024-06-05 | 2024-07-08 | 34 | 24 | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-08-26 | 1 | 1 | 34 | 24 | 2 | 2 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 1289.96 | Unknown | Unknown | Unknown | 6.08 | 1283.88 | Unknown | 1441.31 | 1289.96 | 151.35 | Yes | N/A | N/A | 2024-09-19 | 2024-11-06 | 49 | 35 | 2024-11-06 | 2024-11-11 | 6 | 4 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-01-07 | 58 | 42 | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-07 | 2025-01-16 | 10 | 8 | 2025-01-16 | 2025-01-15 | Unknown | Unknown | 107 | 77 | 16 | 12 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -221 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | -336.37 | 862.3 | Unknown | 106.33 | -1905 | 600 | Unknown | 1904.61 | -336.37 | 2240.98 | Yes | N/A | N/A | 2024-04-04 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | -186 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 2364.3 | Unknown | Unknown | Unknown | Unknown | 2364.3 | Unknown | 539.93 | 2364.3 | -1824.37 | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-10 | 8 | 6 | 2023-10-10 | 2023-10-10 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-08-05 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 5.36 | Unknown | Unknown | Unknown | Unknown | 5.36 | Unknown | 192.95 | 5.36 | 187.59 | Yes | N/A | N/A | 2024-07-15 | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2024-08-09 | 60 | 44 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-27 | 12 | 8 | 2024-08-27 | 2024-08-27 | 1 | 1 | 8 | 6 | 73 | 53 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | San Diego PA10 PH4 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 577 | 414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 75550.1 | 8929.21 | Unknown | Unknown | 4389.57 | 62231.32 | 0 | 29604.38 | 75550.1 | -45945.72 | Yes | N/A | N/A | 2022-04-27 | 2023-07-17 | 447 | 319 | 2023-07-17 | 2023-10-16 | 92 | 66 | 2023-07-27 | 2024-04-08 | 241 | 172 | 2023-10-02 | 2023-10-11 | 10 | 8 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-08 | 335 | 239 | 2024-10-09 | 2024-10-17 | 9 | 7 | 2024-10-17 | 2024-10-17 | 1 | 1 | 688 | 491 | 447 | 321 | 1135 | 812 | Steps 2,3,5,6,7 | 270 | 192 | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | 480 | 480 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 525 | 376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-28 | 2023-05-19 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 82619.39 | 5151.88 | Unknown | Unknown | 791.25 | 76676.26 | 0 | 36667.65 | 82619.39 | -45951.74 | Yes | N/A | N/A | 2022-10-28 | 2023-05-18 | 203 | 145 | 2023-05-18 | 2024-06-20 | 400 | 286 | 2023-08-15 | 2024-03-19 | 4 | 4 | 2023-08-11 | 2024-07-01 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-12-20 | 148 | 106 | 2024-07-02 | 2025-02-28 | 242 | 174 | 2025-02-28 | 2025-02-28 | 1 | 1 | 207 | 149 | 810 | 580 | 1017 | 729 | Steps 2,3,5,6,7 | 702 | 502 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-29 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 1000.17 | Unknown | Unknown | Unknown | Unknown | 1000.17 | 3981 | 890.41 | 1000.17 | -109.76 | Yes | N/A | N/A | 2024-03-28 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-03-28 | 3 | 3 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-09-24 | 180 | 128 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-24 | 2024-10-04 | 11 | 9 | 2024-10-04 | 2024-10-04 | 1 | 1 | 180 | 128 | 15 | 13 | 195 | 141 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -409 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 23.58 | Unknown | Unknown | Unknown | Unknown | 23.58 | 3981 | 716.26 | 23.58 | 692.68 | Yes | N/A | N/A | 2024-04-04 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-04-04 | 93 | 67 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-10-31 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 7 | 5 | 2024-11-06 | 2024-11-06 | 1 | 1 | 211 | 151 | 101 | 73 | 312 | 224 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-09-18 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 4401.63 | 999.04 | Unknown | 447.03 | Unknown | 2955.56 | 7962 | 1571.75 | 4401.63 | -2829.88 | Yes | N/A | N/A | 2024-07-09 | 2024-09-18 | 72 | 52 | 2024-09-18 | 2024-12-26 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | 2025-04-04 | 1 | 1 | 72 | 52 | 102 | 74 | 174 | 126 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-22 | 178 | 129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 182.22 | Unknown | Unknown | Unknown | Unknown | 182.22 | 3981 | 1287.27 | 182.22 | 1105.05 | Yes | N/A | N/A | 2023-03-23 | 2024-08-06 | 503 | 359 | 2024-08-06 | 2024-08-09 | 4 | 4 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-17 | Unknown | Unknown | 503 | 359 | 4 | 4 | 507 | 363 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | 92 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | Unknown | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 508.15 | -19.95 | Unknown | Unknown | Unknown | 528.1 | 3885 | 688.59 | 508.15 | 180.44 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2024-02-07 | 344 | 246 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-16 | 10 | 8 | 2024-02-16 | 2024-02-15 | Unknown | Unknown | 345 | 247 | 10 | 8 | 355 | 255 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | -149 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 0.29 | -4.45 | Unknown | Unknown | Unknown | 4.74 | Unknown | 206.56 | 0.29 | 206.27 | Yes | N/A | N/A | 2023-12-26 | 2023-06-04 | Unknown | Unknown | 2023-06-04 | 2023-12-26 | 206 | 147 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2023-12-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2023-12-29 | 3 | 3 | 2023-12-29 | 2023-12-29 | 1 | 1 | 2 | 2 | 210 | 151 | 212 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 217.57 | -2.88 | Unknown | Unknown | Unknown | 220.45 | Unknown | 208.79 | 217.57 | -8.78 | Yes | N/A | N/A | 2023-02-14 | 2023-02-16 | 3 | 3 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-06-19 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3869.83 | 3798.63 | Unknown | 2602.67 | -4314 | 1782.53 | Unknown | 4314.12 | 3869.83 | 444.29 | Yes | N/A | N/A | 2023-04-20 | 2023-06-06 | 48 | 34 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2023-12-21 | 1 | 1 | 48 | 34 | 1 | 1 | 49 | 35 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-11 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2023-07-11 | IOU Designed & Installed | N/A | No | N/A | -3.7 | -7.15 | Unknown | Unknown | Unknown | 3.45 | Unknown | 748.64 | -3.7 | 752.34 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-07-11 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-07-31 | 21 | 15 | 2023-07-31 | 2023-07-31 | 1 | 1 | 71 | 51 | 22 | 16 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 309 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 80462.69 | 13017.18 | Unknown | Unknown | -7967.96 | 75413.47 | 0 | 63933.5 | 80462.69 | -16529.19 | Yes | N/A | N/A | 2024-07-01 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2025-03-18 | 314 | 224 | 2025-03-07 | 2025-03-14 | 8 | 6 | 2024-09-09 | 2025-03-25 | 51 | 37 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-04-02 | 2025-05-06 | 35 | 25 | 2025-05-06 | 2025-05-06 | 1 | 1 | 8 | 6 | 401 | 287 | 409 | 293 | Steps 2,3,5,6,7 | 204 | 146 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-19 | -158 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | 7813.67 | Unknown | Unknown | Unknown | Unknown | 7813.67 | Unknown | 642.58 | 7813.67 | -7171.09 | Yes | N/A | N/A | 2023-04-28 | 2023-05-03 | 6 | 4 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-09-07 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-15 | 9 | 7 | 2023-09-15 | 2023-09-14 | Unknown | Unknown | 134 | 96 | 9 | 7 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 27.18 | Unknown | Unknown | Unknown | Unknown | 27.18 | Unknown | 1475.87 | 27.18 | 1448.69 | Yes | N/A | N/A | 2024-10-09 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-10-09 | 29 | 21 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2025-01-06 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-14 | 9 | 7 | 2025-01-14 | 2025-01-14 | 1 | 1 | 90 | 64 | 39 | 29 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | -548 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | -148.27 | -11.78 | Unknown | Unknown | -698.07 | 561.58 | Unknown | 701.79 | -148.27 | 850.06 | Yes | N/A | N/A | 2023-11-15 | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-11-27 | 67 | 47 | 2023-11-27 | 2024-01-08 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-02-16 | 40 | 30 | Unknown | 2024-02-06 | Unknown | Unknown | 2024-02-16 | 2024-03-15 | 29 | 21 | 2024-03-15 | 2024-03-15 | 1 | 1 | 83 | 61 | 97 | 69 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-03 | -177 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 702.61 | -13.1 | Unknown | Unknown | Unknown | 715.71 | 3981 | 6131.02 | 702.61 | 5428.41 | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-03-06 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-11 | 6 | 4 | 2025-03-11 | 2025-03-10 | Unknown | Unknown | 129 | 93 | 7 | 5 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-02 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-07-16 | IOU Designed & Installed | N/A | No | N/A | 1544.16 | 538.88 | Unknown | 79.26 | Unknown | 926.02 | 3981 | 942.77 | 1544.16 | -601.39 | Yes | N/A | N/A | 2023-06-13 | 2023-06-14 | 2 | 2 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-07-16 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-07-16 | 2023-07-19 | 4 | 3 | 2023-07-19 | 2023-07-19 | 1 | 1 | 35 | 25 | 5 | 4 | 40 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 382 | 275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2024-01-31 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 26563.87 | 803.15 | Unknown | Unknown | 156.9 | 25603.82 | 308705 | 27600.72 | 26563.87 | 1036.85 | Yes | N/A | N/A | 2023-06-23 | 2023-12-01 | 162 | 116 | 2023-12-01 | 2024-08-06 | 250 | 178 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-06-17 | 2024-08-13 | 38 | 28 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-13 | 36 | 26 | 2024-09-27 | 2025-01-17 | 113 | 81 | 2025-01-17 | 2025-01-17 | 1 | 1 | 163 | 117 | 438 | 314 | 601 | 431 | Steps 2,3,5,6,7 | 57 | 41 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -681 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-20 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 50.02 | Unknown | Unknown | Unknown | Unknown | 50.02 | 3981 | 1521.7 | 50.02 | 1471.68 | Yes | N/A | N/A | 2024-09-19 | 2024-09-20 | 2 | 2 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-02 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-17 | 16 | 12 | 2024-10-17 | 2024-10-17 | 1 | 1 | 15 | 11 | 18 | 14 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | -46 | -34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-22 | 2023-07-22 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | -9.24 | -8.23 | Unknown | Unknown | Unknown | -1.01 | 3961 | 158.14 | -9.24 | 167.38 | Yes | N/A | N/A | 2023-07-22 | 2023-07-25 | 4 | 2 | 2023-07-25 | 2023-10-27 | 95 | 69 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-12-14 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-01-16 | 34 | 24 | 2024-01-16 | 2024-01-16 | 1 | 1 | 53 | 37 | 130 | 94 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 59340 | 59340 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-01 | 286 | 205 | No | 2022-10-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | Yes | 311 | 585.22 | -11.09 | Unknown | Unknown | Unknown | 596.31 | 15924 | 501.37 | 585.22 | -83.85 | Yes | N/A | N/A | 2022-10-04 | 2023-08-10 | 311 | 223 | 2023-08-10 | 2024-08-06 | 363 | 259 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2024-02-27 | 8 | 4 | 2024-08-06 | 2024-08-05 | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-13 | Unknown | Unknown | 311 | 223 | 371 | 263 | 682 | 486 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | 251 | 180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 929.04 | -17.67 | Unknown | Unknown | Unknown | 946.71 | 7962 | 1002.29 | 929.04 | 73.25 | Yes | N/A | N/A | 2023-10-26 | 2024-03-14 | 141 | 101 | 2024-03-14 | 2024-08-22 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-08 | 32 | 22 | 2024-08-22 | 2024-10-07 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-08 | 1 | 1 | 188 | 134 | 195 | 139 | 383 | 273 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | 1413.71 | 438.03 | Unknown | Unknown | 4.14 | 971.54 | 3981 | 1017.88 | 1413.71 | -395.83 | Yes | N/A | N/A | 2023-09-27 | 2023-07-03 | Unknown | Unknown | 2023-07-03 | 2023-10-19 | 109 | 79 | 2023-10-19 | 2024-05-06 | 201 | 143 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-03-28 | 162 | 116 | Unknown | 2024-01-31 | Unknown | Unknown | 2024-03-28 | 2024-05-23 | 57 | 41 | 2024-05-23 | 2024-05-23 | 1 | 1 | 363 | 259 | 167 | 121 | 530 | 380 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 499.24 | -10.96 | Unknown | Unknown | Unknown | 510.2 | 3981 | 915.91 | 499.24 | 416.67 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-01-05 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-10 | 6 | 4 | 2024-01-10 | 2024-01-10 | 1 | 1 | 59 | 43 | 8 | 6 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 1149.14 | 528.11 | Unknown | 243.48 | Unknown | 377.55 | Unknown | 916.71 | 1149.14 | -232.43 | Yes | N/A | N/A | 2023-11-29 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-11-29 | 51 | 37 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-12 | 6 | 4 | 2023-12-12 | 2023-12-12 | 1 | 1 | 9 | 7 | 58 | 42 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-16 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 7299.81 | Unknown | Unknown | Unknown | Unknown | 7299.81 | Unknown | 262.61 | 7299.81 | -7037.2 | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | 2024-06-17 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-09-24 | 96 | 68 | 2024-09-24 | 2024-09-24 | 1 | 1 | 1 | 1 | 131 | 93 | 132 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-05 | -203 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.35 | -8.94 | Unknown | Unknown | Unknown | -3.41 | Unknown | 363.72 | -12.35 | 376.07 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-05-16 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-07 | -463 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-30 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 7401.33 | 1403.44 | Unknown | 167.44 | -1540 | 7370.45 | Unknown | 1567.22 | 7401.33 | -5834.11 | Yes | N/A | N/A | 2024-07-26 | 2024-07-29 | 4 | 2 | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2025-01-23 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-02-26 | 59 | 43 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-26 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-03-31 | 60 | 42 | 241 | 173 | 62 | 44 | 303 | 217 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 2518 | 2518 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-03-15 | -590 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 19.78 | -11.76 | Unknown | Unknown | Unknown | 31.54 | Unknown | 443.54 | 19.78 | 423.76 | Yes | N/A | N/A | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-21 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-08-02 | 43 | 31 | 2024-08-02 | 2024-08-02 | 1 | 1 | 23 | 17 | 45 | 33 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2056.16 | 34.58 | Unknown | Unknown | -2130 | 39.26 | 0 | 3506.96 | -2056.16 | 5563.12 | Yes | N/A | N/A | 2024-05-07 | 2024-05-08 | 2 | 2 | 2024-05-08 | 2025-02-24 | 293 | 209 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-09 | 27 | 19 | 2025-02-24 | 2025-05-22 | 88 | 64 | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-24 | 2025-06-19 | Unknown | Unknown | 90 | 66 | 320 | 228 | 410 | 294 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-19 | -262 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-09-27 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1819.46 | 472.95 | Unknown | 48.3 | Unknown | 1298.21 | 3981 | 1594.44 | 1819.46 | -225.02 | Yes | N/A | N/A | 2023-12-05 | 2024-09-17 | 288 | 206 | 2024-09-17 | 2024-09-27 | 11 | 9 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-29 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-10-30 | 2 | 2 | 2024-10-30 | 2024-10-30 | 1 | 1 | 321 | 229 | 14 | 12 | 335 | 241 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 32.23 | Unknown | Unknown | Unknown | Unknown | 32.23 | 3981 | 1560.56 | 32.23 | 1528.33 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-27 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-13 | 18 | 14 | 2025-02-13 | 2025-02-13 | 1 | 1 | 20 | 14 | 20 | 16 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | -194 | -139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-02 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 46.64 | -6.13 | Unknown | Unknown | 0.48 | 52.29 | 3981 | 787.91 | 46.64 | 741.27 | Yes | N/A | N/A | 2023-11-01 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-11-02 | 57 | 41 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-07 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-02-13 | 99 | 71 | 2024-02-13 | 2024-02-13 | 1 | 1 | 6 | 4 | 157 | 113 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-21 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | Unknown | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 18.56 | -14.31 | Unknown | Unknown | Unknown | 32.87 | 3981 | 928.14 | 18.56 | 909.58 | Yes | N/A | N/A | 2024-04-26 | 2024-04-26 | 1 | 1 | 2024-04-26 | 2024-04-26 | 1 | 1 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-06-28 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-09 | 12 | 8 | 2024-07-09 | 2024-07-09 | 1 | 1 | 65 | 47 | 14 | 10 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-10 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-11-18 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1852.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-11-18 | 172 | 122 | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-05-02 | 166 | 120 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-22 | 21 | 15 | 2025-05-22 | 2025-05-20 | Unknown | Unknown | 338 | 242 | 22 | 16 | 360 | 258 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 5.8 | Unknown | Unknown | Unknown | Unknown | 5.8 | Unknown | 192.95 | 5.8 | 187.15 | Yes | N/A | N/A | 2024-07-03 | 2024-07-29 | 27 | 19 | 2024-07-29 | 2024-08-01 | 4 | 4 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-10-23 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-20 | 29 | 21 | 2024-11-20 | 2024-11-20 | 1 | 1 | 111 | 79 | 34 | 26 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 375.5 | 375.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | -9 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-10 | 2023-04-12 | IOU Designed & Installed | N/A | No | N/A | 4867.15 | -20.79 | Unknown | Unknown | Unknown | 4887.94 | Unknown | 4118.64 | 4867.15 | -748.51 | Yes | N/A | N/A | 2023-02-08 | 2023-02-10 | 3 | 3 | 2023-02-10 | 2023-03-07 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2023-06-20 | 70 | 50 | 2023-06-20 | 2023-06-20 | 1 | 1 | 3 | 3 | 97 | 69 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2318.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-04-10 | 10 | 8 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-06-26 | 78 | 56 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-26 | 2025-06-30 | 5 | 3 | 2025-06-30 | 2025-06-30 | 1 | 1 | 78 | 56 | 16 | 12 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 125 | 125 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 318 | 228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 1647.21 | -54.23 | Unknown | Unknown | 6.23 | 1695.21 | 3981 | 841.99 | 1647.21 | -805.22 | Yes | N/A | N/A | 2023-08-15 | 2023-06-08 | Unknown | Unknown | 2023-06-08 | 2023-08-18 | 72 | 52 | 2023-08-18 | 2024-06-03 | 5 | 3 | 2024-05-13 | 2024-06-06 | 22 | 18 | 2023-08-18 | 2024-06-03 | 291 | 207 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-25 | 23 | 17 | 2024-06-25 | 2024-08-14 | 51 | 37 | 296 | 210 | 168 | 124 | 464 | 334 | Steps 2,3,5,6,7 | 314 | 224 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | San Diego | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | 57 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-09 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 10186.53 | Unknown | Unknown | Unknown | -5069.79 | 15256.32 | Unknown | 3506.32 | 10186.53 | -6680.21 | Yes | N/A | N/A | 2024-07-09 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-08-15 | 71 | 51 | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-08-06 | 2024-08-28 | 23 | 17 | 2024-08-26 | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-09 | 15 | 11 | 2024-09-23 | 2024-10-17 | 25 | 19 | 2024-10-17 | 2024-10-17 | 1 | 1 | 1 | 1 | 135 | 99 | 136 | 100 | Steps 2,3,5,6,7 | 26 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-13 | 2024-10-13 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 814.9 | -16.08 | Unknown | Unknown | Unknown | 830.98 | 3981 | 2086.11 | 814.9 | 1271.21 | Yes | N/A | N/A | 2024-10-13 | 2024-10-16 | 4 | 3 | 2024-10-16 | 2024-10-18 | 3 | 3 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-01-09 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-01-28 | 2025-01-28 | 1 | 1 | 88 | 63 | 24 | 18 | 112 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -619 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-29 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 774.56 | 240.29 | Unknown | Unknown | Unknown | 534.27 | 3981 | 1290.4 | 774.56 | 515.84 | Yes | N/A | N/A | 2024-05-17 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-29 | 71 | 51 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-07-01 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-03 | 3 | 3 | 2024-07-03 | 2024-07-03 | 1 | 1 | 34 | 24 | 75 | 55 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 374.34 | 191.07 | Unknown | 65.08 | Unknown | 118.19 | Unknown | 158.14 | 374.34 | -216.2 | Yes | N/A | N/A | 2023-10-09 | 2023-11-13 | 36 | 26 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-11 | 14 | 10 | 2023-12-11 | 2023-12-11 | 1 | 1 | 52 | 38 | 16 | 12 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | ENCINITAS | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 511 | 366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-10-02 | 2024-03-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -70.76 | Unknown | Unknown | Unknown | -2486.59 | 2415.83 | 382743 | 6000.32 | -70.76 | 6071.08 | Yes | N/A | N/A | 2023-04-07 | 2023-06-29 | 84 | 60 | 2023-06-29 | 2023-12-05 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-02-27 | 1 | 1 | 2023-12-05 | 2024-03-13 | 100 | 72 | Unknown | 2024-03-18 | Unknown | Unknown | 2024-03-22 | 2024-03-28 | 7 | 5 | 2024-03-28 | 2024-03-26 | Unknown | Unknown | 184 | 132 | 168 | 120 | 352 | 252 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2024-01-08 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 1985.1 | -48.98 | Unknown | Unknown | Unknown | 2034.08 | Unknown | 1079.83 | 1985.1 | -905.27 | Yes | N/A | N/A | 2023-06-05 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2024-01-08 | 270 | 192 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-18 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | 2024-01-18 | 1 | 1 | 11 | 9 | 272 | 194 | 283 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-11-27 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 720.7 | -24.87 | Unknown | Unknown | Unknown | 745.57 | 3981 | 1011.48 | 720.7 | 290.78 | Yes | N/A | N/A | 2023-10-27 | 2023-11-27 | 32 | 22 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-01-02 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-24 | 23 | 17 | 2024-01-24 | 2024-01-24 | 1 | 1 | 69 | 49 | 25 | 19 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 265 | 265 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-15 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-12 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | -2087.29 | -2.19 | Unknown | Unknown | -2249 | 163.9 | Unknown | 2002.47 | -2087.29 | 4089.76 | Yes | N/A | N/A | 2024-08-09 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2025-03-06 | 214 | 154 | 2025-03-06 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-11-12 | 75 | 53 | Unknown | 2024-11-11 | Unknown | Unknown | 2024-11-12 | 2024-11-19 | 8 | 6 | 2024-11-19 | 2024-11-18 | Unknown | Unknown | 75 | 53 | 222 | 160 | 297 | 213 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-01 | 1006 | 720 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | 2024-07-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 6109.07 | 1820.36 | Unknown | Unknown | -20264.13 | 24552.84 | 2875.23 | 17258.69 | 6109.07 | 11149.62 | Yes | N/A | N/A | 2022-11-14 | 2023-05-15 | 183 | 131 | 2023-05-15 | 2023-06-28 | 45 | 33 | 2023-05-15 | 2023-05-22 | 8 | 6 | 2023-05-16 | 2023-07-27 | 41 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-06-25 | 58 | 42 | 2024-07-15 | 2024-08-16 | 33 | 25 | 2024-08-16 | 2024-08-03 | Unknown | Unknown | 191 | 137 | 177 | 131 | 368 | 268 | Steps 2,3,5,6,7 | 50 | 36 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 7.64 | Unknown | Unknown | Unknown | Unknown | 7.64 | 3981 | 197.01 | 7.64 | 189.37 | Yes | N/A | N/A | 2024-09-30 | 2024-10-04 | 5 | 5 | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-11-26 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-05 | 10 | 8 | 2024-12-05 | 2024-12-05 | 1 | 1 | 59 | 43 | 12 | 10 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-20 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 696.22 | -20.95 | Unknown | Unknown | Unknown | 717.17 | 3981 | 805.75 | 696.22 | 109.53 | Yes | N/A | N/A | 2023-06-13 | 2023-06-20 | 8 | 6 | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | Unknown | Unknown | Unknown | 2023-06-20 | 2023-06-21 | 2 | 2 | 2023-06-23 | 2023-07-27 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-08 | 13 | 9 | 2023-08-08 | 2023-08-08 | 1 | 1 | 43 | 31 | 17 | 13 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10.02 | 10.02 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -528 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-10-24 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 1764.7 | -34.83 | Unknown | Unknown | Unknown | 1799.53 | Unknown | 1528.79 | 1764.7 | -235.91 | Yes | N/A | N/A | 2024-08-06 | 2024-10-23 | 79 | 57 | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-25 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-07 | 44 | 32 | 2025-01-07 | 2025-01-07 | 1 | 1 | 112 | 80 | 47 | 35 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 2132.37 | 509.4 | Unknown | 215.74 | Unknown | 1407.23 | Unknown | 1447.61 | 2132.37 | -684.76 | Yes | N/A | N/A | 2024-09-20 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-20 | 31 | 23 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-30 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-19 | 21 | 15 | 2024-11-19 | 2024-11-19 | 1 | 1 | 41 | 29 | 53 | 39 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 126 | 126 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 571.25 | -12.13 | Unknown | Unknown | 5.49 | 577.89 | 3981 | 986.26 | 571.25 | 415.01 | Yes | N/A | N/A | 2023-06-29 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-29 | 8 | 6 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-10-04 | 98 | 70 | Unknown | 2023-09-25 | Unknown | Unknown | 2023-10-04 | 2023-10-17 | 14 | 10 | 2023-10-17 | 2023-10-17 | 1 | 1 | 98 | 70 | 23 | 17 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 407.15 | 407.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | -480 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | 2023-01-31 | 2023-05-31 | IOU Designed & Installed | N/A | No | N/A | 1331.69 | 430.86 | Unknown | 147.7 | Unknown | 753.13 | Unknown | 690.94 | 1331.69 | -640.75 | Yes | N/A | N/A | 2022-12-28 | 2023-01-31 | 35 | 25 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-05-31 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-06 | 7 | 5 | 2023-06-06 | 2023-06-06 | 1 | 1 | 156 | 112 | 8 | 6 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-04-03 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | -8.54 | -8.57 | Unknown | Unknown | Unknown | 0.03 | Unknown | 163.83 | -8.54 | 172.37 | Yes | N/A | N/A | 2024-02-16 | 2024-02-27 | 12 | 8 | 2024-02-27 | 2024-04-11 | 45 | 33 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-06-24 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-11 | 18 | 14 | 2024-07-11 | 2024-07-10 | Unknown | Unknown | 83 | 59 | 63 | 47 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | -304 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-09-26 | IOU Designed & Installed | N/A | No | N/A | -1191.97 | 1650.54 | Unknown | 787 | -4600 | 970.49 | Unknown | 4600.28 | -1191.97 | 5792.25 | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | 2023-09-25 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-09-27 | 2 | 2 | 2023-09-27 | 2023-09-27 | 1 | 1 | 1 | 1 | 21 | 15 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 130 | 130 | Not Available | <1MW | No | N/A | N/A | N/A | 2020-10-01 | 1301 | 930 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 1668 | 268.78 | Unknown | Unknown | -337.86 | 1737.08 | 0 | 337.94 | 1668 | -1330.06 | Yes | N/A | N/A | 2023-05-31 | 2023-05-30 | Unknown | Unknown | 2023-05-30 | 2023-06-28 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-08-08 | 42 | 30 | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-04-29 | 7 | 5 | 2024-04-29 | 2024-04-24 | Unknown | Unknown | 42 | 30 | 37 | 27 | 79 | 57 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 272.25 | 272.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | -258 | -185 | No | 2023-08-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-17 | 2024-07-13 | IOU Designed & Installed | N/A | Yes | 7 | 10750.89 | 2364.55 | Unknown | Unknown | Unknown | 8386.34 | 3961 | 668.79 | 10750.89 | -10082.1 | Yes | N/A | N/A | 2023-08-10 | 2023-08-17 | 8 | 6 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2024-07-13 | 332 | 237 | Unknown | 2024-06-27 | Unknown | Unknown | 2024-07-13 | 2024-07-16 | 4 | 2 | 2024-07-16 | 2024-07-16 | 1 | 1 | 340 | 243 | 6 | 4 | 346 | 247 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | -31 | -24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-07-22 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 1143.11 | -29.73 | Unknown | Unknown | Unknown | 1172.84 | Unknown | 1018.68 | 1143.11 | -124.43 | Yes | N/A | N/A | 2023-06-01 | 2023-04-06 | Unknown | Unknown | 2023-04-06 | 2023-07-21 | 107 | 77 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | 2023-12-15 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-02-20 | 68 | 48 | 2024-02-20 | 2024-02-20 | 1 | 1 | 147 | 105 | 176 | 126 | 323 | 231 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-25 | 64 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.42 | -11.04 | Unknown | Unknown | Unknown | 23.46 | 3981 | 1032.3 | 12.42 | 1019.88 | Yes | N/A | N/A | 2022-06-08 | 2023-08-14 | 433 | 309 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-05-28 | Unknown | Unknown | 433 | 309 | 0 | 0 | 433 | 309 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.1 | -2.98 | Unknown | Unknown | Unknown | -1.12 | Unknown | 363.72 | -4.1 | 367.82 | Yes | N/A | N/A | 2023-02-27 | 2023-02-27 | 1 | 1 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-05-17 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -616 | -441 | No | 2023-04-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-05-09 | Unknown | IOU Designed & Installed | N/A | Yes | 26 | -2.77 | -8.21 | Unknown | Unknown | Unknown | 5.44 | 3981 | 1116.26 | -2.77 | 1119.03 | Yes | N/A | N/A | 2023-04-27 | 2023-05-23 | 27 | 19 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | 2023-06-16 | 2023-06-16 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | -149 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.62 | -7.81 | Unknown | Unknown | 2.23 | 3.96 | 3981 | 553.66 | -1.62 | 555.28 | Yes | N/A | N/A | 2023-02-22 | 2023-03-07 | 14 | 10 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-08-16 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | 82 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-25 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 5829.59 | Unknown | Unknown | Unknown | Unknown | 5829.59 | 7219.83 | 614.13 | 5829.59 | -5215.46 | Yes | N/A | N/A | 2023-09-20 | 2023-09-25 | 6 | 4 | 2023-09-25 | 2023-11-21 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-03 | 8 | 6 | 2023-11-21 | 2024-11-12 | 358 | 256 | Unknown | 2024-09-25 | Unknown | Unknown | 2024-11-19 | 2024-12-26 | 38 | 28 | 2024-12-26 | 2024-12-18 | Unknown | Unknown | 364 | 260 | 104 | 76 | 468 | 336 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-22 | 305 | 220 | No | 2022-10-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | 2023-05-30 | IOU Designed & Installed | N/A | Yes | 238 | 651.64 | 234.43 | Unknown | Unknown | 5.58 | 411.63 | 6481 | 1083.54 | 651.64 | 431.9 | Yes | N/A | N/A | 2022-10-18 | 2023-06-13 | 239 | 171 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-18 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-08-09 | 72 | 52 | 2023-08-09 | 2023-06-23 | Unknown | Unknown | 239 | 171 | 72 | 52 | 311 | 223 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | 228 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-03 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 1217.26 | -36.88 | Unknown | Unknown | 144.26 | 1109.88 | 3981 | 812.62 | 1217.26 | -404.64 | Yes | N/A | N/A | 2023-11-02 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2023-11-03 | 53 | 39 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2024-03-26 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2025-04-02 | 373 | 267 | 2025-04-02 | 2025-04-02 | 1 | 1 | 145 | 103 | 427 | 307 | 572 | 410 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -123 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 933.13 | 2654.23 | Unknown | 652.21 | -3724 | 1350.69 | Unknown | 3723.53 | 933.13 | 2790.4 | Yes | N/A | N/A | 2024-01-09 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | 279 | 200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16137.07 | 409.92 | Unknown | Unknown | 80.92 | 15646.23 | 3981 | 806.64 | 16137.07 | -15330.43 | Yes | N/A | N/A | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | 2025-03-13 | 2025-02-25 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-06-17 | 782 | 559 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2022-11-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 675.75 | Unknown | Unknown | Unknown | -450 | 1125.75 | 0 | 348.82 | 675.75 | -326.93 | Yes | N/A | N/A | 2022-09-29 | 2023-07-11 | 286 | 204 | 2023-07-11 | 2024-07-22 | 378 | 270 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-08-07 | Unknown | Unknown | 286 | 204 | 378 | 270 | 664 | 474 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3391.7 | -66.09 | Unknown | Unknown | 157.16 | 3300.63 | 3981 | 498.53 | 3391.7 | -2893.17 | Yes | N/A | N/A | 2023-02-27 | 2023-08-02 | 157 | 113 | 2023-08-02 | 2023-08-14 | 13 | 9 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-02-15 | 1 | 1 | 157 | 113 | 14 | 10 | 171 | 123 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 1419.1 | 1419.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-02-01 | -289 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 21197.92 | 15736.36 | Unknown | Unknown | -15112 | 20573.56 | 0 | 21127.24 | 21197.92 | -70.68 | Yes | N/A | N/A | 2024-03-14 | 2024-04-11 | 29 | 21 | 2024-04-11 | 2024-07-25 | 106 | 76 | 2024-06-20 | 2024-07-03 | 14 | 10 | 2024-07-16 | 2024-07-26 | 10 | 7 | 2024-07-25 | 2025-04-08 | 258 | 184 | 2024-08-20 | 2025-04-01 | 225 | 161 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-18 | Unknown | Unknown | 301 | 215 | 341 | 244 | 642 | 459 | Steps 2,3,5,6,7 | 267 | 191 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3907 | 3907 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-08-20 | 38 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | -5.25 | -10.26 | Unknown | Unknown | Unknown | 5.01 | 3941 | 781.67 | -5.25 | 786.92 | Yes | N/A | N/A | 2023-08-09 | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-08-09 | 62 | 44 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-09-11 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-27 | 17 | 13 | 2023-09-27 | 2023-09-27 | 1 | 1 | 34 | 24 | 80 | 58 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | -17.53 | -14.25 | Unknown | Unknown | Unknown | -3.28 | Unknown | 186.4 | -17.53 | 203.93 | Yes | N/A | N/A | 2024-05-29 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-29 | 49 | 35 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-05-31 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-21 | 22 | 16 | 2024-06-21 | 2024-06-21 | 1 | 1 | 3 | 3 | 72 | 52 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-11-13 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 1255.69 | 456.85 | Unknown | Unknown | Unknown | 798.84 | Unknown | 1004.83 | 1255.69 | -250.86 | Yes | N/A | N/A | 2023-09-08 | 2023-11-13 | 67 | 47 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-29 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-11-30 | 2 | 2 | 2023-11-30 | 2023-11-30 | 1 | 1 | 84 | 60 | 4 | 4 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 73.1 | 73.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -462 | -331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-08 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 42.75 | Unknown | Unknown | Unknown | Unknown | 42.75 | 3981 | 1482.56 | 42.75 | 1439.81 | Yes | N/A | N/A | 2024-07-05 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-05 | 17 | 13 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-08-08 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-29 | 22 | 16 | 2024-08-29 | 2024-08-29 | 1 | 1 | 32 | 24 | 40 | 30 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 5.97 | Unknown | Unknown | Unknown | Unknown | 5.97 | 3981 | 192.95 | 5.97 | 186.98 | Yes | N/A | N/A | 2024-09-13 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-09-18 | 22 | 16 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-28 | 12 | 8 | 2024-10-28 | 2024-10-28 | 1 | 1 | 30 | 22 | 35 | 25 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | Chula Vista | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 180 | 129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2024-12-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 511195.35 | 76174.03 | Unknown | 95.73 | 28919.93 | 406005.66 | 259676.81 | 158325.39 | 511195.35 | -352869.96 | Yes | N/A | N/A | 2023-09-15 | 2023-11-08 | 55 | 39 | 2023-11-08 | 2024-07-11 | 247 | 177 | 2024-05-03 | 2024-08-27 | 32 | 22 | 2024-04-02 | 2024-11-27 | 77 | 55 | 2024-07-11 | Unknown | Unknown | Unknown | 2024-07-23 | 2024-11-12 | 113 | 81 | 2024-12-13 | 2025-01-28 | 47 | 33 | 2025-01-28 | 2025-01-28 | 1 | 1 | 87 | 61 | 485 | 347 | 572 | 408 | Steps 2,3,5,6,7 | 355 | 253 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 65.4 | 65.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -509 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 1583.81 | -56.03 | Unknown | Unknown | Unknown | 1639.84 | 3981 | 1853.8 | 1583.81 | 269.99 | Yes | N/A | N/A | 2024-11-19 | 2024-11-25 | 7 | 5 | 2024-11-25 | 2024-12-19 | 25 | 19 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-03-11 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-08 | 29 | 21 | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 90 | 64 | 54 | 40 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 163.96 | -6.45 | Unknown | Unknown | Unknown | 170.41 | 3981 | 787.91 | 163.96 | 623.95 | Yes | N/A | N/A | 2023-11-22 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-11-22 | 113 | 81 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-02-08 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-21 | 14 | 10 | 2024-02-21 | 2024-02-21 | 1 | 1 | 79 | 57 | 128 | 92 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -167 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 508.39 | -20.69 | Unknown | Unknown | Unknown | 529.08 | Unknown | 497.98 | 508.39 | -10.41 | Yes | N/A | N/A | 2023-10-12 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-10-12 | 65 | 47 | 2023-10-12 | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-16 | 10 | 8 | 2023-10-12 | 2024-01-26 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-08 | 14 | 10 | 2024-02-08 | 2024-02-09 | 2 | 2 | 107 | 77 | 91 | 67 | 198 | 144 | Steps 2,3,5,6,7 | 127 | 91 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | 47 | 34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -740.29 | -0.63 | Unknown | Unknown | -791 | 51.34 | 0 | 687.2 | -740.29 | 1427.49 | Yes | N/A | N/A | 2023-11-08 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2023-11-09 | 14 | 10 | 2023-11-09 | 2024-02-20 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-02 | 1 | 1 | 104 | 74 | 15 | 11 | 119 | 85 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | -332 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 928.48 | Unknown | Unknown | Unknown | 27.22 | 901.26 | 3981 | 2145.05 | 928.48 | 1216.57 | Yes | N/A | N/A | 2023-10-03 | 2023-12-18 | 77 | 55 | 2023-12-18 | 2024-01-09 | 23 | 17 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-07-08 | 188 | 134 | Unknown | 2024-06-10 | Unknown | Unknown | 2024-07-08 | 2024-08-16 | 40 | 30 | 2024-08-16 | 2024-08-16 | 1 | 1 | 265 | 189 | 64 | 48 | 329 | 237 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-07 | -188 | -135 | No | 2016-10-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2016-10-28 | 2016-10-28 | 2025-05-30 | IOU Designed & Installed | N/A | Yes | 2916 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 5490 | 474.92 | Unknown | Unknown | Yes | N/A | N/A | 2016-10-28 | 2024-10-21 | 2916 | 2082 | 2024-10-21 | 2024-10-22 | 2 | 2 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2016-10-28 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-02 | 4 | 2 | 2025-06-02 | 2025-06-02 | 1 | 1 | 2916 | 2082 | 7 | 5 | 2923 | 2087 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -437 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | 5564.59 | 2355.3 | Unknown | 1635.68 | Unknown | 1573.61 | 26990 | 320.3 | 5564.59 | -5244.29 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-10-25 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-11-01 | 8 | 6 | 2023-11-01 | 2023-11-01 | 1 | 1 | 120 | 86 | 10 | 8 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 590.7 | -9.55 | Unknown | Unknown | Unknown | 600.25 | Unknown | 1176.99 | 590.7 | 586.29 | Yes | N/A | N/A | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-08 | 2 | 2 | 2023-12-07 | 2023-12-07 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-08 | 2 | 2 | 2023-12-08 | 2023-12-08 | 1 | 1 | 2 | 2 | 6 | 6 | 8 | 8 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 993.37 | -6.46 | Unknown | Unknown | 51.91 | 947.92 | 1192.8 | 606.35 | 993.37 | -387.02 | Yes | N/A | N/A | 2024-07-29 | 2024-08-13 | 16 | 12 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-09 | 28 | 20 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-23 | 1 | 1 | 16 | 12 | 30 | 22 | 46 | 34 | Steps 2,3,5,6,7 | 27 | 19 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Descanso | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | -145 | -104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | 37596.97 | 14810.8 | Unknown | 2587.38 | -7853.25 | 28052.04 | 2038 | 19428.09 | 37596.97 | -18168.88 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | 2023-06-22 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-26 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-12-29 | 150 | 108 | 2023-12-29 | 2023-12-29 | 1 | 1 | 1 | 1 | 187 | 135 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-23 | -249 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | -5.16 | -4.26 | Unknown | Unknown | Unknown | -0.9 | Unknown | 740.74 | -5.16 | 745.9 | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-26 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-07-18 | 23 | 17 | 2023-07-18 | 2023-07-18 | 1 | 1 | 22 | 16 | 24 | 18 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-21 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 1326.67 | -7.66 | Unknown | Unknown | 13.17 | 1321.16 | 3961 | 1004.33 | 1326.67 | -322.34 | Yes | N/A | N/A | 2024-03-07 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-04-15 | 74 | 52 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-31 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-07-10 | 41 | 29 | 2024-07-10 | 2024-07-10 | 1 | 1 | 47 | 35 | 116 | 82 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-06 | -773 | -552 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | 1176.91 | Unknown | Unknown | Unknown | Unknown | 1176.91 | 0 | 403.94 | 1176.91 | -772.97 | Yes | N/A | N/A | 2023-08-04 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-08-11 | 101 | 73 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-08-22 | 12 | 8 | Unknown | 2025-04-16 | Unknown | Unknown | 2023-08-22 | 2025-04-25 | 613 | 439 | 2025-04-25 | 2025-04-24 | Unknown | Unknown | 12 | 8 | 714 | 512 | 726 | 520 | Steps 2,3,5,6,7 | 603 | 431 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -347 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.2 | -3.4 | Unknown | Unknown | Unknown | -0.8 | Unknown | 495.75 | -4.2 | 499.95 | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-03-02 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 8.29 | -7.36 | Unknown | Unknown | Unknown | 15.65 | Unknown | 308.87 | 8.29 | 300.58 | Yes | N/A | N/A | 2024-02-15 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-03-01 | 44 | 32 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-06-25 | 112 | 80 | 2024-06-25 | 2024-06-25 | 1 | 1 | 5 | 3 | 157 | 113 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 827.56 | 827.56 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-09 | -591 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-26 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | -895.53 | -70.8 | Unknown | Unknown | -1530 | 705.27 | 3981 | 2948.92 | -895.53 | 3844.45 | Yes | N/A | N/A | 2024-12-12 | 2024-12-16 | 5 | 3 | 2024-12-16 | 2024-12-26 | 11 | 9 | 2024-12-26 | 2025-01-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-02-26 | 58 | 42 | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-26 | 2025-03-28 | 31 | 23 | 2025-03-28 | 2025-03-28 | 1 | 1 | 71 | 51 | 43 | 33 | 114 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | 2023-01-27 | 2023-06-12 | IOU Designed & Installed | N/A | No | N/A | 1705.59 | 411 | Unknown | 134.04 | Unknown | 1160.55 | 3981 | 1560.61 | 1705.59 | -144.98 | Yes | N/A | N/A | 2023-01-27 | 2023-02-16 | 21 | 15 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-06-12 | 109 | 77 | Unknown | 2023-05-31 | Unknown | Unknown | 2023-06-12 | 2023-06-12 | 1 | 1 | 2023-06-12 | 2023-06-12 | 1 | 1 | 130 | 92 | 2 | 2 | 132 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-26 | 371 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 775.92 | 1073.1 | Unknown | 160.58 | -1060 | 602.24 | Unknown | 1060.28 | 775.92 | 284.36 | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-07-31 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 1438.96 | Unknown | Unknown | Unknown | 7.98 | 1430.98 | 15924 | 1316.1 | 1438.96 | -122.86 | Yes | N/A | N/A | 2024-11-15 | 2025-02-20 | 98 | 70 | 2025-02-20 | 2025-04-02 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-04-15 | 27 | 20 | 2025-04-02 | 2025-06-23 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 181 | 129 | 71 | 52 | 252 | 181 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -537 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.98 | -2.88 | Unknown | Unknown | Unknown | 1.9 | Unknown | 273.56 | -0.98 | 274.54 | Yes | N/A | N/A | 2023-03-27 | 2023-04-10 | 15 | 11 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -718 | -514 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 486.54 | -15.84 | Unknown | Unknown | Unknown | 502.38 | 3981 | 1364.79 | 486.54 | 878.25 | Yes | N/A | N/A | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-06-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-02 | 7 | 5 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2 | 2 | 9 | 7 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -1184 | -847 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 406.18 | 252.46 | Unknown | Unknown | Unknown | 153.72 | 23991 | 324.29 | 406.18 | -81.89 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-10-11 | 216 | 154 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-12 | 2 | 2 | 2023-10-12 | 2023-10-12 | 1 | 1 | 217 | 155 | 3 | 3 | 220 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 150230.4 | 150230.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-12-09 | 325 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | Unknown | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | 769.46 | -32.23 | Unknown | Unknown | 8.95 | 792.74 | 3981 | 828.65 | 769.46 | 59.19 | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-09-12 | 13 | 9 | 2023-03-28 | 2023-08-22 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-12-04 | 105 | 75 | 2023-12-04 | 2023-10-30 | Unknown | Unknown | 149 | 107 | 118 | 84 | 267 | 191 | Steps 2,3,5,6,7 | 168 | 120 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -276 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 0.27 | -3.93 | Unknown | Unknown | Unknown | 4.2 | Unknown | 193.42 | 0.27 | 193.15 | Yes | N/A | N/A | 2022-09-15 | 2023-12-18 | 460 | 328 | 2023-12-18 | 2023-12-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-03-15 | 87 | 63 | 2024-03-15 | 2024-03-15 | 1 | 1 | 460 | 328 | 90 | 66 | 550 | 394 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-26 | 930 | 665 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 729.05 | -14.65 | Unknown | Unknown | Unknown | 743.7 | Unknown | 769.77 | 729.05 | 40.72 | Yes | N/A | N/A | 2024-12-09 | 2025-04-10 | 123 | 89 | 2025-04-10 | 2025-04-29 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-13 | 1 | 1 | 123 | 89 | 21 | 15 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | -609 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 3520.92 | 129 | Unknown | Unknown | Unknown | 3391.92 | Unknown | 515.73 | 3520.92 | -3005.19 | Yes | N/A | N/A | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-04-15 | 26 | 18 | 2025-04-15 | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-14 | 13 | 9 | 2025-04-15 | 2025-06-05 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-07 | 3 | 2 | 2025-06-07 | 2025-06-07 | 1 | 0 | 53 | 39 | 43 | 29 | 96 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-09-01 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 3420.6 | -25.95 | Unknown | Unknown | 8.73 | 3437.82 | 23150 | 2639.23 | 3420.6 | -781.37 | Yes | N/A | N/A | 2023-06-28 | 2023-08-08 | 42 | 30 | 2023-08-08 | 2024-02-01 | 178 | 128 | 2023-12-05 | 2024-01-29 | 56 | 40 | 2023-11-22 | 2024-02-05 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-17 | 23 | 17 | 2024-04-17 | 2024-04-17 | 1 | 1 | 98 | 70 | 271 | 195 | 369 | 265 | Steps 2,3,5,6,7 | 126 | 90 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | LAKESIDE | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -388 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 17439.48 | 150.83 | Unknown | Unknown | 196.37 | 17092.28 | 3981 | 725.93 | 17439.48 | -16713.55 | Yes | N/A | N/A | 2023-11-14 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2024-04-25 | 266 | 190 | 2023-11-14 | 2024-05-09 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-05-21 | 7 | 5 | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-21 | 2024-06-04 | 15 | 11 | 2024-06-04 | 2024-06-24 | 21 | 15 | 185 | 133 | 302 | 216 | 487 | 349 | Steps 2,3,5,6,7 | 163 | 117 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-01-05 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | -6.32 | -5.12 | Unknown | Unknown | Unknown | -1.2 | Unknown | 885.55 | -6.32 | 891.87 | Yes | N/A | N/A | 2023-11-28 | 2023-09-18 | Unknown | Unknown | 2023-09-18 | 2024-01-05 | 110 | 80 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-03-04 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-04-16 | 44 | 32 | 2024-04-16 | 2024-04-16 | 1 | 1 | 60 | 42 | 155 | 113 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-27 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 62.33 | Unknown | Unknown | Unknown | Unknown | 62.33 | 3981 | 2077.67 | 62.33 | 2015.34 | Yes | N/A | N/A | 2024-12-09 | 2024-12-10 | 2 | 2 | 2024-12-10 | 2024-12-12 | 3 | 3 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-24 | -516 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 966.38 | -14.71 | Unknown | Unknown | 4.94 | 976.15 | 3981 | 671.67 | 966.38 | -294.71 | Yes | N/A | N/A | 2023-10-25 | 2023-12-01 | 38 | 28 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-01-19 | 50 | 36 | Unknown | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-01-25 | 7 | 5 | 2024-01-25 | 2024-03-26 | 62 | 44 | 88 | 64 | 69 | 49 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -647 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 353.73 | -6.46 | Unknown | Unknown | Unknown | 360.19 | 3981 | 1531.24 | 353.73 | 1177.51 | Yes | N/A | N/A | 2024-09-27 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-27 | 23 | 17 | 2024-09-27 | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-31 | 25 | 19 | 2024-09-27 | 2024-11-05 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-21 | 17 | 13 | 2024-11-21 | 2024-11-21 | 1 | 1 | 40 | 28 | 66 | 50 | 106 | 78 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -316 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 985.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-30 | 2024-12-11 | Unknown | Unknown | 2024-12-11 | 2024-12-30 | 20 | 14 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-04-29 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-14 | 16 | 12 | 2025-05-14 | 2025-05-14 | 1 | 1 | 121 | 87 | 37 | 27 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-09 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | -433.12 | Unknown | Unknown | Unknown | -486 | 52.88 | 3981 | 2108.96 | -433.12 | 2542.08 | Yes | N/A | N/A | 2024-09-06 | 2024-09-09 | 4 | 2 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | 2024-09-12 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-01-30 | 72 | 52 | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-30 | 2025-02-11 | 13 | 9 | 2025-02-11 | 2025-02-11 | 1 | 1 | 80 | 58 | 15 | 11 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | -704 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-02-01 | IOU Designed & Installed | N/A | No | N/A | -2313.83 | 10095.13 | Unknown | 1359.52 | -19870 | 6101.52 | Unknown | 19870.1 | -2313.83 | 22183.93 | Yes | N/A | N/A | 2024-12-11 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-01 | 2025-02-05 | 5 | 3 | 2025-02-05 | 2025-02-05 | 1 | 1 | 0 | 0 | 6 | 4 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | -470 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-05-24 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 32.29 | Unknown | Unknown | Unknown | Unknown | 32.29 | 3981 | 1138.52 | 32.29 | 1106.23 | Yes | N/A | N/A | 2024-04-04 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-05-24 | 149 | 107 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-08-06 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-09-16 | 42 | 30 | 2024-09-16 | 2024-08-13 | Unknown | Unknown | 75 | 53 | 191 | 137 | 266 | 190 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-30 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 932.86 | -16.99 | Unknown | Unknown | Unknown | 949.85 | Unknown | 297.33 | 932.86 | -635.53 | Yes | N/A | N/A | 2024-04-24 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-05-03 | 57 | 41 | 2024-05-03 | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-06 | 35 | 25 | 2024-05-03 | 2024-06-19 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-11 | 23 | 17 | 2024-07-11 | 2024-07-11 | 1 | 1 | 48 | 34 | 116 | 84 | 164 | 118 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | 3845.73 | 253.12 | Unknown | Unknown | 25.04 | 3567.57 | 3981 | 2107.87 | 3845.73 | -1737.86 | Yes | N/A | N/A | 2024-12-09 | 2024-12-26 | 18 | 14 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-03-21 | 86 | 62 | Unknown | 2025-01-14 | Unknown | Unknown | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 104 | 76 | 3 | 3 | 107 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 503 | 360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3400.43 | -48.65 | Unknown | Unknown | Unknown | 3449.08 | 600349 | 23481.62 | 3400.43 | 20081.19 | Yes | N/A | N/A | 2024-06-19 | 2024-06-19 | 1 | 1 | 2024-06-19 | 2024-07-17 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-09-04 | 415 | 297 | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 416 | 298 | 30 | 22 | 446 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -292 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | -12.27 | -11.13 | Unknown | Unknown | Unknown | -1.14 | Unknown | 192.83 | -12.27 | 205.1 | Yes | N/A | N/A | 2024-05-23 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-03 | 54 | 38 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-14 | 10 | 8 | 2024-06-14 | 2024-06-14 | 1 | 1 | 3 | 3 | 65 | 47 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-30 | -254 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-04-12 | IOU Designed & Installed | N/A | No | N/A | 1763.05 | 650.2 | Unknown | 110.13 | Unknown | 1002.72 | 3981 | 896.78 | 1763.05 | -866.27 | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-04-12 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2023-04-20 | 9 | 7 | 2023-04-20 | 2023-04-20 | 1 | 1 | 45 | 33 | 10 | 8 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 3.44 | Unknown | Unknown | Unknown | Unknown | 3.44 | Unknown | 1049.43 | 3.44 | 1045.99 | Yes | N/A | N/A | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-11-07 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-19 | 13 | 9 | 2024-11-19 | 2024-11-19 | 1 | 1 | 127 | 91 | 15 | 11 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 124.05 | 124.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | -141 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-25 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 1590.21 | 446.93 | Unknown | 294.8 | 63.53 | 784.95 | 0 | 848.71 | 1590.21 | -741.5 | Yes | N/A | N/A | 2023-08-30 | 2023-05-30 | Unknown | Unknown | 2023-05-30 | 2023-09-25 | 119 | 85 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-24 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2024-11-02 | 376 | 269 | 2024-11-02 | 2024-11-02 | 1 | 0 | 30 | 22 | 496 | 354 | 526 | 376 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 179 | 179 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 305 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-10-04 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 34098.82 | 476.83 | Unknown | Unknown | Unknown | 33621.99 | 135072 | 23827.36 | 34098.82 | -10271.46 | Yes | N/A | N/A | 2023-03-30 | 2023-04-04 | 6 | 4 | 2023-04-04 | 2023-11-16 | 227 | 163 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-05-01 | 168 | 120 | Unknown | 2024-05-28 | Unknown | Unknown | 2024-06-06 | 2024-07-22 | 47 | 33 | 2024-07-22 | 2024-07-13 | Unknown | Unknown | 174 | 124 | 274 | 196 | 448 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -528 | -378 | No | 2024-02-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-07-22 | IOU Designed & Installed | N/A | Yes | 36 | 6.1 | Unknown | Unknown | Unknown | Unknown | 6.1 | Unknown | 697.94 | 6.1 | 691.84 | Yes | N/A | N/A | 2024-02-29 | 2024-04-05 | 37 | 27 | 2024-04-05 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-07-22 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-07 | 17 | 13 | 2024-08-07 | 2024-08-07 | 1 | 1 | 219 | 157 | 18 | 14 | 237 | 171 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | -132 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26.28 | Unknown | Unknown | Unknown | Unknown | 26.28 | 0 | 887.05 | 26.28 | 860.77 | Yes | N/A | N/A | 2023-07-14 | 2023-04-28 | Unknown | Unknown | 2023-04-28 | 2023-09-19 | 145 | 103 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-05 | 1 | 1 | 0 | 0 | 146 | 104 | 146 | 104 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-16 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 5.31 | Unknown | Unknown | Unknown | Unknown | 5.31 | Unknown | 192.83 | 5.31 | 187.52 | Yes | N/A | N/A | 2024-05-07 | 2024-05-24 | 18 | 14 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-07-22 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-28 | 38 | 28 | 2024-08-28 | 2024-08-28 | 1 | 1 | 78 | 56 | 40 | 30 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | -381 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-24 | 2024-11-24 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | -4.49 | -18.81 | Unknown | Unknown | Unknown | 14.32 | 3981 | 1662.8 | -4.49 | 1667.29 | Yes | N/A | N/A | 2024-11-24 | 2024-12-17 | 24 | 17 | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-03 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-17 | 15 | 11 | 2025-04-17 | 2025-04-17 | 1 | 1 | 132 | 95 | 17 | 13 | 149 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | La Jolla | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 991.76 | -19.63 | Unknown | Unknown | Unknown | 1011.39 | Unknown | 466.88 | 991.76 | -524.88 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-05 | 27 | 19 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-07-30 | 1 | 1 | 2 | 2 | 79 | 57 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 181.34 | -13.42 | Unknown | Unknown | Unknown | 194.76 | 3981 | 897.13 | 181.34 | 715.79 | Yes | N/A | N/A | 2024-04-11 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-04-11 | 81 | 59 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-12 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-17 | 36 | 26 | 2024-05-17 | 2024-05-17 | 1 | 1 | 2 | 2 | 118 | 86 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -409 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 470.11 | -8.77 | Unknown | Unknown | Unknown | 478.88 | 3981 | 4441.22 | 470.11 | 3971.11 | Yes | N/A | N/A | 2024-03-28 | 2023-11-18 | Unknown | Unknown | 2023-11-18 | 2024-08-15 | 272 | 194 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-23 | 31 | 23 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-03 | 1 | 1 | 0 | 0 | 304 | 218 | 304 | 218 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -563 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 786.36 | -15.3 | Unknown | Unknown | Unknown | 801.66 | Unknown | 1506.92 | 786.36 | 720.56 | Yes | N/A | N/A | 2024-08-06 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-08-06 | 40 | 28 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-10-22 | 2024-10-29 | 8 | 6 | 2024-08-06 | 2024-11-07 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-12-04 | 28 | 20 | 2024-12-04 | 2024-12-04 | 1 | 1 | 94 | 68 | 77 | 55 | 171 | 123 | Steps 2,3,5,6,7 | 84 | 60 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -201 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.66 | -4.91 | Unknown | Unknown | Unknown | 3.25 | Unknown | 92.21 | -1.66 | 93.87 | Yes | N/A | N/A | 2023-03-07 | 2023-03-07 | 1 | 1 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-05-01 | 41 | 29 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 1 | 42 | 30 | 43 | 31 | Steps 2,3,5,6,7 | 55 | 39 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-01 | 1290 | 922 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-11-09 | 2020-11-09 | 2024-09-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 763644.75 | 249929.82 | Unknown | 258.36 | 10550 | 502906.57 | 6547485 | Not available | 763644.75 | Unknown | Yes | N/A | N/A | 2020-11-09 | 2023-08-29 | 1024 | 732 | 2023-08-29 | 2024-07-31 | 338 | 242 | 2023-09-28 | 2024-09-04 | 254 | 180 | 2023-10-18 | 2024-08-12 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-09-05 | 36 | 26 | 2024-09-23 | 2024-10-15 | 23 | 17 | 2024-10-15 | 2024-10-12 | Unknown | Unknown | 1278 | 912 | 509 | 365 | 1787 | 1277 | Steps 2,3,5,6,7 | 629 | 449 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 358.02 | -64.21 | Unknown | Unknown | Unknown | 422.23 | 3981 | 661.88 | 358.02 | 303.86 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | 2023-04-13 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 1 | 16 | 12 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTA YSABEL | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -669 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 639.49 | 740.13 | Unknown | 117.92 | -1382 | 1163.44 | 3981 | 1879.13 | 639.49 | 1239.64 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-23 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2023-07-24 | 34 | 24 | Unknown | 2023-07-03 | Unknown | Unknown | 2023-07-24 | 2023-08-02 | 10 | 8 | 2023-08-02 | 2023-08-02 | 1 | 1 | 38 | 28 | 12 | 10 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | -310 | -223 | No | 2022-08-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-23 | 2022-08-23 | 2023-01-18 | IOU Designed & Installed | N/A | Yes | 162 | 34.79 | -7.68 | Unknown | Unknown | -581.01 | 623.48 | Unknown | 537.71 | 34.79 | 502.92 | Yes | N/A | N/A | 2022-08-23 | 2023-02-01 | 163 | 117 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-01-18 | Unknown | Unknown | Unknown | 2023-05-02 | Unknown | Unknown | 2023-01-18 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 163 | 117 | 1 | 1 | 164 | 118 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -122 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 926.87 | 303.18 | Unknown | Unknown | Unknown | 623.69 | Unknown | 1023.22 | 926.87 | 96.35 | Yes | N/A | N/A | 2024-02-01 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-02-01 | 23 | 17 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-08-08 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-13 | 6 | 4 | 2024-08-13 | 2024-08-27 | 15 | 11 | 190 | 136 | 44 | 32 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | LAGUNA BEACH | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -222 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-24 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 7977.97 | Unknown | Unknown | Unknown | Unknown | 7977.97 | 3981 | 1653.54 | 7977.97 | -6324.43 | Yes | N/A | N/A | 2024-06-17 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-06-25 | 56 | 40 | 2024-06-25 | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-22 | 29 | 21 | 2024-06-24 | 2024-08-14 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-06 | 24 | 18 | 2024-09-06 | 2024-09-06 | 1 | 1 | 52 | 38 | 110 | 80 | 162 | 118 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-21 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | -11.54 | -8.37 | Unknown | Unknown | Unknown | -3.17 | Unknown | 480.44 | -11.54 | 491.98 | Yes | N/A | N/A | 2023-07-19 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-07-21 | 73 | 53 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-08-07 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-30 | 24 | 18 | 2023-08-30 | 2023-08-30 | 1 | 1 | 18 | 12 | 98 | 72 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 359.32 | Unknown | Unknown | Unknown | Unknown | 359.32 | Unknown | 343.42 | 359.32 | -15.9 | Yes | N/A | N/A | 2024-02-15 | 2024-02-20 | 6 | 4 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-07-29 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-16 | 19 | 15 | 2024-08-16 | 2024-08-16 | 1 | 1 | 167 | 119 | 21 | 17 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 19784.26 | Unknown | Unknown | Unknown | Unknown | 19784.26 | Unknown | 2127.92 | 19784.26 | -17656.34 | Yes | N/A | N/A | 2024-11-22 | 2024-11-22 | 1 | 1 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-02-25 | 71 | 51 | 2025-02-25 | 2025-02-25 | 1 | 1 | 1 | 1 | 72 | 52 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-30 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 15.06 | Unknown | Unknown | Unknown | Unknown | 15.06 | Unknown | 1526.33 | 15.06 | 1511.27 | Yes | N/A | N/A | 2024-07-25 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-30 | 42 | 30 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-16 | 12 | 10 | 2024-08-16 | 2024-08-16 | 1 | 1 | 7 | 5 | 55 | 41 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-18 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 27.95 | Unknown | Unknown | Unknown | Unknown | 27.95 | 3981 | 1524.98 | 27.95 | 1497.03 | Yes | N/A | N/A | 2024-06-13 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-06-18 | 68 | 48 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-30 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-02 | 4 | 4 | 2024-08-02 | 2024-08-02 | 1 | 1 | 43 | 31 | 73 | 53 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-27 | -561 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 10.07 | -8.98 | Unknown | Unknown | Unknown | 19.05 | 3981 | 953.61 | 10.07 | 943.54 | Yes | N/A | N/A | 2024-02-12 | 2024-02-14 | 3 | 3 | 2024-02-14 | 2024-02-14 | 1 | 1 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-04 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-18 | 15 | 11 | 2024-03-18 | 2024-03-15 | Unknown | Unknown | 23 | 17 | 16 | 12 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 189 | 189 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 1353.15 | Unknown | Unknown | Unknown | 18.03 | 1335.12 | 3981 | 1349.35 | 1353.15 | -3.8 | Yes | N/A | N/A | 2024-12-12 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-10 | 115 | 83 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-04-10 | 2025-05-05 | 26 | 18 | 2025-05-05 | 2025-05-05 | 1 | 1 | 115 | 83 | 28 | 20 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | N/A | 63.2 | 63.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | 108 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-05-22 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 8712.29 | 256.6 | Unknown | 38.97 | Unknown | 8416.72 | 4678 | 2855.22 | 8712.29 | -5857.07 | Yes | N/A | N/A | 2023-04-03 | 2023-05-22 | 50 | 36 | 2023-05-22 | 2023-11-03 | 166 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2024-04-10 | 160 | 114 | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-06 | 2024-05-20 | 15 | 11 | 2024-05-20 | 2024-05-13 | Unknown | Unknown | 210 | 150 | 181 | 131 | 391 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -468.24 | -13.96 | Unknown | Unknown | -717 | 262.72 | Unknown | 717.32 | -468.24 | 1185.56 | Yes | N/A | N/A | 2023-08-02 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-11-02 | 171 | 123 | 2023-11-02 | 2023-11-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-03-18 | 1 | 1 | 1 | 1 | 172 | 124 | 173 | 125 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-30 | 891 | 637 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-09 | 2023-06-23 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 6401.1 | -73.37 | Unknown | Unknown | Unknown | 6474.47 | 3981 | 719.91 | 6401.1 | -5681.19 | Yes | N/A | N/A | 2022-11-09 | 2023-06-23 | 227 | 163 | 2023-06-23 | 2024-12-06 | 533 | 381 | 2023-10-24 | 2024-11-13 | 387 | 277 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-09 | 8 | 6 | 2025-04-09 | 2025-04-08 | Unknown | Unknown | 614 | 440 | 541 | 387 | 1155 | 827 | Steps 2,3,5,6,7 | 409 | 293 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-07-01 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 74.44 | -0.63 | Unknown | Unknown | Unknown | 75.07 | 3981 | 1541.95 | 74.44 | 1467.51 | Yes | N/A | N/A | 2024-05-21 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-07-01 | 71 | 51 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-12-11 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-23 | 13 | 9 | 2024-12-23 | 2024-12-19 | Unknown | Unknown | 164 | 118 | 84 | 60 | 248 | 178 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | -154 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 0.81 | -11.33 | Unknown | Unknown | Unknown | 12.14 | 3981 | 771.42 | 0.81 | 770.61 | Yes | N/A | N/A | 2023-10-18 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-10-18 | 9 | 7 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-11-22 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-11-29 | 8 | 6 | 2023-11-29 | 2023-11-29 | 1 | 1 | 36 | 26 | 18 | 14 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | -179 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | 1157.72 | -27.16 | Unknown | Unknown | 5.25 | 1179.63 | 3981 | 1197.31 | 1157.72 | 39.59 | Yes | N/A | N/A | 2024-01-23 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-02-01 | 30 | 22 | 2024-02-01 | 2024-04-25 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-29 | 29 | 21 | Unknown | 2024-04-09 | Unknown | Unknown | 2024-02-29 | 2024-04-30 | 62 | 44 | 2024-04-30 | 2024-04-30 | 1 | 1 | 114 | 82 | 93 | 67 | 207 | 149 | Steps 2,3,5,6,7 | 40 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -179 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-20 | 2024-12-07 | IOU Designed & Installed | N/A | No | N/A | -2242.77 | 2608.64 | Unknown | 76.96 | -7510 | 2581.63 | Unknown | 4644.61 | -2242.77 | 6887.38 | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-11-13 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | 2024-12-07 | 2024-12-07 | 1 | 0 | 2024-12-07 | 2024-12-07 | 1 | 0 | 1 | 1 | 114 | 80 | 115 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 395 | 282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -839.61 | 1855.76 | Unknown | 144.13 | -3712 | 872.5 | Unknown | 3711.56 | -839.61 | 4551.17 | Yes | N/A | N/A | 2022-06-22 | 2024-02-13 | 602 | 430 | 2024-02-13 | 2024-02-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 602 | 430 | 9 | 7 | 611 | 437 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | -211 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-05-18 | IOU Designed & Installed | N/A | No | N/A | 621.31 | -10.77 | Unknown | Unknown | 4.08 | 628 | Unknown | 1744.88 | 621.31 | 1123.57 | Yes | N/A | N/A | 2023-02-13 | 2023-02-28 | 16 | 12 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-05-18 | 80 | 58 | Unknown | 2023-05-17 | Unknown | Unknown | 2023-05-18 | 2023-06-12 | 26 | 18 | 2023-06-12 | 2023-06-12 | 1 | 1 | 96 | 70 | 27 | 19 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 654 | -25.25 | Unknown | Unknown | Unknown | 679.25 | Unknown | 940.76 | 654 | 286.76 | Yes | N/A | N/A | 2024-03-29 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-29 | 80 | 58 | 2024-03-29 | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-28 | 20 | 14 | 2024-03-29 | 2024-05-08 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-29 | 22 | 16 | 2024-05-29 | 2024-05-29 | 1 | 1 | 41 | 29 | 123 | 89 | 164 | 118 | Steps 2,3,5,6,7 | 60 | 42 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -763 | -546 | No | 2022-09-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | 2022-09-19 | Unknown | IOU Designed & Installed | N/A | Yes | 207 | 670.35 | -7.07 | Unknown | Unknown | Unknown | 677.42 | 3885 | 625.91 | 670.35 | -44.44 | Yes | N/A | N/A | 2022-09-19 | 2023-04-14 | 208 | 150 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-05-12 | Unknown | Unknown | 208 | 150 | 0 | 0 | 208 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -249 | -178 | No | 2024-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-07-15 | IOU Designed & Installed | N/A | Yes | 148 | 390.35 | -0.94 | Unknown | Unknown | 4.86 | 386.43 | 3981 | 1462.39 | 390.35 | 1072.04 | Yes | N/A | N/A | 2024-02-15 | 2024-07-12 | 149 | 107 | 2024-07-12 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-15 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-14 | 31 | 23 | 2024-08-14 | 2024-08-14 | 1 | 1 | 167 | 119 | 32 | 24 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -658 | -471 | No | 2024-06-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2024-07-08 | IOU Designed & Installed | N/A | Yes | 4 | 38.5 | Unknown | Unknown | Unknown | Unknown | 38.5 | Unknown | 1476.09 | 38.5 | 1437.59 | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-06-24 | 5 | 3 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-08 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-25 | 18 | 14 | 2024-07-25 | 2024-07-25 | 1 | 1 | 20 | 14 | 24 | 18 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-30 | 686 | 491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-20 | 2022-01-20 | 2024-02-21 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 638304.09 | 201151.34 | Unknown | Unknown | 8996.16 | 428156.59 | 1597754 | 335004.35 | 638304.09 | -303299.74 | Yes | N/A | N/A | 2022-01-20 | 2023-02-09 | 386 | 276 | 2023-02-09 | 2023-06-22 | 134 | 96 | 2023-02-24 | 2023-06-15 | 30 | 20 | 2023-03-08 | 2023-07-25 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-02-01 | 88 | 64 | 2024-02-21 | 2024-04-15 | 55 | 39 | 2024-04-15 | 2024-04-15 | 1 | 1 | 416 | 296 | 329 | 237 | 745 | 533 | Steps 2,3,5,6,7 | 217 | 155 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -266 | -191 | No | 2024-07-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-08-30 | IOU Designed & Installed | N/A | Yes | 3 | 3.33 | Unknown | Unknown | Unknown | Unknown | 3.33 | Unknown | 186.09 | 3.33 | 182.76 | Yes | N/A | N/A | 2024-07-16 | 2024-07-19 | 4 | 4 | 2024-07-19 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-30 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-11 | 13 | 9 | 2024-09-11 | 2024-09-11 | 1 | 1 | 50 | 38 | 14 | 10 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -473 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 7005.52 | Unknown | Unknown | Unknown | Unknown | 7005.52 | Unknown | 2038.63 | 7005.52 | -4966.89 | Yes | N/A | N/A | 2024-07-24 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-11-18 | 160 | 114 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-01-30 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-24 | 26 | 18 | 2025-02-24 | 2025-02-24 | 1 | 1 | 74 | 54 | 187 | 133 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 777.05 | 777.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -84 | -61 | No | 2023-11-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-02-12 | IOU Designed & Installed | N/A | Yes | 92 | 65.93 | -6.44 | Unknown | Unknown | 0.31 | 72.06 | 3981 | 837.09 | 65.93 | 771.16 | Yes | N/A | N/A | 2023-11-06 | 2024-02-02 | 89 | 65 | 2024-02-02 | 2024-02-06 | 5 | 3 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-02-12 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-14 | 32 | 24 | 2024-03-14 | 2024-03-14 | 1 | 1 | 184 | 132 | 38 | 28 | 222 | 160 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 20.25 | Unknown | Unknown | Unknown | Unknown | 20.25 | 3941 | 1410.19 | 20.25 | 1389.94 | Yes | N/A | N/A | 2024-08-13 | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-08-13 | 20 | 14 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-11 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-18 | 8 | 6 | 2024-10-18 | 2024-10-18 | 1 | 1 | 60 | 44 | 29 | 21 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 127.05 | 127.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | -408 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 506.95 | -17.31 | Unknown | Unknown | Unknown | 524.26 | 1000 | 849.11 | 506.95 | 342.16 | Yes | N/A | N/A | 2022-10-24 | 2023-03-24 | 152 | 110 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-05-30 | 40 | 28 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-06-30 | 1 | 1 | 152 | 110 | 41 | 29 | 193 | 139 | Steps 2,3,5,6,7 | 67 | 47 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 420 | 420 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-07 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 1097.58 | -17.12 | Unknown | Unknown | 23.62 | 1091.08 | 3981 | 734.32 | 1097.58 | -363.26 | Yes | N/A | N/A | 2023-10-26 | 2023-12-05 | 41 | 29 | 2023-12-05 | 2023-12-13 | 9 | 7 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-05-31 | 171 | 123 | Unknown | 2024-05-30 | Unknown | Unknown | 2024-05-31 | 2024-06-13 | 14 | 10 | 2024-06-13 | 2024-06-13 | 1 | 1 | 212 | 152 | 24 | 18 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 172 | 172 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 1476.33 | 385.62 | Unknown | Unknown | Unknown | 1090.71 | Unknown | 1604.41 | 1476.33 | 128.08 | Yes | N/A | N/A | 2024-12-11 | 2024-11-29 | Unknown | Unknown | 2024-11-29 | 2024-12-11 | 13 | 9 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-26 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-02-11 | 48 | 34 | 2025-02-11 | 2025-02-11 | 1 | 1 | 16 | 12 | 62 | 44 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 634 | 453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4416.18 | 678.22 | Unknown | 141.5 | 73.3 | 3523.16 | Unknown | 1685.57 | 4416.18 | -2730.61 | Yes | N/A | N/A | 2023-04-20 | 2024-10-01 | 531 | 379 | 2024-10-01 | 2024-10-15 | 15 | 11 | 2023-09-05 | 2024-08-15 | 346 | 248 | 2023-08-11 | 2025-02-15 | 76 | 53 | 2024-10-15 | 2024-11-26 | 43 | 31 | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-11 | 1 | 1 | 920 | 658 | 92 | 65 | 1012 | 723 | Steps 2,3,5,6,7 | 899 | 642 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 342.23 | Unknown | Unknown | Unknown | Unknown | 342.23 | 3981 | 2377.57 | 342.23 | 2035.34 | Yes | N/A | N/A | 2024-06-18 | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-06-28 | 40 | 30 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-25 | 1 | 1 | 0 | 0 | 41 | 31 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 247.17 | -17.14 | Unknown | Unknown | Unknown | 264.31 | 0 | 466.88 | 247.17 | 219.71 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-09-04 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 3 | 3 | 154 | 110 | 157 | 113 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-12-07 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 1.88 | -6.9 | Unknown | Unknown | Unknown | 8.78 | 3981 | 969.62 | 1.88 | 967.74 | Yes | N/A | N/A | 2023-11-07 | 2023-12-07 | 31 | 23 | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-16 | 36 | 26 | 2024-01-16 | 2024-01-16 | 1 | 1 | 37 | 27 | 38 | 28 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -311 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-12 | 2024-03-16 | IOU Designed & Installed | N/A | No | N/A | -659.7 | 753.75 | Unknown | 96.2 | -2034 | 524.35 | Unknown | 2034.1 | -659.7 | 2693.8 | Yes | N/A | N/A | 2024-02-05 | 2024-02-12 | 8 | 6 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-16 | 2024-03-19 | 4 | 2 | 2024-03-19 | 2024-03-19 | 1 | 1 | 8 | 6 | 5 | 3 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -577 | -414 | No | 2024-01-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-17 | 2024-03-22 | IOU Designed & Installed | N/A | Yes | 73 | 284 | -11.09 | Unknown | Unknown | 3.42 | 291.67 | 3981 | 800.22 | 284 | 516.22 | Yes | N/A | N/A | 2024-01-12 | 2024-03-25 | 74 | 52 | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-03-22 | 3 | 3 | Unknown | 2024-04-01 | Unknown | Unknown | 2024-03-22 | 2024-04-02 | 12 | 8 | 2024-04-02 | 2024-04-02 | 1 | 1 | 77 | 55 | 14 | 10 | 91 | 65 | Steps 2,3,5,6,7 | 10 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-03-30 | IOU Designed & Installed | N/A | No | N/A | 28.65 | -9.03 | Unknown | Unknown | Unknown | 37.68 | 3981 | 653.77 | 28.65 | 625.12 | Yes | N/A | N/A | 2023-02-02 | 2023-02-03 | 2 | 2 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-03-30 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-04-18 | 20 | 14 | 2023-04-18 | 2023-04-18 | 1 | 1 | 58 | 42 | 21 | 15 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 266.1 | 266.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -141 | -102 | No | 2023-10-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2023-11-21 | 2024-04-17 | IOU Designed & Installed | N/A | Yes | 56 | 1287.62 | -6.66 | Unknown | Unknown | 13.39 | 1280.89 | 3241 | 516.61 | 1287.62 | -771.01 | Yes | N/A | N/A | 2022-12-14 | 2023-11-21 | 343 | 245 | 2023-11-21 | 2023-11-29 | 9 | 7 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-04-17 | 141 | 101 | Unknown | 2024-04-09 | Unknown | Unknown | 2024-04-17 | 2024-05-08 | 22 | 16 | 2024-05-08 | 2024-05-08 | 1 | 1 | 484 | 346 | 32 | 24 | 516 | 370 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | -129 | -93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.45 | -16.12 | Unknown | Unknown | Unknown | 10.67 | Unknown | 776.51 | -5.45 | 781.96 | Yes | N/A | N/A | 2023-03-06 | 2023-03-21 | 16 | 12 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-08-30 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 70.75 | Unknown | Unknown | Unknown | Unknown | 70.75 | Unknown | 1996.25 | 70.75 | 1925.5 | Yes | N/A | N/A | 2024-11-05 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-05 | 19 | 13 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-07 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-12-18 | 42 | 30 | 2024-12-18 | 2024-12-18 | 1 | 1 | 3 | 3 | 62 | 44 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 3862.84 | 1123.89 | Unknown | 181.72 | Unknown | 2557.23 | Unknown | 1433.33 | 3862.84 | -2429.51 | Yes | N/A | N/A | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-07-12 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-23 | 12 | 8 | 2024-07-23 | 2024-07-23 | 1 | 1 | 44 | 32 | 14 | 10 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 225 | 162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-07 | 2022-06-07 | 2024-06-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 116018.54 | 9532.21 | Unknown | Unknown | 23888.55 | 82597.78 | 0 | 54142.49 | 116018.54 | -61876.05 | Yes | N/A | N/A | 2022-06-07 | 2023-06-09 | 368 | 264 | 2023-06-09 | 2023-09-26 | 110 | 78 | 2023-07-13 | 2024-06-07 | 144 | 103 | 2023-09-26 | 2023-10-12 | 17 | 13 | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-17 | 2024-06-06 | 234 | 168 | 2024-06-11 | 2024-07-30 | 50 | 36 | 2024-07-30 | 2024-07-30 | 1 | 1 | 512 | 367 | 412 | 296 | 924 | 663 | Steps 2,3,5,6,7 | 330 | 236 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 9 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-03 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 1567.65 | Unknown | Unknown | Unknown | Unknown | 1567.65 | Unknown | 1285.91 | 1567.65 | -281.74 | Yes | N/A | N/A | 2023-04-12 | 2023-09-26 | 168 | 120 | 2023-09-26 | 2023-09-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-24 | 14 | 10 | 2023-10-24 | 2023-10-24 | 1 | 1 | 168 | 120 | 17 | 13 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 480 | 480 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-31 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 8356.86 | 3084.03 | Unknown | Unknown | 324.19 | 4948.64 | 3981 | 591.35 | 8356.86 | -7765.51 | Yes | N/A | N/A | 2023-05-30 | 2023-07-06 | 38 | 28 | 2023-07-06 | 2023-07-06 | 1 | 1 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2024-04-25 | 295 | 211 | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-25 | 2024-05-01 | 7 | 5 | 2024-05-01 | 2024-05-01 | 1 | 1 | 333 | 239 | 9 | 7 | 342 | 246 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -619 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 65.54 | -10.25 | Unknown | Unknown | Unknown | 75.79 | Unknown | 192.83 | 65.54 | 127.29 | Yes | N/A | N/A | 2024-04-29 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-06-07 | 68 | 50 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-16 | 28 | 20 | 2024-07-16 | 2024-07-16 | 1 | 1 | 13 | 9 | 97 | 71 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | 34 | 25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2024-04-06 | IOU Designed & Installed | N/A | No | N/A | -11.28 | -9.16 | Unknown | Unknown | Unknown | -2.12 | Unknown | 534.57 | -11.28 | 545.85 | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-06 | 4 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-04-06 | 2024-05-07 | 32 | 22 | 2024-05-07 | 2024-05-07 | 1 | 1 | 5 | 4 | 33 | 23 | 38 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-10 | 387 | 278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-06-27 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 698.85 | -13.55 | Unknown | Unknown | Unknown | 712.4 | 3981 | 1677.59 | 698.85 | 978.74 | Yes | N/A | N/A | 2024-04-09 | 2024-06-27 | 80 | 58 | 2024-06-27 | 2024-06-27 | 1 | 1 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-09-18 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-31 | 44 | 32 | 2024-10-31 | 2024-10-31 | 1 | 1 | 164 | 118 | 46 | 34 | 210 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -430 | -307 | No | 2023-12-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-08-14 | IOU Designed & Installed | N/A | Yes | 44 | 10283.69 | 3891.09 | Unknown | Unknown | -211.54 | 6604.14 | 3981 | 4138.85 | 10283.69 | -6144.84 | Yes | N/A | N/A | 2023-12-11 | 2024-01-30 | 51 | 37 | 2024-01-30 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-04-01 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-08-14 | 225 | 161 | Unknown | 2024-06-13 | Unknown | Unknown | 2024-08-14 | 2024-08-30 | 17 | 13 | 2024-08-30 | 2024-09-05 | 7 | 5 | 366 | 262 | 24 | 18 | 390 | 280 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | -24 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 7589.06 | 2908.32 | Unknown | Unknown | -684 | 5364.74 | 3981 | 1666.53 | 7589.06 | -5922.53 | Yes | N/A | N/A | 2023-03-17 | 2023-08-30 | 167 | 119 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | 2023-09-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-12-06 | 100 | 72 | Unknown | 2023-12-12 | Unknown | Unknown | 2023-12-06 | 2023-12-07 | 2 | 2 | 2023-12-07 | 2023-12-07 | 1 | 1 | 270 | 194 | 4 | 4 | 274 | 198 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-25 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 1684.18 | 506.8 | Unknown | 26.6 | Unknown | 1150.78 | Unknown | 1488.37 | 1684.18 | -195.81 | Yes | N/A | N/A | 2024-06-12 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-06-25 | 36 | 26 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-30 | 21 | 15 | 2024-07-30 | 2024-07-30 | 1 | 1 | 16 | 12 | 58 | 42 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -666 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | Unknown | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 35.07 | Unknown | Unknown | Unknown | Unknown | 35.07 | 3981 | 1554.28 | 35.07 | 1519.21 | Yes | N/A | N/A | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-12 | 28 | 20 | 2024-09-12 | 2024-09-12 | 1 | 1 | 2 | 2 | 30 | 22 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-14 | -268 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | 1311.09 | Unknown | Unknown | Unknown | 30.65 | 1280.44 | 3981 | 2055.57 | 1311.09 | 744.48 | Yes | N/A | N/A | 2024-04-22 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-05-02 | 80 | 58 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2025-03-07 | 310 | 222 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-03-07 | 2025-03-21 | 15 | 11 | 2025-03-21 | 2025-03-21 | 1 | 1 | 310 | 222 | 96 | 70 | 406 | 292 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | -317 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 815.69 | -18.46 | Unknown | Unknown | 20.38 | 813.77 | 3981 | 1091.49 | 815.69 | 275.8 | Yes | N/A | N/A | 2024-05-07 | 2024-08-02 | 88 | 64 | 2024-08-02 | 2024-08-02 | 1 | 1 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-27 | Unknown | Unknown | 88 | 64 | 1 | 1 | 89 | 65 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 21333.16 | Unknown | Unknown | Unknown | Unknown | 21333.16 | 3981 | 734.05 | 21333.16 | -20599.11 | Yes | N/A | N/A | 2023-01-04 | 2023-06-30 | 178 | 128 | 2023-06-30 | 2024-02-22 | 238 | 170 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-10-08 | 230 | 164 | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-18 | 2024-11-18 | 32 | 22 | 2024-11-18 | 2024-11-14 | Unknown | Unknown | 408 | 292 | 270 | 192 | 678 | 484 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | -64 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2024-01-18 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 809.45 | 241.68 | Unknown | 117.92 | Unknown | 449.85 | Unknown | 241.12 | 809.45 | -568.33 | Yes | N/A | N/A | 2023-09-06 | 2024-01-19 | 136 | 98 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-23 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | 2024-01-23 | 1 | 1 | 141 | 101 | 3 | 3 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -182 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -148.17 | -10.69 | Unknown | Unknown | -609.23 | 471.75 | 0 | 614.72 | -148.17 | 762.89 | Yes | N/A | N/A | 2023-06-07 | 2023-07-16 | 40 | 28 | 2023-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-16 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-06-28 | Unknown | Unknown | 40 | 28 | 0 | 0 | 40 | 28 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-09-18 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 1661.11 | 321.05 | Unknown | Unknown | Unknown | 1340.06 | Unknown | 1201.55 | 1661.11 | -459.56 | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-07 | 19 | 13 | 2024-10-07 | 2024-10-07 | 1 | 1 | 3 | 3 | 21 | 15 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1297.4 | Unknown | Unknown | Unknown | 73.3 | 1224.1 | 79620 | 14605.71 | 1297.4 | 13308.31 | Yes | N/A | N/A | 2023-03-31 | 2023-08-31 | 154 | 110 | 2023-08-31 | 2024-06-13 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-06-13 | 2958465 | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-04 | Unknown | Unknown | 154 | 110 | 289 | 207 | 443 | 317 | Steps 2,3,5,6,7 | 95 | 67 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-28 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1970.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-26 | 13 | 9 | 2025-03-26 | 2025-03-28 | 3 | 3 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-03-31 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-05-02 | 33 | 25 | 2025-05-02 | 2025-05-02 | 1 | 1 | 17 | 11 | 37 | 29 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -663 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-29 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1751.95 | 435.37 | Unknown | 164.82 | Unknown | 1151.76 | Unknown | 1595.46 | 1751.95 | -156.49 | Yes | N/A | N/A | 2024-10-28 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-10-29 | 42 | 30 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-10-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-18 | 21 | 15 | 2024-11-18 | 2024-11-18 | 1 | 1 | 1 | 1 | 64 | 46 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-09 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 526.28 | 379.53 | Unknown | Unknown | Unknown | 146.75 | Unknown | 1440.83 | 526.28 | 914.55 | Yes | N/A | N/A | 2024-08-07 | 2024-08-13 | 7 | 5 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-29 | 78 | 56 | Unknown | 2024-11-21 | Unknown | Unknown | 2024-10-29 | 2024-11-25 | 28 | 20 | 2024-11-25 | 2024-11-25 | 1 | 1 | 85 | 61 | 30 | 22 | 115 | 83 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | 106 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 884.78 | -17.49 | Unknown | Unknown | 6.64 | 895.63 | 3241 | 1437.89 | 884.78 | 553.11 | Yes | N/A | N/A | 2024-04-26 | 2024-07-16 | 82 | 58 | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-27 | 1 | 1 | 82 | 58 | 2 | 2 | 84 | 60 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 595.1 | 595.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -303 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-05-09 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | 139263.96 | 19421.18 | Unknown | 58.96 | 225.62 | 119558.2 | Unknown | 53494.62 | 139263.96 | -85769.34 | Yes | N/A | N/A | 2023-04-13 | 2023-05-03 | 21 | 15 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-09-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-11-14 | 57 | 41 | 2023-11-14 | 2023-11-14 | 1 | 1 | 21 | 15 | 71 | 51 | 92 | 66 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | -316 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-04-21 | IOU Designed & Installed | N/A | No | N/A | -5.25 | -15.38 | Unknown | Unknown | Unknown | 10.13 | Unknown | 763.23 | -5.25 | 768.48 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | 2023-04-21 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-06-12 | 53 | 37 | 2023-06-12 | 2023-04-28 | Unknown | Unknown | 39 | 29 | 53 | 37 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-05-22 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 35595.74 | 4902.37 | Unknown | 122.37 | -9461 | 40032 | 2312 | 21233.27 | 35595.74 | -14362.47 | Yes | N/A | N/A | 2024-04-12 | 2024-04-12 | 1 | 1 | 2024-04-12 | 2024-09-03 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-22 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-11-05 | 33 | 23 | 2024-11-05 | 2024-11-05 | 1 | 1 | 1 | 1 | 190 | 134 | 191 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA8 PH3 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 584 | 419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | 2022-09-09 | 2024-10-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 38573.34 | 8489.17 | Unknown | Unknown | 1764.67 | 28319.5 | 0 | 19774.68 | 38573.34 | -18798.66 | Yes | N/A | N/A | 2022-09-09 | 2023-04-18 | 222 | 158 | 2023-04-18 | 2023-11-17 | 214 | 154 | 2023-05-10 | 2024-04-08 | 232 | 166 | 2023-10-12 | 2023-11-08 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-24 | 17 | 13 | 2024-10-24 | 2024-10-24 | 1 | 1 | 454 | 324 | 260 | 188 | 714 | 512 | Steps 2,3,5,6,7 | 370 | 264 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-14 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 1141.49 | 350.3 | Unknown | 108.46 | 45.71 | 637.02 | 0 | 886.68 | 1141.49 | -254.81 | Yes | N/A | N/A | 2023-08-07 | 2023-08-14 | 8 | 6 | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-11-09 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-10 | 337 | 241 | 2024-10-10 | 2024-10-10 | 1 | 1 | 96 | 70 | 339 | 243 | 435 | 313 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-17 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 1235.25 | -24.15 | Unknown | Unknown | Unknown | 1259.4 | Unknown | 2183.32 | 1235.25 | 948.07 | Yes | N/A | N/A | 2025-01-16 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-17 | 9 | 7 | 2025-01-17 | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-10 | 48 | 34 | 2025-01-17 | 2025-03-10 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-20 | 11 | 9 | 2025-03-20 | 2025-03-20 | 1 | 1 | 53 | 37 | 69 | 51 | 122 | 88 | Steps 2,3,5,6,7 | 52 | 36 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | vs 1088-C3 | N/A | 2059 | 2059 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-01 | 749 | 536 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 2607.3 | 4890.96 | Unknown | Unknown | -9707 | 7423.34 | 2407.92 | 12115.35 | 2607.3 | 9508.05 | Yes | N/A | N/A | 2023-04-03 | 2023-05-10 | 38 | 28 | 2023-05-10 | 2023-08-08 | 91 | 65 | 2023-05-10 | 2023-07-26 | 1 | 1 | 2023-07-27 | 2023-07-31 | 5 | 3 | 2023-08-08 | Unknown | Unknown | Unknown | 2024-04-24 | 2025-05-22 | 394 | 282 | 2025-06-02 | 2025-06-19 | 18 | 14 | 2025-06-19 | 2025-06-19 | 1 | 1 | 39 | 29 | 509 | 365 | 548 | 394 | Steps 2,3,5,6,7 | 90 | 64 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -493 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-12-21 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 31.49 | Unknown | Unknown | Unknown | Unknown | 31.49 | 3241 | 2753.9 | 31.49 | 2722.41 | Yes | N/A | N/A | 2023-09-28 | 2024-08-22 | 330 | 236 | 2024-08-22 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-09-16 | 271 | 193 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-25 | 10 | 8 | 2024-09-25 | 2024-09-26 | 2 | 2 | 601 | 429 | 12 | 10 | 613 | 439 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 155.1 | 155.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | 255 | 182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-05-03 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | -4532.94 | Unknown | Unknown | Unknown | -6754.85 | 2221.91 | 7962 | 17341.31 | -4532.94 | 21874.25 | Yes | N/A | N/A | 2023-01-18 | 2023-02-06 | 20 | 14 | 2023-02-06 | 2023-06-28 | 143 | 103 | 2023-05-04 | 2025-04-07 | 695 | 495 | 2023-06-19 | 2025-06-20 | -10 | -9 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2025-05-27 | 685 | 489 | 2025-06-20 | 2025-06-27 | 8 | 6 | 2025-06-27 | 2025-06-23 | Unknown | Unknown | 715 | 509 | 826 | 589 | 1541 | 1098 | Steps 2,3,5,6,7 | 713 | 509 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-15 | 2024-02-06 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | 25.14 | -19.37 | Unknown | Unknown | Unknown | 44.51 | 3981 | 2521.58 | 25.14 | 2496.44 | Yes | N/A | N/A | 2022-07-15 | 2024-02-07 | 573 | 409 | 2024-02-07 | 2024-03-26 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-16 | 12 | 8 | 2024-07-16 | 2024-07-11 | Unknown | Unknown | 573 | 409 | 61 | 43 | 634 | 452 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -429 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 1721.8 | 522.48 | Unknown | Unknown | Unknown | 1199.32 | Unknown | 975.84 | 1721.8 | -745.96 | Yes | N/A | N/A | 2024-05-06 | 2024-05-04 | Unknown | Unknown | 2024-05-04 | 2024-05-06 | 3 | 1 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-07-23 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-27 | 36 | 26 | 2024-08-27 | 2024-08-27 | 1 | 1 | 79 | 57 | 40 | 28 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 31.5 | 31.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -76 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 731.4 | -13.6 | Unknown | Unknown | Unknown | 745 | Unknown | 1050.75 | 731.4 | 319.35 | Yes | N/A | N/A | 2024-07-01 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-08-14 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-05 | 35 | 25 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-10-04 | 1 | 1 | 0 | 0 | 94 | 68 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-27 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 17792.93 | 163.77 | Unknown | Unknown | -10254 | 27883.16 | Unknown | 10254.29 | 17792.93 | -7538.64 | Yes | N/A | N/A | 2023-12-05 | 2023-12-08 | 4 | 4 | 2023-12-08 | 2024-02-05 | 60 | 42 | 2023-12-15 | Unknown | Unknown | Unknown | 2024-02-23 | 2024-02-26 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-29 | 19 | 15 | 2024-03-29 | 2024-03-29 | 1 | 1 | 4 | 4 | 84 | 60 | 88 | 64 | Steps 2,3,5,6,7 | 52 | 36 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-08 | 325 | 233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1154.18 | -35.81 | Unknown | Unknown | 224.9 | 965.09 | 3981 | 1438.05 | 1154.18 | 283.87 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | 2023-08-11 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | Unknown | Unknown | Unknown | 2024-09-28 | Unknown | Unknown | 2024-09-28 | 2024-09-28 | 1 | 0 | 1 | 1 | 61 | 44 | 62 | 45 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | -333 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-03 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 2281.82 | 710.23 | Unknown | 312.65 | Unknown | 1258.94 | Unknown | 270.38 | 2281.82 | -2011.44 | Yes | N/A | N/A | 2023-07-03 | 2023-07-03 | 1 | 1 | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-07-18 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-25 | 8 | 6 | 2023-07-25 | 2023-07-25 | 1 | 1 | 17 | 13 | 9 | 7 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -163 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-06 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 1950.62 | 616.7 | Unknown | Unknown | Unknown | 1333.92 | 3981 | 963.64 | 1950.62 | -986.98 | Yes | N/A | N/A | 2024-06-05 | 2024-06-06 | 2 | 2 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-09 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-11 | 3 | 3 | 2024-07-11 | 2024-07-11 | 1 | 1 | 36 | 26 | 4 | 4 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-07 | 708 | 507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-13 | 2023-08-24 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 12166.97 | 5237.33 | Unknown | 364.04 | -1518.59 | 8084.19 | 3241 | 2717.55 | 12166.97 | -9449.42 | Yes | N/A | N/A | 2021-09-13 | 2023-08-24 | 711 | 509 | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | 2023-10-04 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2024-07-11 | 282 | 202 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-07-11 | 2024-08-14 | 35 | 25 | 2024-08-14 | 2024-08-15 | 2 | 2 | 1035 | 741 | 38 | 28 | 1073 | 769 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-03 | -491 | -351 | No | 2022-12-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | 2022-12-28 | 2022-12-28 | IOU Designed & Installed | N/A | Yes | 55 | -1.81 | -5.3 | Unknown | Unknown | Unknown | 3.49 | Unknown | 967.92 | -1.81 | 969.73 | Yes | N/A | N/A | 2022-12-28 | 2023-02-21 | 56 | 40 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2022-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-28 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-03-31 | 1 | 1 | 56 | 40 | 1 | 1 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-16 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | -2951.12 | 402.96 | Unknown | Unknown | -3546 | 191.92 | Unknown | 3545.54 | -2951.12 | 6496.66 | Yes | N/A | N/A | 2025-03-31 | 2025-04-16 | 17 | 13 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-15 | 2 | 2 | 2025-05-15 | 2025-05-15 | 1 | 1 | 17 | 13 | 3 | 3 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -705 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 25.94 | Unknown | Unknown | Unknown | Unknown | 25.94 | 3981 | 1392.17 | 25.94 | 1366.23 | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-02 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-12 | 11 | 7 | 2024-08-12 | 2024-08-12 | 1 | 1 | 6 | 6 | 13 | 9 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | DEL MAR | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 194 | 139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1486.87 | -24.15 | Unknown | Unknown | 18.47 | 1492.55 | Unknown | 405.34 | 1486.87 | -1081.53 | Yes | N/A | N/A | 2023-07-17 | 2023-08-16 | 31 | 23 | 2023-08-16 | 2023-10-24 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-08-04 | 8 | 6 | 2023-10-24 | 2023-10-12 | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2023-12-27 | Unknown | Unknown | 31 | 23 | 78 | 56 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -304 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1120.31 | -22.18 | Unknown | Unknown | Unknown | 1142.49 | 3981 | 753.15 | 1120.31 | -367.16 | Yes | N/A | N/A | 2024-01-25 | 2024-02-09 | 16 | 12 | 2024-02-09 | 2024-02-26 | 18 | 12 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-09 | Unknown | Unknown | 16 | 12 | 18 | 12 | 34 | 24 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Agricultural | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-06-11 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 5192.37 | 1054.92 | Unknown | Unknown | -6268 | 10405.45 | 18670 | 23246.23 | 5192.37 | 18053.86 | Yes | N/A | N/A | 2024-04-22 | 2024-05-02 | 11 | 9 | 2024-05-02 | 2024-07-03 | 63 | 45 | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-06-29 | 2024-07-11 | 13 | 9 | 2024-07-03 | 2024-08-16 | 45 | 33 | 2024-07-18 | 2024-08-21 | 35 | 25 | 2024-09-06 | 2024-09-24 | 19 | 13 | 2024-09-24 | 2024-09-19 | Unknown | Unknown | 57 | 43 | 130 | 92 | 187 | 135 | Steps 2,3,5,6,7 | 87 | 63 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -170 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-02-12 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2189.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-02-10 | 33 | 23 | 2025-02-10 | 2025-02-12 | 3 | 3 | 2025-02-12 | 2025-06-17 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-19 | 8 | 6 | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 162 | 116 | 11 | 9 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -392 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-04 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 934.14 | 176.57 | Unknown | 30.42 | Unknown | 727.15 | Unknown | 196.67 | 934.14 | -737.47 | Yes | N/A | N/A | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-04 | 5 | 3 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-12 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-28 | 17 | 13 | 2025-03-28 | 2025-03-28 | 1 | 1 | 37 | 27 | 23 | 17 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | N/A | CB 1126-H4 | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | 174 | 125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2025-03-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 52203.33 | 13113.13 | Unknown | Unknown | 2253.46 | 36836.74 | 206843 | 44543.21 | 52203.33 | -7660.12 | Yes | N/A | N/A | 2024-03-26 | 2024-08-19 | 147 | 105 | 2024-08-19 | 2024-11-13 | 87 | 63 | 2024-09-10 | 2025-02-03 | 104 | 76 | 2024-07-23 | 2024-11-19 | 25 | 17 | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-03 | 2025-02-25 | 85 | 61 | 2025-03-05 | 2025-03-24 | 20 | 14 | 2025-03-24 | 2025-03-24 | 1 | 1 | 251 | 181 | 218 | 156 | 469 | 337 | Steps 2,3,5,6,7 | 259 | 185 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PH8 PH2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 612 | 439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-10-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 62968.84 | 8815.88 | Unknown | Unknown | 2056.43 | 52096.53 | 0 | 20506.81 | 62968.84 | -42462.03 | Yes | N/A | N/A | 2022-04-27 | 2023-04-05 | 344 | 246 | 2023-04-05 | 2024-09-05 | 520 | 372 | 2023-04-27 | 2024-04-08 | 286 | 202 | 2023-09-12 | 2023-10-18 | 37 | 27 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-08 | 335 | 239 | 2024-10-08 | 2024-11-21 | 45 | 33 | 2024-11-21 | 2024-11-21 | 1 | 1 | 630 | 448 | 938 | 672 | 1568 | 1120 | Steps 2,3,5,6,7 | 706 | 504 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-01-13 | 1012 | 723 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-05 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 16197.69 | 3492.41 | Unknown | 176.37 | Unknown | 12528.91 | Unknown | 1634.56 | 16197.69 | -14563.13 | Yes | N/A | N/A | 2023-09-05 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-08-11 | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-10 | 2023-10-24 | 15 | 11 | 2023-10-24 | 2023-10-22 | Unknown | Unknown | 0 | 0 | 36 | 26 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 1915.41 | -46.42 | Unknown | Unknown | Unknown | 1961.83 | 3941 | 1019.6 | 1915.41 | -895.81 | Yes | N/A | N/A | 2024-06-25 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-06-25 | 42 | 30 | 2024-06-25 | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-03 | 9 | 7 | 2024-06-25 | 2024-07-12 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-18 | 7 | 5 | 2024-07-18 | 2024-07-18 | 1 | 1 | 18 | 14 | 59 | 43 | 77 | 57 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.22 | -3.42 | Unknown | Unknown | Unknown | -0.8 | Unknown | Not available | -4.22 | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-10-27 | 39 | 29 | 2023-10-27 | 2023-11-17 | 22 | 16 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 39 | 29 | 23 | 17 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -610 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 2765.65 | 568.42 | Unknown | 282.89 | Unknown | 1914.34 | Unknown | 2703.56 | 2765.65 | -62.09 | Yes | N/A | N/A | 2024-12-12 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-02-25 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-14 | 18 | 14 | 2025-03-14 | 2025-03-14 | 1 | 1 | 76 | 54 | 19 | 15 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-30 | 339 | 242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | 2023-03-14 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 38372.08 | 3455.19 | Unknown | Unknown | 404.35 | 34512.54 | Unknown | 24046.18 | 38372.08 | -14325.9 | Yes | N/A | N/A | 2022-07-25 | 2023-03-07 | 226 | 162 | 2023-03-07 | 2023-07-17 | 133 | 95 | 2023-04-03 | 2023-04-15 | 13 | 10 | 2023-03-22 | 2023-07-26 | -37 | -34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-12-04 | 98 | 70 | 2023-12-04 | 2023-12-04 | 1 | 1 | 239 | 172 | 195 | 132 | 434 | 304 | Steps 2,3,5,6,7 | 129 | 92 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -662 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 2034.16 | 508.46 | Unknown | 76.95 | Unknown | 1448.75 | 3981 | 1456.69 | 2034.16 | -577.47 | Yes | N/A | N/A | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-28 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-06 | 10 | 8 | 2024-11-06 | 2024-11-06 | 1 | 1 | 44 | 32 | 12 | 10 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-17 | 197 | 142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-11-14 | 2024-01-08 | IOU Designed & Installed | N/A | No | N/A | -27.56 | -29.23 | Unknown | Unknown | Unknown | 1.67 | 3981 | 1121.95 | -27.56 | 1149.51 | Yes | N/A | N/A | 2023-10-16 | 2023-11-14 | 30 | 22 | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-01-08 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-30 | 23 | 17 | 2024-01-30 | 2024-01-30 | 1 | 1 | 86 | 62 | 25 | 19 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 633.98 | -18.9 | Unknown | Unknown | -513 | 1165.88 | 7931.4 | 1914.66 | 633.98 | 1280.68 | Yes | N/A | N/A | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-03-22 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-07-15 | 116 | 82 | Unknown | 2024-05-30 | Unknown | Unknown | 2024-07-15 | 2024-07-16 | 2 | 2 | 2024-07-16 | 2024-07-16 | 1 | 1 | 141 | 101 | 4 | 4 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-03-08 | IOU Designed & Installed | N/A | No | N/A | 2460.4 | 3716.41 | Unknown | 811.23 | -3773 | 1705.76 | Unknown | 3773.45 | 2460.4 | 1313.05 | Yes | N/A | N/A | 2023-02-07 | 2023-02-07 | 1 | 1 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-04-07 | 31 | 23 | 2023-04-07 | 2023-04-07 | 1 | 1 | 1 | 1 | 32 | 24 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-27 | -208 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -272.67 | 1248.44 | Unknown | 312.78 | -2368 | 534.11 | Unknown | 2368.35 | -272.67 | 2641.02 | Yes | N/A | N/A | 2023-05-16 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | 234 | 167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-20 | 2024-10-20 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 2377.52 | 303.12 | Unknown | 157.35 | Unknown | 1917.05 | 3981 | 1197.6 | 2377.52 | -1179.92 | Yes | N/A | N/A | 2024-10-20 | 2024-11-20 | 32 | 23 | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-05-19 | 181 | 129 | Unknown | 2025-05-09 | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | 2025-05-19 | 1 | 1 | 213 | 152 | 3 | 3 | 216 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -723 | -518 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 1958.1 | 502.72 | Unknown | 199.03 | Unknown | 1256.35 | Unknown | 1073.95 | 1958.1 | -884.15 | Yes | N/A | N/A | 2024-10-03 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-08 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-09 | 2 | 2 | 2024-10-09 | 2024-10-09 | 1 | 1 | 6 | 4 | 4 | 4 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 524 | 524 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-05 | 2023-02-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.6 | -4.82 | Unknown | Unknown | Unknown | 3.22 | 3981 | 652.02 | -1.6 | 653.62 | Yes | N/A | N/A | 2023-02-05 | 2023-02-05 | 1 | 0 | 2023-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | 2023-04-03 | 2023-04-14 | 12 | 10 | 1 | 0 | 12 | 10 | 13 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 437.73 | -11.78 | Unknown | Unknown | 12.04 | 437.47 | 3981 | 637.68 | 437.73 | 199.95 | Yes | N/A | N/A | 2023-03-13 | 2023-04-17 | 36 | 26 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 36 | 26 | 1 | 1 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 188 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 48.59 | -25.31 | Unknown | Unknown | Unknown | 73.9 | Unknown | 697.32 | 48.59 | 648.73 | Yes | N/A | N/A | 2023-01-25 | 2023-04-14 | 80 | 58 | 2023-04-14 | 2023-05-30 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-05-09 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-10-06 | 1 | 1 | 80 | 58 | 60 | 42 | 140 | 100 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 14670 | 14670 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-01 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 2279.06 | Unknown | Unknown | Unknown | Unknown | 2279.06 | Unknown | 1200.05 | 2279.06 | -1079.01 | Yes | N/A | N/A | 2024-04-25 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2024-05-28 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-20 | 22 | 16 | 2024-06-20 | 2024-06-20 | 1 | 1 | 0 | 0 | 206 | 148 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -238 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 12.92 | -11.47 | Unknown | Unknown | Unknown | 24.39 | 3241 | 917.02 | 12.92 | 904.1 | Yes | N/A | N/A | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-20 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-31 | 12 | 10 | 2024-05-31 | 2024-05-31 | 1 | 1 | 29 | 21 | 14 | 12 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -402 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 8123.09 | 2148.11 | Unknown | 1815.1 | 241.4 | 3918.48 | 3981 | 1666.38 | 8123.09 | -6456.71 | Yes | N/A | N/A | 2023-05-04 | 2023-05-04 | 1 | 1 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-11-27 | 208 | 148 | Unknown | 2023-11-17 | Unknown | Unknown | 2023-11-27 | 2023-12-13 | 17 | 13 | 2023-12-13 | 2023-12-13 | 1 | 1 | 209 | 149 | 18 | 14 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -631 | -452 | No | 2024-07-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-05 | 2024-08-12 | IOU Designed & Installed | N/A | Yes | 38 | 936.18 | -17.35 | Unknown | Unknown | Unknown | 953.53 | 3981 | 1722.58 | 936.18 | 786.4 | Yes | N/A | N/A | 2024-07-23 | 2024-08-30 | 39 | 29 | 2024-08-30 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-05 | 25 | 19 | 2024-09-05 | 2024-09-04 | Unknown | Unknown | 47 | 35 | 25 | 19 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | 205 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-21 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 10077.62 | 320.75 | Unknown | Unknown | -5550.34 | 15307.21 | 0 | 5597.28 | 10077.62 | -4480.34 | Yes | N/A | N/A | 2023-05-24 | 2023-06-07 | 15 | 11 | 2023-06-07 | 2023-07-28 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2024-07-25 | 364 | 260 | Unknown | 2024-06-21 | Unknown | Unknown | 2024-06-27 | 2024-09-30 | 96 | 68 | 2024-09-30 | 2024-09-30 | 1 | 1 | 379 | 271 | 149 | 107 | 528 | 378 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -619 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 72.86 | -22.24 | Unknown | Unknown | Unknown | 95.1 | 3981 | 1716.03 | 72.86 | 1643.17 | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -11.35 | -8.22 | Unknown | Unknown | Unknown | -3.13 | Unknown | 98.41 | -11.35 | 109.76 | Yes | N/A | N/A | 2023-02-15 | 2023-02-22 | 8 | 6 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 236.25 | 236.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 730 | 523 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1291.36 | -11 | Unknown | Unknown | 88.93 | 1213.43 | 2875.23 | 258.9 | 1291.36 | -1032.46 | Yes | N/A | N/A | 2023-05-22 | 2023-04-20 | Unknown | Unknown | 2023-04-20 | 2023-06-01 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2025-04-23 | 693 | 495 | Unknown | 2023-11-28 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-04-30 | Unknown | Unknown | 693 | 495 | 43 | 31 | 736 | 526 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | N/A | 2533.75 | 2533.75 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-12-23 | 96 | 69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2024-01-31 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 8817.44 | 241.68 | Unknown | 40.86 | -1183 | 9717.9 | 3981 | 1720.44 | 8817.44 | -7097 | Yes | N/A | N/A | 2023-10-25 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-02-21 | 7 | 5 | Unknown | 2024-02-20 | Unknown | Unknown | 2024-02-21 | 2024-03-05 | 14 | 10 | 2024-03-05 | 2024-03-28 | 24 | 18 | 8 | 6 | 38 | 28 | 46 | 34 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 955.09 | -18.3 | Unknown | Unknown | Unknown | 973.39 | 3981 | 1505 | 955.09 | 549.91 | Yes | N/A | N/A | 2024-10-10 | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-10 | 3 | 3 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-21 | 12 | 8 | 2024-10-21 | 2024-10-21 | 1 | 1 | 1 | 1 | 16 | 12 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-31 | -713 | -510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 76.09 | Unknown | Unknown | Unknown | Unknown | 76.09 | 3981 | 1622.14 | 76.09 | 1546.05 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-08-21 | 2 | 2 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -292 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1226.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-01 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-20 | 20 | 14 | 2023-11-20 | 2023-11-20 | 1 | 1 | 22 | 16 | 22 | 16 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | -136 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 938.08 | -23.71 | Unknown | Unknown | Unknown | 961.79 | Unknown | 810.01 | 938.08 | -128.07 | Yes | N/A | N/A | 2023-08-23 | 2023-08-24 | 2 | 2 | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-01 | 5 | 5 | 2023-08-24 | 2023-12-28 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-30 | 34 | 24 | 2024-01-30 | 2024-01-30 | 1 | 1 | 129 | 93 | 41 | 31 | 170 | 124 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-18 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 58.64 | Unknown | Unknown | Unknown | Unknown | 58.64 | 7882 | 832.35 | 58.64 | 773.71 | Yes | N/A | N/A | 2024-01-16 | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2024-01-16 | 30 | 22 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-10-11 | 270 | 194 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-01 | 22 | 16 | 2024-11-01 | 2024-11-06 | 6 | 4 | 270 | 194 | 58 | 42 | 328 | 236 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -624 | -447 | No | 2023-03-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | Yes | 21 | -1.53 | -4.42 | Unknown | Unknown | Unknown | 2.89 | 3981 | 937.55 | -1.53 | 939.08 | Yes | N/A | N/A | 2023-03-23 | 2023-04-13 | 22 | 16 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | 2023-08-21 | IOU Designed & Installed | N/A | No | N/A | 634.87 | -20.98 | Unknown | Unknown | Unknown | 655.85 | Unknown | 770.58 | 634.87 | 135.71 | Yes | N/A | N/A | 2023-08-17 | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-08-17 | 67 | 49 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-21 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-09-27 | 38 | 28 | 2023-09-27 | 2023-09-27 | 1 | 1 | 5 | 3 | 106 | 78 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -672 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-03-03 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 1358.33 | 246.46 | Unknown | Unknown | Unknown | 1111.87 | Unknown | 2036.85 | 1358.33 | 678.52 | Yes | N/A | N/A | 2025-02-19 | 2025-03-03 | 13 | 9 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-26 | 10 | 8 | 2025-03-26 | 2025-03-26 | 1 | 1 | 28 | 20 | 12 | 10 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -641 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 328.91 | -14.13 | Unknown | Unknown | Unknown | 343.04 | 3981 | 803.05 | 328.91 | 474.14 | Yes | N/A | N/A | 2023-12-12 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2023-12-12 | 21 | 15 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-16 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-02-13 | 29 | 21 | 2024-02-13 | 2024-02-13 | 1 | 1 | 36 | 26 | 51 | 37 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 261.81 | -8.55 | Unknown | Unknown | 13.34 | 257.02 | 3981 | 231.98 | 261.81 | -29.83 | Yes | N/A | N/A | 2023-12-04 | 2024-01-09 | 37 | 27 | 2024-01-09 | 2024-01-12 | 4 | 4 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-06-14 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-01 | 18 | 12 | 2024-07-01 | 2024-07-01 | 1 | 1 | 192 | 138 | 23 | 17 | 215 | 155 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 321.43 | -6.46 | Unknown | Unknown | Unknown | 327.89 | Unknown | 2035.01 | 321.43 | 1713.58 | Yes | N/A | N/A | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-07 | 16 | 12 | 2024-12-18 | 2025-05-15 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-23 | 9 | 7 | 2025-05-23 | 2025-05-23 | 1 | 1 | 150 | 108 | 27 | 21 | 177 | 129 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-10 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 526.73 | -10.19 | Unknown | Unknown | Unknown | 536.92 | Unknown | 1784.77 | 526.73 | 1258.04 | Yes | N/A | N/A | 2025-01-08 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-10 | 15 | 11 | 2025-01-10 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-04 | 22 | 16 | 2025-01-10 | 2025-03-11 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-21 | 11 | 9 | 2025-03-21 | 2025-03-21 | 1 | 1 | 61 | 43 | 49 | 37 | 110 | 80 | Steps 2,3,5,6,7 | 25 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -645 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 637.55 | Unknown | Unknown | Unknown | Unknown | 637.55 | 3981 | 1511.67 | 637.55 | 874.12 | Yes | N/A | N/A | 2024-10-10 | 2024-10-23 | 14 | 10 | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1 | 1 | 14 | 10 | 3 | 3 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2638.25 | 2638.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-20 | -201 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1451.36 | -8.92 | Unknown | Unknown | 94.09 | 1366.19 | 3981 | 995.25 | 1451.36 | -456.11 | Yes | N/A | N/A | 2023-02-22 | 2023-04-19 | 57 | 41 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-04-02 | 1 | 1 | 57 | 41 | 1 | 1 | 58 | 42 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -156 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | -8.06 | -6.06 | Unknown | Unknown | Unknown | -2 | Unknown | 484.71 | -8.06 | 492.77 | Yes | N/A | N/A | 2023-09-29 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-09-29 | 67 | 49 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-12-14 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-02-13 | 62 | 44 | 2024-02-13 | 2024-02-13 | 1 | 1 | 77 | 55 | 130 | 94 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-11 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 34.72 | Unknown | Unknown | Unknown | Unknown | 34.72 | 3981 | 1747.83 | 34.72 | 1713.11 | Yes | N/A | N/A | 2024-05-07 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-07-24 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-31 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-19 | 27 | 19 | 2024-08-19 | 2024-08-19 | 1 | 1 | 8 | 6 | 112 | 80 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 542.05 | 542.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 18 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 438.37 | -4.15 | Unknown | Unknown | 16.96 | 425.56 | 3885 | 552.02 | 438.37 | 113.65 | Yes | N/A | N/A | 2023-12-05 | 2023-12-15 | 11 | 9 | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-18 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-03-15 | 58 | 42 | 2024-03-15 | 2024-03-19 | 5 | 3 | 46 | 34 | 64 | 46 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 328.66 | 190.31 | Unknown | Unknown | Unknown | 138.35 | 3981 | 186.52 | 328.66 | -142.14 | Yes | N/A | N/A | 2024-07-17 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-07-30 | 79 | 57 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-12 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-09-12 | 1 | 1 | 2024-09-12 | 2024-09-12 | 1 | 1 | 45 | 33 | 81 | 59 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | -5.25 | -5.31 | Unknown | Unknown | Unknown | 0.06 | Unknown | 158.37 | -5.25 | 163.62 | Yes | N/A | N/A | 2024-01-23 | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-02-08 | 35 | 25 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-08 | 1 | 1 | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-08 | 2024-03-04 | 26 | 18 | 2024-03-04 | 2024-03-04 | 1 | 1 | 1 | 1 | 62 | 44 | 63 | 45 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-18 | 2022-05-18 | 2025-01-02 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 165011.3 | 12162.78 | Unknown | Unknown | 12004.22 | 140844.3 | Unknown | 57210.03 | 165011.3 | -107801.27 | Yes | N/A | N/A | 2022-05-18 | 2024-06-29 | 774 | 553 | 2024-06-29 | 2024-08-08 | 41 | 29 | 2024-07-03 | 2025-03-04 | 7 | 5 | 2024-07-08 | 2024-09-26 | 64 | 48 | 2024-11-14 | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-16 | 33 | 23 | 2025-01-02 | 2025-02-06 | 36 | 26 | 2025-02-06 | 2025-02-06 | 1 | 1 | 781 | 558 | 175 | 127 | 956 | 685 | Steps 2,3,5,6,7 | 275 | 197 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | -170 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | -1309.65 | -6.19 | Unknown | Unknown | -1985 | 681.54 | Unknown | 1984.87 | -1309.65 | 3294.52 | Yes | N/A | N/A | 2023-07-17 | 2023-07-18 | 2 | 2 | 2023-07-18 | 2023-08-04 | 18 | 14 | 2023-08-04 | 2023-08-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-10-05 | 59 | 43 | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-05 | 2023-10-06 | 2 | 2 | 2023-10-06 | 2023-10-06 | 1 | 1 | 66 | 48 | 21 | 17 | 87 | 65 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 39.63 | -0.31 | Unknown | Unknown | Unknown | 39.94 | 3981 | 1555.45 | 39.63 | 1515.82 | Yes | N/A | N/A | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-11 | 19 | 13 | 2024-11-11 | 2024-11-11 | 1 | 1 | 24 | 18 | 21 | 15 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 596 | 596 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | 271 | 195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3819.13 | 312.48 | Unknown | 25.24 | Unknown | 3481.41 | 244295 | 7199.98 | 3819.13 | 3380.85 | Yes | N/A | N/A | 2023-12-07 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2024-10-09 | 336 | 240 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-10 | Unknown | Unknown | 0 | 0 | 336 | 240 | 336 | 240 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 43652 | 43652 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-03 | -130 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.47 | -10.31 | Unknown | Unknown | Unknown | 6.84 | Unknown | 646.61 | -3.47 | 650.08 | Yes | N/A | N/A | 2023-01-25 | 2023-02-06 | 13 | 9 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 13 | 9 | 1 | 1 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -52 | -39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | 1236.58 | -11.78 | Unknown | Unknown | 216.71 | 1031.65 | 3981 | 1179.62 | 1236.58 | -56.96 | Yes | N/A | N/A | 2023-08-15 | 2023-08-31 | 17 | 13 | 2023-08-31 | 2023-09-08 | 9 | 7 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2024-03-28 | 203 | 145 | Unknown | 2024-04-04 | Unknown | Unknown | 2024-03-28 | 2024-04-15 | 19 | 13 | 2024-04-15 | 2024-04-15 | 1 | 1 | 220 | 158 | 29 | 21 | 249 | 179 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 228 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-08-15 | IOU Designed & Installed | N/A | No | N/A | 496.16 | -13.78 | Unknown | Unknown | Unknown | 509.94 | Unknown | 1292.25 | 496.16 | 796.09 | Yes | N/A | N/A | 2023-06-07 | 2023-06-08 | 2 | 2 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-11 | 2 | 2 | 2023-06-08 | 2023-08-15 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-08-16 | 2 | 2 | 2023-08-16 | 2023-08-16 | 1 | 1 | 71 | 51 | 5 | 5 | 76 | 56 | Steps 2,3,5,6,7 | 64 | 46 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -620 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 1803.34 | Unknown | Unknown | Unknown | 11.05 | 1792.29 | 3981 | 1376.75 | 1803.34 | -426.59 | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-14 | 11 | 9 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-01-17 | 66 | 48 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-01-17 | 2025-01-21 | 5 | 3 | 2025-01-21 | 2025-01-21 | 1 | 1 | 67 | 49 | 17 | 13 | 84 | 62 | Steps 2,3,5,6,7 | 45 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | -206 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-08-03 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 2740.88 | 695.89 | Unknown | Unknown | Unknown | 2044.99 | Unknown | 1560.92 | 2740.88 | -1179.96 | Yes | N/A | N/A | 2023-07-31 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-08-03 | 64 | 46 | 2023-08-03 | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-25 | 7 | 5 | 2023-08-03 | 2023-10-19 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-11-02 | 15 | 11 | 2023-11-02 | 2023-11-02 | 1 | 1 | 78 | 56 | 87 | 63 | 165 | 119 | Steps 2,3,5,6,7 | 83 | 59 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 227 | 162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 834.46 | 1415.78 | Unknown | 278.67 | -1538 | 678.01 | Unknown | 1537.69 | 834.46 | 703.23 | Yes | N/A | N/A | 2024-03-14 | 2024-03-15 | 2 | 2 | 2024-03-15 | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-21 | 5 | 3 | 2024-04-22 | 2024-05-17 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 7 | 5 | 27 | 21 | 34 | 26 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | -312 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-11 | Unknown | 2023-03-13 | IOU Designed & Installed | N/A | No | N/A | -1259.54 | -12.35 | Unknown | Unknown | -1255.35 | 8.16 | Unknown | 1477.76 | -1259.54 | 2737.3 | Yes | N/A | N/A | 2023-02-11 | 2023-02-11 | 1 | 0 | 2023-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-11 | 2023-03-13 | 31 | 21 | Unknown | 2023-03-13 | Unknown | Unknown | 2023-03-13 | 2023-03-31 | 19 | 15 | 2023-03-31 | 2023-03-17 | Unknown | Unknown | 32 | 21 | 19 | 15 | 51 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 83 | 60 | No | 2022-12-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-12-12 | 2023-08-22 | IOU Designed & Installed | N/A | Yes | 163 | 1107.43 | 419.8 | Unknown | Unknown | Unknown | 687.63 | 3885 | 569.15 | 1107.43 | -538.28 | Yes | N/A | N/A | 2022-10-19 | 2023-05-24 | 218 | 156 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-21 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-08-23 | 2 | 2 | 2023-08-23 | 2023-08-23 | 1 | 1 | 218 | 156 | 3 | 3 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | -662 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-20 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 520.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-06-10 | 27 | 19 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-26 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-06-28 | 3 | 2 | 2025-06-28 | 2025-06-28 | 1 | 0 | 17 | 13 | 31 | 21 | 48 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-09-03 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 2.94 | Unknown | Unknown | Unknown | Unknown | 2.94 | Unknown | 1050.75 | 2.94 | 1047.81 | Yes | N/A | N/A | 2024-08-30 | 2024-09-03 | 5 | 3 | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-01 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-16 | 16 | 12 | 2024-10-16 | 2024-10-16 | 1 | 1 | 34 | 24 | 18 | 14 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -96 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5207.03 | 4383.5 | Unknown | 2376.94 | -3712 | 2158.59 | Unknown | 3711.73 | 5207.03 | -1495.3 | Yes | N/A | N/A | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | LAKESIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-25 | 336 | 241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 601.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-10 | 1 | 1 | 2024-12-10 | 2025-01-23 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-02 | 8 | 6 | 2025-01-23 | 2024-12-31 | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | 2025-02-24 | 1 | 1 | 1 | 1 | 55 | 41 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 228 | 228 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-20 | 2023-08-21 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 1506.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-20 | 2023-08-21 | 2 | 1 | 2023-08-21 | 2025-03-06 | 564 | 404 | 2025-03-06 | 2024-01-11 | Unknown | Unknown | 2023-08-24 | 2024-02-14 | 61 | 43 | 2024-02-13 | 2024-03-07 | 24 | 18 | Unknown | 2024-02-14 | Unknown | Unknown | 2024-03-07 | 2024-03-08 | 2 | 2 | 2024-03-08 | 2024-03-08 | 1 | 1 | 26 | 19 | 628 | 450 | 654 | 469 | Steps 2,3,5,6,7 | 141 | 101 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 960 | 687 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2024-08-21 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 27962.88 | 1925.34 | Unknown | Unknown | 479.16 | 25558.38 | 152336 | 34811.23 | 27962.88 | 6848.35 | Yes | N/A | N/A | 2022-09-01 | 2023-03-28 | 209 | 149 | 2023-03-28 | 2023-08-28 | 154 | 110 | 2023-04-04 | 2023-08-18 | 4 | 4 | 2023-04-17 | 2023-10-10 | 55 | 41 | 2023-09-05 | Unknown | Unknown | Unknown | 2023-09-05 | 2024-04-03 | 212 | 152 | 2024-08-21 | 2024-09-18 | 29 | 21 | 2024-09-18 | 2024-09-18 | 1 | 1 | 213 | 153 | 451 | 325 | 664 | 478 | Steps 2,3,5,6,7 | 304 | 218 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -12 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2024-07-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 132.45 | 9.77 | Unknown | Unknown | -1383.26 | 1505.94 | Unknown | 938.61 | 132.45 | 806.16 | Yes | N/A | N/A | 2023-07-10 | 2024-07-31 | 388 | 278 | 2024-07-31 | 2024-08-14 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2025-04-30 | 260 | 186 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 648 | 464 | 16 | 12 | 664 | 476 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -472 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-07-10 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -13.56 | -11.32 | Unknown | Unknown | Unknown | -2.24 | 3981 | 872.23 | -13.56 | 885.79 | Yes | N/A | N/A | 2023-06-13 | 2023-07-10 | 28 | 20 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-12-04 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-02-12 | 71 | 51 | 2024-02-12 | 2023-12-13 | Unknown | Unknown | 176 | 126 | 72 | 52 | 248 | 178 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 304 | 217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 5578.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-04-22 | 6 | 4 | 2024-04-22 | 2024-04-22 | 1 | 1 | 1 | 1 | 7 | 5 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SB 1187-G1 SOLANA HGLD PH2 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 611 | 437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-07 | 2021-09-07 | 2025-04-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 24538.02 | 1667.8 | Unknown | Unknown | 2179.76 | 20690.46 | 188957 | 23222.66 | 24538.02 | -1315.36 | Yes | N/A | N/A | 2021-09-07 | 2024-01-24 | 870 | 622 | 2024-01-24 | 2024-09-10 | 231 | 165 | 2024-01-26 | 2025-04-16 | 368 | 264 | 2024-08-02 | 2024-09-12 | 42 | 30 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-19 | 2025-04-10 | 113 | 81 | 2025-04-25 | 2025-06-17 | 54 | 38 | 2025-06-17 | 2025-06-17 | 1 | 1 | 1238 | 886 | 441 | 315 | 1679 | 1201 | Steps 2,3,5,6,7 | 485 | 345 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 655 | 468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2025-01-14 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 4225.88 | Unknown | Unknown | Unknown | -1061 | 5286.88 | Unknown | 956.13 | 4225.88 | -3269.75 | Yes | N/A | N/A | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2025-01-31 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-05 | 23 | 17 | 2025-01-31 | 2025-02-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-26 | 34 | 24 | 2025-03-26 | 2025-03-24 | Unknown | Unknown | 8 | 6 | 117 | 85 | 125 | 91 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -589 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 61.69 | -7.59 | Unknown | Unknown | Unknown | 69.28 | Unknown | 2156.65 | 61.69 | 2094.96 | Yes | N/A | N/A | 2023-11-10 | 2023-09-01 | Unknown | Unknown | 2023-09-01 | 2023-12-13 | 104 | 74 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-04 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-05 | 2 | 2 | 2024-01-05 | 2024-01-05 | 1 | 1 | 23 | 17 | 107 | 77 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 621.51 | -6.02 | Unknown | Unknown | -401.35 | 1028.88 | Unknown | 373.97 | 621.51 | -247.54 | Yes | N/A | N/A | 2023-03-03 | 2023-04-14 | 43 | 31 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-10 | 1 | 1 | 43 | 31 | 1 | 1 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | -562 | -403 | No | 2023-02-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | Yes | 14 | -1.76 | -1.29 | Unknown | Unknown | Unknown | -0.47 | Unknown | 363.72 | -1.76 | 365.48 | Yes | N/A | N/A | 2023-02-17 | 2023-03-03 | 15 | 11 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-05-16 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | -436 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 485.74 | -12.44 | Unknown | Unknown | 5.82 | 492.36 | 3981 | 1107.76 | 485.74 | 622.02 | Yes | N/A | N/A | 2023-06-20 | 2023-07-13 | 24 | 18 | 2023-07-13 | 2023-09-11 | 61 | 43 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2024-01-09 | 121 | 87 | Unknown | 2024-01-08 | Unknown | Unknown | 2024-01-09 | 2024-01-11 | 3 | 3 | 2024-01-11 | 2024-01-11 | 1 | 1 | 145 | 105 | 65 | 47 | 210 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 46.65 | -0.94 | Unknown | Unknown | Unknown | 47.59 | Unknown | 2036.01 | 46.65 | 1989.36 | Yes | N/A | N/A | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | 2024-12-19 | 7 | 5 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-24 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | 2023-06-05 | IOU Designed & Installed | N/A | No | N/A | -839.49 | 2196.64 | Unknown | 259.94 | -4319 | 1022.93 | Unknown | 4318.74 | -839.49 | 5158.23 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-10-27 | 145 | 105 | 2023-10-27 | 2023-10-27 | 1 | 1 | 1 | 1 | 146 | 106 | 147 | 107 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-16 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 1211.9 | -37.76 | Unknown | Unknown | Unknown | 1249.66 | 3981 | 1095.35 | 1211.9 | -116.55 | Yes | N/A | N/A | 2024-04-10 | 2024-04-17 | 8 | 6 | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-21 | 35 | 25 | 2024-04-17 | 2024-04-29 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-06-17 | 50 | 36 | 2024-06-17 | 2024-06-17 | 1 | 1 | 21 | 15 | 87 | 63 | 108 | 78 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | -437 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.17 | -5.31 | Unknown | Unknown | Unknown | -0.86 | Unknown | 153.83 | -6.17 | 160 | Yes | N/A | N/A | 2023-06-21 | 2023-08-04 | 45 | 33 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-01-19 | 1 | 1 | 45 | 33 | 2 | 2 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -349 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 50.35 | Unknown | Unknown | Unknown | Unknown | 50.35 | Unknown | 2162.65 | 50.35 | 2112.3 | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-15 | 8 | 6 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2 | 2 | 10 | 8 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 46.24 | Unknown | Unknown | Unknown | Unknown | 46.24 | 3981 | 1530.02 | 46.24 | 1483.78 | Yes | N/A | N/A | 2024-09-17 | 2024-09-25 | 9 | 7 | 2024-09-25 | 2024-10-04 | 10 | 8 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2024-12-26 | Unknown | Unknown | 9 | 7 | 10 | 8 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -250 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2025-03-30 | IOU Designed & Installed | N/A | No | N/A | 140.34 | -28.33 | Unknown | Unknown | 107.2 | 61.47 | 3981 | 4966.31 | 140.34 | 4825.97 | Yes | N/A | N/A | 2024-04-25 | 2024-05-10 | 16 | 12 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-03-30 | 322 | 230 | Unknown | Unknown | Unknown | Unknown | 2025-03-30 | 2025-08-15 | 139 | 100 | 2025-08-15 | 2024-07-08 | Unknown | Unknown | 338 | 242 | 140 | 101 | 478 | 343 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-22 | 832 | 595 | No | 2022-07-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-21 | 2022-07-22 | Unknown | IOU Designed & Installed | N/A | Yes | 239 | 59.19 | Unknown | Unknown | Unknown | Unknown | 59.19 | 3885 | 2033.31 | 59.19 | 1974.12 | Yes | N/A | N/A | 2022-07-21 | 2023-03-17 | 240 | 172 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-07-22 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-01 | Unknown | Unknown | 240 | 172 | 0 | 0 | 240 | 172 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1567.92 | -30.79 | Unknown | Unknown | Unknown | 1598.71 | 3981 | 1133 | 1567.92 | -434.92 | Yes | N/A | N/A | 2024-04-03 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | 2024-04-16 | 43 | 31 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-19 | Unknown | Unknown | 0 | 0 | 43 | 31 | 43 | 31 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -569.64 | -11 | Unknown | Unknown | -1146 | 587.36 | Unknown | 1933.02 | -569.64 | 2502.66 | Yes | N/A | N/A | 2024-09-10 | 2024-09-13 | 4 | 4 | 2024-09-13 | 2024-09-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-17 | 30 | 22 | 2024-09-20 | 2024-11-01 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-19 | Unknown | Unknown | 47 | 35 | 38 | 28 | 85 | 63 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.01 | -14.64 | Unknown | Unknown | Unknown | 9.63 | 6123 | 760.72 | -5.01 | 765.73 | Yes | N/A | N/A | 2023-02-16 | 2023-02-16 | 1 | 1 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-05-11 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-06-20 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 34.81 | Unknown | Unknown | Unknown | Unknown | 34.81 | 3981 | 1380.97 | 34.81 | 1346.16 | Yes | N/A | N/A | 2024-05-16 | 2024-06-05 | 21 | 15 | 2024-06-05 | 2024-06-20 | 16 | 12 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-02 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-25 | 24 | 18 | 2024-07-25 | 2024-07-25 | 1 | 1 | 34 | 24 | 41 | 31 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-11-04 | IOU Designed & Installed | N/A | No | N/A | 2133.14 | 1089.63 | Unknown | 332.04 | Unknown | 711.47 | 3981 | 158.51 | 2133.14 | -1974.63 | Yes | N/A | N/A | 2023-10-04 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2023-10-12 | 17 | 13 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-04 | 24 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-11-04 | 2023-11-17 | 14 | 10 | 2023-11-17 | 2023-11-17 | 1 | 1 | 24 | 17 | 32 | 24 | 56 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -285 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 0.72 | -9.51 | Unknown | Unknown | Unknown | 10.23 | Unknown | 564.71 | 0.72 | 563.99 | Yes | N/A | N/A | 2023-11-27 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-11-27 | 42 | 30 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-11-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-11 | 15 | 11 | 2023-12-11 | 2023-12-11 | 1 | 1 | 1 | 1 | 58 | 42 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-02 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-14 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 5266.54 | -63.71 | Unknown | Unknown | 33 | 5297.25 | 3981 | 1098.97 | 5266.54 | -4167.57 | Yes | N/A | N/A | 2024-02-01 | 2024-03-26 | 55 | 39 | 2024-03-26 | 2024-03-29 | 4 | 4 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-05-10 | 43 | 31 | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-10 | 2024-05-22 | 13 | 9 | 2024-05-22 | 2024-05-21 | Unknown | Unknown | 98 | 70 | 17 | 13 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-06 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-08 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 9327.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-06-06 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-23 | 12 | 8 | 2025-06-23 | 2025-06-23 | 1 | 1 | 0 | 0 | 74 | 54 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | -1988.86 | -15.52 | Unknown | Unknown | -2878 | 904.66 | Unknown | 2733.84 | -1988.86 | 4722.7 | Yes | N/A | N/A | 2024-12-10 | 2024-12-17 | 8 | 6 | 2024-12-17 | 2024-12-20 | 4 | 4 | 2024-12-20 | 2024-12-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-03-21 | 85 | 61 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-21 | 2025-04-03 | 14 | 10 | 2025-04-03 | 2025-04-01 | Unknown | Unknown | 101 | 73 | 18 | 14 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-09-09 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 60.01 | Unknown | Unknown | Unknown | Unknown | 60.01 | 3981 | 1489.86 | 60.01 | 1429.85 | Yes | N/A | N/A | 2024-06-28 | 2024-09-06 | 71 | 51 | 2024-09-06 | 2024-10-01 | 26 | 18 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-02-26 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-10-22 | 1 | 1 | 220 | 158 | 27 | 19 | 247 | 177 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | -97 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 704.56 | -10.47 | Unknown | Unknown | 12.15 | 702.88 | 3981 | 701.9 | 704.56 | -2.66 | Yes | N/A | N/A | 2023-07-05 | 2023-07-05 | 1 | 1 | 2023-07-05 | 2023-08-01 | 28 | 20 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-12-05 | 127 | 91 | Unknown | 2023-11-21 | Unknown | Unknown | 2023-12-05 | 2023-12-15 | 11 | 9 | 2023-12-15 | 2023-12-15 | 1 | 1 | 128 | 92 | 40 | 30 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 523.26 | -7.03 | Unknown | Unknown | 3.71 | 526.58 | 3941 | 1278.15 | 523.26 | 754.89 | Yes | N/A | N/A | 2023-11-15 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-11-15 | 49 | 35 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-25 | 36 | 26 | 2024-01-25 | 2024-01-25 | 1 | 1 | 37 | 27 | 86 | 62 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-02 | -676 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1134.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-05-29 | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-25 | 6 | 4 | 2025-06-25 | 2025-06-25 | 1 | 1 | 1 | 1 | 7 | 5 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-06 | -253 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-23 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 1872.08 | Unknown | Unknown | Unknown | 11.77 | 1860.31 | 3981 | 1265.58 | 1872.08 | -606.5 | Yes | N/A | N/A | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | 2025-02-04 | 14 | 10 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-04-23 | 79 | 57 | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-23 | 2025-04-28 | 6 | 4 | 2025-04-28 | 2025-04-28 | 1 | 1 | 80 | 58 | 21 | 15 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -253 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-28 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | -430.05 | 192.82 | Unknown | Unknown | -1184 | 561.13 | Unknown | 900.93 | -430.05 | 1330.98 | Yes | N/A | N/A | 2025-04-25 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-28 | 6 | 4 | 2025-04-28 | 2025-05-16 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-18 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 53 | 39 | 8 | 6 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -31 | -22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2024-08-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 118419.57 | 24980.56 | Unknown | Unknown | -17187.95 | 110626.96 | 333186.47 | 95049.84 | 118419.57 | -23369.73 | Yes | N/A | N/A | 2023-08-16 | 2023-12-08 | 115 | 83 | 2023-12-08 | 2024-03-19 | 103 | 73 | 2023-12-18 | 2024-03-14 | 32 | 24 | 2024-03-15 | 2024-03-22 | 8 | 6 | 2024-03-19 | 2024-07-26 | 130 | 94 | 2024-04-11 | 2024-07-30 | 111 | 79 | 2024-08-13 | 2024-09-06 | 25 | 19 | 2024-09-06 | 2024-08-31 | Unknown | Unknown | 277 | 201 | 247 | 177 | 524 | 378 | Steps 2,3,5,6,7 | 201 | 145 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 236 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-06-11 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 9490.61 | 3620.94 | Unknown | Unknown | -6668 | 12537.67 | Unknown | 13336.75 | 9490.61 | 3846.14 | Yes | N/A | N/A | 2024-04-22 | 2024-05-02 | 11 | 9 | 2024-05-02 | 2024-07-03 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-06-29 | 2024-07-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-24 | 19 | 13 | 2024-09-24 | 2024-09-24 | 1 | 1 | 11 | 9 | 96 | 68 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-18 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 2668.69 | 665.15 | Unknown | 204.56 | Unknown | 1798.98 | Unknown | 1774.35 | 2668.69 | -894.34 | Yes | N/A | N/A | 2024-10-28 | 2024-10-29 | 2 | 2 | 2024-10-29 | 2024-11-13 | 16 | 12 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-03-31 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-04 | 5 | 5 | 2025-04-04 | 2025-04-04 | 1 | 1 | 141 | 101 | 22 | 18 | 163 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 181.05 | 181.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 246 | 177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 612.69 | -10.71 | Unknown | Unknown | Unknown | 623.4 | 3981 | 917.58 | 612.69 | 304.89 | Yes | N/A | N/A | 2024-04-02 | 2024-05-16 | 45 | 33 | 2024-05-16 | 2024-06-03 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-05 | 1 | 1 | 45 | 33 | 20 | 14 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | 40 | 30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-24 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | -731.54 | 559.58 | Unknown | 57.66 | -1735 | 386.22 | Unknown | 1735.01 | -731.54 | 2466.55 | Yes | N/A | N/A | 2024-10-17 | 2024-11-05 | 20 | 14 | 2024-11-05 | 2024-12-12 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-31 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-05 | 2 | 2 | 2025-02-05 | 2025-02-21 | 17 | 13 | 71 | 51 | 57 | 43 | 128 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-13 | 7 | 5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13040.73 | Unknown | Unknown | Unknown | Unknown | 13040.73 | 3981 | 1009.67 | 13040.73 | -12031.06 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-01-20 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 404 | 289 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1969.66 | Unknown | Unknown | Unknown | 80.76 | 1888.9 | 0 | 1849.87 | 1969.66 | -119.79 | Yes | N/A | N/A | 2023-04-20 | 2023-07-03 | 75 | 53 | 2023-07-03 | 2023-07-28 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2024-01-24 | 17 | 13 | 2023-07-28 | 2024-07-16 | 355 | 253 | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-07-31 | Unknown | Unknown | 430 | 306 | 43 | 33 | 473 | 339 | Steps 2,3,5,6,7 | 180 | 128 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-14 | 487 | 348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1396.42 | -27.11 | Unknown | Unknown | Unknown | 1423.53 | 5562 | 784.87 | 1396.42 | -611.55 | Yes | N/A | N/A | 2022-12-20 | 2024-01-09 | 386 | 276 | 2024-01-09 | 2025-02-04 | 393 | 281 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-03 | 15 | 11 | 2025-02-04 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 386 | 276 | 409 | 293 | 795 | 569 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-11 | 884 | 631 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 566.56 | -8.14 | Unknown | Unknown | 16.87 | 557.83 | 1091 | 238.98 | 566.56 | -327.58 | Yes | N/A | N/A | 2023-11-22 | 2023-11-13 | Unknown | Unknown | 2023-11-13 | 2024-02-12 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-05-03 | 82 | 60 | Unknown | 2024-03-07 | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-13 | Unknown | Unknown | 82 | 60 | 92 | 66 | 174 | 126 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -513 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 690.12 | -19.18 | Unknown | Unknown | Unknown | 709.3 | Unknown | 817.51 | 690.12 | 127.39 | Yes | N/A | N/A | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-26 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-13 | 19 | 13 | 2024-02-13 | 2024-07-25 | 164 | 118 | 23 | 17 | 184 | 132 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 1869 | 1336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.24 | -6.99 | Unknown | Unknown | Unknown | -2.25 | Unknown | 744.64 | -9.24 | 753.88 | Yes | N/A | N/A | 2023-09-01 | 2023-09-05 | 5 | 3 | 2023-09-05 | 2023-09-11 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 5 | 3 | 8 | 6 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 128 | 128 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 13 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | Unknown | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 704.47 | -16.66 | Unknown | Unknown | 8.6 | 712.53 | 3981 | 2313.32 | 704.47 | 1608.85 | Yes | N/A | N/A | 2023-03-23 | 2023-05-03 | 42 | 30 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2024-01-09 | 293 | 209 | Unknown | 2024-01-18 | Unknown | Unknown | 2024-01-09 | 2024-02-13 | 36 | 26 | 2024-02-13 | 2024-02-14 | 2 | 2 | 335 | 239 | 38 | 28 | 373 | 267 | Steps 2,3,5,6,7 | 9 | 7 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 719.05 | 719.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 1275 | Unknown | Unknown | Unknown | 13.16 | 1261.84 | 3885 | 1166.61 | 1275 | -108.39 | Yes | N/A | N/A | 2023-11-10 | 2024-08-16 | 281 | 201 | 2024-08-16 | 2024-10-07 | 53 | 37 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-03-05 | 150 | 108 | Unknown | 2025-02-28 | Unknown | Unknown | 2025-03-05 | 2025-03-18 | 14 | 10 | 2025-03-18 | 2025-03-17 | Unknown | Unknown | 431 | 309 | 67 | 47 | 498 | 356 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1904.62 | -18.26 | Unknown | Unknown | Unknown | 1922.88 | Unknown | 1195.53 | 1904.62 | -709.09 | Yes | N/A | N/A | 2024-04-24 | 2024-05-13 | 20 | 14 | 2024-05-13 | 2024-08-20 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-16 | 32 | 22 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | 20 | 14 | 133 | 95 | 153 | 109 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -423 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 460.09 | -4.33 | Unknown | Unknown | 29.03 | 435.39 | 3981 | 719.4 | 460.09 | 259.31 | Yes | N/A | N/A | 2023-05-05 | 2023-05-05 | 1 | 1 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-10-23 | 172 | 122 | Unknown | 2023-10-13 | Unknown | Unknown | 2023-10-23 | 2023-11-08 | 17 | 13 | 2023-11-08 | 2023-11-08 | 1 | 1 | 173 | 123 | 18 | 14 | 191 | 137 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 274 | 197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | Unknown | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1711.04 | Unknown | Unknown | Unknown | 46.79 | 1664.25 | 2875.23 | 834.36 | 1711.04 | -876.68 | Yes | N/A | N/A | 2024-08-05 | 2024-08-14 | 10 | 8 | 2024-08-14 | 2024-08-26 | 13 | 9 | 2024-08-30 | 2024-09-03 | 5 | 3 | 2024-08-29 | 2024-09-23 | 23 | 17 | 2024-08-26 | 2025-01-16 | 144 | 104 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-21 | 2025-01-28 | 8 | 6 | 2025-01-28 | 2025-04-01 | 64 | 46 | 159 | 115 | 108 | 78 | 267 | 193 | Steps 2,3,5,6,7 | 33 | 23 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -321 | -230 | No | 2023-09-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | 2024-04-01 | IOU Designed & Installed | N/A | Yes | 197 | 815.19 | -14.67 | Unknown | Unknown | 13.64 | 816.22 | 3981 | 222.89 | 815.19 | -592.3 | Yes | N/A | N/A | 2023-09-13 | 2024-03-28 | 198 | 142 | 2024-03-28 | 2023-10-02 | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2024-04-01 | 183 | 131 | Unknown | 2024-04-05 | Unknown | Unknown | 2024-04-01 | 2024-04-10 | 10 | 8 | 2024-04-10 | 2024-04-09 | Unknown | Unknown | 381 | 273 | 10 | 8 | 391 | 281 | Steps 2,3,5,6,7 | 4 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | -171 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-13 | 2023-05-13 | IOU Designed & Installed | N/A | No | N/A | 1977.04 | 536.1 | Unknown | 470.76 | Unknown | 970.18 | 3991 | 1551.51 | 1977.04 | -425.53 | Yes | N/A | N/A | 2023-01-10 | 2023-02-10 | 32 | 24 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-05-13 | 93 | 66 | Unknown | 2023-05-02 | Unknown | Unknown | 2023-05-13 | 2023-05-16 | 4 | 2 | 2023-05-16 | 2023-05-16 | 1 | 1 | 125 | 90 | 5 | 3 | 130 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -632 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-29 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | -13.72 | -8.9 | Unknown | Unknown | Unknown | -4.82 | Unknown | 997.93 | -13.72 | 1011.65 | Yes | N/A | N/A | 2025-01-15 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-29 | 16 | 12 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-05 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-27 | 23 | 17 | 2025-03-27 | 2025-03-27 | 1 | 1 | 36 | 26 | 40 | 30 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-07 | -347 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 126.46 | -18.05 | Unknown | Unknown | Unknown | 144.51 | 3981 | 830.72 | 126.46 | 704.26 | Yes | N/A | N/A | 2023-04-21 | 2023-04-21 | 1 | 1 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-01-26 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2025-02-12 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | -1796 | -16.83 | Unknown | Unknown | -1792 | 12.83 | Unknown | 1517.93 | -1796 | 3313.93 | Yes | N/A | N/A | 2024-03-08 | 2025-02-12 | 342 | 244 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-03-17 | 34 | 24 | 2025-02-12 | 2025-02-25 | 14 | 10 | 2025-03-17 | 2025-03-19 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-01 | 14 | 10 | 2025-04-01 | 2025-04-01 | 1 | 1 | 379 | 271 | 30 | 22 | 409 | 293 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -626 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-24 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 507.56 | -10.2 | Unknown | Unknown | Unknown | 517.76 | 3981 | 1740.76 | 507.56 | 1233.2 | Yes | N/A | N/A | 2025-02-11 | 2025-03-07 | 25 | 19 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-05-05 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-07 | 3 | 3 | 2025-05-07 | 2025-05-07 | 1 | 1 | 85 | 61 | 5 | 5 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 127760 | 127760 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-20 | 235 | 170 | No | 2024-01-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-05-06 | 2024-06-25 | IOU Designed & Installed | N/A | Yes | 140 | 19.73 | -15.2 | Unknown | Unknown | Unknown | 34.93 | 7962 | 1160.69 | 19.73 | 1140.96 | Yes | N/A | N/A | 2024-01-10 | 2024-05-23 | 135 | 97 | 2024-05-23 | 2024-05-29 | 7 | 5 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-25 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-15 | 21 | 15 | 2024-07-15 | 2024-07-12 | Unknown | Unknown | 186 | 134 | 28 | 20 | 214 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-06-19 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 36.91 | Unknown | Unknown | Unknown | Unknown | 36.91 | 3981 | 1380.51 | 36.91 | 1343.6 | Yes | N/A | N/A | 2024-05-23 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-06-19 | 57 | 41 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-08-02 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-19 | 18 | 12 | 2024-08-19 | 2024-08-19 | 1 | 1 | 45 | 33 | 76 | 54 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | -365 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | 56.72 | -13.27 | Unknown | Unknown | Unknown | 69.99 | 3941 | 540.68 | 56.72 | 483.96 | Yes | N/A | N/A | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-01 | 2 | 2 | 2023-08-01 | 2023-08-01 | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -274 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 17.66 | -13.61 | Unknown | Unknown | Unknown | 31.27 | Unknown | 1442.65 | 17.66 | 1424.99 | Yes | N/A | N/A | 2024-06-12 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-09 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-16 | 8 | 6 | 2024-07-16 | 2024-07-16 | 1 | 1 | 28 | 20 | 10 | 8 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | 82 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 22.71 | -4.59 | Unknown | Unknown | 17.53 | 9.77 | 0 | 676.53 | 22.71 | 653.82 | Yes | N/A | N/A | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2024-03-01 | 352 | 252 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2025-04-03 | 399 | 285 | 2025-04-03 | 2024-05-30 | Unknown | Unknown | 353 | 253 | 399 | 285 | 752 | 538 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | 265 | 190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2024-01-18 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | 346.2 | -12.27 | Unknown | Unknown | Unknown | 358.47 | 3981 | 797.96 | 346.2 | 451.76 | Yes | N/A | N/A | 2023-11-15 | 2023-12-07 | 23 | 17 | 2023-12-07 | 2024-01-18 | 43 | 31 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-21 | 22 | 16 | 2024-03-21 | 2024-03-21 | 1 | 1 | 66 | 48 | 66 | 48 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -513 | -367 | No | 2023-01-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | 2023-03-29 | IOU Designed & Installed | N/A | Yes | 36 | 978.32 | 234.26 | Unknown | 155.78 | Unknown | 588.28 | 3241 | 701.95 | 978.32 | -276.37 | Yes | N/A | N/A | 2023-01-04 | 2023-02-09 | 37 | 27 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-04 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-03-30 | 2 | 2 | 2023-03-30 | 2023-03-30 | 1 | 1 | 37 | 27 | 3 | 3 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-23 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 242.53 | Unknown | Unknown | Unknown | Unknown | 242.53 | Unknown | 444.8 | 242.53 | 202.27 | Yes | N/A | N/A | 2024-07-22 | 2024-07-23 | 2 | 2 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-28 | 35 | 25 | 2024-07-31 | 2024-09-27 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-07 | 11 | 7 | 2024-10-07 | 2024-10-07 | 1 | 1 | 61 | 45 | 47 | 33 | 108 | 78 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN MARCOS | N/A | 11.5 | 11.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 593.74 | -3.23 | Unknown | Unknown | Unknown | 596.97 | 3981 | 2243.52 | 593.74 | 1649.78 | Yes | N/A | N/A | 2024-08-07 | 2024-10-31 | 86 | 62 | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-08 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-21 | 14 | 10 | 2024-11-21 | 2024-11-20 | Unknown | Unknown | 95 | 69 | 15 | 11 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 569.77 | -10.9 | Unknown | Unknown | Unknown | 580.67 | 3981 | 1690.96 | 569.77 | 1121.19 | Yes | N/A | N/A | 2024-10-16 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-16 | 22 | 16 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-15 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-04 | 20 | 14 | 2024-12-04 | 2024-12-04 | 1 | 1 | 31 | 23 | 43 | 31 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.68 | -23.92 | Unknown | Unknown | Unknown | 32.6 | 17711 | 1928.55 | 8.68 | 1919.87 | Yes | N/A | N/A | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2023-11-16 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-15 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-01-08 | Unknown | Unknown | 31 | 23 | 7 | 5 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | -169 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-27 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | -986.77 | -3.06 | Unknown | Unknown | -987 | 3.29 | Unknown | 882.47 | -986.77 | 1869.24 | Yes | N/A | N/A | 2023-10-19 | 2023-06-02 | Unknown | Unknown | 2023-06-02 | 2023-10-27 | 148 | 106 | 2023-10-27 | 2023-11-09 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-27 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-06 | 10 | 8 | 2023-12-06 | 2023-12-05 | Unknown | Unknown | 33 | 23 | 158 | 114 | 191 | 137 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -397 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 1457.98 | -2.5 | Unknown | Unknown | 16.01 | 1444.47 | 3981 | 1299.41 | 1457.98 | -158.57 | Yes | N/A | N/A | 2024-07-17 | 2024-07-29 | 13 | 9 | 2024-07-29 | 2024-08-07 | 10 | 8 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2025-05-29 | 296 | 212 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-29 | 2025-05-30 | 2 | 2 | 2025-05-30 | 2025-05-30 | 1 | 1 | 309 | 221 | 13 | 11 | 322 | 232 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-17 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-27 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1578.35 | 377.04 | Unknown | 89.69 | Unknown | 1111.62 | 3981 | 1225.48 | 1578.35 | -352.87 | Yes | N/A | N/A | 2024-12-20 | 2024-12-23 | 4 | 2 | 2024-12-23 | 2024-12-27 | 5 | 5 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-02-03 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-18 | 16 | 12 | 2025-02-18 | 2025-02-18 | 1 | 1 | 43 | 29 | 22 | 18 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | 487.02 | -15.32 | Unknown | Unknown | Unknown | 502.34 | 3981 | 823.51 | 487.02 | 336.49 | Yes | N/A | N/A | 2024-01-10 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-01-10 | 23 | 17 | 2024-01-10 | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-18 | 9 | 7 | 2024-01-10 | 2024-03-12 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-04-03 | 23 | 17 | 2024-04-03 | 2024-04-03 | 1 | 1 | 63 | 45 | 56 | 42 | 119 | 87 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -43 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -428.64 | Unknown | Unknown | Unknown | -479 | 50.36 | 3981 | 1994.24 | -428.64 | 2422.88 | Yes | N/A | N/A | 2024-04-25 | 2024-05-29 | 35 | 25 | 2024-05-29 | 2024-07-01 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-12-20 | 173 | 125 | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-16 | Unknown | Unknown | 208 | 150 | 34 | 24 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -275 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 164.11 | -6.56 | Unknown | Unknown | Unknown | 170.67 | Unknown | 811.97 | 164.11 | 647.86 | Yes | N/A | N/A | 2023-12-20 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2023-12-20 | 20 | 14 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-22 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-13 | 23 | 17 | 2024-02-13 | 2024-02-13 | 1 | 1 | 34 | 24 | 44 | 32 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RANCHITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | -191 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | 3215.2 | 966.72 | Unknown | 471.68 | Unknown | 1776.8 | 3981 | 865.6 | 3215.2 | -2349.6 | Yes | N/A | N/A | 2023-06-21 | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-21 | 13 | 9 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2023-08-17 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-09-21 | 36 | 26 | 2023-09-21 | 2023-09-21 | 1 | 1 | 58 | 42 | 50 | 36 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -206.89 | Unknown | Unknown | Unknown | -216 | 9.11 | 0 | 297.38 | -206.89 | 504.27 | Yes | N/A | N/A | 2023-03-24 | 2023-03-06 | Unknown | Unknown | 2023-03-06 | 2024-02-26 | 358 | 256 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-03-28 | 1 | 1 | 0 | 0 | 359 | 257 | 359 | 257 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | PALA | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-29 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-03-27 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 8348.5 | 355.53 | Unknown | Unknown | -753.62 | 8746.59 | 3981 | 1700.03 | 8348.5 | -6648.47 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | 2023-04-06 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-06-07 | 63 | 45 | Unknown | 2023-05-26 | Unknown | Unknown | 2023-05-30 | 2023-07-03 | 35 | 25 | 2023-07-03 | 2023-06-23 | Unknown | Unknown | 64 | 46 | 87 | 63 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -472 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 6679.81 | 1406.86 | Unknown | 75.12 | 15.3 | 5182.53 | 7962 | 3647.57 | 6679.81 | -3032.24 | Yes | N/A | N/A | 2025-02-10 | 2025-02-19 | 10 | 8 | 2025-02-19 | 2025-02-24 | 6 | 4 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-17 | 22 | 16 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-17 | 2025-04-01 | 16 | 12 | 2025-04-01 | 2025-04-01 | 1 | 1 | 32 | 24 | 23 | 17 | 55 | 41 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 188 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2149.5 | -9.21 | Unknown | Unknown | 15.37 | 2143.34 | 3981 | 2161.69 | 2149.5 | 12.19 | Yes | N/A | N/A | 2024-02-02 | 2024-03-15 | 43 | 31 | 2024-03-15 | 2024-05-29 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-03 | 23 | 17 | 2024-05-29 | 2024-08-07 | 71 | 51 | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-08-07 | Unknown | Unknown | 114 | 82 | 99 | 71 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-08-18 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | -4.71 | -9.13 | Unknown | Unknown | Unknown | 4.42 | Unknown | 906.87 | -4.71 | 911.58 | Yes | N/A | N/A | 2023-07-12 | 2023-08-18 | 38 | 28 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-10-02 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-12-04 | 64 | 46 | 2023-12-04 | 2023-12-04 | 1 | 1 | 84 | 60 | 66 | 48 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -562 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | -2.81 | -5.3 | Unknown | Unknown | Unknown | 2.49 | 3961 | 814.08 | -2.81 | 816.89 | Yes | N/A | N/A | 2023-11-14 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2023-11-14 | 8 | 6 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-01-22 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-01-31 | 10 | 8 | 2024-01-31 | 2024-01-26 | Unknown | Unknown | 70 | 50 | 18 | 14 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-04 | 101 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | 2023-10-26 | IOU Designed & Installed | N/A | No | N/A | -0.71 | -0.83 | Unknown | Unknown | Unknown | 0.12 | 3941 | 480.37 | -0.71 | 481.08 | Yes | N/A | N/A | 2023-07-27 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | 2023-07-27 | 81 | 59 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-10-26 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-13 | 19 | 13 | 2023-11-13 | 2023-11-13 | 1 | 1 | 92 | 66 | 101 | 73 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 169.05 | 169.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-20 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | 2024-12-26 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | -4.75 | -19.78 | Unknown | Unknown | Unknown | 15.03 | 3981 | 1362.46 | -4.75 | 1367.21 | Yes | N/A | N/A | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-04-01 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-04 | 4 | 4 | 2025-04-04 | 2025-04-03 | Unknown | Unknown | 98 | 70 | 5 | 5 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-05-07 | 1812 | 1295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -554.89 | -7.32 | Unknown | Unknown | -919 | 371.43 | Unknown | 929.04 | -554.89 | 1483.93 | Yes | N/A | N/A | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-02-21 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-21 | 38 | 28 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 1 | 1 | 78 | 58 | 79 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | Chula Vista | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-16 | 2022-08-16 | 2024-10-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 176020.88 | 20506.04 | Unknown | Unknown | 12382.39 | 143132.45 | 339553.66 | 115810.15 | 176020.88 | -60210.73 | Yes | N/A | N/A | 2022-08-16 | 2023-10-09 | 420 | 300 | 2023-10-09 | 2024-04-23 | 198 | 142 | 2023-10-26 | 2024-04-29 | 85 | 61 | 2024-01-12 | 2024-06-11 | 74 | 52 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-04-23 | 2024-10-17 | 178 | 128 | 2024-10-23 | 2024-12-05 | 44 | 32 | 2024-12-05 | 2024-12-05 | 1 | 1 | 505 | 361 | 495 | 355 | 1000 | 716 | Steps 2,3,5,6,7 | 337 | 239 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | 312 | 223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -14.53 | -11.79 | Unknown | Unknown | Unknown | -2.74 | 3981 | 1029.74 | -14.53 | 1044.27 | Yes | N/A | N/A | 2024-03-08 | 2024-03-11 | 4 | 2 | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-06 | 1 | 1 | 4 | 2 | 2 | 2 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1240.59 | Unknown | Unknown | Unknown | 13.27 | 1227.32 | 3981 | 1198.88 | 1240.59 | -41.71 | Yes | N/A | N/A | 2024-04-26 | 2024-06-17 | 53 | 37 | 2024-06-17 | 2024-06-19 | 3 | 3 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-07 | Unknown | Unknown | 53 | 37 | 3 | 3 | 56 | 40 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16.42 | Unknown | Unknown | Unknown | Unknown | 16.42 | Unknown | 1542.14 | 16.42 | 1525.72 | Yes | N/A | N/A | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | 2024-07-30 | 28 | 20 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-11-14 | 1 | 1 | 1 | 1 | 29 | 21 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | -1034.25 | Unknown | Unknown | Unknown | -1123 | 88.75 | 3981 | 2584.19 | -1034.25 | 3618.44 | Yes | N/A | N/A | 2024-06-05 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-06-26 | 52 | 38 | 2024-06-26 | 2024-06-28 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-09-27 | 92 | 66 | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-27 | 2024-10-17 | 21 | 15 | 2024-10-17 | 2024-10-17 | 1 | 1 | 95 | 69 | 74 | 54 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | -268 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 25.33 | Unknown | Unknown | Unknown | Unknown | 25.33 | Unknown | 1398.29 | 25.33 | 1372.96 | Yes | N/A | N/A | 2024-06-19 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-19 | 43 | 31 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-19 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-01 | 14 | 10 | 2024-08-01 | 2024-08-01 | 1 | 1 | 31 | 23 | 58 | 42 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-28 | -702 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 965.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-25 | 21 | 15 | 2025-06-25 | 2025-06-25 | 1 | 1 | 4 | 4 | 23 | 17 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 502.05 | 502.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-30 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | 2727.54 | 495.57 | Unknown | 928.42 | Unknown | 1303.55 | 3981 | 605.93 | 2727.54 | -2121.61 | Yes | N/A | N/A | 2023-10-02 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-10-02 | 54 | 38 | 2023-10-02 | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-18 | 8 | 6 | 2023-10-02 | 2023-12-14 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2023-12-14 | 1 | 1 | 2023-12-14 | 2023-12-18 | 5 | 3 | 74 | 54 | 68 | 48 | 142 | 102 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | 199 | 144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2522.55 | -23.79 | Unknown | Unknown | Unknown | 2546.34 | 619610 | 18436.66 | 2522.55 | 15914.11 | Yes | N/A | N/A | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | 2024-01-19 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2958465 | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-08-30 | Unknown | Unknown | 1 | 1 | 40 | 30 | 41 | 31 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | 81 | 58 | No | 2024-04-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | Yes | 232 | 14981.93 | 4.99 | Unknown | Unknown | Unknown | 14976.94 | 7962 | 1762.75 | 14981.93 | -13219.18 | Yes | N/A | N/A | 2024-02-22 | 2024-11-22 | 275 | 197 | 2024-11-22 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-19 | 31 | 23 | 2024-09-04 | 2025-05-14 | 253 | 181 | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-14 | Unknown | Unknown | 528 | 378 | 31 | 23 | 559 | 401 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -287 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 173.64 | -11.68 | Unknown | Unknown | Unknown | 185.32 | Unknown | 856.84 | 173.64 | 683.2 | Yes | N/A | N/A | 2024-01-30 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-30 | 22 | 16 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-15 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-03-15 | 30 | 22 | 2024-03-15 | 2024-03-15 | 1 | 1 | 17 | 13 | 53 | 39 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-21 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | 33.1 | Unknown | Unknown | Unknown | Unknown | 33.1 | Unknown | 1990.4 | 33.1 | 1957.3 | Yes | N/A | N/A | 2025-03-14 | 2025-03-20 | 7 | 5 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-14 | 25 | 17 | 2025-04-14 | 2025-04-14 | 1 | 1 | 8 | 6 | 27 | 19 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | -536 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-08-04 | 2023-09-26 | IOU Designed & Installed | N/A | No | N/A | -15.41 | -11.16 | Unknown | Unknown | Unknown | -4.25 | 3981 | 465.36 | -15.41 | 480.77 | Yes | N/A | N/A | 2023-06-01 | 2023-08-04 | 65 | 47 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-09-26 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-09-27 | 2 | 2 | 2023-09-27 | 2023-09-27 | 1 | 1 | 119 | 85 | 4 | 4 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | 137 | 99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 3972.23 | 951.18 | Unknown | Unknown | -391 | 3412.05 | 1460 | 1806.11 | 3972.23 | -2166.12 | Yes | N/A | N/A | 2023-05-09 | 2023-05-09 | 1 | 1 | 2023-05-09 | 2023-08-02 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-28 | 26 | 20 | 2023-08-02 | 2024-07-15 | 349 | 249 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-07-19 | 3 | 3 | 2024-07-19 | 2024-07-18 | Unknown | Unknown | 350 | 250 | 115 | 85 | 465 | 335 | Steps 2,3,5,6,7 | 331 | 237 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 637.05 | 637.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 192 | 137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 9.91 | -8.81 | Unknown | Unknown | Unknown | 18.72 | 3941 | 812.98 | 9.91 | 803.07 | Yes | N/A | N/A | 2023-09-21 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-09-21 | 70 | 50 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2024-05-22 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-10 | 20 | 14 | 2024-06-10 | 2024-06-24 | 15 | 11 | 245 | 175 | 105 | 75 | 350 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-01-28 | -1092 | -781 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 72.06 | Unknown | Unknown | Unknown | Unknown | 72.06 | 3981 | 1353.37 | 72.06 | 1281.31 | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-01-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-01-31 | 2 | 2 | 2025-01-31 | 2025-01-31 | 1 | 1 | 3 | 3 | 4 | 4 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 1963.72 | 876.08 | Unknown | Unknown | 7.91 | 1079.73 | 3981 | 1179.81 | 1963.72 | -783.91 | Yes | N/A | N/A | 2024-12-04 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-12-04 | 22 | 16 | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-06-03 | 181 | 129 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-18 | 16 | 12 | 2025-06-18 | 2025-06-18 | 1 | 1 | 181 | 129 | 39 | 29 | 220 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -485 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-24 | 2022-02-24 | 2024-07-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 18586.35 | 856.9 | Unknown | Unknown | 48.34 | 17681.11 | 139720 | 29584.44 | 18586.35 | 10998.09 | Yes | N/A | N/A | 2022-02-24 | 2023-12-04 | 649 | 463 | 2023-12-04 | 2024-02-22 | 81 | 59 | 2023-12-11 | 2023-12-20 | 10 | 8 | 2024-02-22 | 2024-02-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-07-10 | 128 | 92 | 2024-07-18 | 2024-08-03 | 17 | 12 | 2024-08-03 | 2024-08-03 | 1 | 0 | 659 | 471 | 233 | 167 | 892 | 638 | Steps 2,3,5,6,7 | 73 | 53 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-23 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | 43.55 | -11.93 | Unknown | Unknown | Unknown | 55.48 | 3981 | 959.2 | 43.55 | 915.65 | Yes | N/A | N/A | 2024-02-08 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-02-23 | 67 | 49 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-02-29 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-15 | 16 | 12 | 2024-03-15 | 2024-03-15 | 1 | 1 | 7 | 5 | 84 | 62 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -170 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 917 | -7 | Unknown | Unknown | 21.8 | 902.2 | 3941 | 1152.49 | 917 | 235.49 | Yes | N/A | N/A | 2023-11-06 | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2023-11-14 | 56 | 40 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-03-05 | 113 | 81 | Unknown | 2024-02-01 | Unknown | Unknown | 2024-03-05 | 2024-03-20 | 16 | 12 | 2024-03-20 | 2024-03-20 | 1 | 1 | 113 | 81 | 73 | 53 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 145 | 145 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-31 | 461 | 330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-28 | 2023-04-02 | IOU Designed & Installed | N/A | No | N/A | 752.13 | 248.3 | Unknown | 88.1 | Unknown | 415.73 | Unknown | 216.32 | 752.13 | -535.81 | Yes | N/A | N/A | 2023-03-22 | 2023-03-28 | 7 | 5 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-04-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-04-02 | 2023-04-06 | 5 | 4 | 2023-04-06 | 2023-04-06 | 1 | 1 | 13 | 9 | 6 | 5 | 19 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 342 | 245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 2554.87 | 782.71 | Unknown | 129.86 | Unknown | 1642.3 | 13352 | 455.15 | 2554.87 | -2099.72 | Yes | N/A | N/A | 2023-11-03 | 2024-01-08 | 67 | 47 | 2024-01-08 | 2024-01-24 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2023-12-07 | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | 2024-02-08 | 2024-02-09 | 2 | 2 | 2024-02-09 | 2024-05-08 | 90 | 64 | 67 | 47 | 109 | 79 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -499 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 129.48 | Unknown | Unknown | Unknown | -1167.52 | 1297 | Unknown | 1195.2 | 129.48 | 1065.72 | Yes | N/A | N/A | 2024-09-25 | 2024-10-23 | 29 | 21 | 2024-10-23 | 2024-10-28 | 6 | 4 | 2024-10-28 | 2024-12-03 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 66 | 48 | 7 | 5 | 73 | 53 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.35 | 9.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 481.38 | -17.25 | Unknown | Unknown | Unknown | 498.63 | 3241 | 939.5 | 481.38 | 458.12 | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-05-31 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-05 | 6 | 4 | 2024-06-05 | 2024-06-05 | 1 | 1 | 60 | 44 | 8 | 6 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 428 | 307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3340.98 | -13.5 | Unknown | Unknown | Unknown | 3354.48 | 1532099 | Not available | 3340.98 | Unknown | Yes | N/A | N/A | 2024-06-14 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-07-17 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-09-08 | 419 | 299 | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 419 | 299 | 113 | 81 | 532 | 380 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 1403.07 | -27.39 | Unknown | Unknown | Unknown | 1430.46 | 3981 | 2072.99 | 1403.07 | 669.92 | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2024-12-30 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-02-20 | 53 | 39 | 2025-02-20 | 2025-02-20 | 1 | 1 | 12 | 8 | 55 | 41 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -109 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -281.79 | 1776.35 | Unknown | 301.62 | -3199 | 839.24 | Unknown | 3199.49 | -281.79 | 3481.28 | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-10 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 688.31 | -13.2 | Unknown | Unknown | Unknown | 701.51 | Unknown | 1652.2 | 688.31 | 963.89 | Yes | N/A | N/A | 2024-12-09 | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-12-10 | 19 | 13 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-31 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-02-20 | 52 | 38 | 2025-02-20 | 2025-02-20 | 1 | 1 | 22 | 16 | 72 | 52 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1648.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-04-03 | 31 | 23 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-14 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-15 | 32 | 24 | 2025-05-15 | 2025-05-15 | 1 | 1 | 12 | 8 | 64 | 48 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -534 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 5552.56 | 705.54 | Unknown | 223.32 | 36.23 | 4587.47 | 3981 | 2347.73 | 5552.56 | -3204.83 | Yes | N/A | N/A | 2024-07-15 | 2024-09-25 | 73 | 53 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-12-19 | 86 | 62 | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-26 | 8 | 6 | 2024-12-26 | 2024-12-26 | 1 | 1 | 159 | 115 | 10 | 8 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -648 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-08 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 1352.13 | 735.16 | Unknown | 89.11 | Unknown | 527.86 | Unknown | 192.95 | 1352.13 | -1159.18 | Yes | N/A | N/A | 2024-07-03 | 2024-08-15 | 44 | 32 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-26 | 6 | 4 | 2024-08-26 | 2024-08-26 | 1 | 1 | 51 | 37 | 8 | 6 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SM 1108-E6 W.mission rd | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 304 | 217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 1769.3 | Unknown | Unknown | Unknown | 5.56 | 1763.74 | 144836 | Not available | 1769.3 | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-09-13 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 2024-09-13 | 2025-09-03 | 356 | 254 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-15 | 5 | 3 | 2025-06-15 | 2025-06-15 | 1 | 0 | 356 | 254 | 130 | 93 | 486 | 347 | Steps 2,3,5,6,7 | 270 | 192 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -185 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -675.63 | 171.99 | Unknown | Unknown | -1627 | 779.38 | Unknown | 1626.6 | -675.63 | 2302.23 | Yes | N/A | N/A | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | 2025-04-09 | 50 | 36 | 2025-02-24 | 2025-02-25 | 2 | 2 | 2025-02-25 | 2025-03-07 | 11 | 9 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 3 | 3 | 62 | 46 | 65 | 49 | Steps 2,3,5,6,7 | 44 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 4.44 | Unknown | Unknown | Unknown | Unknown | 4.44 | Unknown | 186.4 | 4.44 | 181.96 | Yes | N/A | N/A | 2024-06-14 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2025-03-06 | 310 | 222 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-11-15 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-05 | 21 | 15 | 2024-12-05 | 2024-12-05 | 1 | 1 | 155 | 111 | 332 | 238 | 487 | 349 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -11.99 | -50.14 | Unknown | Unknown | Unknown | 38.15 | Unknown | 1959.18 | -11.99 | 1971.17 | Yes | N/A | N/A | 2024-12-31 | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2025-01-08 | 24 | 18 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 0 | 0 | 25 | 19 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -456 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 121.88 | Unknown | Unknown | Unknown | Unknown | 121.88 | 7962 | 1572.83 | 121.88 | 1450.95 | Yes | N/A | N/A | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2024-12-10 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-03 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 196.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-04-03 | 18 | 14 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-06-17 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-26 | 10 | 8 | 2025-06-26 | 2025-06-26 | 1 | 1 | 76 | 54 | 29 | 23 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -241 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 541.49 | 1801.16 | Unknown | Unknown | -2085 | 825.33 | Unknown | 2085.12 | 541.49 | 1543.63 | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2023-12-27 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-01-10 | 1 | 1 | 1 | 1 | 24 | 18 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | -255 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1045.89 | Unknown | Unknown | Unknown | -1110 | 64.11 | 3981 | 1990.27 | -1045.89 | 3036.16 | Yes | N/A | N/A | 2023-09-27 | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-10-12 | 85 | 61 | 2023-10-12 | 2024-09-10 | 335 | 239 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-10-15 | Unknown | Unknown | 335 | 239 | 85 | 61 | 420 | 300 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.19 | -15.32 | Unknown | Unknown | Unknown | 10.13 | 3981 | 865.06 | -5.19 | 870.25 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | -318 | -227 | No | 2022-12-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-13 | 2022-12-13 | 2023-09-28 | IOU Designed & Installed | N/A | Yes | 276 | 39.14 | -7.62 | Unknown | Unknown | 38.91 | 7.85 | 3981 | 538.09 | 39.14 | 498.95 | Yes | N/A | N/A | 2022-12-13 | 2023-09-15 | 277 | 199 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-21 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2024-11-20 | 420 | 300 | 2024-11-20 | 2023-10-12 | Unknown | Unknown | 277 | 199 | 420 | 300 | 697 | 499 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 340 | 243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-28 | 2022-08-02 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 770.8 | -5.64 | Unknown | Unknown | 13.35 | 763.09 | 3981 | 546.48 | 770.8 | -224.32 | Yes | N/A | N/A | 2022-07-28 | 2023-03-27 | 243 | 173 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2024-03-14 | 354 | 254 | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | 2024-03-05 | Unknown | Unknown | 597 | 427 | 1 | 1 | 598 | 428 | Steps 2,3,5,6,7 | 11 | 7 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -458 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3241 | 340.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-30 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2025-01-02 | 116 | 84 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-05-28 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-24 | 28 | 20 | 2025-06-24 | 2025-06-24 | 1 | 1 | 147 | 105 | 145 | 105 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | -692.49 | 1068.76 | Unknown | 20.9 | -2441 | 658.85 | Unknown | 2441.23 | -692.49 | 3133.72 | Yes | N/A | N/A | 2024-03-19 | 2024-04-11 | 24 | 18 | 2024-04-11 | Unknown | Unknown | Unknown | 2024-04-29 | 2024-04-30 | 2 | 2 | 2024-04-15 | 2024-06-13 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 26 | 20 | 42 | 30 | 68 | 50 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 127.05 | 127.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-08 | 144 | 105 | No | 2023-02-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-03-01 | 2024-03-15 | IOU Designed & Installed | N/A | Yes | 312 | 15.01 | -13.3 | Unknown | Unknown | Unknown | 28.31 | Unknown | 1102.75 | 15.01 | 1087.74 | Yes | N/A | N/A | 2023-02-27 | 2024-01-04 | 312 | 224 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2024-03-15 | 381 | 273 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-28 | 14 | 10 | 2024-03-28 | 2024-05-31 | 65 | 47 | 693 | 497 | 79 | 57 | 772 | 554 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -669 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | -975.62 | Unknown | Unknown | Unknown | -1350 | 374.38 | Unknown | 1230.52 | -975.62 | 2206.14 | Yes | N/A | N/A | 2024-08-06 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-15 | 17 | 13 | 2024-08-15 | 2024-09-04 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-10 | 7 | 5 | 2024-09-10 | 2024-09-16 | 7 | 5 | 22 | 16 | 31 | 23 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-28 | 177 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-08 | 2022-10-23 | 2023-03-03 | IOU Designed & Installed | N/A | No | N/A | -1.91 | -5.62 | Unknown | Unknown | Unknown | 3.71 | 2841 | 544.54 | -1.91 | 546.45 | Yes | N/A | N/A | 2022-09-08 | 2023-02-24 | 170 | 122 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-23 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-03-24 | 22 | 16 | 2023-03-24 | 2023-03-24 | 1 | 1 | 170 | 122 | 23 | 17 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | -177 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2361.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-09 | 2023-05-30 | 22 | 16 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-10-27 | 131 | 95 | 2023-10-27 | 2023-10-27 | 1 | 1 | 22 | 16 | 132 | 96 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-07 | 699 | 500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-11-14 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 134.1 | Unknown | Unknown | Unknown | Unknown | 134.1 | 28804 | 342.24 | 134.1 | 208.14 | Yes | N/A | N/A | 2023-09-08 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-12-01 | 254 | 182 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-11-05 | 160 | 114 | 2024-11-05 | 2024-11-05 | 1 | 1 | 0 | 0 | 415 | 297 | 415 | 297 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -272 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-08 | 2023-02-10 | IOU Designed & Installed | N/A | No | N/A | -8.98 | -6.51 | Unknown | Unknown | Unknown | -2.47 | Unknown | 363.72 | -8.98 | 372.7 | Yes | N/A | N/A | 2023-02-03 | 2023-02-08 | 6 | 4 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-02-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-04-08 | 58 | 41 | 2023-04-08 | 2023-04-08 | 1 | 0 | 9 | 7 | 59 | 41 | 68 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | 1201 | 859 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 1224.88 | 73.13 | Unknown | Unknown | 28.68 | 1123.07 | 0 | 2377.56 | 1224.88 | 1152.68 | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | 2024-09-04 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-21 | 29 | 21 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-28 | 2025-05-29 | 2 | 2 | 2025-05-29 | 2025-05-29 | 1 | 1 | 1 | 1 | 221 | 159 | 222 | 160 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2016-12-31 | 2853 | 2038 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-20 | 2016-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -364.47 | Unknown | Unknown | Unknown | -1335 | 970.53 | Unknown | 1092.61 | -364.47 | 1457.08 | Yes | N/A | N/A | 2016-04-20 | 2024-06-03 | 2967 | 2119 | 2024-06-03 | 2016-09-12 | Unknown | Unknown | 2016-05-20 | 2016-09-09 | 113 | 81 | 2024-07-18 | 2024-07-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 3080 | 2200 | 1 | 1 | 3081 | 2201 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-15 | 334 | 239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | Unknown | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 41.05 | Unknown | Unknown | Unknown | Unknown | 41.05 | 3885 | 1060.64 | 41.05 | 1019.59 | Yes | N/A | N/A | 2023-02-22 | 2023-02-22 | 1 | 1 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2024-07-03 | 497 | 355 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-07 | 36 | 26 | 2024-08-07 | 2024-08-14 | 8 | 6 | 498 | 356 | 44 | 32 | 542 | 388 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-16 | 48 | 35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-02-22 | 2023-04-29 | IOU Designed & Installed | N/A | No | N/A | -23.91 | -18.01 | Unknown | Unknown | Unknown | -5.9 | Unknown | 98.41 | -23.91 | 122.32 | Yes | N/A | N/A | 2023-02-20 | 2023-03-09 | 18 | 14 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-04-29 | 40 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-04-29 | 2023-06-15 | 48 | 34 | 2023-06-15 | 2024-01-03 | 203 | 145 | 58 | 43 | 251 | 179 | 309 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 37.7 | 37.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 15.56 | -0.31 | Unknown | Unknown | Unknown | 15.87 | 3981 | 1122.8 | 15.56 | 1107.24 | Yes | N/A | N/A | 2025-04-16 | 2025-05-06 | 21 | 15 | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-05 | 10 | 8 | 2025-06-05 | 2025-06-05 | 1 | 1 | 43 | 31 | 12 | 10 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -688 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 540.55 | 303.12 | Unknown | 24.57 | Unknown | 212.86 | Unknown | 197.01 | 540.55 | -343.54 | Yes | N/A | N/A | 2024-09-23 | 2024-09-25 | 3 | 3 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | 2024-10-10 | 1 | 1 | 19 | 15 | 3 | 3 | 22 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 754 | 539 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 246.3 | -9.52 | Unknown | Unknown | -302 | 557.82 | Unknown | 340.77 | 246.3 | 94.47 | Yes | N/A | N/A | 2023-07-19 | 2023-10-20 | 94 | 68 | 2023-10-20 | 2024-01-08 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-26 | 19 | 15 | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-02-25 | Unknown | Unknown | 113 | 83 | 81 | 57 | 194 | 140 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-16 | 205 | 147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-09-05 | IOU Designed & Installed | N/A | No | N/A | 2239.29 | 2453.44 | Unknown | 635.04 | -2147 | 1297.81 | Unknown | 2146.68 | 2239.29 | -92.61 | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | 2023-08-24 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2024-02-06 | 155 | 111 | 2024-02-06 | 2024-02-06 | 1 | 1 | 1 | 1 | 173 | 125 | 174 | 126 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -394 | -282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-14 | 2023-11-16 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 282.93 | -7.08 | Unknown | Unknown | -262.65 | 552.66 | 7962 | 902.53 | 282.93 | 619.6 | Yes | N/A | N/A | 2023-10-14 | 2023-10-19 | 6 | 4 | 2023-10-19 | 2023-11-16 | 29 | 21 | 2023-11-16 | 2023-12-27 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-03-08 | 114 | 82 | Unknown | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-03-14 | 7 | 5 | 2024-03-14 | 2024-03-14 | 1 | 1 | 162 | 116 | 37 | 27 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | -585 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-30 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1313.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-30 | 72 | 52 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-19 | 23 | 17 | 2024-07-19 | 2024-07-19 | 1 | 1 | 29 | 21 | 96 | 70 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | San Clemente | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | -186 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 2280.73 | 224.46 | Unknown | Unknown | -5338 | 7394.27 | Unknown | 15184.43 | 2280.73 | 12903.7 | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | 2023-09-15 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-09-29 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-10 | 8 | 6 | 2023-10-10 | 2023-10-10 | 1 | 1 | 1 | 1 | 40 | 32 | 41 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-31 | -707 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1051.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-23 | 12 | 8 | 2025-06-23 | 2025-06-23 | 1 | 1 | 4 | 4 | 14 | 10 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-26 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 45.37 | Unknown | Unknown | Unknown | Unknown | 45.37 | Unknown | 1268.6 | 45.37 | 1223.23 | Yes | N/A | N/A | 2024-06-11 | 2024-07-26 | 46 | 34 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-28 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-19 | 23 | 17 | 2024-09-19 | 2024-09-19 | 1 | 1 | 80 | 58 | 25 | 19 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -286 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-10 | 2024-05-05 | IOU Designed & Installed | N/A | No | N/A | 2159.34 | 2736.16 | Unknown | 558.13 | -2441 | 1306.05 | Unknown | 2441.31 | 2159.34 | 281.97 | Yes | N/A | N/A | 2024-04-09 | 2024-04-10 | 2 | 2 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-05 | 2024-06-20 | 47 | 34 | 2024-06-20 | 2024-06-20 | 1 | 1 | 2 | 2 | 48 | 35 | 50 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 150000 | 150000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-02 | 123 | 90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10104.94 | Unknown | Unknown | Unknown | Unknown | 10104.94 | 11928 | 5428.65 | 10104.94 | -4676.29 | Yes | N/A | N/A | 2024-05-03 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-06-21 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-06-21 | 2025-04-07 | 291 | 207 | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 291 | 207 | 118 | 86 | 409 | 293 | Steps 2,3,5,6,7 | 47 | 33 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-23 | 190 | 137 | No | 2022-01-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-07 | 2022-01-07 | Unknown | IOU Designed & Installed | N/A | Yes | 440 | 591.27 | -5.12 | Unknown | Unknown | Unknown | 596.39 | 3241 | 879.02 | 591.27 | 287.75 | Yes | N/A | N/A | 2022-01-07 | 2023-03-23 | 441 | 315 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-06-01 | 1 | 1 | 441 | 315 | 1 | 1 | 442 | 316 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | 4408.59 | 606.24 | Unknown | 113.51 | Unknown | 3688.84 | 3981 | 1637.09 | 4408.59 | -2771.5 | Yes | N/A | N/A | 2024-10-09 | 2025-02-10 | 125 | 89 | 2025-02-10 | 2025-02-11 | 2 | 2 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-28 | 76 | 54 | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-28 | 2025-05-08 | 11 | 9 | 2025-05-08 | 2025-05-08 | 1 | 1 | 201 | 143 | 14 | 12 | 215 | 155 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | -138 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -21.08 | -15.27 | Unknown | Unknown | Unknown | -5.81 | 3981 | 98.66 | -21.08 | 119.74 | Yes | N/A | N/A | 2023-03-24 | 2023-04-03 | 11 | 7 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 11 | 7 | 1 | 1 | 12 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 446.44 | Unknown | Unknown | Unknown | 2.92 | 443.52 | 3981 | 1300.08 | 446.44 | 853.64 | Yes | N/A | N/A | 2024-11-19 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-12-11 | 34 | 24 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-10 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-24 | 15 | 11 | 2025-01-24 | 2025-01-23 | Unknown | Unknown | 31 | 23 | 49 | 35 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 7.86 | -9.92 | Unknown | Unknown | Unknown | 17.78 | 3981 | 1049 | 7.86 | 1041.14 | Yes | N/A | N/A | 2023-10-20 | 2023-07-03 | Unknown | Unknown | 2023-07-03 | 2023-10-20 | 110 | 80 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-01-29 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-08 | 11 | 9 | 2024-02-08 | 2024-02-08 | 1 | 1 | 102 | 72 | 122 | 90 | 224 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-17 | -290 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.46 | -10.21 | Unknown | Unknown | Unknown | 2.75 | Unknown | 158.14 | -7.46 | 165.6 | Yes | N/A | N/A | 2023-04-26 | 2023-07-21 | 87 | 63 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-03 | 1 | 1 | 87 | 63 | 1 | 1 | 88 | 64 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 2243.64 | Unknown | Unknown | Unknown | 8.27 | 2235.37 | 3961 | 1158.4 | 2243.64 | -1085.24 | Yes | N/A | N/A | 2024-10-02 | 2024-10-23 | 22 | 16 | 2024-10-23 | 2024-10-25 | 3 | 3 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2025-01-22 | 90 | 64 | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-22 | 2025-02-26 | 36 | 26 | 2025-02-26 | 2025-02-26 | 1 | 1 | 112 | 80 | 40 | 30 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | -872 | -623 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.78 | -4.19 | Unknown | Unknown | Unknown | -1.59 | 3981 | 468.73 | -5.78 | 474.51 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | 2023-08-15 | 2023-05-26 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 39.4 | 39.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-16 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1088.65 | -15.07 | Unknown | Unknown | 13.13 | 1090.59 | 3981 | 2284.62 | 1088.65 | 1195.97 | Yes | N/A | N/A | 2023-02-28 | 2023-07-22 | 145 | 104 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-03-06 | 1 | 1 | 145 | 104 | 1 | 1 | 146 | 105 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ALISO VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 28.86 | 2325.7 | Unknown | Unknown | -3778 | 1481.16 | Unknown | 3777.92 | 28.86 | 3749.06 | Yes | N/A | N/A | 2024-10-18 | 2024-10-24 | 7 | 5 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-12 | 4 | 4 | 2024-12-12 | 2024-12-12 | 1 | 1 | 7 | 5 | 5 | 5 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 126.05 | 126.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -478 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 1584.9 | Unknown | Unknown | Unknown | 36.38 | 1548.52 | 3981 | 1650.79 | 1584.9 | 65.89 | Yes | N/A | N/A | 2024-09-03 | 2024-10-30 | 58 | 42 | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-01-13 | 76 | 54 | Unknown | 2024-12-31 | Unknown | Unknown | 2025-01-13 | 2025-01-24 | 12 | 10 | 2025-01-24 | 2025-02-27 | 35 | 25 | 134 | 96 | 48 | 36 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-06 | 442 | 317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1038.06 | -10.36 | Unknown | Unknown | 16.14 | 1032.28 | 7962 | 1157.11 | 1038.06 | 119.05 | Yes | N/A | N/A | 2023-07-05 | 2024-07-16 | 378 | 270 | 2024-07-16 | 2024-08-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-19 | 37 | 27 | 2024-08-07 | 2024-10-25 | 80 | 58 | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-21 | Unknown | Unknown | 458 | 328 | 60 | 44 | 518 | 372 | Steps 2,3,5,6,7 | 134 | 96 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-18 | 286 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-13 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 1274.02 | Unknown | Unknown | Unknown | 20.85 | 1253.17 | 3961 | 1080.8 | 1274.02 | -193.22 | Yes | N/A | N/A | 2024-01-31 | 2024-02-13 | 14 | 10 | 2024-02-13 | 2024-05-20 | 98 | 70 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-08-19 | 92 | 66 | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-19 | 2024-09-03 | 16 | 12 | 2024-09-03 | 2024-08-30 | Unknown | Unknown | 106 | 76 | 114 | 82 | 220 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | -198 | -143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | 245.65 | -11.35 | Unknown | Unknown | Unknown | 257 | Unknown | 812.23 | 245.65 | 566.58 | Yes | N/A | N/A | 2023-03-29 | 2023-03-29 | 1 | 1 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-06-26 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-08-01 | 37 | 27 | 2023-08-01 | 2023-08-01 | 1 | 1 | 91 | 65 | 38 | 28 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | -675 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-05-01 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 561.47 | -11.23 | Unknown | Unknown | 2.76 | 569.94 | Unknown | 1400.37 | 561.47 | 838.9 | Yes | N/A | N/A | 2025-04-29 | 2025-04-25 | Unknown | Unknown | 2025-04-25 | 2025-05-01 | 7 | 5 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-14 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-04 | 22 | 16 | 2025-06-04 | 2025-06-04 | 1 | 1 | 14 | 10 | 30 | 22 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -488 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-22 | 2023-12-08 | IOU Designed & Installed | N/A | No | N/A | 0.97 | -13.47 | Unknown | Unknown | Unknown | 14.44 | 3981 | 558.28 | 0.97 | 557.31 | Yes | N/A | N/A | 2023-06-15 | 2023-06-22 | 8 | 6 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-12-08 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-15 | 8 | 6 | 2023-12-15 | 2023-12-15 | 1 | 1 | 178 | 128 | 9 | 7 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-16 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | -7 | -5.29 | Unknown | Unknown | Unknown | -1.71 | Unknown | 514.57 | -7 | 521.57 | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-25 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-12-14 | 51 | 37 | 2023-12-14 | 2023-12-14 | 1 | 1 | 28 | 20 | 53 | 39 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-31 | 2024-08-31 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 788.17 | -15.3 | Unknown | Unknown | Unknown | 803.47 | 3981 | 1397.06 | 788.17 | 608.89 | Yes | N/A | N/A | 2024-08-31 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-09-04 | 8 | 6 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-31 | 2024-12-23 | 115 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-23 | 32 | 24 | 2025-01-23 | 2025-01-23 | 1 | 1 | 115 | 81 | 41 | 31 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-21 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-21 | 16 | 12 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-08 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-04-25 | 108 | 78 | 2025-04-25 | 2025-04-25 | 1 | 1 | 49 | 35 | 125 | 91 | 174 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | ALPINE | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 235 | 168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 531.97 | Unknown | Unknown | Unknown | 39.21 | 492.76 | 3981 | 682.82 | 531.97 | 150.85 | Yes | N/A | N/A | 2023-10-30 | 2024-02-20 | 114 | 82 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-09-04 | 296 | 212 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-12 | 9 | 7 | 2024-09-12 | 2024-09-23 | 12 | 8 | 410 | 294 | 22 | 16 | 432 | 310 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 1280 | 883.15 | Unknown | Unknown | Unknown | 396.85 | 8997 | 554.66 | 1280 | -725.34 | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2024-09-17 | 499 | 357 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-11 | 25 | 19 | 2024-10-11 | 2024-10-11 | 1 | 1 | 500 | 358 | 26 | 20 | 526 | 378 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-07-25 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | 1679.11 | 604.05 | Unknown | 75.92 | Unknown | 999.14 | 3981 | 924.36 | 1679.11 | -754.75 | Yes | N/A | N/A | 2023-05-16 | 2023-07-25 | 71 | 51 | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-08-17 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-22 | 6 | 4 | 2023-08-22 | 2023-08-22 | 1 | 1 | 95 | 69 | 8 | 6 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 604.74 | -18.77 | Unknown | Unknown | Unknown | 623.51 | 3241 | 899.29 | 604.74 | 294.55 | Yes | N/A | N/A | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-24 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-03-15 | 52 | 38 | 2024-03-15 | 2024-03-15 | 1 | 1 | 3 | 3 | 54 | 40 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | -206 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2022-11-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.97 | -9.42 | Unknown | Unknown | Unknown | -3.55 | 3981 | 98.41 | -12.97 | 111.38 | Yes | N/A | N/A | 2022-11-17 | 2023-01-31 | 76 | 54 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | Unknown | Unknown | 2023-04-05 | 2023-04-05 | 1 | 1 | 76 | 54 | 1 | 1 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-19 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 1010.6 | -41.13 | Unknown | Unknown | Unknown | 1051.73 | Unknown | 1676.05 | 1010.6 | 665.45 | Yes | N/A | N/A | 2025-02-18 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-02-19 | 10 | 8 | 2025-02-19 | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-27 | 7 | 5 | 2025-02-19 | 2025-03-06 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-26 | 21 | 15 | 2025-03-26 | 2025-03-26 | 1 | 1 | 16 | 12 | 39 | 29 | 55 | 41 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -479 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-21 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | -8.29 | -16.31 | Unknown | Unknown | Unknown | 8.02 | Unknown | 754.27 | -8.29 | 762.56 | Yes | N/A | N/A | 2023-03-06 | 2023-03-21 | 16 | 12 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-08-29 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-09-13 | 16 | 12 | 2023-09-13 | 2023-09-13 | 1 | 1 | 178 | 128 | 17 | 13 | 195 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-19 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | -1920.25 | 472.95 | Unknown | 58.53 | -2651 | 199.27 | 0 | 2651.2 | -1920.25 | 4571.45 | Yes | N/A | N/A | 2024-03-28 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2025-04-11 | 390 | 280 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 1 | 0 | 0 | 393 | 283 | 393 | 283 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -652 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-06 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 4.99 | Unknown | Unknown | Unknown | Unknown | 4.99 | 3981 | 985.1 | 4.99 | 980.11 | Yes | N/A | N/A | 2024-07-23 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-08-06 | 50 | 36 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-23 | 18 | 14 | 2024-08-23 | 2024-08-23 | 1 | 1 | 1 | 1 | 69 | 51 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-02-06 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 42408.18 | 14852.02 | Unknown | 58.42 | 60.35 | 27437.39 | 283855 | 31994.9 | 42408.18 | -10413.28 | Yes | N/A | N/A | 2024-01-30 | 2024-01-31 | 2 | 2 | 2024-01-31 | 2024-06-05 | 127 | 91 | 2024-04-05 | 2024-05-21 | 1 | 1 | 2024-05-02 | 2024-06-07 | 37 | 27 | 2024-06-05 | 2024-08-30 | 87 | 63 | 2024-06-24 | 2024-09-06 | 75 | 55 | 2024-09-13 | 2024-09-18 | 6 | 4 | 2024-09-18 | 2024-09-18 | 1 | 1 | 90 | 66 | 246 | 178 | 336 | 244 | Steps 2,3,5,6,7 | 149 | 107 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -591 | -423 | No | 2023-10-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | 2024-01-16 | IOU Designed & Installed | N/A | Yes | 51 | 465.77 | -14.31 | Unknown | Unknown | -742.17 | 1222.25 | Unknown | 742.97 | 465.77 | 277.2 | Yes | N/A | N/A | 2023-10-30 | 2023-12-14 | 46 | 34 | 2023-12-14 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2023-12-18 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-16 | 30 | 22 | Unknown | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2024-01-30 | 15 | 11 | 2024-01-30 | 2024-01-31 | 2 | 2 | 89 | 65 | 17 | 13 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-18 | 28 | 20 | 2024-12-18 | 2025-04-28 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-04-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-13 | 15 | 11 | 2025-05-13 | 2025-05-12 | Unknown | Unknown | 134 | 96 | 43 | 31 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | 59340 | 59340 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-01 | 98 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-21 | 2024-01-12 | IOU Designed & Installed | N/A | No | N/A | 66584.58 | 24721.16 | Unknown | Unknown | -11767.65 | 53631.07 | Unknown | 11776.98 | 66584.58 | -54807.6 | Yes | N/A | N/A | 2023-08-01 | 2023-08-08 | 8 | 6 | 2023-08-08 | 2023-12-20 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-01-04 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-02-07 | 27 | 19 | 2024-02-07 | 2024-02-07 | 1 | 1 | 8 | 6 | 186 | 134 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-04-14 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | -5.68 | -11.13 | Unknown | Unknown | Unknown | 5.45 | 3981 | 905.94 | -5.68 | 911.62 | Yes | N/A | N/A | 2023-03-29 | 2023-04-14 | 17 | 13 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-08-01 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-09-11 | 42 | 30 | 2023-09-11 | 2023-09-11 | 1 | 1 | 127 | 91 | 43 | 31 | 170 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -555 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 171.5 | -2.5 | Unknown | Unknown | Unknown | 174 | 3981 | 1447.53 | 171.5 | 1276.03 | Yes | N/A | N/A | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-12-06 | 145 | 105 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-19 | 14 | 10 | 2024-12-19 | 2024-12-19 | 1 | 1 | 146 | 106 | 16 | 12 | 162 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-27 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-21 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 1059.81 | Unknown | Unknown | Unknown | 14.65 | 1045.16 | 3981 | 1048.7 | 1059.81 | -11.11 | Yes | N/A | N/A | 2024-06-11 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-07-08 | 63 | 45 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-10-22 | 107 | 77 | Unknown | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-11-12 | 22 | 16 | 2024-11-12 | 2024-11-12 | 1 | 1 | 107 | 77 | 86 | 62 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | DEL MAR | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-03 | 84 | 61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14251.71 | 4072.95 | Unknown | Unknown | 596.5 | 9582.26 | 11821 | 1781.39 | 14251.71 | -12470.32 | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | 2023-04-19 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-04-11 | 12 | 8 | 2023-04-19 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2023-04-28 | Unknown | Unknown | 1 | 1 | 32 | 22 | 33 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 388 | 277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2022-10-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1503.06 | 3980.5 | Unknown | 792.57 | -4811 | 1540.99 | 0 | 4810.78 | 1503.06 | 3307.72 | Yes | N/A | N/A | 2022-10-21 | 2023-05-25 | 217 | 155 | 2023-05-25 | 2023-05-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 217 | 155 | 3 | 3 | 220 | 158 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.11 | Unknown | Unknown | Unknown | Unknown | 30.11 | 3981 | 1623.06 | 30.11 | 1592.95 | Yes | N/A | N/A | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | -196 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.03 | -14.91 | Unknown | Unknown | Unknown | 9.88 | Unknown | 264.43 | -5.03 | 269.46 | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | -647 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 497.99 | -26.82 | Unknown | Unknown | Unknown | 524.81 | Unknown | 895.35 | 497.99 | 397.36 | Yes | N/A | N/A | 2024-01-31 | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-01-31 | 34 | 24 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-08 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-03-15 | 37 | 27 | 2024-03-15 | 2024-03-15 | 1 | 1 | 9 | 7 | 72 | 52 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 113 | 113 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -439 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2024-01-22 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 814.47 | Unknown | Unknown | Unknown | 12.03 | 802.44 | 3981 | 944.51 | 814.47 | 130.04 | Yes | N/A | N/A | 2023-11-03 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2024-02-01 | 122 | 88 | 2024-01-19 | 2024-01-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-07-24 | 175 | 125 | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-26 | 2024-08-01 | 7 | 5 | 2024-08-01 | 2024-07-31 | Unknown | Unknown | 176 | 126 | 129 | 93 | 305 | 219 | Steps 2,3,5,6,7 | 13 | 9 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 57 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 650.12 | -12.11 | Unknown | Unknown | 12.88 | 649.35 | 3981 | 655.72 | 650.12 | 5.6 | Yes | N/A | N/A | 2023-08-10 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-08-29 | 90 | 64 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-12-20 | 113 | 81 | Unknown | 2023-12-14 | Unknown | Unknown | 2023-12-20 | 2023-12-28 | 9 | 7 | 2023-12-28 | 2023-12-28 | 1 | 1 | 113 | 81 | 100 | 72 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -11 | -9 | No | 2023-06-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | Yes | 111 | -12.66 | -10.28 | Unknown | Unknown | Unknown | -2.38 | 3981 | 464.78 | -12.66 | 477.44 | Yes | N/A | N/A | 2023-06-13 | 2023-10-02 | 112 | 80 | 2023-10-02 | 2023-10-02 | 1 | 1 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-02-13 | 1 | 1 | 112 | 80 | 2 | 2 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | 92 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-24 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2617.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | 2025-04-07 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-12-06 | 38 | 28 | 2025-04-07 | 2025-04-24 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-23 | 15 | 11 | 2025-04-23 | 2025-04-22 | Unknown | Unknown | 19 | 15 | 228 | 164 | 247 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | 60 | 44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | -9.43 | -8.59 | Unknown | Unknown | Unknown | -0.84 | 0 | 154.99 | -9.43 | 164.42 | Yes | N/A | N/A | 2023-09-18 | 2023-04-28 | Unknown | Unknown | 2023-04-28 | 2023-09-28 | 154 | 110 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2024-06-17 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-20 | 4 | 4 | 2024-06-20 | 2024-06-20 | 1 | 1 | 264 | 188 | 159 | 115 | 423 | 303 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OC 1106-D2 CA WEST CMTY | N/A | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-17 | 445 | 320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-06 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 8968.16 | 388.23 | Unknown | 54.22 | 4.07 | 8521.64 | 3981 | Not available | 8968.16 | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2024-01-10 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-01-10 | 2024-12-06 | 332 | 238 | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-10-04 | Unknown | Unknown | 332 | 238 | 196 | 140 | 528 | 378 | Steps 2,3,5,6,7 | 98 | 70 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-13 | -352 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 3207.51 | 385.02 | Unknown | 239.55 | Unknown | 2582.94 | 3981 | 783.54 | 3207.51 | -2423.97 | Yes | N/A | N/A | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-24 | 5 | 3 | 2023-07-19 | 2023-07-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-07-27 | 3 | 3 | 2023-07-27 | 2023-07-27 | 1 | 1 | 8 | 6 | 10 | 8 | 18 | 14 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -521 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-11 | 2023-05-14 | IOU Designed & Installed | N/A | No | N/A | 1293.21 | 421.38 | Unknown | 134.04 | Unknown | 737.79 | 3981 | 780.07 | 1293.21 | -513.14 | Yes | N/A | N/A | 2023-02-28 | 2023-03-11 | 12 | 9 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | 2023-05-14 | 65 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-05-14 | 2023-05-17 | 4 | 3 | 2023-05-17 | 2023-05-17 | 1 | 1 | 77 | 54 | 5 | 4 | 82 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | -298 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-08 | 2023-03-22 | IOU Designed & Installed | N/A | No | N/A | -2.89 | -8.53 | Unknown | Unknown | Unknown | 5.64 | Unknown | 670.3 | -2.89 | 673.19 | Yes | N/A | N/A | 2023-01-25 | 2023-02-08 | 15 | 11 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-03-22 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-06-12 | 83 | 59 | 2023-06-12 | 2023-03-28 | Unknown | Unknown | 58 | 42 | 83 | 59 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 121.05 | 121.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 631.99 | -5.27 | Unknown | Unknown | 3.38 | 633.88 | 3981 | 652.41 | 631.99 | 20.42 | Yes | N/A | N/A | 2023-02-28 | 2023-04-06 | 38 | 28 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-06-29 | 1 | 1 | 38 | 28 | 1 | 1 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 48.1 | 48.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-25 | -124 | -90 | No | 2024-01-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-09 | 2025-06-23 | IOU Designed & Installed | N/A | Yes | 98 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 494.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-12 | 2024-04-16 | 96 | 68 | 2024-04-16 | 2024-04-19 | 4 | 4 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2025-06-23 | 431 | 307 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 527 | 375 | 6 | 6 | 533 | 381 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -515 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 900.82 | Unknown | Unknown | Unknown | 14.58 | 886.24 | 3981 | 1175.27 | 900.82 | 274.45 | Yes | N/A | N/A | 2024-11-14 | 2025-01-21 | 69 | 49 | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 69 | 49 | 2 | 2 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | -619 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | -12.68 | -10.3 | Unknown | Unknown | Unknown | -2.38 | Unknown | 928.5 | -12.68 | 941.18 | Yes | N/A | N/A | 2024-05-03 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-03 | 58 | 42 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-03 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-21 | 19 | 15 | 2024-06-21 | 2024-06-21 | 1 | 1 | 32 | 22 | 78 | 58 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41.4 | 41.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -276 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-21 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 20.61 | Unknown | Unknown | Unknown | Unknown | 20.61 | 3981 | 1634.89 | 20.61 | 1614.28 | Yes | N/A | N/A | 2024-11-14 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-21 | 9 | 7 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-25 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-13 | 19 | 15 | 2024-12-13 | 2024-12-13 | 1 | 1 | 5 | 3 | 29 | 23 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-06 | 648 | 463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1718.72 | 1197.3 | Unknown | 442.2 | -3864 | 505.78 | 0 | 3863.7 | -1718.72 | 5582.42 | Yes | N/A | N/A | 2023-08-14 | 2023-08-15 | 2 | 2 | 2023-08-15 | 2023-09-11 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2 | 2 | 29 | 21 | 31 | 23 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -591 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-17 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | -6.73 | -6.51 | Unknown | Unknown | Unknown | -0.22 | Unknown | 163.83 | -6.73 | 170.56 | Yes | N/A | N/A | 2024-01-12 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2024-02-09 | 95 | 69 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-13 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-15 | 32 | 24 | 2024-03-15 | 2024-03-15 | 1 | 1 | 5 | 3 | 128 | 94 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -623 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-02-27 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 576.03 | -38.72 | Unknown | Unknown | Unknown | 614.75 | 3981 | 1681.11 | 576.03 | 1105.08 | Yes | N/A | N/A | 2025-01-23 | 2025-02-20 | 29 | 21 | 2025-02-20 | 2025-02-27 | 8 | 6 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-04-02 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-07 | 6 | 4 | 2025-04-07 | 2025-04-06 | Unknown | Unknown | 64 | 46 | 14 | 10 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-09 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 11359.16 | 3038.72 | Unknown | Unknown | 46.91 | 8273.53 | Unknown | 1824.58 | 11359.16 | -9534.58 | Yes | N/A | N/A | 2025-01-03 | 2025-01-09 | 7 | 5 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-04-23 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-21 | 29 | 21 | 2025-05-21 | 2025-05-21 | 1 | 1 | 112 | 80 | 31 | 23 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-28 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-13 | 2023-07-13 | IOU Designed & Installed | N/A | No | N/A | 1225.78 | 465.88 | Unknown | Unknown | Unknown | 759.9 | 3885 | 1401.94 | 1225.78 | 176.16 | Yes | N/A | N/A | 2023-04-06 | 2023-04-13 | 8 | 6 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-07-13 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-07-14 | 2 | 2 | 2023-07-14 | 2023-07-14 | 1 | 1 | 100 | 72 | 3 | 3 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-23 | -719 | -514 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 657 | 150.3 | Unknown | Unknown | Unknown | 506.7 | 3981 | 1915.88 | 657 | 1258.88 | Yes | N/A | N/A | 2025-03-25 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-26 | 3 | 3 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-03-28 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-03 | 7 | 5 | 2025-04-03 | 2025-04-03 | 1 | 1 | 3 | 3 | 11 | 9 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 116.05 | 116.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | 2023-06-09 | IOU Designed & Installed | N/A | No | N/A | 1857.14 | 504.2 | Unknown | 235.84 | 3.94 | 1113.16 | 3981 | 983.42 | 1857.14 | -873.72 | Yes | N/A | N/A | 2023-03-22 | 2023-03-24 | 3 | 3 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-06-09 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-24 | 46 | 32 | 2023-07-24 | 2023-07-24 | 1 | 1 | 20 | 16 | 47 | 33 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 47.1 | 47.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-10 | -551 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2025-01-02 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 2869.78 | 601.93 | Unknown | Unknown | Unknown | 2267.85 | 7962 | 719.62 | 2869.78 | -2150.16 | Yes | N/A | N/A | 2024-12-31 | 2024-12-31 | 1 | 1 | 2024-12-31 | 2025-01-02 | 3 | 3 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-03 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-10 | 8 | 6 | 2025-02-10 | 2025-02-05 | Unknown | Unknown | 34 | 24 | 11 | 9 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | -696 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 973.28 | -19.56 | Unknown | Unknown | Unknown | 992.84 | 3981 | 1700.87 | 973.28 | 727.59 | Yes | N/A | N/A | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-17 | 30 | 22 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2 | 2 | 32 | 24 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -141 | -102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 1699.39 | 616.87 | Unknown | 71.14 | -1279.22 | 2290.6 | Unknown | 1158.77 | 1699.39 | -540.62 | Yes | N/A | N/A | 2024-09-19 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-10-03 | 28 | 20 | 2024-10-03 | 2024-10-08 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-12-27 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-16 | 21 | 15 | 2025-01-16 | 2025-01-02 | Unknown | Unknown | 87 | 63 | 49 | 35 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -332 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 364.06 | 188.52 | Unknown | 36.96 | Unknown | 138.58 | Unknown | 153.49 | 364.06 | -210.57 | Yes | N/A | N/A | 2024-01-04 | 2024-01-19 | 16 | 12 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-09-18 | 244 | 174 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-21 | 34 | 24 | 2024-10-21 | 2024-10-21 | 1 | 1 | 260 | 186 | 36 | 26 | 296 | 212 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-14 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-29 | 2023-05-02 | IOU Designed & Installed | N/A | No | N/A | 5923.6 | 340.48 | Unknown | 259.74 | 58.54 | 5264.84 | 35875 | 2517.47 | 5923.6 | -3406.13 | Yes | N/A | N/A | 2023-03-27 | 2023-03-29 | 3 | 3 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | Unknown | Unknown | 2023-05-02 | 2023-07-19 | 79 | 57 | 2023-07-19 | 2023-07-19 | 1 | 1 | 3 | 3 | 80 | 58 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | -919.34 | -2.64 | Unknown | Unknown | -918 | 1.3 | Unknown | 918.48 | -919.34 | 1837.82 | Yes | N/A | N/A | 2023-05-23 | 2023-07-14 | 53 | 39 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-09-27 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-27 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-03 | 7 | 5 | 2023-10-03 | 2023-10-03 | 1 | 1 | 146 | 106 | 9 | 7 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | EL CAJON | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-06 | 136 | 99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 358.14 | -6.79 | Unknown | Unknown | Unknown | 364.93 | 3981 | 1368.86 | 358.14 | 1010.72 | Yes | N/A | N/A | 2024-07-19 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-08-07 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-23 | 32 | 24 | 2024-08-07 | 2024-09-03 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-19 | Unknown | Unknown | 28 | 20 | 102 | 74 | 130 | 94 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | -416 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-09-15 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 825.59 | 252.46 | Unknown | 43.38 | Unknown | 529.75 | 3981 | 1004.32 | 825.59 | 178.73 | Yes | N/A | N/A | 2023-08-21 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | 2023-09-15 | 156 | 112 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2024-02-12 | 151 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-14 | 3 | 3 | 2024-02-14 | 2024-02-14 | 1 | 1 | 151 | 107 | 160 | 116 | 311 | 223 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 236 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-05-30 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | -3091.42 | 300.29 | Unknown | Unknown | -14450 | 11058.29 | 0 | 13351.19 | -3091.42 | 16442.61 | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | 2023-11-06 | 224 | 160 | 2023-08-28 | Unknown | Unknown | Unknown | 2023-09-07 | 2024-05-16 | 24 | 18 | 2023-11-30 | Unknown | Unknown | Unknown | 2023-11-30 | 2024-08-07 | 252 | 180 | 2024-09-09 | 2024-10-16 | 38 | 28 | 2024-10-16 | 2024-10-16 | 1 | 1 | 1 | 1 | 539 | 387 | 540 | 388 | Steps 2,3,5,6,7 | 238 | 170 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-29 | -64 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3283.27 | -47.04 | Unknown | Unknown | Unknown | 3330.31 | Unknown | 4160.9 | 3283.27 | 877.63 | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-10 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-24 | 1 | 1 | 1 | 1 | 5 | 3 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -625 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-22 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 330.57 | -8.54 | Unknown | Unknown | Unknown | 339.11 | Unknown | 917.57 | 330.57 | 587 | Yes | N/A | N/A | 2024-02-12 | 2024-02-22 | 11 | 9 | 2024-02-22 | 2024-02-22 | 1 | 1 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-02-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-15 | 18 | 14 | 2024-03-15 | 2024-03-15 | 1 | 1 | 17 | 13 | 20 | 16 | 37 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 717.05 | 717.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-24 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 33.98 | Unknown | Unknown | Unknown | Unknown | 33.98 | 3981 | 917.56 | 33.98 | 883.58 | Yes | N/A | N/A | 2023-03-20 | 2023-03-24 | 5 | 5 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2024-09-17 | 544 | 388 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-24 | 8 | 6 | 2024-09-24 | 2024-09-24 | 1 | 1 | 549 | 393 | 9 | 7 | 558 | 400 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -690 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | Unknown | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 1823.82 | -36.22 | Unknown | Unknown | Unknown | 1860.04 | 3981 | 1587.31 | 1823.82 | -236.51 | Yes | N/A | N/A | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-22 | 16 | 12 | 2024-08-07 | 2024-08-30 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-11 | 13 | 9 | 2024-09-11 | 2024-09-11 | 1 | 1 | 25 | 19 | 31 | 23 | 56 | 42 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-08-11 | IOU Designed & Installed | N/A | No | N/A | 628.44 | -29.84 | Unknown | Unknown | Unknown | 658.28 | 3981 | 1037.24 | 628.44 | 408.8 | Yes | N/A | N/A | 2023-02-28 | 2023-08-11 | 165 | 119 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-08-11 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-08-25 | 15 | 11 | 2023-08-25 | 2023-08-25 | 1 | 1 | 330 | 238 | 16 | 12 | 346 | 250 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | PINE VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -359 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-02-07 | IOU Designed & Installed | N/A | No | N/A | 996.48 | 332.85 | Unknown | 57.35 | Unknown | 606.28 | 3885 | 472.13 | 996.48 | -524.35 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-02-07 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | 2023-02-07 | 1 | 1 | 2023-02-07 | 2023-02-07 | 1 | 1 | 6 | 4 | 2 | 2 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-07 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-02-01 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 8.91 | -7.92 | Unknown | Unknown | Unknown | 16.83 | 3981 | 881.79 | 8.91 | 872.88 | Yes | N/A | N/A | 2024-01-10 | 2024-01-30 | 21 | 15 | 2024-01-30 | 2024-02-01 | 3 | 3 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-19 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-03 | 16 | 12 | 2024-04-03 | 2024-04-03 | 1 | 1 | 69 | 49 | 20 | 16 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | PW 1170-D7 LYON PH2 | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 365 | 262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 27165.69 | 3887.54 | Unknown | Unknown | Unknown | 23278.15 | 3981 | Not available | 27165.69 | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-07-08 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-09-11 | 66 | 48 | Unknown | 2024-09-17 | Unknown | Unknown | 2024-10-02 | 2024-10-21 | 20 | 14 | 2024-10-21 | 2024-10-31 | 11 | 9 | 66 | 48 | 240 | 172 | 306 | 220 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-11 | 2023-11-15 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 1168.72 | 410.86 | Unknown | Unknown | Unknown | 757.86 | Unknown | 855.69 | 1168.72 | -313.03 | Yes | N/A | N/A | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-11-27 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-07 | 11 | 9 | 2023-12-07 | 2023-12-07 | 1 | 1 | 14 | 9 | 13 | 10 | 27 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 18.32 | -19.75 | Unknown | Unknown | 0.56 | 37.51 | 3981 | 2220.61 | 18.32 | 2202.29 | Yes | N/A | N/A | 2023-12-20 | 2024-01-03 | 15 | 11 | 2024-01-03 | 2024-01-05 | 3 | 3 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-03 | 1 | 1 | 15 | 11 | 4 | 4 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 607 | 607 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -150 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4781.93 | 909.55 | Unknown | 832.75 | 29.46 | 3010.17 | 3981 | 2170.79 | 4781.93 | -2611.14 | Yes | N/A | N/A | 2023-10-25 | 2023-12-05 | 42 | 30 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-03 | 1 | 1 | 42 | 30 | 2 | 2 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Pauma Valley | CALTRANS-NORTH of 56 | 699 | 699 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | 102 | 75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-13 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 9797.19 | 2182.16 | Unknown | 392.55 | Unknown | 7222.48 | Unknown | 9248.57 | 9797.19 | -548.62 | Yes | N/A | N/A | 2024-08-02 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-12-06 | 130 | 94 | 2024-09-12 | 2025-02-05 | 54 | 41 | 2024-09-18 | 2025-01-31 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-13 | 8 | 6 | 2024-12-13 | 2024-12-13 | 1 | 1 | 54 | 41 | 210 | 152 | 264 | 193 | Steps 2,3,5,6,7 | 225 | 161 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 219.91 | 100.94 | Unknown | 37.94 | Unknown | 81.03 | 3981 | 153.26 | 219.91 | -66.65 | Yes | N/A | N/A | 2024-03-19 | 2024-04-04 | 17 | 13 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-04-26 | 1 | 1 | 17 | 13 | 2 | 2 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -282 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 2859.26 | 530.72 | Unknown | Unknown | 34.21 | 2294.33 | 3941 | 1025.83 | 2859.26 | -1833.43 | Yes | N/A | N/A | 2024-04-16 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-05-06 | 75 | 53 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2025-05-09 | 369 | 265 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 369 | 265 | 77 | 55 | 446 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | -14 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 747.45 | -16.68 | Unknown | Unknown | 110.39 | 653.74 | 31848 | 2852.85 | 747.45 | 2105.4 | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | 2023-07-21 | 75 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-07-24 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-09-07 | Unknown | Unknown | 5 | 3 | 75 | 55 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-01-13 | 1013 | 724 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-25 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 34173.49 | 2427.91 | Unknown | 382.14 | Unknown | 31363.44 | Unknown | 4265.47 | 34173.49 | -29908.02 | Yes | N/A | N/A | 2023-09-13 | 2023-09-25 | 13 | 9 | 2023-09-25 | 2023-09-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-13 | 18 | 14 | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-17 | 2023-10-24 | 8 | 6 | 2023-10-24 | 2023-10-23 | Unknown | Unknown | 31 | 23 | 10 | 8 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -655 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-03 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 5.14 | Unknown | Unknown | Unknown | Unknown | 5.14 | Unknown | 197.01 | 5.14 | 191.87 | Yes | N/A | N/A | 2024-12-02 | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-12-12 | 24 | 18 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-13 | 33 | 23 | 2025-01-13 | 2025-01-13 | 1 | 1 | 1 | 1 | 58 | 42 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 6 | 5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-01 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 1.02 | -13.52 | Unknown | Unknown | Unknown | 14.54 | 3981 | 815.85 | 1.02 | 814.83 | Yes | N/A | N/A | 2023-08-30 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-09-01 | 64 | 46 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-11-28 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-07 | 10 | 8 | 2023-12-07 | 2023-12-07 | 1 | 1 | 89 | 63 | 75 | 55 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -90.62 | -4.19 | Unknown | Unknown | -311 | 224.57 | 0 | 266.52 | -90.62 | 357.14 | Yes | N/A | N/A | 2022-12-06 | 2023-07-11 | 218 | 156 | 2023-07-11 | 2023-07-17 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-06 | Unknown | Unknown | 218 | 156 | 7 | 5 | 225 | 161 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -593 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 896.75 | 268.39 | Unknown | Unknown | Unknown | 628.36 | 3981 | 1718.79 | 896.75 | 822.04 | Yes | N/A | N/A | 2024-06-19 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-06-19 | 37 | 27 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-21 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-15 | 25 | 17 | 2024-07-15 | 2024-07-15 | 1 | 1 | 3 | 3 | 63 | 45 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 90.35 | 90.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 552.24 | -7.57 | Unknown | Unknown | Unknown | 559.81 | 3981 | 725.85 | 552.24 | 173.61 | Yes | N/A | N/A | 2023-08-23 | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-11-17 | 157 | 113 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-04-26 | Unknown | Unknown | 0 | 0 | 157 | 113 | 157 | 113 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | Chula Vista | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-16 | 2022-08-16 | 2025-03-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 227681.3 | 56798.93 | Unknown | Unknown | 4550.19 | 166332.18 | 630964.86 | 204351.37 | 227681.3 | -23329.93 | Yes | N/A | N/A | 2022-08-16 | 2023-12-14 | 486 | 348 | 2023-12-14 | 2024-04-08 | 117 | 83 | 2024-01-05 | 2024-02-08 | 35 | 25 | 2024-04-18 | 2024-05-16 | 22 | 12 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-04-23 | 2025-02-25 | 309 | 221 | 2025-03-14 | 2025-05-05 | 53 | 37 | 2025-05-05 | 2025-05-05 | 1 | 1 | 521 | 373 | 502 | 354 | 1023 | 727 | Steps 2,3,5,6,7 | 117 | 83 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | 133 | 96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2025-05-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 32962.49 | 13963.29 | Unknown | Unknown | 222.23 | 18776.97 | 353273 | 45802.17 | 32962.49 | 12839.68 | Yes | N/A | N/A | 2023-03-10 | 2023-06-30 | 113 | 81 | 2023-06-30 | 2024-07-16 | 383 | 273 | 2023-08-07 | 2024-06-29 | 11 | 8 | 2024-07-12 | 2024-07-24 | 13 | 9 | 2024-08-15 | Unknown | Unknown | Unknown | 2024-08-15 | 2025-04-23 | 252 | 180 | 2025-05-12 | 2025-06-11 | 31 | 23 | 2025-06-11 | 2025-06-11 | 1 | 1 | 124 | 89 | 680 | 486 | 804 | 575 | Steps 2,3,5,6,7 | 344 | 246 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -145 | -104 | No | 2023-11-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2025-05-12 | IOU Designed & Installed | N/A | Yes | 158 | 3102.79 | Unknown | Unknown | Unknown | 99.14 | 3003.65 | 3981 | 887.3 | 3102.79 | -2215.49 | Yes | N/A | N/A | 2023-11-20 | 2024-04-25 | 158 | 114 | 2024-04-25 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2025-05-12 | 530 | 378 | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-12 | 2025-05-22 | 11 | 9 | 2025-05-22 | 2025-05-14 | Unknown | Unknown | 688 | 492 | 11 | 9 | 699 | 501 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -473 | -340 | No | 2024-12-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | 2025-02-21 | IOU Designed & Installed | N/A | Yes | 6 | 1065.43 | Unknown | Unknown | Unknown | Unknown | 1065.43 | 3981 | 1983.61 | 1065.43 | 918.18 | Yes | N/A | N/A | 2024-12-06 | 2024-12-09 | 4 | 2 | 2024-12-09 | 2024-12-12 | 4 | 4 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-02-21 | 78 | 56 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-21 | 2025-02-25 | 5 | 3 | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 82 | 58 | 9 | 7 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 90.32 | -1.25 | Unknown | Unknown | Unknown | 91.57 | 3981 | 1738.49 | 90.32 | 1648.17 | Yes | N/A | N/A | 2024-09-25 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-11-20 | 92 | 66 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-01-10 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-06 | 28 | 20 | 2025-02-06 | 2025-02-06 | 1 | 1 | 52 | 38 | 121 | 87 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -253 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-22 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | 395.72 | Unknown | Unknown | Unknown | Unknown | 395.72 | Unknown | 2521.02 | 395.72 | 2125.3 | Yes | N/A | N/A | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | 2025-05-02 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-07 | 15 | 11 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-21 | 3 | 2 | 2025-06-21 | 2025-06-21 | 1 | 0 | 1 | 1 | 51 | 37 | 52 | 38 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -156 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 1470.6 | -58.47 | Unknown | Unknown | 60.14 | 1468.93 | 3981 | 1116.66 | 1470.6 | -353.94 | Yes | N/A | N/A | 2023-10-18 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-10-18 | 51 | 37 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2024-04-18 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-11-09 | 206 | 147 | 2024-11-09 | 2024-11-09 | 1 | 0 | 184 | 132 | 258 | 184 | 442 | 316 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 24.35 | 24.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -506 | -363 | No | 2024-01-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-06-25 | IOU Designed & Installed | N/A | Yes | 139 | 898.76 | -10.03 | Unknown | Unknown | 12.51 | 896.28 | 3981 | 767.8 | 898.76 | -130.96 | Yes | N/A | N/A | 2024-01-23 | 2024-06-10 | 140 | 100 | 2024-06-10 | 2024-04-15 | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-06-25 | 72 | 52 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-25 | 2024-07-02 | 8 | 6 | 2024-07-02 | 2024-07-02 | 1 | 1 | 212 | 152 | 9 | 7 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -475 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 1306.24 | Unknown | Unknown | Unknown | 7.18 | 1299.06 | 3981 | 2317.6 | 1306.24 | 1011.36 | Yes | N/A | N/A | 2024-04-05 | 2024-04-24 | 20 | 14 | 2024-04-24 | 2024-04-25 | 2 | 2 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-11-05 | 195 | 139 | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-05 | 2024-11-22 | 18 | 14 | 2024-11-22 | 2024-11-22 | 1 | 1 | 215 | 153 | 21 | 17 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | -228 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | -423.32 | -12.96 | Unknown | Unknown | -616 | 205.64 | Unknown | 615.8 | -423.32 | 1039.12 | Yes | N/A | N/A | 2023-04-19 | 2023-05-15 | 27 | 19 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-07-18 | 62 | 44 | Unknown | 2023-06-22 | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 89 | 63 | 2 | 2 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -667 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-31 | 2024-08-31 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 39.06 | Unknown | Unknown | Unknown | Unknown | 39.06 | 3981 | 1411.72 | 39.06 | 1372.66 | Yes | N/A | N/A | 2024-08-31 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-09-04 | 7 | 5 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-31 | 2024-09-27 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-18 | 22 | 16 | 2024-10-18 | 2024-10-18 | 1 | 1 | 28 | 20 | 30 | 22 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 3103 | 3103 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-15 | 92 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-10-13 | IOU Designed & Installed | N/A | No | N/A | 2775.26 | 768.73 | Unknown | 178.29 | Unknown | 1828.24 | 11943 | 914.8 | 2775.26 | -1860.46 | Yes | N/A | N/A | 2024-08-14 | 2024-08-21 | 8 | 6 | 2024-08-21 | 2024-08-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-25 | 37 | 27 | 2024-08-29 | 2024-09-03 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-13 | 2024-10-15 | 3 | 2 | 2024-10-15 | 2024-10-15 | 1 | 1 | 14 | 10 | 50 | 37 | 64 | 47 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -703 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 29.41 | -4.22 | Unknown | Unknown | Unknown | 33.63 | Unknown | 1576.73 | 29.41 | 1547.32 | Yes | N/A | N/A | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-11 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-29 | 19 | 13 | 2024-07-29 | 2024-07-29 | 1 | 1 | 11 | 9 | 21 | 15 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-10 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.25 | -12.71 | Unknown | Unknown | Unknown | 8.46 | 3981 | 1564.88 | -4.25 | 1569.13 | Yes | N/A | N/A | 2023-02-27 | 2023-03-06 | 8 | 6 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | Unknown | Unknown | 2023-04-12 | 2023-04-12 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-10 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 1255.04 | Unknown | Unknown | Unknown | 12.27 | 1242.77 | 3981 | 1412.81 | 1255.04 | 157.77 | Yes | N/A | N/A | 2024-10-10 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-28 | 42 | 30 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-30 | 64 | 46 | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-30 | 2025-01-03 | 5 | 5 | 2025-01-03 | 2025-01-03 | 1 | 1 | 64 | 46 | 48 | 36 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -41 | -30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1194.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-11-06 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-03-25 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-06-13 | 50 | 36 | 2025-06-13 | 2025-06-13 | 1 | 1 | 141 | 101 | 71 | 51 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | 874.33 | -9.69 | Unknown | Unknown | 15.57 | 868.45 | 3981 | 806.87 | 874.33 | -67.46 | Yes | N/A | N/A | 2024-02-22 | 2024-02-22 | 1 | 1 | 2024-02-22 | 2024-02-28 | 7 | 5 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-06-12 | 106 | 76 | Unknown | 2024-05-30 | Unknown | Unknown | 2024-06-12 | 2024-06-21 | 10 | 8 | 2024-06-21 | 2024-06-21 | 1 | 1 | 107 | 77 | 18 | 14 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-20 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 2219.38 | 364.12 | Unknown | 85.11 | Unknown | 1770.15 | Unknown | 1683.66 | 2219.38 | -535.72 | Yes | N/A | N/A | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-20 | 3 | 3 | 2024-12-20 | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-10 | 16 | 12 | 2024-12-20 | 2025-02-27 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-02-27 | 1 | 1 | 70 | 50 | 21 | 17 | 91 | 67 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2023-04-29 | IOU Designed & Installed | N/A | No | N/A | -12.45 | -9.88 | Unknown | Unknown | Unknown | -2.57 | Unknown | 149.62 | -12.45 | 162.07 | Yes | N/A | N/A | 2023-04-03 | 2023-04-10 | 8 | 6 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-04-29 | 20 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-04-29 | 2023-06-12 | 45 | 31 | 2023-06-12 | 2023-06-12 | 1 | 1 | 28 | 21 | 46 | 32 | 74 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 1929 | 1380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.73 | Unknown | Unknown | Unknown | 0.65 | 0.08 | Unknown | 1703.51 | 0.73 | 1702.78 | Yes | N/A | N/A | 2023-08-08 | 2023-08-09 | 2 | 2 | 2023-08-09 | 2023-10-24 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-08-16 | 8 | 6 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-04-12 | 1 | 1 | 2 | 2 | 86 | 62 | 88 | 64 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-16 | 2023-01-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1453.3 | -930.95 | Unknown | Unknown | Unknown | -522.35 | 3981 | 1010.58 | -1453.3 | 2463.88 | Yes | N/A | N/A | 2023-01-16 | 2023-03-24 | 68 | 50 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-06-28 | 1 | 1 | 68 | 50 | 1 | 1 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-18 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 22.92 | Unknown | Unknown | Unknown | Unknown | 22.92 | 3981 | 196.69 | 22.92 | 173.77 | Yes | N/A | N/A | 2024-07-16 | 2025-01-24 | 193 | 139 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 193 | 139 | 2 | 2 | 195 | 141 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 1484.74 | 249.56 | Unknown | Unknown | Unknown | 1235.18 | Unknown | 1861.42 | 1484.74 | 376.68 | Yes | N/A | N/A | 2025-03-17 | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-03-18 | 9 | 7 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-24 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-12 | 19 | 13 | 2025-05-12 | 2025-05-12 | 1 | 1 | 38 | 28 | 29 | 21 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -696 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 1315.17 | 410.25 | Unknown | 176.88 | Unknown | 728.04 | 3981 | 653.18 | 1315.17 | -661.99 | Yes | N/A | N/A | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-25 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-07-26 | 2 | 2 | 2023-07-26 | 2023-07-26 | 1 | 1 | 7 | 5 | 4 | 4 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1753.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-04 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-04-23 | 51 | 37 | 2025-04-23 | 2025-04-23 | 1 | 1 | 14 | 10 | 53 | 39 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-28 | 567 | 406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 65148.71 | 11987.21 | Unknown | Unknown | 40.28 | 53121.22 | 0 | 20666.78 | 65148.71 | -44481.93 | Yes | N/A | N/A | 2023-07-07 | 2023-07-07 | 1 | 1 | 2023-07-07 | 2024-02-06 | 215 | 153 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2024-02-13 | 104 | 74 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-17 | 35 | 25 | 2024-06-17 | 2024-06-17 | 1 | 1 | 1 | 1 | 355 | 253 | 356 | 254 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-01-08 | IOU Designed & Installed | N/A | No | N/A | 507.37 | -19.35 | Unknown | Unknown | Unknown | 526.72 | Unknown | 1531.53 | 507.37 | 1024.16 | Yes | N/A | N/A | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-01 | 14 | 10 | 2023-12-27 | 2024-01-08 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-02-01 | 25 | 19 | 2024-02-01 | 2024-02-01 | 1 | 1 | 14 | 10 | 41 | 31 | 55 | 41 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 778.05 | 778.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-28 | -319 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2998.52 | -88.09 | Unknown | Unknown | 31.97 | 3054.64 | 3981 | 1012.19 | 2998.52 | -1986.33 | Yes | N/A | N/A | 2023-04-12 | 2023-04-12 | 1 | 1 | 2023-04-12 | 2023-04-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-04-20 | 8 | 6 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 1 | 1 | 16 | 12 | 17 | 13 | Steps 2,3,5,6,7 | 2 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | 7150 | 7150 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-02 | -96 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 88949.88 | 11506.46 | Unknown | 47.69 | Unknown | 77395.73 | 0 | 44217.05 | 88949.88 | -44732.83 | Yes | N/A | N/A | 2024-02-26 | 2024-02-26 | 1 | 1 | 2024-02-26 | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-01 | 2 | 2 | 2024-06-03 | 2025-04-17 | 165 | 117 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-28 | 1 | 1 | 3 | 3 | 166 | 118 | 169 | 121 | Steps 2,3,5,6,7 | 59 | 43 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 483.05 | 483.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1808.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-04 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 317.81 | Unknown | Unknown | Unknown | -789.08 | 1106.89 | Unknown | 790.36 | 317.81 | 472.55 | Yes | N/A | N/A | 2024-01-03 | 2024-03-02 | 60 | 43 | 2024-03-02 | 2024-03-12 | 11 | 7 | 2024-03-12 | 2024-04-01 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-07-12 | 103 | 75 | Unknown | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-07-29 | 18 | 12 | 2024-07-29 | 2024-07-29 | 1 | 1 | 184 | 133 | 30 | 20 | 214 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-02 | -710 | -507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 802.9 | Unknown | Unknown | Unknown | Unknown | 802.9 | Unknown | 614.53 | 802.9 | -188.37 | Yes | N/A | N/A | 2025-05-14 | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-20 | 8 | 6 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 0 | 0 | 9 | 7 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 1320.52 | -13.19 | Unknown | Unknown | 28.45 | 1305.26 | Unknown | 1536.31 | 1320.52 | 215.79 | Yes | N/A | N/A | 2024-11-05 | 2024-11-20 | 16 | 12 | 2024-11-20 | 2024-12-02 | 13 | 9 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-03-11 | 100 | 72 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-11 | 2025-04-03 | 24 | 18 | 2025-04-03 | 2025-04-02 | Unknown | Unknown | 116 | 84 | 37 | 27 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2024-06-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 6420.42 | Unknown | Unknown | Unknown | -2288 | 8708.42 | Unknown | 2646.87 | 6420.42 | -3773.55 | Yes | N/A | N/A | 2023-11-03 | 2024-02-13 | 103 | 73 | 2024-02-13 | 2024-06-11 | 120 | 86 | 2024-03-27 | 2024-04-02 | 7 | 5 | 2024-04-22 | 2024-06-13 | 37 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-23 | 30 | 22 | 2024-07-23 | 2024-07-23 | 1 | 1 | 110 | 78 | 188 | 134 | 298 | 212 | Steps 2,3,5,6,7 | 76 | 54 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3694.22 | 826.29 | Unknown | Unknown | 74.18 | 2793.75 | 3981 | 1539.73 | 3694.22 | -2154.49 | Yes | N/A | N/A | 2023-12-04 | 2024-03-21 | 109 | 79 | 2024-03-21 | 2024-11-14 | 239 | 171 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-01-07 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-10 | Unknown | Unknown | 164 | 118 | 239 | 171 | 403 | 289 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-05-31 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | -5.5 | -4.72 | Unknown | Unknown | Unknown | -0.78 | 3981 | 787.98 | -5.5 | 793.48 | Yes | N/A | N/A | 2024-04-25 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | 2024-05-31 | 64 | 46 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-04 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-25 | 52 | 38 | 2024-07-25 | 2024-07-25 | 1 | 1 | 5 | 3 | 117 | 85 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | 257 | 184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 400.19 | -7.41 | Unknown | Unknown | Unknown | 407.6 | 3981 | 427.5 | 400.19 | 27.31 | Yes | N/A | N/A | 2024-01-02 | 2024-01-03 | 2 | 2 | 2024-01-03 | 2024-04-24 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-01-08 | 6 | 4 | 2024-04-24 | 2024-10-28 | 188 | 134 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | 2024-12-11 | 2024-12-10 | Unknown | Unknown | 190 | 136 | 119 | 85 | 309 | 221 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 845.79 | Unknown | Unknown | Unknown | Unknown | 845.79 | 3981 | 800.33 | 845.79 | -45.46 | Yes | N/A | N/A | 2024-04-02 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-04-05 | 50 | 36 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-08-20 | 138 | 98 | Unknown | 2024-08-14 | Unknown | Unknown | 2024-08-20 | 2024-08-27 | 8 | 6 | 2024-08-27 | 2024-08-27 | 1 | 1 | 138 | 98 | 59 | 43 | 197 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -551 | -394 | No | 2024-08-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | Yes | 20 | 14.13 | Unknown | Unknown | Unknown | Unknown | 14.13 | Unknown | 1448.36 | 14.13 | 1434.23 | Yes | N/A | N/A | 2024-08-28 | 2024-09-11 | 15 | 11 | 2024-09-11 | 2024-09-17 | 7 | 5 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-01-21 | 1 | 1 | 15 | 11 | 8 | 6 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 352 | 352 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-15 | 597 | 428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2024-03-07 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 53042.03 | 2265.14 | Unknown | Unknown | 5519.28 | 45257.61 | 13927.6 | 4328.91 | 53042.03 | -48713.12 | Yes | N/A | N/A | 2023-11-20 | 2024-03-07 | 109 | 79 | 2024-03-07 | 2024-11-11 | 250 | 178 | 2024-09-06 | 2024-11-05 | 9 | 7 | 2024-12-03 | 2024-12-09 | 7 | 5 | 2024-12-11 | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-02 | Unknown | Unknown | 2024-12-27 | 2025-04-03 | 98 | 70 | 2025-04-03 | 2025-04-03 | 1 | 1 | 118 | 86 | 356 | 254 | 474 | 340 | Steps 2,3,5,6,7 | 66 | 46 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-15 | -668 | -477 | No | 2024-05-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-10 | 2024-08-14 | IOU Designed & Installed | N/A | Yes | 5 | 1339.53 | 380.74 | Unknown | Unknown | -511 | 1469.79 | 7962 | 1725.38 | 1339.53 | 385.85 | Yes | N/A | N/A | 2024-05-09 | 2024-05-14 | 6 | 4 | 2024-05-14 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-05-15 | 6 | 4 | 2024-05-10 | 2024-06-11 | 33 | 23 | 2024-05-14 | 2024-08-14 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-16 | 3 | 3 | 2024-08-16 | 2024-08-16 | 1 | 1 | 105 | 75 | 37 | 27 | 142 | 102 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 394 | 394 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.25 | Unknown | Unknown | Unknown | Unknown | 12.25 | 3981 | 192.95 | 12.25 | 180.7 | Yes | N/A | N/A | 2024-06-28 | 2024-08-23 | 57 | 41 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 57 | 41 | 2 | 2 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.39 | -9.89 | Unknown | Unknown | Unknown | 7.5 | Unknown | 447.77 | -2.39 | 450.16 | Yes | N/A | N/A | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 7300 | 7300 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-15 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-11-02 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 892.59 | 302.11 | Unknown | Unknown | Unknown | 590.48 | 3981 | 879.66 | 892.59 | -12.93 | Yes | N/A | N/A | 2023-09-08 | 2023-11-02 | 56 | 40 | 2023-11-02 | 2025-03-06 | 491 | 351 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-12-18 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2023-12-21 | 4 | 4 | 2023-12-21 | 2023-12-21 | 1 | 1 | 103 | 73 | 496 | 356 | 599 | 429 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Warner Springs | COUNTY OF SAN DIEGO-SOUTH of 56 | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-30 | 848 | 606 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 19976.17 | 2370.51 | Unknown | Unknown | -5872 | 23477.66 | 1905 | 13648.24 | 19976.17 | -6327.93 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | 2023-11-06 | 263 | 187 | 2023-02-21 | 2023-11-03 | 249 | 178 | 2023-09-20 | 2023-11-14 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-24 | 34 | 24 | 2025-02-24 | 2025-02-24 | 1 | 1 | 250 | 179 | 310 | 222 | 560 | 401 | Steps 2,3,5,6,7 | 302 | 216 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 261 | 261 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-01 | 371 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 858.03 | -31.47 | Unknown | Unknown | 153.87 | 735.63 | 15924 | 488.8 | 858.03 | -369.23 | Yes | N/A | N/A | 2023-03-06 | 2023-02-27 | Unknown | Unknown | 2023-02-27 | 2023-05-23 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-10-10 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2022-11-07 | Unknown | Unknown | 141 | 101 | 86 | 62 | 227 | 163 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -443 | -318 | No | 2023-12-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-01-22 | 2024-06-07 | IOU Designed & Installed | N/A | Yes | 167 | 11.12 | -9.88 | Unknown | Unknown | Unknown | 21 | 3981 | 875.03 | 11.12 | 863.91 | Yes | N/A | N/A | 2023-12-05 | 2024-05-20 | 168 | 120 | 2024-05-20 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-06-07 | 138 | 100 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-13 | 7 | 5 | 2024-06-13 | 2024-06-11 | Unknown | Unknown | 306 | 220 | 7 | 5 | 313 | 225 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 2046.55 | 454.68 | Unknown | 235.99 | Unknown | 1355.88 | 3981 | 2036.68 | 2046.55 | -9.87 | Yes | N/A | N/A | 2025-04-02 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | 2025-04-02 | 21 | 15 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-05-05 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-19 | 15 | 11 | 2025-05-19 | 2025-05-19 | 1 | 1 | 34 | 24 | 37 | 27 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-14 | 24 | 19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16371.42 | 12210.98 | Unknown | 1977.84 | -2847 | 5029.6 | Unknown | 2847.34 | 16371.42 | -13524.08 | Yes | N/A | N/A | 2023-05-01 | 2023-05-01 | 1 | 1 | 2023-05-01 | 2023-05-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-08 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -422 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-11-06 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 10.95 | -9.71 | Unknown | Unknown | Unknown | 20.66 | Unknown | 934 | 10.95 | 923.05 | Yes | N/A | N/A | 2023-10-12 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-11-06 | 85 | 61 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-05-20 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-07 | 19 | 15 | 2024-06-07 | 2024-06-07 | 1 | 1 | 197 | 141 | 105 | 77 | 302 | 218 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -29.86 | -22.6 | Unknown | Unknown | Unknown | -7.26 | Unknown | 153.83 | -29.86 | 183.69 | Yes | N/A | N/A | 2023-08-02 | 2023-08-02 | 1 | 1 | 2023-08-02 | 2023-08-10 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-02-07 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | -241 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-13 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 334.39 | Unknown | Unknown | Unknown | 1.68 | 332.71 | 3961 | 1174.73 | 334.39 | 840.34 | Yes | N/A | N/A | 2024-06-11 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-06-26 | 56 | 40 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-12 | 17 | 13 | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-12 | 2024-07-25 | 14 | 10 | 2024-07-25 | 2024-07-24 | Unknown | Unknown | 17 | 13 | 70 | 50 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 917.15 | 917.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 436 | 313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | 2025-02-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 44157.52 | 935.29 | Unknown | Unknown | 1232.34 | 41989.89 | 45683 | 21970.86 | 44157.52 | -22186.66 | Yes | N/A | N/A | 2023-05-18 | 2023-08-07 | 82 | 58 | 2023-08-07 | 2023-11-14 | 100 | 72 | 2023-09-06 | 2023-11-14 | 17 | 11 | 2023-06-28 | 2023-11-21 | 22 | 16 | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-07 | 2025-02-04 | 90 | 64 | 2025-02-13 | 2025-03-12 | 28 | 20 | 2025-03-12 | 2025-03-12 | 1 | 1 | 99 | 69 | 241 | 173 | 340 | 242 | Steps 2,3,5,6,7 | 208 | 148 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -324 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | -12.81 | -10.34 | Unknown | Unknown | Unknown | -2.47 | Unknown | 480.37 | -12.81 | 493.18 | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-10-31 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-04-09 | 162 | 116 | 2024-04-09 | 2024-04-09 | 1 | 1 | 78 | 56 | 164 | 118 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | -1043.77 | Unknown | Unknown | Unknown | -1129 | 85.23 | 3981 | 3767.7 | -1043.77 | 4811.47 | Yes | N/A | N/A | 2024-12-19 | 2025-01-07 | 20 | 14 | 2025-01-07 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2025-01-07 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-19 | 44 | 32 | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-03-06 | 2025-03-06 | 1 | 1 | 83 | 59 | 17 | 13 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA16 PH3 | San Diego PA16 PH3 | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 584 | 419 | No | 2022-06-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-10-17 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 299 | 241366.76 | 33775.73 | Unknown | Unknown | 7268.65 | 200322.38 | 0 | 119504.75 | 241366.76 | -121862.01 | Yes | N/A | N/A | 2022-04-27 | 2023-04-18 | 357 | 255 | 2023-04-18 | 2023-07-24 | 98 | 70 | 2023-05-10 | 2025-02-03 | 321 | 229 | 2023-07-24 | 2025-02-24 | 96 | 70 | 2023-09-19 | Unknown | Unknown | Unknown | 2023-09-19 | 2024-10-15 | 393 | 281 | 2024-10-17 | 2024-10-24 | 8 | 6 | 2024-10-24 | 2024-10-24 | 1 | 1 | 678 | 484 | 596 | 428 | 1274 | 912 | Steps 2,3,5,6,7 | 1159 | 827 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 34.28 | Unknown | Unknown | Unknown | Unknown | 34.28 | 3981 | 1443.1 | 34.28 | 1408.82 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-20 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | -276 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 2205.77 | 296.33 | Unknown | Unknown | 3.28 | 1906.16 | 3981 | 751.88 | 2205.77 | -1453.89 | Yes | N/A | N/A | 2023-07-24 | 2023-08-28 | 36 | 26 | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-07 | 2024-05-15 | 39 | 28 | Unknown | 2024-05-01 | Unknown | Unknown | 2024-05-15 | 2024-05-17 | 3 | 3 | 2024-05-17 | 2024-05-16 | Unknown | Unknown | 75 | 54 | 4 | 4 | 79 | 58 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6036.2 | 6036.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-05 | -544 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | 2023-11-02 | IOU Designed & Installed | N/A | No | N/A | 1410.87 | 309 | Unknown | Unknown | 80.71 | 1021.16 | 3981 | 950.04 | 1410.87 | -460.83 | Yes | N/A | N/A | 2023-08-02 | 2023-05-19 | Unknown | Unknown | 2023-05-19 | 2023-09-22 | 127 | 91 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-11-02 | 42 | 30 | Unknown | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2024-10-10 | 344 | 246 | 2024-10-10 | 2023-11-08 | Unknown | Unknown | 42 | 30 | 471 | 337 | 513 | 367 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 87.83 | 22.7 | Unknown | Unknown | -1247 | 1312.13 | Unknown | 1247.45 | 87.83 | 1159.62 | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-03-25 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-28 | 19 | 15 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-03 | 2 | 2 | 2025-06-03 | 2025-06-03 | 1 | 1 | 1 | 1 | 66 | 50 | 67 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 4853.7 | 1280.99 | Unknown | 1142.54 | -486 | 2916.17 | 3981 | 1592.86 | 4853.7 | -3260.84 | Yes | N/A | N/A | 2024-08-07 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-08-07 | 8 | 6 | 2024-08-07 | 2024-08-16 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-10-15 | 61 | 43 | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-15 | 2024-10-23 | 9 | 7 | 2024-10-23 | 2024-10-23 | 1 | 1 | 71 | 51 | 18 | 14 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONSALL | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-11 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 69.04 | Unknown | Unknown | Unknown | Unknown | 69.04 | 3981 | 1002.69 | 69.04 | 933.65 | Yes | N/A | N/A | 2024-03-01 | 2024-03-04 | 4 | 2 | 2024-03-04 | 2024-03-06 | 3 | 3 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-09-12 | 186 | 134 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-10-01 | 20 | 14 | 2024-10-01 | 2024-09-30 | Unknown | Unknown | 190 | 136 | 23 | 17 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 135 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-03 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 12031.53 | 513.2 | Unknown | Unknown | Unknown | 11518.33 | Unknown | 2141.17 | 12031.53 | -9890.36 | Yes | N/A | N/A | 2022-11-17 | 2023-09-26 | 314 | 224 | 2023-09-26 | 2023-11-01 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-02-27 | 93 | 67 | 2024-02-27 | 2024-02-27 | 1 | 1 | 314 | 224 | 131 | 95 | 445 | 319 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -55 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1656.92 | 2083.64 | Unknown | Unknown | -4650 | 909.44 | Unknown | 4649.68 | -1656.92 | 6306.6 | Yes | N/A | N/A | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | 2023-11-27 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 15 | 11 | 16 | 12 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 125 | 125 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 143 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2022-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1709.54 | -28.83 | Unknown | Unknown | 68.67 | 1669.7 | 112126 | 3905.23 | 1709.54 | 2195.69 | Yes | N/A | N/A | 2022-09-28 | 2023-02-24 | 150 | 108 | 2023-02-24 | 2023-03-17 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-02 | Unknown | Unknown | 150 | 108 | 22 | 16 | 172 | 124 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 156.05 | 156.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-23 | -200 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-20 | 2023-08-11 | IOU Designed & Installed | N/A | No | N/A | -22.17 | -17.59 | Unknown | Unknown | Unknown | -4.58 | 3961 | 153.87 | -22.17 | 176.04 | Yes | N/A | N/A | 2023-06-15 | 2023-07-22 | 38 | 27 | 2023-07-22 | 2023-07-22 | 1 | 0 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | 2023-08-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-09-05 | 26 | 18 | 2023-09-05 | 2023-09-05 | 1 | 1 | 59 | 42 | 28 | 19 | 87 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | 320 | 229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-10 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 4415.58 | 729.92 | Unknown | 115.23 | 67.08 | 3503.35 | 3885 | 342.42 | 4415.58 | -4073.16 | Yes | N/A | N/A | 2023-01-31 | 2023-02-24 | 25 | 19 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2025-01-28 | 705 | 503 | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-28 | 2025-01-29 | 2 | 2 | 2025-01-29 | 2025-01-29 | 1 | 1 | 730 | 522 | 3 | 3 | 733 | 525 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 36550.2 | 36550.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-01 | 67 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-11-21 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 15783.33 | 1490.57 | Unknown | Unknown | 12.23 | 14280.53 | Unknown | 11169.95 | 15783.33 | -4613.38 | Yes | N/A | N/A | 2024-09-30 | 2024-10-01 | 2 | 2 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-03-05 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-09 | 24 | 18 | 2025-04-09 | 2025-04-09 | 1 | 1 | 2 | 2 | 65 | 49 | 67 | 51 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -589 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-29 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 29.2 | Unknown | Unknown | Unknown | Unknown | 29.2 | Unknown | 1571.57 | 29.2 | 1542.37 | Yes | N/A | N/A | 2024-10-28 | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-10-29 | 26 | 18 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-01-07 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-14 | 39 | 29 | 2025-02-14 | 2025-02-14 | 1 | 1 | 71 | 51 | 66 | 48 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 987 | 987 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-03-21 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2372.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-03-20 | 43 | 31 | 2025-03-20 | 2025-03-28 | 9 | 7 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-05-30 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 107 | 77 | 10 | 8 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | 900 | 900 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-21 | 608 | 435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 15902.31 | 391.05 | Unknown | Unknown | 1122.53 | 14388.73 | Unknown | 13188.34 | 15902.31 | -2713.97 | Yes | N/A | N/A | 2023-08-14 | 2024-05-29 | 290 | 208 | 2024-05-29 | 2024-01-05 | Unknown | Unknown | 2023-09-01 | Unknown | Unknown | Unknown | 2023-09-05 | 2024-05-03 | 242 | 174 | 2024-01-10 | Unknown | Unknown | Unknown | 2024-01-10 | 2024-07-03 | 176 | 126 | 2024-07-11 | 2025-03-20 | 253 | 181 | 2025-03-20 | 2025-03-20 | 1 | 1 | 290 | 208 | 672 | 482 | 962 | 690 | Steps 2,3,5,6,7 | 240 | 172 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | POWAY | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-31 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 693.47 | 124.03 | Unknown | Unknown | Unknown | 569.44 | Unknown | 449.58 | 693.47 | -243.89 | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2024-09-11 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-11-15 | 43 | 33 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2024-12-31 | 2025-01-07 | 8 | 6 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2 | 2 | 96 | 72 | 98 | 74 | Steps 2,3,5,6,7 | 171 | 123 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | -422 | -302 | No | 2023-09-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-04-23 | IOU Designed & Installed | N/A | Yes | 52 | 1024.61 | -3.75 | Unknown | Unknown | 30.83 | 997.53 | 3961 | 894.15 | 1024.61 | -130.46 | Yes | N/A | N/A | 2023-09-29 | 2023-11-17 | 50 | 36 | 2023-11-17 | 2023-11-20 | 4 | 2 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-04-23 | 156 | 112 | Unknown | 2024-04-22 | Unknown | Unknown | 2024-04-23 | 2024-05-03 | 11 | 9 | 2024-05-03 | 2024-05-02 | Unknown | Unknown | 206 | 148 | 15 | 11 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-05-19 | IOU Designed & Installed | N/A | No | N/A | 3038.56 | 3662.52 | Unknown | 59.78 | -2441 | 1757.26 | Unknown | 2441.23 | 3038.56 | -597.33 | Yes | N/A | N/A | 2024-03-19 | 2024-04-11 | 24 | 18 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-19 | 2024-05-22 | 4 | 3 | 2024-05-22 | 2024-05-22 | 1 | 1 | 24 | 18 | 5 | 4 | 29 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | -626 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 1023.48 | 182.98 | Unknown | Unknown | Unknown | 840.5 | 3981 | 1640.98 | 1023.48 | 617.5 | Yes | N/A | N/A | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-30 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-10-10 | 42 | 30 | 2024-10-10 | 2024-10-10 | 1 | 1 | 52 | 38 | 44 | 32 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | -408 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 54.07 | -6.19 | Unknown | Unknown | -620.7 | 680.96 | Unknown | 651.64 | 54.07 | 597.57 | Yes | N/A | N/A | 2023-05-26 | 2023-06-05 | 11 | 7 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-09-22 | 39 | 29 | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-22 | 2024-02-03 | 135 | 96 | 2024-02-03 | 2024-02-03 | 1 | 0 | 50 | 36 | 136 | 96 | 186 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-09-07 | -1455 | -1040 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 856.35 | -23.99 | Unknown | Unknown | Unknown | 880.34 | 3981 | 677.33 | 856.35 | -179.02 | Yes | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -521 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 434.43 | -7.48 | Unknown | Unknown | 4.38 | 437.53 | 3981 | 676.16 | 434.43 | 241.73 | Yes | N/A | N/A | 2023-02-28 | 2023-04-06 | 38 | 28 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-07-12 | 1 | 1 | 38 | 28 | 1 | 1 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | 359 | 257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 18760.97 | Unknown | Unknown | Unknown | Unknown | 18760.97 | Unknown | 11056.96 | 18760.97 | -7704.01 | Yes | N/A | N/A | 2024-12-31 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2025-01-24 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-18 | 27 | 19 | 2025-03-18 | 2025-03-18 | 1 | 1 | 0 | 0 | 82 | 60 | 82 | 60 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -681 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1074.13 | -39.87 | Unknown | Unknown | 2.9 | 1111.1 | 3981 | 1253.06 | 1074.13 | 178.93 | Yes | N/A | N/A | 2025-02-25 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-03-07 | 17 | 13 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 0 | 0 | 18 | 14 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-18 | -264 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 1643.15 | 435.54 | Unknown | Unknown | 26.94 | 1180.67 | 3981 | 760.13 | 1643.15 | -883.02 | Yes | N/A | N/A | 2023-02-08 | 2023-03-14 | 35 | 25 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-12-28 | 290 | 208 | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-28 | 2023-12-29 | 2 | 2 | 2023-12-29 | 2023-12-29 | 1 | 1 | 325 | 233 | 3 | 3 | 328 | 236 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 220.1 | 220.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -133 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-08 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10 | -8.89 | Unknown | Unknown | Unknown | 18.89 | 3981 | 520.98 | 10 | 510.98 | Yes | N/A | N/A | 2023-04-08 | 2023-06-08 | 62 | 44 | 2023-06-08 | 2023-07-06 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2024-02-29 | 239 | 171 | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-03-21 | 1 | 1 | 301 | 215 | 30 | 22 | 331 | 237 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-10 | 938 | 670 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-08-28 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 731.48 | -88.13 | Unknown | Unknown | Unknown | 819.61 | 57521 | 7300.87 | 731.48 | 6569.39 | Yes | N/A | N/A | 2020-08-28 | 2023-05-12 | 988 | 706 | 2023-05-12 | 2023-08-17 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-03 | Unknown | Unknown | 988 | 706 | 98 | 70 | 1086 | 776 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 602 | 431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-10-12 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 4801.45 | 1298.47 | Unknown | 150.15 | Unknown | 3352.83 | 48121 | 11293.62 | 4801.45 | 6492.17 | Yes | N/A | N/A | 2023-08-25 | 2023-10-03 | 40 | 28 | 2023-10-03 | 2023-10-30 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-07-03 | 248 | 178 | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-22 | 2024-07-25 | 4 | 4 | 2024-07-25 | 2024-07-25 | 1 | 1 | 288 | 206 | 33 | 25 | 321 | 231 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 380.05 | 380.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | 68 | 49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2579.48 | Unknown | Unknown | Unknown | 9.5 | 2569.98 | 3981 | 1074.31 | 2579.48 | -1505.17 | Yes | N/A | N/A | 2024-06-27 | 2024-07-15 | 19 | 13 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-04 | Unknown | Unknown | 19 | 13 | 1 | 1 | 20 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | 765.26 | 251.21 | Unknown | Unknown | Unknown | 514.05 | 3981 | 805.59 | 765.26 | 40.33 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-12-13 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-15 | 3 | 3 | 2023-12-15 | 2023-12-15 | 1 | 1 | 39 | 29 | 5 | 5 | 44 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 418 | 299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-01-17 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 981.01 | -17 | Unknown | Unknown | 27.11 | 970.9 | 3981 | 592.32 | 981.01 | -388.69 | Yes | N/A | N/A | 2023-01-11 | 2023-02-21 | 42 | 30 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2024-05-06 | 441 | 315 | Unknown | 2024-04-17 | Unknown | Unknown | 2024-05-06 | 2024-05-28 | 23 | 17 | 2024-05-28 | 2024-05-23 | Unknown | Unknown | 483 | 345 | 23 | 17 | 506 | 362 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | EL CAJON | 2272 | 2272 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-01 | 139 | 100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-10-11 | 2025-04-27 | IOU Designed & Installed | N/A | No | N/A | 3232.67 | 839.76 | Unknown | 141.96 | Unknown | 2250.95 | 15924 | 870.98 | 3232.67 | -2361.69 | Yes | N/A | N/A | 2024-06-05 | 2024-08-28 | 85 | 61 | 2024-08-28 | 2024-12-26 | 121 | 87 | 2024-10-11 | 2024-10-14 | 4 | 2 | 2024-10-14 | 2025-03-28 | 45 | 33 | 2024-12-26 | 2025-03-04 | 69 | 49 | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-27 | 2025-04-27 | 1 | 0 | 2025-04-27 | 2025-05-20 | 24 | 17 | 158 | 112 | 191 | 137 | 349 | 249 | Steps 2,3,5,6,7 | 168 | 120 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 45.4 | 45.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 814.03 | -14.87 | Unknown | Unknown | -752 | 1580.9 | Unknown | 751.7 | 814.03 | -62.33 | Yes | N/A | N/A | 2023-11-28 | 2024-01-03 | 37 | 27 | 2024-01-03 | 2024-01-05 | 3 | 3 | 2024-01-05 | 2024-03-05 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-02 | 1 | 1 | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-02 | 2024-05-22 | 21 | 15 | 2024-05-22 | 2024-05-22 | 1 | 1 | 99 | 71 | 25 | 19 | 124 | 90 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-13 | -255 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 0.52 | -15.54 | Unknown | Unknown | Unknown | 16.06 | 3941 | 806.98 | 0.52 | 806.46 | Yes | N/A | N/A | 2023-09-28 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-09-28 | 77 | 55 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-02 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-11-01 | 31 | 23 | 2023-11-01 | 2023-11-01 | 1 | 1 | 5 | 3 | 109 | 79 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | 350 | 251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 65.71 | Unknown | Unknown | Unknown | Unknown | 65.71 | 33635 | 873.57 | 65.71 | 807.86 | Yes | N/A | N/A | 2024-05-01 | 2024-05-09 | 9 | 7 | 2024-05-09 | 2024-08-30 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-09-05 | Unknown | Unknown | 9 | 7 | 114 | 82 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -211 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2913.96 | Unknown | Unknown | Unknown | 95.79 | 2818.17 | 3981 | 1396.62 | 2913.96 | -1517.34 | Yes | N/A | N/A | 2024-04-09 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-05-23 | 134 | 96 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-21 | 1 | 1 | 0 | 0 | 135 | 97 | 135 | 97 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -352 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 885.99 | 264.18 | Unknown | 149.98 | Unknown | 471.83 | 3941 | 745.47 | 885.99 | -140.52 | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-03 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2023-10-04 | 2 | 2 | 8 | 6 | 4 | 4 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 158 | 113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 861.09 | -16.1 | Unknown | Unknown | Unknown | 877.19 | 3981 | 2384.84 | 861.09 | 1523.75 | Yes | N/A | N/A | 2024-07-19 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-07-19 | 4 | 4 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-09-12 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-10-18 | 37 | 27 | 2024-10-18 | 2024-11-06 | 20 | 14 | 56 | 40 | 61 | 45 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20402 | 20402 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-06 | 192 | 139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 10240.79 | Unknown | Unknown | Unknown | 81.88 | 10158.91 | 3981 | 865.22 | 10240.79 | -9375.57 | Yes | N/A | N/A | 2023-02-16 | 2023-04-07 | 51 | 37 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-08-30 | 146 | 104 | Unknown | 2023-08-29 | Unknown | Unknown | 2023-08-30 | 2023-09-19 | 21 | 15 | 2023-09-19 | 2023-09-14 | Unknown | Unknown | 197 | 141 | 21 | 15 | 218 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-04 | -25 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 32.68 | -10.66 | Unknown | Unknown | 38.15 | 5.19 | 3981 | 603.29 | 32.68 | 570.61 | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-09-28 | 164 | 118 | Unknown | 2023-09-01 | Unknown | Unknown | 2023-09-28 | 2025-01-10 | 471 | 337 | 2025-01-10 | 2025-01-10 | 1 | 1 | 165 | 119 | 472 | 338 | 637 | 457 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-17 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-18 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 10.13 | Unknown | Unknown | Unknown | Unknown | 10.13 | Unknown | 192.95 | 10.13 | 182.82 | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | 2024-09-18 | 2 | 2 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-08 | 15 | 11 | 2024-10-08 | 2024-10-08 | 1 | 1 | 8 | 6 | 18 | 14 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -275 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 18.25 | 2011.75 | Unknown | Unknown | -2897 | 903.5 | Unknown | 2897.46 | 18.25 | 2879.21 | Yes | N/A | N/A | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | 2024-09-11 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-07-16 | 2024-09-11 | 58 | 42 | 2024-09-11 | 2024-09-11 | 1 | 1 | 1 | 1 | 140 | 102 | 141 | 103 | Steps 2,3,5,6,7 | 57 | 41 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -319 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-06-17 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 224.85 | -12.92 | Unknown | Unknown | -468 | 705.77 | 3981 | 1399.94 | 224.85 | 1175.09 | Yes | N/A | N/A | 2024-03-27 | 2024-06-17 | 83 | 59 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-06-20 | 4 | 4 | 2024-11-07 | 2025-01-21 | 76 | 54 | 2024-06-26 | 2024-10-28 | 125 | 89 | Unknown | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2025-01-27 | 92 | 66 | 2025-01-27 | 2025-01-27 | 1 | 1 | 212 | 152 | 170 | 122 | 382 | 274 | Steps 2,3,5,6,7 | 209 | 149 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-26 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-26 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 25.34 | Unknown | Unknown | Unknown | Unknown | 25.34 | 3981 | 1716.71 | 25.34 | 1691.37 | Yes | N/A | N/A | 2025-02-18 | 2025-02-26 | 9 | 7 | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-04-01 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-16 | 16 | 12 | 2025-04-16 | 2025-04-15 | Unknown | Unknown | 44 | 32 | 17 | 13 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 8.78 | Unknown | Unknown | Unknown | 1.84 | 6.94 | 3981 | 1150.65 | 8.78 | 1141.87 | Yes | N/A | N/A | 2024-11-04 | 2024-11-14 | 11 | 9 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-11 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-28 | 49 | 35 | 2025-01-28 | 2025-01-28 | 1 | 1 | 39 | 29 | 51 | 37 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -619 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-19 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 37.33 | Unknown | Unknown | Unknown | Unknown | 37.33 | 3981 | 1558.2 | 37.33 | 1520.87 | Yes | N/A | N/A | 2024-12-11 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-12-18 | 29 | 21 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-10 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-02-24 | 5 | 3 | 54 | 38 | 45 | 33 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-30 | 2089 | 1492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 388.87 | -7.34 | Unknown | Unknown | Unknown | 396.21 | Unknown | 3327.36 | 388.87 | 2938.49 | Yes | N/A | N/A | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | 2024-06-26 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-20 | 24 | 18 | 2024-06-26 | 2024-11-19 | 147 | 105 | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-17 | Unknown | Unknown | 148 | 106 | 58 | 42 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 306 | 306 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -56 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | 2022-12-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1704.11 | -12.92 | Unknown | Unknown | 12.84 | 1704.19 | 1000 | 539.65 | 1704.11 | -1164.46 | Yes | N/A | N/A | 2022-12-28 | 2023-03-13 | 76 | 54 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2024-07-12 | 51 | 37 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-02 | 1 | 1 | 76 | 54 | 52 | 38 | 128 | 92 | Steps 2,3,5,6,7 | 487 | 349 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | -472 | -337 | No | 2022-08-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2023-09-27 | IOU Designed & Installed | N/A | Yes | 183 | 237.34 | -12.31 | Unknown | Unknown | 19 | 230.65 | 3885 | 801.33 | 237.34 | 563.99 | Yes | N/A | N/A | 2022-08-31 | 2023-03-02 | 184 | 132 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-31 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-02-23 | Unknown | Unknown | 184 | 132 | 1 | 1 | 185 | 133 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-02-03 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 767.81 | -15.43 | Unknown | Unknown | Unknown | 783.24 | 3981 | 1600.23 | 767.81 | 832.42 | Yes | N/A | N/A | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-06-04 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-05 | 2 | 2 | 2025-06-05 | 2025-06-05 | 1 | 1 | 126 | 90 | 4 | 4 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 77.1 | 77.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -605 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 2602.53 | 481.66 | Unknown | 16.26 | 15.54 | 2089.07 | 3981 | 1235.04 | 2602.53 | -1367.49 | Yes | N/A | N/A | 2024-04-10 | 2024-05-03 | 24 | 18 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-25 | 54 | 38 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-25 | 2024-07-03 | 9 | 7 | 2024-07-03 | 2024-07-03 | 1 | 1 | 78 | 56 | 11 | 9 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-16 | 303 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.72 | -2.07 | Unknown | Unknown | Unknown | 3.79 | 0 | 193.76 | 1.72 | 192.04 | Yes | N/A | N/A | 2023-02-24 | 2023-02-25 | 2 | 1 | 2023-02-25 | 2023-03-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 2 | 1 | 7 | 5 | 9 | 6 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-27 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 175.25 | -7.99 | Unknown | Unknown | Unknown | 183.24 | Unknown | 1173.2 | 175.25 | 997.95 | Yes | N/A | N/A | 2024-04-10 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-04-10 | 69 | 49 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-23 | 43 | 31 | 2024-05-23 | 2024-05-23 | 1 | 1 | 2 | 2 | 113 | 81 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-05 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 6.74 | -5.97 | Unknown | Unknown | Unknown | 12.71 | Unknown | 1008.88 | 6.74 | 1002.14 | Yes | N/A | N/A | 2024-03-04 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2024-03-05 | 99 | 71 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-26 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-15 | 21 | 15 | 2024-04-15 | 2024-04-15 | 1 | 1 | 22 | 16 | 121 | 87 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-30 | 760 | 543 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3032.33 | -12.8 | Unknown | Unknown | 75.98 | 2969.15 | 79809 | 4404.92 | 3032.33 | 1372.59 | Yes | N/A | N/A | 2023-03-31 | 2023-03-07 | Unknown | Unknown | 2023-03-07 | 2023-07-26 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2025-01-14 | 539 | 385 | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1 | 1 | 539 | 385 | 143 | 103 | 682 | 488 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | EL CAJON, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | 61 | 44 | No | 2024-07-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-13 | 2025-03-27 | IOU Designed & Installed | N/A | Yes | 91 | 24746.84 | 471.04 | Unknown | Unknown | 29.7 | 24246.1 | Unknown | 17265.06 | 24746.84 | -7481.78 | Yes | N/A | N/A | 2024-07-23 | 2024-10-24 | 94 | 68 | 2024-10-24 | Unknown | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 2024-11-21 | 2025-03-26 | 48 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-17 | 22 | 16 | 2025-04-17 | 2025-04-17 | 1 | 1 | 95 | 69 | 71 | 49 | 166 | 118 | Steps 2,3,5,6,7 | 98 | 70 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 84.75 | 84.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1563.42 | -29.12 | Unknown | Unknown | 0.82 | 1591.72 | 3981 | 1736.71 | 1563.42 | 173.29 | Yes | N/A | N/A | 2024-06-07 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-10-22 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-08-01 | 35 | 25 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 0 | 0 | 247 | 177 | 247 | 177 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -590 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 1362.98 | 421.38 | Unknown | 176.88 | -654.18 | 1418.9 | Unknown | 656.47 | 1362.98 | -706.51 | Yes | N/A | N/A | 2023-04-12 | 2023-04-27 | 16 | 12 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-07-26 | 55 | 39 | Unknown | 2023-07-11 | Unknown | Unknown | 2023-07-26 | 2023-08-03 | 9 | 7 | 2023-08-03 | 2023-08-03 | 1 | 1 | 71 | 51 | 10 | 8 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | -260 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2688.71 | -15.48 | Unknown | Unknown | Unknown | 2704.19 | Unknown | 587.61 | 2688.71 | -2101.1 | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | 2024-10-18 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-20 | 36 | 26 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-04 | 1 | 1 | 1 | 1 | 122 | 88 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 11.51 | -10.27 | Unknown | Unknown | Unknown | 21.78 | Unknown | 969.12 | 11.51 | 957.61 | Yes | N/A | N/A | 2024-02-06 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2024-02-06 | 71 | 51 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-12 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-25 | 43 | 31 | 2024-03-25 | 2024-03-25 | 1 | 1 | 7 | 5 | 115 | 83 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-09-17 | -918 | -657 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 1276.39 | 776.26 | Unknown | 8.57 | Unknown | 491.56 | 9150 | 507.87 | 1276.39 | -768.52 | Yes | N/A | N/A | 2024-09-23 | 2024-10-15 | 23 | 17 | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-01-22 | 100 | 72 | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-22 | 2025-03-13 | 51 | 37 | 2025-03-13 | 2025-03-13 | 1 | 1 | 123 | 89 | 53 | 39 | 176 | 128 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | POWAY | 386 | 386 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-22 | 2022-02-22 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 3008.99 | 512.28 | Unknown | 206.36 | 3.63 | 2286.72 | 3981 | 337.66 | 3008.99 | -2671.33 | Yes | N/A | N/A | 2022-02-22 | 2023-02-22 | 366 | 262 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | 2023-07-17 | 146 | 104 | Unknown | 2023-06-19 | Unknown | Unknown | 2023-07-17 | 2023-08-24 | 39 | 29 | 2023-08-24 | 2023-08-24 | 1 | 1 | 512 | 366 | 40 | 30 | 552 | 396 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | national city | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | 144 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28932.54 | 2385.8 | Unknown | Unknown | 29.07 | 26517.67 | 27801 | 14003.71 | 28932.54 | -14928.83 | Yes | N/A | N/A | 2023-09-11 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2024-09-04 | 394 | 282 | 2024-01-22 | 2024-01-24 | 3 | 3 | 2023-12-17 | 2024-08-31 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-10-16 | 1 | 1 | 3 | 3 | 461 | 331 | 464 | 334 | Steps 2,3,5,6,7 | 264 | 189 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -695 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-14 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 359.71 | -22.1 | Unknown | Unknown | Unknown | 381.81 | 3981 | 1006.92 | 359.71 | 647.21 | Yes | N/A | N/A | 2023-12-06 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2023-12-14 | 15 | 11 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2023-12-20 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-05 | 17 | 13 | 2024-01-05 | 2024-01-05 | 1 | 1 | 7 | 5 | 33 | 25 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 285 | 285 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-02 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 2667.13 | Unknown | Unknown | Unknown | 26.55 | 2640.58 | 3981 | 1591.39 | 2667.13 | -1075.74 | Yes | N/A | N/A | 2024-08-16 | 2024-09-16 | 32 | 22 | 2024-09-16 | 2024-10-01 | 16 | 12 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-02-05 | 128 | 92 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-05 | 2025-02-11 | 7 | 5 | 2025-02-11 | 2025-02-03 | Unknown | Unknown | 160 | 114 | 23 | 17 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.39 | -6.03 | Unknown | Unknown | Unknown | 0.64 | Unknown | 98.41 | -5.39 | 103.8 | Yes | N/A | N/A | 2023-01-20 | 2023-03-03 | 43 | 31 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 43 | 31 | 1 | 1 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -158 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 581.68 | Unknown | Unknown | Unknown | Unknown | 581.68 | Unknown | 449.58 | 581.68 | -132.1 | Yes | N/A | N/A | 2024-09-05 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2025-01-29 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 0 | 0 | 149 | 107 | 149 | 107 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 8.48 | Unknown | Unknown | Unknown | Unknown | 8.48 | Unknown | 186.52 | 8.48 | 178.04 | Yes | N/A | N/A | 2024-08-28 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-28 | 22 | 16 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-08-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-04 | 8 | 6 | 2024-09-04 | 2024-09-04 | 1 | 1 | 1 | 1 | 31 | 23 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-27 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 1017.96 | 258.94 | Unknown | Unknown | Unknown | 759.02 | Unknown | 1750.77 | 1017.96 | 732.81 | Yes | N/A | N/A | 2025-03-26 | 2025-03-27 | 2 | 2 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-12 | 32 | 22 | 2025-05-12 | 2025-05-12 | 1 | 1 | 18 | 14 | 34 | 24 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -8.27 | -5.98 | Unknown | Unknown | Unknown | -2.29 | Unknown | 479.76 | -8.27 | 488.03 | Yes | N/A | N/A | 2023-05-11 | 2023-05-11 | 1 | 1 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-07-17 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-10-12 | 88 | 64 | 2023-10-12 | 2023-10-12 | 1 | 1 | 69 | 49 | 89 | 65 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2025-01-03 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 378.94 | -7.62 | Unknown | Unknown | Unknown | 386.56 | 3981 | 2109.03 | 378.94 | 1730.09 | Yes | N/A | N/A | 2024-10-30 | 2024-12-23 | 55 | 39 | 2024-12-23 | 2025-01-03 | 12 | 10 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-05-01 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-23 | 23 | 17 | 2025-05-23 | 2025-05-23 | 1 | 1 | 174 | 124 | 36 | 28 | 210 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 80.15 | 80.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 25.16 | -20.55 | Unknown | Unknown | Unknown | 45.71 | 3981 | 1338.3 | 25.16 | 1313.14 | Yes | N/A | N/A | 2024-01-11 | 2024-01-12 | 2 | 2 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-09 | 2024-07-09 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-15 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 1051.36 | 251.36 | Unknown | 56.74 | Unknown | 743.26 | Unknown | 1706.86 | 1051.36 | 655.5 | Yes | N/A | N/A | 2024-11-11 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-11-15 | 17 | 13 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-02-27 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-02-27 | 1 | 1 | 105 | 75 | 19 | 15 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 264.1 | 264.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-04 | -148 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-10-17 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 0.72 | -9.5 | Unknown | Unknown | Unknown | 10.22 | 3981 | 867.88 | 0.72 | 867.16 | Yes | N/A | N/A | 2023-09-26 | 2023-10-11 | 16 | 12 | 2023-10-11 | 2023-10-17 | 7 | 5 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-12-05 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-08 | 4 | 4 | 2023-12-08 | 2023-12-08 | 1 | 1 | 66 | 48 | 12 | 10 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 141.05 | 141.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -437 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 1915.14 | 325.46 | Unknown | 9.77 | 42.99 | 1536.92 | 3961 | 1084.26 | 1915.14 | -830.88 | Yes | N/A | N/A | 2024-01-09 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-01-23 | 86 | 62 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-07-29 | 189 | 135 | Unknown | 2024-07-17 | Unknown | Unknown | 2024-07-29 | 2024-09-28 | 62 | 45 | 2024-09-28 | 2024-08-06 | Unknown | Unknown | 189 | 135 | 148 | 107 | 337 | 242 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EN 1147-D3 | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 674 | 483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 9416.47 | Unknown | Unknown | Unknown | Unknown | 9416.47 | 9749 | Not available | 9416.47 | Unknown | Yes | N/A | N/A | 2024-04-09 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2024-04-17 | 328 | 234 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-08-26 | 2024-09-05 | 11 | 9 | 2024-09-05 | 2024-09-05 | 1 | 1 | 0 | 0 | 340 | 244 | 340 | 244 | Steps 2,3,5,6,7 | 71 | 51 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-12 | 1310 | 937 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2024-05-07 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 563061.97 | 216624.55 | Unknown | 81.39 | 1929.59 | 344426.44 | 496435 | 270780.47 | 563061.97 | -292281.5 | Yes | N/A | N/A | 2022-09-15 | 2023-03-27 | 194 | 138 | 2023-03-27 | 2023-08-24 | 151 | 109 | 2023-04-06 | 2023-08-08 | 58 | 42 | 2023-05-09 | 2023-09-25 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2024-05-06 | 244 | 174 | 2024-05-07 | 2024-06-14 | 39 | 29 | 2024-06-14 | 2024-06-14 | 1 | 1 | 252 | 180 | 470 | 338 | 722 | 518 | Steps 2,3,5,6,7 | 231 | 165 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | -8.45 | -6.86 | Unknown | Unknown | Unknown | -1.59 | Unknown | 158.37 | -8.45 | 166.82 | Yes | N/A | N/A | 2024-04-02 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-02 | 50 | 36 | 2024-04-02 | 2024-05-15 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-24 | 32 | 24 | 2024-05-24 | 2024-05-24 | 1 | 1 | 66 | 48 | 83 | 61 | 149 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-22 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 282.49 | -5 | Unknown | Unknown | Unknown | 287.49 | 3981 | 1401.88 | 282.49 | 1119.39 | Yes | N/A | N/A | 2024-07-05 | 2024-07-16 | 12 | 8 | 2024-07-16 | 2024-07-22 | 7 | 5 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-29 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-23 | 26 | 18 | 2024-09-23 | 2024-09-16 | Unknown | Unknown | 51 | 37 | 33 | 23 | 84 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-12 | 622 | 445 | No | 2023-04-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-05-02 | 2024-12-10 | IOU Designed & Installed | N/A | Yes | 585 | 4470.8 | 824.31 | Unknown | 97.67 | 11.19 | 3537.63 | 3981 | 45124.7 | 4470.8 | 40653.9 | Yes | N/A | N/A | 2023-04-13 | 2024-11-18 | 586 | 418 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2024-12-10 | 589 | 421 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-06-25 | 198 | 142 | 2025-06-25 | 2025-06-25 | 1 | 1 | 1175 | 839 | 199 | 143 | 1374 | 982 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -462 | -331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -31.32 | -15.66 | Unknown | Unknown | Unknown | -15.66 | Unknown | 363.72 | -31.32 | 395.04 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-01-13 | 1011 | 723 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-01 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 14184.81 | 3358.63 | Unknown | 117.58 | Unknown | 10708.6 | Unknown | 1634.55 | 14184.81 | -12550.26 | Yes | N/A | N/A | 2023-09-01 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-08-11 | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-10 | 2023-10-24 | 15 | 11 | 2023-10-24 | 2023-10-21 | Unknown | Unknown | 0 | 0 | 36 | 26 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 692.05 | 692.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | -88 | -65 | No | 2023-11-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-14 | 2024-04-10 | IOU Designed & Installed | N/A | Yes | 35 | 515.07 | -20.12 | Unknown | Unknown | Unknown | 535.19 | 3991 | 820.54 | 515.07 | 305.47 | Yes | N/A | N/A | 2023-11-07 | 2023-12-12 | 36 | 26 | 2023-12-12 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-04-10 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-24 | 15 | 11 | 2024-04-24 | 2024-06-03 | 41 | 29 | 185 | 133 | 56 | 40 | 241 | 173 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | CHULA VISTA, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-31 | 996 | 713 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 153904.02 | 16618.15 | Unknown | Unknown | -50913.51 | 188199.38 | 0 | 42055.76 | 153904.02 | -111848.26 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | 2024-08-01 | 498 | 356 | 2024-04-29 | 2025-04-18 | 22 | 18 | 2024-06-27 | 2025-04-04 | -267 | -194 | 2024-08-30 | Unknown | Unknown | Unknown | 2024-08-30 | 2025-05-01 | 245 | 175 | 2025-08-27 | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-23 | 1 | 1 | 23 | 19 | 477 | 338 | 500 | 357 | Steps 2,3,5,6,7 | 606 | 434 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | -8.63 | -6.52 | Unknown | Unknown | Unknown | -2.11 | Unknown | 158.51 | -8.63 | 167.14 | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-11-28 | 43 | 31 | 2023-11-28 | 2023-11-28 | 1 | 1 | 20 | 14 | 45 | 33 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Valley Center | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-23 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 18991.03 | 3224.65 | Unknown | 658.68 | -9083.66 | 24191.36 | 6710.74 | 16217.18 | 18991.03 | -2773.85 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | 2023-07-31 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-25 | 16 | 12 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-12-12 | 50 | 36 | 2023-12-12 | 2023-12-12 | 1 | 1 | 1 | 1 | 157 | 113 | 158 | 114 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 2017.69 | -49.29 | Unknown | Unknown | -1587 | 3653.98 | Unknown | 1586.88 | 2017.69 | -430.81 | Yes | N/A | N/A | 2024-02-02 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-18 | 14 | 10 | 2024-03-18 | 2024-03-18 | 1 | 1 | 0 | 0 | 22 | 16 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -372 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3946.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-07-09 | 5 | 3 | 2024-07-09 | 2024-08-09 | 32 | 24 | 2024-08-09 | 2024-08-19 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | 2025-04-25 | 2025-04-24 | Unknown | Unknown | 16 | 10 | 32 | 24 | 48 | 34 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DESCANSO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | 195 | 140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 6999.74 | 2476.56 | Unknown | Unknown | -872 | 5395.18 | 3941 | 2542.01 | 6999.74 | -4457.73 | Yes | N/A | N/A | 2024-01-02 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2024-01-02 | 55 | 39 | 2024-01-02 | 2024-01-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-07-09 | 155 | 111 | Unknown | 2024-05-02 | Unknown | Unknown | 2024-07-09 | 2024-07-12 | 4 | 4 | 2024-07-12 | 2024-08-01 | 21 | 15 | 163 | 117 | 80 | 58 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-22 | 2023-04-29 | 2023-06-27 | IOU Designed & Installed | N/A | No | N/A | -51.96 | 252.1 | Unknown | 41.6 | -784 | 438.34 | Unknown | 783.58 | -51.96 | 835.54 | Yes | N/A | N/A | 2023-04-22 | 2023-04-29 | 8 | 5 | 2023-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-06-27 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-06-28 | 2 | 2 | 2023-06-28 | 2023-06-28 | 1 | 1 | 63 | 44 | 3 | 3 | 66 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 601 | 430 | No | 2023-07-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | 2024-11-22 | IOU Designed & Installed | N/A | Yes | 410 | 3876.46 | 2207.19 | Unknown | 1070.47 | -468 | 1066.8 | 3941 | 1243.28 | 3876.46 | -2633.18 | Yes | N/A | N/A | 2023-07-13 | 2024-08-26 | 411 | 293 | 2024-08-26 | 2025-03-06 | 193 | 139 | 2025-03-06 | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-11-22 | 253 | 181 | Unknown | 2024-11-07 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1 | 1 | 2024-11-22 | 2024-11-22 | 1 | 1 | 664 | 474 | 195 | 141 | 859 | 615 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-24 | -128 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 231.09 | -5.87 | Unknown | Unknown | Unknown | 236.96 | Unknown | 529.38 | 231.09 | 298.29 | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | 2023-05-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | 450 | 323 | No | 2023-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-09-22 | 2025-04-22 | IOU Designed & Installed | N/A | Yes | 639 | 18786.33 | 125.99 | Unknown | Unknown | -1561.75 | 20222.09 | Unknown | 1296.02 | 18786.33 | -17490.31 | Yes | N/A | N/A | 2023-02-15 | 2024-11-15 | 640 | 458 | 2024-11-15 | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2025-01-21 | 488 | 348 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2025-04-22 | 579 | 413 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-04-22 | 2025-05-05 | 14 | 10 | 2025-05-05 | 2025-04-24 | Unknown | Unknown | 1707 | 1219 | 14 | 10 | 1721 | 1229 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 49.05 | 49.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -13.91 | -10.94 | Unknown | Unknown | Unknown | -2.97 | 3981 | 98.41 | -13.91 | 112.32 | Yes | N/A | N/A | 2022-12-07 | 2023-03-22 | 106 | 76 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 106 | 76 | 1 | 1 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -586 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-12 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 1187.69 | 370.02 | Unknown | 6.83 | Unknown | 810.84 | 3981 | 1153.46 | 1187.69 | -34.23 | Yes | N/A | N/A | 2024-02-08 | 2024-03-07 | 29 | 21 | 2024-03-07 | 2024-03-18 | 12 | 8 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-04-15 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-06 | 22 | 16 | 2024-05-06 | 2024-05-06 | 1 | 1 | 58 | 42 | 35 | 25 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | 149 | 107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1175.17 | Unknown | Unknown | Unknown | 16.92 | 1158.25 | 3981 | 725.85 | 1175.17 | -449.32 | Yes | N/A | N/A | 2023-10-24 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-10-30 | 53 | 37 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 0 | 0 | 54 | 38 | 54 | 38 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-16 | -493 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-19 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 3.93 | -4.96 | Unknown | Unknown | Unknown | 8.89 | 3941 | 671.11 | 3.93 | 667.18 | Yes | N/A | N/A | 2023-10-06 | 2023-07-03 | Unknown | Unknown | 2023-07-03 | 2023-10-19 | 109 | 79 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-12-18 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-04 | 18 | 14 | 2024-01-04 | 2024-02-09 | 37 | 27 | 61 | 43 | 164 | 120 | 225 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 515 | 368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1358.74 | Unknown | Unknown | Unknown | 29.49 | 1329.25 | 0 | 595.57 | 1358.74 | -763.17 | Yes | N/A | N/A | 2023-04-27 | 2023-07-05 | 70 | 50 | 2023-07-05 | 2023-07-13 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-06-01 | 15 | 11 | 2023-07-13 | 2024-10-11 | 457 | 327 | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-12 | Unknown | Unknown | 527 | 377 | 24 | 18 | 551 | 395 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 3623.11 | 845.76 | Unknown | Unknown | Unknown | 2777.35 | Unknown | 1224.04 | 3623.11 | -2399.07 | Yes | N/A | N/A | 2025-04-24 | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-04-24 | 28 | 20 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-05-30 | 2 | 2 | 2025-05-30 | 2025-05-30 | 1 | 1 | 36 | 26 | 31 | 23 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-31 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 2921.45 | 763.86 | Unknown | Unknown | 5.96 | 2151.63 | Unknown | 1916.41 | 2921.45 | -1005.04 | Yes | N/A | N/A | 2024-05-06 | 2024-05-31 | 26 | 20 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-09-17 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-11-01 | 46 | 34 | 2024-11-01 | 2024-11-01 | 1 | 1 | 136 | 98 | 48 | 36 | 184 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 253.06 | -5.22 | Unknown | Unknown | Unknown | 258.28 | 3981 | 1989.05 | 253.06 | 1735.99 | Yes | N/A | N/A | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-10 | 31 | 23 | 2025-03-10 | 2025-05-09 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-22 | 14 | 10 | 2025-05-22 | 2025-05-22 | 1 | 1 | 62 | 46 | 47 | 35 | 109 | 81 | Steps 2,3,5,6,7 | 31 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 4424.2 | 4424.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-01-18 | -319 | -228 | No | 2024-03-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-06-21 | 2025-02-19 | IOU Designed & Installed | N/A | Yes | 139 | 4067.63 | -31.93 | Unknown | Unknown | 30.87 | 4068.69 | 3961 | 1331.86 | 4067.63 | -2735.77 | Yes | N/A | N/A | 2024-03-12 | 2024-06-04 | 85 | 61 | 2024-06-04 | 2024-07-29 | 56 | 40 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2025-02-19 | 244 | 174 | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-19 | 2025-03-05 | 15 | 11 | 2025-03-05 | 2025-03-05 | 1 | 1 | 329 | 235 | 72 | 52 | 401 | 287 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | -493 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-07-18 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 38.32 | Unknown | Unknown | Unknown | Unknown | 38.32 | 7962 | 1497.75 | 38.32 | 1459.43 | Yes | N/A | N/A | 2024-06-28 | 2024-07-18 | 21 | 15 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-09-30 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-10 | 11 | 9 | 2024-10-10 | 2024-10-09 | Unknown | Unknown | 96 | 68 | 12 | 10 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-27 | 141 | 102 | No | 2023-08-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-14 | 2023-11-16 | IOU Designed & Installed | N/A | Yes | 4 | 1.16 | -15.82 | Unknown | Unknown | Unknown | 16.98 | 3981 | 774.52 | 1.16 | 773.36 | Yes | N/A | N/A | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2023-08-15 | 6 | 4 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-11-16 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-18 | 33 | 23 | 2023-12-18 | 2023-12-15 | Unknown | Unknown | 95 | 69 | 39 | 27 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | -129 | -93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 10603.56 | Unknown | Unknown | Unknown | -1370.21 | 11973.77 | Unknown | 1461.16 | 10603.56 | -9142.4 | Yes | N/A | N/A | 2023-09-12 | 2023-09-22 | 11 | 9 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-10-31 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-02-21 | 114 | 82 | 2024-02-21 | 2024-02-21 | 1 | 1 | 16 | 12 | 115 | 83 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | Unknown | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | -9.2 | -7.47 | Unknown | Unknown | Unknown | -1.73 | 3885 | 891.87 | -9.2 | 901.07 | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-05-21 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-04 | 15 | 11 | 2024-06-04 | 2024-06-04 | 1 | 1 | 57 | 41 | 17 | 13 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-02-18 | -1065 | -762 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 3144.17 | 719.02 | Unknown | Unknown | Unknown | 2425.15 | 3981 | 230.15 | 3144.17 | -2914.02 | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-03-06 | 8 | 6 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-20 | 2 | 2 | 2025-03-20 | 2025-03-20 | 1 | 1 | 15 | 11 | 11 | 9 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-28 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 591.05 | -11.71 | Unknown | Unknown | 113.39 | 489.37 | 3981 | 1544.56 | 591.05 | 953.51 | Yes | N/A | N/A | 2023-12-05 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-12-20 | 134 | 96 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-06-03 | 167 | 119 | Unknown | 2024-05-29 | Unknown | Unknown | 2024-06-03 | 2025-06-30 | 393 | 281 | 2025-06-30 | 2025-06-30 | 1 | 1 | 167 | 119 | 528 | 378 | 695 | 497 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 719 | 514 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11657.73 | -6.46 | Unknown | Unknown | 140 | 11524.19 | 16935 | 3837.66 | 11657.73 | -7820.07 | Yes | N/A | N/A | 2023-01-25 | 2023-02-23 | 30 | 22 | 2023-02-23 | 2024-03-19 | 391 | 279 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-10 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-20 | Unknown | Unknown | 30 | 22 | 410 | 292 | 440 | 314 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 737 | 528 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2023-12-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 83262.82 | 20797.3 | Unknown | Unknown | 370.94 | 62094.58 | 223933 | 77429.83 | 83262.82 | -5832.99 | Yes | N/A | N/A | 2022-09-01 | 2023-02-10 | 163 | 117 | 2023-02-10 | 2023-05-16 | 96 | 68 | 2023-02-28 | 2023-07-21 | 25 | 19 | 2023-04-10 | 2023-06-28 | 52 | 38 | 2023-06-13 | Unknown | Unknown | Unknown | 2023-06-13 | 2023-12-21 | 192 | 138 | 2023-12-29 | 2024-02-08 | 42 | 30 | 2024-02-08 | 2024-02-08 | 1 | 1 | 188 | 136 | 383 | 275 | 571 | 411 | Steps 2,3,5,6,7 | 194 | 140 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 66528.62 | 11841.69 | Unknown | 30.08 | -5120 | 59776.85 | 4172862 | 39487.73 | 66528.62 | -27040.89 | Yes | N/A | N/A | 2023-12-12 | 2024-02-08 | 59 | 43 | 2024-02-08 | 2024-05-13 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-07-24 | 73 | 53 | Unknown | 2024-05-24 | Unknown | Unknown | 2024-07-30 | 2024-08-12 | 14 | 10 | 2024-08-12 | 2024-08-08 | Unknown | Unknown | 132 | 96 | 110 | 78 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 487 | 348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 576.24 | -24.57 | Unknown | Unknown | -647 | 1247.81 | Unknown | 544.92 | 576.24 | -31.32 | Yes | N/A | N/A | 2023-05-01 | 2024-01-09 | 254 | 182 | 2024-01-09 | 2024-03-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-01 | Unknown | Unknown | 254 | 182 | 71 | 51 | 325 | 233 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 3656 | 3656 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-07 | 228 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2024-08-30 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 10659.83 | Unknown | Unknown | Unknown | Unknown | 10659.83 | 43791 | 4780.72 | 10659.83 | -5879.11 | Yes | N/A | N/A | 2023-07-17 | 2024-08-30 | 411 | 295 | 2024-08-30 | 2024-09-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2025-01-08 | 104 | 74 | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-14 | 2025-01-29 | 16 | 12 | 2025-01-29 | 2025-01-21 | Unknown | Unknown | 515 | 369 | 45 | 33 | 560 | 402 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 61.59 | -24.15 | Unknown | Unknown | -1550.65 | 1636.39 | Unknown | 1552.21 | 61.59 | 1490.62 | Yes | N/A | N/A | 2025-01-07 | 2025-01-24 | 18 | 14 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-03-06 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-06 | 1 | 1 | 60 | 44 | 2 | 2 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -207 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | 2023-05-24 | IOU Designed & Installed | N/A | No | N/A | 244.71 | -10.09 | Unknown | Unknown | Unknown | 254.8 | 3981 | 607.69 | 244.71 | 362.98 | Yes | N/A | N/A | 2023-02-10 | 2023-02-10 | 1 | 1 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-05-24 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-06-12 | 20 | 14 | 2023-06-12 | 2023-06-12 | 1 | 1 | 105 | 75 | 21 | 15 | 126 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | -239 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-05-15 | IOU Designed & Installed | N/A | No | N/A | 3274.56 | Unknown | Unknown | Unknown | 46.84 | 3227.72 | 3981 | 967.23 | 3274.56 | -2307.33 | Yes | N/A | N/A | 2023-03-15 | 2023-03-16 | 2 | 2 | 2023-03-16 | 2023-04-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-08-04 | 82 | 60 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2 | 2 | 105 | 77 | 107 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 803 | 803 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | 121 | 86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2187.43 | -41.23 | Unknown | Unknown | 35.59 | 2193.07 | 7962 | 1803.83 | 2187.43 | -383.6 | Yes | N/A | N/A | 2024-07-23 | 2024-10-28 | 98 | 70 | 2024-10-28 | 2024-11-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-04-16 | 143 | 103 | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-05 | 19 | 13 | 241 | 173 | 48 | 34 | 289 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | -3 | -4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 411.65 | -27.52 | Unknown | Unknown | Unknown | 439.17 | 11943 | 413.87 | 411.65 | 2.22 | Yes | N/A | N/A | 2023-09-19 | 2023-09-28 | 10 | 8 | 2023-09-28 | 2023-10-10 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-09-30 | 10 | 7 | 2023-10-10 | 2024-05-21 | 225 | 161 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-03 | Unknown | Unknown | 235 | 169 | 23 | 16 | 258 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-14 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 1286.34 | Unknown | Unknown | Unknown | 20.84 | 1265.5 | 3981 | 1311.67 | 1286.34 | 25.33 | Yes | N/A | N/A | 2024-07-23 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-08-19 | 39 | 27 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-11-04 | 78 | 56 | Unknown | 2024-10-30 | Unknown | Unknown | 2024-11-04 | 2025-02-07 | 96 | 70 | 2025-02-07 | 2025-02-07 | 1 | 1 | 78 | 56 | 136 | 98 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-18 | -136 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | 217.55 | -15.92 | Unknown | Unknown | 8.01 | 225.46 | 3885 | 723.61 | 217.55 | 506.06 | Yes | N/A | N/A | 2023-06-20 | 2023-07-06 | 17 | 13 | 2023-07-06 | 2023-07-13 | 8 | 6 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-09-13 | 63 | 45 | Unknown | 2023-11-03 | Unknown | Unknown | 2023-09-13 | 2023-11-03 | 52 | 38 | 2023-11-03 | 2023-11-03 | 1 | 1 | 80 | 58 | 61 | 45 | 141 | 103 | Steps 2,3,5,6,7 | 51 | 37 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 56.68 | -10.12 | Unknown | Unknown | Unknown | 66.8 | 3981 | 1236.71 | 56.68 | 1180.03 | Yes | N/A | N/A | 2024-03-20 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-03-20 | 101 | 73 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-03 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-05-07 | 35 | 25 | 2024-05-07 | 2024-05-07 | 1 | 1 | 15 | 11 | 137 | 99 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 315 | 226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 56884.03 | 20174.74 | Unknown | 1325.28 | 391.52 | 34992.49 | 0 | 52603.88 | 56884.03 | -4280.15 | Yes | N/A | N/A | 2023-08-15 | 2023-08-17 | 3 | 3 | 2023-08-17 | 2023-11-15 | 91 | 65 | 2023-08-24 | 2023-09-01 | 9 | 7 | 2023-11-15 | 2023-11-29 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-25 | 1 | 1 | 12 | 10 | 107 | 77 | 119 | 87 | Steps 2,3,5,6,7 | 83 | 59 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-18 | -372 | -267 | No | 2023-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-11 | 2023-06-16 | IOU Designed & Installed | N/A | Yes | 132 | 253.53 | -9.23 | Unknown | Unknown | Unknown | 262.76 | 3241 | 777.78 | 253.53 | 524.25 | Yes | N/A | N/A | 2023-04-07 | 2023-08-17 | 133 | 95 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-06-16 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-09-12 | 89 | 63 | 2023-09-12 | 2023-09-12 | 1 | 1 | 200 | 144 | 90 | 64 | 290 | 208 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 529 | 378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 594.72 | -11.96 | Unknown | Unknown | Unknown | 606.68 | 18178 | 2126.1 | 594.72 | 1531.38 | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-03-04 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-13 | 1 | 1 | 1 | 1 | 24 | 18 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 80 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 602.65 | -31.37 | Unknown | Unknown | Unknown | 634.02 | Unknown | 432 | 602.65 | -170.65 | Yes | N/A | N/A | 2023-02-14 | 2023-02-17 | 4 | 4 | 2023-02-17 | 2023-05-12 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | 2023-04-27 | 42 | 30 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | 4 | 4 | 128 | 92 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -611 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 18.16 | Unknown | Unknown | Unknown | Unknown | 18.16 | Unknown | 105.72 | 18.16 | 87.56 | Yes | N/A | N/A | 2024-11-26 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2025-01-03 | 52 | 38 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-02-24 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-06 | 11 | 9 | 2025-03-06 | 2025-03-06 | 1 | 1 | 53 | 37 | 64 | 48 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-25 | 103 | 74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-03-10 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 2123.13 | 733.6 | Unknown | Unknown | 5.8 | 1383.73 | 0 | 690.14 | 2123.13 | -1432.99 | Yes | N/A | N/A | 2023-01-10 | 2023-03-10 | 60 | 44 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-02-01 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-05 | 5 | 3 | 2024-02-05 | 2024-02-05 | 1 | 1 | 70 | 52 | 6 | 4 | 76 | 56 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | -124 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 6140.7 | 1912.85 | Unknown | 486.8 | 13.51 | 3727.54 | 3981 | 2810.47 | 6140.7 | -3330.23 | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-18 | 38 | 28 | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-18 | 2023-11-22 | 36 | 26 | 2023-11-22 | 2023-11-29 | 8 | 6 | 39 | 29 | 45 | 33 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -555 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-05-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -528.46 | -12.26 | Unknown | Unknown | -773 | 256.8 | Unknown | 772.83 | -528.46 | 1301.29 | Yes | N/A | N/A | 2023-04-24 | 2023-05-11 | 18 | 14 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1 | 1 | 18 | 14 | 1 | 1 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | N/A | Carlsbad | CARLSBAD | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | 2023-06-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 12142.19 | 80.6 | Unknown | 36.1 | -5175 | 17200.49 | Unknown | 8586.21 | 12142.19 | -3555.98 | Yes | N/A | N/A | 2022-06-23 | 2023-04-10 | 292 | 208 | 2023-04-10 | 2023-06-13 | 65 | 47 | 2023-04-19 | 2023-05-25 | 20 | 12 | 2023-05-01 | 2023-06-13 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-07-03 | 19 | 13 | 2023-07-03 | 2023-07-03 | 1 | 1 | 312 | 220 | 118 | 84 | 430 | 304 | Steps 2,3,5,6,7 | 79 | 57 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | -600 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 688.47 | -20.9 | Unknown | Unknown | Unknown | 709.37 | Unknown | 2050.27 | 688.47 | 1361.8 | Yes | N/A | N/A | 2024-04-05 | 2024-04-10 | 6 | 4 | 2024-04-10 | 2024-04-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-04-25 | 1 | 1 | 6 | 4 | 7 | 5 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-27 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 879.15 | 465.88 | Unknown | 124.12 | Unknown | 289.15 | 3961 | 153.87 | 879.15 | -725.28 | Yes | N/A | N/A | 2023-06-07 | 2023-07-22 | 46 | 33 | 2023-07-22 | 2023-07-22 | 1 | 0 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | 2023-07-26 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-02 | 8 | 6 | 2023-08-02 | 2023-08-02 | 1 | 1 | 51 | 36 | 10 | 7 | 61 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 19.73 | Unknown | Unknown | Unknown | Unknown | 19.73 | 2842 | 639.15 | 19.73 | 619.42 | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-07-03 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-09-16 | 76 | 54 | Unknown | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-09-30 | 8 | 6 | 2024-09-30 | 2024-09-30 | 1 | 1 | 77 | 55 | 26 | 20 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -103 | -74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-18 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | -8034.57 | Unknown | Unknown | Unknown | -8090 | 55.43 | Unknown | 7448.48 | -8034.57 | 15483.05 | Yes | N/A | N/A | 2024-09-10 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-12-09 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-12-06 | 36 | 26 | 2024-12-09 | 2025-03-11 | 93 | 67 | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-20 | 14 | 10 | 2025-03-20 | 2025-03-20 | 1 | 1 | 93 | 67 | 147 | 105 | 240 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 19.57 | -15.37 | Unknown | Unknown | Unknown | 34.94 | Unknown | 961.15 | 19.57 | 941.58 | Yes | N/A | N/A | 2024-05-15 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-15 | 50 | 36 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-06-06 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-16 | 41 | 29 | 2024-07-16 | 2024-07-16 | 1 | 1 | 23 | 17 | 92 | 66 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-15 | 213 | 154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 914.52 | Unknown | Unknown | Unknown | -275 | 1189.52 | Unknown | 275 | 914.52 | -639.52 | Yes | N/A | N/A | 2023-11-15 | 2023-11-22 | 8 | 6 | 2023-11-22 | 2023-11-22 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-14 | 16 | 12 | 2023-12-14 | 2023-12-14 | 1 | 1 | 8 | 6 | 18 | 14 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -526 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-11-30 | IOU Designed & Installed | N/A | No | N/A | 7471.24 | 1472.48 | Unknown | 864.05 | 28.48 | 5106.23 | 3981 | 1122.44 | 7471.24 | -6348.8 | Yes | N/A | N/A | 2024-06-26 | 2024-08-15 | 51 | 37 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-11-30 | 108 | 77 | Unknown | 2024-10-15 | Unknown | Unknown | 2024-11-30 | 2024-12-03 | 4 | 2 | 2024-12-03 | 2024-12-03 | 1 | 1 | 159 | 114 | 6 | 4 | 165 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | 21 | 16 | No | 2023-08-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-17 | 2025-02-17 | IOU Designed & Installed | N/A | Yes | 173 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 4215.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2024-01-24 | 199 | 143 | 2024-01-24 | 2024-01-31 | 8 | 6 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2025-02-17 | 582 | 416 | Unknown | 2024-11-18 | Unknown | Unknown | 2025-02-17 | 2025-04-07 | 50 | 36 | 2025-04-07 | 2025-04-07 | 1 | 1 | 781 | 559 | 59 | 43 | 840 | 602 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 172 | 172 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | -292 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-29 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 1295.25 | Unknown | Unknown | Unknown | 21.96 | 1273.29 | 3981 | 1109.05 | 1295.25 | -186.2 | Yes | N/A | N/A | 2024-05-23 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-14 | 54 | 40 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2025-06-10 | 362 | 258 | Unknown | 2025-06-05 | Unknown | Unknown | 2025-06-10 | 2025-06-16 | 7 | 5 | 2025-06-16 | 2025-06-16 | 1 | 1 | 362 | 258 | 62 | 46 | 424 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | -211 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | -4.6 | -3.74 | Unknown | Unknown | Unknown | -0.86 | Unknown | 515.81 | -4.6 | 520.41 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-03-14 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-27 | 14 | 10 | 2024-03-27 | 2024-03-27 | 1 | 1 | 89 | 65 | 16 | 12 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4807.05 | 4807.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-04-20 | 96 | 69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-01-19 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 1786.91 | -20.14 | Unknown | Unknown | 198.6 | 1608.45 | 3981 | 729.15 | 1786.91 | -1057.76 | Yes | N/A | N/A | 2023-01-19 | 2023-02-24 | 37 | 27 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2024-04-24 | 426 | 304 | Unknown | 2023-06-22 | Unknown | Unknown | 2024-04-24 | 2025-08-15 | 479 | 343 | 2025-08-15 | 2023-07-25 | Unknown | Unknown | 463 | 331 | 479 | 343 | 942 | 674 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | -408 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-05-04 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | -6.1 | -11.96 | Unknown | Unknown | Unknown | 5.86 | Unknown | 986.15 | -6.1 | 992.25 | Yes | N/A | N/A | 2023-01-23 | 2023-05-04 | 102 | 74 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-09-07 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-12 | 6 | 4 | 2023-09-12 | 2023-09-12 | 1 | 1 | 229 | 165 | 7 | 5 | 236 | 170 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -614 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-10 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 6.8 | -6.04 | Unknown | Unknown | Unknown | 12.84 | Unknown | 953.95 | 6.8 | 947.15 | Yes | N/A | N/A | 2023-12-26 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-10 | 64 | 46 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-02-26 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-15 | 19 | 15 | 2024-03-15 | 2024-03-04 | Unknown | Unknown | 48 | 34 | 83 | 61 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3121.03 | 894.52 | Unknown | 339.24 | Unknown | 1887.27 | 3981 | 847.65 | 3121.03 | -2273.38 | Yes | N/A | N/A | 2024-02-05 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-05 | 4 | 2 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-04-02 | 1 | 1 | 0 | 0 | 5 | 3 | 5 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -603 | -431 | No | 2024-02-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-03-02 | 2024-04-22 | IOU Designed & Installed | N/A | Yes | 73 | 1809.2 | -45.91 | Unknown | Unknown | Unknown | 1855.11 | 3981 | 1060.72 | 1809.2 | -748.48 | Yes | N/A | N/A | 2024-02-23 | 2024-05-06 | 74 | 52 | 2024-05-06 | 2024-03-02 | Unknown | Unknown | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-04-22 | 52 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-17 | 26 | 20 | 2024-05-17 | 2024-05-17 | 1 | 1 | 126 | 88 | 27 | 21 | 153 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 1685 | 1685 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-12-31 | 166 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-11 | 2024-02-28 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 34590.74 | 6937.1 | Unknown | Unknown | -4217.95 | 31871.59 | Unknown | 4218.6 | 34590.74 | -30372.14 | Yes | N/A | N/A | 2021-10-11 | 2024-03-01 | 873 | 625 | 2024-03-01 | 2024-05-08 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-05-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-14 | 26 | 20 | 2024-06-14 | 2024-06-14 | 1 | 1 | 873 | 625 | 124 | 90 | 997 | 715 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 7.7 | 7.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-08 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 624 | 385.62 | Unknown | Unknown | Unknown | 238.38 | Unknown | 192.51 | 624 | -431.49 | Yes | N/A | N/A | 2024-07-02 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-07-08 | 76 | 54 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-01-16 | 193 | 139 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-02-12 | 28 | 20 | 2025-02-12 | 2025-02-12 | 1 | 1 | 193 | 139 | 105 | 75 | 298 | 214 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | 219 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1990.95 | Unknown | Unknown | Unknown | Unknown | 1990.95 | 3981 | 574.93 | 1990.95 | -1416.02 | Yes | N/A | N/A | 2023-08-23 | 2024-01-02 | 133 | 95 | 2024-01-02 | 2024-01-02 | 1 | 1 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-09-26 | Unknown | Unknown | 133 | 95 | 1 | 1 | 134 | 96 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -137 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 13847.32 | Unknown | Unknown | Unknown | Unknown | 13847.32 | 386157 | 7294.12 | 13847.32 | -6553.2 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | 2023-03-02 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2024-09-23 | 572 | 408 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-24 | 2024-07-08 | 15 | 11 | 2024-07-08 | 2024-07-01 | Unknown | Unknown | 573 | 409 | 31 | 23 | 604 | 432 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1485 | 1062 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-11-02 | 2024-01-20 | IOU Designed & Installed | N/A | No | N/A | 14618.9 | 4741.34 | Unknown | 749 | Unknown | 9128.56 | Unknown | 717.32 | 14618.9 | -13901.58 | Yes | N/A | N/A | 2023-08-09 | 2023-11-02 | 86 | 62 | 2023-11-02 | 2024-01-19 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | 2024-01-20 | 2024-01-24 | 5 | 3 | 2024-01-24 | 2024-01-24 | 1 | 1 | 86 | 62 | 85 | 61 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | -460 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 216.35 | 89.58 | Unknown | Unknown | Unknown | 126.77 | 3961 | 153.83 | 216.35 | -62.52 | Yes | N/A | N/A | 2023-03-23 | 2023-09-07 | 169 | 121 | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-31 | 51 | 37 | 2023-10-31 | 2023-10-31 | 1 | 1 | 174 | 124 | 53 | 39 | 227 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -373 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 11.31 | Unknown | Unknown | Unknown | Unknown | 11.31 | 3961 | 1005.27 | 11.31 | 993.96 | Yes | N/A | N/A | 2024-07-08 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-07-08 | 14 | 10 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-01-06 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-21 | 16 | 12 | 2025-01-21 | 2025-01-21 | 1 | 1 | 183 | 131 | 31 | 23 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-11 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 803.54 | 119.54 | Unknown | Unknown | Unknown | 684 | 3981 | 1489.43 | 803.54 | 685.89 | Yes | N/A | N/A | 2024-06-25 | 2024-07-10 | 16 | 12 | 2024-07-10 | 2024-07-11 | 2 | 2 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-09-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-10 | 22 | 16 | 2024-10-10 | 2024-10-10 | 1 | 1 | 87 | 63 | 25 | 19 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -479 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -238.47 | -1.26 | Unknown | Unknown | -349 | 111.79 | 1786.6 | 2012.9 | -238.47 | 2251.37 | Yes | N/A | N/A | 2024-09-23 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-12-05 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-12-04 | 57 | 41 | 2024-12-05 | 2025-01-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 43 | 31 | 135 | 97 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -685 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | 1049.66 | -53.18 | Unknown | Unknown | Unknown | 1102.84 | Unknown | 1697.18 | 1049.66 | 647.52 | Yes | N/A | N/A | 2025-03-12 | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-03-12 | 14 | 10 | 2025-03-12 | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-19 | 6 | 4 | 2025-03-12 | 2025-04-03 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-10 | 8 | 6 | 2025-04-10 | 2025-04-10 | 1 | 1 | 23 | 17 | 29 | 21 | 52 | 38 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Juan Capistrano | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | 1240 | 887 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-02-01 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 136913.12 | 23337.4 | Unknown | 68.5 | -6711 | 120218.22 | 1917273 | Not available | 136913.12 | Unknown | Yes | N/A | N/A | 2024-01-10 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-05-23 | 2024-05-24 | 2 | 2 | 2024-05-24 | 2024-05-24 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | Steps 2,3,5,6,7 | 126 | 90 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | -4.46 | -3.23 | Unknown | Unknown | Unknown | -1.23 | Unknown | 495.75 | -4.46 | 500.21 | Yes | N/A | N/A | 2023-04-30 | 2023-04-30 | 1 | 0 | 2023-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-07-18 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-31 | 14 | 10 | 2023-07-31 | 2023-07-31 | 1 | 1 | 80 | 57 | 15 | 11 | 95 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Residential | Underserved Community | VS 1087-H2 | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 566 | 405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2024-01-10 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 10808.03 | 2290.42 | Unknown | Unknown | -7807.12 | 16324.73 | 3416 | 19491.62 | 10808.03 | 8683.59 | Yes | N/A | N/A | 2023-11-30 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2024-04-04 | 155 | 111 | 2024-01-10 | 2024-04-17 | 42 | 29 | 2024-04-09 | 2024-04-10 | 2 | 2 | 2024-04-10 | Unknown | Unknown | Unknown | 2024-04-10 | 2024-10-08 | 182 | 130 | 2024-10-15 | 2025-01-17 | 95 | 69 | 2025-01-17 | 2025-01-17 | 1 | 1 | 42 | 29 | 435 | 313 | 477 | 342 | Steps 2,3,5,6,7 | 93 | 67 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 748.2 | 748.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-26 | -61 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 421.66 | -12.59 | Unknown | Unknown | Unknown | 434.25 | 11943 | 1907.78 | 421.66 | 1486.12 | Yes | N/A | N/A | 2024-04-15 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-04-15 | 11 | 7 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-04-26 | Unknown | Unknown | 0 | 0 | 11 | 7 | 11 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-07 | -353 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-10-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.92 | -13.23 | Unknown | Unknown | Unknown | 28.15 | 0 | 700.08 | 14.92 | 685.16 | Yes | N/A | N/A | 2023-09-28 | 2023-07-05 | Unknown | Unknown | 2023-07-05 | 2023-10-19 | 107 | 77 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-06-19 | 1 | 1 | 0 | 0 | 108 | 78 | 108 | 78 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | 974 | 697 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-05-30 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 455.75 | -9.52 | Unknown | Unknown | 8.01 | 457.26 | 3885 | 401.89 | 455.75 | -53.86 | Yes | N/A | N/A | 2023-03-16 | 2023-05-30 | 76 | 54 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-08-29 | 92 | 66 | Unknown | 2023-08-07 | Unknown | Unknown | 2023-08-29 | 2023-09-05 | 8 | 6 | 2023-09-05 | 2023-09-01 | Unknown | Unknown | 168 | 120 | 8 | 6 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 367 | 367 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | 46 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-24 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 15205.23 | Unknown | Unknown | Unknown | 26.48 | 15178.75 | 708731 | 9627.03 | 15205.23 | -5578.2 | Yes | N/A | N/A | 2024-09-10 | 2024-09-25 | 16 | 12 | 2024-09-25 | 2024-11-19 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-01-16 | 59 | 43 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-02-03 | 2025-02-24 | 22 | 16 | 2025-02-24 | 2025-02-19 | Unknown | Unknown | 75 | 55 | 78 | 56 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | 4 | 5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.94 | -28.94 | Unknown | Unknown | Unknown | 22 | Unknown | 1754.55 | -6.94 | 1761.49 | Yes | N/A | N/A | 2025-03-20 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 85 | 85 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-28 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 125.51 | -7.06 | Unknown | Unknown | Unknown | 132.57 | 3885 | 865.19 | 125.51 | 739.68 | Yes | N/A | N/A | 2023-06-19 | 2023-06-28 | 10 | 8 | 2023-06-28 | 2023-06-28 | 1 | 1 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-26 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-22 | 28 | 20 | 2023-08-22 | 2023-08-22 | 1 | 1 | 39 | 29 | 30 | 22 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -248 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-04-17 | IOU Designed & Installed | N/A | No | N/A | 992.38 | Unknown | Unknown | Unknown | Unknown | 992.38 | Unknown | 33.61 | 992.38 | -958.77 | Yes | N/A | N/A | 2023-03-28 | 2023-03-29 | 2 | 2 | 2023-03-29 | 2023-04-05 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-03-28 | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | 2023-04-17 | 2023-07-10 | 85 | 61 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2 | 2 | 94 | 68 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 54.75 | 54.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -290 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | -940.84 | -11.7 | Unknown | Unknown | -1538 | 608.86 | Unknown | 1426.5 | -940.84 | 2367.34 | Yes | N/A | N/A | 2024-08-07 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-08-09 | 30 | 22 | 2024-08-09 | 2024-08-15 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-13 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-20 | 8 | 6 | 2024-09-20 | 2024-09-24 | 5 | 3 | 43 | 31 | 43 | 31 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-01 | 2022-04-01 | 2025-03-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 86656.34 | 567.92 | Unknown | Unknown | 5807.35 | 80281.07 | 231809.29 | 61842.01 | 86656.34 | -24814.33 | Yes | N/A | N/A | 2022-04-01 | 2023-04-28 | 393 | 281 | 2023-04-28 | 2024-01-16 | 264 | 188 | 2023-05-09 | 2025-06-19 | 82 | 60 | 2024-01-10 | 2024-01-25 | 16 | 12 | 2024-10-31 | Unknown | Unknown | Unknown | 2024-10-31 | 2025-07-02 | 245 | 175 | 2025-03-13 | 2025-05-05 | 54 | 38 | 2025-05-05 | 2025-05-05 | 1 | 1 | 475 | 341 | 580 | 414 | 1055 | 755 | Steps 2,3,5,6,7 | 889 | 635 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -527 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-10 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1631.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-01-10 | 8 | 6 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-04-04 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-05-08 | 35 | 25 | 2025-05-08 | 2025-05-08 | 1 | 1 | 85 | 61 | 44 | 32 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | N/A | 1103 | 1103 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-02 | 94 | 69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | -2203.62 | 630.6 | Unknown | 422.05 | -3724 | 467.73 | Unknown | 3723.56 | -2203.62 | 5927.18 | Yes | N/A | N/A | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-09-11 | 2024-10-04 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | 2024-10-04 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | 516.98 | Unknown | Unknown | Unknown | Unknown | 516.98 | Unknown | 617.61 | 516.98 | 100.63 | Yes | N/A | N/A | 2025-03-13 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | 2025-04-14 | 2025-04-15 | 2 | 2 | 2025-03-31 | 2025-05-30 | 61 | 45 | 2025-03-31 | 2025-06-20 | 82 | 60 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-20 | 2025-06-24 | 5 | 3 | 2025-06-24 | 2025-06-24 | 1 | 1 | 84 | 62 | 67 | 49 | 151 | 111 | Steps 2,3,5,6,7 | 75 | 55 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-11 | 534 | 383 | No | 2021-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-06 | 2021-04-07 | 2023-06-08 | IOU Designed & Installed | N/A | Yes | 748 | 450.11 | 361.24 | Unknown | Unknown | -698 | 786.87 | 3885 | 1351.38 | 450.11 | 901.27 | Yes | N/A | N/A | 2021-04-06 | 2023-04-25 | 750 | 536 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-05-14 | 2023-06-08 | Unknown | Unknown | Unknown | 2023-05-25 | Unknown | Unknown | 2023-06-08 | 2023-06-29 | 22 | 16 | 2023-06-29 | 2023-06-29 | 1 | 1 | 750 | 536 | 23 | 17 | 773 | 553 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-14 | -213 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-26 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | 665.7 | -13.34 | Unknown | Unknown | 26.82 | 652.22 | 3885 | 763.27 | 665.7 | 97.57 | Yes | N/A | N/A | 2023-01-26 | 2023-02-01 | 7 | 5 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-08-23 | 203 | 145 | Unknown | 2023-06-13 | Unknown | Unknown | 2023-08-23 | 2023-09-19 | 28 | 20 | 2023-09-19 | 2023-06-15 | Unknown | Unknown | 210 | 150 | 28 | 20 | 238 | 170 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-02-10 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 535.75 | -10.76 | Unknown | Unknown | Unknown | 546.51 | Unknown | 2035.16 | 535.75 | 1499.41 | Yes | N/A | N/A | 2025-01-02 | 2025-01-09 | 8 | 6 | 2025-01-09 | 2025-02-10 | 33 | 23 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-11 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-23 | 44 | 32 | 2025-04-23 | 2025-04-23 | 1 | 1 | 38 | 28 | 78 | 56 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1525.22 | 2038.15 | Unknown | 510.14 | -1824 | 800.93 | 0 | 1824.15 | 1525.22 | 298.93 | Yes | N/A | N/A | 2023-06-05 | 2023-06-05 | 1 | 1 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -172 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-07-01 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 140457.48 | 21305.88 | Unknown | Unknown | 208.55 | 118943.05 | 0 | 65531.48 | 140457.48 | -74926 | Yes | N/A | N/A | 2024-03-28 | 2024-04-17 | 21 | 15 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-04-15 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-06-11 | 51 | 37 | 2025-06-11 | 2025-06-11 | 1 | 1 | 21 | 15 | 80 | 58 | 101 | 73 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -425 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-26 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 984.06 | 513.68 | Unknown | 33.49 | Unknown | 436.89 | 3981 | 1106.84 | 984.06 | 122.78 | Yes | N/A | N/A | 2024-04-16 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-26 | 58 | 42 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-29 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-12 | 15 | 11 | 2024-06-12 | 2024-06-12 | 1 | 1 | 34 | 24 | 74 | 54 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-22 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 33.81 | Unknown | Unknown | Unknown | Unknown | 33.81 | Unknown | 904.98 | 33.81 | 871.17 | Yes | N/A | N/A | 2024-04-15 | 2024-04-22 | 8 | 6 | 2024-04-22 | 2024-04-22 | 1 | 1 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-07-10 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-08 | 30 | 22 | 2024-08-08 | 2024-08-08 | 1 | 1 | 88 | 64 | 32 | 24 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -527 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-30 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | -209.41 | Unknown | Unknown | Unknown | 30.33 | -239.74 | 3981 | 1262.11 | -209.41 | 1471.52 | Yes | N/A | N/A | 2024-07-12 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-08-16 | 61 | 45 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-11-18 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-23 | 36 | 26 | 2024-12-23 | 2024-12-20 | Unknown | Unknown | 95 | 67 | 97 | 71 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 180.24 | -3.37 | Unknown | Unknown | Unknown | 183.61 | Unknown | 466.88 | 180.24 | 286.64 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-06-19 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-07-31 | 1 | 1 | 3 | 3 | 77 | 55 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 248.05 | 248.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-15 | 660 | 473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1087.26 | -19.32 | Unknown | Unknown | -1109 | 41.06 | 3981 | 1798.94 | -1087.26 | 2886.2 | Yes | N/A | N/A | 2023-07-12 | 2023-07-25 | 14 | 10 | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | 2024-03-06 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-05 | Unknown | Unknown | 240 | 172 | 1 | 1 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-24 | 96 | 70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 1494.65 | 520.62 | Unknown | 18.95 | Unknown | 955.08 | Unknown | 1740.88 | 1494.65 | 246.23 | Yes | N/A | N/A | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | 2024-01-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | 2024-03-26 | 2024-03-29 | 4 | 4 | 2024-03-29 | 2024-03-29 | 1 | 1 | 1 | 1 | 7 | 7 | 8 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | -327 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-19 | 2024-05-19 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 628.16 | 181.27 | Unknown | Unknown | Unknown | 446.89 | 3981 | 1770.67 | 628.16 | 1142.51 | Yes | N/A | N/A | 2024-05-19 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-06-28 | 120 | 86 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-23 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-19 | 28 | 20 | 2024-08-19 | 2024-08-19 | 1 | 1 | 26 | 18 | 149 | 107 | 175 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 76.37 | 3.69 | Unknown | Unknown | 1.18 | 71.5 | 3981 | 999.84 | 76.37 | 923.47 | Yes | N/A | N/A | 2023-12-21 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-21 | 14 | 10 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-06-04 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-25 | 22 | 16 | 2024-06-25 | 2024-06-25 | 1 | 1 | 167 | 119 | 37 | 27 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -612 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-26 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 1488.69 | 413.42 | Unknown | 74.08 | -751 | 1752.19 | Unknown | 751.43 | 1488.69 | -737.26 | Yes | N/A | N/A | 2024-04-26 | 2024-04-19 | Unknown | Unknown | 2024-04-19 | 2024-04-26 | 8 | 6 | 2024-04-26 | 2024-05-29 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-08-12 | 64 | 46 | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-12 | 2024-08-15 | 4 | 4 | 2024-08-15 | 2024-08-15 | 1 | 1 | 98 | 70 | 13 | 11 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2302.87 | Unknown | Unknown | Unknown | 1.83 | 2301.04 | 3981 | 3030.55 | 2302.87 | 727.68 | Yes | N/A | N/A | 2025-01-24 | 2025-02-21 | 29 | 21 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1 | 1 | 29 | 21 | 2 | 2 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 360.38 | -6.64 | Unknown | Unknown | Unknown | 367.02 | 3981 | 253.82 | 360.38 | -106.56 | Yes | N/A | N/A | 2023-01-20 | 2023-02-07 | 19 | 13 | 2023-02-07 | 2023-02-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 19 | 13 | 9 | 7 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -436 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 893.81 | -12.46 | Unknown | Unknown | 12.14 | 894.13 | 3981 | 725.76 | 893.81 | -168.05 | Yes | N/A | N/A | 2023-12-14 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-01-17 | 111 | 79 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-06-28 | 164 | 118 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-06-28 | 2024-07-02 | 5 | 3 | 2024-07-02 | 2024-07-02 | 1 | 1 | 164 | 118 | 117 | 83 | 281 | 201 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 370.05 | -12.03 | Unknown | Unknown | Unknown | 382.08 | Unknown | 897.88 | 370.05 | 527.83 | Yes | N/A | N/A | 2023-06-21 | 2023-06-28 | 8 | 6 | 2023-06-28 | 2023-06-28 | 1 | 1 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 8 | 6 | 2 | 2 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -144 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 29.05 | Unknown | Unknown | Unknown | Unknown | 29.05 | 3885 | 887.73 | 29.05 | 858.68 | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2024-10-21 | 406 | 290 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-13 | 24 | 18 | 2024-11-13 | 2024-11-13 | 1 | 1 | 407 | 291 | 26 | 20 | 433 | 311 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-12 | 67 | 50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-02-14 | IOU Designed & Installed | N/A | No | N/A | 727.87 | 354.06 | Unknown | 132.15 | Unknown | 241.66 | Unknown | 771.19 | 727.87 | 43.32 | Yes | N/A | N/A | 2023-01-24 | 2023-02-08 | 16 | 12 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-02-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | 2023-02-17 | 4 | 4 | 2023-02-17 | 2023-02-17 | 1 | 1 | 23 | 17 | 5 | 5 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 6742.89 | 1783.87 | Unknown | 98.84 | 142.82 | 4717.36 | 3981 | 3735.03 | 6742.89 | -3007.86 | Yes | N/A | N/A | 2024-02-22 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-03-29 | 54 | 40 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2025-05-20 | 418 | 298 | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-20 | 2025-05-21 | 2 | 2 | 2025-05-21 | 2025-05-21 | 1 | 1 | 418 | 298 | 57 | 43 | 475 | 341 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | 253 | 182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-10-03 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 40481.7 | 1056.72 | Unknown | Unknown | -8833 | 48257.98 | 0 | 7700.7 | 40481.7 | -32781 | Yes | N/A | N/A | 2023-09-19 | 2023-10-31 | 43 | 31 | 2023-10-31 | 2024-10-03 | 339 | 243 | 2024-02-08 | 2024-02-09 | 2 | 2 | 2024-06-05 | 2024-10-08 | 43 | 31 | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-24 | 17 | 13 | 2024-11-14 | 2025-05-08 | 176 | 126 | 2025-05-08 | 2025-05-08 | 1 | 1 | 45 | 33 | 576 | 414 | 621 | 447 | Steps 2,3,5,6,7 | 238 | 170 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 533 | 382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 39627.95 | 13000.19 | Unknown | 1591.3 | 2811.43 | 22225.03 | 5373324 | 28479.2 | 39627.95 | -11148.75 | Yes | N/A | N/A | 2022-10-19 | 2023-02-24 | 129 | 93 | 2023-02-24 | 2023-05-05 | 71 | 51 | 2023-03-03 | 2023-03-13 | 11 | 7 | 2023-05-05 | 2023-05-23 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-11-15 | 1 | 1 | 140 | 100 | 91 | 65 | 231 | 165 | Steps 2,3,5,6,7 | 63 | 45 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 403 | 288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1099.94 | Unknown | Unknown | Unknown | -1156 | 56.06 | 3981 | 2266.59 | -1099.94 | 3366.53 | Yes | N/A | N/A | 2023-09-14 | 2024-01-02 | 111 | 79 | 2024-01-02 | 2024-01-03 | 2 | 2 | 2024-01-03 | 2024-01-30 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-07 | Unknown | Unknown | 139 | 99 | 2 | 2 | 141 | 101 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Clemente | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -253 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-30 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 847.78 | 3281.69 | Unknown | Unknown | -4478 | 2044.09 | Unknown | 4478.49 | 847.78 | 3630.71 | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-02-28 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-08 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 1897.85 | Unknown | Unknown | Unknown | -545.19 | 2443.04 | Unknown | 429.96 | 1897.85 | -1467.89 | Yes | N/A | N/A | 2025-05-13 | 2025-05-16 | 4 | 4 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-04 | 17 | 13 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-04 | 1 | 1 | 21 | 17 | 2 | 2 | 23 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 1366.94 | Unknown | Unknown | Unknown | 6.57 | 1360.37 | 3941 | 1112.29 | 1366.94 | -254.65 | Yes | N/A | N/A | 2024-05-22 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-04 | 44 | 32 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-23 | 50 | 36 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-07-23 | 2024-07-30 | 8 | 6 | 2024-07-30 | 2024-07-29 | Unknown | Unknown | 50 | 36 | 52 | 38 | 102 | 74 | Steps 2,3,5,6,7 | 225 | 161 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-06-17 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | -428.66 | -9.41 | Unknown | Unknown | -429 | 9.75 | 3981 | 859.63 | -428.66 | 1288.29 | Yes | N/A | N/A | 2023-05-15 | 2023-06-17 | 34 | 25 | 2023-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-10-24 | 117 | 83 | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-24 | 2023-11-01 | 9 | 7 | 2023-11-01 | 2023-11-01 | 1 | 1 | 151 | 108 | 10 | 8 | 161 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | -292 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-21 | 2023-03-23 | IOU Designed & Installed | N/A | No | N/A | 218.42 | -12.01 | Unknown | Unknown | Unknown | 230.43 | Unknown | 723.35 | 218.42 | 504.93 | Yes | N/A | N/A | 2023-02-16 | 2023-02-21 | 6 | 4 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-03-23 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-04-18 | 27 | 19 | 2023-04-18 | 2023-04-18 | 1 | 1 | 35 | 25 | 28 | 20 | 63 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-13 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 2424.7 | 646.97 | Unknown | 24.11 | 23.57 | 1730.05 | 3981 | 1096.01 | 2424.7 | -1328.69 | Yes | N/A | N/A | 2024-05-31 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-07-08 | 76 | 54 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-10-02 | 87 | 63 | Unknown | 2024-09-26 | Unknown | Unknown | 2024-10-02 | 2024-10-28 | 27 | 19 | 2024-10-28 | 2024-10-28 | 1 | 1 | 87 | 63 | 104 | 74 | 191 | 137 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 728.96 | -11.01 | Unknown | Unknown | 5.86 | 734.11 | Unknown | 729.47 | 728.96 | 0.51 | Yes | N/A | N/A | 2023-12-18 | 2024-01-23 | 37 | 27 | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-26 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-03-15 | 50 | 36 | 2024-03-15 | 2024-03-15 | 1 | 1 | 41 | 31 | 52 | 38 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-04-22 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1918.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-04-01 | 28 | 20 | 2025-04-01 | 2025-04-22 | 22 | 16 | 2025-04-22 | 2025-05-28 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-27 | 3 | 3 | 2025-06-27 | 2025-06-26 | Unknown | Unknown | 94 | 68 | 25 | 19 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1578.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2024-12-27 | 5 | 5 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-02-03 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-19 | 17 | 13 | 2025-02-19 | 2025-02-19 | 1 | 1 | 39 | 27 | 23 | 19 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 515 | 369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 1903.02 | 508.6 | Unknown | 297.65 | 77.43 | 1019.34 | 3981 | 810.69 | 1903.02 | -1092.33 | Yes | N/A | N/A | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2025-01-06 | 454 | 324 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2024-12-17 | 434 | 310 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-13 | 28 | 20 | 2025-01-13 | 2025-02-27 | 46 | 34 | 889 | 635 | 75 | 55 | 964 | 690 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RANCHITA | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -547 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-04-26 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 3757.24 | 1457.58 | Unknown | 352.74 | -461 | 2407.92 | 3981 | 2288.84 | 3757.24 | -1468.4 | Yes | N/A | N/A | 2023-03-14 | 2023-04-26 | 44 | 32 | 2023-04-26 | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-22 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-08-30 | 70 | 50 | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-30 | 2023-09-08 | 10 | 8 | 2023-09-08 | 2023-09-08 | 1 | 1 | 115 | 83 | 11 | 9 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -713 | -510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 128.85 | -1.5 | Unknown | Unknown | Unknown | 130.35 | 3981 | 1647.26 | 128.85 | 1518.41 | Yes | N/A | N/A | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-01-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-13 | 14 | 10 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2 | 2 | 16 | 12 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -394 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-21 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 1153.45 | -11.39 | Unknown | Unknown | 25.45 | 1139.39 | 3981 | 799.52 | 1153.45 | -353.93 | Yes | N/A | N/A | 2023-08-03 | 2023-11-01 | 91 | 65 | 2023-11-01 | 2023-11-08 | 8 | 6 | 2023-11-08 | 2024-01-29 | 42 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-02-09 | 52 | 38 | Unknown | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 36 | 26 | 2024-03-15 | 2024-03-12 | Unknown | Unknown | 185 | 131 | 44 | 32 | 229 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | -46 | -33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2024-04-30 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 47427.95 | 584.82 | Unknown | Unknown | 3285.42 | 43557.71 | 264408 | 33068.06 | 47427.95 | -14359.89 | Yes | N/A | N/A | 2022-11-11 | 2023-04-04 | 145 | 103 | 2023-04-04 | 2023-11-21 | 232 | 166 | 2023-08-08 | 2023-11-20 | 76 | 52 | 2023-10-19 | 2023-11-29 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-04-25 | 99 | 71 | 2024-04-30 | 2024-05-16 | 17 | 13 | 2024-05-16 | 2024-05-16 | 1 | 1 | 221 | 155 | 367 | 265 | 588 | 420 | Steps 2,3,5,6,7 | 137 | 97 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DULZURA | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -260 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2024-01-01 | IOU Designed & Installed | N/A | No | N/A | 3864.87 | 1329.24 | Unknown | Unknown | Unknown | 2535.63 | 3981 | 905.48 | 3864.87 | -2959.39 | Yes | N/A | N/A | 2023-11-10 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-11-15 | 42 | 30 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-01-01 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-01-01 | 2024-01-04 | 4 | 4 | 2024-01-04 | 2024-01-04 | 1 | 1 | 48 | 34 | 47 | 35 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | 374 | 267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1277.45 | Unknown | Unknown | Unknown | 24.51 | 1252.94 | 3981 | 798.48 | 1277.45 | -478.97 | Yes | N/A | N/A | 2023-11-29 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-12-13 | 86 | 62 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 0 | 0 | 87 | 63 | 87 | 63 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -411 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 1402.26 | 244.25 | Unknown | Unknown | Unknown | 1158.01 | 3941 | 1281.24 | 1402.26 | -121.02 | Yes | N/A | N/A | 2024-03-28 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-03-28 | 44 | 32 | 2024-03-28 | 2024-12-10 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-12-11 | 259 | 185 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-17 | 7 | 5 | 2024-12-17 | 2024-12-17 | 1 | 1 | 517 | 369 | 52 | 38 | 569 | 407 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-14 | -390 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 735.57 | -13.44 | Unknown | Unknown | Unknown | 749.01 | 7952 | 1735.88 | 735.57 | 1000.31 | Yes | N/A | N/A | 2024-02-21 | 2024-07-19 | 150 | 108 | 2024-07-19 | 2024-10-17 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-24 | 35 | 25 | 2024-10-17 | 2024-10-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-19 | Unknown | Unknown | 156 | 112 | 126 | 90 | 282 | 202 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 157 | 112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 6594.7 | 28.74 | Unknown | Unknown | 23.82 | 6542.14 | Unknown | 374.98 | 6594.7 | -6219.72 | Yes | N/A | N/A | 2023-06-06 | 2023-07-26 | 51 | 37 | 2023-07-26 | 2023-08-15 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-07-12 | 20 | 14 | 2023-08-15 | 2023-11-02 | 80 | 58 | Unknown | 2023-11-01 | Unknown | Unknown | 2023-11-08 | 2023-11-28 | 21 | 15 | 2023-11-28 | 2023-11-27 | Unknown | Unknown | 131 | 95 | 62 | 44 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -548 | -393 | No | 2023-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-03-14 | 2023-04-16 | IOU Designed & Installed | N/A | Yes | 69 | 2521.66 | 837.06 | Unknown | 310.24 | Unknown | 1374.36 | 3981 | 732.43 | 2521.66 | -1789.23 | Yes | N/A | N/A | 2023-02-16 | 2023-04-26 | 70 | 50 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-04-16 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-04-16 | 2023-05-03 | 18 | 13 | 2023-05-03 | 2023-05-03 | 1 | 1 | 104 | 74 | 19 | 14 | 123 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 166 | 166 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -313 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 265.42 | Unknown | Unknown | Unknown | 21.07 | 244.35 | 3981 | 732.74 | 265.42 | 467.32 | Yes | N/A | N/A | 2023-11-06 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-12-17 | 102 | 72 | 2023-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-07-11 | 207 | 149 | Unknown | 2024-04-02 | Unknown | Unknown | 2024-07-11 | 2024-07-23 | 13 | 9 | 2024-07-23 | 2024-07-22 | Unknown | Unknown | 207 | 149 | 115 | 81 | 322 | 230 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | -102 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1073.86 | 1718.31 | Unknown | 1098.91 | -4693 | 801.92 | Unknown | 4693.39 | -1073.86 | 5767.25 | Yes | N/A | N/A | 2023-11-10 | 2023-11-13 | 4 | 2 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 4 | 2 | 1 | 1 | 5 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8.49 | -7 | Unknown | Unknown | Unknown | -1.49 | Unknown | 98.66 | -8.49 | 107.15 | Yes | N/A | N/A | 2023-03-22 | 2023-03-28 | 7 | 5 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 7 | 5 | 1 | 1 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 134.25 | 134.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -179 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1367.33 | Unknown | Unknown | Unknown | -1810.96 | 443.63 | Unknown | 2782.1 | -1367.33 | 4149.43 | Yes | N/A | N/A | 2024-10-30 | 2024-11-21 | 23 | 17 | 2024-11-21 | 2025-03-21 | 121 | 87 | 2025-03-21 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-10 | Unknown | Unknown | 23 | 17 | 121 | 87 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 171 | 122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 657.67 | 2325 | Unknown | 75.6 | -2753 | 1010.07 | Unknown | 2753.5 | 657.67 | 2095.83 | Yes | N/A | N/A | 2023-07-10 | 2023-10-11 | 94 | 68 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 94 | 68 | 1 | 1 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | 237 | 170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 274.65 | -13.85 | Unknown | Unknown | 60.44 | 228.06 | 7962 | 686.67 | 274.65 | 412.02 | Yes | N/A | N/A | 2023-05-15 | 2023-07-23 | 70 | 50 | 2023-07-23 | 2023-07-28 | 6 | 5 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-10-17 | 82 | 58 | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2024-11-14 | 395 | 283 | 2024-11-14 | 2024-11-14 | 1 | 1 | 152 | 108 | 402 | 289 | 554 | 397 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9512 | 9512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-04-03 | 393 | 282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 722.07 | -14.48 | Unknown | Unknown | 1.08 | 735.47 | 7962 | 1202.2 | 722.07 | 480.13 | Yes | N/A | N/A | 2024-06-14 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2024-07-10 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2025-04-03 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-01 | Unknown | Unknown | 268 | 192 | 324 | 232 | 592 | 424 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 14.65 | -14.69 | Unknown | Unknown | Unknown | 29.34 | Unknown | 794.04 | 14.65 | 779.39 | Yes | N/A | N/A | 2024-01-03 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-01-03 | 51 | 37 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-02-26 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-28 | 32 | 24 | 2024-03-28 | 2024-03-28 | 1 | 1 | 55 | 39 | 84 | 62 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 17.57 | -4.89 | Unknown | Unknown | Unknown | 22.46 | Unknown | 1027.42 | 17.57 | 1009.85 | Yes | N/A | N/A | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-06-13 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-08-21 | 70 | 50 | 2024-08-21 | 2024-08-21 | 1 | 1 | 99 | 71 | 72 | 52 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 40.34 | Unknown | Unknown | Unknown | Unknown | 40.34 | 3981 | 1601.43 | 40.34 | 1561.09 | Yes | N/A | N/A | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-04 | 21 | 15 | 2024-12-04 | 2024-12-04 | 1 | 1 | 9 | 7 | 23 | 17 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 34.13 | Unknown | Unknown | Unknown | Unknown | 34.13 | 3981 | 565.15 | 34.13 | 531.02 | Yes | N/A | N/A | 2023-09-29 | 2024-02-09 | 134 | 96 | 2024-02-09 | 2024-04-12 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-07-24 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-04 | Unknown | Unknown | 238 | 170 | 64 | 46 | 302 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-26 | 1362 | 973 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | -437.54 | 385.46 | Unknown | 76.31 | -1632 | 732.69 | Unknown | 1631.61 | -437.54 | 2069.15 | Yes | N/A | N/A | 2024-10-08 | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-11-01 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-05-14 | 195 | 139 | Unknown | 2024-11-19 | Unknown | Unknown | 2025-03-17 | 2025-05-19 | 64 | 46 | 2025-05-19 | 2025-05-19 | 1 | 1 | 195 | 139 | 104 | 76 | 299 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 0.09 | -2.04 | Unknown | Unknown | Unknown | 2.13 | Unknown | 274.65 | 0.09 | 274.56 | Yes | N/A | N/A | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-16 | 7 | 5 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2 | 2 | 8 | 6 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-21 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 620.29 | -16.44 | Unknown | Unknown | 4.02 | 632.71 | 3981 | 925.82 | 620.29 | 305.53 | Yes | N/A | N/A | 2022-12-06 | 2023-05-15 | 161 | 115 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-07-24 | 71 | 51 | Unknown | 2023-06-27 | Unknown | Unknown | 2023-07-24 | 2023-07-24 | 1 | 1 | 2023-07-24 | 2023-07-24 | 1 | 1 | 232 | 166 | 2 | 2 | 234 | 168 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | 345 | 345 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -288 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 4707.89 | Unknown | Unknown | Unknown | Unknown | 4707.89 | 6286 | 573.98 | 4707.89 | -4133.91 | Yes | N/A | N/A | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2023-10-12 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-03 | 23 | 17 | Unknown | 2023-11-07 | Unknown | Unknown | 2023-11-13 | 2023-11-20 | 8 | 6 | 2023-11-20 | 2023-11-17 | Unknown | Unknown | 24 | 18 | 18 | 14 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -17.92 | -24.47 | Unknown | Unknown | -625 | 631.55 | 7962 | 1569.86 | -17.92 | 1587.78 | Yes | N/A | N/A | 2023-02-28 | 2023-06-23 | 116 | 84 | 2023-06-23 | 2023-07-11 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-05 | 8 | 6 | 2023-07-11 | 2023-12-28 | 171 | 123 | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-01-31 | Unknown | Unknown | 287 | 207 | 27 | 19 | 314 | 226 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 2438.86 | 454.68 | Unknown | 190.6 | 3.03 | 1790.55 | 3981 | 1476.3 | 2438.86 | -962.56 | Yes | N/A | N/A | 2025-02-27 | 2025-03-11 | 13 | 9 | 2025-03-11 | 2025-03-11 | 1 | 1 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-08 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-15 | 8 | 6 | 2025-04-15 | 2025-04-15 | 1 | 1 | 42 | 30 | 10 | 8 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | 308 | 221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 62.17 | Unknown | Unknown | Unknown | 5.61 | 56.56 | 3981 | 1214.4 | 62.17 | 1152.23 | Yes | N/A | N/A | 2024-06-28 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-01 | 49 | 35 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-09-30 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-14 | 46 | 34 | 2024-11-14 | 2025-02-27 | 106 | 76 | 92 | 66 | 201 | 145 | 293 | 211 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 101.12 | 101.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | 215 | 155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 568.09 | -11 | Unknown | Unknown | Unknown | 579.09 | Unknown | 444.8 | 568.09 | -123.29 | Yes | N/A | N/A | 2024-02-08 | 2024-07-18 | 162 | 116 | 2024-07-18 | 2024-08-14 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-22 | 24 | 18 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | 162 | 116 | 53 | 39 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 613.1 | -11.7 | Unknown | Unknown | Unknown | 624.8 | 3981 | 1506.16 | 613.1 | 893.06 | Yes | N/A | N/A | 2024-10-16 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-10-16 | 21 | 15 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-27 | 7 | 5 | 2024-11-27 | 2024-11-27 | 1 | 1 | 37 | 27 | 29 | 21 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-02-20 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3735.28 | 3169.14 | Unknown | 241.15 | -1227 | 1551.99 | Unknown | 1227.49 | 3735.28 | -2507.79 | Yes | N/A | N/A | 2024-02-20 | 2024-02-28 | 9 | 7 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | -676 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 597.77 | -4.07 | Unknown | Unknown | 4.44 | 597.4 | Unknown | 356.73 | 597.77 | -241.04 | Yes | N/A | N/A | 2023-06-30 | 2023-07-10 | 11 | 7 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-25 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-08-24 | 31 | 23 | 2023-08-24 | 2023-08-24 | 1 | 1 | 27 | 19 | 33 | 25 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | -4.98 | -3.92 | Unknown | Unknown | Unknown | -1.06 | Unknown | 515.81 | -4.98 | 520.79 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-01-10 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-16 | 7 | 5 | 2024-01-16 | 2024-01-16 | 1 | 1 | 46 | 34 | 9 | 7 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | -179 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.12 | -10.73 | Unknown | Unknown | Unknown | 22.85 | 3981 | 918.66 | 12.12 | 906.54 | Yes | N/A | N/A | 2023-10-23 | 2023-10-23 | 1 | 1 | 2023-10-23 | 2023-10-26 | 4 | 4 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-03 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -316 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 906.65 | Unknown | Unknown | Unknown | 28.44 | 878.21 | 3981 | 795.84 | 906.65 | -110.81 | Yes | N/A | N/A | 2023-11-28 | 2023-12-12 | 15 | 11 | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-08-14 | 247 | 177 | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-14 | 2024-08-29 | 16 | 12 | 2024-08-29 | 2024-08-29 | 1 | 1 | 262 | 188 | 18 | 14 | 280 | 202 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-16 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 634.66 | -12.75 | Unknown | Unknown | Unknown | 647.41 | Unknown | 2342.81 | 634.66 | 1708.15 | Yes | N/A | N/A | 2025-01-14 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2025-01-16 | 18 | 14 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-05-27 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-05 | 10 | 8 | 2025-06-05 | 2025-06-05 | 1 | 1 | 132 | 94 | 29 | 23 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | -695 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-05 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 22.43 | Unknown | Unknown | Unknown | Unknown | 22.43 | Unknown | 1676.05 | 22.43 | 1653.62 | Yes | N/A | N/A | 2025-02-03 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-05 | 15 | 11 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-07 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-19 | 13 | 9 | 2025-02-19 | 2025-02-19 | 1 | 1 | 3 | 3 | 29 | 21 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -463 | -331 | No | 2024-01-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-02-22 | IOU Designed & Installed | N/A | Yes | 23 | -6.39 | -5.19 | Unknown | Unknown | Unknown | -1.2 | 3981 | 1030.7 | -6.39 | 1037.09 | Yes | N/A | N/A | 2024-01-22 | 2024-02-07 | 17 | 13 | 2024-02-07 | 2024-02-14 | 8 | 6 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-22 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-15 | 23 | 17 | 2024-03-15 | 2024-03-15 | 1 | 1 | 49 | 37 | 32 | 24 | 81 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -434 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-03 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 1227.62 | 321.36 | Unknown | Unknown | Unknown | 906.26 | Unknown | 1193.26 | 1227.62 | -34.36 | Yes | N/A | N/A | 2025-01-03 | 2024-12-15 | Unknown | Unknown | 2024-12-15 | 2025-01-03 | 20 | 15 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-30 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-21 | 23 | 17 | 2025-02-21 | 2025-02-21 | 1 | 1 | 28 | 20 | 44 | 33 | 72 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 38 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | 2024-03-19 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 3515.62 | Unknown | Unknown | Unknown | Unknown | 3515.62 | Unknown | 1104.88 | 3515.62 | -2410.74 | Yes | N/A | N/A | 2023-06-05 | 2024-03-01 | 271 | 195 | 2024-03-01 | 2024-03-11 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-08 | 21 | 15 | 2024-04-08 | 2024-04-08 | 1 | 1 | 271 | 195 | 33 | 23 | 304 | 218 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 30.41 | Unknown | Unknown | Unknown | Unknown | 30.41 | 3981 | 1790.05 | 30.41 | 1759.64 | Yes | N/A | N/A | 2025-01-21 | 2025-02-10 | 21 | 15 | 2025-02-10 | 2025-03-21 | 40 | 30 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-11 | 15 | 11 | 2025-03-11 | 2025-03-11 | 1 | 1 | 29 | 21 | 56 | 42 | 85 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | -205 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | -3.3 | -2.39 | Unknown | Unknown | Unknown | -0.91 | Unknown | 55.52 | -3.3 | 58.82 | Yes | N/A | N/A | 2023-09-14 | 2023-05-01 | Unknown | Unknown | 2023-05-01 | 2023-09-19 | 142 | 102 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-10-02 | 13 | 9 | 2023-10-02 | 2023-10-02 | 1 | 1 | 2 | 2 | 156 | 112 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 4338.71 | -51.63 | Unknown | Unknown | Unknown | 4390.34 | Unknown | 6768.56 | 4338.71 | 2429.85 | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-26 | 17 | 13 | 2025-02-26 | 2025-02-26 | 1 | 1 | 15 | 11 | 18 | 14 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-28 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 264.66 | -9.33 | Unknown | Unknown | Unknown | 273.99 | Unknown | 883.1 | 264.66 | 618.44 | Yes | N/A | N/A | 2023-09-21 | 2023-04-28 | Unknown | Unknown | 2023-04-28 | 2023-09-28 | 154 | 110 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-02 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-31 | 30 | 22 | 2023-10-31 | 2023-10-31 | 1 | 1 | 5 | 3 | 185 | 133 | 190 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -281 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-24 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 20.27 | Unknown | Unknown | Unknown | Unknown | 20.27 | 3981 | 1316.43 | 20.27 | 1296.16 | Yes | N/A | N/A | 2024-06-04 | 2024-06-17 | 14 | 10 | 2024-06-17 | 2024-06-24 | 8 | 6 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-25 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-07 | 14 | 10 | 2024-08-07 | 2024-08-07 | 1 | 1 | 46 | 34 | 23 | 17 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 2061.45 | 514.16 | Unknown | 163.63 | Unknown | 1383.66 | 3981 | 1591.73 | 2061.45 | -469.72 | Yes | N/A | N/A | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-24 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-04-03 | 11 | 9 | 2025-04-03 | 2025-04-03 | 1 | 1 | 48 | 34 | 13 | 11 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 86.15 | 86.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 690.58 | -16.49 | Unknown | Unknown | 10.69 | 696.38 | 3961 | 986.6 | 690.58 | 296.02 | Yes | N/A | N/A | 2023-08-17 | 2023-09-11 | 26 | 18 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-09 | 29 | 21 | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-09 | 2023-11-15 | 38 | 28 | 2023-11-15 | 2023-11-14 | Unknown | Unknown | 55 | 39 | 39 | 29 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-02-21 | -85 | -62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 72.81 | -16.06 | Unknown | Unknown | 54.76 | 34.11 | 3981 | 510.91 | 72.81 | 438.1 | Yes | N/A | N/A | 2024-02-21 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-03-01 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | Unknown | 2024-11-28 | Unknown | Unknown | 2024-11-28 | 2024-11-28 | 1 | 1 | 0 | 0 | 40 | 30 | 40 | 30 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 337.82 | -8.92 | Unknown | Unknown | Unknown | 346.74 | Unknown | 383.08 | 337.82 | 45.26 | Yes | N/A | N/A | 2023-10-20 | 2023-10-26 | 7 | 5 | 2023-10-26 | 2023-10-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2024-01-10 | 76 | 54 | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-01-17 | Unknown | Unknown | 83 | 59 | 2 | 2 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -431 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | -10.67 | -9.38 | Unknown | Unknown | Unknown | -1.29 | Unknown | 158.51 | -10.67 | 169.18 | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | 2024-02-14 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-25 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2024-04-15 | 174 | 124 | 2024-04-15 | 2024-04-15 | 1 | 1 | 150 | 108 | 176 | 126 | 326 | 234 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 155.05 | 155.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-05 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 466.23 | 129.54 | Unknown | 58.96 | 8.61 | 269.12 | 3981 | 1124.6 | 466.23 | 658.37 | Yes | N/A | N/A | 2023-08-02 | 2023-10-17 | 77 | 55 | 2023-10-17 | 2023-10-18 | 2 | 2 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | 77 | 55 | 3 | 3 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | -91 | -66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | -710.5 | 1555.86 | Unknown | 165.3 | -3158 | 726.34 | Unknown | 3158.2 | -710.5 | 3868.7 | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2025-01-17 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-17 | 1 | 1 | 2024-12-04 | 2025-01-17 | 45 | 33 | 2025-01-17 | 2025-01-17 | 1 | 1 | 1 | 1 | 141 | 103 | 142 | 104 | Steps 2,3,5,6,7 | 44 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 125.05 | 125.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-05-10 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 38.9 | Unknown | Unknown | Unknown | Unknown | 38.9 | 3981 | 868.67 | 38.9 | 829.77 | Yes | N/A | N/A | 2024-04-04 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-10 | 65 | 47 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-07-31 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-10-30 | 92 | 66 | 2024-10-30 | 2024-10-29 | Unknown | Unknown | 83 | 59 | 157 | 113 | 240 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -745 | -534 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 27.36 | Unknown | Unknown | Unknown | Unknown | 27.36 | 3981 | 891.67 | 27.36 | 864.31 | Yes | N/A | N/A | 2024-04-01 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-01 | 40 | 28 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-09-09 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-17 | 9 | 7 | 2024-09-17 | 2024-09-17 | 1 | 1 | 162 | 116 | 50 | 36 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | 58 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 2368.9 | -8.62 | Unknown | 269.29 | 94.43 | 2013.8 | 7962 | 463.9 | 2368.9 | -1905 | Yes | N/A | N/A | 2023-05-30 | 2023-03-21 | Unknown | Unknown | 2023-03-21 | 2023-09-20 | 184 | 132 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2025-04-16 | 575 | 411 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-04-16 | 2025-04-22 | 7 | 5 | 2025-04-22 | 2025-04-21 | Unknown | Unknown | 575 | 411 | 191 | 137 | 766 | 548 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-08 | 531 | 380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 22217.84 | 9546.03 | Unknown | Unknown | 21.04 | 12650.77 | 52984 | 6668.1 | 22217.84 | -15549.74 | Yes | N/A | N/A | 2023-05-18 | 2023-05-18 | 1 | 1 | 2023-05-18 | 2023-08-24 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2024-07-01 | 313 | 223 | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-07-23 | Unknown | Unknown | 314 | 224 | 99 | 71 | 413 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1636.58 | -14.86 | Unknown | Unknown | Unknown | 1651.44 | Unknown | 1236.73 | 1636.58 | -399.85 | Yes | N/A | N/A | 2023-02-02 | 2023-02-02 | 1 | 1 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | 2023-04-07 | 2023-03-29 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-01 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3981 | 1582.1 | Unknown | 1582.1 | Yes | N/A | N/A | 2024-07-31 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-08-01 | 23 | 17 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-10-24 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-14 | 22 | 16 | 2024-11-14 | 2024-11-13 | Unknown | Unknown | 85 | 61 | 45 | 33 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -522 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 175.64 | 72.32 | Unknown | Unknown | Unknown | 103.32 | Unknown | 327.31 | 175.64 | 151.67 | Yes | N/A | N/A | 2023-03-15 | 2023-03-20 | 6 | 4 | 2023-03-20 | 2023-03-31 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-04-04 | 15 | 11 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 6 | 4 | 28 | 22 | 34 | 26 | Steps 2,3,5,6,7 | 4 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -543 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | -1349.8 | -11.22 | Unknown | Unknown | -1951 | 612.42 | Unknown | 1820.76 | -1349.8 | 3170.56 | Yes | N/A | N/A | 2024-11-13 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-11-13 | 31 | 23 | 2024-11-13 | 2025-01-07 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-01-16 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-02-24 | 40 | 28 | 2025-02-24 | 2025-02-18 | Unknown | Unknown | 121 | 87 | 71 | 51 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 81.15 | 81.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 1524.78 | -33.24 | Unknown | Unknown | Unknown | 1558.02 | Unknown | 307.58 | 1524.78 | -1217.2 | Yes | N/A | N/A | 2024-05-07 | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-05-07 | 5 | 3 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-22 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-04 | 14 | 10 | 2024-06-04 | 2024-06-04 | 1 | 1 | 16 | 12 | 20 | 14 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -298 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 624.81 | -21.94 | Unknown | Unknown | 1.07 | 645.68 | 7962 | 2598.73 | 624.81 | 1973.92 | Yes | N/A | N/A | 2023-02-03 | 2023-07-24 | 172 | 122 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2024-02-05 | 197 | 141 | Unknown | 2024-01-24 | Unknown | Unknown | 2024-02-05 | 2024-02-06 | 2 | 2 | 2024-02-06 | 2024-02-06 | 1 | 1 | 369 | 263 | 3 | 3 | 372 | 266 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-01 | 972 | 695 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-11-20 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 9330.15 | Unknown | Unknown | Unknown | Unknown | 9330.15 | 15278.62 | 1128.58 | 9330.15 | -8201.57 | Yes | N/A | N/A | 2024-09-03 | 2024-11-18 | 77 | 55 | 2024-11-18 | 2024-12-05 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-03-18 | 2025-04-30 | 44 | 32 | 2025-04-30 | 2025-04-30 | 1 | 1 | 77 | 55 | 63 | 47 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -579 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-26 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -4.56 | -19.12 | Unknown | Unknown | Unknown | 14.56 | 3981 | 1244.15 | -4.56 | 1248.71 | Yes | N/A | N/A | 2024-11-25 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-11-26 | 12 | 8 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-03-31 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-07 | 8 | 6 | 2025-04-07 | 2025-04-07 | 1 | 1 | 126 | 90 | 21 | 15 | 147 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-04-21 | IOU Designed & Installed | N/A | No | N/A | 15.56 | -0.31 | Unknown | Unknown | Unknown | 15.87 | 3981 | 1661.84 | 15.56 | 1646.28 | Yes | N/A | N/A | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-21 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-05-01 | 11 | 9 | 2025-05-01 | 2025-05-01 | 1 | 1 | 5 | 3 | 13 | 11 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.2 | -5.48 | Unknown | Unknown | Unknown | 11.68 | 3981 | 1040.6 | 6.2 | 1034.4 | Yes | N/A | N/A | 2023-03-31 | 2023-04-07 | 8 | 6 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-03-27 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 473 | 338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-17 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 41372.55 | 6968.2 | Unknown | 56.59 | 616.77 | 33730.99 | 43752 | 16151.75 | 41372.55 | -25220.8 | Yes | N/A | N/A | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | 2024-05-01 | 216 | 154 | 2024-02-14 | 2024-04-02 | 34 | 24 | 2024-01-19 | 2024-05-23 | 97 | 69 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-09-23 | 106 | 76 | 2024-09-23 | 2024-09-23 | 1 | 1 | 35 | 25 | 420 | 300 | 455 | 325 | Steps 2,3,5,6,7 | 173 | 123 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | 220 | 220 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-29 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 61.84 | Unknown | Unknown | Unknown | Unknown | 61.84 | Unknown | 1507.32 | 61.84 | 1445.48 | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-07-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-05 | 7 | 5 | 2024-08-05 | 2024-08-05 | 1 | 1 | 3 | 3 | 9 | 7 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -25 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2024-04-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 40483.13 | 5406.37 | Unknown | Unknown | -12751.32 | 47828.08 | 114533.38 | 25928.85 | 40483.13 | -14554.28 | Yes | N/A | N/A | 2023-08-16 | 2023-12-08 | 115 | 83 | 2023-12-08 | 2024-04-09 | 124 | 88 | 2023-12-18 | 2025-02-27 | 28 | 20 | 2024-03-15 | 2024-03-22 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-09-06 | 144 | 104 | 2024-09-06 | 2024-09-06 | 1 | 1 | 143 | 103 | 277 | 199 | 420 | 302 | Steps 2,3,5,6,7 | 462 | 330 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 359 | 359 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -164 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1580.99 | -66.56 | Unknown | Unknown | 5.15 | 1642.4 | 7962 | 1062.28 | 1580.99 | -518.71 | Yes | N/A | N/A | 2024-11-21 | 2024-11-22 | 2 | 2 | 2024-11-22 | 2024-12-03 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-04-01 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-01 | Unknown | Unknown | 122 | 88 | 12 | 8 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -475 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 13.73 | Unknown | Unknown | Unknown | Unknown | 13.73 | 3961 | 1111.33 | 13.73 | 1097.6 | Yes | N/A | N/A | 2024-08-23 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-23 | 3 | 3 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2025-01-22 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-27 | 6 | 4 | 2025-01-27 | 2025-01-23 | Unknown | Unknown | 153 | 109 | 9 | 7 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -522 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | 2023-06-09 | IOU Designed & Installed | N/A | No | N/A | 927.22 | 352.51 | Unknown | Unknown | 2.73 | 571.98 | 3241 | 1176.86 | 927.22 | 249.64 | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-06-09 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-17 | 39 | 27 | 2023-07-17 | 2023-07-17 | 1 | 1 | 30 | 22 | 40 | 28 | 70 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-24 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 9.27 | -8.24 | Unknown | Unknown | Unknown | 17.51 | Unknown | 942.83 | 9.27 | 933.56 | Yes | N/A | N/A | 2024-04-23 | 2024-04-24 | 2 | 2 | 2024-04-24 | 2024-04-25 | 2 | 2 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-28 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-07-02 | 36 | 26 | 2024-07-02 | 2024-07-02 | 1 | 1 | 37 | 27 | 39 | 29 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 14303.56 | 6380.12 | Unknown | Unknown | 57.64 | 7865.8 | Unknown | 1668.59 | 14303.56 | -12634.97 | Yes | N/A | N/A | 2025-04-03 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-04-03 | 16 | 12 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-05-15 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-22 | 8 | 6 | 2025-05-22 | 2025-05-22 | 1 | 1 | 43 | 31 | 25 | 19 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-13 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 168.79 | Unknown | Unknown | Unknown | Unknown | 168.79 | 3981 | 1928.86 | 168.79 | 1760.07 | Yes | N/A | N/A | 2024-12-10 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-13 | 23 | 17 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-27 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-31 | 5 | 5 | 2025-01-31 | 2025-01-31 | 1 | 1 | 46 | 32 | 29 | 23 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | -15.82 | -11.48 | Unknown | Unknown | Unknown | -4.34 | Unknown | 512.85 | -15.82 | 528.67 | Yes | N/A | N/A | 2023-06-13 | 2023-06-14 | 2 | 2 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-08-18 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-09-21 | 35 | 25 | 2023-09-21 | 2023-09-21 | 1 | 1 | 68 | 50 | 36 | 26 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-05 | 888 | 635 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-17 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2746.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-22 | 7 | 5 | 2025-04-22 | 2025-04-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-06-11 | 34 | 24 | 2025-06-11 | 2025-06-11 | 1 | 1 | 7 | 5 | 42 | 30 | 49 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 611 | 611 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 127 | 92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1625.53 | Unknown | Unknown | Unknown | 103.41 | 1522.12 | 7952 | 1073.93 | 1625.53 | -551.6 | Yes | N/A | N/A | 2024-02-22 | 2024-03-12 | 20 | 14 | 2024-03-12 | 2024-05-13 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-11-04 | 176 | 126 | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-15 | Unknown | Unknown | 196 | 140 | 63 | 45 | 259 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-16 | -668 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 1051.27 | -20.4 | Unknown | Unknown | Unknown | 1071.67 | 3941 | 1488.12 | 1051.27 | 436.85 | Yes | N/A | N/A | 2024-08-20 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-08-20 | 28 | 20 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-12 | 24 | 18 | 2024-09-12 | 2024-09-16 | 5 | 3 | 1 | 1 | 57 | 41 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-21 | -167 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1477.09 | -13.38 | Unknown | Unknown | 2.42 | 1488.05 | Unknown | 709.38 | 1477.09 | -767.71 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-07-07 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-09 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 6135.73 | 5794.31 | Unknown | 297.06 | -2421 | 2465.36 | Unknown | 2421.36 | 6135.73 | -3714.37 | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | 2025-04-01 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 327.05 | 327.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -256 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1345.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2023-11-09 | 23 | 17 | 2023-11-09 | 2024-04-22 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 166 | 118 | 23 | 17 | 189 | 135 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 408.29 | -15.49 | Unknown | Unknown | 10.33 | 413.45 | 3981 | 1190.83 | 408.29 | 782.54 | Yes | N/A | N/A | 2024-11-25 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-27 | 16 | 12 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-02 | 127 | 91 | Unknown | 2025-02-27 | Unknown | Unknown | 2025-04-02 | 2025-04-22 | 21 | 15 | 2025-04-22 | 2025-05-02 | 11 | 9 | 127 | 91 | 48 | 36 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | 396 | 283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 25.9 | Unknown | Unknown | Unknown | Unknown | 25.9 | 3981 | 862.09 | 25.9 | 836.19 | Yes | N/A | N/A | 2023-02-07 | 2024-08-16 | 557 | 399 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-18 | 1 | 1 | 557 | 399 | 1 | 1 | 558 | 400 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | 110 | 110 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | 79 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-11-07 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 23919.52 | 6505.4 | Unknown | Unknown | -10560 | 27974.12 | 2465 | 34408.21 | 23919.52 | 10488.69 | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-12-06 | 137 | 99 | 2024-11-14 | 2024-11-21 | 8 | 6 | 2024-11-13 | 2024-12-05 | 16 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-21 | 26 | 18 | 2025-04-21 | 2025-04-21 | 1 | 1 | 9 | 7 | 180 | 128 | 189 | 135 | Steps 2,3,5,6,7 | 30 | 22 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 18.45 | -16.37 | Unknown | Unknown | Unknown | 34.82 | Unknown | 812.71 | 18.45 | 794.26 | Yes | N/A | N/A | 2024-02-14 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-02-14 | 27 | 19 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-04-03 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-18 | 16 | 12 | 2024-04-18 | 2024-04-18 | 1 | 1 | 50 | 36 | 44 | 32 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 178.05 | 178.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -438 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | -2317.24 | Unknown | Unknown | Unknown | -2387 | 69.76 | Unknown | 2386.94 | -2317.24 | 4704.18 | Yes | N/A | N/A | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-12-09 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-02-05 | 59 | 43 | Unknown | 2025-01-24 | Unknown | Unknown | 2025-02-05 | 2025-03-03 | 27 | 19 | 2025-03-03 | 2025-03-03 | 1 | 1 | 80 | 58 | 29 | 21 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 1289.35 | Unknown | Unknown | Unknown | 12.81 | 1276.54 | 3981 | 1191.83 | 1289.35 | -97.52 | Yes | N/A | N/A | 2024-10-18 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-11-06 | 41 | 29 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-02-24 | 111 | 79 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-24 | 2025-03-24 | 29 | 21 | 2025-03-24 | 2025-03-24 | 1 | 1 | 111 | 79 | 71 | 51 | 182 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | -179 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1172.9 | 1852.25 | Unknown | 513.83 | -4271 | 732.02 | Unknown | 4270.94 | -1172.9 | 5443.84 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-11 | 642 | 459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 844.41 | 378.44 | Unknown | Unknown | 20.1 | 445.87 | 3981 | 296.68 | 844.41 | -547.73 | Yes | N/A | N/A | 2023-02-22 | 2023-03-29 | 36 | 26 | 2023-03-29 | 2023-03-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-03-09 | 9 | 7 | 2023-03-30 | 2023-10-10 | 195 | 139 | Unknown | 2023-11-06 | Unknown | Unknown | 2023-11-06 | 2024-01-30 | 86 | 62 | 2024-01-30 | 2023-11-15 | Unknown | Unknown | 231 | 165 | 97 | 71 | 328 | 236 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 16.05 | -14.24 | Unknown | Unknown | Unknown | 30.29 | Unknown | 876.73 | 16.05 | 860.68 | Yes | N/A | N/A | 2024-04-09 | 2024-04-09 | 1 | 1 | 2024-04-09 | 2024-04-09 | 1 | 1 | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-05-07 | 22 | 16 | 2024-05-07 | 2024-05-07 | 1 | 1 | 9 | 7 | 24 | 18 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | -640 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 21.94 | Unknown | Unknown | Unknown | Unknown | 21.94 | 3981 | 1609.3 | 21.94 | 1587.36 | Yes | N/A | N/A | 2024-10-15 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-10-15 | 5 | 3 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-13 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-20 | 8 | 6 | 2024-11-20 | 2024-11-20 | 1 | 1 | 30 | 22 | 14 | 10 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -408 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1521.81 | -18.81 | Unknown | Unknown | 30.55 | 1510.07 | 3981 | 1319.03 | 1521.81 | -202.78 | Yes | N/A | N/A | 2024-06-10 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-20 | 44 | 32 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-03-20 | 1 | 1 | 0 | 0 | 45 | 33 | 45 | 33 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 6528.97 | 1881.45 | Unknown | 479.1 | 5.09 | 4163.33 | 3981 | 1966.52 | 6528.97 | -4562.45 | Yes | N/A | N/A | 2023-07-13 | 2023-07-28 | 16 | 12 | 2023-07-28 | 2023-07-28 | 1 | 1 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-10-18 | 83 | 59 | Unknown | 2023-11-08 | Unknown | Unknown | 2023-10-18 | 2023-12-11 | 55 | 39 | 2023-12-11 | 2023-12-11 | 1 | 1 | 99 | 71 | 57 | 41 | 156 | 112 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | -138 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 796.34 | Unknown | Unknown | Unknown | Unknown | 796.34 | Unknown | 3155.61 | 796.34 | 2359.27 | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-19 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-11-14 | 27 | 19 | 2023-11-14 | 2023-11-14 | 1 | 1 | 5 | 5 | 29 | 21 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -514 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | -268.9 | Unknown | Unknown | Unknown | -1336.97 | 1068.07 | Unknown | 1238.86 | -268.9 | 1507.76 | Yes | N/A | N/A | 2024-07-22 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-07-22 | 27 | 19 | 2024-07-22 | 2024-07-25 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-10-04 | 67 | 49 | Unknown | 2024-09-05 | Unknown | Unknown | 2024-10-04 | 2024-11-13 | 41 | 29 | 2024-11-13 | 2024-12-11 | 29 | 21 | 71 | 53 | 97 | 69 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | -321 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-29 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | -517.2 | -21.9 | Unknown | Unknown | -1637 | 1141.7 | Unknown | 1571.57 | -517.2 | 2088.77 | Yes | N/A | N/A | 2024-10-25 | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-29 | 29 | 21 | 2024-10-29 | 2024-11-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-11-26 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-19 | 24 | 18 | 2024-12-19 | 2025-02-27 | 71 | 51 | 30 | 22 | 124 | 90 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 753.94 | 711.99 | Unknown | Unknown | -2516 | 2557.95 | Unknown | 2808.41 | 753.94 | 2054.47 | Yes | N/A | N/A | 2024-12-05 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-12-05 | 53 | 39 | 2024-12-05 | 2024-12-09 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-03-06 | 88 | 64 | Unknown | 2025-01-13 | Unknown | Unknown | 2025-03-06 | 2025-04-21 | 47 | 33 | 2025-04-21 | 2025-04-21 | 1 | 1 | 93 | 67 | 101 | 73 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -11.24 | -8.13 | Unknown | Unknown | Unknown | -3.11 | 3981 | 546.86 | -11.24 | 558.1 | Yes | N/A | N/A | 2023-02-09 | 2023-02-10 | 2 | 2 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-05-11 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -30 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -620.74 | 17.49 | Unknown | Unknown | -1447 | 808.77 | Unknown | 1447.29 | -620.74 | 2068.03 | Yes | N/A | N/A | 2025-02-10 | 2025-01-18 | Unknown | Unknown | 2025-01-18 | 2025-03-26 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-06 | 21 | 15 | 2025-03-26 | 2025-03-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-04-01 | 1 | 1 | 1 | 1 | 90 | 64 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | 202 | 145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 2226.53 | -12.92 | Unknown | Unknown | 62.66 | 2176.79 | 3753.77 | 430.73 | 2226.53 | -1795.8 | Yes | N/A | N/A | 2024-03-28 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-04-04 | 23 | 17 | 2024-04-04 | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-28 | 12 | 10 | 2024-04-05 | 2024-10-11 | 190 | 136 | Unknown | 2024-08-22 | Unknown | Unknown | 2024-10-11 | 2024-10-28 | 18 | 12 | 2024-10-28 | 2024-10-15 | Unknown | Unknown | 190 | 136 | 53 | 39 | 243 | 175 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -18 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 7807.14 | 3872 | Unknown | Unknown | -1049 | 4984.14 | 3416 | 2730.56 | 7807.14 | -5076.58 | Yes | N/A | N/A | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | 2024-08-09 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-11-18 | 102 | 72 | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-06 | 2024-11-19 | 14 | 10 | 2024-11-19 | 2024-11-18 | Unknown | Unknown | 103 | 73 | 38 | 28 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -450 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 1719.19 | 802.53 | Unknown | 6.36 | -1183 | 2093.3 | 895.62 | 1960.4 | 1719.19 | 241.21 | Yes | N/A | N/A | 2024-02-14 | 2024-02-14 | 1 | 1 | 2024-02-14 | 2024-02-14 | 1 | 1 | 2024-02-14 | 2024-03-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-17 | 42 | 30 | Unknown | 2024-04-04 | Unknown | Unknown | 2024-04-17 | 2024-04-30 | 14 | 10 | 2024-04-30 | 2024-04-30 | 1 | 1 | 66 | 48 | 16 | 12 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-29 | -499 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-20 | IOU Designed & Installed | N/A | No | N/A | -358.67 | -6.72 | Unknown | Unknown | -958.14 | 606.19 | Unknown | 760.13 | -358.67 | 1118.8 | Yes | N/A | N/A | 2023-02-28 | 2023-03-15 | 16 | 12 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | 2023-04-11 | Unknown | Unknown | 2023-03-20 | 2023-08-18 | 152 | 110 | 2023-08-18 | 2023-08-18 | 1 | 1 | 16 | 12 | 153 | 111 | 169 | 123 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-09 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 1993.79 | -23.07 | Unknown | Unknown | 52.02 | 1964.84 | 3981 | 1384.15 | 1993.79 | -609.64 | Yes | N/A | N/A | 2023-08-09 | 2023-11-16 | 100 | 72 | 2023-11-16 | 2023-12-07 | 22 | 16 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2024-03-01 | 86 | 62 | Unknown | 2024-02-05 | Unknown | Unknown | 2024-03-01 | 2024-03-19 | 19 | 13 | 2024-03-19 | 2024-03-19 | 1 | 1 | 186 | 134 | 42 | 30 | 228 | 164 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-15 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -24.5 | -15.87 | Unknown | Unknown | Unknown | -8.63 | Unknown | 1631.94 | -24.5 | 1656.44 | Yes | N/A | N/A | 2024-11-11 | 2024-11-15 | 5 | 5 | 2024-11-15 | 2025-01-24 | 71 | 51 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-28 | 46 | 34 | 2025-03-28 | 2025-03-28 | 1 | 1 | 7 | 7 | 118 | 86 | 125 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 985.25 | -18.3 | Unknown | Unknown | 1.72 | 1001.83 | 3981 | 1485.54 | 985.25 | 500.29 | Yes | N/A | N/A | 2024-10-17 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-18 | 4 | 4 | 2024-10-18 | Unknown | Unknown | Unknown | 2024-12-17 | 2024-12-27 | 11 | 9 | 2024-10-18 | 2024-11-21 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-02-06 | 78 | 56 | 2025-02-06 | 2025-02-06 | 1 | 1 | 35 | 25 | 94 | 70 | 129 | 95 | Steps 2,3,5,6,7 | 70 | 50 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21.2 | 21.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-05 | 2023-09-15 | IOU Designed & Installed | N/A | No | N/A | 1015.08 | 362.52 | Unknown | Unknown | Unknown | 652.56 | 3981 | 988.59 | 1015.08 | -26.49 | Yes | N/A | N/A | 2023-04-26 | 2023-05-05 | 10 | 8 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-09-15 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-09-22 | 8 | 6 | 2023-09-22 | 2023-09-22 | 1 | 1 | 144 | 104 | 9 | 7 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -350 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-24 | 2023-06-15 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -1.06 | -2.07 | Unknown | Unknown | Unknown | 1.01 | 3981 | 902.62 | -1.06 | 903.68 | Yes | N/A | N/A | 2022-10-24 | 2023-06-15 | 235 | 169 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-07-31 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-03 | 4 | 4 | 2023-08-03 | 2023-08-03 | 1 | 1 | 282 | 202 | 5 | 5 | 287 | 207 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-08-26 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1830.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-27 | 2024-08-05 | 161 | 115 | 2024-08-05 | 2024-12-18 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-04-30 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-11 | 29 | 21 | 2025-06-11 | 2025-06-03 | Unknown | Unknown | 295 | 211 | 165 | 119 | 460 | 330 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | 252 | 252 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-25 | 512 | 367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-03 | 2023-05-31 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 340363.23 | 15698.17 | Unknown | Unknown | 2465.99 | 322199.07 | 24642 | 127950.67 | 340363.23 | -212412.56 | Yes | N/A | N/A | 2022-11-03 | 2023-11-09 | 372 | 266 | 2023-11-09 | 2024-07-31 | 266 | 190 | 2024-02-05 | 2024-07-25 | 3 | 3 | 2024-02-12 | 2024-07-31 | 12 | 10 | 2024-07-31 | 2024-10-25 | 87 | 63 | 2024-09-16 | 2024-11-01 | 47 | 35 | 2024-08-13 | 2024-12-18 | 128 | 92 | 2024-12-18 | 2024-12-18 | 1 | 1 | 462 | 332 | 454 | 328 | 916 | 660 | Steps 2,3,5,6,7 | 460 | 332 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1614 | 1153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2025-02-25 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | 470.29 | -9.45 | Unknown | Unknown | Unknown | 479.74 | Unknown | 3742.47 | 470.29 | 3272.18 | Yes | N/A | N/A | 2024-08-08 | 2025-02-25 | 202 | 144 | 2025-02-25 | 2025-04-14 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-02 | 4 | 2 | 2025-06-02 | 2025-06-02 | 1 | 1 | 202 | 144 | 54 | 38 | 256 | 182 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | -87 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | 2023-11-23 | IOU Designed & Installed | N/A | No | N/A | 2220.94 | 749.83 | Unknown | 89.36 | 8.4 | 1373.35 | 3981 | 753.61 | 2220.94 | -1467.33 | Yes | N/A | N/A | 2023-04-21 | 2023-03-01 | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-11-23 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-11-23 | 2023-11-27 | 5 | 3 | 2023-11-27 | 2023-11-27 | 1 | 1 | 122 | 88 | 6 | 4 | 128 | 92 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -635 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 5.06 | Unknown | Unknown | Unknown | Unknown | 5.06 | 3981 | 197.01 | 5.06 | 191.95 | Yes | N/A | N/A | 2024-10-01 | 2024-10-03 | 3 | 3 | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-09 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-21 | 13 | 9 | 2024-10-21 | 2024-10-21 | 1 | 1 | 10 | 8 | 15 | 11 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 2795.35 | 668.12 | Unknown | 228.27 | Unknown | 1898.96 | 3981 | 956.01 | 2795.35 | -1839.34 | Yes | N/A | N/A | 2024-03-01 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2024-03-04 | 106 | 76 | 2024-03-04 | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-07 | 4 | 4 | 2024-03-04 | 2024-08-14 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-18 | 36 | 26 | 2024-09-18 | 2024-09-18 | 1 | 1 | 164 | 118 | 147 | 107 | 311 | 225 | Steps 2,3,5,6,7 | 3 | 3 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-08-14 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 1213.1 | 387.6 | Unknown | 121.74 | Unknown | 703.76 | 3981 | 1193.92 | 1213.1 | -19.18 | Yes | N/A | N/A | 2023-05-30 | 2023-07-06 | 38 | 28 | 2023-07-06 | 2023-08-14 | 40 | 28 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-09-11 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-13 | 3 | 3 | 2023-09-13 | 2023-09-13 | 1 | 1 | 67 | 49 | 44 | 32 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -336 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-11-12 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3241 | 2562.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-11-12 | 134 | 96 | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2025-01-09 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-06-16 | 160 | 114 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-16 | 2025-06-19 | 4 | 4 | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 353 | 253 | 5 | 5 | 358 | 258 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | 293.33 | 18.72 | Unknown | Unknown | Unknown | 274.61 | 3981 | 369.54 | 293.33 | 76.21 | Yes | N/A | N/A | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-08-17 | 21 | 15 | Unknown | 2023-08-15 | Unknown | Unknown | 2023-08-17 | 2023-08-18 | 2 | 2 | 2023-08-18 | 2023-08-18 | 1 | 1 | 22 | 16 | 3 | 3 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 3042 | 3042 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-16 | -192 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | 2023-03-15 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 5759.42 | 678.52 | Unknown | Unknown | 3.81 | 5077.09 | 3981 | 467.03 | 5759.42 | -5292.39 | Yes | N/A | N/A | 2022-06-21 | 2023-03-15 | 268 | 192 | 2023-03-15 | 2023-04-19 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-01-23 | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-24 | 2024-05-09 | 16 | 12 | 2024-05-09 | 2024-05-08 | Unknown | Unknown | 268 | 192 | 52 | 38 | 320 | 230 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | 159 | 159 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | 2023-09-01 | IOU Designed & Installed | N/A | No | N/A | 1201.4 | 362.52 | Unknown | 176.88 | Unknown | 662 | 3981 | 600.64 | 1201.4 | -600.76 | Yes | N/A | N/A | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-09-01 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-09-06 | 6 | 4 | 2023-09-06 | 2023-09-06 | 1 | 1 | 80 | 58 | 7 | 5 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -646 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 2101.58 | 509.4 | Unknown | 182.49 | Unknown | 1409.69 | 3981 | 1431.43 | 2101.58 | -670.15 | Yes | N/A | N/A | 2024-10-04 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-04 | 2 | 2 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-15 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-07 | 24 | 18 | 2024-11-07 | 2024-11-07 | 1 | 1 | 12 | 8 | 27 | 21 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-28 | -192 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 4704.17 | 1040.64 | Unknown | 1293.18 | 0.98 | 2369.37 | 3981 | 2024.13 | 4704.17 | -2680.04 | Yes | N/A | N/A | 2023-07-17 | 2023-08-18 | 33 | 25 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-10-13 | 45 | 33 | Unknown | 2023-09-20 | Unknown | Unknown | 2023-10-13 | 2023-10-19 | 7 | 5 | 2023-10-19 | 2023-10-19 | 1 | 1 | 78 | 58 | 9 | 7 | 87 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | 115 | 84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2025-03-17 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 15073.76 | 3802.78 | Unknown | Unknown | Unknown | 11270.98 | Unknown | 2397.28 | 15073.76 | -12676.48 | Yes | N/A | N/A | 2024-12-23 | 2025-02-26 | 66 | 48 | 2025-02-26 | 2025-03-18 | 21 | 15 | 2025-03-18 | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-07 | 11 | 7 | 2025-03-17 | 2025-04-07 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-10 | 4 | 4 | 2025-04-10 | 2025-04-10 | 1 | 1 | 88 | 64 | 37 | 27 | 125 | 91 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 265 | 190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1960.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | 2024-06-18 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-17 | 28 | 20 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-21 | 3 | 3 | 2024-06-21 | 2024-06-21 | 1 | 1 | 1 | 1 | 61 | 45 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | San Clemente | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | 166 | 119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-02-02 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 130463.87 | 20387.63 | Unknown | Unknown | 5452.62 | 104623.62 | 0 | 54346.97 | 130463.87 | -76116.9 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-18 | 2025-04-07 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-05-05 | 257 | 183 | 2025-05-05 | 2025-05-05 | 1 | 1 | 1 | 1 | 353 | 251 | 354 | 252 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 595 | 426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 2065.69 | 3099.92 | Unknown | 479.33 | -3364 | 1850.44 | Unknown | 3363.86 | 2065.69 | 1298.17 | Yes | N/A | N/A | 2024-09-23 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-15 | 2 | 2 | 2024-10-15 | 2024-10-15 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 307 | 220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -746.61 | 1944.88 | Unknown | 648.56 | -4179 | 838.95 | Unknown | 4179.25 | -746.61 | 4925.86 | Yes | N/A | N/A | 2022-02-10 | 2023-03-16 | 400 | 286 | 2023-03-16 | 2024-01-03 | 294 | 210 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-01-18 | 1 | 1 | 400 | 286 | 295 | 211 | 695 | 497 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-06-04 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 3072.89 | 1549.84 | Unknown | 423.47 | Unknown | 1099.58 | 3961 | 192.83 | 3072.89 | -2880.06 | Yes | N/A | N/A | 2024-05-30 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-06-20 | 57 | 41 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-31 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-09-28 | 60 | 43 | 2024-09-28 | 2024-09-28 | 1 | 0 | 42 | 30 | 118 | 84 | 160 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 157 | 112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | -2580.24 | 932.94 | Unknown | 198.57 | -4124 | 412.25 | Unknown | 4123.56 | -2580.24 | 6703.8 | Yes | N/A | N/A | 2023-04-20 | 2023-06-06 | 48 | 34 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-27 | 15 | 11 | 2023-11-27 | 2023-11-27 | 1 | 1 | 48 | 34 | 16 | 12 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | -154 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1742.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-04-22 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-05 | 14 | 10 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-06 | 2025-05-14 | 9 | 7 | 2025-05-14 | 2025-05-13 | Unknown | Unknown | 15 | 11 | 23 | 17 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 149 | 149 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-30 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 5050.7 | Unknown | Unknown | Unknown | Unknown | 5050.7 | 3981 | 1488.86 | 5050.7 | -3561.84 | Yes | N/A | N/A | 2024-07-29 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-08-29 | 51 | 37 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-10-30 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-01-15 | 78 | 56 | 2025-01-15 | 2024-11-19 | Unknown | Unknown | 62 | 44 | 129 | 93 | 191 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | 763.98 | -13.69 | Unknown | Unknown | Unknown | 777.67 | 3981 | 778.33 | 763.98 | 14.35 | Yes | N/A | N/A | 2024-01-22 | 2024-02-02 | 12 | 10 | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-29 | 57 | 41 | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-29 | 2024-04-16 | 19 | 13 | 2024-04-16 | 2024-04-16 | 1 | 1 | 69 | 51 | 21 | 15 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-08-02 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 28.47 | Unknown | Unknown | Unknown | Unknown | 28.47 | Unknown | 1526.33 | 28.47 | 1497.86 | Yes | N/A | N/A | 2024-07-16 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-08-02 | 50 | 36 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-08 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-26 | 19 | 13 | 2024-08-26 | 2024-08-26 | 1 | 1 | 7 | 5 | 70 | 50 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.13 | -17.17 | Unknown | Unknown | Unknown | 13.04 | Unknown | 1763.19 | -4.13 | 1767.32 | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -606 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 1537.31 | Unknown | Unknown | Unknown | 17.28 | 1520.03 | 3981 | 1177.58 | 1537.31 | -359.73 | Yes | N/A | N/A | 2024-12-03 | 2024-12-10 | 8 | 6 | 2024-12-10 | 2024-12-10 | 1 | 1 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-03-13 | 94 | 68 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-03-13 | 2025-03-18 | 6 | 4 | 2025-03-18 | 2025-03-18 | 1 | 1 | 102 | 74 | 8 | 6 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-11 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | 1010.48 | Unknown | Unknown | Unknown | Unknown | 1010.48 | 2875.23 | 484.69 | 1010.48 | -525.79 | Yes | N/A | N/A | 2024-03-06 | 2024-03-07 | 2 | 2 | 2024-03-07 | 2024-10-11 | 219 | 157 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2025-06-02 | 235 | 167 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 237 | 169 | 221 | 159 | 458 | 328 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 9 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-08 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 2106.52 | Unknown | Unknown | Unknown | Unknown | 2106.52 | Unknown | 2142.95 | 2106.52 | 36.43 | Yes | N/A | N/A | 2022-11-17 | 2023-09-26 | 314 | 224 | 2023-09-26 | 2023-10-04 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-24 | 14 | 10 | 2023-10-24 | 2023-10-24 | 1 | 1 | 314 | 224 | 24 | 18 | 338 | 242 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 129600 | 129600 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-09-29 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | 2023-05-04 | IOU Designed & Installed | N/A | No | N/A | 227.83 | -10.93 | Unknown | Unknown | -364.61 | 603.37 | Unknown | 542.25 | 227.83 | 314.42 | Yes | N/A | N/A | 2023-01-25 | 2023-02-01 | 8 | 6 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-05-04 | 64 | 46 | Unknown | 2023-05-01 | Unknown | Unknown | 2023-05-04 | 2023-08-18 | 107 | 77 | 2023-08-18 | 2023-08-18 | 1 | 1 | 72 | 52 | 108 | 78 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -640 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-02 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1629.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-04-02 | 15 | 11 | 2025-04-02 | 2025-05-09 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-22 | 14 | 10 | 2025-05-22 | 2025-05-21 | Unknown | Unknown | 39 | 29 | 29 | 21 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -480 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-09 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 546.48 | 147.38 | Unknown | 117.92 | Unknown | 281.18 | 3885 | 991.44 | 546.48 | 444.96 | Yes | N/A | N/A | 2023-05-02 | 2023-05-09 | 8 | 6 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-10-23 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-11-06 | 15 | 11 | 2023-11-06 | 2023-11-06 | 1 | 1 | 176 | 126 | 16 | 12 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-14 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2023-06-15 | IOU Designed & Installed | N/A | No | N/A | -5.63 | -4.09 | Unknown | Unknown | Unknown | -1.54 | Unknown | 364.52 | -5.63 | 370.15 | Yes | N/A | N/A | 2023-04-03 | 2023-04-03 | 1 | 1 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-06-15 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-07-10 | 26 | 18 | 2023-07-10 | 2023-07-10 | 1 | 1 | 75 | 55 | 27 | 19 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 171 | 122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-30 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 12228.24 | Unknown | Unknown | Unknown | 24.76 | 12203.48 | 155223 | 17402.74 | 12228.24 | 5174.5 | Yes | N/A | N/A | 2023-08-28 | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-10-06 | 82 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2024-01-17 | 104 | 74 | Unknown | 2024-03-18 | Unknown | Unknown | 2024-04-10 | 2024-05-24 | 45 | 33 | 2024-05-24 | 2024-05-20 | Unknown | Unknown | 104 | 74 | 127 | 93 | 231 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 10792.16 | Unknown | Unknown | Unknown | 10.98 | 10781.18 | 3981 | 2189.87 | 10792.16 | -8602.29 | Yes | N/A | N/A | 2024-10-23 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-11-18 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-03 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-14 | 2025-03-24 | 39 | 27 | 2025-03-24 | 2025-03-24 | 1 | 1 | 0 | 0 | 82 | 58 | 82 | 58 | Steps 2,3,5,6,7 | 46 | 34 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | 42 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 8.95 | Unknown | Unknown | Unknown | Unknown | 8.95 | Unknown | 1082.33 | 8.95 | 1073.38 | Yes | N/A | N/A | 2024-11-26 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-26 | 15 | 11 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-02-07 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-26 | 48 | 34 | 2025-03-26 | 2025-03-26 | 1 | 1 | 74 | 54 | 64 | 46 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-21 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 20.15 | -18.01 | Unknown | Unknown | Unknown | 38.16 | Unknown | 849.35 | 20.15 | 829.2 | Yes | N/A | N/A | 2024-01-31 | 2024-02-21 | 22 | 16 | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-15 | 11 | 9 | 2024-03-15 | 2024-03-28 | 14 | 10 | 36 | 26 | 26 | 20 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 5.48 | Unknown | Unknown | Unknown | Unknown | 5.48 | Unknown | 186.4 | 5.48 | 180.92 | Yes | N/A | N/A | 2024-06-12 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-06-12 | 45 | 33 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-09-10 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-02 | 23 | 17 | 2024-10-02 | 2024-10-02 | 1 | 1 | 91 | 65 | 69 | 51 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -270 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-30 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 21.81 | Unknown | Unknown | Unknown | Unknown | 21.81 | Unknown | 1970.25 | 21.81 | 1948.44 | Yes | N/A | N/A | 2025-01-22 | 2025-01-30 | 9 | 7 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-04-04 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-14 | 11 | 7 | 2025-04-14 | 2025-04-14 | 1 | 1 | 74 | 54 | 13 | 9 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-16 | -890 | -637 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-25 | 2023-08-11 | IOU Designed & Installed | N/A | No | N/A | 741.6 | -31.37 | Unknown | Unknown | Unknown | 772.97 | 3241 | 1040.07 | 741.6 | 298.47 | Yes | N/A | N/A | 2023-05-16 | 2023-05-22 | 7 | 5 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-08-11 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-10 | 1 | 1 | 86 | 62 | 1 | 1 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -281 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-04-18 | IOU Designed & Installed | N/A | No | N/A | 428.93 | -4.64 | Unknown | Unknown | 28.16 | 405.41 | 3981 | 1004.34 | 428.93 | 575.41 | Yes | N/A | N/A | 2023-02-09 | 2023-02-09 | 1 | 1 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | 2023-04-18 | 69 | 49 | Unknown | 2025-03-05 | Unknown | Unknown | 2023-04-18 | 2023-08-11 | 116 | 84 | 2023-08-11 | 2023-04-26 | Unknown | Unknown | 70 | 50 | 116 | 84 | 186 | 134 | Steps 2,3,5,6,7 | 687 | 491 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 43.4 | 43.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -220 | -158 | No | 2024-02-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2025-04-01 | IOU Designed & Installed | N/A | Yes | 347 | 7679.31 | 1661.21 | Unknown | 481.91 | 15.68 | 5520.51 | 3941 | 1266.51 | 7679.31 | -6412.8 | Yes | N/A | N/A | 2024-02-26 | 2025-02-07 | 348 | 250 | 2025-02-07 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2025-02-12 | 338 | 242 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2025-04-01 | 386 | 276 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | 2025-06-04 | 65 | 47 | 1072 | 768 | 66 | 48 | 1138 | 816 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.04 | -8.95 | Unknown | Unknown | Unknown | 5.91 | Unknown | 804.89 | -3.04 | 807.93 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-07-06 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 5335.83 | 446.15 | Unknown | Unknown | -11454.74 | 16344.42 | Unknown | 11458.17 | 5335.83 | 6122.34 | Yes | N/A | N/A | 2023-01-04 | 2023-04-10 | 97 | 69 | 2023-04-10 | 2023-10-31 | 205 | 147 | 2023-08-29 | 2023-08-30 | 2 | 2 | 2023-11-01 | 2023-11-13 | 13 | 9 | 2023-12-04 | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | 2023-12-06 | 2024-01-05 | 31 | 23 | 2024-01-05 | 2024-01-05 | 1 | 1 | 99 | 71 | 250 | 180 | 349 | 251 | Steps 2,3,5,6,7 | 63 | 45 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-02 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 225.9 | -16.15 | Unknown | Unknown | 36.65 | 205.4 | 3981 | 1003.33 | 225.9 | 777.43 | Yes | N/A | N/A | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2024-06-20 | 259 | 185 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-01 | 12 | 8 | 2024-07-01 | 2024-06-24 | Unknown | Unknown | 260 | 186 | 13 | 9 | 273 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 197 | 197 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | -191 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-03-05 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 27.54 | Unknown | Unknown | Unknown | Unknown | 27.54 | 7962 | 873.4 | 27.54 | 845.86 | Yes | N/A | N/A | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-06-04 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-07-09 | 38 | 26 | 2024-06-04 | 2024-09-11 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-29 | 8 | 6 | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 101 | 73 | 144 | 102 | 245 | 175 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | 283.44 | 283.44 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-15 | 153 | 110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-19 | 2022-12-19 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 2875.14 | 1903.97 | Unknown | 1992.84 | -2141 | 1119.33 | Unknown | 2140.53 | 2875.14 | -734.61 | Yes | N/A | N/A | 2022-12-19 | 2023-11-09 | 326 | 234 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-15 | 5 | 5 | 2023-12-15 | 2023-12-15 | 1 | 1 | 326 | 234 | 6 | 6 | 332 | 240 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 375.5 | 375.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | 4 | 3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-13 | 2023-04-13 | IOU Designed & Installed | N/A | No | N/A | 5115.68 | -8.81 | Unknown | Unknown | Unknown | 5124.49 | 3981 | 3897.51 | 5115.68 | -1218.17 | Yes | N/A | N/A | 2023-02-08 | 2023-02-13 | 6 | 4 | 2023-02-13 | 2023-03-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-07-03 | 82 | 58 | 2023-07-03 | 2023-07-03 | 1 | 1 | 6 | 4 | 106 | 76 | 112 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | SAN YSIDRO | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | 417 | 298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2702.02 | -10.37 | Unknown | Unknown | 231.14 | 2481.25 | 15924 | 1114.3 | 2702.02 | -1587.72 | Yes | N/A | N/A | 2023-06-07 | 2023-07-07 | 31 | 23 | 2023-07-07 | 2023-08-30 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2024-08-15 | 8 | 6 | 2023-08-30 | 2024-10-25 | 423 | 303 | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-18 | 1 | 1 | 454 | 326 | 64 | 46 | 518 | 372 | Steps 2,3,5,6,7 | 351 | 251 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | 1461.15 | 380.61 | Unknown | Unknown | Unknown | 1080.54 | Unknown | 1657.68 | 1461.15 | 196.53 | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-07 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-14 | 8 | 6 | 2025-03-14 | 2025-03-14 | 1 | 1 | 25 | 19 | 10 | 8 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-13 | 1131 | 808 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 481.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-11-21 | 28 | 20 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-17 | 1 | 1 | 0 | 0 | 29 | 21 | 29 | 21 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-26 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 4.13 | Unknown | Unknown | Unknown | Unknown | 4.13 | 3981 | 1015.58 | 4.13 | 1011.45 | Yes | N/A | N/A | 2024-07-18 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-07-26 | 43 | 31 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-07-29 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-10-24 | 88 | 64 | 2024-10-24 | 2024-10-24 | 1 | 1 | 4 | 2 | 132 | 96 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | -131 | -94 | No | 2023-06-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-29 | 2023-11-14 | IOU Designed & Installed | N/A | Yes | 111 | -5.03 | -8.57 | Unknown | Unknown | Unknown | 3.54 | 3961 | 158.51 | -5.03 | 163.54 | Yes | N/A | N/A | 2023-06-27 | 2023-10-13 | 109 | 79 | 2023-10-13 | 2023-10-16 | 4 | 2 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-11-14 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-11-21 | 8 | 6 | 2023-11-21 | 2023-11-21 | 1 | 1 | 139 | 101 | 13 | 9 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -236 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | 182.96 | 83.67 | Unknown | Unknown | Unknown | 99.29 | 0 | 98.41 | 182.96 | -84.55 | Yes | N/A | N/A | 2023-02-02 | 2023-02-17 | 16 | 12 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2023-08-04 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-04-08 | 249 | 177 | 2024-04-08 | 2024-04-08 | 1 | 1 | 185 | 133 | 250 | 178 | 435 | 311 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | -207 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.55 | -5.48 | Unknown | Unknown | Unknown | -2.07 | Unknown | 154.79 | -7.55 | 162.34 | Yes | N/A | N/A | 2023-03-28 | 2023-04-07 | 11 | 9 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-06-05 | 1 | 1 | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | MISSION VIEJO | MISSION VIEJO | 212 | 212 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-04 | 520 | 373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-07-18 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 86767.1 | 28751.09 | Unknown | 91.23 | -27851 | 85775.78 | 0 | 25516.42 | 86767.1 | -61250.68 | Yes | N/A | N/A | 2023-06-05 | 2023-06-23 | 19 | 15 | 2023-06-23 | Unknown | Unknown | Unknown | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-09-29 | 2023-12-15 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | 2024-01-02 | 2024-01-17 | 16 | 12 | 2024-01-17 | 2025-03-07 | 416 | 298 | 20 | 16 | 470 | 338 | 490 | 354 | Steps 2,3,5,6,7 | 400 | 286 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-03 | 871 | 624 | No | 2023-04-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2025-02-04 | IOU Designed & Installed | N/A | Yes | 511 | 4271 | 1867.43 | Unknown | Unknown | Unknown | 2403.57 | 64335 | 24965.2 | 4271 | 20694.2 | Yes | N/A | N/A | 2023-04-20 | 2024-07-11 | 449 | 321 | 2024-07-11 | 2024-09-17 | 69 | 49 | 2023-07-13 | 2023-08-14 | 33 | 23 | 2023-10-06 | 2025-01-21 | 46 | 32 | 2024-09-17 | 2025-01-06 | 112 | 80 | 2024-10-03 | 2025-01-21 | 111 | 79 | 2025-02-04 | 2025-02-24 | 21 | 15 | 2025-02-24 | 2025-02-20 | Unknown | Unknown | 594 | 424 | 247 | 175 | 841 | 599 | Steps 2,3,5,6,7 | 653 | 465 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-07 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1714.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-14 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-22 | 9 | 7 | 2025-05-22 | 2025-05-22 | 1 | 1 | 35 | 25 | 11 | 9 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | 659.49 | -5.85 | Unknown | Unknown | 4.9 | 660.44 | 3981 | 2013.12 | 659.49 | 1353.63 | Yes | N/A | N/A | 2023-03-28 | 2023-04-11 | 15 | 11 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-11-20 | 224 | 160 | Unknown | 2023-11-06 | Unknown | Unknown | 2023-11-20 | 2023-11-29 | 10 | 8 | 2023-11-29 | 2023-11-29 | 1 | 1 | 239 | 171 | 11 | 9 | 250 | 180 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 1831 | 1831 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-06-01 | 589 | 422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11684.65 | Unknown | Unknown | Unknown | Unknown | 11684.65 | 74373 | 4510.3 | 11684.65 | -7174.35 | Yes | N/A | N/A | 2023-08-30 | 2023-09-01 | 3 | 3 | 2023-09-01 | 2023-09-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2024-12-09 | 460 | 328 | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-01-10 | Unknown | Unknown | 463 | 331 | 7 | 5 | 470 | 336 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAS FLORES | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | -128 | -92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | 2024-01-12 | IOU Designed & Installed | N/A | No | N/A | 5450.28 | Unknown | Unknown | Unknown | Unknown | 5450.28 | Unknown | 2276.67 | 5450.28 | -3173.61 | Yes | N/A | N/A | 2023-12-08 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2024-01-08 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | 2024-01-12 | 2024-01-18 | 7 | 5 | 2024-01-18 | 2024-01-18 | 1 | 1 | 0 | 0 | 69 | 49 | 69 | 49 | Steps 2,3,5,6,7 | 4 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-15 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 910.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-02-15 | 4 | 4 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-08-05 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2025-08-15 | 376 | 270 | 2025-08-15 | 2024-09-10 | Unknown | Unknown | 177 | 127 | 376 | 270 | 553 | 397 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 365.29 | Unknown | Unknown | Unknown | 13.34 | 351.95 | 3981 | 1136.34 | 365.29 | 771.05 | Yes | N/A | N/A | 2024-07-08 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-07-17 | 36 | 26 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-01-08 | 176 | 126 | Unknown | 2024-12-19 | Unknown | Unknown | 2025-01-08 | 2025-01-27 | 20 | 14 | 2025-01-27 | 2025-01-27 | 1 | 1 | 176 | 126 | 57 | 41 | 233 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1296 | 1296 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-01-08 | 539 | 386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1680.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-11-11 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 0 | 0 | 127 | 91 | 127 | 91 | Steps 2,3,5,6,7 | 170 | 122 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 486 | 347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 22.85 | Unknown | Unknown | Unknown | Unknown | 22.85 | 0 | 747.31 | 22.85 | 724.46 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2024-07-23 | 512 | 366 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-30 | 8 | 6 | 2024-07-30 | 2024-07-30 | 1 | 1 | 513 | 367 | 9 | 7 | 522 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | -423 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 304.42 | Unknown | Unknown | Unknown | -441.3 | 745.72 | Unknown | 720.6 | 304.42 | 416.18 | Yes | N/A | N/A | 2024-06-12 | 2024-07-02 | 21 | 15 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | 2024-09-18 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 100 | 72 | 2 | 2 | 102 | 74 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2023-09-15 | IOU Designed & Installed | N/A | No | N/A | 1462.11 | 362.52 | Unknown | Unknown | -631.81 | 1731.4 | Unknown | 641.97 | 1462.11 | -820.14 | Yes | N/A | N/A | 2023-05-25 | 2023-06-20 | 27 | 19 | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | 2023-06-22 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-09-15 | 75 | 55 | Unknown | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-09-20 | 6 | 4 | 2023-09-20 | 2023-09-20 | 1 | 1 | 105 | 77 | 8 | 6 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -332 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-25 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 10259.11 | 9828.86 | Unknown | 1902.03 | -21831 | 20359.22 | Unknown | 43660.8 | 10259.11 | 33401.69 | Yes | N/A | N/A | 2024-04-02 | 2024-04-18 | 17 | 13 | 2024-04-18 | 2024-12-05 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-12-11 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-24 | 4 | 2 | 2025-02-24 | 2025-02-24 | 1 | 1 | 17 | 13 | 247 | 177 | 264 | 190 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 198.25 | 198.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-16 | -16 | -13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-23 | 2022-08-23 | 2023-07-10 | IOU Designed & Installed | N/A | No | N/A | 3952.26 | 350.69 | Unknown | Unknown | -648.6 | 4250.17 | 4553.02 | 1384.09 | 3952.26 | -2568.17 | Yes | N/A | N/A | 2022-08-23 | 2023-06-13 | 295 | 211 | 2023-06-13 | 2023-06-22 | 10 | 8 | 2023-06-22 | 2023-06-29 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-07-10 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-08-16 | 38 | 28 | 2023-08-16 | 2023-07-31 | Unknown | Unknown | 315 | 225 | 48 | 36 | 363 | 261 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-03 | 722 | 517 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2023-05-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 621.88 | -12.48 | Unknown | Unknown | Unknown | 634.36 | 285691 | 8331.98 | 621.88 | 7710.1 | Yes | N/A | N/A | 2022-11-14 | 2023-02-10 | 89 | 65 | 2023-02-10 | 2023-06-08 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-05-23 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 89 | 65 | 131 | 93 | 220 | 158 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -115 | -84 | No | 2023-10-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-12-21 | 2024-04-02 | IOU Designed & Installed | N/A | Yes | 101 | 11.17 | -9.92 | Unknown | Unknown | Unknown | 21.09 | 3981 | 836.53 | 11.17 | 825.36 | Yes | N/A | N/A | 2023-10-13 | 2024-01-22 | 102 | 72 | 2024-01-22 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-04-02 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-15 | 14 | 10 | 2024-04-15 | 2024-04-15 | 1 | 1 | 206 | 146 | 15 | 11 | 221 | 157 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | -332 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 607.81 | -21.38 | Unknown | Unknown | Unknown | 629.19 | 3241 | 642.65 | 607.81 | 34.84 | Yes | N/A | N/A | 2023-07-05 | 2023-07-06 | 2 | 2 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-25 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-08-02 | 9 | 7 | 2023-08-02 | 2023-08-02 | 1 | 1 | 22 | 16 | 10 | 8 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -700 | -501 | No | 2022-08-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-22 | 2022-08-22 | Unknown | IOU Designed & Installed | N/A | Yes | 247 | 1320.3 | -11.44 | Unknown | Unknown | Unknown | 1331.74 | 6481 | 729 | 1320.3 | -591.3 | Yes | N/A | N/A | 2022-08-22 | 2023-04-26 | 248 | 178 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-06-01 | 1 | 1 | 248 | 178 | 1 | 1 | 249 | 179 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | -604 | -433 | No | 2022-11-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2022-12-19 | 2023-08-15 | IOU Designed & Installed | N/A | Yes | 200 | 5160.52 | 2200.39 | Unknown | 389.25 | -946.73 | 3517.61 | 11655 | 2130.88 | 5160.52 | -3029.64 | Yes | N/A | N/A | 2022-11-17 | 2023-06-16 | 212 | 152 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-15 | 61 | 43 | Unknown | 2023-07-21 | Unknown | Unknown | 2023-08-15 | 2023-11-01 | 79 | 57 | 2023-11-01 | 2023-08-16 | Unknown | Unknown | 273 | 195 | 79 | 57 | 352 | 252 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | -211 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | 2023-05-23 | IOU Designed & Installed | N/A | No | N/A | 739.21 | -15.07 | Unknown | Unknown | Unknown | 754.28 | Unknown | 907.24 | 739.21 | 168.03 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-05-23 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-06-09 | 18 | 14 | 2023-06-09 | 2023-06-09 | 1 | 1 | 49 | 35 | 19 | 15 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-10 | -145 | -104 | No | 2023-02-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | Yes | 6 | 2430.79 | -54.21 | Unknown | Unknown | Unknown | 2485 | 3981 | 341 | 2430.79 | -2089.79 | Yes | N/A | N/A | 2023-02-22 | 2023-02-28 | 7 | 5 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 7 | 5 | 1 | 1 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -640 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2023-05-26 | IOU Designed & Installed | N/A | No | N/A | 1740.8 | 236.04 | Unknown | Unknown | Unknown | 1504.76 | Unknown | 255.53 | 1740.8 | -1485.27 | Yes | N/A | N/A | 2023-04-25 | 2023-05-17 | 23 | 17 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-05-26 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | 2023-05-26 | 1 | 1 | 33 | 25 | 2 | 2 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -819 | -586 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-20 | 2022-12-20 | 2023-08-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 9734.26 | 4081.57 | Unknown | Unknown | -12126 | 17778.69 | Unknown | 3506.42 | 9734.26 | -6227.84 | Yes | N/A | N/A | 2022-12-20 | 2023-03-30 | 101 | 73 | 2023-03-30 | 2023-05-23 | 55 | 39 | 2023-04-07 | 2023-04-10 | 4 | 2 | 2023-05-23 | 2023-09-20 | -69 | -53 | 2023-08-08 | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-17 | 10 | 8 | 2023-08-24 | 2023-10-04 | 42 | 30 | 2023-10-04 | 2023-10-04 | 1 | 1 | 105 | 75 | 39 | 25 | 144 | 100 | Steps 2,3,5,6,7 | 89 | 63 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 148.73 | -3.3 | Unknown | Unknown | Unknown | 152.03 | 0 | 466.88 | 148.73 | 318.15 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2025-03-20 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 3 | 3 | 351 | 251 | 354 | 254 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1916.75 | 1916.75 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-07-23 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-10-10 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 1874.45 | 405.97 | Unknown | Unknown | Unknown | 1468.48 | 3981 | 2776.81 | 1874.45 | 902.36 | Yes | N/A | N/A | 2024-09-23 | 2024-10-03 | 11 | 9 | 2024-10-03 | 2024-10-10 | 8 | 6 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-01-15 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-19 | 36 | 26 | 2025-02-19 | 2025-02-19 | 1 | 1 | 109 | 79 | 45 | 33 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 1860.1 | 1860.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-09-21 | -141 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | -3.14 | -2.55 | Unknown | Unknown | Unknown | -0.59 | Unknown | 534.57 | -3.14 | 537.71 | Yes | N/A | N/A | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-03 | 24 | 18 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2 | 2 | 26 | 20 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-31 | 717 | 514 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 501.96 | -9.35 | Unknown | Unknown | 12.61 | 498.7 | 3981 | 531.94 | 501.96 | 29.98 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | 2023-05-23 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2024-01-16 | 223 | 159 | 2023-05-23 | 2024-01-10 | 233 | 167 | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-01-18 | Unknown | Unknown | 234 | 168 | 288 | 206 | 522 | 374 | Steps 2,3,5,6,7 | 238 | 170 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 7039.6 | Unknown | Unknown | Unknown | -817.62 | 7857.22 | Unknown | 929.91 | 7039.6 | -6109.69 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-29 | 2025-04-15 | 169 | 121 | 2025-04-15 | 2025-04-15 | 1 | 1 | 1 | 1 | 170 | 122 | 171 | 123 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-21 | -72 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1470.85 | Unknown | Unknown | Unknown | -1599 | 128.15 | Unknown | 1599.33 | -1470.85 | 3070.18 | Yes | N/A | N/A | 2024-08-27 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-10-03 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-03-10 | 1 | 1 | 0 | 0 | 53 | 39 | 53 | 39 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -397 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1847.41 | Unknown | Unknown | Unknown | 32.24 | 1815.17 | 3981 | 1728.05 | 1847.41 | -119.36 | Yes | N/A | N/A | 2024-10-14 | 2024-11-07 | 25 | 19 | 2024-11-07 | 2024-11-25 | 19 | 13 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-24 | 2025-04-25 | 153 | 110 | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-25 | 2025-04-30 | 6 | 4 | 2025-04-30 | 2025-04-29 | Unknown | Unknown | 178 | 129 | 25 | 17 | 203 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | -573.81 | 252.46 | Unknown | Unknown | -1292 | 465.73 | Unknown | 1292.04 | -573.81 | 1865.85 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-08 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-13 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-15 | 3 | 3 | 2023-12-15 | 2023-12-15 | 1 | 1 | 40 | 30 | 5 | 5 | 45 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1682.05 | 1682.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-11-28 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1264.58 | -0.94 | Unknown | Unknown | 16.3 | 1249.22 | 3981 | 806.87 | 1264.58 | -457.71 | Yes | N/A | N/A | 2024-02-06 | 2024-03-07 | 31 | 23 | 2024-03-07 | 2024-03-18 | 12 | 8 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-08 | 1 | 1 | 31 | 23 | 13 | 9 | 44 | 32 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-08 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-06 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 4173.4 | 1352.08 | Unknown | Unknown | -1499 | 4320.32 | Unknown | 1499.44 | 4173.4 | -2673.96 | Yes | N/A | N/A | 2023-10-04 | 2025-02-12 | 498 | 356 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-03-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-05-01 | 58 | 42 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-05-01 | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 578 | 414 | 2 | 2 | 580 | 416 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9512 | 9512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-04-03 | 393 | 282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 680.67 | -13.66 | Unknown | Unknown | 0.67 | 693.66 | 15924 | 1137.58 | 680.67 | 456.91 | Yes | N/A | N/A | 2024-06-14 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2025-04-11 | 599 | 429 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-01 | Unknown | Unknown | 0 | 0 | 599 | 429 | 599 | 429 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -205 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | -1335.45 | 63 | Unknown | Unknown | -1470 | 71.55 | Unknown | Not available | -1335.45 | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-02-16 | 26 | 18 | 2025-02-16 | 2025-03-11 | 24 | 17 | 2025-03-11 | 2025-04-11 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-13 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-11 | 30 | 22 | 2025-06-11 | 2025-06-06 | Unknown | Unknown | 91 | 65 | 54 | 39 | 145 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 301.05 | 301.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-03-07 | 2023-06-09 | IOU Designed & Installed | N/A | No | N/A | 4488.63 | Unknown | Unknown | Unknown | -354 | 4842.63 | 3981 | 759.7 | 4488.63 | -3728.93 | Yes | N/A | N/A | 2023-01-23 | 2023-03-07 | 44 | 32 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-04-04 | 2023-06-09 | 67 | 49 | Unknown | 2023-04-05 | Unknown | Unknown | 2023-06-09 | 2023-07-03 | 25 | 17 | 2023-07-03 | 2023-06-23 | Unknown | Unknown | 111 | 81 | 26 | 18 | 137 | 99 | Steps 2,3,5,6,7 | 45 | 33 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10.35 | 10.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-09 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 12.08 | Unknown | Unknown | Unknown | Unknown | 12.08 | Unknown | 1677.82 | 12.08 | 1665.74 | Yes | N/A | N/A | 2024-11-25 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-06 | 23 | 17 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-01-28 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-06 | 10 | 8 | 2025-02-06 | 2025-02-06 | 1 | 1 | 51 | 37 | 34 | 26 | 85 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 2116 | 1513 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-06-27 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 5835.62 | 861.63 | Unknown | 1120.74 | 24.36 | 3828.89 | 19905 | 2884.93 | 5835.62 | -2950.69 | Yes | N/A | N/A | 2024-04-05 | 2024-06-27 | 84 | 60 | 2024-06-27 | 2024-08-14 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-27 | 32 | 23 | 2024-08-14 | 2024-08-28 | 15 | 11 | Unknown | 2024-09-03 | Unknown | Unknown | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2024-10-16 | 1 | 1 | 99 | 71 | 83 | 60 | 182 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-10-07 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 1765.44 | 844.83 | Unknown | 388.93 | -2024 | 2555.68 | Unknown | 2023.96 | 1765.44 | 258.52 | Yes | N/A | N/A | 2024-08-21 | 2024-10-02 | 43 | 31 | 2024-10-02 | 2024-10-29 | 28 | 20 | 2024-10-16 | 2024-10-22 | 7 | 5 | 2024-10-22 | 2024-10-29 | 8 | 6 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-02-21 | 2025-02-24 | 4 | 2 | 2025-02-24 | 2025-02-24 | 1 | 1 | 50 | 36 | 41 | 29 | 91 | 65 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 54.29 | Unknown | Unknown | Unknown | Unknown | 54.29 | 3981 | 1138.17 | 54.29 | 1083.88 | Yes | N/A | N/A | 2025-01-02 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2025-01-02 | 4 | 4 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-03-03 | 47 | 33 | 2025-03-03 | 2025-03-03 | 1 | 1 | 15 | 11 | 52 | 38 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 45.74 | Unknown | Unknown | Unknown | Unknown | 45.74 | 3981 | 1514.24 | 45.74 | 1468.5 | Yes | N/A | N/A | 2024-08-30 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-09-16 | 43 | 31 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2025-01-15 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-24 | 10 | 8 | 2025-01-24 | 2025-01-24 | 1 | 1 | 122 | 88 | 54 | 40 | 176 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-10 | -236 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | -172.46 | -9.47 | Unknown | Unknown | -641 | 478.01 | Unknown | 641.08 | -172.46 | 813.54 | Yes | N/A | N/A | 2023-09-25 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-09-25 | 15 | 11 | 2023-09-25 | 2023-10-11 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-01 | 21 | 15 | Unknown | 2023-10-31 | Unknown | Unknown | 2023-11-01 | 2023-11-17 | 17 | 13 | 2023-11-17 | 2023-11-17 | 1 | 1 | 38 | 28 | 33 | 25 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 146.8 | -2.5 | Unknown | Unknown | Unknown | 149.3 | 3981 | 1561.26 | 146.8 | 1414.46 | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-12-12 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-15 | 35 | 25 | 2025-01-15 | 2025-01-15 | 1 | 1 | 40 | 30 | 37 | 27 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-11-20 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 622.56 | -22.11 | Unknown | Unknown | Unknown | 644.67 | Unknown | 842.62 | 622.56 | 220.06 | Yes | N/A | N/A | 2023-10-05 | 2023-11-20 | 47 | 33 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-01-26 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-07 | 13 | 9 | 2024-02-07 | 2024-02-07 | 1 | 1 | 115 | 83 | 15 | 11 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | 58 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11.48 | Unknown | Unknown | Unknown | Unknown | 11.48 | 0 | 239.38 | 11.48 | 227.9 | Yes | N/A | N/A | 2023-08-15 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-10-02 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 0 | 0 | 210 | 150 | 210 | 150 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | Unknown | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 1654.87 | -32.78 | Unknown | Unknown | Unknown | 1687.65 | 3981 | 1745.58 | 1654.87 | 90.71 | Yes | N/A | N/A | 2024-10-25 | 2024-10-25 | 1 | 1 | 2024-10-25 | 2024-10-25 | 1 | 1 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-10-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-05 | 12 | 8 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2 | 2 | 14 | 10 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -526 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-23 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | -2.12 | -8.9 | Unknown | Unknown | Unknown | 6.78 | Unknown | 2204.23 | -2.12 | 2206.35 | Yes | N/A | N/A | 2024-12-12 | 2024-12-11 | Unknown | Unknown | 2024-12-11 | 2024-12-23 | 13 | 9 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-03-10 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-27 | 18 | 14 | 2025-03-27 | 2025-03-27 | 1 | 1 | 78 | 56 | 32 | 24 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -124 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1182.37 | 1438.01 | Unknown | 311.93 | -1303 | 735.43 | Unknown | 1303.21 | 1182.37 | 120.84 | Yes | N/A | N/A | 2023-12-04 | 2023-12-04 | 1 | 1 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-21 | 203 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-13 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1192.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-12-13 | 19 | 15 | 2024-12-13 | 2025-03-28 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-12 | 33 | 23 | 2025-05-12 | 2025-05-12 | 1 | 1 | 120 | 86 | 53 | 39 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 1973.25 | 1973.25 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-06-28 | 400 | 287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-09 | 2022-12-09 | 2024-07-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 12089.32 | Unknown | Unknown | Unknown | 1379.82 | 10709.5 | 22200.58 | 3093 | 12089.32 | -8996.32 | Yes | N/A | N/A | 2022-11-09 | 2023-07-07 | 241 | 173 | 2023-07-07 | 2023-10-09 | 95 | 67 | 2023-06-16 | 2023-10-03 | 35 | 25 | 2023-02-18 | 2023-10-16 | 24 | 16 | 2024-01-16 | Unknown | Unknown | Unknown | 2024-01-16 | 2024-08-26 | 224 | 160 | 2024-07-11 | 2024-08-01 | 22 | 16 | 2024-08-01 | 2024-08-01 | 1 | 1 | 276 | 198 | 366 | 260 | 642 | 458 | Steps 2,3,5,6,7 | 388 | 274 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -426 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-22 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 615.81 | Unknown | Unknown | Unknown | -276.07 | 891.88 | 3981 | 1213.24 | 615.81 | 597.43 | Yes | N/A | N/A | 2025-01-14 | 2025-02-21 | 39 | 29 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | 2025-03-27 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-28 | 36 | 26 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-28 | 2025-04-21 | 25 | 17 | 2025-04-21 | 2025-04-18 | Unknown | Unknown | 110 | 80 | 26 | 18 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 443.5 | 443.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | -243 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2025-02-26 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 7216.19 | Unknown | Unknown | Unknown | Unknown | 7216.19 | 7962 | 2606.44 | 7216.19 | -4609.75 | Yes | N/A | N/A | 2024-12-09 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2025-03-27 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-06-16 | 77 | 55 | 2025-06-16 | 2025-06-16 | 1 | 1 | 0 | 0 | 242 | 174 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 9.7 | Unknown | Unknown | Unknown | Unknown | 9.7 | 3981 | 1372.72 | 9.7 | 1363.02 | Yes | N/A | N/A | 2024-08-13 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-14 | 6 | 4 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-11 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-17 | 7 | 5 | 2024-09-17 | 2024-09-17 | 1 | 1 | 30 | 22 | 14 | 10 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -515 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 1046.41 | 253.76 | Unknown | Unknown | Unknown | 792.65 | Unknown | 1882.99 | 1046.41 | 836.58 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-25 | 43 | 31 | 2025-02-25 | 2025-02-25 | 1 | 1 | 7 | 5 | 45 | 33 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-12-05 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | -174.39 | -17.41 | Unknown | Unknown | -1041 | 884.02 | Unknown | 1478.26 | -174.39 | 1652.65 | Yes | N/A | N/A | 2024-10-30 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-03-12 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-04-01 | 21 | 15 | 2025-04-01 | 2025-03-21 | Unknown | Unknown | 86 | 62 | 21 | 15 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 374.59 | -22.86 | Unknown | Unknown | Unknown | 397.45 | 3981 | 983.72 | 374.59 | 609.13 | Yes | N/A | N/A | 2023-11-27 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-11-27 | 117 | 83 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-01-16 | 51 | 37 | Unknown | 2024-02-12 | Unknown | Unknown | 2024-01-16 | 2024-02-13 | 29 | 21 | 2024-02-13 | 2024-02-13 | 1 | 1 | 51 | 37 | 147 | 105 | 198 | 142 | Steps 2,3,5,6,7 | 27 | 19 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | Poway | POWAY | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | 216 | 155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2022-08-11 | 2024-09-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 40612.03 | 9536.06 | Unknown | Unknown | -39469 | 70544.97 | 0 | 40713.13 | 40612.03 | 101.1 | Yes | N/A | N/A | 2022-08-11 | 2024-01-03 | 511 | 365 | 2024-01-03 | 2024-08-26 | 237 | 169 | 2024-02-05 | 2024-06-20 | 137 | 99 | 2024-06-18 | 2025-02-12 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2025-03-05 | 182 | 130 | 2025-03-05 | 2025-03-05 | 1 | 1 | 648 | 464 | 459 | 329 | 1107 | 793 | Steps 2,3,5,6,7 | 205 | 147 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | -557 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-08 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 105.43 | -0.94 | Unknown | Unknown | Unknown | 106.37 | Unknown | 1675.34 | 105.43 | 1569.91 | Yes | N/A | N/A | 2024-07-30 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-08-23 | 58 | 42 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-25 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-01 | 7 | 5 | 2024-10-01 | 2024-10-01 | 1 | 1 | 34 | 24 | 66 | 48 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 89.42 | Unknown | Unknown | Unknown | Unknown | 89.42 | Unknown | 1884.97 | 89.42 | 1795.55 | Yes | N/A | N/A | 2024-09-26 | 2024-10-18 | 23 | 17 | 2024-10-18 | 2024-11-26 | 40 | 28 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-02-05 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-10 | 34 | 24 | 2025-03-10 | 2025-03-10 | 1 | 1 | 95 | 69 | 75 | 53 | 170 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-01 | 821 | 588 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 31.74 | Unknown | Unknown | Unknown | Unknown | 31.74 | 19393 | 425.65 | 31.74 | 393.91 | Yes | N/A | N/A | 2023-08-17 | 2023-10-17 | 62 | 44 | 2023-10-17 | 2023-10-19 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-08-23 | 310 | 222 | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-08-30 | Unknown | Unknown | 372 | 266 | 3 | 3 | 375 | 269 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | -406 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 814.41 | -15.29 | Unknown | Unknown | Unknown | 829.7 | Unknown | 3931.45 | 814.41 | 3117.04 | Yes | N/A | N/A | 2024-04-05 | 2024-06-04 | 61 | 43 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-12 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-05 | 1 | 1 | 61 | 43 | 33 | 25 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 1076.37 | -20.4 | Unknown | Unknown | 9.29 | 1087.48 | Unknown | 939.41 | 1076.37 | -136.96 | Yes | N/A | N/A | 2024-05-20 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-20 | 48 | 34 | 2024-05-20 | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-03 | 13 | 9 | 2024-05-20 | 2024-07-08 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-09-13 | 68 | 50 | 2024-09-13 | 2024-09-13 | 1 | 1 | 50 | 36 | 130 | 94 | 180 | 130 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 459.26 | -8.74 | Unknown | Unknown | Unknown | 468 | Unknown | 1656 | 459.26 | 1196.74 | Yes | N/A | N/A | 2024-12-09 | 2024-12-17 | 9 | 7 | 2024-12-17 | 2025-02-14 | 60 | 44 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-04 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-04-09 | 37 | 27 | 2025-04-09 | 2025-04-09 | 1 | 1 | 28 | 20 | 98 | 72 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -632 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2016.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-05-06 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-29 | 24 | 18 | 2025-05-29 | 2025-05-29 | 1 | 1 | 65 | 47 | 26 | 20 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 246 | 246 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 887.96 | 280.92 | Unknown | 114.54 | Unknown | 492.5 | Unknown | 1482.13 | 887.96 | 594.17 | Yes | N/A | N/A | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-06-23 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-27 | 5 | 3 | 2023-06-27 | 2023-06-27 | 1 | 1 | 10 | 8 | 6 | 4 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 1311.06 | Unknown | Unknown | Unknown | 14.14 | 1296.92 | 3981 | 1158.4 | 1311.06 | -152.66 | Yes | N/A | N/A | 2024-10-17 | 2024-10-24 | 8 | 6 | 2024-10-24 | 2024-11-11 | 19 | 13 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-04-16 | 157 | 113 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-04-16 | 2025-04-28 | 13 | 9 | 2025-04-28 | 2025-04-28 | 1 | 1 | 165 | 119 | 33 | 23 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -380 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 1829.18 | -7.14 | Unknown | Unknown | 12.57 | 1823.75 | 3981 | 760.44 | 1829.18 | -1068.74 | Yes | N/A | N/A | 2023-12-20 | 2023-12-29 | 10 | 8 | 2023-12-29 | 2024-01-12 | 15 | 11 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-06-19 | 160 | 114 | Unknown | 2024-06-17 | Unknown | Unknown | 2024-06-19 | 2024-07-10 | 22 | 16 | 2024-07-10 | 2024-07-10 | 1 | 1 | 170 | 122 | 38 | 28 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Ramona | N/A | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-10 | 62 | 45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-30 | 2024-08-17 | IOU Designed & Installed | N/A | No | N/A | 20451.54 | 10369.01 | Unknown | Unknown | -19009.98 | 29092.51 | 3194.59 | 22231.68 | 20451.54 | 1780.14 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2024-03-27 | 122 | 88 | 2024-02-08 | 2023-12-12 | Unknown | Unknown | 2024-02-22 | 2024-08-05 | 166 | 118 | 2024-03-27 | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-30 | 51 | 37 | 2024-08-17 | 2024-10-11 | 56 | 40 | 2024-10-11 | 2024-10-11 | 1 | 1 | 1 | 1 | 396 | 284 | 397 | 285 | Steps 2,3,5,6,7 | 179 | 127 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 193.37 | 1673.73 | Unknown | 374.43 | -2516 | 661.21 | 0 | 2515.62 | 193.37 | 2322.25 | Yes | N/A | N/A | 2023-03-22 | 2023-03-17 | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | 480 | 480 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 297 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-16 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 7951.26 | Unknown | Unknown | Unknown | Unknown | 7951.26 | Unknown | 662.64 | 7951.26 | -7288.62 | Yes | N/A | N/A | 2024-05-10 | 2024-06-12 | 34 | 24 | 2024-06-12 | 2024-06-20 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-23 | 7 | 5 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-15 | 25 | 17 | 2024-07-15 | 2024-07-15 | 1 | 1 | 34 | 24 | 42 | 30 | 76 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -620 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-09 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | -433.95 | Unknown | Unknown | Unknown | -486 | 52.05 | 3981 | 1249.06 | -433.95 | 1683.01 | Yes | N/A | N/A | 2024-08-02 | 2024-08-05 | 4 | 2 | 2024-08-05 | 2024-08-09 | 5 | 5 | 2024-08-09 | 2024-08-21 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-10-01 | 42 | 30 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-10-01 | 2024-10-07 | 7 | 5 | 2024-10-07 | 2024-10-07 | 1 | 1 | 59 | 41 | 13 | 11 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | 66 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4314.36 | 3950.93 | Unknown | 593.52 | -1889 | 1658.91 | 0 | 1889.35 | 4314.36 | -2425.01 | Yes | N/A | N/A | 2023-06-02 | 2023-06-03 | 2 | 1 | 2023-06-03 | 2023-06-19 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2 | 1 | 18 | 12 | 20 | 13 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 2240.08 | 727.28 | Unknown | 162.32 | Unknown | 1350.48 | 3981 | 881.82 | 2240.08 | -1358.26 | Yes | N/A | N/A | 2023-12-11 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-12-14 | 121 | 87 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2023-12-26 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-09 | 15 | 11 | 2024-01-09 | 2024-01-09 | 1 | 1 | 13 | 9 | 137 | 99 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -246 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-06-12 | IOU Designed & Installed | N/A | No | N/A | 2611.63 | 739.65 | Unknown | Unknown | 19.39 | 1852.59 | 3981 | 381.26 | 2611.63 | -2230.37 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-06-12 | 109 | 77 | Unknown | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-07-06 | 25 | 19 | 2023-07-06 | 2023-06-23 | Unknown | Unknown | 110 | 78 | 25 | 19 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -471 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 2215.21 | 731.47 | Unknown | Unknown | Unknown | 1483.74 | Unknown | 1239.29 | 2215.21 | -975.92 | Yes | N/A | N/A | 2024-03-28 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-04-24 | 134 | 96 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-13 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-30 | 18 | 14 | 2024-05-30 | 2024-05-30 | 1 | 1 | 20 | 14 | 153 | 111 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.4 | 48.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -124 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -14.31 | -6.81 | Unknown | Unknown | Unknown | -7.5 | 3241 | 501.14 | -14.31 | 515.45 | Yes | N/A | N/A | 2023-03-28 | 2023-08-30 | 156 | 112 | 2023-08-30 | 2024-02-06 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 156 | 112 | 162 | 116 | 318 | 228 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.45 | -3.94 | Unknown | Unknown | Unknown | -1.51 | Unknown | 363.72 | -5.45 | 369.17 | Yes | N/A | N/A | 2023-02-09 | 2023-02-10 | 2 | 2 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -638 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 330.43 | 144.44 | Unknown | Unknown | Unknown | 185.99 | 3961 | 192.95 | 330.43 | -137.48 | Yes | N/A | N/A | 2024-07-11 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-07-29 | 56 | 40 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-02 | 5 | 5 | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-23 | 22 | 16 | 2024-08-23 | 2024-08-23 | 1 | 1 | 5 | 5 | 79 | 57 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | 108 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-26 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 2559.4 | 242.49 | Unknown | Unknown | -10031 | 12347.91 | Unknown | 12615.1 | 2559.4 | 10055.7 | Yes | N/A | N/A | 2024-02-05 | 2024-06-18 | 135 | 97 | 2024-06-18 | 2024-07-12 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-07-12 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-09-23 | 71 | 51 | 2024-09-23 | 2024-09-23 | 1 | 1 | 135 | 97 | 197 | 143 | 332 | 240 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 2575.32 | 502.72 | Unknown | 23.75 | Unknown | 2048.85 | 3981 | 1120.15 | 2575.32 | -1455.17 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | 2024-07-18 | 108 | 78 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-09-16 | 61 | 43 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-16 | 2024-09-18 | 3 | 3 | 2024-09-18 | 2024-09-18 | 1 | 1 | 62 | 44 | 112 | 82 | 174 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -339 | -244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 917.64 | -0.31 | Unknown | Unknown | 44.46 | 873.49 | 15924 | 1926.29 | 917.64 | 1008.65 | Yes | N/A | N/A | 2024-05-29 | 2024-09-12 | 107 | 77 | 2024-09-12 | 2024-10-03 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-09-22 | 2024-10-24 | 33 | 24 | 2024-10-03 | 2025-03-11 | 160 | 114 | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 267 | 191 | 55 | 40 | 322 | 231 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 767.81 | -15.43 | Unknown | Unknown | Unknown | 783.24 | Unknown | 1250.85 | 767.81 | 483.04 | Yes | N/A | N/A | 2025-05-07 | 2025-04-25 | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-04 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-05 | 2 | 2 | 2025-06-05 | 2025-06-05 | 1 | 1 | 29 | 21 | 3 | 3 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-25 | -249 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-07 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 0.22 | -5.88 | Unknown | Unknown | Unknown | 6.1 | 3981 | 840.18 | 0.22 | 839.96 | Yes | N/A | N/A | 2023-09-05 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-07 | 72 | 52 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-10-20 | 30 | 22 | 2023-10-20 | 2023-10-20 | 1 | 1 | 15 | 11 | 103 | 75 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -617 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 1378.97 | Unknown | Unknown | Unknown | 11.68 | 1367.29 | 3981 | 1336.34 | 1378.97 | -42.63 | Yes | N/A | N/A | 2024-07-16 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-07-30 | 35 | 25 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-19 | 52 | 38 | Unknown | 2024-10-02 | Unknown | Unknown | 2024-09-19 | 2024-10-11 | 23 | 17 | 2024-10-11 | 2024-10-11 | 1 | 1 | 52 | 38 | 59 | 43 | 111 | 81 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-10 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 35.87 | Unknown | Unknown | Unknown | Unknown | 35.87 | Unknown | 1826.16 | 35.87 | 1790.29 | Yes | N/A | N/A | 2025-01-02 | 2025-01-10 | 9 | 7 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-13 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-26 | 45 | 33 | 2025-02-26 | 2025-02-26 | 1 | 1 | 13 | 9 | 47 | 35 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | -734.13 | 253.74 | Unknown | Unknown | -1729 | 741.13 | Unknown | 1602.66 | -734.13 | 2336.79 | Yes | N/A | N/A | 2024-09-05 | 2024-10-10 | 36 | 26 | 2024-10-10 | 2024-11-22 | 44 | 32 | 2024-11-22 | 2025-01-09 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-23 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-03 | 12 | 8 | 2025-02-03 | 2025-02-03 | 1 | 1 | 100 | 72 | 57 | 41 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-09-11 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 2905.11 | Unknown | Unknown | Unknown | 29.58 | 2875.53 | 3981 | 1098.48 | 2905.11 | -1806.63 | Yes | N/A | N/A | 2024-07-12 | 2024-09-06 | 57 | 41 | 2024-09-06 | 2024-09-10 | 5 | 3 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-12-31 | 110 | 78 | Unknown | 2024-12-09 | Unknown | Unknown | 2024-12-31 | 2025-01-23 | 24 | 18 | 2025-01-23 | 2025-01-23 | 1 | 1 | 167 | 119 | 30 | 22 | 197 | 141 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2025-05-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 22890.06 | 179.83 | Unknown | Unknown | 21.5 | 22688.73 | Unknown | 12851.75 | 22890.06 | -10038.31 | Yes | N/A | N/A | 2024-07-11 | 2025-04-07 | 271 | 193 | 2025-04-07 | 2025-04-22 | 16 | 12 | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-09 | 2025-04-30 | 20 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-10 | 27 | 19 | 2025-06-10 | 2025-06-10 | 1 | 1 | 272 | 194 | 64 | 44 | 336 | 238 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 214.2 | 123.34 | Unknown | Unknown | Unknown | 90.86 | Unknown | 153.49 | 214.2 | -60.71 | Yes | N/A | N/A | 2024-01-04 | 2024-01-19 | 16 | 12 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-07-03 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-08 | 6 | 4 | 2024-07-08 | 2024-07-08 | 1 | 1 | 183 | 131 | 8 | 6 | 191 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -557 | -400 | No | 2024-09-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2024-11-01 | IOU Designed & Installed | N/A | Yes | 70 | 124.85 | Unknown | Unknown | Unknown | 3.45 | 121.4 | 3981 | 190.44 | 124.85 | 65.59 | Yes | N/A | N/A | 2024-09-25 | 2024-12-03 | 70 | 50 | 2024-12-03 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-01-27 | 88 | 62 | 2025-01-27 | 2025-01-27 | 1 | 1 | 71 | 51 | 89 | 63 | 160 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -88 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | 2023-12-01 | IOU Designed & Installed | N/A | No | N/A | 2204.56 | 774.99 | Unknown | Unknown | Unknown | 1429.57 | 3981 | 627.74 | 2204.56 | -1576.82 | Yes | N/A | N/A | 2023-05-01 | 2023-06-09 | 40 | 30 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-12-01 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-04 | 4 | 2 | 2023-12-04 | 2023-12-04 | 1 | 1 | 216 | 156 | 5 | 3 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-03 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 12.68 | -11.23 | Unknown | Unknown | Unknown | 23.91 | Unknown | 856.76 | 12.68 | 844.08 | Yes | N/A | N/A | 2024-05-02 | 2024-05-03 | 2 | 2 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-24 | 46 | 32 | 2024-06-24 | 2024-06-24 | 1 | 1 | 10 | 8 | 48 | 34 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-16 | 957 | 684 | No | 2024-02-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | Unknown | IOU Designed & Installed | N/A | Yes | 266 | 55.71 | Unknown | Unknown | Unknown | Unknown | 55.71 | 3941 | 1842.15 | 55.71 | 1786.44 | Yes | N/A | N/A | 2024-02-13 | 2024-12-01 | 293 | 209 | 2024-12-01 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-08-20 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-02-27 | 73 | 53 | 483 | 345 | 73 | 53 | 556 | 398 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -296 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 39.15 | Unknown | Unknown | Unknown | 3.32 | 35.83 | 3981 | 1022.87 | 39.15 | 983.72 | Yes | N/A | N/A | 2024-05-07 | 2024-05-07 | 1 | 1 | 2024-05-07 | 2024-05-07 | 1 | 1 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-11-06 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-02-26 | 113 | 81 | 2025-02-26 | 2025-02-26 | 1 | 1 | 185 | 133 | 115 | 83 | 300 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | -536 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 4377.99 | 1525.39 | Unknown | 350.27 | -903 | 3405.33 | Unknown | 629.36 | 4377.99 | -3748.63 | Yes | N/A | N/A | 2023-08-23 | 2023-05-24 | Unknown | Unknown | 2023-05-24 | 2023-09-11 | 111 | 79 | 2023-09-11 | 2023-10-23 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-23 | 40 | 28 | Unknown | 2023-10-19 | Unknown | Unknown | 2023-10-23 | 2023-10-31 | 9 | 7 | 2023-10-31 | 2023-10-31 | 1 | 1 | 83 | 59 | 121 | 87 | 204 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | 260 | 187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 309.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-03-28 | 21 | 15 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 0 | 0 | 22 | 16 | 22 | 16 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 528.66 | -10.2 | Unknown | Unknown | Unknown | 538.86 | 3981 | 1656.91 | 528.66 | 1128.25 | Yes | N/A | N/A | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-23 | 9 | 7 | 2025-01-23 | 2025-01-16 | Unknown | Unknown | 3 | 3 | 10 | 8 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 187 | 187 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | -207 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-26 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 826.1 | Unknown | Unknown | Unknown | 4.65 | 821.45 | 3981 | 969.31 | 826.1 | 143.21 | Yes | N/A | N/A | 2023-05-10 | 2023-07-12 | 64 | 46 | 2023-07-12 | 2023-07-21 | 10 | 8 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2024-08-22 | 455 | 325 | Unknown | 2024-06-10 | Unknown | Unknown | 2024-08-22 | 2024-08-26 | 5 | 3 | 2024-08-26 | 2024-08-23 | Unknown | Unknown | 519 | 371 | 15 | 11 | 534 | 382 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-18 | 862 | 617 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-19 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 9090.46 | Unknown | Unknown | Unknown | Unknown | 9090.46 | 7962 | 1156.7 | 9090.46 | -7933.76 | Yes | N/A | N/A | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | 2024-03-19 | 5 | 3 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-08-09 | 144 | 104 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-04 | 27 | 19 | 2024-09-04 | 2024-08-27 | Unknown | Unknown | 145 | 105 | 32 | 22 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-07 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | 1916.79 | Unknown | Unknown | Unknown | 42.87 | 1873.92 | 3981 | 445.2 | 1916.79 | -1471.59 | Yes | N/A | N/A | 2024-05-06 | 2024-05-07 | 2 | 2 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2025-06-20 | 410 | 294 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-06-20 | 2025-06-20 | 1 | 1 | 412 | 296 | 2 | 2 | 414 | 298 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 493 | 352 | No | 2022-03-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-04 | Unknown | 2024-04-09 | IOU Designed & Installed | N/A | Yes | 780 | 648.29 | -30.55 | Unknown | Unknown | 0.62 | 678.22 | 3981 | 2082.25 | 648.29 | 1433.96 | Yes | N/A | N/A | 2022-03-04 | 2024-04-22 | 781 | 557 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-03-10 | 2024-04-09 | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-05-07 | 29 | 21 | 2024-05-07 | 2024-05-07 | 1 | 1 | 781 | 557 | 30 | 22 | 811 | 579 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Rancho Santa Fe | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 321 | 230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2024-03-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 95218.77 | 28519.55 | Unknown | Unknown | -7481.3 | 74180.52 | 0 | 18647.48 | 95218.77 | -76571.29 | Yes | N/A | N/A | 2023-02-09 | 2023-05-01 | 82 | 58 | 2023-05-01 | 2023-09-26 | 149 | 107 | 2023-06-21 | 2024-02-12 | 66 | 46 | 2023-09-20 | 2023-09-26 | 7 | 5 | 2023-12-01 | Unknown | Unknown | Unknown | 2023-12-01 | 2024-03-20 | 111 | 79 | 2024-03-25 | 2024-04-17 | 24 | 18 | 2024-04-17 | 2024-04-17 | 1 | 1 | 148 | 104 | 292 | 210 | 440 | 314 | Steps 2,3,5,6,7 | 242 | 172 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | 44 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-10-17 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | 5948.42 | 35.61 | Unknown | Unknown | Unknown | 5912.81 | Unknown | 7735.67 | 5948.42 | 1787.25 | Yes | N/A | N/A | 2023-08-28 | 2023-10-30 | 64 | 46 | 2023-10-30 | 2023-11-22 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-25 | 44 | 32 | 2024-01-25 | 2024-01-25 | 1 | 1 | 64 | 46 | 69 | 51 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1636 | 1169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 5740.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-16 | 1 | 1 | 2025-04-16 | 2025-06-11 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-01 | 14 | 10 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 1 | 1 | 74 | 54 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-15 | 615 | 440 | No | 2022-05-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-11 | 2022-05-11 | Unknown | IOU Designed & Installed | N/A | Yes | 443 | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3885 | 949.81 | Unknown | 949.81 | Yes | N/A | N/A | 2022-05-11 | 2023-07-28 | 444 | 318 | 2023-07-28 | 2023-07-28 | 1 | 1 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-19 | 1 | 1 | 444 | 318 | 2 | 2 | 446 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -521 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | 2024-12-26 | 2025-01-03 | IOU Designed & Installed | N/A | No | N/A | 558.48 | -10.2 | Unknown | Unknown | 3.23 | 565.45 | 3281 | 1239.56 | 558.48 | 681.08 | Yes | N/A | N/A | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-03 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-02-20 | 49 | 35 | 2025-02-20 | 2025-02-20 | 1 | 1 | 10 | 8 | 51 | 37 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 92.75 | 92.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 544 | 389 | No | 2022-10-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2022-10-21 | 2024-07-25 | IOU Designed & Installed | N/A | Yes | 614 | 920.18 | 483.36 | Unknown | Unknown | Unknown | 436.82 | 3885 | 728.77 | 920.18 | -191.41 | Yes | N/A | N/A | 2022-10-21 | 2024-06-26 | 615 | 439 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-07-30 | 6 | 4 | 2024-07-30 | 2024-07-29 | Unknown | Unknown | 617 | 441 | 6 | 4 | 623 | 445 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-17 | -541 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-12-18 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 13671.07 | 5936.92 | Unknown | Unknown | Unknown | 7734.15 | Unknown | 1130.91 | 13671.07 | -12540.16 | Yes | N/A | N/A | 2023-11-07 | 2023-12-12 | 36 | 26 | 2023-12-12 | 2023-12-18 | 7 | 5 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-02-07 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-23 | 17 | 13 | 2024-02-23 | 2024-02-23 | 1 | 1 | 88 | 64 | 25 | 19 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -592 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-28 | Unknown | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.03 | Unknown | Unknown | Unknown | 6.21 | -6.24 | 3981 | 341.61 | -0.03 | 341.64 | Yes | N/A | N/A | 2024-12-28 | 2025-01-23 | 27 | 19 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 27 | 19 | 2 | 2 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 1143.12 | -34.39 | Unknown | Unknown | Unknown | 1177.51 | Unknown | 856.04 | 1143.12 | -287.08 | Yes | N/A | N/A | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | 2023-10-12 | 115 | 83 | 2023-10-12 | Unknown | Unknown | Unknown | 2023-06-20 | 2023-07-31 | 42 | 30 | 2023-06-20 | 2023-10-12 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-25 | 14 | 10 | 2023-10-25 | 2023-10-25 | 1 | 1 | 116 | 84 | 172 | 124 | 288 | 208 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 595 | 426 | No | 2022-05-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-24 | 2024-10-16 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 475 | 69635 | 2576.41 | Unknown | Unknown | 8269.44 | 58789.15 | 0 | 26763.5 | 69635 | -42871.5 | Yes | N/A | N/A | 2022-04-27 | 2023-08-27 | 488 | 348 | 2023-08-27 | 2024-04-16 | 234 | 167 | 2023-05-01 | 2024-04-11 | 150 | 106 | 2023-09-11 | 2024-05-05 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | 2024-10-16 | 2024-11-04 | 20 | 14 | 2024-11-04 | 2024-11-04 | 1 | 1 | 638 | 454 | 284 | 203 | 922 | 657 | Steps 2,3,5,6,7 | 564 | 404 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -696 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 5667.48 | 1669.44 | Unknown | 855.44 | Unknown | 3142.6 | 3981 | 838.74 | 5667.48 | -4828.74 | Yes | N/A | N/A | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-10 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-18 | 9 | 7 | 2023-10-18 | 2023-10-18 | 1 | 1 | 28 | 20 | 11 | 9 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | 147 | 147 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-04-02 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 17153.13 | 4200.25 | Unknown | Unknown | -22268.46 | 35221.34 | 2555.31 | 47123.94 | 17153.13 | 29970.81 | Yes | N/A | N/A | 2024-02-01 | 2024-03-01 | 30 | 22 | 2024-03-01 | 2024-10-25 | 239 | 171 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-09-04 | 2024-10-07 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-01-15 | 77 | 55 | 2025-01-15 | 2025-01-15 | 1 | 1 | 31 | 23 | 336 | 240 | 367 | 263 | Steps 2,3,5,6,7 | 51 | 37 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | -486 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 100.05 | -9.05 | Unknown | Unknown | Unknown | 109.1 | Unknown | 148.7 | 100.05 | 48.65 | Yes | N/A | N/A | 2023-08-03 | 2023-08-19 | 17 | 12 | 2023-08-19 | 2023-08-19 | 1 | 0 | 2023-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-19 | 2024-01-09 | 144 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-11 | 3 | 3 | 2024-01-11 | 2024-01-11 | 1 | 1 | 161 | 114 | 5 | 4 | 166 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 2044 | 2044 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-01-19 | 97 | 70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 1028.95 | -39.39 | Unknown | Unknown | 62.49 | 1005.85 | 11943 | 566.54 | 1028.95 | -462.41 | Yes | N/A | N/A | 2023-05-11 | 2023-09-20 | 133 | 95 | 2023-09-20 | 2023-11-13 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-04-23 | 163 | 117 | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-24 | 2024-04-29 | 6 | 4 | 2024-04-29 | 2024-04-25 | Unknown | Unknown | 296 | 212 | 61 | 43 | 357 | 255 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 319.4 | 319.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -147 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1132.21 | -20.94 | Unknown | Unknown | Unknown | 1153.15 | 7962 | 1062.28 | 1132.21 | -69.93 | Yes | N/A | N/A | 2024-11-21 | 2024-11-22 | 2 | 2 | 2024-11-22 | 2024-11-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-07 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-04-18 | 43 | 31 | 134 | 96 | 49 | 35 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 581 | 415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 747.71 | -22.53 | Unknown | Unknown | 113.74 | 656.5 | 0 | 1748.36 | 747.71 | 1000.65 | Yes | N/A | N/A | 2023-06-09 | 2023-06-13 | 5 | 3 | 2023-06-13 | 2023-07-28 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 5 | 3 | 47 | 34 | 52 | 37 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 18.05 | 18.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -773 | -554 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | 628.35 | 7.33 | Unknown | Unknown | 8.37 | 612.65 | Unknown | 2066.35 | 628.35 | 1438 | Yes | N/A | N/A | 2023-03-08 | 2023-05-11 | 65 | 47 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-08-22 | 104 | 74 | Unknown | 2023-08-01 | Unknown | Unknown | 2023-08-22 | 2023-10-24 | 64 | 46 | 2023-10-24 | 2023-10-24 | 1 | 1 | 169 | 121 | 65 | 47 | 234 | 168 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-23 | 355 | 254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1247.25 | -6.47 | Unknown | Unknown | 64.66 | 1189.06 | 7962 | 617.43 | 1247.25 | -629.82 | Yes | N/A | N/A | 2023-09-08 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-10-27 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2024-05-01 | 188 | 134 | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-12 | Unknown | Unknown | 188 | 134 | 67 | 49 | 255 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | EN 1147-B5 solar EV (E) | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 35353.93 | 9948.84 | Unknown | Unknown | 1257.71 | 24147.38 | 1912 | 49658.91 | 35353.93 | 14304.98 | Yes | N/A | N/A | 2025-03-27 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-04-04 | 17 | 13 | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-03 | 2025-04-11 | 9 | 7 | 2025-04-18 | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-16 | 29 | 21 | 2025-05-22 | 2025-06-18 | 28 | 20 | 2025-06-18 | 2025-06-18 | 1 | 1 | 1 | 1 | 84 | 62 | 85 | 63 | Steps 2,3,5,6,7 | 2 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | 84 | 61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 10604.84 | 512.83 | Unknown | Unknown | 2.11 | 10089.9 | 3981 | 2617.04 | 10604.84 | -7987.8 | Yes | N/A | N/A | 2023-04-05 | 2023-04-28 | 24 | 18 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2024-04-22 | 361 | 257 | Unknown | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-05-16 | 25 | 19 | 2024-05-16 | 2024-05-16 | 1 | 1 | 385 | 275 | 26 | 20 | 411 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -458 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | 1007.58 | -12.64 | Unknown | Unknown | 8.69 | 1011.53 | 3981 | 813.73 | 1007.58 | -193.85 | Yes | N/A | N/A | 2023-11-22 | 2023-12-21 | 30 | 22 | 2023-12-21 | 2024-01-09 | 20 | 14 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-04-26 | 109 | 79 | Unknown | 2024-04-17 | Unknown | Unknown | 2024-04-26 | 2024-05-13 | 18 | 12 | 2024-05-13 | 2024-05-10 | Unknown | Unknown | 139 | 101 | 38 | 26 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | Escondido | COUNTY OF SAN DIEGO-NORTH of 56 | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -135 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-06-16 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 27279.16 | 6555.71 | Unknown | Unknown | -19093 | 39816.45 | 3099 | 41338.31 | 27279.16 | 14059.15 | Yes | N/A | N/A | 2023-02-23 | 2023-06-06 | 104 | 74 | 2023-06-06 | 2024-06-13 | 374 | 268 | 2023-10-23 | 2024-07-30 | 8 | 6 | 2023-10-16 | 2024-01-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-04 | 20 | 14 | 2024-09-04 | 2024-09-04 | 1 | 1 | 112 | 80 | 397 | 285 | 509 | 365 | Steps 2,3,5,6,7 | 522 | 374 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-02-22 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | -21.58 | -16.3 | Unknown | Unknown | Unknown | -5.28 | Unknown | 363.72 | -21.58 | 385.3 | Yes | N/A | N/A | 2023-02-20 | 2023-02-22 | 3 | 3 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | 2023-10-12 | 233 | 167 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-15 | 35 | 25 | 2023-11-15 | 2023-11-15 | 1 | 1 | 236 | 170 | 36 | 26 | 272 | 196 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | -114 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-16 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | -2.4 | -4.67 | Unknown | Unknown | Unknown | 2.27 | 3981 | 318.98 | -2.4 | 321.38 | Yes | N/A | N/A | 2023-03-06 | 2023-03-16 | 11 | 9 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2023-08-01 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-10 | 10 | 8 | 2023-08-10 | 2024-08-16 | 373 | 267 | 150 | 108 | 383 | 275 | 533 | 383 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -360 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 2872.43 | 973.55 | Unknown | Unknown | -644 | 2542.88 | Unknown | 662.74 | 2872.43 | -2209.69 | Yes | N/A | N/A | 2023-02-28 | 2023-04-11 | 43 | 31 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-05-30 | 50 | 36 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-05-30 | 2023-10-17 | 141 | 101 | 2023-10-17 | 2023-10-18 | 2 | 2 | 93 | 67 | 143 | 103 | 236 | 170 | Steps 2,3,5,6,7 | 122 | 88 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-26 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 3596.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-24 | 2 | 2 | 2024-09-24 | 2024-09-26 | 3 | 3 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-01-16 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-02-19 | 35 | 25 | 2025-02-19 | 2025-02-18 | Unknown | Unknown | 115 | 83 | 38 | 28 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-16 | 143 | 102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-20 | 2022-08-24 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 1270.31 | -11.77 | Unknown | Unknown | 51.69 | 1230.39 | 3885 | 529.78 | 1270.31 | -740.53 | Yes | N/A | N/A | 2022-08-20 | 2023-03-14 | 207 | 147 | 2023-03-14 | 2023-03-27 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-01-30 | 93 | 67 | 2024-01-30 | 2023-11-06 | Unknown | Unknown | 207 | 147 | 108 | 78 | 315 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | -271 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-01 | 2023-08-14 | IOU Designed & Installed | N/A | No | N/A | -6.36 | -4.61 | Unknown | Unknown | Unknown | -1.75 | Unknown | 372.29 | -6.36 | 378.65 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-08-01 | 7 | 5 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-14 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-21 | 8 | 6 | 2023-08-21 | 2023-08-21 | 1 | 1 | 15 | 11 | 16 | 12 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -570 | -407 | No | 2023-04-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-11 | 2023-06-22 | IOU Designed & Installed | N/A | Yes | 23 | 970.87 | 356.64 | Unknown | Unknown | Unknown | 614.23 | 3981 | 994.47 | 970.87 | 23.6 | Yes | N/A | N/A | 2023-04-05 | 2023-04-28 | 24 | 18 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-06-22 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-23 | 2 | 2 | 2023-06-23 | 2023-06-23 | 1 | 1 | 97 | 71 | 3 | 3 | 100 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 432 | 432 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-29 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1005.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-04-24 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-19 | 25 | 18 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-16 | 11 | 9 | 2025-05-16 | 2025-05-16 | 1 | 1 | 0 | 0 | 117 | 86 | 117 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | 187 | 134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1225.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-05 | 6 | 4 | 2025-03-05 | 2025-03-07 | 3 | 3 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 6 | 4 | 4 | 4 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-20 | 13 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 2690.96 | 1075.57 | Unknown | 183.83 | Unknown | 1431.56 | Unknown | 4798.25 | 2690.96 | 2107.29 | Yes | N/A | N/A | 2023-06-05 | 2023-03-07 | Unknown | Unknown | 2023-03-07 | 2023-06-16 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-02 | 8 | 6 | 2023-08-02 | 2023-08-02 | 1 | 1 | 0 | 0 | 111 | 81 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -248 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 3232.45 | 4228.19 | Unknown | 329.88 | -25276 | 23950.38 | Unknown | 24664.48 | 3232.45 | 21432.03 | Yes | N/A | N/A | 2023-06-23 | 2023-08-29 | 68 | 48 | 2023-08-29 | 2023-10-26 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-05 | 2 | 2 | 2023-11-08 | 2023-11-21 | 14 | 10 | 2023-11-08 | 2023-11-14 | 7 | 5 | 2024-01-09 | 2024-01-29 | 21 | 15 | 2024-01-29 | 2024-01-29 | 1 | 1 | 82 | 58 | 90 | 66 | 172 | 124 | Steps 2,3,5,6,7 | 71 | 51 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 223.25 | 223.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | -347 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-23 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 65.11 | Unknown | Unknown | Unknown | 15.5 | 49.61 | 3981 | 1594.37 | 65.11 | 1529.26 | Yes | N/A | N/A | 2024-07-30 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-08-23 | 59 | 43 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-26 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-12-18 | 115 | 83 | 2024-12-18 | 2024-09-09 | Unknown | Unknown | 4 | 2 | 174 | 126 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | 148 | 106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11027.54 | 4873.79 | Unknown | Unknown | Unknown | 6153.75 | Unknown | 1217.47 | 11027.54 | -9810.07 | Yes | N/A | N/A | 2024-12-12 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2025-01-08 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-17 | 32 | 24 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-01-27 | 1 | 1 | 0 | 0 | 67 | 49 | 67 | 49 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -319 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-27 | 2023-04-13 | IOU Designed & Installed | N/A | No | N/A | 5766.27 | 3448.91 | Unknown | 3776.77 | -3950 | 2490.59 | Unknown | 3950.18 | 5766.27 | -1816.09 | Yes | N/A | N/A | 2023-03-24 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-04-17 | 5 | 3 | 2023-04-17 | 2023-04-17 | 1 | 1 | 0 | 0 | 6 | 4 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 162.1 | 162.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-13 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 582.23 | -11.7 | Unknown | Unknown | Unknown | 593.93 | 3981 | 2296.25 | 582.23 | 1714.02 | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-02-13 | 17 | 13 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-04-23 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-04-25 | 3 | 3 | 2025-04-25 | 2025-04-24 | Unknown | Unknown | 71 | 51 | 20 | 16 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-05-09 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 1039.09 | Unknown | Unknown | Unknown | 5.11 | 1033.98 | 3961 | 1352.76 | 1039.09 | 313.67 | Yes | N/A | N/A | 2024-04-23 | 2024-07-01 | 70 | 50 | 2024-07-01 | 2024-07-16 | 16 | 12 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-09-04 | 51 | 37 | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-04 | 2024-09-17 | 14 | 10 | 2024-09-17 | 2024-09-17 | 1 | 1 | 121 | 87 | 31 | 23 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | 412 | 295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1165.79 | -40.97 | Unknown | Unknown | -1156 | 31.18 | 7432.2 | 1961.34 | -1165.79 | 3127.13 | Yes | N/A | N/A | 2023-04-21 | 2023-11-21 | 215 | 153 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 215 | 153 | 1 | 1 | 216 | 154 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -554 | -397 | No | 2023-04-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-04-13 | 2023-06-05 | IOU Designed & Installed | N/A | Yes | 39 | -11.49 | -33.99 | Unknown | Unknown | Unknown | 22.5 | Unknown | 934.88 | -11.49 | 946.37 | Yes | N/A | N/A | 2023-03-01 | 2023-05-22 | 83 | 59 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-06-05 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-06-07 | 3 | 3 | 2023-06-07 | 2023-06-07 | 1 | 1 | 137 | 97 | 4 | 4 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 2419.63 | -48.27 | Unknown | Unknown | Unknown | 2467.9 | 3981 | 1874.32 | 2419.63 | -545.31 | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-14 | 27 | 19 | 2025-01-14 | 2025-01-14 | 1 | 1 | 2 | 2 | 29 | 21 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -59 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2024-02-09 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 46245.79 | 4940.37 | Unknown | 42.95 | -17901.62 | 59164.09 | 0 | 35016.79 | 46245.79 | -11229 | Yes | N/A | N/A | 2023-11-10 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-11-04 | 363 | 259 | 2024-10-01 | 2024-10-30 | 30 | 22 | 2024-06-17 | 2024-11-12 | 12 | 10 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-01-15 | 62 | 44 | 2025-01-15 | 2025-01-15 | 1 | 1 | 30 | 22 | 438 | 314 | 468 | 336 | Steps 2,3,5,6,7 | 177 | 127 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.07 | -10.95 | Unknown | Unknown | Unknown | -1.12 | Unknown | 512.85 | -12.07 | 524.92 | Yes | N/A | N/A | 2023-04-03 | 2023-05-22 | 50 | 36 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 50 | 36 | 1 | 1 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 536 | 383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1380.99 | 192.18 | Unknown | 30.77 | Unknown | 1158.04 | Unknown | 4273.65 | 1380.99 | 2892.66 | Yes | N/A | N/A | 2024-03-05 | 2024-03-07 | 3 | 3 | 2024-03-07 | 2024-03-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-18 | 1 | 1 | 3 | 3 | 14 | 10 | 17 | 13 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | 19.2 | 19.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | 69 | 50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 928.89 | Unknown | Unknown | Unknown | Unknown | 928.89 | 7782 | 3238.84 | 928.89 | 2309.95 | Yes | N/A | N/A | 2024-07-10 | 2024-08-22 | 44 | 32 | 2024-08-22 | 2025-01-22 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-05-02 | 101 | 73 | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-12 | 2025-06-23 | 43 | 31 | 2025-06-23 | 2025-06-19 | Unknown | Unknown | 145 | 105 | 197 | 141 | 342 | 246 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2457.42 | Unknown | Unknown | Unknown | -2486 | 28.58 | Unknown | 2485.94 | -2457.42 | 4943.36 | Yes | N/A | N/A | 2024-06-04 | 2024-06-12 | 9 | 7 | 2024-06-12 | 2024-06-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-28 | 1 | 1 | 9 | 7 | 18 | 14 | 27 | 21 | Steps 2,3,5,6,7 | 284 | 202 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -321 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-23 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 419.45 | -8.43 | Unknown | Unknown | Unknown | 427.88 | Unknown | 1303.32 | 419.45 | 883.87 | Yes | N/A | N/A | 2025-04-18 | 2025-04-22 | 5 | 3 | 2025-04-22 | 2025-04-25 | 4 | 4 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-06 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-16 | 11 | 9 | 2025-05-16 | 2025-05-16 | 1 | 1 | 17 | 11 | 16 | 14 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-02-01 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | -5.46 | -4.43 | Unknown | Unknown | Unknown | -1.03 | 3981 | 1105.93 | -5.46 | 1111.39 | Yes | N/A | N/A | 2024-01-02 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2024-02-01 | 100 | 72 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-01 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-25 | 25 | 17 | 2024-03-25 | 2024-03-25 | 1 | 1 | 30 | 22 | 126 | 90 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -709 | -507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | Unknown | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 30.24 | Unknown | Unknown | Unknown | Unknown | 30.24 | 3981 | 1546.8 | 30.24 | 1516.56 | Yes | N/A | N/A | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-17 | 9 | 7 | 2024-10-17 | 2024-10-17 | 1 | 1 | 9 | 7 | 11 | 9 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -462 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2025-01-02 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 8805.7 | 1999.81 | Unknown | 1184.01 | Unknown | 5621.88 | 7960 | 80.07 | 8805.7 | -8725.63 | Yes | N/A | N/A | 2024-12-11 | 2025-01-02 | 23 | 17 | 2025-01-02 | 2025-01-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-24 | 15 | 11 | 2025-03-24 | 2025-03-22 | Unknown | Unknown | 32 | 24 | 20 | 14 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -294 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 2025-06-07 | IOU Designed & Installed | N/A | No | N/A | -1292.97 | 1905.36 | Unknown | Unknown | -3956 | 757.67 | Unknown | 3956.22 | -1292.97 | 5249.19 | Yes | N/A | N/A | 2025-04-17 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-07 | 2025-06-07 | 1 | 0 | 2025-06-07 | 2025-06-07 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -463 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-13 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1468.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-09-11 | 20 | 14 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2025-05-06 | 236 | 168 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-07 | 2 | 2 | 2025-05-07 | 2025-05-07 | 1 | 1 | 236 | 168 | 23 | 17 | 259 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 134.05 | 134.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -297 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 863.87 | -16.59 | Unknown | Unknown | Unknown | 880.46 | 3981 | 1305.7 | 863.87 | 441.83 | Yes | N/A | N/A | 2023-10-31 | 2023-08-06 | Unknown | Unknown | 2023-08-06 | 2024-03-29 | 237 | 170 | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-06 | 20 | 14 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-02 | 1 | 1 | 0 | 0 | 258 | 185 | 258 | 185 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 473 | 338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2024-02-07 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 155269.45 | 49522.29 | Unknown | 84.97 | 572.1 | 105090.09 | 36285 | 74529.9 | 155269.45 | -80739.55 | Yes | N/A | N/A | 2023-12-01 | 2024-01-02 | 33 | 23 | 2024-01-02 | 2024-07-11 | 192 | 138 | 2024-03-28 | 2024-04-01 | 5 | 3 | 2024-06-04 | 2024-07-09 | 33 | 23 | 2024-07-11 | Unknown | Unknown | Unknown | 2024-07-23 | 2025-03-28 | 249 | 179 | 2025-04-11 | 2025-06-10 | 61 | 43 | 2025-06-10 | 2025-06-10 | 1 | 1 | 38 | 26 | 536 | 384 | 574 | 410 | Steps 2,3,5,6,7 | 105 | 75 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -652 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-27 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 6395.15 | 1456.43 | Unknown | 158.77 | Unknown | 4779.95 | Unknown | 2529.31 | 6395.15 | -3865.84 | Yes | N/A | N/A | 2025-01-21 | 2025-01-23 | 3 | 3 | 2025-01-23 | 2025-01-27 | 5 | 3 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-24 | 29 | 21 | 2025-01-27 | 2025-03-27 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-03-28 | 2 | 2 | 2025-03-28 | 2025-03-28 | 1 | 1 | 63 | 47 | 37 | 27 | 100 | 74 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | -1870.09 | Unknown | Unknown | Unknown | -1910 | 39.91 | Unknown | 1910.05 | -1870.09 | 3780.14 | Yes | N/A | N/A | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | 2024-09-27 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-21 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-22 | 8 | 6 | 2024-10-22 | 2024-10-21 | Unknown | Unknown | 26 | 18 | 46 | 34 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -294 | -211 | No | 2024-08-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2025-01-15 | IOU Designed & Installed | N/A | Yes | 148 | 1078.77 | 192.82 | Unknown | Unknown | Unknown | 885.95 | Unknown | Not available | 1078.77 | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-20 | 7 | 5 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-15 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-30 | 16 | 12 | 2025-01-30 | 2025-01-30 | 1 | 1 | 14 | 10 | 18 | 14 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 337.05 | 337.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 931.82 | Unknown | Unknown | Unknown | 16.1 | 915.72 | 3981 | 804.7 | 931.82 | -127.12 | Yes | N/A | N/A | 2024-04-30 | 2024-05-17 | 18 | 14 | 2024-05-17 | 2024-05-20 | 4 | 2 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-30 | 72 | 52 | Unknown | 2024-06-19 | Unknown | Unknown | 2024-07-30 | 2024-08-02 | 4 | 4 | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 90 | 66 | 8 | 6 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-19 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 871.45 | -16.15 | Unknown | Unknown | 5.29 | 882.31 | 3981 | 1554.28 | 871.45 | 682.83 | Yes | N/A | N/A | 2024-09-10 | 2024-09-18 | 9 | 7 | 2024-09-18 | 2024-09-19 | 2 | 2 | 2024-09-19 | Unknown | Unknown | Unknown | 2024-09-20 | 2024-09-30 | 11 | 7 | 2024-09-19 | 2024-10-31 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-12-18 | 49 | 35 | 2024-12-18 | 2024-12-18 | 1 | 1 | 52 | 38 | 63 | 45 | 115 | 83 | Steps 2,3,5,6,7 | 11 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -473 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-18 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | -64.73 | Unknown | Unknown | Unknown | -881.45 | 816.72 | Unknown | 891.53 | -64.73 | 956.26 | Yes | N/A | N/A | 2024-03-08 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-03-18 | 60 | 42 | 2024-03-18 | 2024-03-28 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-09-20 | 164 | 118 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-09-20 | 2024-09-30 | 11 | 7 | 2024-09-30 | 2024-09-30 | 1 | 1 | 175 | 127 | 72 | 50 | 247 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6852 | 6852 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-08-07 | 282 | 202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-06 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 618.21 | -34.81 | Unknown | Unknown | 13.43 | 639.59 | 15924 | 510.07 | 618.21 | -108.14 | Yes | N/A | N/A | 2022-04-06 | 2023-02-08 | 309 | 221 | 2023-02-08 | 2023-03-22 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-05-16 | Unknown | Unknown | 309 | 221 | 43 | 31 | 352 | 252 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -206 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-12 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 61342.79 | 11435.15 | Unknown | Unknown | 62.7 | 49844.94 | 3512770 | 32932.81 | 61342.79 | -28409.98 | Yes | N/A | N/A | 2023-12-11 | 2024-02-08 | 60 | 44 | 2024-02-08 | 2024-05-13 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-05-13 | 2958465 | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | 2024-07-01 | 2024-08-01 | 32 | 24 | 2024-08-01 | 2024-07-21 | Unknown | Unknown | 60 | 44 | 129 | 93 | 189 | 137 | Steps 2,3,5,6,7 | 60 | 44 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 636.05 | 636.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -136 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 651.34 | -22.92 | Unknown | Unknown | Unknown | 674.26 | 3981 | 675.16 | 651.34 | 23.82 | Yes | N/A | N/A | 2024-01-29 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-01-29 | 8 | 6 | 2024-01-29 | 2024-05-03 | 5 | 5 | 2024-04-17 | 2024-05-16 | 20 | 12 | 2024-01-29 | 2024-04-15 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-20 | 36 | 26 | 2024-05-20 | 2024-05-17 | Unknown | Unknown | 83 | 61 | 64 | 44 | 147 | 105 | Steps 2,3,5,6,7 | 124 | 90 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 1009.76 | Unknown | Unknown | Unknown | 13 | 996.76 | 3981 | 767.8 | 1009.76 | -241.96 | Yes | N/A | N/A | 2024-03-07 | 2024-04-08 | 33 | 23 | 2024-04-08 | 2024-04-12 | 5 | 5 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-10-01 | 173 | 123 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-10-01 | 2024-10-15 | 15 | 11 | 2024-10-15 | 2024-10-15 | 1 | 1 | 206 | 146 | 21 | 17 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 535.2 | -8.16 | Unknown | Unknown | Unknown | 543.36 | Unknown | 1427.13 | 535.2 | 891.93 | Yes | N/A | N/A | 2024-06-03 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-04-18 | 1 | 1 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-18 | 9 | 7 | 2024-06-18 | 2024-06-18 | 1 | 1 | 8 | 6 | 11 | 9 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 383.05 | 383.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | 140 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 9090.23 | Unknown | Unknown | Unknown | Unknown | 9090.23 | 3981 | 1484.8 | 9090.23 | -7605.43 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-06-11 | 206 | 148 | 2025-06-11 | 2025-05-19 | Unknown | Unknown | 1 | 1 | 206 | 148 | 207 | 149 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-31 | 1401 | 1002 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-03 | 2022-08-03 | 2023-06-30 | IOU Designed & Installed | N/A | No | N/A | 76644.07 | 5289.41 | Unknown | 97.61 | 429.68 | 70827.37 | Unknown | 26571.67 | 76644.07 | -50072.4 | Yes | N/A | N/A | 2022-08-03 | 2023-06-09 | 311 | 223 | 2023-06-09 | 2023-06-26 | 18 | 12 | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-05-07 | 2023-06-22 | 5 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-09-01 | 64 | 46 | 2023-09-01 | 2023-09-01 | 1 | 1 | 312 | 224 | 88 | 63 | 400 | 287 | Steps 2,3,5,6,7 | 50 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-11 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 47.77 | Unknown | Unknown | Unknown | Unknown | 47.77 | 3981 | 1771.64 | 47.77 | 1723.87 | Yes | N/A | N/A | 2025-03-10 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-11 | 14 | 10 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-02 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-07 | 6 | 4 | 2025-04-07 | 2025-04-07 | 1 | 1 | 23 | 17 | 21 | 15 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 447.21 | -6.19 | Unknown | Unknown | Unknown | 453.4 | 3981 | 618.36 | 447.21 | 171.15 | Yes | N/A | N/A | 2023-04-27 | 2023-04-27 | 1 | 1 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-07-26 | 91 | 65 | Unknown | 2023-07-18 | Unknown | Unknown | 2023-07-26 | 2023-08-09 | 15 | 11 | 2023-08-09 | 2023-08-09 | 1 | 1 | 92 | 66 | 16 | 12 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -160 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 3090.6 | Unknown | Unknown | Unknown | 134.18 | 2956.42 | 3981 | 609.71 | 3090.6 | -2480.89 | Yes | N/A | N/A | 2024-01-05 | 2024-09-19 | 259 | 185 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-05-01 | 225 | 161 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-05-01 | 2025-05-07 | 7 | 5 | 2025-05-07 | 2025-05-06 | Unknown | Unknown | 484 | 346 | 8 | 6 | 492 | 352 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 438.1 | 438.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-10 | 16 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 398.59 | -11.99 | Unknown | Unknown | Unknown | 410.58 | 3981 | 965.2 | 398.59 | 566.61 | Yes | N/A | N/A | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | 2024-01-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-02-09 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-02-26 | Unknown | Unknown | 31 | 23 | 16 | 12 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-24 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1030.01 | Unknown | Unknown | Unknown | Unknown | 1030.01 | 3981 | 1136.89 | 1030.01 | 106.88 | Yes | N/A | N/A | 2024-08-29 | 2024-09-24 | 27 | 19 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-01-21 | 120 | 86 | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-21 | 2025-01-28 | 8 | 6 | 2025-01-28 | 2025-01-28 | 1 | 1 | 147 | 105 | 10 | 8 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 491 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-18 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 5611.23 | Unknown | Unknown | Unknown | Unknown | 5611.23 | 0 | 206.27 | 5611.23 | -5404.96 | Yes | N/A | N/A | 2023-10-16 | 2023-10-30 | 15 | 11 | 2023-10-30 | 2024-06-11 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-18 | 26 | 18 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-05 | 20 | 14 | 2025-05-05 | 2025-05-05 | 1 | 1 | 15 | 11 | 273 | 195 | 288 | 206 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | -613 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1069.66 | -15.3 | Unknown | Unknown | -1831 | 776.64 | Unknown | 1689.13 | -1069.66 | 2758.79 | Yes | N/A | N/A | 2025-02-28 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-02-28 | 19 | 15 | 2025-02-28 | 2025-05-13 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-05-27 | Unknown | Unknown | 75 | 53 | 19 | 15 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 58 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | 2021-03-03 | 2024-01-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 6255.4 | 417.33 | Unknown | Unknown | -4431 | 10269.07 | 1329 | 10398.98 | 6255.4 | 4143.58 | Yes | N/A | N/A | 2021-03-03 | 2023-05-23 | 812 | 580 | 2023-05-23 | 2023-10-17 | 148 | 106 | 2023-05-31 | 2023-10-04 | 68 | 50 | 2023-10-12 | 2023-10-16 | 5 | 3 | 2023-10-20 | Unknown | Unknown | Unknown | 2023-10-20 | 2024-01-12 | 85 | 61 | 2024-01-26 | 2024-02-27 | 33 | 23 | 2024-02-27 | 2024-02-27 | 1 | 1 | 880 | 630 | 272 | 194 | 1152 | 824 | Steps 2,3,5,6,7 | 139 | 99 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 29.05 | 29.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-23 | -124 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | 1105.82 | -12.86 | Unknown | Unknown | 6.4 | 1112.28 | 3981 | 902.39 | 1105.82 | -203.43 | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-08-02 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-08-28 | 27 | 19 | 2023-08-28 | 2023-05-22 | Unknown | Unknown | 185 | 133 | 27 | 19 | 212 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 1670 | 1195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.17 | -4.91 | Unknown | Unknown | Unknown | 1.74 | Unknown | 320.48 | -3.17 | 323.65 | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | 2023-03-21 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -128 | -93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-05 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 2114.13 | 670.41 | Unknown | Unknown | 32.12 | 1411.6 | 3981 | 1054.8 | 2114.13 | -1059.33 | Yes | N/A | N/A | 2024-03-07 | 2024-04-05 | 30 | 22 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-08-22 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-25 | 35 | 25 | 2024-09-25 | 2024-09-25 | 1 | 1 | 170 | 122 | 37 | 27 | 207 | 149 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-14 | -236 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.22 | Unknown | Unknown | Unknown | Unknown | 15.22 | 3981 | 180.09 | 15.22 | 164.87 | Yes | N/A | N/A | 2024-06-27 | 2024-07-26 | 30 | 22 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | 30 | 22 | 2 | 2 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1377.69 | -8.08 | Unknown | Unknown | Unknown | 1385.77 | 3981 | 1150.65 | 1377.69 | -227.04 | Yes | N/A | N/A | 2024-10-25 | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-11-03 | 35 | 25 | 2024-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-03 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 0 | 0 | 36 | 26 | 36 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 59 | 59 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-07 | 172 | 123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | 2023-02-09 | 2023-06-16 | IOU Designed & Installed | N/A | No | N/A | -15.85 | -11.49 | Unknown | Unknown | Unknown | -4.36 | 3241 | 902.26 | -15.85 | 918.11 | Yes | N/A | N/A | 2022-09-20 | 2023-05-10 | 233 | 167 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | 2023-06-16 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-28 | 13 | 9 | 2023-06-28 | 2023-06-28 | 1 | 1 | 271 | 195 | 14 | 10 | 285 | 205 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-10 | 895 | 640 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-21 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 531.14 | -28.17 | Unknown | Unknown | 31.55 | 527.76 | 3981 | 555.68 | 531.14 | 24.54 | Yes | N/A | N/A | 2023-07-20 | 2023-06-23 | Unknown | Unknown | 2023-06-23 | 2023-08-16 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2024-04-18 | 247 | 177 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-22 | 2024-04-29 | 8 | 6 | 2024-04-29 | 2024-04-23 | Unknown | Unknown | 247 | 177 | 63 | 45 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | -431 | -309 | No | 2022-10-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | 2022-11-10 | Unknown | IOU Designed & Installed | N/A | Yes | 99 | 845.26 | -11.29 | Unknown | Unknown | Unknown | 856.55 | Unknown | 866.33 | 845.26 | 21.07 | Yes | N/A | N/A | 2022-10-25 | 2023-02-01 | 100 | 72 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | 2023-06-13 | 2023-06-13 | 1 | 1 | 100 | 72 | 1 | 1 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 143.75 | 143.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | 30 | 21 | No | 2022-10-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-21 | 2022-10-11 | 2024-06-13 | IOU Designed & Installed | N/A | Yes | 532 | 1868.75 | 291.46 | Unknown | 479.31 | 9.57 | 1088.41 | 3981 | 2788.69 | 1868.75 | 919.94 | Yes | N/A | N/A | 2022-08-21 | 2024-03-26 | 584 | 417 | 2024-03-26 | 2024-03-26 | 1 | 1 | 2024-03-26 | Unknown | Unknown | Unknown | 2023-04-10 | 2023-06-05 | 57 | 41 | 2023-04-10 | 2024-06-13 | 431 | 309 | Unknown | 2024-05-15 | Unknown | Unknown | 2024-06-13 | 2024-06-17 | 5 | 3 | 2024-06-17 | 2024-06-17 | 1 | 1 | 1015 | 726 | 64 | 46 | 1079 | 772 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-10 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 10.56 | Unknown | Unknown | Unknown | Unknown | 10.56 | Unknown | 197.01 | 10.56 | 186.45 | Yes | N/A | N/A | 2024-12-09 | 2024-12-31 | 23 | 17 | 2024-12-31 | 2024-12-31 | 1 | 1 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2024-12-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-15 | 16 | 12 | 2025-01-15 | 2025-01-15 | 1 | 1 | 24 | 18 | 18 | 14 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 31.05 | Unknown | Unknown | Unknown | Unknown | 31.05 | 3981 | 1102.17 | 31.05 | 1071.12 | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-24 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-29 | 6 | 4 | 2025-01-29 | 2025-01-29 | 1 | 1 | 18 | 14 | 8 | 6 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-10 | 254 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-13 | 2023-09-12 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 1161.52 | -30.84 | Unknown | Unknown | Unknown | 1192.36 | 3981 | 756.58 | 1161.52 | -404.94 | Yes | N/A | N/A | 2022-04-13 | 2023-09-07 | 513 | 367 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2023-10-26 | 45 | 33 | 2023-09-12 | 2023-11-08 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-10 | 3 | 3 | 2023-11-10 | 2023-11-19 | 10 | 6 | 571 | 409 | 58 | 42 | 629 | 451 | Steps 2,3,5,6,7 | 44 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -347 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | -453.98 | 229.92 | Unknown | 166.86 | -1539 | 688.24 | 497 | 1889.88 | -453.98 | 2343.86 | Yes | N/A | N/A | 2024-09-26 | 2025-03-18 | 174 | 124 | 2025-03-18 | 2025-04-04 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-03-28 | 9 | 7 | 2025-04-04 | 2025-04-21 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | 2025-04-28 | 1 | 1 | 192 | 136 | 29 | 23 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | -1.02 | Unknown | Unknown | Unknown | Unknown | -1.02 | 3981 | 484.71 | -1.02 | 485.73 | Yes | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-15 | 17 | 13 | 2023-11-15 | 2023-11-15 | 1 | 1 | 1 | 1 | 18 | 14 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 1510.55 | Unknown | Unknown | Unknown | 5.3 | 1505.25 | 3981 | 2420.65 | 1510.55 | 910.1 | Yes | N/A | N/A | 2023-07-10 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-07-14 | 66 | 48 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-07-19 | 4 | 4 | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-19 | 2024-08-05 | 18 | 12 | 2024-08-05 | 2024-08-05 | 1 | 1 | 4 | 4 | 85 | 61 | 89 | 65 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-27 | -465 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-02-21 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 1315.07 | -8.64 | Unknown | Unknown | 13.7 | 1310.01 | 3981 | 710.24 | 1315.07 | -604.83 | Yes | N/A | N/A | 2024-01-16 | 2024-02-16 | 32 | 24 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-10 | 61 | 43 | Unknown | 2024-05-31 | Unknown | Unknown | 2024-06-10 | 2024-06-20 | 11 | 9 | 2024-06-20 | 2024-06-19 | Unknown | Unknown | 93 | 67 | 12 | 10 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-31 | 361 | 259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 4815.25 | 34.35 | Unknown | Unknown | -13898 | 18678.9 | 0 | 13898.07 | 4815.25 | 9082.82 | Yes | N/A | N/A | 2023-11-15 | 2023-11-15 | 1 | 1 | 2023-11-15 | 2024-09-20 | 311 | 223 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-28 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-12-26 | 45 | 33 | 2024-12-26 | 2024-12-26 | 1 | 1 | 1 | 1 | 369 | 265 | 370 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | -2444.77 | 615.84 | Unknown | 142.41 | -3623 | 419.98 | Unknown | 3623.45 | -2444.77 | 6068.22 | Yes | N/A | N/A | 2024-07-25 | 2024-08-05 | 12 | 8 | 2024-08-05 | 2024-10-18 | 75 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-08-26 | 2024-10-22 | 58 | 42 | 2024-10-22 | 2024-10-22 | 1 | 1 | 12 | 8 | 134 | 98 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -298 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2023-11-04 | IOU Designed & Installed | N/A | No | N/A | 1239.95 | 1020.11 | Unknown | 1753.57 | -2365 | 831.27 | Unknown | 2365.13 | 1239.95 | 1125.18 | Yes | N/A | N/A | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-04 | 2023-11-07 | 4 | 2 | 2023-11-07 | 2023-11-07 | 1 | 1 | 1 | 1 | 5 | 3 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -298 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 6.19 | -5.48 | Unknown | Unknown | Unknown | 11.67 | Unknown | 307.58 | 6.19 | 301.39 | Yes | N/A | N/A | 2024-04-23 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-23 | 55 | 39 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-29 | 7 | 5 | 2024-04-29 | 2024-04-29 | 1 | 1 | 1 | 1 | 63 | 45 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 124.05 | 124.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -442 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-26 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 478.56 | -15.68 | Unknown | Unknown | Unknown | 494.24 | 3981 | 1107.56 | 478.56 | 629 | Yes | N/A | N/A | 2023-12-20 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | 2024-01-26 | 110 | 80 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-06-17 | 144 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-28 | 12 | 10 | 2024-06-28 | 2024-06-28 | 1 | 1 | 144 | 102 | 123 | 91 | 267 | 193 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | 100.4 | 100.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-26 | -76 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-26 | 2023-08-26 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 12653.85 | 2513.21 | Unknown | Unknown | 140.86 | 9999.78 | 3981 | 650.54 | 12653.85 | -12003.31 | Yes | N/A | N/A | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-05-06 | 187 | 133 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-05-06 | 2025-06-11 | 37 | 27 | 2025-06-11 | 2025-06-11 | 1 | 1 | 188 | 133 | 38 | 28 | 226 | 161 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -113 | -82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-05-12 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 88.77 | -11.76 | Unknown | Unknown | Unknown | 100.53 | 3981 | 968.23 | 88.77 | 879.46 | Yes | N/A | N/A | 2023-04-25 | 2023-05-12 | 18 | 14 | 2023-05-12 | 2023-08-14 | 95 | 67 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-10-03 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-27 | 25 | 19 | 2023-10-27 | 2023-10-26 | Unknown | Unknown | 163 | 117 | 120 | 86 | 283 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -194 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1591.06 | Unknown | Unknown | Unknown | 16.01 | 1575.05 | 3961 | 1529.84 | 1591.06 | -61.22 | Yes | N/A | N/A | 2024-01-31 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2024-04-15 | 130 | 92 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 0 | 0 | 130 | 92 | 130 | 92 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 25.1 | 25.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 13319 | 1460.11 | Unknown | Unknown | 22.44 | 11836.45 | 3981 | 1376.32 | 13319 | -11942.68 | Yes | N/A | N/A | 2024-08-28 | 2024-09-24 | 28 | 20 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-02-25 | 155 | 111 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | 2025-02-25 | 1 | 1 | 183 | 131 | 3 | 3 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-07 | 2024-09-07 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | -2811.03 | 3216.1 | Unknown | 770.2 | -8272 | 1474.67 | Unknown | 8271.51 | -2811.03 | 11082.54 | Yes | N/A | N/A | 2024-09-07 | 2024-09-13 | 7 | 5 | 2024-09-13 | 2024-10-29 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-10 | 2024-11-06 | 28 | 20 | 2024-11-06 | 2024-11-06 | 1 | 1 | 7 | 5 | 77 | 55 | 84 | 60 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -526 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | -7.78 | -5.64 | Unknown | Unknown | Unknown | -2.14 | Unknown | 483.84 | -7.78 | 491.62 | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-08-08 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-06-14 | 1 | 1 | 112 | 80 | 1 | 1 | 113 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-07 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.31 | -11.74 | Unknown | Unknown | Unknown | -0.57 | Unknown | 438.07 | -12.31 | 450.38 | Yes | N/A | N/A | 2023-06-09 | 2023-07-18 | 40 | 28 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 40 | 28 | 1 | 1 | 41 | 29 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 1128.99 | -5.67 | Unknown | Unknown | Unknown | 1134.66 | 3981 | 733.78 | 1128.99 | -395.21 | Yes | N/A | N/A | 2024-01-16 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | 2024-01-16 | 51 | 37 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-01-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-02-09 | 25 | 19 | 2024-02-09 | 2024-02-09 | 1 | 1 | 1 | 1 | 77 | 57 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-03 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | -879.29 | 2115.99 | Unknown | 373.93 | -4346 | 976.79 | Unknown | 4346.23 | -879.29 | 5225.52 | Yes | N/A | N/A | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | 2024-09-11 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-07-19 | 2024-09-11 | 55 | 39 | 2024-09-11 | 2024-09-11 | 1 | 1 | 1 | 1 | 123 | 89 | 124 | 90 | Steps 2,3,5,6,7 | 54 | 38 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-02 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-11 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1868.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-04-11 | 22 | 16 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-07 | 13 | 9 | 2025-05-07 | 2025-05-07 | 1 | 1 | 15 | 11 | 36 | 26 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -667 | -478 | No | 2023-02-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | 2024-07-11 | IOU Designed & Installed | N/A | Yes | 525 | 8.95 | -6.9 | Unknown | Unknown | Unknown | 15.85 | 7882 | 2147.2 | 8.95 | 2138.25 | Yes | N/A | N/A | 2023-02-01 | 2024-07-10 | 526 | 376 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | 2024-07-11 | 527 | 377 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-07-16 | 6 | 4 | 2024-07-16 | 2024-07-23 | 8 | 6 | 1053 | 753 | 14 | 10 | 1067 | 763 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 208 | 208 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -26 | -19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2833.4 | Unknown | Unknown | Unknown | 39.89 | 2793.51 | 3981 | 885.95 | 2833.4 | -1947.45 | Yes | N/A | N/A | 2024-06-03 | 2024-10-09 | 129 | 93 | 2024-10-09 | 2024-10-10 | 2 | 2 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 129 | 93 | 3 | 3 | 132 | 96 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-27 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 1064.53 | 592.66 | Unknown | Unknown | -784 | 1255.87 | 3981 | 1639.36 | 1064.53 | 574.83 | Yes | N/A | N/A | 2024-04-26 | 2024-04-29 | 4 | 2 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-05-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-20 | 2 | 2 | 2024-06-20 | 2024-06-20 | 1 | 1 | 57 | 41 | 4 | 4 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | 605.2 | 605.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -55 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2025-05-23 | IOU Designed & Installed | N/A | No | N/A | 1281.06 | Unknown | Unknown | Unknown | -3788.66 | 5069.72 | 271297 | 11700.17 | 1281.06 | 10419.11 | Yes | N/A | N/A | 2024-07-25 | 2024-10-09 | 77 | 55 | 2024-10-09 | 2024-11-22 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-05-21 | 181 | 129 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-23 | 2025-06-10 | 19 | 13 | 2025-06-10 | 2025-05-29 | Unknown | Unknown | 258 | 184 | 64 | 46 | 322 | 230 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -374 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 1391.79 | 510.06 | Unknown | Unknown | -1205.07 | 2086.8 | Unknown | 606.52 | 1391.79 | -785.27 | Yes | N/A | N/A | 2023-04-10 | 2023-05-19 | 40 | 30 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2024-01-19 | 228 | 164 | Unknown | 2024-01-17 | Unknown | Unknown | 2024-01-19 | 2024-01-22 | 4 | 2 | 2024-01-22 | 2024-01-22 | 1 | 1 | 268 | 194 | 5 | 3 | 273 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -257 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 2705.73 | 1609.92 | Unknown | Unknown | Unknown | 1095.81 | Unknown | 6099.56 | 2705.73 | 3393.83 | Yes | N/A | N/A | 2024-05-09 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-10 | 8 | 6 | 2024-06-10 | 2024-06-10 | 1 | 1 | 0 | 0 | 9 | 7 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-31 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 822.51 | 122.12 | Unknown | Unknown | Unknown | 700.39 | Unknown | 1777.14 | 822.51 | 954.63 | Yes | N/A | N/A | 2024-10-08 | 2024-10-23 | 16 | 12 | 2024-10-23 | 2024-10-31 | 9 | 7 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-12-26 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-02-06 | 43 | 31 | 2025-02-06 | 2025-02-06 | 1 | 1 | 73 | 53 | 53 | 39 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 862.05 | 862.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-28 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | -2.23 | -4.43 | Unknown | Unknown | Unknown | 2.2 | 3981 | 669.75 | -2.23 | 671.98 | Yes | N/A | N/A | 2023-02-21 | 2023-02-28 | 8 | 6 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-08-28 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-12 | 16 | 12 | 2023-09-12 | 2023-09-12 | 1 | 1 | 190 | 136 | 17 | 13 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | -339 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 616 | -12.62 | Unknown | Unknown | Unknown | 628.62 | 2781 | 839.07 | 616 | 223.07 | Yes | N/A | N/A | 2023-05-19 | 2023-05-30 | 12 | 8 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-06-14 | 1 | 1 | 12 | 8 | 1 | 1 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 2787.4 | 718.36 | Unknown | Unknown | Unknown | 2069.04 | 3981 | 1312.78 | 2787.4 | -1474.62 | Yes | N/A | N/A | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-16 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-17 | 33 | 23 | 2025-06-17 | 2025-06-17 | 1 | 1 | 3 | 3 | 35 | 25 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | Lemon Grove | LEMON GROVE | 31955 | 31955 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-15 | 215 | 154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-08-14 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 88426.7 | 25904.2 | Unknown | 878.05 | 851.47 | 60792.98 | 417431.01 | 76628.92 | 88426.7 | -11797.78 | Yes | N/A | N/A | 2023-04-20 | 2023-08-08 | 111 | 79 | 2023-08-08 | 2024-03-11 | 217 | 155 | 2023-12-26 | 2024-05-13 | 111 | 79 | 2023-12-06 | 2024-07-23 | 63 | 45 | 2024-03-11 | Unknown | Unknown | Unknown | 2024-06-11 | 2024-10-07 | 119 | 85 | 2024-10-15 | 2024-12-16 | 63 | 45 | 2024-12-16 | 2024-12-16 | 1 | 1 | 222 | 158 | 463 | 331 | 685 | 489 | Steps 2,3,5,6,7 | 369 | 263 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 659872 | 659872 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-20 | 182 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-03-01 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 12.29 | -10.92 | Unknown | Unknown | Unknown | 23.21 | 3981 | 803.42 | 12.29 | 791.13 | Yes | N/A | N/A | 2024-01-31 | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2024-03-01 | 86 | 62 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-04-09 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-22 | 14 | 10 | 2024-04-22 | 2024-04-19 | Unknown | Unknown | 40 | 28 | 100 | 72 | 140 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 2082.12 | 2082.12 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-24 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3563.33 | 1121.21 | Unknown | 207.66 | -5400 | 507.8 | Unknown | 5399.89 | -3563.33 | 8963.22 | Yes | N/A | N/A | 2024-04-22 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-06-04 | Unknown | Unknown | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 352 | 352 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-15 | 511 | 366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2024-03-07 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 5858.63 | -100.54 | Unknown | Unknown | 192.11 | 5767.06 | 7962 | 745.33 | 5858.63 | -5113.3 | Yes | N/A | N/A | 2023-11-20 | 2024-03-07 | 109 | 79 | 2024-03-07 | 2024-10-15 | 223 | 159 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-26 | 43 | 31 | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-27 | 2025-03-26 | 90 | 64 | 2025-03-26 | 2025-01-07 | Unknown | Unknown | 152 | 110 | 313 | 223 | 465 | 333 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -604 | -433 | No | 2024-05-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-07-23 | IOU Designed & Installed | N/A | Yes | 68 | 28.03 | Unknown | Unknown | Unknown | Unknown | 28.03 | 3941 | 859.65 | 28.03 | 831.62 | Yes | N/A | N/A | 2024-05-09 | 2024-07-16 | 69 | 49 | 2024-07-16 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-07-23 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-29 | 7 | 5 | 2024-07-29 | 2024-07-29 | 1 | 1 | 145 | 103 | 8 | 6 | 153 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-13 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 255.56 | -5.33 | Unknown | Unknown | Unknown | 260.89 | 3981 | 1914.96 | 255.56 | 1659.4 | Yes | N/A | N/A | 2025-02-06 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-13 | 15 | 11 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-03 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-05-22 | 81 | 59 | 2025-05-22 | 2025-05-22 | 1 | 1 | 19 | 13 | 97 | 71 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-04 | -214 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 483.58 | -9.75 | Unknown | Unknown | Unknown | 493.33 | 7962 | 1498.12 | 483.58 | 1014.54 | Yes | N/A | N/A | 2024-10-07 | 2024-10-22 | 16 | 12 | 2024-10-22 | 2024-10-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-19 | 29 | 21 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-02 | 1 | 1 | 16 | 12 | 32 | 24 | 48 | 36 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1944.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-16 | 23 | 17 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-19 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-17 | 30 | 22 | 2025-06-17 | 2025-06-17 | 1 | 1 | 34 | 24 | 54 | 40 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 284.48 | -5.5 | Unknown | Unknown | Unknown | 289.98 | Unknown | 466.88 | 284.48 | 182.4 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-03 | 26 | 18 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-04 | 1 | 1 | 2 | 2 | 78 | 56 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56, VISTA | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-09 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3241 | 2463.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-09 | 18 | 14 | 2025-05-09 | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-05 | 25 | 19 | 2025-05-09 | 2025-06-23 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-25 | 3 | 3 | 2025-06-25 | 2025-06-25 | 1 | 1 | 46 | 32 | 47 | 37 | 93 | 69 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 811.75 | 811.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5244.25 | 1298.2 | Unknown | 112.73 | Unknown | 3833.32 | 3981 | 1237.55 | 5244.25 | -4006.7 | Yes | N/A | N/A | 2024-09-18 | 2024-10-18 | 31 | 23 | 2024-10-18 | 2024-10-21 | 4 | 2 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-30 | 1 | 1 | 31 | 23 | 5 | 3 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -192 | -139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 738.98 | -14.09 | Unknown | Unknown | Unknown | 753.07 | 7962 | 3219.45 | 738.98 | 2480.47 | Yes | N/A | N/A | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | 2024-06-05 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-04 | 28 | 20 | 2024-06-05 | 2024-08-12 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-10 | Unknown | Unknown | 70 | 50 | 71 | 51 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 801.05 | 801.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | -120 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | -9.57 | -7.88 | Unknown | Unknown | Unknown | -1.69 | Unknown | 153.75 | -9.57 | 163.32 | Yes | N/A | N/A | 2023-05-03 | 2023-05-19 | 17 | 13 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-10-02 | 137 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-26 | 25 | 19 | 2023-10-26 | 2023-10-26 | 1 | 1 | 154 | 110 | 26 | 20 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 253 | 253 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -196 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7 | -20.68 | Unknown | Unknown | Unknown | 13.68 | 3981 | 1095.43 | -7 | 1102.43 | Yes | N/A | N/A | 2023-04-25 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | 2023-06-05 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-06-15 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-09-14 | 1 | 1 | 11 | 9 | 55 | 39 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | 2023-08-14 | IOU Designed & Installed | N/A | No | N/A | -4.68 | -3.39 | Unknown | Unknown | Unknown | -1.29 | 3981 | 1069.58 | -4.68 | 1074.26 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-08-14 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-16 | 3 | 3 | 2023-08-16 | 2023-08-16 | 1 | 1 | 147 | 105 | 4 | 4 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | 270 | 193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 138237.03 | 33921.44 | Unknown | Unknown | -28995.57 | 133311.16 | 3981 | 91307.29 | 138237.03 | -46929.74 | Yes | N/A | N/A | 2024-05-14 | 2025-02-06 | 269 | 193 | 2025-02-06 | 2024-09-17 | Unknown | Unknown | 2024-08-06 | 2025-02-07 | 20 | 14 | 2024-09-02 | 2024-09-10 | 9 | 7 | 2024-09-17 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-03-26 | 149 | 107 | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 289 | 207 | 158 | 114 | 447 | 321 | Steps 2,3,5,6,7 | 200 | 144 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 327.05 | 327.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-05-29 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1229.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-05-15 | 42 | 30 | 2025-05-15 | 2025-05-29 | 15 | 11 | 2025-05-20 | 2025-05-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-19 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-27 | 9 | 7 | 2025-06-27 | 2025-06-27 | 1 | 1 | 65 | 47 | 25 | 19 | 90 | 66 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | 1478.63 | 472.4 | Unknown | Unknown | 5.73 | 1000.5 | 3981 | 372.16 | 1478.63 | -1106.47 | Yes | N/A | N/A | 2023-05-30 | 2023-06-07 | 9 | 7 | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-08-22 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-09-01 | 11 | 9 | 2023-09-01 | 2023-09-01 | 1 | 1 | 86 | 62 | 12 | 10 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2025-01-03 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | -1508.79 | Unknown | Unknown | Unknown | -1557 | 48.21 | Unknown | 1424.07 | -1508.79 | 2932.86 | Yes | N/A | N/A | 2024-12-10 | 2024-12-27 | 18 | 14 | 2024-12-27 | 2025-01-06 | 11 | 7 | 2025-01-06 | 2025-01-08 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-29 | 22 | 16 | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-29 | 2025-02-14 | 17 | 13 | 2025-02-14 | 2025-02-14 | 1 | 1 | 43 | 33 | 29 | 21 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -600 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-13 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 602.87 | -1.5 | Unknown | Unknown | Unknown | 604.37 | 3981 | 1741.22 | 602.87 | 1138.35 | Yes | N/A | N/A | 2025-02-10 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-02-13 | 17 | 13 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-05-21 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-02 | 13 | 9 | 2025-06-02 | 2025-06-02 | 1 | 1 | 98 | 70 | 31 | 23 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1559.05 | 1559.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-30 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-09-08 | 2023-10-06 | IOU Designed & Installed | N/A | No | N/A | -8.38 | -6.35 | Unknown | Unknown | Unknown | -2.03 | 3981 | 751.45 | -8.38 | 759.83 | Yes | N/A | N/A | 2023-08-11 | 2023-09-08 | 29 | 21 | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-10-06 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-11-30 | 56 | 40 | 2023-11-30 | 2023-11-30 | 1 | 1 | 58 | 42 | 58 | 42 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -715 | -512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | Unknown | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 2990.99 | 870.36 | Unknown | Unknown | Unknown | 2120.63 | 3981 | 1497.88 | 2990.99 | -1493.11 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-08-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-03 | 8 | 6 | 2024-09-03 | 2024-09-03 | 1 | 1 | 3 | 3 | 10 | 8 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 152.05 | 152.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-31 | -480 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2041.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-10-24 | 108 | 78 | 2024-10-24 | 2025-02-11 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-20 | 22 | 16 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 108 | 78 | 134 | 96 | 242 | 174 | Steps 2,3,5,6,7 | 9 | 7 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 642 | 459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 36010 | Unknown | Unknown | Unknown | -25961.67 | 61971.67 | Unknown | 25197.47 | 36010 | -10812.53 | Yes | N/A | N/A | 2024-05-30 | 2024-07-02 | 34 | 24 | 2024-07-02 | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-28 | 24 | 18 | 2025-01-07 | 2025-04-11 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | 2024-12-13 | 2025-05-05 | 144 | 102 | 2025-05-05 | 2025-05-05 | 1 | 1 | 58 | 42 | 224 | 160 | 282 | 202 | Steps 2,3,5,6,7 | 77 | 55 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 3874 | 3874 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-15 | 39 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9090.62 | Unknown | Unknown | Unknown | Unknown | 9090.62 | 380772 | 18276.17 | 9090.62 | 9185.55 | Yes | N/A | N/A | 2023-07-10 | 2023-07-11 | 2 | 2 | 2023-07-11 | 2023-08-21 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2025-02-24 | 554 | 396 | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-03-26 | Unknown | Unknown | 556 | 398 | 42 | 30 | 598 | 428 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -659 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 148.13 | -2.52 | Unknown | Unknown | Unknown | 150.65 | 3981 | 1833.65 | 148.13 | 1685.52 | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-29 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-28 | 31 | 23 | 2025-02-28 | 2025-02-28 | 1 | 1 | 15 | 11 | 33 | 25 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -514 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-10 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 18126.86 | 4656.26 | Unknown | Unknown | -26189.81 | 39660.41 | 0 | 26371.63 | 18126.86 | 8244.77 | Yes | N/A | N/A | 2023-08-03 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2025-01-21 | 580 | 414 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2025-01-15 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-05-05 | 91 | 65 | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 684 | 488 | 684 | 488 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-14 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 789.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2024-01-08 | Unknown | Unknown | 2024-01-08 | 2025-04-04 | 453 | 325 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-05-01 | 28 | 20 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-06-11 | 31 | 23 | 2025-06-11 | 2025-06-11 | 1 | 1 | 28 | 20 | 485 | 349 | 513 | 369 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 94.4 | 94.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-26 | 2025-01-03 | IOU Designed & Installed | N/A | No | N/A | 1009.91 | Unknown | Unknown | Unknown | Unknown | 1009.91 | 3981 | 793.98 | 1009.91 | -215.93 | Yes | N/A | N/A | 2024-09-19 | 2024-08-24 | Unknown | Unknown | 2024-08-24 | 2024-10-24 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-01-03 | 72 | 52 | Unknown | 2024-11-25 | Unknown | Unknown | 2025-01-03 | 2025-01-21 | 19 | 13 | 2025-01-21 | 2025-01-17 | Unknown | Unknown | 72 | 52 | 81 | 57 | 153 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-01 | -842 | -603 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 2354.1 | -0.31 | Unknown | Unknown | Unknown | 2354.41 | Unknown | 1542.93 | 2354.1 | -811.17 | Yes | N/A | N/A | 2025-03-11 | 2025-03-11 | 1 | 1 | 2025-03-11 | 2025-05-30 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-17 | 23 | 17 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-11 | 3 | 3 | 2025-06-11 | 2025-06-11 | 1 | 1 | 1 | 1 | 108 | 80 | 109 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | -663 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-25 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 447.83 | Unknown | Unknown | Unknown | 3.03 | 444.8 | 3981 | 1221.47 | 447.83 | 773.64 | Yes | N/A | N/A | 2025-03-14 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-04-09 | 34 | 24 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-16 | 8 | 6 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-16 | 2025-05-05 | 20 | 14 | 2025-05-05 | 2025-05-05 | 1 | 1 | 8 | 6 | 55 | 39 | 63 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | -285 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -310.17 | 3184.94 | Unknown | 483.27 | -5519 | 1540.62 | Unknown | 5519.36 | -310.17 | 5829.53 | Yes | N/A | N/A | 2024-05-02 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 95.08 | -1.88 | Unknown | Unknown | Unknown | 96.96 | 3981 | 1475.87 | 95.08 | 1380.79 | Yes | N/A | N/A | 2024-10-09 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-09 | 8 | 6 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-24 | 16 | 12 | 2024-10-24 | 2024-10-24 | 1 | 1 | 1 | 1 | 25 | 19 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | 201 | 145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 7496.43 | Unknown | Unknown | Unknown | 15.74 | 7480.69 | 7962 | 642.8 | 7496.43 | -6853.63 | Yes | N/A | N/A | 2024-05-14 | 2024-08-06 | 85 | 61 | 2024-08-06 | 2024-08-15 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-12-10 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | 2025-01-17 | Unknown | Unknown | 203 | 145 | 11 | 9 | 214 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 619.96 | Unknown | Unknown | Unknown | 20.15 | 599.81 | Unknown | 1550.9 | 619.96 | 930.94 | Yes | N/A | N/A | 2024-09-06 | 2024-09-11 | 6 | 4 | 2024-09-11 | 2024-10-24 | 44 | 32 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-02-20 | 120 | 86 | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-20 | 2025-03-26 | 35 | 25 | 2025-03-26 | 2025-03-26 | 1 | 1 | 126 | 90 | 80 | 58 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2436.32 | 1401.66 | Unknown | Unknown | -4468 | 630.02 | Unknown | 4468.32 | -2436.32 | 6904.64 | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2023-12-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | 429 | 308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2024-01-17 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 165103.74 | 36705.75 | Unknown | 484.13 | 2011.96 | 125901.9 | 2367483 | 125858.94 | 165103.74 | -39244.8 | Yes | N/A | N/A | 2023-06-30 | 2024-01-16 | 201 | 143 | 2024-01-16 | 2025-01-14 | 365 | 261 | 2024-03-08 | 2025-01-07 | 26 | 16 | 2024-04-02 | 2025-01-23 | 31 | 23 | 2025-01-14 | 2025-03-27 | 73 | 53 | 2025-03-03 | 2025-03-28 | 26 | 20 | 2025-01-21 | 2025-06-20 | 151 | 109 | 2025-06-20 | 2025-06-20 | 1 | 1 | 300 | 212 | 574 | 414 | 874 | 626 | Steps 2,3,5,6,7 | 691 | 495 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | -648 | -463 | No | 2025-03-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-18 | 2025-05-12 | IOU Designed & Installed | N/A | Yes | 56 | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1762.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-05-12 | 57 | 41 | 2025-05-12 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-24 | 6 | 4 | 2025-03-18 | 2025-05-12 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-14 | 3 | 3 | 2025-05-14 | 2025-05-14 | 1 | 1 | 113 | 81 | 10 | 8 | 123 | 89 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 744994.9 | 744994.9 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-04-04 | -533 | -381 | No | 2024-06-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-26 | 2024-09-12 | IOU Designed & Installed | N/A | Yes | 71 | 14241.95 | 2045.37 | Unknown | 200.47 | 18.79 | 11977.32 | 3981 | 1130.51 | 14241.95 | -13111.44 | Yes | N/A | N/A | 2024-06-20 | 2024-08-30 | 72 | 52 | 2024-08-30 | 2024-07-08 | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-09-12 | 67 | 49 | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-12 | 2024-10-18 | 37 | 27 | 2024-10-18 | 2024-10-18 | 1 | 1 | 139 | 101 | 38 | 28 | 177 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-06-17 | 782 | 559 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2022-11-15 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 71.04 | Unknown | Unknown | Unknown | -396 | 467.04 | 0 | 345.7 | 71.04 | 274.66 | Yes | N/A | N/A | 2022-09-29 | 2023-07-25 | 300 | 214 | 2023-07-25 | 2024-07-22 | 364 | 260 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | 2023-10-18 | 2024-08-13 | 301 | 215 | 2024-08-13 | 2024-08-07 | Unknown | Unknown | 300 | 214 | 665 | 475 | 965 | 689 | Steps 2,3,5,6,7 | 293 | 209 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -506 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 2933.95 | Unknown | Unknown | Unknown | 47.36 | 2886.59 | 3981 | 3156.13 | 2933.95 | 222.18 | Yes | N/A | N/A | 2024-08-12 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-09-11 | 50 | 36 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-02-20 | 163 | 117 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-20 | 2025-02-28 | 9 | 7 | 2025-02-28 | 2025-02-28 | 1 | 1 | 163 | 117 | 60 | 44 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 540 | 540 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-14 | -415 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -8.99 | -6.51 | Unknown | Unknown | Unknown | -2.48 | Unknown | 98.41 | -8.99 | 107.4 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-07-27 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | 2023-07-27 | 1 | 1 | 130 | 94 | 2 | 2 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | -9.65 | -8.06 | Unknown | Unknown | Unknown | -1.59 | Unknown | 153.75 | -9.65 | 163.4 | Yes | N/A | N/A | 2023-04-18 | 2023-05-03 | 16 | 12 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-06-28 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-08-16 | 50 | 36 | 2023-08-16 | 2023-08-16 | 1 | 1 | 73 | 53 | 51 | 37 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 74.5 | 74.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 766.06 | -14.7 | Unknown | Unknown | Unknown | 780.76 | 3981 | 35273.28 | 766.06 | 34507.22 | Yes | N/A | N/A | 2024-11-27 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-27 | 15 | 11 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-20 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-03 | 15 | 11 | 2025-01-03 | 2025-01-02 | Unknown | Unknown | 24 | 18 | 30 | 22 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-10 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 6.89 | Unknown | Unknown | Unknown | Unknown | 6.89 | Unknown | 192.51 | 6.89 | 185.62 | Yes | N/A | N/A | 2024-05-07 | 2024-07-17 | 72 | 52 | 2024-07-17 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-09-09 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-21 | 43 | 31 | 2024-10-21 | 2024-10-21 | 1 | 1 | 125 | 89 | 44 | 32 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.98 | Unknown | Unknown | Unknown | Unknown | 8.98 | 0 | 163.83 | 8.98 | 154.85 | Yes | N/A | N/A | 2024-03-05 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-03-18 | 68 | 48 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-09 | 1 | 1 | 0 | 0 | 69 | 49 | 69 | 49 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1880.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-13 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-11 | 30 | 22 | 2025-06-11 | 2025-06-11 | 1 | 1 | 37 | 27 | 32 | 24 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -465 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 181.68 | -14.81 | Unknown | Unknown | Unknown | 196.49 | Unknown | 656.26 | 181.68 | 474.58 | Yes | N/A | N/A | 2023-02-02 | 2023-02-14 | 13 | 9 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-10-06 | 1 | 1 | 13 | 9 | 1 | 1 | 14 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 216 | 216 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-06 | 343 | 246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 444.65 | -8.21 | Unknown | Unknown | Unknown | 452.86 | 15924 | 2590.32 | 444.65 | 2145.67 | Yes | N/A | N/A | 2024-03-26 | 2024-12-11 | 261 | 187 | 2024-12-11 | 2025-01-22 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-31 | 19 | 15 | 2025-01-22 | 2025-03-25 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-14 | Unknown | Unknown | 324 | 232 | 62 | 46 | 386 | 278 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -452 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 3.83 | -3.4 | Unknown | Unknown | Unknown | 7.23 | 3981 | 955.12 | 3.83 | 951.29 | Yes | N/A | N/A | 2024-01-30 | 2024-02-23 | 25 | 19 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-04-05 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-05-02 | 28 | 20 | 2024-05-02 | 2024-04-29 | Unknown | Unknown | 63 | 47 | 28 | 20 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | -576 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 840.85 | Unknown | Unknown | Unknown | 16.26 | 824.59 | 3981 | 1269.98 | 840.85 | 429.13 | Yes | N/A | N/A | 2024-10-29 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-07 | 21 | 15 | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-04 | 2025-01-22 | 80 | 58 | 2024-11-07 | 2025-02-10 | 96 | 68 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-02-20 | 1 | 1 | 96 | 68 | 113 | 83 | 209 | 151 | Steps 2,3,5,6,7 | 76 | 54 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 1649 | 1180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1226.33 | -35.41 | Unknown | Unknown | 26.17 | 1235.57 | Unknown | 1899.41 | 1226.33 | 673.08 | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | 2023-04-18 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2023-04-04 | 9 | 7 | 2023-04-18 | 2023-06-23 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2023-07-07 | Unknown | Unknown | 68 | 50 | 32 | 24 | 100 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 110 | 110 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-18 | -180 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 967.74 | -19.35 | Unknown | Unknown | Unknown | 987.09 | 3981 | 2004.96 | 967.74 | 1037.22 | Yes | N/A | N/A | 2023-10-05 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-10-23 | 64 | 46 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2024-02-08 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-20 | 13 | 9 | 2024-02-20 | 2024-02-20 | 1 | 1 | 109 | 79 | 78 | 56 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | OCEANSIDE | 428 | 428 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | 242 | 173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-20 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 51122.26 | 2549.8 | Unknown | 58.01 | 174.7 | 48339.75 | 709589 | 42654.83 | 51122.26 | -8467.43 | Yes | N/A | N/A | 2023-03-17 | 2023-03-17 | 1 | 1 | 2023-03-17 | 2023-07-06 | 112 | 80 | 2023-03-23 | 2023-03-24 | 2 | 2 | 2023-04-17 | 2024-04-08 | 117 | 83 | 2023-07-06 | 2024-07-30 | 391 | 279 | 2023-07-19 | 2024-06-27 | 345 | 247 | 2024-05-21 | 2024-09-10 | 113 | 81 | 2024-09-10 | 2024-09-03 | Unknown | Unknown | 394 | 282 | 687 | 491 | 1081 | 773 | Steps 2,3,5,6,7 | 796 | 568 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -1079 | -772 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 300.03 | 206 | Unknown | Unknown | Unknown | 94.03 | 8997 | 554.66 | 300.03 | 254.63 | Yes | N/A | N/A | 2023-05-24 | 2023-05-24 | 1 | 1 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-11-29 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-02-29 | 93 | 67 | 2024-02-29 | 2024-02-29 | 1 | 1 | 191 | 137 | 94 | 68 | 285 | 205 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-23 | -520 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 624.09 | -6.71 | Unknown | Unknown | -486.24 | 1117.04 | Unknown | 505.69 | 624.09 | -118.4 | Yes | N/A | N/A | 2023-06-20 | 2023-03-30 | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-10-11 | 83 | 59 | Unknown | 2023-10-13 | Unknown | Unknown | 2023-10-11 | 2023-10-20 | 10 | 8 | 2023-10-20 | 2023-10-20 | 1 | 1 | 83 | 59 | 11 | 9 | 94 | 68 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -299 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | -936.32 | 218.99 | Unknown | Unknown | -2098 | 942.69 | Unknown | 1954.9 | -936.32 | 2891.22 | Yes | N/A | N/A | 2025-02-13 | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-13 | 3 | 3 | 2025-02-13 | 2025-02-19 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-24 | 6 | 4 | 2025-02-24 | 2025-02-24 | 1 | 1 | 8 | 6 | 10 | 8 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 45.5 | 45.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -317 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -352.83 | -17.12 | Unknown | Unknown | -354 | 18.29 | 3981 | 1284.83 | -352.83 | 1637.66 | Yes | N/A | N/A | 2023-03-22 | 2023-03-23 | 2 | 2 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2023-12-19 | Unknown | Unknown | 2 | 2 | 0 | 0 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 129 | 129 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | -340 | -244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | 2022-10-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -390.37 | -10 | Unknown | Unknown | -387 | 6.63 | 3885 | 1034.35 | -390.37 | 1424.72 | Yes | N/A | N/A | 2022-10-26 | 2023-02-21 | 119 | 85 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 119 | 85 | 1 | 1 | 120 | 86 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -423 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-16 | 2023-11-23 | IOU Designed & Installed | N/A | No | N/A | 587.27 | 383.91 | Unknown | Unknown | Unknown | 203.36 | Unknown | 2906.04 | 587.27 | 2318.77 | Yes | N/A | N/A | 2023-11-01 | 2023-11-02 | 2 | 2 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-23 | 2024-02-08 | 78 | 56 | 2024-02-08 | 2024-02-08 | 1 | 1 | 2 | 2 | 79 | 57 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1607.1 | 1607.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-02-02 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-05-03 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 220.75 | 198.06 | Unknown | Unknown | -389.85 | 412.54 | 3981 | 1620.04 | 220.75 | 1399.29 | Yes | N/A | N/A | 2023-03-29 | 2023-05-03 | 36 | 26 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-07-17 | 75 | 53 | Unknown | 2023-05-09 | Unknown | Unknown | 2023-07-17 | 2023-08-18 | 33 | 25 | 2023-08-18 | 2023-08-18 | 1 | 1 | 111 | 79 | 34 | 26 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 392.05 | 392.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-01-29 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | -29.13 | -23.67 | Unknown | Unknown | Unknown | -5.46 | 3981 | 910.75 | -29.13 | 939.88 | Yes | N/A | N/A | 2023-12-27 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-01-29 | 103 | 73 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-04-10 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-15 | 6 | 4 | 2024-04-15 | 2024-04-12 | Unknown | Unknown | 73 | 53 | 109 | 77 | 182 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 949 | 678 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 815.01 | 124.03 | Unknown | Unknown | Unknown | 690.98 | 0 | 439.25 | 815.01 | -375.76 | Yes | N/A | N/A | 2023-08-22 | 2024-03-11 | 203 | 145 | 2024-03-11 | 2025-02-11 | 338 | 242 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-11-01 | 31 | 23 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1 | 1 | 203 | 145 | 370 | 266 | 573 | 411 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-08 | -486 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 510.74 | -10.2 | Unknown | Unknown | 3.52 | 517.42 | Unknown | 1207.2 | 510.74 | 696.46 | Yes | N/A | N/A | 2024-10-15 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-15 | 29 | 21 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-14 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-02-07 | 86 | 62 | 2025-02-07 | 2025-02-07 | 1 | 1 | 31 | 23 | 116 | 84 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-01 | 1013 | 724 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 2180.15 | Unknown | Unknown | Unknown | Unknown | 2180.15 | 3981 | Not available | 2180.15 | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-05-22 | Unknown | Unknown | 2023-05-22 | 2024-09-04 | 472 | 338 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 2025-06-10 | 2025-06-10 | 1 | 1 | 0 | 0 | 474 | 340 | 474 | 340 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-10 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 46.64 | -0.94 | Unknown | Unknown | Unknown | 47.58 | Unknown | 1978.4 | 46.64 | 1931.76 | Yes | N/A | N/A | 2025-04-07 | 2025-04-10 | 4 | 4 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-02 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-06 | 5 | 3 | 2025-05-06 | 2025-05-06 | 1 | 1 | 27 | 21 | 7 | 5 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | -72 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-01 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 831.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-01 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-09-01 | 40 | 30 | 2023-09-01 | 2024-03-13 | 18 | 10 | 2023-09-05 | 2023-09-22 | 16 | 14 | 2024-03-12 | 2024-03-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-15 | 4 | 4 | 2024-03-15 | 2024-03-15 | 1 | 1 | 19 | 11 | 61 | 49 | 80 | 60 | Steps 2,3,5,6,7 | 190 | 136 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | 483 | 346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 735.21 | 60.58 | Unknown | Unknown | 42.77 | 631.86 | 2875.23 | 269.47 | 735.21 | -465.74 | Yes | N/A | N/A | 2023-07-18 | 2023-07-27 | 10 | 8 | 2023-07-27 | 2023-08-22 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2024-01-19 | 151 | 109 | 2023-10-26 | 2023-12-08 | 44 | 32 | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-01 | Unknown | Unknown | 161 | 117 | 71 | 51 | 232 | 168 | Steps 2,3,5,6,7 | 85 | 61 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | -58 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 1565.53 | 420.74 | Unknown | Unknown | Unknown | 1144.79 | 3981 | 1245.03 | 1565.53 | -320.5 | Yes | N/A | N/A | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-04 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-01-17 | 45 | 33 | 2025-01-17 | 2025-01-17 | 1 | 1 | 4 | 4 | 47 | 35 | 51 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -627 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-15 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 75.08 | -13.07 | Unknown | Unknown | Unknown | 88.15 | 3981 | 1163.53 | 75.08 | 1088.45 | Yes | N/A | N/A | 2024-03-14 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-03-15 | 58 | 42 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-10 | 21 | 15 | 2024-04-10 | 2024-04-10 | 1 | 1 | 7 | 5 | 80 | 58 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -620 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | 2024-12-26 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 1052.41 | 186.88 | Unknown | Unknown | Unknown | 865.53 | Unknown | 1906.67 | 1052.41 | 854.26 | Yes | N/A | N/A | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-14 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-24 | 42 | 30 | 2025-02-24 | 2025-02-24 | 1 | 1 | 21 | 15 | 44 | 32 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -235 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1136.62 | Unknown | Unknown | Unknown | 23.96 | 1112.66 | 2875.23 | 437.62 | 1136.62 | -699 | Yes | N/A | N/A | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | 2023-12-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-19 | 16 | 12 | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-01-17 | Unknown | Unknown | 17 | 13 | 7 | 5 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | -8.82 | -6.67 | Unknown | Unknown | Unknown | -2.15 | Unknown | 497.98 | -8.82 | 506.8 | Yes | N/A | N/A | 2023-10-11 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-10-11 | 44 | 32 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-11-08 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-13 | 36 | 26 | 2023-12-13 | 2023-12-13 | 1 | 1 | 29 | 21 | 81 | 59 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -571 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 26.28 | Unknown | Unknown | Unknown | Unknown | 26.28 | 3981 | 1605.98 | 26.28 | 1579.7 | Yes | N/A | N/A | 2024-08-08 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-08-08 | 92 | 66 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-10-03 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-07 | 5 | 3 | 2024-10-07 | 2024-10-07 | 1 | 1 | 57 | 41 | 98 | 70 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-22 | 2025-02-22 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 62.7 | Unknown | Unknown | Unknown | Unknown | 62.7 | 3981 | 2017.35 | 62.7 | 1954.65 | Yes | N/A | N/A | 2025-02-22 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-22 | 3 | 2 | 2025-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-22 | 2025-04-09 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-15 | 7 | 5 | 2025-04-15 | 2025-04-15 | 1 | 1 | 47 | 33 | 11 | 8 | 58 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -596 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-17 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | -10.29 | -43.21 | Unknown | Unknown | Unknown | 32.92 | 3981 | 1797.26 | -10.29 | 1807.55 | Yes | N/A | N/A | 2024-12-10 | 2024-12-17 | 8 | 6 | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-03-18 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-07 | 21 | 15 | 2025-04-07 | 2025-04-04 | Unknown | Unknown | 100 | 72 | 22 | 16 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | 554 | 397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1924.97 | Unknown | Unknown | Unknown | -732 | 2656.97 | Unknown | 686.03 | 1924.97 | -1238.94 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | 2023-04-20 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-09-19 | 153 | 109 | Unknown | 2023-09-21 | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-09-29 | Unknown | Unknown | 154 | 110 | 57 | 41 | 211 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | 89 | 65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-25 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 12734.43 | 2484.28 | Unknown | Unknown | -518 | 10768.15 | 7962 | 2419.68 | 12734.43 | -10314.75 | Yes | N/A | N/A | 2024-09-24 | 2024-09-25 | 2 | 2 | 2024-09-25 | 2024-10-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2025-03-06 | 156 | 112 | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-24 | 20 | 14 | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 158 | 114 | 28 | 20 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 45.4 | 45.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -542 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 1945.97 | 397.23 | Unknown | Unknown | Unknown | 1548.74 | 3981 | 1651.35 | 1945.97 | -294.62 | Yes | N/A | N/A | 2024-09-25 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-09-25 | 91 | 65 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-04 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-08 | 5 | 3 | 2024-10-08 | 2024-10-08 | 1 | 1 | 10 | 8 | 97 | 69 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 809.05 | 809.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-05 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | 2023-06-24 | IOU Designed & Installed | N/A | No | N/A | 1045.77 | 351.15 | Unknown | 136.21 | Unknown | 558.41 | 3981 | 449.79 | 1045.77 | -595.98 | Yes | N/A | N/A | 2023-01-04 | 2023-02-06 | 34 | 24 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2023-06-24 | 139 | 100 | Unknown | 2023-06-14 | Unknown | Unknown | 2023-06-24 | 2023-06-27 | 4 | 2 | 2023-06-27 | 2023-06-27 | 1 | 1 | 173 | 124 | 5 | 3 | 178 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | 248 | 177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 2403.95 | -15.73 | Unknown | Unknown | 20.62 | 2399.06 | Unknown | 642.1 | 2403.95 | -1761.85 | Yes | N/A | N/A | 2023-06-19 | 2023-07-28 | 40 | 30 | 2023-07-28 | 2023-08-01 | 5 | 3 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2024-02-15 | 199 | 143 | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-03-04 | 19 | 13 | 2024-03-04 | 2024-03-04 | 1 | 1 | 239 | 173 | 25 | 17 | 264 | 190 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | El Cajon | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 228 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-29 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 60690.88 | 4678.03 | Unknown | 96.33 | -7642 | 63558.52 | 0 | 18417.72 | 60690.88 | -42273.16 | Yes | N/A | N/A | 2023-08-28 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-11-22 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-13 | 7 | 5 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-15 | 21 | 15 | 2024-10-15 | 2024-10-15 | 1 | 1 | 0 | 0 | 151 | 109 | 151 | 109 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -635 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 9.17 | Unknown | Unknown | Unknown | Unknown | 9.17 | Unknown | 192.51 | 9.17 | 183.34 | Yes | N/A | N/A | 2024-07-03 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-09 | 21 | 15 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-29 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-16 | 19 | 13 | 2024-09-16 | 2024-09-16 | 1 | 1 | 52 | 38 | 41 | 29 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 383 | 274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-04 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 702.69 | -5.17 | Unknown | Unknown | 31.53 | 676.33 | Unknown | 1439.78 | 702.69 | 737.09 | Yes | N/A | N/A | 2023-08-03 | 2023-10-11 | 70 | 50 | 2023-10-11 | 2024-01-03 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-06-04 | 154 | 110 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-02 | 2024-07-11 | 10 | 8 | 2024-07-11 | 2024-07-10 | Unknown | Unknown | 224 | 160 | 95 | 69 | 319 | 229 | Steps 2,3,5,6,7 | 9 | 7 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -423 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 2470.47 | -3.77 | Unknown | Unknown | 16.09 | 2458.15 | 3981 | 1423.91 | 2470.47 | -1046.56 | Yes | N/A | N/A | 2024-05-20 | 2024-07-15 | 57 | 41 | 2024-07-15 | 2024-07-16 | 2 | 2 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2025-02-10 | 210 | 150 | Unknown | 2025-02-07 | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-02-20 | 1 | 1 | 267 | 191 | 14 | 12 | 281 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-05 | -203 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2024-04-22 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 8436.92 | Unknown | Unknown | Unknown | 102.08 | 8334.84 | 7962 | 581.57 | 8436.92 | -7855.35 | Yes | N/A | N/A | 2023-06-05 | 2024-03-19 | 289 | 207 | 2024-03-19 | 2024-08-29 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-24 | 31 | 23 | 2024-08-29 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-12-16 | 83 | 59 | 2024-12-16 | 2024-10-14 | Unknown | Unknown | 289 | 207 | 278 | 200 | 567 | 407 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -675 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 977.26 | -23.34 | Unknown | Unknown | Unknown | 1000.6 | 3981 | 998.32 | 977.26 | 21.06 | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-13 | 43 | 31 | 2024-06-13 | 2024-06-13 | 1 | 1 | 9 | 7 | 45 | 33 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | Applicant Design | Residential | Underserved Community | Oceanside | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 145 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2022-12-08 | 2024-02-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 32938.51 | 2759.63 | Unknown | Unknown | 23.07 | 30155.81 | 74659 | 19874.67 | 32938.51 | -13063.84 | Yes | N/A | N/A | 2022-12-08 | 2023-05-03 | 147 | 105 | 2023-05-03 | 2024-02-13 | 287 | 205 | 2023-06-30 | 2024-01-08 | 148 | 102 | 2023-05-02 | 2024-03-06 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-25 | 41 | 29 | 2024-03-25 | 2024-03-25 | 1 | 1 | 295 | 207 | 471 | 337 | 766 | 544 | Steps 2,3,5,6,7 | 479 | 341 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -697 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 127.58 | -1.5 | Unknown | Unknown | Unknown | 129.08 | 3981 | 1360.83 | 127.58 | 1233.25 | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-04 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-18 | 15 | 11 | 2024-09-18 | 2024-09-18 | 1 | 1 | 10 | 8 | 17 | 13 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 39.46 | Unknown | Unknown | Unknown | Unknown | 39.46 | 3981 | 1399 | 39.46 | 1359.54 | Yes | N/A | N/A | 2024-07-08 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-09 | 5 | 3 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-03-18 | 253 | 181 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-09 | 23 | 17 | 2025-04-09 | 2025-04-09 | 1 | 1 | 253 | 181 | 29 | 21 | 282 | 202 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -607 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-18 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 12.19 | Unknown | Unknown | Unknown | Unknown | 12.19 | Unknown | 192.95 | 12.19 | 180.76 | Yes | N/A | N/A | 2024-07-09 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-23 | 42 | 30 | 2024-09-23 | 2024-09-23 | 1 | 1 | 7 | 5 | 43 | 31 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | -158 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-15 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 91.89 | -1.88 | Unknown | Unknown | Unknown | 93.77 | Unknown | 778.9 | 91.89 | 687.01 | Yes | N/A | N/A | 2023-11-14 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-11-15 | 150 | 108 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-26 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-03 | 9 | 7 | 2024-01-03 | 2024-01-03 | 1 | 1 | 42 | 30 | 160 | 116 | 202 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-30 | 126 | 91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2023-02-27 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 1627 | -4.67 | Unknown | Unknown | 34.62 | 1597.05 | 3981 | 515.49 | 1627 | -1111.51 | Yes | N/A | N/A | 2022-08-01 | 2023-02-27 | 211 | 151 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-03-01 | 3 | 3 | 2024-03-29 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2024-07-08 | 357 | 255 | 2024-07-08 | 2023-05-05 | Unknown | Unknown | 211 | 151 | 360 | 258 | 571 | 409 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -533 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2023-04-27 | IOU Designed & Installed | N/A | No | N/A | -3.54 | -10.45 | Unknown | Unknown | Unknown | 6.91 | 3981 | 816.99 | -3.54 | 820.53 | Yes | N/A | N/A | 2023-04-05 | 2023-04-05 | 1 | 1 | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-04-27 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-08-18 | 114 | 82 | 2023-08-18 | 2023-08-18 | 1 | 1 | 24 | 18 | 115 | 83 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-23 | -200 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1267.55 | 1778.16 | Unknown | 385.2 | -4124 | 693.09 | Unknown | 4123.6 | -1267.55 | 5391.15 | Yes | N/A | N/A | 2023-05-02 | 2023-05-03 | 2 | 2 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 207.05 | 207.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-09 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 23.74 | Unknown | Unknown | Unknown | Unknown | 23.74 | Unknown | 1537.12 | 23.74 | 1513.38 | Yes | N/A | N/A | 2025-01-07 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-09 | 4 | 4 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-23 | 7 | 5 | 2025-01-23 | 2025-01-23 | 1 | 1 | 9 | 7 | 12 | 10 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -480 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | 2164.6 | 575.75 | Unknown | Unknown | Unknown | 1588.85 | Unknown | 1293.28 | 2164.6 | -871.32 | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-04-23 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-06-06 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-10 | 5 | 3 | 2025-06-10 | 2025-06-10 | 1 | 1 | 175 | 127 | 7 | 5 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-05-15 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | -19.31 | -15.66 | Unknown | Unknown | Unknown | -3.65 | 19905 | 984.98 | -19.31 | 1004.29 | Yes | N/A | N/A | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | 2024-06-19 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-07-11 | 37 | 27 | 2024-07-11 | 2024-06-20 | Unknown | Unknown | 3 | 3 | 121 | 87 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | -192 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-06-27 | IOU Designed & Installed | N/A | No | N/A | 8366.57 | 175.06 | Unknown | Unknown | 1.96 | 8189.55 | Unknown | 5052.18 | 8366.57 | -3314.39 | Yes | N/A | N/A | 2023-06-16 | 2023-06-16 | 1 | 1 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-27 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-08-24 | 59 | 43 | 2023-08-24 | 2023-08-24 | 1 | 1 | 13 | 9 | 60 | 44 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 104 | 104 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | 119 | 86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.34 | -3.87 | Unknown | Unknown | Unknown | 8.21 | 3981 | 1034.07 | 4.34 | 1029.73 | Yes | N/A | N/A | 2023-08-23 | 2024-01-02 | 133 | 95 | 2024-01-02 | 2024-01-02 | 1 | 1 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-06-18 | Unknown | Unknown | 133 | 95 | 1 | 1 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 270 | 193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-09-05 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 4766.41 | Unknown | Unknown | Unknown | Unknown | 4766.41 | 20184 | 2784.96 | 4766.41 | -1981.45 | Yes | N/A | N/A | 2023-08-24 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-12-05 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-13 | 1 | 1 | 2023-12-05 | 2024-07-03 | 212 | 152 | Unknown | 2024-07-31 | Unknown | Unknown | 2024-09-25 | 2024-11-27 | 64 | 46 | 2024-11-27 | 2024-11-26 | Unknown | Unknown | 212 | 152 | 200 | 144 | 412 | 296 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-20 | -634 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 739.29 | Unknown | Unknown | Unknown | Unknown | 739.29 | 3981 | 1106.45 | 739.29 | 367.16 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-30 | 49 | 35 | Unknown | 2024-09-27 | Unknown | Unknown | 2024-09-30 | 2024-10-24 | 25 | 19 | 2024-10-24 | 2024-10-24 | 1 | 1 | 50 | 36 | 27 | 21 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 339.2 | 339.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 323 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 62.12 | Unknown | Unknown | Unknown | Unknown | 62.12 | 7962 | 1411.13 | 62.12 | 1349.01 | Yes | N/A | N/A | 2024-07-11 | 2024-04-14 | Unknown | Unknown | 2024-04-14 | 2024-08-29 | 138 | 99 | 2024-07-12 | 2024-07-15 | 4 | 2 | 2024-07-11 | 2024-07-17 | 5 | 5 | 2024-08-29 | 2024-11-07 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-19 | Unknown | Unknown | 75 | 53 | 143 | 104 | 218 | 157 | Steps 2,3,5,6,7 | 52 | 36 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -59 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.82 | Unknown | Unknown | Unknown | Unknown | 7.82 | Unknown | 158.79 | 7.82 | 150.97 | Yes | N/A | N/A | 2024-01-04 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-05 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 206 | 206 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | 194 | 139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1219.69 | Unknown | Unknown | Unknown | -1223 | 3.31 | 0 | 1223.33 | -1219.69 | 2443.02 | Yes | N/A | N/A | 2023-08-30 | 2023-09-01 | 3 | 3 | 2023-09-01 | 2024-12-09 | 466 | 332 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-12-04 | 34 | 24 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 3 | 3 | 501 | 357 | 504 | 360 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-13 | 296 | 213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-19 | 2023-02-13 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 493.37 | -17.44 | Unknown | Unknown | Unknown | 510.81 | 2841 | 462.26 | 493.37 | -31.11 | Yes | N/A | N/A | 2021-12-19 | 2023-02-13 | 422 | 301 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-09-19 | 7 | 5 | 2023-09-13 | 2023-09-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-05 | 8 | 6 | 2023-10-05 | 2023-10-05 | 1 | 1 | 438 | 313 | 16 | 12 | 454 | 325 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | 613 | 438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 554.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | 2024-06-28 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-08 | 11 | 7 | Unknown | 2024-07-02 | Unknown | Unknown | 2024-07-09 | 2024-07-23 | 15 | 11 | 2024-07-23 | 2024-07-09 | Unknown | Unknown | 12 | 8 | 30 | 22 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -120 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-26 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 2.46 | -2.21 | Unknown | Unknown | Unknown | 4.67 | Unknown | 287.46 | 2.46 | 285 | Yes | N/A | N/A | 2024-01-16 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2024-01-26 | 116 | 84 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-05-14 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-29 | 16 | 12 | 2024-05-29 | 2024-05-29 | 1 | 1 | 110 | 78 | 133 | 97 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 56 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-07-12 | IOU Designed & Installed | N/A | No | N/A | 4637.3 | Unknown | Unknown | Unknown | -236 | 4873.3 | Unknown | 282.53 | 4637.3 | -4354.77 | Yes | N/A | N/A | 2023-02-08 | 2023-02-13 | 6 | 4 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-12 | 2023-07-21 | 10 | 8 | 2023-07-21 | 2023-07-27 | 7 | 5 | 6 | 4 | 17 | 13 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 270.05 | 270.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 161.92 | -0.62 | Unknown | Unknown | Unknown | 162.54 | 7962 | 780.32 | 161.92 | 618.4 | Yes | N/A | N/A | 2024-10-29 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-11-14 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-27 | 22 | 16 | 2024-11-14 | 2025-03-11 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 118 | 84 | 94 | 68 | 212 | 152 | Steps 2,3,5,6,7 | 105 | 75 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | -105 | -76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 670.03 | -7.57 | Unknown | Unknown | 4.87 | 672.73 | 3981 | 1978.2 | 670.03 | 1308.17 | Yes | N/A | N/A | 2023-05-23 | 2023-06-26 | 35 | 25 | 2023-06-26 | 2023-07-03 | 8 | 6 | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-10-27 | 117 | 85 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-10-27 | 2023-11-15 | 20 | 14 | 2023-11-15 | 2023-11-15 | 1 | 1 | 152 | 110 | 29 | 21 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 628.16 | -28.53 | Unknown | Unknown | Unknown | 656.69 | 3981 | 854.45 | 628.16 | 226.29 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-20 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-02-06 | 49 | 35 | 2024-02-06 | 2024-02-06 | 1 | 1 | 36 | 26 | 51 | 37 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 125 | 125 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -113 | -82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.12 | -8.04 | Unknown | Unknown | 1.76 | 14.4 | 3981 | 2151.66 | 8.12 | 2143.54 | Yes | N/A | N/A | 2023-12-12 | 2024-01-05 | 25 | 19 | 2024-01-05 | 2024-01-05 | 1 | 1 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-17 | 1 | 1 | 25 | 19 | 2 | 2 | 27 | 21 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-08 | 132 | 95 | No | 2022-05-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | 2022-05-24 | Unknown | IOU Designed & Installed | N/A | Yes | 339 | -1.68 | -4.98 | Unknown | Unknown | Unknown | 3.3 | 3885 | 842.91 | -1.68 | 844.59 | Yes | N/A | N/A | 2022-05-24 | 2023-04-28 | 340 | 244 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 340 | 244 | 1 | 1 | 341 | 245 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-20 | 136 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2022-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.08 | -8.4 | Unknown | Unknown | 5.41 | 4.07 | 3981 | 1990.45 | 1.08 | 1989.37 | Yes | N/A | N/A | 2022-11-08 | 2023-04-24 | 168 | 120 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 168 | 120 | 1 | 1 | 169 | 121 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -441 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 1022.3 | Unknown | Unknown | Unknown | 23.89 | 998.41 | 3981 | 1185.5 | 1022.3 | 163.2 | Yes | N/A | N/A | 2023-12-27 | 2024-03-12 | 77 | 55 | 2024-03-12 | 2024-03-18 | 7 | 5 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-07-18 | 123 | 89 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-18 | 2024-08-08 | 22 | 16 | 2024-08-08 | 2024-07-25 | Unknown | Unknown | 200 | 144 | 29 | 21 | 229 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 43 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 506.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-14 | 4 | 4 | 2025-02-14 | 2025-03-03 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-03 | 18 | 12 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 4 | 4 | 37 | 25 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-24 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 739.91 | -14.73 | Unknown | Unknown | 29.59 | 725.05 | 3981 | 1089.63 | 739.91 | 349.72 | Yes | N/A | N/A | 2023-09-26 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-10-04 | 56 | 40 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2024-03-01 | 150 | 108 | Unknown | 2024-02-15 | Unknown | Unknown | 2024-03-01 | 2024-03-28 | 28 | 20 | 2024-03-28 | 2024-03-28 | 1 | 1 | 150 | 108 | 85 | 61 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 819.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-05-27 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-03-26 | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-06-18 | 2025-06-20 | 3 | 3 | 2025-06-20 | 2025-06-19 | Unknown | Unknown | 1 | 1 | 51 | 37 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -479 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-21 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 1581.9 | Unknown | Unknown | Unknown | 24.43 | 1557.47 | 3941 | 1128.11 | 1581.9 | -453.79 | Yes | N/A | N/A | 2024-05-17 | 2024-09-20 | 127 | 91 | 2024-09-20 | 2024-09-23 | 4 | 2 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-22 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-21 | 31 | 23 | 2024-11-21 | 2024-10-30 | Unknown | Unknown | 157 | 113 | 35 | 25 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -551 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 9049.42 | -24 | Unknown | Unknown | Unknown | 9073.42 | Unknown | 8942.45 | 9049.42 | -106.97 | Yes | N/A | N/A | 2024-06-04 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-20 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-07 | 2 | 2 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-09 | 19 | 13 | 2024-09-09 | 2024-09-09 | 1 | 1 | 0 | 0 | 40 | 30 | 40 | 30 | Steps 2,3,5,6,7 | 48 | 34 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 1019.24 | 378.15 | Unknown | Unknown | Unknown | 641.09 | Unknown | 847.46 | 1019.24 | -171.78 | Yes | N/A | N/A | 2023-05-15 | 2023-05-15 | 1 | 1 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-07-27 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-01 | 6 | 4 | 2023-08-01 | 2023-08-01 | 1 | 1 | 75 | 55 | 7 | 5 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | -691 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 493.41 | -8.7 | Unknown | Unknown | Unknown | 502.11 | 3981 | 1557.39 | 493.41 | 1063.98 | Yes | N/A | N/A | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-18 | 13 | 9 | 2025-03-18 | 2025-03-18 | 1 | 1 | 15 | 11 | 15 | 11 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-05 | -316 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 281.51 | Unknown | Unknown | Unknown | 18.5 | 263.01 | 0 | 1296.31 | 281.51 | 1014.8 | Yes | N/A | N/A | 2023-12-01 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2024-01-17 | 121 | 87 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1 | 1 | 0 | 0 | 122 | 88 | 122 | 88 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -633 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-04 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | -9.9 | -8.06 | Unknown | Unknown | Unknown | -1.84 | 3981 | 850.59 | -9.9 | 860.49 | Yes | N/A | N/A | 2024-03-27 | 2024-04-04 | 9 | 7 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-11 | 8 | 6 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-04-11 | 2024-04-29 | 19 | 13 | 2024-04-29 | 2024-04-29 | 1 | 1 | 17 | 13 | 21 | 15 | 38 | 28 | Steps 2,3,5,6,7 | 328 | 234 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 83.3 | 83.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-18 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 18041.41 | Unknown | Unknown | Unknown | Unknown | 18041.41 | 37616 | 2040.34 | 18041.41 | -16001.07 | Yes | N/A | N/A | 2024-07-15 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-07-23 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2025-01-29 | 185 | 133 | 2025-01-29 | 2025-01-29 | 1 | 1 | 0 | 0 | 207 | 149 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 928 | 663 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 459.15 | -9.24 | Unknown | Unknown | 13.03 | 455.36 | 3981 | 2969.37 | 459.15 | 2510.22 | Yes | N/A | N/A | 2023-04-14 | 2023-03-09 | Unknown | Unknown | 2023-03-09 | 2023-04-21 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-07-05 | 76 | 54 | Unknown | 2023-06-27 | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-07-17 | Unknown | Unknown | 76 | 54 | 44 | 32 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-02 | -318 | -227 | No | 2022-07-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-06 | 2022-07-06 | 2023-06-14 | IOU Designed & Installed | N/A | Yes | 336 | 5211.93 | -100.31 | Unknown | Unknown | -345.4 | 5657.64 | Unknown | 589.93 | 5211.93 | -4622 | Yes | N/A | N/A | 2022-07-06 | 2023-07-20 | 380 | 272 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-07-25 | 2023-06-14 | Unknown | Unknown | Unknown | 2023-07-03 | Unknown | Unknown | 2023-06-14 | 2023-07-20 | 37 | 27 | 2023-07-20 | 2023-07-20 | 1 | 1 | 380 | 272 | 38 | 28 | 418 | 300 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | Unknown | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 2049.55 | -40.61 | Unknown | Unknown | Unknown | 2090.16 | 3981 | 1654.49 | 2049.55 | -395.06 | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | Unknown | Unknown | Unknown | 2024-08-08 | 2024-09-12 | 36 | 26 | 2024-08-08 | 2024-09-17 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-15 | 29 | 21 | 2024-10-15 | 2024-10-15 | 1 | 1 | 42 | 30 | 67 | 49 | 109 | 79 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -533 | -382 | No | 2024-03-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-19 | 2024-06-10 | IOU Designed & Installed | N/A | Yes | 34 | -12.7 | -10.31 | Unknown | Unknown | Unknown | -2.39 | 3981 | 963.73 | -12.7 | 976.43 | Yes | N/A | N/A | 2024-03-28 | 2024-04-17 | 21 | 15 | 2024-04-17 | 2024-05-01 | 15 | 11 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-06-10 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-18 | 9 | 7 | 2024-06-18 | 2024-08-14 | 58 | 42 | 74 | 52 | 82 | 60 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 64154.81 | 12666.86 | Unknown | 285.78 | -63391 | 114593.17 | Unknown | 67219.13 | 64154.81 | 3064.32 | Yes | N/A | N/A | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | 2024-06-28 | 193 | 139 | 2024-04-12 | 2024-04-23 | 12 | 8 | 2024-07-08 | 2024-07-12 | 5 | 5 | 2024-07-12 | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | 2024-09-26 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-19 | 1 | 1 | 13 | 9 | 199 | 145 | 212 | 154 | Steps 2,3,5,6,7 | 77 | 55 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-06 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 2176.21 | 532.2 | Unknown | Unknown | Unknown | 1644.01 | 3981 | 1440.56 | 2176.21 | -735.65 | Yes | N/A | N/A | 2024-09-05 | 2024-09-06 | 2 | 2 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-05-19 | 256 | 182 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | 2025-05-19 | 1 | 1 | 258 | 184 | 3 | 3 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 240.4 | 240.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -446 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 7031.92 | 3147.96 | Unknown | 1059.52 | Unknown | 2824.44 | 3981 | 879.52 | 7031.92 | -6152.4 | Yes | N/A | N/A | 2023-06-05 | 2023-06-05 | 1 | 1 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-10-04 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-10-09 | 6 | 4 | 2023-10-09 | 2023-10-09 | 1 | 1 | 123 | 89 | 7 | 5 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | -274 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-23 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | -2915.21 | 2877.84 | Unknown | 244.17 | -7260 | 1222.78 | Unknown | 7260.14 | -2915.21 | 10175.35 | Yes | N/A | N/A | 2024-10-18 | 2024-10-23 | 6 | 4 | 2024-10-23 | 2025-01-17 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-17 | 1 | 1 | 2024-12-18 | 2025-01-17 | 31 | 23 | 2025-01-17 | 2025-01-17 | 1 | 1 | 6 | 4 | 120 | 88 | 126 | 92 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 722 | 517 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 85602.76 | 30051.43 | Unknown | Unknown | 14.9 | 55536.43 | 495230 | 30946.5 | 85602.76 | -54656.26 | Yes | N/A | N/A | 2023-03-20 | 2023-03-28 | 9 | 7 | 2023-03-28 | 2024-06-26 | 457 | 327 | 2023-10-18 | 2025-08-20 | 3 | 3 | 2023-10-24 | 2025-06-19 | 334 | 240 | 2024-06-26 | Unknown | Unknown | Unknown | 2024-11-26 | 2025-04-29 | 155 | 111 | 2025-06-05 | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-23 | 1 | 1 | 12 | 10 | 947 | 679 | 959 | 689 | Steps 2,3,5,6,7 | 1276 | 912 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-05-14 | 980 | 701 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9.24 | -11.64 | Unknown | Unknown | Unknown | 20.88 | 3981 | 1095.25 | 9.24 | 1086.01 | Yes | N/A | N/A | 2023-05-31 | 2023-06-13 | 14 | 10 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-01-19 | Unknown | Unknown | 14 | 10 | 0 | 0 | 14 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | -415 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-11-30 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 610.9 | -18.55 | Unknown | Unknown | Unknown | 629.45 | 3981 | 1228.13 | 610.9 | 617.23 | Yes | N/A | N/A | 2023-07-27 | 2023-05-12 | Unknown | Unknown | 2023-05-12 | 2023-11-30 | 203 | 145 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-02-26 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-14 | 18 | 14 | 2024-03-14 | 2024-03-04 | Unknown | Unknown | 89 | 63 | 221 | 159 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Agricultural | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-13 | 999 | 714 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 177.57 | -6.48 | Unknown | Unknown | -451 | 635.05 | Unknown | 398.35 | 177.57 | 220.78 | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-04-24 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-03-19 | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-20 | 15 | 11 | 2024-05-20 | 2024-05-08 | Unknown | Unknown | 1 | 1 | 99 | 71 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -648 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-11-01 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | -1771.69 | Unknown | Unknown | Unknown | -1799 | 27.31 | Unknown | 1667.93 | -1771.69 | 3439.62 | Yes | N/A | N/A | 2024-10-22 | 2024-11-01 | 11 | 9 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2024-11-26 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-11-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-11 | 15 | 11 | 2024-12-11 | 2024-12-11 | 1 | 1 | 39 | 29 | 17 | 13 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | CALTRANS-NORTH of 56, COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -311 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-26 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 3371.19 | 781.79 | Unknown | 56.56 | Unknown | 2532.84 | Unknown | 718.08 | 3371.19 | -2653.11 | Yes | N/A | N/A | 2023-05-24 | 2023-06-16 | 24 | 18 | 2023-06-16 | 2023-06-28 | 13 | 9 | 2023-06-28 | Unknown | Unknown | Unknown | 2023-07-14 | 2023-08-21 | 39 | 27 | 2023-06-26 | 2023-12-19 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-03-27 | 100 | 72 | 2024-03-27 | 2024-03-27 | 1 | 1 | 201 | 145 | 153 | 109 | 354 | 254 | Steps 2,3,5,6,7 | 56 | 40 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 949 | 678 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 352.9 | -0.31 | Unknown | Unknown | Unknown | 353.21 | 0 | 439.25 | 352.9 | 86.35 | Yes | N/A | N/A | 2023-08-22 | 2024-03-11 | 203 | 145 | 2024-03-11 | 2025-02-11 | 338 | 242 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-28 | 32 | 22 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1 | 1 | 203 | 145 | 371 | 265 | 574 | 410 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Imperial Beach | N/A | 131164 | 131164 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-09-26 | 710 | 509 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 25791.37 | 4734.55 | Unknown | Unknown | 128.34 | 20928.48 | 30254 | Not available | 25791.37 | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-12-01 | 206 | 148 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-07-11 | 224 | 160 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-06 | 2024-10-16 | 41 | 29 | 2024-10-16 | 2024-09-05 | Unknown | Unknown | 224 | 160 | 247 | 177 | 471 | 337 | Steps 2,3,5,6,7 | 24 | 16 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 261 | 261 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-02 | 677 | 484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 75.55 | -14.27 | Unknown | Unknown | 82.88 | 6.94 | 15924 | 483.23 | 75.55 | 407.68 | Yes | N/A | N/A | 2023-03-06 | 2023-02-27 | Unknown | Unknown | 2023-02-27 | 2023-05-23 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-09-25 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-10-10 | Unknown | Unknown | 126 | 90 | 86 | 62 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 1941.63 | 606.36 | Unknown | Unknown | Unknown | 1335.27 | Unknown | 435.21 | 1941.63 | -1506.42 | Yes | N/A | N/A | 2024-05-21 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-05-21 | 40 | 28 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-03 | 6 | 4 | 2024-06-03 | 2024-06-03 | 1 | 1 | 9 | 7 | 47 | 33 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-28 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 26.87 | Unknown | Unknown | Unknown | Unknown | 26.87 | 3981 | 1051.55 | 26.87 | 1024.68 | Yes | N/A | N/A | 2024-08-16 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-08-28 | 14 | 10 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-06 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-16 | 11 | 7 | 2024-09-16 | 2024-08-13 | Unknown | Unknown | 10 | 8 | 25 | 17 | 35 | 25 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | 155 | 112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 721.93 | 210.69 | Unknown | 88.44 | 9.16 | 413.64 | 3981 | 2029.24 | 721.93 | 1307.31 | Yes | N/A | N/A | 2023-08-03 | 2023-08-31 | 29 | 21 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-18 | 1 | 1 | 29 | 21 | 2 | 2 | 31 | 23 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -558 | -399 | No | 2022-03-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-24 | 2022-03-30 | Unknown | IOU Designed & Installed | N/A | Yes | 426 | 839.25 | -30.41 | Unknown | Unknown | 18.4 | 851.26 | Unknown | 1030.75 | 839.25 | 191.5 | Yes | N/A | N/A | 2022-03-24 | 2023-05-24 | 427 | 305 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-22 | 1 | 1 | 427 | 305 | 1 | 1 | 428 | 306 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | -135 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.76 | -4.9 | Unknown | Unknown | Unknown | -1.86 | Unknown | 341 | -6.76 | 347.76 | Yes | N/A | N/A | 2023-02-28 | 2023-03-07 | 8 | 6 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-08-16 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -10.25 | -7.44 | Unknown | Unknown | Unknown | -2.81 | 3981 | 341 | -10.25 | 351.25 | Yes | N/A | N/A | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 3952.33 | 965.97 | Unknown | 40.59 | 0.18 | 2945.59 | 3981 | 2064.69 | 3952.33 | -1887.64 | Yes | N/A | N/A | 2024-12-16 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-18 | 13 | 9 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-23 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-02-04 | 44 | 32 | 2025-02-04 | 2025-02-04 | 1 | 1 | 6 | 4 | 58 | 42 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 28.1 | 28.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -529 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 1337.21 | Unknown | Unknown | Unknown | 10.3 | 1326.91 | 3981 | 3350.61 | 1337.21 | 2013.4 | Yes | N/A | N/A | 2024-10-22 | 2024-11-26 | 36 | 26 | 2024-11-26 | 2024-12-18 | 23 | 17 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-04-02 | 106 | 76 | Unknown | 2025-03-18 | Unknown | Unknown | 2025-04-02 | 2025-04-14 | 13 | 9 | 2025-04-14 | 2025-04-14 | 1 | 1 | 142 | 102 | 37 | 27 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 17.85 | Unknown | Unknown | Unknown | Unknown | 17.85 | 3981 | 1032.15 | 17.85 | 1014.3 | Yes | N/A | N/A | 2024-12-06 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-12-06 | 32 | 24 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-03-03 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-18 | 16 | 12 | 2025-03-18 | 2025-03-18 | 1 | 1 | 88 | 62 | 49 | 37 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | -276 | -199 | No | 2023-12-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | Yes | 173 | 671.79 | -11.43 | Unknown | Unknown | Unknown | 683.22 | 3981 | 1118.89 | 671.79 | 447.1 | Yes | N/A | N/A | 2023-12-20 | 2024-06-10 | 174 | 124 | 2024-06-10 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-07 | Unknown | Unknown | 174 | 124 | 0 | 0 | 174 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | -4.46 | -5.47 | Unknown | Unknown | Unknown | 1.01 | Unknown | 163.83 | -4.46 | 168.29 | Yes | N/A | N/A | 2024-02-13 | 2024-02-13 | 1 | 1 | 2024-02-13 | 2024-03-04 | 21 | 15 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-05-03 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-15 | 13 | 9 | 2024-05-15 | 2024-05-15 | 1 | 1 | 62 | 46 | 35 | 25 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 2159.14 | 1371.24 | Unknown | 77.81 | Unknown | 710.09 | 3981 | 197.01 | 2159.14 | -1962.13 | Yes | N/A | N/A | 2024-10-01 | 2024-10-08 | 8 | 6 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-21 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-24 | 4 | 4 | 2024-10-24 | 2024-10-24 | 1 | 1 | 22 | 16 | 6 | 6 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | 209 | 150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-19 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 169.89 | 279.33 | Unknown | Unknown | -461 | 351.56 | 3981 | 1542.4 | 169.89 | 1372.51 | Yes | N/A | N/A | 2023-04-12 | 2023-02-17 | Unknown | Unknown | 2023-02-17 | 2023-06-14 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-05-16 | 163 | 117 | 2023-06-14 | 2024-05-09 | 331 | 237 | Unknown | 2024-04-12 | Unknown | Unknown | 2024-05-28 | 2024-05-30 | 3 | 3 | 2024-05-30 | 2024-05-30 | 1 | 1 | 331 | 237 | 285 | 205 | 616 | 442 | Steps 2,3,5,6,7 | 337 | 241 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -454 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-05-10 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 706.18 | 341.51 | Unknown | 16.12 | Unknown | 348.55 | Unknown | 901.16 | 706.18 | 194.98 | Yes | N/A | N/A | 2024-04-19 | 2024-05-10 | 22 | 16 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-10 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-07-01 | 22 | 16 | 2024-07-01 | 2024-07-01 | 1 | 1 | 54 | 38 | 24 | 18 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1421.14 | 252.5 | Unknown | 99.31 | 26.65 | 1042.68 | 7962 | 1111.17 | 1421.14 | -309.97 | Yes | N/A | N/A | 2023-12-06 | 2023-12-06 | 1 | 1 | 2023-12-06 | 2024-02-01 | 58 | 42 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-07-18 | 1 | 1 | 1 | 1 | 59 | 43 | 60 | 44 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-06-18 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 612.37 | -11.7 | Unknown | Unknown | Unknown | 624.07 | Unknown | 1539.47 | 612.37 | 927.1 | Yes | N/A | N/A | 2024-04-22 | 2024-06-18 | 58 | 42 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-08-28 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-10 | 14 | 10 | 2024-09-10 | 2024-09-10 | 1 | 1 | 130 | 94 | 16 | 12 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 146.36 | Unknown | Unknown | Unknown | -1303 | 1449.36 | Unknown | 1302.72 | 146.36 | 1156.36 | Yes | N/A | N/A | 2024-10-30 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-11-05 | 28 | 20 | 2024-11-05 | 2024-12-17 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-02-05 | 51 | 37 | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-20 | 16 | 12 | 2025-02-20 | 2025-02-20 | 1 | 1 | 94 | 68 | 45 | 33 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 20389.2 | 20389.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-06-05 | -352 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3941 | 1407.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-30 | 21 | 15 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2025-06-09 | 315 | 225 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-18 | 10 | 8 | 2025-06-18 | 2025-06-18 | 1 | 1 | 315 | 225 | 32 | 24 | 347 | 249 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-08-16 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 15662.5 | 1480.38 | Unknown | Unknown | -792.99 | 14975.11 | 87719 | 21127.68 | 15662.5 | 5465.18 | Yes | N/A | N/A | 2023-03-10 | 2023-05-03 | 55 | 39 | 2023-05-03 | 2024-02-14 | 288 | 206 | 2023-11-21 | 2024-01-08 | 7 | 5 | 2023-11-28 | 2024-02-20 | 62 | 46 | 2024-02-14 | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-03 | 10 | 8 | 2024-05-07 | 2024-05-24 | 18 | 14 | 2024-05-24 | 2024-05-24 | 1 | 1 | 62 | 44 | 379 | 275 | 441 | 319 | Steps 2,3,5,6,7 | 132 | 94 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | -3.66 | -4.45 | Unknown | Unknown | Unknown | 0.79 | Unknown | 148.7 | -3.66 | 152.36 | Yes | N/A | N/A | 2023-07-18 | 2023-09-19 | 64 | 46 | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-11-09 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-15 | 7 | 5 | 2023-11-15 | 2023-11-15 | 1 | 1 | 116 | 84 | 9 | 7 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | 117 | 84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -532.58 | 2275.79 | Unknown | 660.76 | -4402 | 932.87 | 0 | 4402.26 | -532.58 | 4934.84 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 177 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-30 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 554.2 | -16.6 | Unknown | Unknown | Unknown | 570.8 | 3981 | 1692.49 | 554.2 | 1138.29 | Yes | N/A | N/A | 2023-06-22 | 2023-06-30 | 9 | 7 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-08-10 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-25 | 16 | 12 | 2023-08-25 | 2023-08-25 | 1 | 1 | 51 | 37 | 18 | 14 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | -220 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 816.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-01-24 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-01-26 | 3 | 3 | 2024-01-26 | 2024-01-26 | 1 | 1 | 121 | 87 | 5 | 5 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1392 | 995 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 110.29 | -0.94 | Unknown | Unknown | Unknown | 111.23 | Unknown | 4024.93 | 110.29 | 3914.64 | Yes | N/A | N/A | 2024-07-31 | 2024-08-08 | 9 | 7 | 2024-08-08 | 2024-09-23 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-12 | 35 | 25 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-10-23 | 1 | 1 | 9 | 7 | 83 | 59 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 26.83 | Unknown | Unknown | Unknown | Unknown | 26.83 | 3981 | 1574.85 | 26.83 | 1548.02 | Yes | N/A | N/A | 2024-07-23 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-07-25 | 8 | 6 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-26 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-12 | 18 | 12 | 2024-08-12 | 2024-08-12 | 1 | 1 | 3 | 3 | 27 | 19 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 769 | -14.67 | Unknown | Unknown | Unknown | 783.67 | 3981 | 1561.26 | 769 | 792.26 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-15 | 12 | 10 | 2024-11-15 | 2024-11-15 | 1 | 1 | 5 | 3 | 14 | 12 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | 90 | 65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | 2024-11-19 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 10426.2 | 714.12 | Unknown | 79.66 | 263.09 | 9369.33 | 32417.5 | 9779.88 | 10426.2 | -646.32 | Yes | N/A | N/A | 2022-12-12 | 2023-04-13 | 123 | 89 | 2023-04-13 | 2023-11-17 | 219 | 157 | 2023-04-24 | 2023-11-14 | 144 | 102 | 2024-09-30 | 2024-10-09 | 10 | 8 | 2024-08-15 | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-25 | 42 | 30 | 2024-11-19 | 2024-12-26 | 38 | 28 | 2024-12-26 | 2024-12-26 | 1 | 1 | 267 | 191 | 310 | 224 | 577 | 415 | Steps 2,3,5,6,7 | 262 | 188 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-18 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 411.22 | -9.57 | Unknown | Unknown | Unknown | 420.79 | 3981 | 1072.03 | 411.22 | 660.81 | Yes | N/A | N/A | 2024-04-12 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-04-18 | 58 | 42 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-06-07 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-27 | 21 | 15 | 2024-06-27 | 2024-06-27 | 1 | 1 | 51 | 37 | 80 | 58 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-20 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 1614.45 | 241.68 | Unknown | 31.53 | -644.99 | 1986.23 | Unknown | 605.91 | 1614.45 | -1008.54 | Yes | N/A | N/A | 2024-05-17 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-06-03 | 85 | 61 | 2024-06-03 | 2024-06-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-07-18 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-22 | 5 | 3 | 2024-07-22 | 2024-07-22 | 1 | 1 | 47 | 35 | 91 | 65 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -550 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1559.36 | 399.19 | Unknown | Unknown | Unknown | 1160.17 | Unknown | 1683.03 | 1559.36 | 123.67 | Yes | N/A | N/A | 2024-09-10 | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-09-30 | 68 | 48 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-01-21 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | 2025-01-21 | 1 | 1 | 114 | 82 | 70 | 50 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 5.69 | Unknown | Unknown | Unknown | Unknown | 5.69 | Unknown | 1050.75 | 5.69 | 1045.06 | Yes | N/A | N/A | 2024-08-21 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-08-21 | 2 | 2 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-08-28 | 7 | 5 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2 | 2 | 10 | 8 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 243.72 | -2.19 | Unknown | Unknown | 1.29 | 244.62 | 3981 | 158.37 | 243.72 | -85.35 | Yes | N/A | N/A | 2023-07-17 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2024-04-19 | 372 | 266 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-07 | Unknown | Unknown | 0 | 0 | 372 | 266 | 372 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 1774.86 | Unknown | Unknown | Unknown | 4.84 | 1770.02 | 3941 | 1252.06 | 1774.86 | -522.8 | Yes | N/A | N/A | 2024-08-06 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-08-19 | 39 | 27 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-09 | 22 | 16 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-09-09 | 2024-10-17 | 39 | 29 | 2024-10-17 | 2024-10-16 | Unknown | Unknown | 22 | 16 | 78 | 56 | 100 | 72 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -388 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-01-02 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 830.95 | -15.58 | Unknown | Unknown | Unknown | 846.53 | 3981 | 660.7 | 830.95 | -170.25 | Yes | N/A | N/A | 2023-12-13 | 2023-12-29 | 17 | 13 | 2023-12-29 | 2024-01-02 | 5 | 3 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-07-03 | 184 | 132 | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-03 | 2024-07-18 | 16 | 12 | 2024-07-18 | 2024-07-18 | 1 | 1 | 201 | 145 | 22 | 16 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 500 | 500 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | 251 | 180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 31848 | 788.08 | Unknown | 788.08 | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-09 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-17 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 41 | 29 | 6 | 6 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1712.2 | Unknown | Unknown | Unknown | 30.57 | 1681.63 | 3981 | 1027.81 | 1712.2 | -684.39 | Yes | N/A | N/A | 2024-04-04 | 2023-12-31 | Unknown | Unknown | 2023-12-31 | 2024-04-19 | 111 | 80 | 2024-04-19 | 2024-06-27 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-06 | 1 | 1 | 70 | 50 | 112 | 81 | 182 | 131 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -332 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2385.25 | Unknown | Unknown | Unknown | Unknown | 2385.25 | Unknown | 501.14 | 2385.25 | -1884.11 | Yes | N/A | N/A | 2024-02-13 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-03-27 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 0 | 0 | 50 | 36 | 50 | 36 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41.85 | 41.85 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -606 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 1322.56 | Unknown | Unknown | Unknown | 18.13 | 1304.43 | 3981 | 1158.77 | 1322.56 | -163.79 | Yes | N/A | N/A | 2024-08-22 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-09-23 | 54 | 38 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-11-18 | 57 | 41 | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-18 | 2024-12-02 | 15 | 11 | 2024-12-02 | 2024-11-25 | Unknown | Unknown | 57 | 41 | 69 | 49 | 126 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -185 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-10-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 423.79 | -7.95 | Unknown | Unknown | Unknown | 431.74 | 7962 | 427.74 | 423.79 | 3.95 | Yes | N/A | N/A | 2023-06-26 | 2023-08-24 | 60 | 44 | 2023-08-24 | 2024-07-08 | 320 | 228 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-15 | 11 | 9 | 2024-07-08 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-06 | Unknown | Unknown | 60 | 44 | 331 | 237 | 391 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | -577 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 350.61 | -9.46 | Unknown | Unknown | 1.1 | 358.97 | 3981 | 659.76 | 350.61 | 309.15 | Yes | N/A | N/A | 2023-06-26 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-07-06 | 98 | 70 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-08-17 | 29 | 21 | 2023-08-17 | 2023-08-17 | 1 | 1 | 15 | 11 | 128 | 92 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | -56 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 905.8 | 291.46 | Unknown | 0.03 | Unknown | 614.31 | 2875 | 455.88 | 905.8 | -449.92 | Yes | N/A | N/A | 2024-01-24 | 2024-01-25 | 2 | 2 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | 2024-02-20 | 2024-02-27 | 8 | 6 | 2024-02-27 | 2024-02-23 | Unknown | Unknown | 2 | 2 | 8 | 6 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 80.2 | -0.94 | Unknown | Unknown | Unknown | 81.14 | 3981 | 2389.75 | 80.2 | 2309.55 | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-19 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-24 | 6 | 4 | 2025-03-24 | 2025-03-24 | 1 | 1 | 39 | 29 | 8 | 6 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 43.17 | -13.73 | Unknown | Unknown | Unknown | 56.9 | 3981 | 517.21 | 43.17 | 474.04 | Yes | N/A | N/A | 2023-03-24 | 2023-04-15 | 23 | 16 | 2023-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 23 | 16 | 1 | 1 | 24 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-14 | 20 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 0.7 | -9.75 | Unknown | Unknown | Unknown | 10.45 | Unknown | 799.55 | 0.7 | 798.85 | Yes | N/A | N/A | 2023-09-19 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-09-19 | 58 | 42 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-11-22 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-04 | 13 | 9 | 2023-12-04 | 2023-12-04 | 1 | 1 | 65 | 47 | 72 | 52 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-14 | -324 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-06-15 | IOU Designed & Installed | N/A | No | N/A | -6015.78 | 3170.54 | Unknown | 1009.57 | -11688 | 1492.11 | Unknown | 11688.29 | -6015.78 | 17704.07 | Yes | N/A | N/A | 2024-05-21 | 2024-05-23 | 3 | 3 | 2024-05-23 | 2024-06-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-15 | 2024-06-24 | 10 | 6 | 2024-06-24 | 2024-06-24 | 1 | 1 | 3 | 3 | 35 | 25 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 38.97 | -11.44 | Unknown | Unknown | -636.04 | 686.45 | Unknown | 642.1 | 38.97 | 603.13 | Yes | N/A | N/A | 2023-07-24 | 2023-05-30 | Unknown | Unknown | 2023-05-30 | 2023-07-27 | 59 | 43 | 2023-07-27 | 2023-08-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-09-21 | 57 | 41 | Unknown | 2023-09-20 | Unknown | Unknown | 2023-09-21 | 2023-10-17 | 27 | 19 | 2023-10-17 | 2023-10-17 | 1 | 1 | 73 | 53 | 87 | 63 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -25 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 23882.75 | 300.29 | Unknown | Unknown | 1275.58 | 22306.88 | 15858 | 14409.64 | 23882.75 | -9473.11 | Yes | N/A | N/A | 2022-09-16 | 2023-03-09 | 175 | 125 | 2023-03-09 | 2023-10-10 | 216 | 154 | 2023-03-30 | 2023-10-09 | 43 | 31 | 2023-07-25 | 2024-07-26 | 37 | 29 | 2023-10-26 | Unknown | Unknown | Unknown | 2023-10-26 | 2024-08-07 | 287 | 205 | Unknown | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | 218 | 156 | 541 | 389 | 759 | 545 | Steps 2,3,5,6,7 | 544 | 388 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-06 | 99 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 7346.35 | 1503.04 | Unknown | 2792.44 | 37.02 | 3013.85 | 3981 | 421.91 | 7346.35 | -6924.44 | Yes | N/A | N/A | 2023-06-11 | 2023-06-12 | 2 | 1 | 2023-06-12 | 2023-08-08 | 58 | 42 | 2023-08-08 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-11-09 | 105 | 75 | Unknown | 2023-09-06 | Unknown | Unknown | 2023-11-09 | 2023-11-10 | 2 | 2 | 2023-11-10 | 2023-11-13 | 4 | 2 | 107 | 76 | 64 | 46 | 171 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 7.36 | Unknown | Unknown | Unknown | Unknown | 7.36 | 3981 | 192.95 | 7.36 | 185.59 | Yes | N/A | N/A | 2024-07-02 | 2024-08-01 | 31 | 23 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-05 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-14 | 10 | 8 | 2024-08-14 | 2024-08-14 | 1 | 1 | 36 | 26 | 12 | 10 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 7.58 | Unknown | Unknown | Unknown | Unknown | 7.58 | 3981 | 1442.19 | 7.58 | 1434.61 | Yes | N/A | N/A | 2024-11-05 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-05 | 19 | 13 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-12-12 | 31 | 23 | 2024-12-12 | 2024-12-12 | 1 | 1 | 8 | 6 | 51 | 37 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 501.02 | Unknown | Unknown | Unknown | 2.9 | 498.12 | 3981 | 1310.13 | 501.02 | 809.11 | Yes | N/A | N/A | 2024-10-15 | 2024-12-12 | 59 | 43 | 2024-12-12 | 2024-12-12 | 1 | 1 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 59 | 43 | 2 | 2 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 45.1 | 45.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-09 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-05-13 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 12.89 | -9.94 | Unknown | Unknown | Unknown | 22.83 | Unknown | 896.86 | 12.89 | 883.97 | Yes | N/A | N/A | 2024-04-11 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-13 | 55 | 39 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-06-13 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-11 | 29 | 21 | 2024-07-11 | 2024-07-11 | 1 | 1 | 32 | 24 | 85 | 61 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-25 | 9 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-11-08 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 768.32 | -1.25 | Unknown | Unknown | Unknown | 769.57 | 3981 | 1659.25 | 768.32 | 890.93 | Yes | N/A | N/A | 2024-10-15 | 2024-11-08 | 25 | 19 | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-12-12 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-06 | 26 | 18 | 2025-01-06 | 2025-01-03 | Unknown | Unknown | 60 | 44 | 27 | 19 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -713 | -510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | Unknown | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 86.23 | Unknown | Unknown | Unknown | Unknown | 86.23 | 3981 | 1479.01 | 86.23 | 1392.78 | Yes | N/A | N/A | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-09-10 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-16 | 7 | 5 | 2024-09-16 | 2024-09-16 | 1 | 1 | 7 | 5 | 9 | 7 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CALTRANS-NORTH of 56, CARLSBAD | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-05-01 | 1039 | 743 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-04 | 2022-11-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -298.93 | Unknown | Unknown | Unknown | -321 | 22.07 | 1376 | 1164.57 | -298.93 | 1463.5 | Yes | N/A | N/A | 2022-11-04 | 2023-02-01 | 90 | 64 | 2023-02-01 | 2023-05-26 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2024-10-30 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-05 | Unknown | Unknown | 90 | 64 | 193 | 139 | 283 | 203 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | 8 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-14 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 4203.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-11 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-14 | 12 | 8 | 2024-10-14 | 2024-10-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2025-04-23 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 193 | 139 | 14 | 10 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | 2023-07-12 | IOU Designed & Installed | N/A | No | N/A | 374.12 | 232.94 | Unknown | Unknown | Unknown | 141.18 | Unknown | 479.76 | 374.12 | 105.64 | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2023-07-12 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2023-07-13 | 2 | 2 | 2023-07-13 | 2023-07-13 | 1 | 1 | 63 | 45 | 3 | 3 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | -214 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-05-04 | IOU Designed & Installed | N/A | No | N/A | 1242.07 | 772.44 | Unknown | Unknown | Unknown | 469.63 | Unknown | 98.41 | 1242.07 | -1143.66 | Yes | N/A | N/A | 2023-02-23 | 2023-03-13 | 19 | 13 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | 2023-05-04 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-05-16 | 13 | 9 | 2023-05-16 | 2023-05-16 | 1 | 1 | 72 | 52 | 14 | 10 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-02-10 | 2023-05-04 | IOU Designed & Installed | N/A | No | N/A | 16496.51 | 5085.8 | Unknown | Unknown | 132.93 | 11277.78 | 3981 | 1089.73 | 16496.51 | -15406.78 | Yes | N/A | N/A | 2023-01-19 | 2023-02-10 | 23 | 17 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-05-04 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-07-10 | 68 | 48 | 2023-07-10 | 2023-05-11 | Unknown | Unknown | 107 | 77 | 68 | 48 | 175 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -269 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 290.37 | -2.59 | Unknown | Unknown | Unknown | 292.96 | Unknown | 1049.95 | 290.37 | 759.58 | Yes | N/A | N/A | 2024-04-23 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-29 | 61 | 43 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-02 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-06 | 5 | 3 | 2024-05-06 | 2024-05-06 | 1 | 1 | 4 | 4 | 67 | 47 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-18 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 1136.06 | Unknown | Unknown | Unknown | 12.31 | 1123.75 | 3961 | 1299.58 | 1136.06 | 163.52 | Yes | N/A | N/A | 2024-04-02 | 2024-05-06 | 35 | 25 | 2024-05-06 | 2024-06-13 | 39 | 29 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-10-23 | 133 | 95 | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-05 | 14 | 10 | 2024-11-05 | 2024-11-05 | 1 | 1 | 168 | 120 | 54 | 40 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 28.51 | Unknown | Unknown | Unknown | Unknown | 28.51 | 3981 | 627.98 | 28.51 | 599.47 | Yes | N/A | N/A | 2024-04-01 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-07-31 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-02 | 3 | 3 | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 122 | 88 | 3 | 3 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 100 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 3810.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | 2022-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1591.17 | 684.81 | Unknown | 201.07 | -2749 | 271.95 | Unknown | 2749.08 | -1591.17 | 4340.25 | Yes | N/A | N/A | 2022-05-02 | 2023-05-16 | 380 | 272 | 2023-05-16 | 2023-05-18 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-06-01 | Unknown | Unknown | 380 | 272 | 3 | 3 | 383 | 275 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -107 | -76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | -2342.25 | 1537.4 | Unknown | Unknown | -4583 | 703.35 | Unknown | 4583.26 | -2342.25 | 6925.51 | Yes | N/A | N/A | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-16 | 2024-06-21 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-05-29 | 2024-06-21 | 24 | 18 | 2024-06-21 | 2024-06-21 | 1 | 1 | 1 | 1 | 93 | 69 | 94 | 70 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -215 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-31 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 1051.5 | -21.13 | Unknown | Unknown | Unknown | 1072.63 | 265913 | Not available | 1051.5 | Unknown | Yes | N/A | N/A | 2023-10-24 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2025-05-06 | 575 | 411 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-20 | 13 | 9 | 2025-05-06 | 2025-07-31 | 87 | 63 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-29 | 2025-05-30 | 2 | 2 | 2025-05-30 | 2025-05-30 | 1 | 1 | 87 | 63 | 591 | 423 | 678 | 486 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | -1067.28 | Unknown | Unknown | Unknown | -1103 | 35.72 | 3981 | 1432.67 | -1067.28 | 2499.95 | Yes | N/A | N/A | 2024-09-30 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-09-30 | 6 | 4 | 2024-09-30 | 2024-12-02 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-12-17 | 43 | 31 | 2024-12-17 | 2024-12-17 | 1 | 1 | 101 | 73 | 50 | 36 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 325.02 | -19.56 | Unknown | Unknown | Unknown | 344.58 | 3981 | 1260.7 | 325.02 | 935.68 | Yes | N/A | N/A | 2024-04-11 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-11 | 46 | 34 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-10 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-19 | 10 | 8 | 2024-06-19 | 2024-06-19 | 1 | 1 | 61 | 43 | 57 | 43 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-01 | 2022-08-31 | 2025-03-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 807238.5 | 230092.8 | Unknown | Unknown | -164307.8 | 741453.5 | 0 | 319868.62 | 807238.5 | -487369.88 | Yes | N/A | N/A | 2022-07-01 | 2023-04-04 | 278 | 198 | 2023-04-04 | 2023-10-04 | 184 | 132 | 2023-04-20 | 2025-08-11 | 36 | 24 | 2023-09-05 | 2025-05-16 | 620 | 444 | 2024-10-04 | Unknown | Unknown | Unknown | 2024-10-04 | 2025-03-27 | 175 | 125 | 2025-03-28 | 2025-05-06 | 40 | 28 | 2025-05-06 | 2025-05-06 | 1 | 1 | 314 | 222 | 1020 | 730 | 1334 | 952 | Steps 2,3,5,6,7 | 1097 | 783 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-NORTH of 56 | 72.1 | 72.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 73 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-15 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 14500.62 | 5443.12 | Unknown | Unknown | -8493.45 | 17550.95 | 3981 | 12504.75 | 14500.62 | -1995.87 | Yes | N/A | N/A | 2023-09-07 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2024-05-03 | 268 | 192 | 2024-01-19 | 2024-07-09 | 3 | 2 | 2024-02-22 | 2024-04-19 | 10 | 8 | 2024-05-03 | 2024-06-26 | 55 | 39 | 2024-05-07 | 2024-06-24 | 49 | 35 | 2024-07-10 | 2024-08-12 | 34 | 24 | 2024-08-12 | 2024-08-12 | 1 | 1 | 58 | 41 | 362 | 260 | 420 | 301 | Steps 2,3,5,6,7 | 293 | 209 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | -345 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 588.24 | -11.78 | Unknown | Unknown | -508.77 | 1108.79 | Unknown | 515.35 | 588.24 | -72.89 | Yes | N/A | N/A | 2023-07-05 | 2023-08-10 | 37 | 27 | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2024-02-27 | 202 | 144 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-05-03 | 67 | 49 | Unknown | 2024-04-05 | Unknown | Unknown | 2024-05-03 | 2024-05-07 | 5 | 3 | 2024-05-07 | 2024-05-07 | 1 | 1 | 306 | 220 | 7 | 5 | 313 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 58.17 | -51.67 | Unknown | Unknown | Unknown | 109.84 | 3981 | 949.93 | 58.17 | 891.76 | Yes | N/A | N/A | 2023-10-04 | 2023-10-26 | 23 | 17 | 2023-10-26 | 2023-11-10 | 16 | 12 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-05-09 | 1 | 1 | 23 | 17 | 17 | 13 | 40 | 30 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | Unknown | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 43.85 | Unknown | Unknown | Unknown | Unknown | 43.85 | 3981 | 1611.19 | 43.85 | 1567.34 | Yes | N/A | N/A | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-16 | 27 | 19 | 2024-10-16 | 2024-10-16 | 1 | 1 | 4 | 4 | 29 | 21 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38.1 | 38.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-27 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1687.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-25 | 14 | 10 | 2025-03-25 | 2025-03-27 | 3 | 3 | 2025-03-27 | 2025-03-31 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-05-28 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-03 | 7 | 5 | 2025-06-03 | 2025-06-03 | 1 | 1 | 78 | 56 | 11 | 9 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | BONITA | N/A | 23.4 | 23.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.15 | -5.47 | Unknown | Unknown | Unknown | 11.62 | Unknown | 880.14 | 6.15 | 873.99 | Yes | N/A | N/A | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-03-28 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-07 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | 1428.08 | -24.15 | Unknown | Unknown | 22.04 | 1430.19 | 3981 | 1152.44 | 1428.08 | -275.64 | Yes | N/A | N/A | 2023-10-03 | 2023-11-17 | 46 | 34 | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-21 | 5 | 3 | Unknown | 2024-01-18 | Unknown | Unknown | 2023-11-21 | 2024-02-08 | 80 | 58 | 2024-02-08 | 2024-02-08 | 1 | 1 | 51 | 37 | 82 | 60 | 133 | 97 | Steps 2,3,5,6,7 | 58 | 42 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | -673 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-05-12 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 642.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-05-12 | 25 | 17 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-14 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-05-23 | 5 | 5 | 2025-05-23 | 2025-05-23 | 1 | 1 | 29 | 21 | 7 | 7 | 36 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | 443 | 317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3661 | 1989.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2023-08-22 | 7 | 5 | 2023-08-22 | 2024-09-12 | 388 | 278 | 2023-09-22 | 2023-09-25 | 4 | 2 | 2023-08-22 | 2024-12-31 | 72 | 54 | 2024-09-12 | 2025-01-16 | 127 | 91 | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-01-28 | Unknown | Unknown | 138 | 98 | 460 | 332 | 598 | 430 | Steps 2,3,5,6,7 | 500 | 356 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-07-29 | 1423 | 1018 | No | 2024-01-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-12 | 2024-06-07 | IOU Designed & Installed | N/A | Yes | 10 | 1059.08 | -4.88 | Unknown | Unknown | 25.37 | 1038.59 | 3961 | 1199.13 | 1059.08 | 140.05 | Yes | N/A | N/A | 2024-01-12 | 2024-01-19 | 8 | 6 | 2024-01-19 | 2024-01-22 | 4 | 2 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-06-07 | 144 | 104 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-07 | 2024-06-21 | 15 | 11 | 2024-06-21 | 2024-06-21 | 1 | 1 | 152 | 110 | 20 | 14 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 70.2 | 70.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | 93 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 296.5 | -5.35 | Unknown | Unknown | Unknown | 301.85 | 3981 | 1696.1 | 296.5 | 1399.6 | Yes | N/A | N/A | 2024-10-29 | 2024-11-21 | 24 | 18 | 2024-11-21 | 2024-12-17 | 27 | 19 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-05 | 38 | 28 | 2025-03-05 | 2025-03-05 | 1 | 1 | 25 | 19 | 66 | 48 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -479 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | 1123.61 | 347.3 | Unknown | 117.92 | Unknown | 658.39 | 3981 | 915.91 | 1123.61 | -207.7 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-02-13 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-02-15 | 3 | 3 | 2024-02-15 | 2024-02-15 | 1 | 1 | 101 | 73 | 5 | 5 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | -3168.46 | 835 | Unknown | 97.44 | -4524 | 423.1 | Unknown | 4523.72 | -3168.46 | 7692.18 | Yes | N/A | N/A | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-01 | 4 | 4 | 2024-08-01 | 2024-08-01 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 7.75 | Unknown | Unknown | Unknown | Unknown | 7.75 | Unknown | 1466.05 | 7.75 | 1458.3 | Yes | N/A | N/A | 2024-08-15 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-08-15 | 24 | 18 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-18 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-02 | 15 | 11 | 2024-10-02 | 2024-10-02 | 1 | 1 | 35 | 25 | 40 | 30 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 297.89 | -11.66 | Unknown | Unknown | Unknown | 309.55 | Unknown | 937.65 | 297.89 | 639.76 | Yes | N/A | N/A | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-01-04 | 58 | 42 | 2024-01-04 | 2024-01-04 | 1 | 1 | 2 | 2 | 60 | 44 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 236 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-08-31 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 14659.7 | 3870.34 | Unknown | Unknown | 21.21 | 10768.15 | 3981 | 1684.95 | 14659.7 | -12974.75 | Yes | N/A | N/A | 2023-03-31 | 2023-10-02 | 186 | 132 | 2023-10-02 | 2023-11-06 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-23 | 8 | 6 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-09-09 | 2024-10-16 | 38 | 28 | 2024-10-16 | 2024-10-16 | 1 | 1 | 186 | 132 | 83 | 61 | 269 | 193 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -585 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-16 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 90.99 | -12.01 | Unknown | Unknown | Unknown | 103 | Unknown | 859.52 | 90.99 | 768.53 | Yes | N/A | N/A | 2024-04-01 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-04-15 | 55 | 39 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-06-25 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-03 | 9 | 7 | 2024-07-03 | 2024-07-03 | 1 | 1 | 71 | 51 | 65 | 47 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | Poway | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 271 | 194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-03-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 70280.17 | -37.2 | Unknown | Unknown | Unknown | 70317.37 | 1312175 | Not available | 70280.17 | Unknown | Yes | N/A | N/A | 2024-01-18 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | 2024-01-29 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-01-29 | 2958465 | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | 2024-03-15 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-02-28 | 1 | 1 | 0 | 0 | 49 | 35 | 49 | 35 | Steps 2,3,5,6,7 | 120 | 86 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-29 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 132.64 | -13.52 | Unknown | Unknown | Unknown | 146.16 | 3981 | 989.4 | 132.64 | 856.76 | Yes | N/A | N/A | 2023-09-19 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-29 | 94 | 68 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-09-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-11-15 | 48 | 34 | 2023-11-15 | 2023-11-15 | 1 | 1 | 1 | 1 | 143 | 103 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -444 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-12-05 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | 41305.46 | 5740.76 | Unknown | Unknown | 72.91 | 35491.79 | Unknown | 62992.01 | 41305.46 | 21686.55 | Yes | N/A | N/A | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-04-22 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-18 | 43 | 31 | 2025-06-18 | 2025-06-18 | 1 | 1 | 1 | 1 | 133 | 95 | 134 | 96 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2063.4 | 2063.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-20 | 116 | 83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1040.57 | Unknown | Unknown | Unknown | -1109 | 68.43 | 3981 | 1993.21 | -1040.57 | 3033.78 | Yes | N/A | N/A | 2023-07-24 | 2023-01-31 | Unknown | Unknown | 2023-01-31 | 2024-02-01 | 367 | 263 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-11-01 | 275 | 197 | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-11-13 | Unknown | Unknown | 275 | 197 | 367 | 263 | 642 | 460 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-10-18 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 294.69 | -5.35 | Unknown | Unknown | Unknown | 300.04 | 3981 | 1477.87 | 294.69 | 1183.18 | Yes | N/A | N/A | 2024-07-30 | 2024-10-18 | 81 | 59 | 2024-10-18 | 2024-10-21 | 4 | 2 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-01-08 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-03-06 | 58 | 42 | 2025-03-06 | 2025-03-06 | 1 | 1 | 164 | 118 | 63 | 45 | 227 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 1241.37 | Unknown | Unknown | Unknown | 26.39 | 1214.98 | 3981 | 825.32 | 1241.37 | -416.05 | Yes | N/A | N/A | 2024-03-08 | 2024-03-22 | 15 | 11 | 2024-03-22 | 2024-04-05 | 15 | 11 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2025-02-14 | 316 | 226 | Unknown | 2024-12-13 | Unknown | Unknown | 2025-02-14 | 2025-02-27 | 14 | 10 | 2025-02-27 | 2025-02-27 | 1 | 1 | 331 | 237 | 30 | 22 | 361 | 259 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 332 | 332 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | 365 | 262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3865.51 | -0.31 | Unknown | Unknown | Unknown | 3865.82 | Unknown | 2079.28 | 3865.51 | -1786.23 | Yes | N/A | N/A | 2024-04-16 | 2024-04-18 | 3 | 3 | 2024-04-18 | 2024-10-23 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-03 | 32 | 22 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-08 | 1 | 1 | 3 | 3 | 222 | 158 | 225 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -612 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 1453.51 | 378.69 | Unknown | 353.25 | Unknown | 721.57 | 3981 | 675.3 | 1453.51 | -778.21 | Yes | N/A | N/A | 2023-08-31 | 2023-09-06 | 7 | 5 | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-22 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-11-01 | 41 | 29 | 2023-11-01 | 2023-11-01 | 1 | 1 | 23 | 17 | 43 | 31 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -449 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-10 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 1343.31 | Unknown | Unknown | Unknown | 15.55 | 1327.76 | 3981 | 1220 | 1343.31 | -123.31 | Yes | N/A | N/A | 2024-09-03 | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-09-19 | 49 | 35 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-05-09 | 233 | 167 | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-09 | 2025-05-20 | 12 | 8 | 2025-05-20 | 2025-05-20 | 1 | 1 | 233 | 167 | 62 | 44 | 295 | 211 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 375 | 375 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | 55 | 40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 749.7 | -13.69 | Unknown | Unknown | Unknown | 763.39 | 3981 | 1901.96 | 749.7 | 1152.26 | Yes | N/A | N/A | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | 2024-07-22 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-14 | 35 | 25 | 2024-07-22 | 2025-02-27 | 221 | 159 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-02-27 | Unknown | Unknown | 222 | 160 | 47 | 33 | 269 | 193 | Steps 2,3,5,6,7 | 23 | 17 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | -550 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 148.4 | -11.04 | Unknown | Unknown | -825 | 984.44 | Unknown | 825.32 | 148.4 | 676.92 | Yes | N/A | N/A | 2024-02-23 | 2024-03-26 | 33 | 23 | 2024-03-26 | 2024-03-28 | 3 | 3 | 2024-03-28 | 2024-04-24 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-03 | 6 | 4 | Unknown | 2024-05-30 | Unknown | Unknown | 2024-06-03 | 2024-07-01 | 29 | 21 | 2024-07-01 | 2024-07-01 | 1 | 1 | 67 | 47 | 33 | 25 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -333 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2829.51 | -6.09 | Unknown | Unknown | -6460 | 3636.58 | 0 | 2781.62 | -2829.51 | 5611.13 | Yes | N/A | N/A | 2023-08-04 | 2023-08-23 | 20 | 14 | 2023-08-23 | 2024-01-31 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2025-03-03 | 398 | 284 | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-15 | Unknown | Unknown | 418 | 298 | 162 | 116 | 580 | 414 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 518 | 371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 17137.97 | 2232.99 | Unknown | Unknown | Unknown | 14904.98 | 3981 | Not available | 17137.97 | Unknown | Yes | N/A | N/A | 2023-12-18 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2024-02-05 | 223 | 159 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-06-05 | 122 | 88 | Unknown | 2024-06-06 | Unknown | Unknown | 2024-06-10 | 2024-06-20 | 11 | 9 | 2024-06-20 | 2024-06-17 | Unknown | Unknown | 122 | 88 | 234 | 168 | 356 | 256 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -421 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 995.71 | 362.52 | Unknown | Unknown | Unknown | 633.19 | 7962 | 1148.76 | 995.71 | 153.05 | Yes | N/A | N/A | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-10-03 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-06 | 4 | 4 | 2023-10-06 | 2023-10-06 | 1 | 1 | 118 | 84 | 5 | 5 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -619 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-06 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1760.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-12 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-22 | 11 | 9 | 2025-05-22 | 2025-05-22 | 1 | 1 | 68 | 48 | 29 | 23 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-07 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 453.87 | Unknown | Unknown | Unknown | 11.64 | 442.23 | 3981 | 1230.06 | 453.87 | 776.19 | Yes | N/A | N/A | 2025-01-30 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-24 | 34 | 24 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-06-02 | 99 | 71 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-06-02 | 2025-06-03 | 2 | 2 | 2025-06-03 | 2025-06-03 | 1 | 1 | 99 | 71 | 37 | 27 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 147 | 147 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 6735.8 | 273.47 | Unknown | Unknown | Unknown | 6462.33 | 3981 | 2303.74 | 6735.8 | -4432.06 | Yes | N/A | N/A | 2024-08-20 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-10-02 | 216 | 154 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-11-13 | 43 | 31 | Unknown | 2024-10-29 | Unknown | Unknown | 2024-10-31 | 2024-12-26 | 57 | 41 | 2024-12-26 | 2024-11-15 | Unknown | Unknown | 43 | 31 | 273 | 195 | 316 | 226 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31.05 | 31.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -88 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-15 | 2023-04-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1170.36 | -38.34 | Unknown | Unknown | Unknown | 1208.7 | 3981 | 1013.35 | 1170.36 | -157.01 | Yes | N/A | N/A | 2023-04-15 | 2023-04-15 | 1 | 0 | 2023-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2024-09-23 | 470 | 336 | 1 | 0 | 470 | 336 | 471 | 336 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-19 | -548 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-01-15 | IOU Designed & Installed | N/A | No | N/A | 1785.19 | 350.8 | Unknown | 170.7 | Unknown | 1263.69 | Unknown | 1029.27 | 1785.19 | -755.92 | Yes | N/A | N/A | 2023-11-14 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-11-14 | 105 | 75 | 2023-11-14 | Unknown | Unknown | Unknown | 2023-11-14 | 2023-11-21 | 8 | 6 | 2023-11-14 | 2024-01-15 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-01-15 | 2024-01-18 | 4 | 4 | 2024-01-18 | 2024-01-18 | 1 | 1 | 63 | 45 | 118 | 86 | 181 | 131 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 175 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 35549.77 | 10956.78 | Unknown | Unknown | 109.83 | 24483.16 | 186327 | 19492.98 | 35549.77 | -16056.79 | Yes | N/A | N/A | 2023-08-28 | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-10-06 | 82 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2024-01-17 | 104 | 74 | Unknown | 2024-03-18 | Unknown | Unknown | 2023-11-03 | 2024-05-24 | 204 | 146 | 2024-05-24 | 2024-05-24 | 1 | 1 | 104 | 74 | 287 | 207 | 391 | 281 | Steps 2,3,5,6,7 | 136 | 96 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-11-04 | -919 | -658 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1840.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-03-10 | 15 | 11 | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-31 | 22 | 16 | 2025-03-10 | 2025-04-24 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-29 | 6 | 4 | 2025-04-29 | 2025-04-29 | 1 | 1 | 46 | 34 | 44 | 32 | 90 | 66 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | -1820.41 | -10.2 | Unknown | Unknown | -2328 | 517.79 | Unknown | 1130.36 | -1820.41 | 2950.77 | Yes | N/A | N/A | 2025-02-11 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-02-11 | 2 | 2 | 2025-02-11 | 2025-03-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-07 | 2 | 2 | 2025-05-07 | 2025-05-07 | 1 | 1 | 22 | 16 | 5 | 5 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -158 | -113 | No | 2024-08-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | Yes | 220 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7862 | 3357.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2025-03-05 | 209 | 149 | 2025-03-05 | 2025-03-17 | 13 | 9 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-22 | Unknown | Unknown | 209 | 149 | 13 | 9 | 222 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -311 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 497.62 | -8.28 | Unknown | Unknown | Unknown | 505.9 | 3981 | 1111.46 | 497.62 | 613.84 | Yes | N/A | N/A | 2024-03-27 | 2024-03-29 | 3 | 3 | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-30 | 1 | 1 | 3 | 3 | 2 | 2 | 5 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | -501 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 2.93 | Unknown | Unknown | Unknown | Unknown | 2.93 | 8997 | 554.66 | 2.93 | 551.73 | Yes | N/A | N/A | 2023-05-24 | 2023-05-24 | 1 | 1 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2024-09-17 | 483 | 345 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-07 | 21 | 15 | 2024-10-07 | 2024-10-07 | 1 | 1 | 484 | 346 | 22 | 16 | 506 | 362 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 6000 | 6000 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-03-23 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-03 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 1718.18 | 515.55 | Unknown | 10.67 | Unknown | 1191.96 | 3981 | 1114.89 | 1718.18 | -603.29 | Yes | N/A | N/A | 2024-05-02 | 2024-05-03 | 2 | 2 | 2024-05-03 | 2025-03-06 | 308 | 220 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-09 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-22 | 14 | 10 | 2024-05-22 | 2024-05-22 | 1 | 1 | 9 | 7 | 323 | 231 | 332 | 238 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-30 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 69.03 | 37 | Unknown | Unknown | Unknown | 32.03 | 3981 | 192.95 | 69.03 | 123.92 | Yes | N/A | N/A | 2024-08-21 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-10 | 34 | 24 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-20 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-02 | 13 | 9 | 2024-10-02 | 2024-10-02 | 1 | 1 | 11 | 9 | 48 | 34 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -590 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-11 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | -5.3 | -22.2 | Unknown | Unknown | Unknown | 16.9 | Unknown | 1676.05 | -5.3 | 1681.35 | Yes | N/A | N/A | 2025-02-10 | 2025-01-29 | Unknown | Unknown | 2025-01-29 | 2025-02-11 | 14 | 10 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-24 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-27 | 4 | 4 | 2025-03-27 | 2025-03-27 | 1 | 1 | 42 | 30 | 19 | 15 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1327.9 | 1880.88 | Unknown | 467.95 | -4454 | 777.27 | Unknown | 4454.15 | -1327.9 | 5782.05 | Yes | N/A | N/A | 2023-10-23 | 2023-10-26 | 4 | 4 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 4 | 4 | 1 | 1 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 21189.12 | 2455.78 | Unknown | Unknown | -504 | 19237.34 | 2105 | 2558.93 | 21189.12 | -18630.19 | Yes | N/A | N/A | 2023-10-10 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | 2023-11-13 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-01-16 | 65 | 47 | Unknown | 2024-01-11 | Unknown | Unknown | 2024-01-18 | 2024-01-31 | 14 | 10 | 2024-01-31 | 2024-01-25 | Unknown | Unknown | 65 | 47 | 50 | 36 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 56.4 | 56.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-08 | 87 | 62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-03-21 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 22169.81 | 1237.81 | Unknown | Unknown | 28.25 | 20903.75 | Unknown | 16638.94 | 22169.81 | -5530.87 | Yes | N/A | N/A | 2023-11-28 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-07-12 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-09-03 | 44 | 32 | 2024-09-03 | 2024-09-03 | 1 | 1 | 0 | 0 | 75 | 55 | 75 | 55 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-16 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1216.05 | -13.15 | Unknown | Unknown | Unknown | 1229.2 | 3981 | 1313.08 | 1216.05 | 97.03 | Yes | N/A | N/A | 2024-05-21 | 2024-06-04 | 15 | 11 | 2024-06-04 | 2024-06-05 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-21 | 18 | 14 | 2024-06-05 | 2024-06-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-06-11 | Unknown | Unknown | 16 | 12 | 20 | 16 | 36 | 28 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -526 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-17 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | -250.85 | Unknown | Unknown | Unknown | -281 | 30.15 | Unknown | 1537.77 | -250.85 | 1788.62 | Yes | N/A | N/A | 2024-09-03 | 2024-09-16 | 14 | 10 | 2024-09-16 | 2024-09-17 | 2 | 2 | 2024-09-17 | 2024-11-21 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-04 | 13 | 9 | 2024-12-04 | 2024-12-04 | 1 | 1 | 82 | 60 | 16 | 12 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | ALPINE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-01-31 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-10 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 168218.77 | 54977.47 | Unknown | 22543.26 | -20171.9 | 110869.94 | 19843 | 60215.61 | 168218.77 | -108003.16 | Yes | N/A | N/A | 2023-02-01 | 2023-02-10 | 10 | 8 | 2023-02-10 | 2023-10-25 | 258 | 184 | 2023-08-07 | 2023-09-12 | 37 | 27 | 2023-10-26 | 2023-11-06 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-30 | 26 | 18 | 2024-01-30 | 2024-01-30 | 1 | 1 | 47 | 35 | 297 | 211 | 344 | 246 | Steps 2,3,5,6,7 | 79 | 57 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | 670 | 479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-08-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -10400.27 | 3801.09 | Unknown | 74.28 | -66712.95 | 52437.31 | Unknown | 112151.65 | -10400.27 | 122551.92 | Yes | N/A | N/A | 2024-04-18 | 2024-04-24 | 7 | 5 | 2024-04-24 | 2024-07-24 | 92 | 66 | 2024-05-07 | 2024-05-08 | 2 | 2 | 2024-07-25 | 2024-07-31 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-09 | 29 | 21 | 2024-09-09 | 2024-09-09 | 1 | 1 | 9 | 7 | 129 | 93 | 138 | 100 | Steps 2,3,5,6,7 | 78 | 56 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | -513 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-06-21 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 6063.58 | Unknown | Unknown | Unknown | Unknown | 6063.58 | Unknown | 1857.53 | 6063.58 | -4206.05 | Yes | N/A | N/A | 2024-05-02 | 2024-05-03 | 2 | 2 | 2024-05-03 | 2024-07-19 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-10-24 | 93 | 67 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2 | 2 | 172 | 124 | 174 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 72.6 | -1.25 | Unknown | Unknown | Unknown | 73.85 | Unknown | 186.4 | 72.6 | 113.8 | Yes | N/A | N/A | 2024-06-12 | 2024-06-18 | 7 | 5 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-09-10 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-08 | 29 | 21 | 2024-10-08 | 2024-10-08 | 1 | 1 | 92 | 66 | 31 | 23 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | 24.05 | 24.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -227 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-05-02 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 1976.99 | 754.08 | Unknown | 193.36 | -1194 | 2223.55 | 3981 | 2788.12 | 1976.99 | 811.13 | Yes | N/A | N/A | 2024-03-13 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-05-02 | 52 | 38 | 2024-05-02 | 2024-10-17 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-03-24 | 133 | 95 | Unknown | 2024-11-14 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-03-24 | 1 | 1 | 191 | 137 | 54 | 40 | 245 | 177 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 264 | 264 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -102 | -74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 3836.6 | 1060.18 | Unknown | 168.38 | 2.63 | 2605.41 | 6481 | 769.59 | 3836.6 | -3067.01 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2024-07-09 | 418 | 298 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-09-17 | 71 | 51 | 2024-09-17 | 2024-09-17 | 1 | 1 | 419 | 299 | 72 | 52 | 491 | 351 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -593 | -424 | No | 2024-10-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-12-03 | IOU Designed & Installed | N/A | Yes | 36 | 12.56 | Unknown | Unknown | Unknown | Unknown | 12.56 | Unknown | 1635.81 | 12.56 | 1623.25 | Yes | N/A | N/A | 2024-10-16 | 2024-11-19 | 35 | 25 | 2024-11-19 | 2024-10-21 | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-12-03 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-01-21 | 50 | 36 | 2025-01-21 | 2025-01-21 | 1 | 1 | 79 | 57 | 51 | 37 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -437 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-03-14 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 121.68 | -11.43 | Unknown | Unknown | Unknown | 133.11 | 3981 | 869.11 | 121.68 | 747.43 | Yes | N/A | N/A | 2024-01-09 | 2024-01-25 | 17 | 13 | 2024-01-25 | 2024-03-14 | 50 | 36 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-04-01 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-08 | 8 | 6 | 2024-04-08 | 2024-06-20 | 74 | 54 | 36 | 26 | 132 | 96 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 1527.42 | 415.91 | Unknown | Unknown | Unknown | 1111.51 | Unknown | 2185.91 | 1527.42 | 658.49 | Yes | N/A | N/A | 2025-01-14 | 2024-12-31 | Unknown | Unknown | 2024-12-31 | 2025-01-14 | 15 | 11 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-11 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-19 | 37 | 27 | 2025-03-19 | 2025-03-19 | 1 | 1 | 29 | 21 | 53 | 39 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -526 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-06-26 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | -9.54 | -6.92 | Unknown | Unknown | Unknown | -2.62 | 3981 | 464.78 | -9.54 | 474.32 | Yes | N/A | N/A | 2023-05-01 | 2023-06-26 | 57 | 41 | 2023-06-26 | 2023-06-26 | 1 | 1 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-08-09 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-09-29 | 52 | 38 | 2023-09-29 | 2023-09-29 | 1 | 1 | 102 | 74 | 54 | 40 | 156 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | -721 | -516 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 2163.18 | 548.28 | Unknown | Unknown | Unknown | 1614.9 | 3981 | 1971.08 | 2163.18 | -192.1 | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-03-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-03 | 7 | 5 | 2025-04-03 | 2025-04-03 | 1 | 1 | 3 | 3 | 9 | 7 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 121.05 | 121.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -439 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-04 | 2023-06-04 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 945.22 | -20.61 | Unknown | Unknown | 19.85 | 945.98 | 3981 | 186.63 | 945.22 | -758.59 | Yes | N/A | N/A | 2023-06-04 | 2023-07-18 | 45 | 32 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-10-03 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-12-05 | 64 | 46 | 2023-12-05 | 2023-11-20 | Unknown | Unknown | 123 | 88 | 64 | 46 | 187 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2.2 | Unknown | Unknown | Unknown | Unknown | 2.2 | 3981 | 501.14 | 2.2 | 498.94 | Yes | N/A | N/A | 2024-03-12 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-03-22 | 39 | 29 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 0 | 0 | 40 | 30 | 40 | 30 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | -612 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2058.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-05-08 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-13 | 6 | 4 | 2025-05-13 | 2025-05-13 | 1 | 1 | 99 | 71 | 8 | 6 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-18 | -155 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 1020.65 | -6.2 | Unknown | Unknown | Unknown | 1026.85 | Unknown | 186.4 | 1020.65 | -834.25 | Yes | N/A | N/A | 2024-06-07 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-06-07 | 44 | 32 | 2024-06-07 | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-24 | 18 | 12 | 2024-06-07 | 2024-06-07 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-16 | 40 | 28 | 2024-07-16 | 2024-07-16 | 1 | 1 | 1 | 1 | 103 | 73 | 104 | 74 | Steps 2,3,5,6,7 | 17 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -8 | -7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 1367.74 | 411.78 | Unknown | Unknown | 68.51 | 887.45 | 3981 | 930.96 | 1367.74 | -436.78 | Yes | N/A | N/A | 2024-04-05 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-05 | 3 | 3 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-07-08 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-02-06 | 214 | 154 | 2025-02-06 | 2025-02-06 | 1 | 1 | 95 | 67 | 218 | 158 | 313 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | 306 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.67 | -3.67 | Unknown | Unknown | -186.23 | 186.23 | Unknown | 2053.53 | -3.67 | 2057.2 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-02-18 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-05 | 24 | 18 | 2025-02-18 | 2025-03-10 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-15 | Unknown | Unknown | 22 | 16 | 65 | 47 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 168.33 | -29.05 | Unknown | Unknown | -488 | 685.38 | 3981 | 2821.97 | 168.33 | 2653.64 | Yes | N/A | N/A | 2023-11-20 | 2023-09-04 | Unknown | Unknown | 2023-09-04 | 2023-11-20 | 78 | 56 | 2023-11-20 | 2024-02-14 | 87 | 63 | 2023-11-20 | 2023-11-30 | 11 | 9 | 2024-02-21 | 2024-04-15 | 55 | 39 | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-04-29 | 15 | 11 | 2024-04-29 | 2024-04-26 | Unknown | Unknown | 142 | 102 | 104 | 76 | 246 | 178 | Steps 2,3,5,6,7 | 86 | 62 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2024-07-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 5841.02 | -1.9 | Unknown | Unknown | -3538 | 9380.92 | Unknown | 3820.38 | 5841.02 | -2020.64 | Yes | N/A | N/A | 2023-11-03 | 2024-02-14 | 104 | 74 | 2024-02-14 | 2024-07-03 | 141 | 101 | 2024-02-23 | 2024-04-02 | 40 | 28 | 2024-06-13 | 2024-07-02 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-01 | 23 | 17 | 2024-08-01 | 2024-08-01 | 1 | 1 | 144 | 102 | 170 | 122 | 314 | 224 | Steps 2,3,5,6,7 | 131 | 93 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 63.5 | 63.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-11-03 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 687.24 | -19.82 | Unknown | Unknown | Unknown | 707.06 | Unknown | 1162.81 | 687.24 | 475.57 | Yes | N/A | N/A | 2023-10-26 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-11-03 | 88 | 64 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2024-03-19 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-11 | 24 | 18 | 2024-04-11 | 2024-04-11 | 1 | 1 | 138 | 98 | 113 | 83 | 251 | 181 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 2 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 675.59 | -29.16 | Unknown | Unknown | Unknown | 704.75 | 3981 | 1542.93 | 675.59 | 867.34 | Yes | N/A | N/A | 2023-10-19 | 2023-10-19 | 1 | 1 | 2023-10-19 | 2023-11-13 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-10 | 3 | 3 | 2023-11-13 | 2023-12-05 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-01-02 | Unknown | Unknown | 24 | 18 | 29 | 21 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-12-05 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | -537.79 | -27.6 | Unknown | Unknown | -1947 | 1436.81 | Unknown | 1947.09 | -537.79 | 2484.88 | Yes | N/A | N/A | 2024-09-23 | 2024-12-05 | 74 | 54 | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | 2025-01-15 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-13 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-04 | 20 | 14 | 2025-03-04 | 2025-03-04 | 1 | 1 | 146 | 106 | 22 | 16 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-21 | 1061 | 758 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-16 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 2413.76 | 243.29 | Unknown | Unknown | 6.41 | 2164.06 | 3241 | 394.53 | 2413.76 | -2019.23 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2025-03-06 | 722 | 516 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-06 | 2025-03-17 | 12 | 8 | 2025-03-17 | 2025-03-17 | 1 | 1 | 723 | 517 | 13 | 9 | 736 | 526 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | 294 | 211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -27.53 | -37.06 | Unknown | Unknown | -626.19 | 635.72 | 3981 | 1371.08 | -27.53 | 1398.61 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-03-16 | 7 | 5 | 2023-03-09 | 2023-07-27 | 141 | 101 | Unknown | 2023-06-08 | Unknown | Unknown | 2023-07-27 | 2024-11-12 | 475 | 339 | 2024-11-12 | 2024-11-12 | 1 | 1 | 142 | 102 | 483 | 345 | 625 | 447 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -379 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-31 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 15946.07 | Unknown | Unknown | Unknown | -1423.93 | 17370 | Unknown | 1456.37 | 15946.07 | -14489.7 | Yes | N/A | N/A | 2024-01-29 | 2024-04-23 | 86 | 62 | 2024-04-23 | 2024-07-03 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-08-08 | 58 | 42 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-19 | 2024-09-05 | 18 | 14 | 2024-09-05 | 2024-09-05 | 1 | 1 | 86 | 62 | 149 | 109 | 235 | 171 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | -27 | -20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 2057.83 | -20.11 | Unknown | Unknown | 91.72 | 1986.22 | 3981 | 1534.99 | 2057.83 | -522.84 | Yes | N/A | N/A | 2024-06-24 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-08-13 | 58 | 42 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2025-03-24 | 224 | 160 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-24 | 2025-03-27 | 4 | 4 | 2025-03-27 | 2025-03-26 | Unknown | Unknown | 224 | 160 | 62 | 46 | 286 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | -451 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-12 | 2023-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -23.22 | -17.54 | Unknown | Unknown | Unknown | -5.68 | Unknown | 425.49 | -23.22 | 448.71 | Yes | N/A | N/A | 2023-08-12 | 2023-08-12 | 1 | 0 | 2023-08-12 | 2023-08-12 | 1 | 0 | 2023-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | 1 | 0 | 2 | 1 | 3 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-21 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 262.74 | -17.12 | Unknown | Unknown | Unknown | 279.86 | 3981 | 776.47 | 262.74 | 513.73 | Yes | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-09-22 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-19 | 28 | 20 | 2023-10-19 | 2023-10-19 | 1 | 1 | 30 | 22 | 30 | 22 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | 186 | 133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | 1001.13 | 2255.75 | Unknown | 538.79 | -2979 | 1185.59 | Unknown | 2978.8 | 1001.13 | 1977.67 | Yes | N/A | N/A | 2023-11-13 | 2024-01-05 | 54 | 40 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-07-15 | 188 | 134 | 2024-07-15 | 2024-07-15 | 1 | 1 | 54 | 40 | 189 | 135 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-03 | 520 | 373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3647.59 | Unknown | Unknown | Unknown | Unknown | 3647.59 | 0 | 671.37 | 3647.59 | -2976.22 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | 2023-03-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-03-06 | 1 | 1 | 1 | 1 | 14 | 10 | 15 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | -108 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 1351.06 | -11.48 | Unknown | Unknown | 40.52 | 1322.02 | 3981 | 1766.05 | 1351.06 | 414.99 | Yes | N/A | N/A | 2023-06-20 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-06-30 | 60 | 44 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-12-04 | 158 | 112 | Unknown | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2023-12-20 | 17 | 13 | 2023-12-20 | 2023-12-20 | 1 | 1 | 158 | 112 | 78 | 58 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 1453.51 | 378.69 | Unknown | 353.25 | Unknown | 721.57 | 3981 | 641.97 | 1453.51 | -811.54 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-10-04 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-11-01 | 29 | 21 | 2023-11-01 | 2023-11-01 | 1 | 1 | 115 | 83 | 30 | 22 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 317 | 317 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-12 | -248 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 0.37 | -11.3 | Unknown | Unknown | Unknown | 11.67 | Unknown | 790.02 | 0.37 | 789.65 | Yes | N/A | N/A | 2023-09-25 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-09-25 | 15 | 11 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-11-01 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-07 | 7 | 5 | 2023-11-07 | 2023-11-07 | 1 | 1 | 38 | 28 | 23 | 17 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 3000 | 3000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-29 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -17.57 | -12.73 | Unknown | Unknown | Unknown | -4.84 | 3981 | 363.72 | -17.57 | 381.29 | Yes | N/A | N/A | 2023-02-16 | 2023-02-16 | 1 | 1 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-07-12 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 465.31 | 257.62 | Unknown | 28.37 | Unknown | 179.32 | Unknown | 158.79 | 465.31 | -306.52 | Yes | N/A | N/A | 2024-01-02 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2024-01-05 | 103 | 75 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-04-05 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-18 | 14 | 10 | 2024-04-18 | 2024-04-18 | 1 | 1 | 92 | 66 | 118 | 86 | 210 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -481 | -344 | No | 2024-11-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2025-02-06 | IOU Designed & Installed | N/A | Yes | 69 | 423.05 | 253.74 | Unknown | Unknown | -573 | 742.31 | Unknown | 1949.41 | 423.05 | 1526.36 | Yes | N/A | N/A | 2024-08-28 | 2025-01-13 | 139 | 99 | 2025-01-13 | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2025-01-08 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-02-06 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-14 | 37 | 27 | 2025-03-14 | 2025-03-14 | 1 | 1 | 183 | 131 | 38 | 28 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-19 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1662.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-03-19 | 34 | 24 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-30 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-16 | 17 | 13 | 2025-05-16 | 2025-05-16 | 1 | 1 | 43 | 31 | 52 | 38 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 226 | 226 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 579 | 415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-09-11 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 22902.82 | 1395.93 | Unknown | Unknown | -6937 | 28443.89 | 20201 | 24455.85 | 22902.82 | 1553.03 | Yes | N/A | N/A | 2023-05-31 | 2023-11-02 | 156 | 112 | 2023-11-02 | 2024-01-03 | 63 | 45 | 2023-06-16 | 2023-07-13 | 28 | 20 | 2023-11-29 | 2024-02-21 | 15 | 9 | 2024-01-03 | 2024-05-31 | 150 | 108 | 2024-01-16 | 2024-07-08 | 175 | 125 | 2024-07-10 | 2024-08-09 | 31 | 23 | 2024-08-09 | 2024-08-02 | Unknown | Unknown | 334 | 240 | 284 | 202 | 618 | 442 | Steps 2,3,5,6,7 | 386 | 276 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 1397.55 | Unknown | Unknown | Unknown | 16.51 | 1381.04 | 3981 | 1412.81 | 1397.55 | 15.26 | Yes | N/A | N/A | 2024-10-21 | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-31 | 31 | 23 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-05-21 | 203 | 145 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-31 | 11 | 8 | 2025-05-31 | 2025-05-31 | 1 | 0 | 203 | 145 | 43 | 31 | 246 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | -599 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-26 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 80.95 | Unknown | Unknown | Unknown | Unknown | 80.95 | 3981 | 1863.79 | 80.95 | 1782.84 | Yes | N/A | N/A | 2025-03-19 | 2025-03-26 | 8 | 6 | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-06-03 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-17 | 15 | 11 | 2025-06-17 | 2025-06-17 | 1 | 1 | 78 | 56 | 17 | 13 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-07-17 | 1519 | 1086 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 4972.1 | Unknown | Unknown | Unknown | 75.1 | 4897 | 2875.23 | 664.18 | 4972.1 | -4307.92 | Yes | N/A | N/A | 2024-06-10 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-14 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-08-26 | 74 | 52 | Unknown | 2024-08-30 | Unknown | Unknown | 2024-09-06 | 2024-09-16 | 11 | 7 | 2024-09-16 | 2024-09-13 | Unknown | Unknown | 74 | 52 | 22 | 16 | 96 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | -355 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 7058.86 | Unknown | Unknown | Unknown | 59.4 | 6999.46 | 3981 | 1119.63 | 7058.86 | -5939.23 | Yes | N/A | N/A | 2024-05-14 | 2024-05-24 | 11 | 9 | 2024-05-24 | 2024-08-26 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | 2025-01-14 | 2025-03-12 | 58 | 42 | 2025-03-12 | 2025-03-12 | 1 | 1 | 11 | 9 | 154 | 110 | 165 | 119 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -668 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 4981.68 | 1082.31 | Unknown | 191.17 | Unknown | 3708.2 | Unknown | 1150.97 | 4981.68 | -3830.71 | Yes | N/A | N/A | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-11-26 | 62 | 44 | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-26 | 2024-11-27 | 2 | 2 | 2024-11-27 | 2024-11-27 | 1 | 1 | 63 | 45 | 4 | 4 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8233.12 | -22.05 | Unknown | Unknown | 11.69 | 8243.48 | 3981 | 1123.25 | 8233.12 | -7109.87 | Yes | N/A | N/A | 2024-08-29 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-09-19 | 37 | 27 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-11-27 | 1 | 1 | 0 | 0 | 38 | 28 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-05 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2025-01-09 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 3088.49 | Unknown | Unknown | Unknown | 116.65 | 2971.84 | 7882 | 792.01 | 3088.49 | -2296.48 | Yes | N/A | N/A | 2024-11-22 | 2025-02-04 | 75 | 53 | 2025-02-04 | 2025-02-06 | 3 | 3 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-05-22 | 106 | 76 | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-22 | 2025-06-23 | 33 | 23 | 2025-06-23 | 2025-06-23 | 1 | 1 | 181 | 129 | 37 | 27 | 218 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-30 | -160 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 46.61 | -13.24 | Unknown | Unknown | Unknown | 59.85 | 7962 | 807.9 | 46.61 | 761.29 | Yes | N/A | N/A | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-11-17 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-22 | 6 | 4 | 2023-11-22 | 2023-11-22 | 1 | 1 | 54 | 40 | 8 | 6 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1329.23 | -18.1 | Unknown | Unknown | 5.1 | 1342.23 | 3981 | 2792.11 | 1329.23 | 1462.88 | Yes | N/A | N/A | 2024-12-11 | 2025-02-06 | 58 | 42 | 2025-02-06 | 2025-02-10 | 5 | 3 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 58 | 42 | 6 | 4 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 3.42 | -3.07 | Unknown | Unknown | Unknown | 6.49 | Unknown | 297.38 | 3.42 | 293.96 | Yes | N/A | N/A | 2024-01-18 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-01-31 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-15 | 25 | 19 | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 74 | 54 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | -381 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-02-13 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 5568.42 | 2464.94 | Unknown | Unknown | 10.69 | 3092.79 | Unknown | 12439.85 | 5568.42 | 6871.43 | Yes | N/A | N/A | 2025-01-07 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-05-06 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-05 | 61 | 41 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-17 | 33 | 23 | 2025-06-17 | 2025-06-17 | 1 | 1 | 0 | 0 | 248 | 174 | 248 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-12 | 986 | 705 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -365 | -32.51 | Unknown | Unknown | -354 | 21.51 | 3981 | 586.62 | -365 | 951.62 | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | 2023-03-16 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-03-23 | 42 | 30 | 2023-03-16 | 2023-04-04 | 20 | 14 | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2024-11-22 | 481 | 345 | 21 | 15 | 562 | 404 | 583 | 419 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 605098 | 605098 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-31 | -60 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-09-13 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 19306.5 | 644.68 | Unknown | Unknown | -5755 | 24416.82 | 162105 | 45903.56 | 19306.5 | 26597.06 | Yes | N/A | N/A | 2023-08-15 | 2023-08-17 | 3 | 3 | 2023-08-17 | 2023-10-16 | 61 | 43 | 2023-10-16 | 2024-03-26 | 138 | 98 | 2023-09-14 | 2024-01-08 | 96 | 68 | 2023-10-16 | 2024-01-16 | 93 | 67 | 2023-10-26 | 2024-01-10 | 77 | 55 | 2024-01-18 | 2024-01-31 | 14 | 10 | 2024-01-31 | 2024-01-31 | 1 | 1 | 234 | 168 | 249 | 177 | 483 | 345 | Steps 2,3,5,6,7 | 360 | 256 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-11 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 348.86 | -14.59 | Unknown | Unknown | Unknown | 363.45 | Unknown | 931.18 | 348.86 | 582.32 | Yes | N/A | N/A | 2024-04-03 | 2024-04-11 | 9 | 7 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-23 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-14 | 22 | 16 | 2024-05-14 | 2024-05-14 | 1 | 1 | 22 | 16 | 24 | 18 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-09 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1230.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-03-20 | 3 | 3 | 2025-03-20 | 2025-04-03 | 15 | 11 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-05 | 12 | 8 | 2025-05-05 | 2025-05-05 | 1 | 1 | 4 | 4 | 28 | 20 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -319 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 4111.51 | Unknown | Unknown | Unknown | 423.31 | 3688.2 | 3981 | 1056.34 | 4111.51 | -3055.17 | Yes | N/A | N/A | 2024-06-06 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2025-06-09 | 347 | 247 | Unknown | 2024-10-31 | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 347 | 247 | 3 | 3 | 350 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-04-21 | IOU Designed & Installed | N/A | No | N/A | 2145.45 | 439.01 | Unknown | Unknown | Unknown | 1706.44 | Unknown | 2096.85 | 2145.45 | -48.6 | Yes | N/A | N/A | 2025-03-03 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-03 | 7 | 5 | 2025-03-03 | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-24 | 22 | 16 | 2025-03-03 | 2025-04-21 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-04-24 | 4 | 4 | 2025-04-24 | 2025-04-24 | 1 | 1 | 50 | 36 | 34 | 26 | 84 | 62 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -704 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 27.69 | Unknown | Unknown | Unknown | Unknown | 27.69 | 3981 | 1539.6 | 27.69 | 1511.91 | Yes | N/A | N/A | 2025-02-21 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-21 | 3 | 3 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-25 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-10 | 14 | 10 | 2025-03-10 | 2025-03-10 | 1 | 1 | 5 | 3 | 18 | 14 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1569.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-25 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-25 | 31 | 23 | 2024-10-25 | 2025-02-26 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-22 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 130 | 92 | 34 | 26 | 164 | 118 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 183 | 183 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | 20 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -619.13 | -5.5 | Unknown | Unknown | -913 | 299.37 | Unknown | 643.19 | -619.13 | 1262.32 | Yes | N/A | N/A | 2024-09-25 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-10-18 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-28 | 33 | 23 | 2024-10-18 | 2025-02-14 | 120 | 86 | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-06 | Unknown | Unknown | 120 | 86 | 143 | 103 | 263 | 189 | Steps 2,3,5,6,7 | 10 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 1074.28 | 186.39 | Unknown | Unknown | Unknown | 887.89 | 3981 | 1747.24 | 1074.28 | 672.96 | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-02-06 | 52 | 38 | 2025-02-06 | 2025-02-06 | 1 | 1 | 10 | 8 | 54 | 40 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | -633 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 321.21 | -13.35 | Unknown | Unknown | Unknown | 334.56 | 3981 | 1156.78 | 321.21 | 835.57 | Yes | N/A | N/A | 2024-04-15 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-05-01 | 78 | 56 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-06 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-15 | 10 | 8 | 2024-05-15 | 2024-05-15 | 1 | 1 | 6 | 4 | 89 | 65 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-28 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -928.07 | 1315.54 | Unknown | 239.79 | -3076 | 592.6 | Unknown | 3075.59 | -928.07 | 4003.66 | Yes | N/A | N/A | 2024-04-11 | 2024-04-16 | 6 | 4 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 6 | 4 | 1 | 1 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-27 | 191 | 138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-29 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | -14.19 | -27.53 | Unknown | Unknown | Unknown | 13.34 | 3885 | 821.11 | -14.19 | 835.3 | Yes | N/A | N/A | 2023-08-25 | 2023-08-29 | 5 | 3 | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-09-11 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-12-11 | 92 | 66 | 2023-12-11 | 2023-10-04 | Unknown | Unknown | 19 | 13 | 93 | 67 | 112 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 438.05 | 438.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 515.65 | Unknown | Unknown | Unknown | -1138.58 | 1654.23 | Unknown | 1174.46 | 515.65 | 658.81 | Yes | N/A | N/A | 2024-08-26 | 2024-09-10 | 16 | 12 | 2024-09-10 | 2024-10-16 | 37 | 27 | 2024-10-16 | 2024-10-24 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-12-06 | 44 | 32 | Unknown | 2025-02-10 | Unknown | Unknown | 2024-12-06 | 2025-02-28 | 85 | 61 | 2025-02-28 | 2025-02-26 | Unknown | Unknown | 69 | 51 | 122 | 88 | 191 | 139 | Steps 2,3,5,6,7 | 66 | 46 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-14 | 142 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-30 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 21.5 | -10.95 | Unknown | Unknown | 27.14 | 5.31 | 3981 | 646.03 | 21.5 | 624.53 | Yes | N/A | N/A | 2022-12-30 | 2023-03-13 | 74 | 52 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 74 | 52 | 1 | 1 | 75 | 53 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-23 | 95 | 68 | No | 2022-06-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-24 | 2022-06-24 | 2023-06-14 | IOU Designed & Installed | N/A | Yes | 234 | -10.51 | -8.27 | Unknown | Unknown | Unknown | -2.24 | 3885 | 343.43 | -10.51 | 353.94 | Yes | N/A | N/A | 2022-06-24 | 2023-02-13 | 235 | 167 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-06-24 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-09-28 | 107 | 77 | 2023-09-28 | 2023-06-26 | Unknown | Unknown | 235 | 167 | 107 | 77 | 342 | 244 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-03 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 8541.51 | Unknown | Unknown | Unknown | -622 | 9163.51 | 3981 | 1619.24 | 8541.51 | -6922.27 | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-17 | 2024-11-20 | 35 | 25 | 2024-11-20 | 2024-11-20 | 1 | 1 | 1 | 1 | 36 | 26 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | 122 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | -2853.51 | 23.64 | Unknown | Unknown | -2904 | 26.85 | 0 | 960.43 | -2853.51 | 3813.94 | Yes | N/A | N/A | 2024-05-21 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2025-01-27 | 319 | 227 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-04-22 | 79 | 57 | 2025-01-27 | 2025-06-09 | 134 | 96 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 134 | 96 | 400 | 286 | 534 | 382 | Steps 2,3,5,6,7 | 85 | 61 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -447 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 1282.26 | Unknown | Unknown | Unknown | 10.35 | 1271.91 | 3981 | 1463.47 | 1282.26 | 181.21 | Yes | N/A | N/A | 2024-03-21 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-09-12 | 161 | 115 | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-12 | 2024-09-30 | 19 | 13 | 2024-09-30 | 2024-09-27 | Unknown | Unknown | 161 | 115 | 19 | 13 | 180 | 128 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-12 | 1660 | 1187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 1545.63 | -9.16 | Unknown | Unknown | Unknown | 1554.79 | 101098 | 4095.55 | 1545.63 | 2549.92 | Yes | N/A | N/A | 2023-12-14 | 2023-12-15 | 2 | 2 | 2023-12-15 | 2024-03-05 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2025-05-21 | 443 | 317 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-29 | 2025-05-30 | 2 | 2 | 2025-05-30 | 2025-05-30 | 1 | 1 | 445 | 319 | 85 | 61 | 530 | 380 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-18 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | 1456.64 | Unknown | Unknown | Unknown | 5.63 | 1451.01 | 3981 | 1220.59 | 1456.64 | -236.05 | Yes | N/A | N/A | 2025-01-30 | 2025-02-26 | 28 | 20 | 2025-02-26 | 2025-03-03 | 6 | 4 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-05-07 | 66 | 48 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-19 | 13 | 9 | 2025-05-19 | 2025-05-19 | 1 | 1 | 94 | 68 | 20 | 14 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2046.15 | 2281.57 | Unknown | 737.29 | -2085 | 1112.29 | Unknown | 2085.15 | 2046.15 | 39 | Yes | N/A | N/A | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -7 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 7962 | 984.98 | Unknown | 984.98 | Yes | N/A | N/A | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | 2024-06-20 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-11-08 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-05 | 22 | 16 | 2024-09-05 | 2024-11-08 | 65 | 47 | 143 | 103 | 158 | 114 | 301 | 217 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 415 | 298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 15030.99 | 2913.68 | Unknown | Unknown | Unknown | 12117.31 | Unknown | 760.87 | 15030.99 | -14270.12 | Yes | N/A | N/A | 2023-12-14 | 2023-12-14 | 1 | 1 | 2023-12-14 | 2024-03-26 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-01-19 | 4 | 4 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-19 | 9 | 7 | 2024-04-19 | 2024-04-19 | 1 | 1 | 1 | 1 | 118 | 86 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 9700.44 | 448.78 | Unknown | Unknown | -3924 | 13175.66 | 8662.55 | 2135.99 | 9700.44 | -7564.45 | Yes | N/A | N/A | 2023-11-10 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2024-03-19 | 341 | 243 | 2023-12-11 | 2024-03-11 | 60 | 42 | 2024-02-02 | 2024-02-28 | 27 | 19 | 2024-04-04 | Unknown | Unknown | Unknown | 2024-04-04 | 2024-05-09 | 36 | 26 | 2024-05-09 | 2024-06-06 | 29 | 21 | 2024-06-06 | 2024-06-06 | 1 | 1 | 60 | 42 | 434 | 310 | 494 | 352 | Steps 2,3,5,6,7 | 137 | 97 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -128 | -93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.3 | -3.82 | Unknown | Unknown | Unknown | 8.12 | Unknown | 571.18 | 4.3 | 566.88 | Yes | N/A | N/A | 2023-12-15 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2023-12-15 | 26 | 20 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-07-02 | 1 | 1 | 0 | 0 | 27 | 21 | 27 | 21 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 406 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-11 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 1326.8 | Unknown | Unknown | Unknown | -364.18 | 1690.98 | Unknown | 394.4 | 1326.8 | -932.4 | Yes | N/A | N/A | 2023-04-07 | 2023-04-25 | 19 | 13 | 2023-04-25 | 2023-06-14 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-11-15 | 155 | 111 | Unknown | 2023-11-16 | Unknown | Unknown | 2024-02-27 | 2024-02-28 | 2 | 2 | 2024-02-28 | 2024-01-11 | Unknown | Unknown | 174 | 124 | 53 | 39 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-15 | 677 | 484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 5921.01 | Unknown | Unknown | Unknown | Unknown | 5921.01 | 4288 | 529.71 | 5921.01 | -5391.3 | Yes | N/A | N/A | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | 2023-10-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-17 | 6 | 4 | Unknown | 2023-10-17 | Unknown | Unknown | 2023-10-19 | 2023-11-29 | 42 | 30 | 2023-11-29 | 2023-10-23 | Unknown | Unknown | 7 | 5 | 45 | 33 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | -140 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | 19146.25 | 4960.61 | Unknown | Unknown | 269.52 | 13916.12 | 3981 | 1212.28 | 19146.25 | -17933.97 | Yes | N/A | N/A | 2023-07-26 | 2023-05-25 | Unknown | Unknown | 2023-05-25 | 2023-07-27 | 64 | 46 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-11-02 | 93 | 67 | 2023-11-02 | 2023-11-02 | 1 | 1 | 7 | 5 | 158 | 114 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-28 | 139 | 100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 204.91 | -9.65 | Unknown | Unknown | 7.96 | 206.6 | 3885 | 340.41 | 204.91 | 135.5 | Yes | N/A | N/A | 2023-04-18 | 2023-04-25 | 8 | 6 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-07-19 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-08-14 | 27 | 19 | 2023-08-14 | 2023-08-14 | 1 | 1 | 94 | 68 | 28 | 20 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 122 | 122 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-11 | 142 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 757.43 | -18.57 | Unknown | Unknown | 5.36 | 770.64 | 3981 | 1100.86 | 757.43 | 343.43 | Yes | N/A | N/A | 2023-12-14 | 2024-01-02 | 20 | 14 | 2024-01-02 | 2024-02-27 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-08 | 3 | 3 | 2024-02-27 | 2024-04-02 | 36 | 26 | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-01 | Unknown | Unknown | 56 | 40 | 60 | 44 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 4.46 | Unknown | Unknown | Unknown | Unknown | 4.46 | Unknown | 683.74 | 4.46 | 679.28 | Yes | N/A | N/A | 2024-04-24 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-04-24 | 70 | 50 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-07-22 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-25 | 4 | 4 | 2024-07-25 | 2024-07-25 | 1 | 1 | 90 | 64 | 75 | 55 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | 248 | 248 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -346 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-07 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 1465.74 | Unknown | Unknown | Unknown | 12.26 | 1453.48 | 3981 | 1423.33 | 1465.74 | -42.41 | Yes | N/A | N/A | 2024-11-01 | 2024-12-12 | 42 | 30 | 2024-12-12 | 2025-03-25 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-05 | 22 | 16 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 42 | 30 | 128 | 92 | 170 | 122 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Poway | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-27 | 541 | 388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-05-08 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 355.17 | Unknown | Unknown | Unknown | Unknown | 355.17 | 15551.06 | 8307.81 | 355.17 | 7952.64 | Yes | N/A | N/A | 2023-01-11 | 2023-02-16 | 37 | 27 | 2023-02-16 | 2023-06-20 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-06-27 | 8 | 6 | 2023-06-20 | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-20 | 15 | 11 | 2024-06-20 | 2024-06-20 | 1 | 1 | 37 | 27 | 149 | 107 | 186 | 134 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JACUMBA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -250 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-25 | 2023-07-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 495.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-05-25 | 16 | 12 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-07-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-10 | 5 | 3 | 2023-07-10 | 2023-07-10 | 1 | 1 | 59 | 43 | 6 | 4 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -287 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 4623.8 | 662.81 | Unknown | 1145.53 | Unknown | 2815.46 | 3941 | 1459.93 | 4623.8 | -3163.87 | Yes | N/A | N/A | 2024-07-05 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | 2024-07-05 | 29 | 21 | 2024-07-05 | 2024-07-16 | 2 | 2 | 2024-07-11 | 2024-07-19 | 9 | 7 | 2024-07-05 | 2024-07-22 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-21 | 31 | 23 | 2024-08-21 | 2024-08-21 | 1 | 1 | 20 | 14 | 70 | 52 | 90 | 66 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -627 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 47.08 | Unknown | Unknown | Unknown | Unknown | 47.08 | 3981 | 1343.76 | 47.08 | 1296.68 | Yes | N/A | N/A | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-08-20 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-26 | 7 | 5 | 2024-08-26 | 2024-08-26 | 1 | 1 | 90 | 64 | 9 | 7 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 43 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 797 | Unknown | Unknown | Unknown | Unknown | 797 | Unknown | 345.92 | 797 | -451.08 | Yes | N/A | N/A | 2024-10-10 | 2024-12-02 | 54 | 38 | 2024-12-02 | 2025-03-06 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-11 | 33 | 23 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 54 | 38 | 129 | 93 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 10.7 | 10.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -366 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-06-28 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | -562.49 | Unknown | Unknown | Unknown | -643 | 80.51 | 3981 | 1725.22 | -562.49 | 2287.71 | Yes | N/A | N/A | 2024-02-13 | 2024-06-28 | 137 | 99 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | 2024-08-13 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-09-24 | 78 | 56 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-24 | 2024-09-30 | 7 | 5 | 2024-09-30 | 2024-09-27 | Unknown | Unknown | 262 | 188 | 8 | 6 | 270 | 194 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2025-01-13 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 106.04 | -14.06 | Unknown | Unknown | Unknown | 120.1 | Unknown | 2460.32 | 106.04 | 2354.28 | Yes | N/A | N/A | 2024-12-06 | 2025-01-13 | 39 | 27 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-03-11 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-27 | 17 | 13 | 2025-03-27 | 2025-03-27 | 1 | 1 | 97 | 69 | 19 | 15 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | 141 | 102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 3999.8 | 697.71 | Unknown | 68.04 | -341.13 | 3575.18 | Unknown | 355.58 | 3999.8 | -3644.22 | Yes | N/A | N/A | 2022-08-31 | 2024-05-28 | 637 | 455 | 2024-05-28 | 2024-05-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | 2025-02-18 | Unknown | Unknown | 637 | 455 | 3 | 3 | 640 | 458 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | -246 | -177 | No | 2023-03-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-26 | 2023-06-01 | IOU Designed & Installed | N/A | Yes | 47 | -7.59 | -5.5 | Unknown | Unknown | Unknown | -2.09 | 3981 | 495.75 | -7.59 | 503.34 | Yes | N/A | N/A | 2023-03-31 | 2023-05-17 | 48 | 34 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-06-01 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-06-07 | 7 | 5 | 2023-06-07 | 2023-06-07 | 1 | 1 | 85 | 61 | 8 | 6 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -527 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 661.83 | -11.6 | Unknown | Unknown | Unknown | 673.43 | 3941 | 1516.74 | 661.83 | 854.91 | Yes | N/A | N/A | 2024-08-28 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-28 | 20 | 14 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2025-02-12 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-26 | 15 | 11 | 2025-02-26 | 2025-02-21 | Unknown | Unknown | 169 | 121 | 35 | 25 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-16 | 373 | 268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 678.96 | -37.68 | Unknown | Unknown | -1984 | 2700.64 | Unknown | 1881.41 | 678.96 | 1202.45 | Yes | N/A | N/A | 2023-05-03 | 2023-09-08 | 129 | 93 | 2023-09-08 | 2023-09-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2024-03-06 | 27 | 19 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-05-23 | 1 | 1 | 129 | 93 | 43 | 31 | 172 | 124 | Steps 2,3,5,6,7 | 166 | 118 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-15 | -264 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4070.27 | 615.67 | Unknown | 320.5 | Unknown | 3134.1 | 3981 | 1055.79 | 4070.27 | -3014.48 | Yes | N/A | N/A | 2023-11-08 | 2023-12-19 | 42 | 30 | 2023-12-19 | 2023-12-26 | 8 | 6 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-01-25 | 1 | 1 | 42 | 30 | 9 | 7 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-09 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 16.4 | Unknown | Unknown | Unknown | Unknown | 16.4 | Unknown | 1677.82 | 16.4 | 1661.42 | Yes | N/A | N/A | 2024-11-25 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-12-09 | 20 | 14 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-01-10 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-06 | 28 | 20 | 2025-02-06 | 2025-02-06 | 1 | 1 | 33 | 25 | 49 | 35 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 164 | 164 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -374 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-14 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 283.52 | -8.42 | Unknown | Unknown | 5.01 | 286.93 | 3961 | 988.17 | 283.52 | 704.65 | Yes | N/A | N/A | 2024-03-07 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-04-15 | 74 | 52 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-06-06 | 53 | 39 | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-06 | 2024-07-09 | 34 | 24 | 2024-07-09 | 2024-07-09 | 1 | 1 | 53 | 39 | 109 | 77 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-18 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-28 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 1152.06 | -1.25 | Unknown | Unknown | 14.56 | 1138.75 | 3981 | 1343.57 | 1152.06 | 191.51 | Yes | N/A | N/A | 2023-12-21 | 2024-01-08 | 19 | 13 | 2024-01-08 | 2024-01-25 | 18 | 14 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-07-12 | 170 | 122 | Unknown | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-07-29 | 18 | 12 | 2024-07-29 | 2024-07-29 | 1 | 1 | 189 | 135 | 37 | 27 | 226 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-13 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 0.19 | -5.71 | Unknown | Unknown | Unknown | 5.9 | 3981 | 818.01 | 0.19 | 817.82 | Yes | N/A | N/A | 2023-09-19 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-19 | 84 | 60 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-10-09 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-23 | 15 | 11 | 2023-10-23 | 2023-10-23 | 1 | 1 | 21 | 15 | 100 | 72 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -225 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-05 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | -2126.58 | 1511.71 | Unknown | Unknown | -4473 | 834.71 | Unknown | 4473.34 | -2126.58 | 6599.92 | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1 | 1 | 2025-03-28 | 2025-03-28 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 162 | 117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 2088.19 | -5.45 | Unknown | Unknown | 43.26 | 2050.38 | 3981 | 604.74 | 2088.19 | -1483.45 | Yes | N/A | N/A | 2024-12-30 | 2025-03-13 | 74 | 54 | 2025-03-13 | 2025-03-19 | 7 | 5 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-03-17 | 2025-03-21 | 5 | 5 | 2025-03-19 | 2025-06-11 | 85 | 61 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-06-11 | 2025-06-12 | 2 | 2 | 2025-06-12 | 2025-06-12 | 1 | 1 | 160 | 116 | 15 | 13 | 175 | 129 | Steps 2,3,5,6,7 | 31 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-19 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 712.53 | -9.76 | Unknown | Unknown | 10.42 | 711.87 | 3981 | 1317.13 | 712.53 | 604.6 | Yes | N/A | N/A | 2023-08-03 | 2023-07-30 | Unknown | Unknown | 2023-07-30 | 2023-09-27 | 60 | 43 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-01-03 | 99 | 71 | Unknown | 2023-12-20 | Unknown | Unknown | 2024-01-03 | 2024-01-09 | 7 | 5 | 2024-01-09 | 2024-01-09 | 1 | 1 | 99 | 71 | 68 | 49 | 167 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-09 | 1435 | 1026 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.19 | -6.52 | Unknown | Unknown | Unknown | 4.33 | Unknown | 603.47 | -2.19 | 605.66 | Yes | N/A | N/A | 2023-05-18 | 2023-05-19 | 2 | 2 | 2023-05-19 | 2023-05-30 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-06-14 | 23 | 17 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 2 | 2 | 36 | 26 | 38 | 28 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 6.96 | Unknown | Unknown | Unknown | Unknown | 6.96 | Unknown | 192.95 | 6.96 | 185.99 | Yes | N/A | N/A | 2024-07-23 | 2024-08-02 | 11 | 9 | 2024-08-02 | 2024-08-02 | 1 | 1 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-13 | 12 | 8 | 2024-08-13 | 2024-08-13 | 1 | 1 | 12 | 10 | 14 | 10 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -508 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 8.72 | -6.72 | Unknown | Unknown | Unknown | 15.44 | Unknown | 368.49 | 8.72 | 359.77 | Yes | N/A | N/A | 2024-01-23 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2024-02-16 | 81 | 59 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-06-10 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-07-02 | 23 | 17 | 2024-07-02 | 2024-07-02 | 1 | 1 | 116 | 82 | 105 | 77 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | -497 | -356 | No | 2023-02-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-04-07 | IOU Designed & Installed | N/A | Yes | 91 | -16.2 | -11.74 | Unknown | Unknown | Unknown | -4.46 | Unknown | 733.16 | -16.2 | 749.36 | Yes | N/A | N/A | 2023-02-21 | 2023-05-23 | 92 | 66 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | 2023-04-07 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-06-26 | 81 | 57 | 2023-06-26 | 2023-06-26 | 1 | 1 | 137 | 99 | 82 | 58 | 219 | 157 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -186 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-03-14 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 603.37 | 185.02 | Unknown | Unknown | Unknown | 418.35 | 3981 | 900.26 | 603.37 | 296.89 | Yes | N/A | N/A | 2023-12-20 | 2024-03-14 | 86 | 62 | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-07-03 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-08 | 6 | 4 | 2024-07-08 | 2024-07-08 | 1 | 1 | 198 | 142 | 8 | 6 | 206 | 148 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-27 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 7014.15 | 1856.83 | Unknown | 1084.25 | Unknown | 4073.07 | Unknown | 308.87 | 7014.15 | -6705.28 | Yes | N/A | N/A | 2024-02-06 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-02-27 | 78 | 56 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-02-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-11 | 14 | 10 | 2024-03-11 | 2024-03-11 | 1 | 1 | 1 | 1 | 93 | 67 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -690 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 299.21 | -4.5 | Unknown | Unknown | 0.38 | 303.33 | 3981 | 1589.1 | 299.21 | 1289.89 | Yes | N/A | N/A | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-03 | 25 | 17 | 2025-03-03 | 2025-03-03 | 1 | 1 | 3 | 3 | 27 | 19 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -614 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | 1429.99 | Unknown | Unknown | Unknown | 8.55 | 1421.44 | 3981 | 1409.67 | 1429.99 | -20.32 | Yes | N/A | N/A | 2025-03-19 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-28 | 25 | 19 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-06-06 | 71 | 51 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-06-06 | 2025-06-16 | 11 | 7 | 2025-06-16 | 2025-06-16 | 1 | 1 | 71 | 51 | 37 | 27 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -2.65 | -5.11 | Unknown | Unknown | Unknown | 2.46 | Unknown | 264.34 | -2.65 | 266.99 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | 2023-07-11 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-10-12 | 88 | 64 | 2023-10-12 | 2023-10-12 | 1 | 1 | 1 | 1 | 118 | 86 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 611 | 611 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 155 | 112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13790.91 | 4861.57 | Unknown | Unknown | 86.64 | 8842.7 | 20269 | 5277.55 | 13790.91 | -8513.36 | Yes | N/A | N/A | 2024-02-22 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-04-16 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-11-07 | 206 | 148 | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-12-13 | 133 | 95 | 206 | 148 | 208 | 148 | 414 | 296 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | 51 | 38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1375.38 | -27.19 | Unknown | Unknown | Unknown | 1402.57 | 3981 | 1575.94 | 1375.38 | 200.56 | Yes | N/A | N/A | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | 2024-06-28 | 3 | 3 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-22 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-03 | -447 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 3848.74 | 1153.08 | Unknown | Unknown | Unknown | 2695.66 | Unknown | 936.46 | 3848.74 | -2912.28 | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-01-09 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-12 | 4 | 4 | 2024-01-12 | 2024-01-12 | 1 | 1 | 106 | 76 | 6 | 6 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -689 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 29.81 | Unknown | Unknown | Unknown | Unknown | 29.81 | 3981 | 1560.56 | 29.81 | 1530.75 | Yes | N/A | N/A | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-15 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-30 | 16 | 12 | 2025-01-30 | 2025-01-30 | 1 | 1 | 4 | 4 | 18 | 14 | 22 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -228 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 12572.7 | 5235.24 | Unknown | 4052.58 | Unknown | 3284.88 | Unknown | 154.99 | 12572.7 | -12417.71 | Yes | N/A | N/A | 2023-09-12 | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-09-28 | 85 | 61 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-09-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-11-21 | 54 | 38 | 2023-11-21 | 2023-11-21 | 1 | 1 | 2 | 2 | 140 | 100 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | 153 | 110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 20423.78 | 276.93 | Unknown | 152.89 | 14.65 | 19979.31 | 3981 | 2039.19 | 20423.78 | -18384.59 | Yes | N/A | N/A | 2023-09-06 | 2023-10-04 | 29 | 21 | 2023-10-04 | 2023-10-04 | 1 | 1 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2024-09-03 | 336 | 240 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-09-03 | 2024-09-26 | 24 | 18 | 2024-09-26 | 2024-09-26 | 1 | 1 | 365 | 261 | 26 | 20 | 391 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 123 | 123 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 31.21 | Unknown | Unknown | Unknown | Unknown | 31.21 | 23886 | 739 | 31.21 | 707.79 | Yes | N/A | N/A | 2023-11-03 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | 2023-11-13 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-10-23 | 346 | 248 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-14 | Unknown | Unknown | 346 | 248 | 82 | 58 | 428 | 306 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 226.4 | 226.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -451 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-12-16 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 11813.36 | Unknown | Unknown | Unknown | Unknown | 11813.36 | 3981 | 1610.88 | 11813.36 | -10202.48 | Yes | N/A | N/A | 2024-10-17 | 2024-12-23 | 68 | 48 | 2024-12-23 | 2025-03-27 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-26 | 22 | 16 | 2025-03-27 | 2025-03-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-05-05 | 35 | 25 | 2025-05-05 | 2025-05-05 | 1 | 1 | 69 | 49 | 153 | 111 | 222 | 160 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -632 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 861.75 | -16.68 | Unknown | Unknown | Unknown | 878.43 | Unknown | 4348.26 | 861.75 | 3486.51 | Yes | N/A | N/A | 2024-09-24 | 2024-10-02 | 9 | 7 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1 | 1 | 9 | 7 | 2 | 2 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-NORTH of 56 | 80.1 | 80.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 111 | 80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-15 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 5767.08 | 564.19 | Unknown | Unknown | -8046.51 | 13249.4 | 3981 | 12040.62 | 5767.08 | 6273.54 | Yes | N/A | N/A | 2023-09-08 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2024-06-03 | 299 | 213 | 2024-01-05 | 2024-04-09 | 5 | 3 | 2024-02-06 | 2024-06-19 | 30 | 22 | 2024-06-03 | 2024-08-08 | 67 | 49 | 2024-06-10 | 2024-08-01 | 53 | 39 | 2024-08-20 | 2024-10-15 | 57 | 41 | 2024-10-15 | 2024-09-19 | Unknown | Unknown | 72 | 52 | 439 | 315 | 511 | 367 | Steps 2,3,5,6,7 | 288 | 206 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-27 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 669.22 | -12.92 | Unknown | Unknown | Unknown | 682.14 | 3981 | 1423.59 | 669.22 | 754.37 | Yes | N/A | N/A | 2024-08-27 | 2024-07-27 | Unknown | Unknown | 2024-07-27 | 2024-08-27 | 32 | 22 | 2024-08-27 | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-06 | 11 | 9 | 2024-08-27 | 2024-10-02 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-15 | 14 | 10 | 2024-10-15 | 2024-10-15 | 1 | 1 | 37 | 27 | 58 | 42 | 95 | 69 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 24.09 | Unknown | Unknown | Unknown | Unknown | 24.09 | 3981 | 1624.03 | 24.09 | 1599.94 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-15 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-09 | 25 | 17 | 2024-12-09 | 2024-12-09 | 1 | 1 | 6 | 6 | 27 | 19 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Agricultural | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-07-07 | 1905 | 1361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | -232.63 | Unknown | Unknown | Unknown | -638 | 405.37 | Unknown | 580.87 | -232.63 | 813.5 | Yes | N/A | N/A | 2024-07-01 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-07-16 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-07-26 | 11 | 9 | Unknown | 2024-09-16 | Unknown | Unknown | 2024-09-17 | 2024-11-29 | 74 | 54 | 2024-11-29 | 2024-09-23 | Unknown | Unknown | 11 | 9 | 96 | 70 | 107 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | -381 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 2895.25 | 244.9 | Unknown | 235.84 | 47.49 | 2367.02 | Unknown | 661.64 | 2895.25 | -2233.61 | Yes | N/A | N/A | 2023-07-25 | 2023-08-22 | 29 | 21 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-11-07 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-11-13 | 7 | 5 | 2023-11-13 | 2023-11-13 | 1 | 1 | 107 | 77 | 8 | 6 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-25 | -933 | -668 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26.22 | Unknown | Unknown | Unknown | Unknown | 26.22 | 3981 | 1708.53 | 26.22 | 1682.31 | Yes | N/A | N/A | 2024-09-16 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-16 | 12 | 8 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-12-04 | 1 | 1 | 0 | 0 | 13 | 9 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 127.05 | 127.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-02 | 58 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1047.14 | -0.94 | Unknown | Unknown | -1156 | 109.8 | 10433.58 | 2946.59 | -1047.14 | 3993.73 | Yes | N/A | N/A | 2023-10-18 | 2023-11-17 | 31 | 23 | 2023-11-17 | 2023-11-30 | 14 | 10 | 2023-11-30 | 2024-02-08 | 10 | 8 | 2023-11-30 | 2024-03-12 | 104 | 74 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-07-30 | 1 | 1 | 41 | 31 | 119 | 85 | 160 | 116 | Steps 2,3,5,6,7 | 166 | 118 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11540.05 | 11540.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-30 | -773 | -552 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-07-17 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 0.37 | -11.46 | Unknown | Unknown | Unknown | 11.83 | 3981 | 846.79 | 0.37 | 846.42 | Yes | N/A | N/A | 2023-06-30 | 2023-07-17 | 18 | 12 | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-10-05 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-17 | 44 | 32 | 2023-11-17 | 2023-10-19 | Unknown | Unknown | 99 | 71 | 45 | 33 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2024-01-24 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 761.18 | -13.69 | Unknown | Unknown | Unknown | 774.87 | 3981 | 769.28 | 761.18 | 8.1 | Yes | N/A | N/A | 2023-10-02 | 2024-01-24 | 115 | 83 | 2024-01-24 | 2024-01-30 | 7 | 5 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-04-19 | 81 | 59 | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-19 | 2024-04-30 | 12 | 8 | 2024-04-30 | 2024-04-30 | 1 | 1 | 196 | 142 | 20 | 14 | 216 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-04 | -508 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-10-01 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | -1695.24 | Unknown | Unknown | Unknown | -1774 | 78.76 | Unknown | 2290.85 | -1695.24 | 3986.09 | Yes | N/A | N/A | 2024-08-08 | 2024-09-25 | 49 | 35 | 2024-09-25 | 2024-10-01 | 7 | 5 | 2024-10-01 | 2024-10-17 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-01-29 | 105 | 75 | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-29 | 2025-02-11 | 14 | 10 | 2025-02-11 | 2025-02-11 | 1 | 1 | 171 | 123 | 22 | 16 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -439 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.19 | Unknown | Unknown | Unknown | Unknown | 14.19 | Unknown | 186.4 | 14.19 | 172.21 | Yes | N/A | N/A | 2024-06-03 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-06-18 | 77 | 55 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-13 | 1 | 1 | 0 | 0 | 78 | 56 | 78 | 56 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | 132 | 95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1013.63 | 246.68 | Unknown | 144.5 | 1.04 | 621.41 | 3981 | 2344.24 | 1013.63 | 1330.61 | Yes | N/A | N/A | 2023-09-19 | 2024-08-01 | 318 | 228 | 2024-08-01 | 2024-08-08 | 8 | 6 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2024-12-12 | 1 | 1 | 318 | 228 | 9 | 7 | 327 | 235 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 12304.35 | Unknown | Unknown | Unknown | Unknown | 12304.35 | 28804 | 626.05 | 12304.35 | -11678.3 | Yes | N/A | N/A | 2024-04-16 | 2024-05-09 | 24 | 18 | 2024-05-09 | Unknown | Unknown | Unknown | 2024-05-22 | 2024-08-01 | 3 | 3 | 2024-05-24 | 2025-05-08 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-08-16 | 52 | 38 | 2024-08-16 | 2024-08-16 | 1 | 1 | 27 | 21 | 147 | 107 | 174 | 128 | Steps 2,3,5,6,7 | 69 | 49 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-11 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2338.71 | -8.05 | Unknown | Unknown | 5.87 | 2340.89 | 3981 | 1202.13 | 2338.71 | -1136.58 | Yes | N/A | N/A | 2025-01-29 | 2025-02-13 | 16 | 12 | 2025-02-13 | 2025-02-14 | 2 | 2 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-18 | 1 | 1 | 16 | 12 | 3 | 3 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | -162 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | 9231.14 | Unknown | Unknown | Unknown | Unknown | 9231.14 | 7349 | 542.52 | 9231.14 | -8688.62 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | 2023-07-11 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-12 | 28 | 20 | 2023-12-12 | 2023-12-07 | Unknown | Unknown | 1 | 1 | 98 | 70 | 99 | 71 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | -47 | -34 | No | 2023-11-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-08-14 | IOU Designed & Installed | N/A | Yes | 143 | 1322.38 | Unknown | Unknown | Unknown | 73.52 | 1248.86 | 3981 | 1325.68 | 1322.38 | 3.3 | Yes | N/A | N/A | 2023-11-28 | 2024-04-19 | 144 | 104 | 2024-04-19 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-08-14 | 259 | 185 | Unknown | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-09-03 | 21 | 15 | 2024-09-03 | 2024-09-03 | 1 | 1 | 403 | 289 | 22 | 16 | 425 | 305 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1285.15 | Unknown | Unknown | Unknown | 13.73 | 1271.42 | Unknown | 1441.31 | 1285.15 | 156.16 | Yes | N/A | N/A | 2024-09-19 | 2024-09-26 | 8 | 6 | 2024-09-26 | 2024-11-01 | 37 | 27 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-01-21 | 82 | 58 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-01-21 | 2025-02-04 | 15 | 11 | 2025-02-04 | 2025-02-03 | Unknown | Unknown | 90 | 64 | 52 | 38 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 106.56 | -1.5 | Unknown | Unknown | Unknown | 108.06 | 3981 | 1456.61 | 106.56 | 1350.05 | Yes | N/A | N/A | 2024-10-16 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-16 | 3 | 3 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-18 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-01 | 15 | 11 | 2024-11-01 | 2024-11-01 | 1 | 1 | 3 | 3 | 19 | 15 | 22 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 22.05 | 22.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-12 | -470 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 1026.84 | 327.9 | Unknown | Unknown | Unknown | 698.94 | 3941 | 920.38 | 1026.84 | -106.46 | Yes | N/A | N/A | 2024-03-06 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-06 | 57 | 41 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-22 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-04-29 | 8 | 6 | 2024-04-29 | 2024-04-29 | 1 | 1 | 48 | 34 | 66 | 48 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-25 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 1360.69 | Unknown | Unknown | Unknown | 16.78 | 1343.91 | 3981 | 800.33 | 1360.69 | -560.36 | Yes | N/A | N/A | 2024-03-04 | 2024-03-27 | 24 | 18 | 2024-03-27 | 2024-03-28 | 2 | 2 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-08-27 | 153 | 109 | Unknown | 2024-08-15 | Unknown | Unknown | 2024-08-27 | 2024-09-05 | 10 | 8 | 2024-09-05 | 2024-09-05 | 1 | 1 | 177 | 127 | 13 | 11 | 190 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-03 | 2023-06-16 | IOU Designed & Installed | N/A | No | N/A | 993.55 | 364.98 | Unknown | Unknown | Unknown | 628.57 | Unknown | 773.55 | 993.55 | -220 | Yes | N/A | N/A | 2023-03-31 | 2023-04-03 | 4 | 2 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-06-16 | 75 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-19 | 4 | 2 | 2023-06-19 | 2023-06-19 | 1 | 1 | 79 | 57 | 5 | 3 | 84 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | -296 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-06 | 2023-01-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 414.13 | -25.15 | Unknown | Unknown | 19.05 | 420.23 | 3981 | 706.21 | 414.13 | 292.08 | Yes | N/A | N/A | 2023-01-06 | 2023-03-07 | 61 | 43 | 2023-03-07 | 2023-09-21 | 199 | 143 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2023-12-07 | 1 | 1 | 61 | 43 | 200 | 144 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 1244.69 | -24.15 | Unknown | Unknown | Unknown | 1268.84 | Unknown | 1701.24 | 1244.69 | 456.55 | Yes | N/A | N/A | 2024-04-23 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-04-23 | 47 | 33 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-08 | 16 | 12 | 2024-04-23 | 2024-10-07 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-21 | 15 | 11 | 2024-10-21 | 2024-10-21 | 1 | 1 | 168 | 120 | 79 | 57 | 247 | 177 | Steps 2,3,5,6,7 | 15 | 11 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -980 | -701 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-08 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.88 | -4.25 | Unknown | Unknown | Unknown | -1.63 | 7827 | 404.77 | -5.88 | 410.65 | Yes | N/A | N/A | 2023-04-08 | 2023-04-10 | 3 | 1 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-09 | 1 | 1 | 3 | 1 | 1 | 1 | 4 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-19 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2302.3 | 472.08 | Unknown | 532.16 | 5.75 | 1292.31 | 3981 | 1082.67 | 2302.3 | -1219.63 | Yes | N/A | N/A | 2023-04-21 | 2024-09-03 | 502 | 358 | 2024-09-03 | 2024-09-06 | 4 | 4 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-07 | 1 | 1 | 502 | 358 | 5 | 5 | 507 | 363 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-03 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 341.42 | Unknown | Unknown | Unknown | 4.99 | 336.43 | 3961 | 1304.13 | 341.42 | 962.71 | Yes | N/A | N/A | 2024-05-02 | 2024-06-27 | 57 | 41 | 2024-06-27 | 2024-07-12 | 16 | 12 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-08-22 | 42 | 30 | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-22 | 2024-09-05 | 15 | 11 | 2024-09-05 | 2024-09-05 | 1 | 1 | 99 | 71 | 32 | 24 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -423 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | 1601.68 | 310.2 | Unknown | 70.42 | 12.74 | 1208.32 | 3981 | 656.47 | 1601.68 | -945.21 | Yes | N/A | N/A | 2023-03-28 | 2023-06-13 | 78 | 56 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-11-15 | 156 | 112 | Unknown | 2023-11-13 | Unknown | Unknown | 2023-11-15 | 2023-11-30 | 16 | 12 | 2023-11-30 | 2023-11-30 | 1 | 1 | 234 | 168 | 17 | 13 | 251 | 181 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 2704.84 | 442.06 | Unknown | Unknown | 13.16 | 2249.62 | 3941 | 726.26 | 2704.84 | -1978.58 | Yes | N/A | N/A | 2024-02-27 | 2024-05-04 | 68 | 49 | 2024-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-04 | 2024-06-06 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-07 | 2 | 2 | 2024-06-07 | 2024-06-07 | 1 | 1 | 102 | 73 | 3 | 3 | 105 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 284 | 284 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | -156 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-04-25 | IOU Designed & Installed | N/A | No | N/A | 211.5 | -8.76 | Unknown | Unknown | Unknown | 220.26 | Unknown | 376.27 | 211.5 | 164.77 | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | 2023-04-25 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-06-12 | 49 | 35 | 2023-06-12 | 2023-06-12 | 1 | 1 | 79 | 57 | 50 | 36 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 777 | 556 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-04-01 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 10897.79 | 23.42 | Unknown | Unknown | 0.12 | 10874.25 | 75103 | 2933.86 | 10897.79 | -7963.93 | Yes | N/A | N/A | 2024-03-19 | 2024-05-28 | 71 | 51 | 2024-05-28 | 2024-06-13 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2025-04-11 | 303 | 217 | Unknown | 2025-04-11 | Unknown | Unknown | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 374 | 268 | 18 | 14 | 392 | 282 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -57 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 454.43 | -4.15 | Unknown | Unknown | Unknown | 458.58 | 3981 | 739 | 454.43 | 284.57 | Yes | N/A | N/A | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | 2023-11-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-16 | 4 | 4 | 2023-11-16 | 2023-12-19 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-01-31 | Unknown | Unknown | 35 | 25 | 8 | 8 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-10 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 133.47 | -47.87 | Unknown | Unknown | -505 | 686.34 | 3981 | 5606.61 | 133.47 | 5473.14 | Yes | N/A | N/A | 2024-01-09 | 2024-01-24 | 16 | 12 | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | 2024-02-22 | 30 | 22 | 2024-01-29 | 2024-01-31 | 3 | 3 | 2024-02-22 | 2024-05-14 | 83 | 59 | Unknown | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-05-23 | 10 | 8 | 2024-05-23 | 2024-05-22 | Unknown | Unknown | 129 | 93 | 14 | 12 | 143 | 105 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-05 | 427 | 306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-04-18 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 30863.28 | -148.62 | Unknown | Unknown | 235.69 | 30776.21 | 0 | 21258.67 | 30863.28 | -9604.61 | Yes | N/A | N/A | 2023-02-28 | 2023-04-14 | 46 | 34 | 2023-04-14 | 2024-04-03 | 356 | 254 | 2023-05-25 | 2023-11-13 | 29 | 21 | 2023-07-05 | 2023-09-21 | 4 | 4 | 2024-04-03 | 2024-08-12 | 132 | 94 | Unknown | 2024-06-21 | Unknown | Unknown | 2024-06-17 | 2024-09-04 | 80 | 58 | 2024-09-04 | 2024-09-04 | 1 | 1 | 207 | 149 | 441 | 317 | 648 | 466 | Steps 2,3,5,6,7 | 449 | 321 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 139 | 100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.41 | -6.82 | Unknown | Unknown | Unknown | -2.59 | 3981 | 835.71 | -9.41 | 845.12 | Yes | N/A | N/A | 2022-08-04 | 2023-03-31 | 240 | 172 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-04-19 | Unknown | Unknown | 240 | 172 | 0 | 0 | 240 | 172 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 8351.14 | -112.18 | Unknown | Unknown | Unknown | 8463.32 | 3981 | Not available | 8351.14 | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-03 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2025-05-20 | 230 | 164 | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | 2025-03-13 | 2025-03-13 | 1 | 1 | 230 | 164 | 30 | 22 | 260 | 186 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Capistrano Beach | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-22 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | -3677.03 | 8008.89 | Unknown | 518.11 | -15834 | 3629.97 | Unknown | 15834.1 | -3677.03 | 19511.13 | Yes | N/A | N/A | 2024-02-01 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-03-05 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-08 | 2024-03-27 | 20 | 14 | 2024-03-27 | 2024-03-27 | 1 | 1 | 0 | 0 | 58 | 42 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | -214 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2854.36 | 436.94 | Unknown | 16.32 | 12.81 | 2388.29 | 3981 | 742.28 | 2854.36 | -2112.08 | Yes | N/A | N/A | 2024-02-15 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-03-12 | 36 | 26 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 54.75 | 54.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 12197.14 | 2341.9 | Unknown | Unknown | 72.16 | 9783.08 | Unknown | 14165.17 | 12197.14 | 1968.03 | Yes | N/A | N/A | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | 2025-01-23 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2025-01-09 | 51 | 37 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-04-09 | 72 | 52 | 2025-04-09 | 2025-04-09 | 1 | 1 | 1 | 1 | 252 | 182 | 253 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-07 | -84 | -61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1018.73 | 1928.88 | Unknown | 680.57 | -4561 | 932.82 | Unknown | 4561.28 | -1018.73 | 5580.01 | Yes | N/A | N/A | 2023-10-13 | 2023-10-30 | 18 | 12 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 18 | 12 | 1 | 1 | 19 | 13 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | -514 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 368.69 | -10.3 | Unknown | Unknown | Unknown | 378.99 | Unknown | 776.51 | 368.69 | 407.82 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-09 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 27.46 | Unknown | Unknown | Unknown | Unknown | 27.46 | Unknown | 1436.54 | 27.46 | 1409.08 | Yes | N/A | N/A | 2024-09-05 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-09-05 | 56 | 40 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-11-11 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-18 | 38 | 28 | 2024-12-18 | 2024-12-18 | 1 | 1 | 68 | 48 | 95 | 69 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72.1 | 72.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | -604 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-22 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 642.7 | -10.51 | Unknown | Unknown | Unknown | 653.21 | 3981 | 1142.13 | 642.7 | 499.43 | Yes | N/A | N/A | 2024-04-03 | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-04-22 | 50 | 36 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-06-13 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-28 | 16 | 12 | 2024-06-28 | 2024-06-28 | 1 | 1 | 53 | 39 | 67 | 49 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-05-15 | 343 | 246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2024-04-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 96284.43 | 9756.16 | Unknown | 103.15 | -23868.31 | 110293.43 | Unknown | 69996.97 | 96284.43 | -26287.46 | Yes | N/A | N/A | 2023-08-16 | 2023-08-24 | 9 | 7 | 2023-08-24 | 2023-11-03 | 72 | 52 | 2023-08-24 | 2024-01-03 | 131 | 93 | 2023-09-08 | 2023-11-09 | 14 | 10 | 2023-11-03 | Unknown | Unknown | Unknown | 2023-12-18 | 2024-03-26 | 100 | 72 | 2024-04-01 | 2024-04-22 | 22 | 16 | 2024-04-22 | 2024-04-22 | 1 | 1 | 140 | 100 | 209 | 151 | 349 | 251 | Steps 2,3,5,6,7 | 194 | 138 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 1324.26 | 397.38 | Unknown | 176.88 | 1.09 | 748.91 | 3981 | 796.8 | 1324.26 | -527.46 | Yes | N/A | N/A | 2023-08-14 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-08-30 | 35 | 25 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-10-16 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-26 | 11 | 9 | 2023-10-26 | 2023-10-26 | 1 | 1 | 48 | 34 | 47 | 35 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-13 | -201 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-06-19 | IOU Designed & Installed | N/A | No | N/A | 206.58 | -13.25 | Unknown | Unknown | -359 | 578.83 | Unknown | 644.83 | 206.58 | 438.25 | Yes | N/A | N/A | 2023-02-28 | 2023-04-14 | 46 | 34 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-06-19 | 54 | 38 | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-06-26 | 8 | 6 | 2023-06-26 | 2023-06-26 | 1 | 1 | 100 | 72 | 9 | 7 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 302 | 217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | 2024-04-21 | IOU Designed & Installed | N/A | No | N/A | 477.14 | -14.88 | Unknown | Unknown | Unknown | 492.02 | 3981 | 949.55 | 477.14 | 472.41 | Yes | N/A | N/A | 2023-10-30 | 2023-10-30 | 1 | 1 | 2023-10-30 | 2023-10-30 | 1 | 1 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-04-21 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | 2024-04-21 | 2024-06-03 | 44 | 31 | 2024-06-03 | 2024-05-29 | Unknown | Unknown | 176 | 126 | 45 | 32 | 221 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 92.1 | 92.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -486 | -347 | No | 2022-12-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-05 | 2022-12-07 | Unknown | IOU Designed & Installed | N/A | Yes | 60 | -440.73 | -18.61 | Unknown | Unknown | -646.83 | 224.71 | 3981 | 1181.95 | -440.73 | 1622.68 | Yes | N/A | N/A | 2022-12-05 | 2023-02-03 | 61 | 45 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-05-25 | Unknown | Unknown | 61 | 45 | 0 | 0 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | -214 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-02-14 | 2025-05-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1949.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-02-14 | 30 | 22 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-05-23 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-06-02 | 11 | 7 | 2025-06-02 | 2025-06-02 | 1 | 1 | 129 | 93 | 13 | 9 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 192.05 | 192.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 795.37 | 206.4 | Unknown | Unknown | Unknown | 588.97 | Unknown | 1052.38 | 795.37 | 257.01 | Yes | N/A | N/A | 2025-05-19 | 2025-05-12 | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-18 | 8 | 6 | 2025-06-12 | 2025-06-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-13 | 2 | 2 | 2025-06-13 | 2025-06-13 | 1 | 1 | 1 | 1 | 11 | 9 | 12 | 10 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -1028 | -735 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 691.07 | -7.14 | Unknown | Unknown | Unknown | 698.21 | Unknown | 383.8 | 691.07 | -307.27 | Yes | N/A | N/A | 2023-03-31 | 2023-04-12 | 13 | 9 | 2023-04-12 | 2023-07-05 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-06-13 | 26 | 18 | 2023-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-10-06 | 1 | 1 | 13 | 9 | 112 | 80 | 125 | 89 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -607 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-08 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 16.57 | -14.72 | Unknown | Unknown | Unknown | 31.29 | 3981 | 501.14 | 16.57 | 484.57 | Yes | N/A | N/A | 2024-02-29 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-03-08 | 40 | 30 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-05-20 | 62 | 44 | 2024-05-20 | 2024-05-20 | 1 | 1 | 13 | 9 | 103 | 75 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | -5.5 | -5.65 | Unknown | Unknown | Unknown | 0.15 | Unknown | 162.34 | -5.5 | 167.84 | Yes | N/A | N/A | 2024-04-16 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-03 | 58 | 42 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-07 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-14 | 8 | 6 | 2024-05-14 | 2024-05-14 | 1 | 1 | 5 | 3 | 67 | 49 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-28 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 292.52 | Unknown | Unknown | Unknown | 15.08 | 277.44 | 3621 | 757.99 | 292.52 | 465.47 | Yes | N/A | N/A | 2024-02-15 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-06 | 57 | 41 | 2024-03-06 | 2025-02-27 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-10-18 | 208 | 150 | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-18 | 2024-11-05 | 19 | 13 | 2024-11-05 | 2024-11-05 | 1 | 1 | 567 | 407 | 77 | 55 | 644 | 462 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 1393.63 | -23.83 | Unknown | Unknown | Unknown | 1417.46 | 3885 | 965.91 | 1393.63 | -427.72 | Yes | N/A | N/A | 2024-04-25 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-04-25 | 147 | 105 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-13 | 44 | 32 | 2024-06-13 | 2024-06-13 | 1 | 1 | 7 | 5 | 192 | 138 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -559 | -400 | No | 2024-12-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-05-12 | IOU Designed & Installed | N/A | Yes | 125 | 444.62 | -8.94 | Unknown | Unknown | Unknown | 453.56 | Unknown | 2193.9 | 444.62 | 1749.28 | Yes | N/A | N/A | 2024-12-11 | 2025-04-15 | 126 | 90 | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-22 | 42 | 30 | 2024-12-12 | 2025-05-12 | 152 | 108 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-22 | 11 | 9 | 2025-05-22 | 2025-05-22 | 1 | 1 | 278 | 198 | 55 | 41 | 333 | 239 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-20 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 16417.29 | 4535.86 | Unknown | 1388.6 | -2230 | 12722.83 | Unknown | 2094.49 | 16417.29 | -14322.8 | Yes | N/A | N/A | 2024-09-19 | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-23 | 12 | 8 | 2024-09-23 | 2024-09-27 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-28 | 21 | 15 | 2024-10-28 | 2024-11-06 | 10 | 8 | 6 | 6 | 43 | 31 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -254 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-12 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 875.52 | -16.8 | Unknown | Unknown | Unknown | 892.32 | Unknown | 1696.99 | 875.52 | 821.47 | Yes | N/A | N/A | 2024-11-19 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-12-12 | 35 | 25 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-02-10 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-02-20 | 1 | 1 | 61 | 43 | 47 | 35 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 228.3 | 228.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3721.25 | Unknown | Unknown | Unknown | Unknown | 3721.25 | 23866 | 2133.87 | 3721.25 | -1587.38 | Yes | N/A | N/A | 2024-10-24 | 2024-11-06 | 14 | 10 | 2024-11-06 | 2024-12-18 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 14 | 10 | 44 | 32 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 215.05 | 215.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-28 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | 430.68 | -6.82 | Unknown | Unknown | 5.54 | 431.96 | 3981 | 861.33 | 430.68 | 430.65 | Yes | N/A | N/A | 2023-08-25 | 2024-01-11 | 140 | 100 | 2024-01-11 | 2024-01-25 | 15 | 11 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-03-29 | 65 | 47 | Unknown | 2024-03-28 | Unknown | Unknown | 2024-03-29 | 2024-04-04 | 7 | 5 | 2024-04-04 | 2024-04-04 | 1 | 1 | 205 | 147 | 23 | 17 | 228 | 164 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2.35 | 2.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -8 | -7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 196111.09 | 14607.23 | Unknown | 70.05 | -24218.57 | 205652.38 | Unknown | 99940.74 | 196111.09 | -96170.35 | Yes | N/A | N/A | 2024-06-27 | 2024-08-26 | 61 | 43 | 2024-08-26 | 2024-11-13 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-11-25 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-03-24 | 77 | 55 | 2025-03-24 | 2025-03-24 | 1 | 1 | 61 | 43 | 185 | 133 | 246 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 164.05 | 164.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-25 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 17.18 | -15.28 | Unknown | Unknown | Unknown | 32.46 | 3981 | 927.51 | 17.18 | 910.33 | Yes | N/A | N/A | 2024-01-05 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-01-05 | 99 | 71 | 2024-01-05 | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-24 | 8 | 6 | 2024-01-25 | 2024-06-28 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-02 | 5 | 3 | 2024-07-02 | 2024-07-02 | 1 | 1 | 156 | 112 | 113 | 81 | 269 | 193 | Steps 2,3,5,6,7 | 151 | 107 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | BOULEVARD | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-28 | 403 | 288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 1922.52 | 979.6 | Unknown | 80.32 | Unknown | 862.6 | 3981 | 552.98 | 1922.52 | -1369.54 | Yes | N/A | N/A | 2024-02-06 | 2023-02-02 | Unknown | Unknown | 2023-02-02 | 2024-02-06 | 370 | 264 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-05-14 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-17 | 4 | 4 | 2024-05-17 | 2024-06-04 | 19 | 13 | 99 | 71 | 393 | 281 | 492 | 352 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1425 | 1425 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-06-01 | -445 | -318 | No | 2023-04-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-16 | 2023-06-02 | 2024-03-01 | IOU Designed & Installed | N/A | Yes | 180 | 696.2 | -5.12 | Unknown | Unknown | 17.73 | 683.59 | 3981 | 699.52 | 696.2 | 3.32 | Yes | N/A | N/A | 2023-04-16 | 2023-10-13 | 181 | 130 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2024-03-01 | 274 | 196 | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-03-14 | 14 | 10 | 2024-03-14 | 2024-03-13 | Unknown | Unknown | 455 | 326 | 15 | 11 | 470 | 337 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | -5.27 | -4.27 | Unknown | Unknown | Unknown | -1 | Unknown | 163.83 | -5.27 | 169.1 | Yes | N/A | N/A | 2024-04-10 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-04-12 | 9 | 7 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-04-23 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-29 | 7 | 5 | 2024-04-29 | 2024-04-26 | Unknown | Unknown | 12 | 8 | 16 | 12 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Ysidro | IMPERIAL BEACH | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | 1378 | 985 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 7434.26 | 273.47 | Unknown | Unknown | -1775.56 | 8936.35 | 0 | 1418.1 | 7434.26 | -6016.16 | Yes | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | 2024-05-14 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-21 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-06 | 2024-12-26 | 51 | 37 | 2024-12-26 | 2024-12-26 | 1 | 1 | 1 | 1 | 341 | 245 | 342 | 246 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -430 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | -438.48 | Unknown | Unknown | Unknown | -505 | 66.52 | 3941 | 1271.17 | -438.48 | 1709.65 | Yes | N/A | N/A | 2024-02-22 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-02-22 | 66 | 48 | 2024-02-22 | 2024-03-18 | 26 | 18 | 2024-02-22 | 2024-03-18 | 26 | 18 | 2024-02-23 | 2024-07-23 | 152 | 108 | Unknown | 2024-06-21 | Unknown | Unknown | 2024-07-23 | 2024-07-29 | 7 | 5 | 2024-07-29 | 2024-07-29 | 1 | 1 | 178 | 126 | 100 | 72 | 278 | 198 | Steps 2,3,5,6,7 | 49 | 33 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | -707 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 766.81 | -14.7 | Unknown | Unknown | Unknown | 781.51 | 3981 | 1462.82 | 766.81 | 696.01 | Yes | N/A | N/A | 2024-10-17 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-17 | 4 | 4 | 2024-10-17 | 2025-03-03 | 138 | 98 | 2024-10-25 | 2024-11-06 | 13 | 9 | 2024-10-17 | 2024-10-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-01 | 16 | 12 | 2024-11-01 | 2024-11-01 | 1 | 1 | 139 | 99 | 34 | 26 | 173 | 125 | Steps 2,3,5,6,7 | 149 | 105 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -648 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 1600.1 | 340.22 | Unknown | 55.15 | Unknown | 1204.73 | Unknown | 1020.02 | 1600.1 | -580.08 | Yes | N/A | N/A | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-27 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-04 | 7 | 5 | 2024-03-04 | 2024-03-04 | 1 | 1 | 34 | 24 | 9 | 7 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | 197 | 142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | 691.25 | -25.23 | Unknown | Unknown | 85.33 | 631.15 | 3981 | 791.38 | 691.25 | 100.13 | Yes | N/A | N/A | 2023-08-15 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-08-15 | 106 | 76 | 2023-08-15 | Unknown | Unknown | Unknown | 2023-08-16 | 2023-08-21 | 6 | 4 | 2023-08-15 | 2023-08-23 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2024-11-15 | 451 | 323 | 2024-11-15 | 2024-11-15 | 1 | 1 | 9 | 7 | 564 | 404 | 573 | 411 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 176 | 176 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2326.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2025-01-28 | 58 | 42 | 2025-01-28 | 2025-02-21 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-18 | 66 | 48 | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-18 | 2025-04-21 | 4 | 2 | 2025-04-21 | 2025-04-22 | 2 | 2 | 91 | 67 | 64 | 46 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SAN DIEGO PA1 PH2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 445 | 320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-05-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 124097.95 | 23550.91 | Unknown | Unknown | 15892.12 | 84654.92 | 0 | 41672.62 | 124097.95 | -82425.33 | Yes | N/A | N/A | 2022-04-27 | 2023-03-14 | 322 | 230 | 2023-03-14 | 2023-08-24 | 164 | 118 | 2023-04-12 | 2024-04-08 | 59 | 43 | 2023-08-23 | 2023-09-11 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-28 | 2024-06-07 | 11 | 9 | 2024-06-07 | 2024-06-07 | 1 | 1 | 381 | 273 | 196 | 142 | 577 | 415 | Steps 2,3,5,6,7 | 363 | 259 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -550 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-30 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | -6.52 | -5.29 | Unknown | Unknown | Unknown | -1.23 | 3981 | 621.5 | -6.52 | 628.02 | Yes | N/A | N/A | 2023-11-14 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-11-30 | 78 | 56 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-01-29 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-26 | 29 | 21 | 2024-02-26 | 2024-02-26 | 1 | 1 | 61 | 43 | 108 | 78 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -374 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 25110.11 | 8024.12 | Unknown | 808.78 | 19.48 | 16257.73 | 3981 | 998.43 | 25110.11 | -24111.68 | Yes | N/A | N/A | 2023-03-29 | 2023-05-31 | 64 | 46 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2024-01-04 | 219 | 157 | Unknown | 2023-12-07 | Unknown | Unknown | 2024-01-04 | 2024-01-24 | 21 | 15 | 2024-01-24 | 2024-01-24 | 1 | 1 | 283 | 203 | 22 | 16 | 305 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -302 | -217 | No | 2024-06-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-09 | Unknown | IOU Designed & Installed | N/A | Yes | 38 | 422.78 | -8.31 | Unknown | Unknown | 7.46 | 423.63 | 3981 | 117.01 | 422.78 | -305.77 | Yes | N/A | N/A | 2024-06-11 | 2024-07-19 | 39 | 29 | 2024-07-19 | 2024-07-09 | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-21 | Unknown | Unknown | 39 | 29 | 0 | 0 | 39 | 29 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-25 | -286 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 922.48 | Unknown | Unknown | Unknown | Unknown | 922.48 | 3981 | 1169.83 | 922.48 | 247.35 | Yes | N/A | N/A | 2024-12-18 | 2025-01-21 | 35 | 25 | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 35 | 25 | 2 | 2 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | PALA | N/A | 163.05 | 163.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -499 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-19 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 4663.86 | 1588 | Unknown | 170.01 | 1.18 | 2904.67 | 3981 | 866.84 | 4663.86 | -3797.02 | Yes | N/A | N/A | 2023-06-13 | 2023-07-19 | 37 | 27 | 2023-07-19 | 2023-07-24 | 6 | 4 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-10-20 | 124 | 90 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-11-02 | 14 | 10 | 2023-11-02 | 2023-11-02 | 1 | 1 | 161 | 117 | 21 | 15 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | SANTEE | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-16 | 677 | 484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 13274.28 | -84.68 | Unknown | Unknown | Unknown | 13358.96 | 21084 | 8192.85 | 13274.28 | -5081.43 | Yes | N/A | N/A | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | 2024-01-16 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-01-22 | 12 | 8 | 2024-01-16 | 2024-01-31 | 16 | 12 | Unknown | 2024-03-05 | Unknown | Unknown | 2024-03-11 | 2024-05-07 | 58 | 42 | 2024-05-07 | 2024-04-23 | Unknown | Unknown | 17 | 13 | 76 | 54 | 93 | 67 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | -367 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | 2023-10-29 | IOU Designed & Installed | N/A | No | N/A | 1428.58 | 691.79 | Unknown | 289 | -814 | 1261.79 | Unknown | 813.99 | 1428.58 | -614.59 | Yes | N/A | N/A | 2023-02-16 | 2023-02-16 | 1 | 1 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-29 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-10-29 | 2023-11-01 | 4 | 3 | 2023-11-01 | 2023-11-01 | 1 | 1 | 34 | 24 | 5 | 4 | 39 | 28 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 24.11 | -30.43 | Unknown | Unknown | Unknown | 54.54 | 3981 | 908.66 | 24.11 | 884.55 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-05 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-30 | 26 | 18 | 2024-01-30 | 2024-01-30 | 1 | 1 | 20 | 16 | 28 | 20 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | 142 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -493.74 | 1963.94 | Unknown | 147.85 | -3588 | 982.47 | Unknown | 3587.78 | -493.74 | 4081.52 | Yes | N/A | N/A | 2024-01-26 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1336.49 | -13.39 | Unknown | Unknown | -2046 | 722.9 | Unknown | 2045.8 | -1336.49 | 3382.29 | Yes | N/A | N/A | 2024-06-04 | 2024-06-12 | 9 | 7 | 2024-06-12 | 2024-06-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-07-23 | 1 | 1 | 9 | 7 | 14 | 10 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | -274 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 1680.48 | -24.64 | Unknown | Unknown | Unknown | 1705.12 | 3941 | 969.46 | 1680.48 | -711.02 | Yes | N/A | N/A | 2024-05-14 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-14 | 49 | 35 | 2024-05-14 | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-18 | 14 | 8 | 2024-05-14 | 2024-05-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-17 | 35 | 25 | 2024-06-17 | 2024-06-17 | 1 | 1 | 1 | 1 | 99 | 69 | 100 | 70 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 92.05 | 92.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1193.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-16 | 1 | 1 | 2025-05-16 | 2025-05-16 | 1 | 1 | 2025-05-16 | 2025-06-03 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-09 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-25 | 17 | 13 | 2025-06-25 | 2025-06-25 | 1 | 1 | 27 | 19 | 19 | 15 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -50 | -36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1136.79 | 301.5 | Unknown | 11.01 | 28.61 | 795.67 | 3981 | 811.08 | 1136.79 | -325.71 | Yes | N/A | N/A | 2024-03-14 | 2024-04-16 | 34 | 24 | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1 | 1 | 34 | 24 | 2 | 2 | 36 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 99.25 | 99.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-04 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 84.49 | -10.73 | Unknown | Unknown | Unknown | 95.22 | Unknown | 1155.45 | 84.49 | 1070.96 | Yes | N/A | N/A | 2024-04-02 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-16 | 12 | 8 | 2024-04-16 | 2024-04-15 | Unknown | Unknown | 0 | 0 | 12 | 8 | 12 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FB 1028-D4 | COUNTY OF SAN DIEGO-NORTH of 56 | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | 89 | 64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 2311.78 | 535.43 | Unknown | Unknown | -8185 | 9961.35 | 3059.98 | 11245.35 | 2311.78 | 8933.57 | Yes | N/A | N/A | 2024-08-13 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-12-04 | 115 | 83 | 2024-10-02 | 2024-10-16 | 15 | 11 | 2024-10-10 | 2024-12-30 | 33 | 23 | 2024-12-04 | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-04 | 48 | 34 | 2025-02-11 | 2025-03-03 | 21 | 15 | 2025-03-03 | 2025-03-03 | 1 | 1 | 15 | 11 | 218 | 156 | 233 | 167 | Steps 2,3,5,6,7 | 95 | 67 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | -17.08 | -14.31 | Unknown | Unknown | Unknown | -2.77 | Unknown | 149.82 | -17.08 | 166.9 | Yes | N/A | N/A | 2023-08-15 | 2023-09-30 | 47 | 34 | 2023-09-30 | 2023-09-30 | 1 | 0 | 2023-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-30 | 2023-10-10 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-12-04 | 56 | 40 | 2023-12-04 | 2023-12-04 | 1 | 1 | 58 | 41 | 58 | 41 | 116 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -479 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 5454.64 | 1182.68 | Unknown | 1109.12 | 30.77 | 3132.07 | 3981 | 1858.13 | 5454.64 | -3596.51 | Yes | N/A | N/A | 2023-05-24 | 2023-06-22 | 30 | 22 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-10-24 | 124 | 88 | Unknown | 2023-10-20 | Unknown | Unknown | 2023-10-24 | 2023-11-15 | 23 | 17 | 2023-11-15 | 2023-11-15 | 1 | 1 | 154 | 110 | 24 | 18 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 138544 | 138544 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-06-02 | -256 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 369.05 | -15.29 | Unknown | Unknown | -401 | 785.34 | 0 | 243.17 | 369.05 | -125.88 | Yes | N/A | N/A | 2023-04-27 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-05-16 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-05-12 | 9 | 7 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-09-19 | 1 | 1 | 0 | 0 | 65 | 47 | 65 | 47 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 479 | 479 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-19 | 252 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-24 | 2023-08-04 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 0.57 | -8.37 | Unknown | Unknown | Unknown | 8.94 | 3981 | 562.74 | 0.57 | 562.17 | Yes | N/A | N/A | 2022-06-24 | 2023-08-04 | 407 | 291 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-12-11 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-28 | 18 | 14 | 2023-12-28 | 2023-12-27 | Unknown | Unknown | 537 | 383 | 19 | 15 | 556 | 398 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-05 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1776.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-03-05 | 30 | 22 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-04-14 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-02 | 19 | 15 | 2025-05-02 | 2025-05-02 | 1 | 1 | 41 | 29 | 50 | 38 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | 22 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 79.49 | Unknown | Unknown | Unknown | Unknown | 79.49 | Unknown | 4868.56 | 79.49 | 4789.07 | Yes | N/A | N/A | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-06-04 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-23 | 16 | 12 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 1 | 1 | 54 | 40 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-31 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 9.55 | Unknown | Unknown | Unknown | Unknown | 9.55 | 3981 | 985.1 | 9.55 | 975.55 | Yes | N/A | N/A | 2024-07-24 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-07-31 | 41 | 29 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-09-16 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-02 | 17 | 13 | 2024-10-02 | 2024-10-02 | 1 | 1 | 48 | 34 | 59 | 43 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-31 | 79 | 58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-12-03 | 2024-12-15 | IOU Designed & Installed | N/A | No | N/A | -2025.1 | 454.68 | Unknown | 84.3 | -2882 | 317.92 | Unknown | 2881.69 | -2025.1 | 4906.79 | Yes | N/A | N/A | 2024-11-18 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2025-01-17 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-15 | 2025-03-20 | 96 | 69 | 2025-03-20 | 2025-03-20 | 1 | 1 | 0 | 0 | 161 | 116 | 161 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-05-03 | 1286 | 920 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-05 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | -1429.24 | 2506.01 | Unknown | 547.67 | -5601 | 1118.08 | Unknown | 5600.84 | -1429.24 | 7030.08 | Yes | N/A | N/A | 2023-10-02 | 2023-10-09 | 8 | 6 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-10 | 5 | 5 | 2023-11-10 | 2023-11-10 | 1 | 1 | 8 | 6 | 6 | 6 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 141.05 | 141.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-14 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 437.99 | Unknown | Unknown | Unknown | 5.18 | 432.81 | 3981 | 1077.26 | 437.99 | 639.27 | Yes | N/A | N/A | 2024-11-12 | 2024-11-11 | Unknown | Unknown | 2024-11-11 | 2024-11-22 | 12 | 10 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-02 | 11 | 7 | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-02 | 2025-01-29 | 59 | 43 | 2025-01-29 | 2025-01-29 | 1 | 1 | 11 | 7 | 72 | 54 | 83 | 61 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 756.23 | 408.26 | Unknown | 82.76 | Unknown | 265.21 | Unknown | 149.82 | 756.23 | -606.41 | Yes | N/A | N/A | 2023-08-15 | 2023-09-30 | 47 | 34 | 2023-09-30 | 2023-09-30 | 1 | 0 | 2023-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-30 | 2023-11-16 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-11-21 | 6 | 4 | 2023-11-21 | 2023-11-21 | 1 | 1 | 95 | 68 | 8 | 5 | 103 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2024-01-12 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 87.39 | -7.89 | Unknown | Unknown | Unknown | 95.28 | Unknown | 947.62 | 87.39 | 860.23 | Yes | N/A | N/A | 2023-12-28 | 2024-01-12 | 16 | 12 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-22 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-12 | 22 | 16 | 2024-02-12 | 2024-02-12 | 1 | 1 | 27 | 19 | 24 | 18 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -428 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 1857.14 | Unknown | Unknown | Unknown | 132.18 | 1724.96 | 3981 | 1241.99 | 1857.14 | -615.15 | Yes | N/A | N/A | 2024-07-23 | 2024-08-08 | 17 | 13 | 2024-08-08 | 2024-08-22 | 15 | 11 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-02-19 | 182 | 130 | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-19 | 2025-03-10 | 20 | 14 | 2025-03-10 | 2025-02-28 | Unknown | Unknown | 199 | 143 | 35 | 25 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | -376 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-09 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 3388.08 | Unknown | Unknown | Unknown | Unknown | 3388.08 | Unknown | 414.27 | 3388.08 | -2973.81 | Yes | N/A | N/A | 2024-01-05 | 2024-01-09 | 5 | 3 | 2024-01-09 | 2024-01-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-02-16 | 32 | 24 | 2024-02-16 | 2024-02-16 | 1 | 1 | 5 | 3 | 41 | 31 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 891.47 | Unknown | Unknown | Unknown | 5.57 | 885.9 | 3981 | 1216.19 | 891.47 | 324.72 | Yes | N/A | N/A | 2025-03-12 | 2025-03-31 | 20 | 14 | 2025-03-31 | 2025-04-02 | 3 | 3 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-13 | 1 | 1 | 20 | 14 | 4 | 4 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-18 | 483 | 346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.09 | -10.72 | Unknown | Unknown | Unknown | 22.81 | Unknown | 332.58 | 12.09 | 320.49 | Yes | N/A | N/A | 2023-07-31 | 2024-01-08 | 162 | 116 | 2024-01-08 | 2024-02-27 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-15 | 14 | 10 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 162 | 116 | 66 | 48 | 228 | 164 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | 60 | 43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 715.67 | -0.94 | Unknown | Unknown | Unknown | 716.61 | 7962 | 1456.28 | 715.67 | 740.61 | Yes | N/A | N/A | 2024-04-25 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2025-04-24 | 386 | 276 | 2024-06-26 | 2024-07-08 | 13 | 9 | 2024-05-01 | 2025-05-08 | 86 | 64 | 2025-04-24 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 13 | 9 | 472 | 340 | 485 | 349 | Steps 2,3,5,6,7 | 384 | 274 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 20.03 | Unknown | Unknown | Unknown | Unknown | 20.03 | 3981 | 1580.4 | 20.03 | 1560.37 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-19 | 9 | 7 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-06 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-20 | 15 | 11 | 2024-12-20 | 2025-01-15 | 27 | 19 | 19 | 15 | 51 | 37 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 1587.98 | 582.92 | Unknown | 224.69 | Unknown | 780.37 | 3981 | 1063.98 | 1587.98 | -524 | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-13 | 37 | 27 | Unknown | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-03-21 | 9 | 7 | 2024-03-21 | 2024-03-21 | 1 | 1 | 38 | 28 | 11 | 9 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -438 | -315 | No | 2023-08-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | 2023-10-23 | IOU Designed & Installed | N/A | Yes | 53 | 399.46 | 244.9 | Unknown | Unknown | Unknown | 154.56 | Unknown | 480.37 | 399.46 | 80.91 | Yes | N/A | N/A | 2023-08-17 | 2023-10-09 | 54 | 38 | 2023-10-09 | 2023-08-17 | Unknown | Unknown | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-10-23 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-10-30 | 8 | 6 | 2023-10-30 | 2023-10-30 | 1 | 1 | 122 | 86 | 9 | 7 | 131 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-14 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 41.79 | Unknown | Unknown | Unknown | 2.93 | 38.86 | 3981 | 1748.88 | 41.79 | 1707.09 | Yes | N/A | N/A | 2024-08-29 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-08-30 | 33 | 25 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-08-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2025-02-24 | 179 | 127 | 2025-02-24 | 2025-02-24 | 1 | 1 | 1 | 1 | 213 | 153 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 460 | 329 | No | 2021-09-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-02 | 2021-09-03 | Unknown | IOU Designed & Installed | N/A | Yes | 939 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3885 | 625.65 | Unknown | Unknown | Yes | N/A | N/A | 2021-09-02 | 2024-03-20 | 931 | 665 | 2024-03-20 | 2024-03-29 | 10 | 8 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-04 | Unknown | Unknown | 931 | 665 | 10 | 8 | 941 | 673 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -465 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-05-22 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 1126.78 | 345.78 | Unknown | Unknown | Unknown | 781 | 3981 | 1774.18 | 1126.78 | 647.4 | Yes | N/A | N/A | 2023-01-23 | 2023-05-22 | 120 | 86 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-07-17 | 57 | 41 | Unknown | 2023-06-23 | Unknown | Unknown | 2023-07-17 | 2023-07-25 | 9 | 7 | 2023-07-25 | 2023-07-25 | 1 | 1 | 177 | 127 | 10 | 8 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | 53 | 38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 256.68 | -24.62 | Unknown | Unknown | Unknown | 281.3 | 0 | 1938.55 | 256.68 | 1681.87 | Yes | N/A | N/A | 2023-04-27 | 2023-04-17 | Unknown | Unknown | 2023-04-17 | 2023-06-16 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-06 | 1 | 1 | 0 | 0 | 62 | 46 | 62 | 46 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -115 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 12.17 | -10.78 | Unknown | Unknown | Unknown | 22.95 | 3981 | 777.92 | 12.17 | 765.75 | Yes | N/A | N/A | 2023-11-02 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-11-02 | 45 | 33 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2024-04-23 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-08 | 16 | 12 | 2024-05-08 | 2024-05-08 | 1 | 1 | 174 | 124 | 62 | 46 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | -272 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-05-15 | IOU Designed & Installed | N/A | No | N/A | 559.82 | 185.51 | Unknown | 93.66 | Unknown | 280.65 | 3981 | 666.56 | 559.82 | 106.74 | Yes | N/A | N/A | 2023-03-28 | 2023-04-07 | 11 | 9 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-05-15 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-05-18 | 4 | 4 | 2023-05-18 | 2023-05-18 | 1 | 1 | 50 | 36 | 5 | 5 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -447 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-05 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 620.82 | -15.55 | Unknown | Unknown | Unknown | 636.37 | Unknown | 1205.31 | 620.82 | 584.49 | Yes | N/A | N/A | 2024-03-20 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-04-05 | 123 | 89 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-07-12 | 87 | 63 | 2024-07-12 | 2024-07-12 | 1 | 1 | 13 | 9 | 211 | 153 | 224 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | 37 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-09-08 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | 20424.84 | -202.1 | Unknown | Unknown | Unknown | 20626.94 | Unknown | 9898.75 | 20424.84 | -10526.09 | Yes | N/A | N/A | 2023-08-28 | 2023-10-30 | 64 | 46 | 2023-10-30 | 2023-11-22 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-18 | 37 | 27 | 2024-01-18 | 2024-01-18 | 1 | 1 | 64 | 46 | 62 | 46 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -260 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1488.41 | 369.91 | Unknown | Unknown | Unknown | 1118.5 | 3981 | 1241.57 | 1488.41 | -246.84 | Yes | N/A | N/A | 2024-02-28 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-02-28 | 51 | 37 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-10-29 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-07 | 10 | 8 | 2024-11-07 | 2025-04-11 | 156 | 112 | 245 | 175 | 217 | 157 | 462 | 332 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 859 | 859 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -255 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-08-24 | 2024-01-17 | IOU Designed & Installed | N/A | No | N/A | -43.35 | -34.19 | Unknown | Unknown | Unknown | -9.16 | 3981 | 799.72 | -43.35 | 843.07 | Yes | N/A | N/A | 2023-07-19 | 2023-08-24 | 37 | 27 | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2024-01-17 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-29 | 13 | 9 | 2024-01-29 | 2024-01-29 | 1 | 1 | 184 | 132 | 15 | 11 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 345 | 248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 2875 | 565.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-02-06 | 9 | 7 | 2025-02-06 | 2025-02-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-25 | 7 | 5 | 2025-02-27 | 2025-05-27 | 90 | 64 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-06-06 | 2025-06-11 | 6 | 4 | 2025-06-11 | 2025-06-11 | 1 | 1 | 99 | 71 | 36 | 26 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 721 | 516 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 8773.5 | 272.1 | Unknown | Unknown | -468 | 8969.4 | 3981 | 896.53 | 8773.5 | -7876.97 | Yes | N/A | N/A | 2023-07-05 | 2023-07-05 | 1 | 1 | 2023-07-05 | 2023-07-05 | 1 | 1 | 2023-07-05 | 2024-08-21 | 414 | 296 | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2024-08-29 | 422 | 302 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-29 | 2024-10-11 | 44 | 32 | 2024-10-11 | 2025-02-18 | 131 | 93 | 837 | 599 | 176 | 126 | 1013 | 725 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | -78 | -57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2024-02-15 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | -10.36 | -8.41 | Unknown | Unknown | Unknown | -1.95 | 3981 | 700.71 | -10.36 | 711.07 | Yes | N/A | N/A | 2023-11-09 | 2024-02-15 | 99 | 71 | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-03-12 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-21 | 10 | 8 | 2024-03-21 | 2024-03-21 | 1 | 1 | 126 | 90 | 12 | 10 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | 413 | 296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 910.07 | -25.08 | Unknown | Unknown | Unknown | 935.15 | 3981 | 363.4 | 910.07 | -546.67 | Yes | N/A | N/A | 2023-05-04 | 2023-05-08 | 5 | 3 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 49.3 | 49.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-09 | -313 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-28 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 2137.14 | 303.12 | Unknown | 116.99 | 23.02 | 1694.01 | 3981 | 1053.98 | 2137.14 | -1083.16 | Yes | N/A | N/A | 2024-06-19 | 2024-06-28 | 10 | 8 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2025-01-08 | 195 | 139 | Unknown | 2024-11-12 | Unknown | Unknown | 2025-01-08 | 2025-01-30 | 23 | 17 | 2025-01-30 | 2025-01-30 | 1 | 1 | 205 | 147 | 25 | 19 | 230 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-24 | -9 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2658.92 | 3333.83 | Unknown | 992.5 | -3328 | 1660.59 | Unknown | 3327.5 | 2658.92 | 668.58 | Yes | N/A | N/A | 2023-11-28 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | -281 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4542.16 | 1073.13 | Unknown | 317.52 | 29.59 | 3121.92 | 3981 | 825.8 | 4542.16 | -3716.36 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | 2024-02-22 | 25 | 19 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-03-27 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 450 | 321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 360.62 | -12.05 | Unknown | Unknown | Unknown | 372.67 | Unknown | 2018.67 | 360.62 | 1658.05 | Yes | N/A | N/A | 2024-01-09 | 2024-01-23 | 15 | 11 | 2024-01-23 | 2024-02-15 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-08 | 16 | 12 | 2024-02-15 | 2024-03-14 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-03-25 | Unknown | Unknown | 44 | 32 | 40 | 30 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | 395 | 395 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 490 | 350 | No | 2024-04-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2025-01-30 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 1 | 76965.41 | 47890.74 | Unknown | 7112.64 | -86274.9 | 108236.93 | Unknown | 93165.5 | 76965.41 | 16200.09 | Yes | N/A | N/A | 2024-04-03 | 2024-07-26 | 115 | 83 | 2024-07-26 | 2024-11-13 | 111 | 79 | 2024-08-09 | 2024-12-02 | 56 | 40 | 2024-09-20 | 2025-01-08 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-02 | 4 | 2 | 2025-02-02 | 2025-02-02 | 1 | 0 | 171 | 123 | 184 | 131 | 355 | 254 | Steps 2,3,5,6,7 | 169 | 119 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-23 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 1209.63 | -4.97 | Unknown | Unknown | 23.41 | 1191.19 | 3981 | 766.83 | 1209.63 | -442.8 | Yes | N/A | N/A | 2024-04-03 | 2024-04-25 | 23 | 17 | 2024-04-25 | 2024-05-17 | 23 | 17 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-17 | 32 | 22 | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-17 | 2024-07-01 | 15 | 11 | 2024-07-01 | 2024-06-28 | Unknown | Unknown | 55 | 39 | 38 | 28 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-15 | 442 | 317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 19.78 | -17.58 | Unknown | Unknown | Unknown | 37.36 | 3981 | 814.29 | 19.78 | 794.51 | Yes | N/A | N/A | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-05-30 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 3751.16 | Unknown | Unknown | Unknown | Unknown | 3751.16 | 3981 | 1391.74 | 3751.16 | -2359.42 | Yes | N/A | N/A | 2023-02-28 | 2023-06-30 | 123 | 89 | 2023-06-30 | 2023-11-17 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-08-24 | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-06 | 2024-06-14 | 9 | 7 | 2024-06-14 | 2024-06-12 | Unknown | Unknown | 123 | 89 | 150 | 108 | 273 | 197 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-13 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-25 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 35.14 | Unknown | Unknown | Unknown | Unknown | 35.14 | 3981 | 1655.9 | 35.14 | 1620.76 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-01-08 | 30 | 22 | 2025-01-08 | 2025-01-08 | 1 | 1 | 17 | 13 | 32 | 24 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-20 | 169 | 122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.75 | -7.8 | Unknown | Unknown | Unknown | 16.55 | 3981 | 617.8 | 8.75 | 609.05 | Yes | N/A | N/A | 2023-06-20 | 2023-07-10 | 21 | 15 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-07 | Unknown | Unknown | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 39.68 | Unknown | Unknown | Unknown | Unknown | 39.68 | 3981 | 1558.07 | 39.68 | 1518.39 | Yes | N/A | N/A | 2024-08-21 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-21 | 3 | 3 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-09-10 | 1 | 1 | 0 | 0 | 4 | 4 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 202 | 145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.26 | Unknown | Unknown | Unknown | Unknown | 14.26 | 3981 | 443.57 | 14.26 | 429.31 | Yes | N/A | N/A | 2024-02-22 | 2024-02-23 | 2 | 2 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-19 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-28 | 263 | 188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 7593.04 | Unknown | Unknown | Unknown | -252.22 | 7845.26 | 4252 | 3595.78 | 7593.04 | -3997.26 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | 2023-06-13 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-07-05 | 42 | 30 | 2023-06-13 | 2023-10-10 | 120 | 86 | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-12 | 2023-10-20 | 9 | 7 | 2023-10-20 | 2023-10-18 | Unknown | Unknown | 121 | 87 | 73 | 53 | 194 | 140 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -440 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-25 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 74.68 | -1.5 | Unknown | Unknown | Unknown | 76.18 | 3981 | 1038.53 | 74.68 | 963.85 | Yes | N/A | N/A | 2025-04-24 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-25 | 10 | 8 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-06 | 5 | 3 | 2025-05-06 | 2025-04-05 | Unknown | Unknown | 8 | 6 | 15 | 11 | 23 | 17 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-11 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 390.08 | 122.27 | Unknown | 8.02 | 9.98 | 249.81 | 3885 | 797.71 | 390.08 | 407.63 | Yes | N/A | N/A | 2023-10-09 | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-10-25 | 34 | 24 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 35 | 25 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Laguna Beach | N/A | 327 | 327 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-17 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 1211.08 | 301.56 | Unknown | Unknown | 3.25 | 906.27 | 2827.02 | 7347.57 | 1211.08 | 6136.49 | Yes | N/A | N/A | 2023-03-07 | 2023-03-07 | 1 | 1 | 2023-03-07 | 2023-12-15 | 284 | 204 | 2023-05-18 | 2023-12-14 | 3 | 3 | 2023-12-15 | 2023-12-19 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | 2024-12-11 | 2025-01-02 | 23 | 17 | 2025-01-02 | 2025-01-02 | 1 | 1 | 4 | 4 | 313 | 225 | 317 | 229 | Steps 2,3,5,6,7 | 211 | 151 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-24 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 468.42 | -28.24 | Unknown | Unknown | 9.11 | 487.55 | 3981 | 1522.61 | 468.42 | 1054.19 | Yes | N/A | N/A | 2025-01-16 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-24 | 10 | 8 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-03-28 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-01 | 5 | 3 | 2025-04-01 | 2025-03-31 | Unknown | Unknown | 64 | 46 | 15 | 11 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Vista | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 581 | 416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-15 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 90118.88 | -571.66 | Unknown | Unknown | 2.47 | 90688.07 | Unknown | 27356.29 | 90118.88 | -62762.59 | Yes | N/A | N/A | 2024-08-06 | 2024-08-15 | 10 | 8 | 2024-08-15 | 2025-01-22 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-13 | 7 | 5 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-04 | 23 | 17 | 2025-03-04 | 2025-03-04 | 1 | 1 | 10 | 8 | 192 | 138 | 202 | 146 | Steps 2,3,5,6,7 | 22 | 16 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -212 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-29 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 31.5 | -24.5 | Unknown | Unknown | Unknown | 56 | Unknown | 1011.52 | 31.5 | 980.02 | Yes | N/A | N/A | 2024-03-21 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-05-15 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-07-10 | 57 | 41 | 2024-07-10 | 2024-07-10 | 1 | 1 | 48 | 34 | 59 | 43 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-12 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 673.8 | -21.77 | Unknown | Unknown | 2.64 | 692.93 | Unknown | 2149.51 | 673.8 | 1475.71 | Yes | N/A | N/A | 2024-11-19 | 2024-12-12 | 24 | 18 | 2024-12-12 | 2024-12-12 | 1 | 1 | 2024-12-12 | 2025-03-27 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-30 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-04-07 | 68 | 48 | 2025-04-07 | 2025-04-07 | 1 | 1 | 180 | 130 | 70 | 50 | 250 | 180 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | -217 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 309.59 | 1172.09 | Unknown | 97.71 | -1624 | 663.79 | Unknown | 1624.48 | 309.59 | 1314.89 | Yes | N/A | N/A | 2024-06-10 | 2024-07-01 | 22 | 16 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-21 | Unknown | Unknown | 2024-09-21 | 2024-09-21 | 1 | 0 | 22 | 16 | 1 | 0 | 23 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-28 | -806 | -577 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.56 | -3.3 | Unknown | Unknown | Unknown | -1.26 | Unknown | 351.99 | -4.56 | 356.55 | Yes | N/A | N/A | 2023-01-31 | 2023-02-02 | 3 | 3 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -333 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-10-20 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 4.86 | -4.33 | Unknown | Unknown | Unknown | 9.19 | 3981 | 833.95 | 4.86 | 829.09 | Yes | N/A | N/A | 2023-06-19 | 2023-10-09 | 113 | 81 | 2023-10-09 | 2023-10-20 | 12 | 10 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-04-29 | 193 | 137 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-07 | 9 | 7 | 2024-05-07 | 2024-05-06 | Unknown | Unknown | 306 | 218 | 21 | 17 | 327 | 235 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-18 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1794.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-18 | 19 | 15 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-07 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-29 | 23 | 17 | 2025-05-29 | 2025-05-29 | 1 | 1 | 39 | 29 | 25 | 19 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 786.69 | 251.99 | Unknown | Unknown | Unknown | 534.7 | Unknown | 1089.29 | 786.69 | 302.6 | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-03 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-07-25 | 53 | 39 | 2024-07-25 | 2024-07-25 | 1 | 1 | 41 | 29 | 55 | 41 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -802 | -575 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -14.34 | -10.38 | Unknown | Unknown | Unknown | -3.96 | Unknown | 363.72 | -14.34 | 378.06 | Yes | N/A | N/A | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | -702 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 51.25 | Unknown | Unknown | Unknown | Unknown | 51.25 | 3981 | 1496.59 | 51.25 | 1445.34 | Yes | N/A | N/A | 2024-11-27 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-11-27 | 2 | 2 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-11-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-20 | 24 | 18 | 2024-12-20 | 2024-12-20 | 1 | 1 | 1 | 1 | 27 | 21 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 2453.69 | -11.76 | Unknown | Unknown | Unknown | 2465.45 | Unknown | 571.43 | 2453.69 | -1882.26 | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-07 | 15 | 11 | 2024-12-30 | 2025-01-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-05-16 | 130 | 94 | 2025-05-16 | 2025-05-16 | 1 | 1 | 10 | 8 | 146 | 106 | 156 | 114 | Steps 2,3,5,6,7 | 39 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | es 1129-d4 | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 308 | 221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2024-10-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -5173.48 | 2192.21 | Unknown | Unknown | -24880 | 17514.31 | 0 | 25012.65 | -5173.48 | 30186.13 | Yes | N/A | N/A | 2023-03-16 | 2023-07-17 | 124 | 88 | 2023-07-17 | 2023-10-31 | 107 | 77 | 2023-07-31 | 2023-10-30 | 20 | 16 | 2023-07-31 | 2024-08-08 | 50 | 38 | 2023-10-31 | Unknown | Unknown | Unknown | 2023-12-01 | 2024-10-15 | 320 | 228 | 2024-10-18 | 2024-11-04 | 18 | 12 | 2024-11-04 | 2024-11-04 | 1 | 1 | 144 | 104 | 496 | 356 | 640 | 460 | Steps 2,3,5,6,7 | 465 | 333 | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | N/A | El Cajon | EL CAJON | 2272 | 2272 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-01 | 116 | 83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-09-26 | 2025-04-27 | IOU Designed & Installed | N/A | No | N/A | 9334.43 | 4840.07 | Unknown | 354.94 | -4772 | 8911.42 | 16783 | 32509.71 | 9334.43 | 23175.28 | Yes | N/A | N/A | 2024-06-07 | 2024-07-10 | 34 | 24 | 2024-07-10 | 2024-12-23 | 167 | 119 | 2024-10-10 | 2024-10-11 | 2 | 2 | 2024-12-10 | 2025-03-18 | 34 | 22 | 2024-12-23 | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-27 | 22 | 16 | 2025-04-27 | 2025-04-27 | 1 | 0 | 2025-04-27 | 2025-04-27 | 1 | 0 | 36 | 26 | 225 | 157 | 261 | 183 | Steps 2,3,5,6,7 | 159 | 113 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | -719 | -514 | No | 2021-02-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-25 | 2021-02-25 | Unknown | IOU Designed & Installed | N/A | Yes | 1337 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 598.84 | Unknown | Unknown | Yes | N/A | N/A | 2021-02-25 | 2024-10-24 | 1338 | 956 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-02-25 | Unknown | Unknown | Unknown | Unknown | 2021-02-27 | Unknown | Unknown | Unknown | 2021-03-12 | Unknown | Unknown | 2021-03-12 | 2021-03-12 | Unknown | Unknown | 1338 | 956 | 0 | 0 | 1338 | 956 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -200 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-14 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 123.32 | Unknown | Unknown | Unknown | -816 | 939.32 | Unknown | 1021.41 | 123.32 | 898.09 | Yes | N/A | N/A | 2024-08-13 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-08-14 | 15 | 11 | 2024-08-14 | 2024-08-19 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-10-02 | 43 | 31 | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-02 | 2024-10-15 | 14 | 10 | 2024-10-15 | 2024-10-15 | 1 | 1 | 49 | 35 | 30 | 22 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 612.05 | 612.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | 1011.04 | Unknown | Unknown | Unknown | 4.14 | 1006.9 | 3981 | 979.34 | 1011.04 | -31.7 | Yes | N/A | N/A | 2025-05-27 | 2025-06-11 | 16 | 12 | 2025-06-11 | 2025-06-16 | 6 | 4 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-26 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-03 | 8 | 6 | 2025-07-03 | 2025-06-30 | Unknown | Unknown | 27 | 21 | 14 | 10 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 148 | 106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-03 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 621.85 | -27.92 | Unknown | Unknown | 18.48 | 631.29 | 3981 | 783.68 | 621.85 | 161.83 | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-04-05 | 3 | 3 | 2023-04-03 | 2023-08-01 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2024-01-18 | 171 | 123 | 2024-01-18 | 2023-09-25 | Unknown | Unknown | 122 | 88 | 174 | 126 | 296 | 214 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -654 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-24 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 2132.21 | 479.02 | Unknown | Unknown | Unknown | 1653.19 | Unknown | 1637.59 | 2132.21 | -494.62 | Yes | N/A | N/A | 2024-10-08 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-24 | 23 | 17 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-18 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-11-20 | 3 | 3 | 2024-11-20 | 2024-11-20 | 1 | 1 | 26 | 18 | 27 | 21 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 227 | 227 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-02 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 1656.78 | Unknown | Unknown | Unknown | 74.46 | 1582.32 | 3981 | 1329.22 | 1656.78 | -327.56 | Yes | N/A | N/A | 2024-06-25 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-19 | 45 | 33 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-10-14 | 88 | 62 | Unknown | 2024-10-07 | Unknown | Unknown | 2024-10-14 | 2024-12-09 | 57 | 41 | 2024-12-09 | 2024-10-18 | Unknown | Unknown | 88 | 62 | 102 | 74 | 190 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1240.05 | 1240.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-04-18 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -614.11 | Unknown | Unknown | Unknown | -669 | 54.89 | 3961 | 1295.66 | -614.11 | 1909.77 | Yes | N/A | N/A | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | 2024-12-10 | 485 | 347 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 486 | 348 | 2 | 2 | 488 | 350 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 213.42 | Unknown | Unknown | Unknown | -1182 | 1395.42 | Unknown | 1181.83 | 213.42 | 968.41 | Yes | N/A | N/A | 2024-10-18 | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-11-14 | 52 | 38 | 2024-11-14 | 2025-02-18 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1 | 1 | 97 | 69 | 53 | 39 | 150 | 108 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 426.02 | 2459.84 | Unknown | 794 | -4036 | 1208.18 | Unknown | 4035.75 | 426.02 | 3609.73 | Yes | N/A | N/A | 2023-12-27 | 2023-12-28 | 2 | 2 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-17 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 2840.06 | 448.94 | Unknown | 170.7 | Unknown | 2220.42 | Unknown | 1116.78 | 2840.06 | -1723.28 | Yes | N/A | N/A | 2023-11-09 | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-11-17 | 134 | 96 | 2023-11-17 | Unknown | Unknown | Unknown | 2023-11-17 | 2024-01-10 | 55 | 39 | 2023-11-17 | 2024-01-23 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-30 | 8 | 6 | 2024-01-30 | 2024-01-30 | 1 | 1 | 68 | 48 | 198 | 142 | 266 | 190 | Steps 2,3,5,6,7 | 54 | 38 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -398 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 573.29 | Unknown | Unknown | Unknown | 32.59 | 540.7 | 3981 | 1360.94 | 573.29 | 787.65 | Yes | N/A | N/A | 2024-02-08 | 2024-03-04 | 26 | 18 | 2024-03-04 | 2024-03-08 | 5 | 5 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-08 | 1 | 1 | 26 | 18 | 6 | 6 | 32 | 24 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 138.78 | -1.26 | Unknown | Unknown | 0.31 | 139.73 | 3981 | 1734.28 | 138.78 | 1595.5 | Yes | N/A | N/A | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-02-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-03-05 | 31 | 23 | 2025-03-05 | 2025-03-05 | 1 | 1 | 37 | 27 | 33 | 25 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -513 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 1733.8 | -8.77 | Unknown | Unknown | 56.97 | 1685.6 | 1000 | 525.88 | 1733.8 | -1207.92 | Yes | N/A | N/A | 2023-02-24 | 2023-03-21 | 26 | 18 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-07-26 | 128 | 92 | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-26 | 2023-08-03 | 9 | 7 | 2023-08-03 | 2023-08-03 | 1 | 1 | 154 | 110 | 10 | 8 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -242 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -1008.38 | 1255.29 | Unknown | Unknown | -2933 | 669.33 | Unknown | 2933.46 | -1008.38 | 3941.84 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-12-29 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | 2023-12-29 | 2023-12-29 | 1 | 1 | 2023-12-04 | 2024-02-28 | 87 | 63 | 2024-02-28 | 2024-02-28 | 1 | 1 | 1 | 1 | 140 | 102 | 141 | 103 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 13.07 | -11.61 | Unknown | Unknown | Unknown | 24.68 | Unknown | 1372.06 | 13.07 | 1358.99 | Yes | N/A | N/A | 2024-05-22 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-22 | 77 | 55 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-05-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-20 | 24 | 18 | 2024-06-20 | 2024-06-20 | 1 | 1 | 7 | 5 | 102 | 74 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | Fallbrook | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | 262 | 188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-10-13 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 18118.92 | 2846.46 | Unknown | Unknown | 34.69 | 15237.77 | 21022.38 | 12986.58 | 18118.92 | -5132.34 | Yes | N/A | N/A | 2023-06-22 | 2023-10-13 | 114 | 82 | 2023-10-13 | 2024-03-08 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-12 | 8 | 6 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-12 | 20 | 14 | 2025-03-12 | 2025-03-12 | 1 | 1 | 114 | 82 | 177 | 127 | 291 | 209 | Steps 2,3,5,6,7 | 4 | 2 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -220 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1056.03 | Unknown | Unknown | Unknown | Unknown | 1056.03 | 3981 | 1359.39 | 1056.03 | 303.36 | Yes | N/A | N/A | 2024-01-22 | 2024-05-30 | 130 | 94 | 2024-05-30 | 2024-06-17 | 19 | 13 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-01-30 | 1 | 1 | 130 | 94 | 20 | 14 | 150 | 108 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-12 | 2024-03-09 | IOU Designed & Installed | N/A | No | N/A | 8939.41 | 2258.72 | Unknown | 1689.44 | Unknown | 4991.25 | Unknown | 1030.7 | 8939.41 | -7908.71 | Yes | N/A | N/A | 2024-01-12 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-01-12 | 3 | 3 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-03-09 | 58 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-03-09 | 2024-03-12 | 4 | 2 | 2024-03-12 | 2024-03-12 | 1 | 1 | 58 | 41 | 8 | 6 | 66 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | SAN YSIDRO | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | 280 | 200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 125.16 | -6.99 | Unknown | Unknown | 36.43 | 95.72 | 0 | 217.66 | 125.16 | 92.5 | Yes | N/A | N/A | 2023-07-07 | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-07-19 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-07-19 | 7 | 5 | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 0 | 0 | 84 | 59 | 84 | 59 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 354 | 253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2024-03-07 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 5829.26 | 273.47 | Unknown | Unknown | 47.64 | 5508.15 | 26864.73 | 3543.65 | 5829.26 | -2285.61 | Yes | N/A | N/A | 2023-09-13 | 2024-02-14 | 155 | 111 | 2024-02-14 | 2024-05-20 | 97 | 69 | 2024-05-17 | 2024-05-17 | 1 | 1 | 2024-05-20 | 2024-05-22 | 3 | 3 | 2024-11-14 | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-15 | 2 | 2 | 2024-12-23 | 2025-03-26 | 94 | 68 | 2025-03-26 | 2025-03-26 | 1 | 1 | 156 | 112 | 197 | 143 | 353 | 255 | Steps 2,3,5,6,7 | 3 | 1 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 82.1 | 82.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -379 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2025-02-21 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | -1224.66 | -9.67 | Unknown | Unknown | -1706 | 491.01 | Unknown | 1705.89 | -1224.66 | 2930.55 | Yes | N/A | N/A | 2024-08-14 | 2025-02-20 | 191 | 137 | 2025-02-20 | 2025-02-21 | 2 | 2 | 2025-02-21 | 2025-03-25 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-05-05 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-19 | 15 | 11 | 2025-05-19 | 2025-05-16 | Unknown | Unknown | 266 | 190 | 17 | 13 | 283 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 383.05 | 383.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-12-11 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 1929.86 | 592.04 | Unknown | 57.06 | Unknown | 1280.76 | 3981 | 1129.14 | 1929.86 | -800.72 | Yes | N/A | N/A | 2023-11-30 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-12-11 | 120 | 86 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-25 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-03-14 | 50 | 36 | 2024-03-14 | 2024-03-14 | 1 | 1 | 46 | 34 | 171 | 123 | 217 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1050.53 | -18.52 | Unknown | Unknown | 44.24 | 1024.81 | 19731 | 3583.86 | 1050.53 | 2533.33 | Yes | N/A | N/A | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | 2023-09-21 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-11-07 | 48 | 34 | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2023-11-29 | Unknown | Unknown | 49 | 35 | 32 | 24 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 1.86 | Unknown | Unknown | Unknown | Unknown | 1.86 | 3961 | 192.95 | 1.86 | 191.09 | Yes | N/A | N/A | 2024-08-21 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-09-16 | 39 | 27 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-23 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-21 | 30 | 22 | 2024-11-21 | 2024-11-21 | 1 | 1 | 38 | 28 | 70 | 50 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | 125.05 | 125.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-09-03 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 4800.78 | 1311.17 | Unknown | 183.12 | -1135 | 4441.49 | 3981 | 2527.62 | 4800.78 | -2273.16 | Yes | N/A | N/A | 2024-08-27 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-09-03 | 9 | 7 | 2024-09-03 | 2024-11-14 | 73 | 53 | 2025-02-11 | 2025-02-27 | 17 | 13 | 2024-12-03 | 2025-03-06 | 94 | 68 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | 2025-03-06 | 1 | 1 | 167 | 121 | 28 | 22 | 195 | 143 | Steps 2,3,5,6,7 | 86 | 62 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.61 | Unknown | Unknown | Unknown | Unknown | -0.61 | 25672.6 | 151.1 | -0.61 | 151.71 | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | 2024-05-30 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-12-04 | 1 | 1 | 1 | 1 | 45 | 33 | 46 | 34 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 368 | 368 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -325 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-26 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 6861.2 | 532.75 | Unknown | Unknown | -11825.58 | 18154.03 | 3981 | 15722.6 | 6861.2 | 8861.4 | Yes | N/A | N/A | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | 2024-06-18 | 92 | 66 | 2024-03-29 | 2024-05-16 | 6 | 4 | 2024-08-14 | 2024-08-15 | 2 | 2 | 2024-06-18 | 2024-07-31 | 44 | 32 | 2024-06-27 | 2024-07-30 | 34 | 24 | 2024-08-09 | 2024-09-24 | 47 | 33 | 2024-09-24 | 2024-09-10 | Unknown | Unknown | 51 | 37 | 175 | 125 | 226 | 162 | Steps 2,3,5,6,7 | 173 | 123 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-28 | -607 | -434 | No | 2023-04-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | Yes | 26 | -4.7 | -3.4 | Unknown | Unknown | Unknown | -1.3 | 3981 | 517.21 | -4.7 | 521.91 | Yes | N/A | N/A | 2023-03-23 | 2023-05-09 | 48 | 34 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-06-01 | 1 | 1 | 48 | 34 | 1 | 1 | 49 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 487 | 348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 744.92 | -12.83 | Unknown | Unknown | Unknown | 757.75 | 7962 | 1214.29 | 744.92 | 469.37 | Yes | N/A | N/A | 2024-01-18 | 2024-06-21 | 156 | 112 | 2024-06-21 | 2024-07-24 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-24 | 34 | 24 | 2024-07-24 | 2025-01-06 | 167 | 119 | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-03 | 1 | 1 | 323 | 231 | 69 | 49 | 392 | 280 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | 140 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3241 | 1923.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2025-06-25 | 394 | 282 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 395 | 283 | 3 | 3 | 398 | 286 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | -327 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 619.76 | -14.27 | Unknown | Unknown | Unknown | 634.03 | Unknown | 772.03 | 619.76 | 152.27 | Yes | N/A | N/A | 2023-06-30 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-06-30 | 2 | 2 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-24 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-08-07 | 15 | 11 | 2023-08-07 | 2023-08-07 | 1 | 1 | 25 | 17 | 18 | 14 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-31 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | -478.06 | -11.29 | Unknown | Unknown | -487 | 20.23 | 3981 | 1673.86 | -478.06 | 2151.92 | Yes | N/A | N/A | 2023-10-24 | 2023-10-31 | 8 | 6 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2023-11-28 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-01-11 | 43 | 31 | Unknown | 2024-01-09 | Unknown | Unknown | 2024-01-11 | 2024-01-17 | 7 | 5 | 2024-01-17 | 2024-01-17 | 1 | 1 | 66 | 48 | 9 | 7 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 226 | 226 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 712 | 510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-09-11 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 25751.94 | 799.13 | Unknown | Unknown | 242.57 | 24710.24 | 29157 | 26946.28 | 25751.94 | 1194.34 | Yes | N/A | N/A | 2023-05-31 | 2023-11-02 | 156 | 112 | 2023-11-02 | 2023-11-30 | 29 | 21 | 2023-06-16 | 2023-07-13 | 28 | 20 | 2023-11-22 | 2024-12-18 | 46 | 34 | 2023-11-30 | 2024-08-21 | 266 | 190 | 2023-12-29 | 2024-11-06 | 314 | 224 | 2024-11-22 | 2024-12-16 | 25 | 17 | 2024-12-16 | 2024-12-13 | Unknown | Unknown | 450 | 322 | 414 | 296 | 864 | 618 | Steps 2,3,5,6,7 | 787 | 561 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 343 | 343 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-01 | 668 | 479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.05 | -12.49 | Unknown | Unknown | Unknown | 26.54 | 11943 | 1372.28 | 14.05 | 1358.23 | Yes | N/A | N/A | 2023-09-27 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-10-23 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2024-05-20 | 211 | 151 | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-05-30 | Unknown | Unknown | 211 | 151 | 39 | 27 | 250 | 178 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 246 | 176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 369.06 | -20.38 | Unknown | Unknown | Unknown | 389.44 | 7962 | 977.96 | 369.06 | 608.9 | Yes | N/A | N/A | 2024-03-15 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-04-30 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-24 | 23 | 17 | 2024-04-30 | 2024-05-14 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-03 | Unknown | Unknown | 15 | 11 | 86 | 62 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-13 | 11 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-07 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 1324.53 | -29.69 | Unknown | Unknown | 4.75 | 1349.47 | 0 | 525.88 | 1324.53 | -798.65 | Yes | N/A | N/A | 2023-03-01 | 2023-03-07 | 7 | 5 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | 2023-12-20 | 281 | 201 | Unknown | 2023-12-15 | Unknown | Unknown | 2023-12-20 | 2024-01-24 | 36 | 26 | 2024-01-24 | 2024-01-24 | 1 | 1 | 288 | 206 | 37 | 27 | 325 | 233 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-05 | -231 | -166 | No | 2023-01-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | 2023-04-04 | IOU Designed & Installed | N/A | Yes | 27 | 58.87 | -13.64 | Unknown | Unknown | Unknown | 72.51 | Unknown | 959.66 | 58.87 | 900.79 | Yes | N/A | N/A | 2023-01-18 | 2023-02-14 | 28 | 20 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2023-04-18 | 15 | 11 | 2023-04-18 | 2023-04-18 | 1 | 1 | 28 | 20 | 16 | 12 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -474 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-10-06 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 1529.85 | 491.73 | Unknown | 86.76 | 29.73 | 921.63 | 3241 | 1215.09 | 1529.85 | -314.76 | Yes | N/A | N/A | 2023-09-26 | 2023-10-06 | 11 | 9 | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-01-02 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-03-04 | 63 | 45 | 2024-03-04 | 2024-03-04 | 1 | 1 | 97 | 71 | 65 | 47 | 162 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | 26 | 19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-13 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 28511.5 | 996.22 | Unknown | 42.89 | 12.46 | 27459.93 | Unknown | 9645.47 | 28511.5 | -18866.03 | Yes | N/A | N/A | 2024-08-07 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-05 | 49 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-24 | 41 | 29 | 2025-03-24 | 2025-03-24 | 1 | 1 | 0 | 0 | 91 | 63 | 91 | 63 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 480 | 480 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | -618 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-10 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 2962.49 | 753.78 | Unknown | 163.63 | Unknown | 2045.08 | Unknown | 1639.94 | 2962.49 | -1322.55 | Yes | N/A | N/A | 2025-01-02 | 2025-01-10 | 9 | 7 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-03-31 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-04 | 5 | 5 | 2025-04-04 | 2025-04-04 | 1 | 1 | 90 | 64 | 7 | 7 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -274 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 736.77 | 133.8 | Unknown | 66.2 | 27.03 | 509.74 | 3981 | 855.18 | 736.77 | 118.41 | Yes | N/A | N/A | 2024-01-11 | 2024-01-12 | 2 | 2 | 2024-01-12 | 2024-01-18 | 7 | 5 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 2 | 2 | 8 | 6 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -444 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 468.94 | Unknown | Unknown | Unknown | 10.44 | 458.5 | 3961 | 1299.58 | 468.94 | 830.64 | Yes | N/A | N/A | 2024-01-24 | 2024-05-29 | 127 | 91 | 2024-05-29 | 2024-06-14 | 17 | 13 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-08-22 | 70 | 50 | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-22 | 2024-09-10 | 20 | 14 | 2024-09-10 | 2024-09-10 | 1 | 1 | 197 | 141 | 38 | 28 | 235 | 169 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 3.86 | -3.42 | Unknown | Unknown | Unknown | 7.28 | Unknown | 308.87 | 3.86 | 305.01 | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-27 | 3 | 3 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2 | 2 | 5 | 5 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 352 | 352 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-15 | 511 | 366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-23 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 5748.93 | Unknown | Unknown | Unknown | 45.84 | 5703.09 | 7962 | 745.33 | 5748.93 | -5003.6 | Yes | N/A | N/A | 2024-08-22 | 2024-09-25 | 35 | 25 | 2024-09-25 | 2024-10-15 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-26 | 43 | 31 | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-27 | 2025-03-26 | 90 | 64 | 2025-03-26 | 2025-01-07 | Unknown | Unknown | 78 | 56 | 111 | 79 | 189 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 974.78 | Unknown | Unknown | Unknown | 7.61 | 967.17 | 3981 | 1092.02 | 974.78 | 117.24 | Yes | N/A | N/A | 2025-04-23 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-05-14 | 31 | 23 | 2025-04-23 | 2025-05-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-09 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-11 | 3 | 3 | 2025-06-11 | 2025-06-11 | 1 | 1 | 41 | 29 | 35 | 27 | 76 | 56 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-18 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | 4517.79 | 5947.35 | Unknown | 1825.26 | -6890 | 3635.18 | Unknown | 6889.55 | 4517.79 | 2371.76 | Yes | N/A | N/A | 2025-03-14 | 2025-03-26 | 13 | 9 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-09 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-04 | 7 | 5 | 2025-05-04 | 2025-05-04 | 1 | 0 | 13 | 9 | 31 | 22 | 44 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 199.1 | 199.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | -2.41 | -15.02 | Unknown | Unknown | 5.3 | 7.31 | 3981 | 1270.08 | -2.41 | 1272.49 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-09-07 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-12-11 | 96 | 68 | 2023-12-11 | 2023-10-04 | Unknown | Unknown | 155 | 111 | 96 | 68 | 251 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | -9.38 | -8.58 | Unknown | Unknown | Unknown | -0.8 | Unknown | 158.79 | -9.38 | 168.17 | Yes | N/A | N/A | 2023-11-13 | 2023-12-08 | 26 | 20 | 2023-12-08 | 2023-12-08 | 1 | 1 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-03-15 | 87 | 63 | 2024-03-15 | 2024-03-15 | 1 | 1 | 39 | 29 | 89 | 65 | 128 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-14 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-09 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 35.43 | Unknown | Unknown | Unknown | Unknown | 35.43 | Unknown | 1578.54 | 35.43 | 1543.11 | Yes | N/A | N/A | 2025-01-08 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-01-09 | 24 | 18 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-14 | 6 | 4 | 2025-01-14 | 2025-01-14 | 1 | 1 | 1 | 1 | 31 | 23 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -460 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-11 | 2023-03-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -17.82 | -12.91 | Unknown | Unknown | Unknown | -4.91 | Unknown | 311.78 | -17.82 | 329.6 | Yes | N/A | N/A | 2023-03-11 | 2023-03-11 | 1 | 0 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -429 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 356.99 | 120.84 | Unknown | Unknown | Unknown | 236.15 | 3981 | 524.33 | 356.99 | 167.34 | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-12-07 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-21 | 15 | 11 | 2023-12-21 | 2023-12-21 | 1 | 1 | 89 | 65 | 17 | 13 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1684.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-24 | 23 | 17 | 2025-04-24 | 2025-04-24 | 1 | 1 | 9 | 7 | 25 | 19 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -409 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 1620.03 | -6 | Unknown | Unknown | 8.08 | 1617.95 | 3981 | 1324.9 | 1620.03 | -295.13 | Yes | N/A | N/A | 2024-09-30 | 2024-11-12 | 44 | 32 | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-02-07 | 88 | 64 | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-07 | 2025-02-13 | 7 | 5 | 2025-02-13 | 2025-02-18 | 6 | 4 | 132 | 96 | 14 | 10 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | 314 | 225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1904.82 | -34.49 | Unknown | Unknown | Unknown | 1939.31 | 0 | 372.29 | 1904.82 | -1532.53 | Yes | N/A | N/A | 2023-08-29 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-08-31 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-06 | 8 | 6 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 0 | 0 | 31 | 23 | 31 | 23 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -298 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | -1541.19 | 458.25 | Unknown | 72.5 | -2387 | 315.06 | Unknown | 2386.5 | -1541.19 | 3927.69 | Yes | N/A | N/A | 2025-03-18 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | 6 | 5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1245.36 | Unknown | Unknown | Unknown | 23.96 | 1221.4 | 3941 | 770.03 | 1245.36 | -475.33 | Yes | N/A | N/A | 2024-01-23 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-02-05 | 41 | 29 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 0 | 0 | 42 | 30 | 42 | 30 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | -454 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 96.1 | Unknown | Unknown | Unknown | Unknown | 96.1 | 3981 | 2105.39 | 96.1 | 2009.29 | Yes | N/A | N/A | 2024-12-13 | 2024-12-16 | 4 | 2 | 2024-12-16 | 2025-01-08 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-04 | 1 | 1 | 4 | 2 | 25 | 19 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -253 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-05-02 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | -974.84 | Unknown | Unknown | Unknown | -1194 | 219.16 | 3981 | 1816.2 | -974.84 | 2791.04 | Yes | N/A | N/A | 2024-03-13 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-05-02 | 52 | 38 | 2024-05-02 | 2024-08-28 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2025-02-24 | 153 | 109 | Unknown | 2024-11-13 | Unknown | Unknown | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | 2025-02-26 | Unknown | Unknown | 211 | 151 | 56 | 42 | 267 | 193 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | Unknown | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 31.03 | Unknown | Unknown | Unknown | Unknown | 31.03 | 3981 | 1688.13 | 31.03 | 1657.1 | Yes | N/A | N/A | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-03 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-15 | 13 | 9 | 2024-10-15 | 2024-10-15 | 1 | 1 | 2 | 2 | 15 | 11 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | -212 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-15 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | 9725.12 | 27.38 | Unknown | Unknown | 3.51 | 9694.23 | Unknown | 16430.68 | 9725.12 | 6705.56 | Yes | N/A | N/A | 2023-05-04 | 2023-11-06 | 187 | 133 | 2023-11-06 | 2024-02-09 | 96 | 70 | 2023-08-16 | 2023-11-06 | 83 | 59 | 2023-12-04 | 2024-02-13 | 9 | 7 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-06 | 20 | 14 | 2024-03-06 | 2024-03-06 | 1 | 1 | 270 | 192 | 126 | 92 | 396 | 284 | Steps 2,3,5,6,7 | 181 | 129 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -403 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-06 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1592.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-06 | 23 | 17 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-06-23 | 200 | 142 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 200 | 142 | 25 | 19 | 225 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-31 | 865 | 620 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 11252.82 | 131.06 | Unknown | Unknown | 9.5 | 11112.26 | 3981 | 925.72 | 11252.82 | -10327.1 | Yes | N/A | N/A | 2024-02-20 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-03-01 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-05-30 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-17 | 13 | 9 | 2024-06-17 | 2024-06-14 | Unknown | Unknown | 91 | 65 | 28 | 20 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -796 | -569 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | 2023-04-07 | IOU Designed & Installed | N/A | No | N/A | 898.3 | 416.08 | Unknown | 233.67 | Unknown | 248.55 | Unknown | 311.78 | 898.3 | -586.52 | Yes | N/A | N/A | 2023-02-27 | 2023-02-27 | 1 | 1 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-04-07 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-08-09 | 125 | 89 | 2023-08-09 | 2023-08-09 | 1 | 1 | 41 | 31 | 126 | 90 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 9.8 | -7.54 | Unknown | Unknown | Unknown | 17.34 | 3941 | 1390.01 | 9.8 | 1380.21 | Yes | N/A | N/A | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-09 | 8 | 6 | 2024-07-09 | 2024-07-09 | 1 | 1 | 8 | 6 | 10 | 8 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -182 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | 1209.35 | -22.64 | Unknown | Unknown | 12.13 | 1219.86 | 7962 | 1164.61 | 1209.35 | -44.74 | Yes | N/A | N/A | 2023-11-07 | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-12-13 | 73 | 53 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-02-22 | 72 | 52 | Unknown | 2024-02-14 | Unknown | Unknown | 2024-02-22 | 2024-03-15 | 23 | 17 | 2024-03-15 | 2024-03-15 | 1 | 1 | 72 | 52 | 97 | 71 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | -107 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 718.59 | -6.23 | Unknown | Unknown | Unknown | 724.82 | Unknown | 967.5 | 718.59 | 248.91 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-08-07 | 165 | 117 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-15 | 9 | 7 | 2023-08-15 | 2023-08-15 | 1 | 1 | 166 | 118 | 10 | 8 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -669 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-03-19 | IOU Designed & Installed | N/A | No | N/A | 1618.21 | 500.56 | Unknown | 276.92 | Unknown | 840.73 | 3981 | 673.67 | 1618.21 | -944.54 | Yes | N/A | N/A | 2023-03-07 | 2023-03-07 | 1 | 1 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-03-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-03-19 | 2023-04-12 | 25 | 18 | 2023-04-12 | 2023-04-12 | 1 | 1 | 14 | 10 | 26 | 19 | 40 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-17 | 142 | 102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5.56 | Unknown | Unknown | Unknown | Unknown | 5.56 | 0 | 341 | 5.56 | 335.44 | Yes | N/A | N/A | 2023-02-01 | 2023-02-01 | 1 | 1 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 281 | 281 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-19 | 108 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -344.15 | -12.33 | Unknown | Unknown | -340 | 8.18 | 3981 | 1271.94 | -344.15 | 1616.09 | Yes | N/A | N/A | 2022-07-11 | 2023-01-31 | 205 | 147 | 2023-01-31 | 2023-02-15 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-06-07 | Unknown | Unknown | 205 | 147 | 16 | 12 | 221 | 159 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -283 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-24 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 7634.92 | -3.64 | Unknown | Unknown | Unknown | 7638.56 | 3981 | 1899.94 | 7634.92 | -5734.98 | Yes | N/A | N/A | 2023-08-23 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2024-05-31 | 290 | 208 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-10-03 | 35 | 25 | 2024-05-31 | 2024-06-12 | 13 | 9 | Unknown | 2024-06-21 | Unknown | Unknown | 2024-07-26 | 2024-09-10 | 47 | 33 | 2024-09-10 | 2024-09-05 | Unknown | Unknown | 13 | 9 | 372 | 266 | 385 | 275 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -578 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 1299.59 | -17.7 | Unknown | Unknown | 9.91 | 1307.38 | 3981 | 1424.73 | 1299.59 | 125.14 | Yes | N/A | N/A | 2024-11-04 | 2024-11-09 | 6 | 5 | 2024-11-09 | 2024-11-15 | 7 | 5 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-02-11 | 89 | 63 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-02-11 | 2025-03-04 | 22 | 16 | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 95 | 68 | 29 | 21 | 124 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-29 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 469.04 | -17.83 | Unknown | Unknown | Unknown | 486.87 | Unknown | 1073.52 | 469.04 | 604.48 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-06-27 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-08 | 12 | 8 | 2024-07-08 | 2024-07-08 | 1 | 1 | 233 | 167 | 14 | 10 | 247 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -325 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 236.43 | -21.55 | Unknown | Unknown | Unknown | 257.98 | Unknown | 838.15 | 236.43 | 601.72 | Yes | N/A | N/A | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | 2024-03-25 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-04 | Unknown | Unknown | 1 | 1 | 18 | 12 | 19 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | -79 | -57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 191.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-03-24 | 53 | 39 | 2023-03-24 | 2023-05-03 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 53 | 39 | 42 | 30 | 95 | 69 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -371 | -266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-09 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 735.05 | Unknown | Unknown | Unknown | Unknown | 735.05 | 3981 | 1285.27 | 735.05 | 550.22 | Yes | N/A | N/A | 2024-07-08 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-07-09 | 212 | 152 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-10-07 | 91 | 65 | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-07 | 2024-10-18 | 12 | 10 | 2024-10-18 | 2024-10-18 | 1 | 1 | 91 | 65 | 225 | 163 | 316 | 228 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-27 | -73 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 131.21 | -9.29 | Unknown | Unknown | -769.46 | 909.96 | Unknown | 778.13 | 131.21 | 646.92 | Yes | N/A | N/A | 2023-10-18 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-11-02 | 116 | 84 | 2023-11-02 | 2023-11-10 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-01-29 | 81 | 57 | Unknown | 2024-01-24 | Unknown | Unknown | 2024-01-29 | 2024-02-14 | 17 | 13 | 2024-02-14 | 2024-02-14 | 1 | 1 | 90 | 64 | 134 | 98 | 224 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | 203 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-10 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 5749.19 | 1598.71 | Unknown | 146.67 | -2197.55 | 6201.36 | 21184 | 2867 | 5749.19 | -2882.19 | Yes | N/A | N/A | 2023-11-08 | 2023-11-10 | 3 | 3 | 2023-11-10 | 2023-11-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-15 | 6 | 4 | 2023-11-15 | 2025-03-25 | 497 | 355 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-11 | 1 | 1 | 500 | 358 | 14 | 10 | 514 | 368 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 2298.71 | 228.69 | Unknown | Unknown | 28.19 | 2041.83 | 3981 | 700.4 | 2298.71 | -1598.31 | Yes | N/A | N/A | 2023-11-01 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-11-21 | 92 | 66 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-03-19 | 120 | 86 | Unknown | 2024-03-08 | Unknown | Unknown | 2024-03-19 | 2024-04-08 | 21 | 15 | 2024-04-08 | 2024-04-08 | 1 | 1 | 120 | 86 | 114 | 82 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.62 | -4.44 | Unknown | Unknown | 3.27 | 4.79 | 7512 | 1794.63 | 3.62 | 1791.01 | Yes | N/A | N/A | 2023-10-25 | 2023-10-25 | 1 | 1 | 2023-10-25 | 2023-11-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-01 | 3 | 3 | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2023-12-04 | Unknown | Unknown | 4 | 4 | 36 | 26 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 628 | 449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2022-10-21 | 2024-05-03 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 21289.74 | 606.99 | Unknown | Unknown | 14.41 | 20668.34 | 905666 | 43455.04 | 21289.74 | 22165.3 | Yes | N/A | N/A | 2022-10-21 | 2023-03-27 | 158 | 112 | 2023-03-27 | 2023-10-13 | 201 | 145 | 2023-04-03 | 2023-04-20 | 18 | 14 | 2024-03-13 | 2024-03-18 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-03-12 | 145 | 103 | 2024-05-03 | 2024-05-22 | 20 | 14 | 2024-05-22 | 2024-05-22 | 1 | 1 | 176 | 126 | 373 | 267 | 549 | 393 | Steps 2,3,5,6,7 | 193 | 139 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 507.79 | -23.38 | Unknown | Unknown | Unknown | 531.17 | 3981 | 388.73 | 507.79 | -119.06 | Yes | N/A | N/A | 2024-02-14 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-02-14 | 2 | 2 | 2024-02-14 | Unknown | Unknown | Unknown | 2024-02-15 | 2024-02-17 | 3 | 2 | 2024-02-15 | 2024-02-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-02-22 | 2 | 2 | 2024-02-22 | 2024-02-22 | 1 | 1 | 7 | 5 | 8 | 7 | 15 | 12 | Steps 2,3,5,6,7 | 2 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | 18 | 13 | No | 2023-04-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | Yes | 293 | -3.15 | -2.55 | Unknown | Unknown | Unknown | -0.6 | 3981 | 798.55 | -3.15 | 801.7 | Yes | N/A | N/A | 2023-04-25 | 2024-02-12 | 294 | 210 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-05 | Unknown | Unknown | 294 | 210 | 0 | 0 | 294 | 210 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -625 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-11 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 6.84 | -10.75 | Unknown | Unknown | Unknown | 17.59 | Unknown | 1612.62 | 6.84 | 1605.78 | Yes | N/A | N/A | 2023-12-08 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2023-12-11 | 77 | 55 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-15 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-28 | 14 | 10 | 2023-12-28 | 2023-12-28 | 1 | 1 | 5 | 5 | 92 | 66 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 174.05 | 174.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-19 | 265 | 190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 241.28 | -5.34 | Unknown | Unknown | Unknown | 246.62 | 3158 | 763.7 | 241.28 | 522.42 | Yes | N/A | N/A | 2023-05-24 | 2023-05-24 | 1 | 1 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-06-10 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-11-12 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 2244.09 | 1285.86 | Unknown | 120.11 | Unknown | 838.12 | Unknown | 197.01 | 2244.09 | -2047.08 | Yes | N/A | N/A | 2024-06-21 | 2024-11-12 | 145 | 103 | 2024-11-12 | 2024-11-14 | 3 | 3 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-01-08 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-02-11 | 35 | 25 | 2025-02-11 | 2025-02-11 | 1 | 1 | 201 | 143 | 39 | 29 | 240 | 172 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -158 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1815.14 | -34.44 | Unknown | Unknown | Unknown | 1849.58 | 15924 | 2108.94 | 1815.14 | 293.8 | Yes | N/A | N/A | 2024-08-21 | 2024-10-25 | 66 | 48 | 2024-10-25 | 2024-12-03 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-12-03 | 36 | 26 | 2024-12-03 | 2025-02-20 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-26 | Unknown | Unknown | 146 | 106 | 76 | 54 | 222 | 160 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | -277 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 37458.46 | 16981.63 | Unknown | Unknown | Unknown | 20476.83 | Unknown | 8356.39 | 37458.46 | -29102.07 | Yes | N/A | N/A | 2025-04-15 | 2025-04-24 | 10 | 8 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-19 | 20 | 14 | 2025-05-19 | 2025-05-19 | 1 | 1 | 24 | 18 | 21 | 15 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 122 | 122 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 1141.15 | -11.09 | Unknown | Unknown | 8.84 | 1143.4 | 3981 | 777.76 | 1141.15 | -363.39 | Yes | N/A | N/A | 2024-02-08 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2024-03-22 | 149 | 107 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-05-22 | 62 | 44 | Unknown | 2025-03-19 | Unknown | Unknown | 2024-05-22 | 2024-05-28 | 7 | 5 | 2024-05-28 | 2024-05-28 | 1 | 1 | 62 | 44 | 157 | 113 | 219 | 157 | Steps 2,3,5,6,7 | 301 | 215 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-24 | -9 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1254.28 | 1904.75 | Unknown | 606.56 | -2065 | 807.97 | 0 | 2065.09 | 1254.28 | 810.81 | Yes | N/A | N/A | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | 2023-08-28 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 23 | 17 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 153.1 | 153.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | -582 | -416 | No | 2025-01-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | Yes | 8 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1370.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-05 | 9 | 7 | 2025-02-05 | 2025-02-07 | 3 | 3 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-09 | 1 | 1 | 9 | 7 | 4 | 4 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 120.05 | 120.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 131 | 95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 198.32 | -33.87 | Unknown | Unknown | 1.1 | 231.09 | 3981 | 1563.93 | 198.32 | 1365.61 | Yes | N/A | N/A | 2023-02-28 | 2023-03-13 | 14 | 10 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-09-08 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | 1273 | 910 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-05-05 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 380.78 | Unknown | Unknown | Unknown | Unknown | 380.78 | Unknown | 2538.31 | 380.78 | 2157.53 | Yes | N/A | N/A | 2025-04-24 | 2025-05-05 | 12 | 8 | 2025-05-05 | 2025-06-11 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-23 | 19 | 15 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-26 | 4 | 4 | 2025-06-26 | 2025-06-26 | 1 | 1 | 12 | 8 | 62 | 48 | 74 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 521 | 374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | 2022-05-03 | 2024-05-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 48135.73 | 9188.31 | Unknown | Unknown | -4623.36 | 43570.78 | 14697 | 23659.54 | 48135.73 | -24476.19 | Yes | N/A | N/A | 2022-05-03 | 2023-08-30 | 485 | 347 | 2023-08-30 | 2024-02-05 | 160 | 114 | 2023-11-01 | 2024-01-30 | 52 | 36 | 2023-11-07 | 2024-02-20 | 27 | 21 | 2024-02-14 | Unknown | Unknown | Unknown | 2024-02-14 | 2024-05-14 | 91 | 65 | 2024-05-14 | 2024-06-20 | 38 | 28 | 2024-06-20 | 2024-06-20 | 1 | 1 | 537 | 383 | 317 | 229 | 854 | 612 | Steps 2,3,5,6,7 | 186 | 132 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-21 | 678 | 485 | No | 2020-09-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-09-22 | 2020-09-22 | Unknown | IOU Designed & Installed | N/A | Yes | 889 | -10.87 | -7.87 | Unknown | Unknown | Unknown | -3 | 3885 | 284.21 | -10.87 | 295.08 | Yes | N/A | N/A | 2020-09-22 | 2023-02-28 | 890 | 636 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-06-30 | Unknown | Unknown | 890 | 636 | 0 | 0 | 890 | 636 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-15 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 48.52 | -4.59 | Unknown | Unknown | 12.56 | 40.55 | 3981 | 1134.45 | 48.52 | 1085.93 | Yes | N/A | N/A | 2024-02-23 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-02-23 | 30 | 22 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-05-08 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-17 | 10 | 8 | 2024-05-17 | 2024-05-20 | 4 | 2 | 76 | 54 | 44 | 32 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | -10.1 | -8.7 | Unknown | Unknown | Unknown | -1.4 | Unknown | 158.14 | -10.1 | 168.24 | Yes | N/A | N/A | 2023-10-19 | 2023-11-09 | 22 | 16 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-12-20 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-12-06 | 27 | 19 | Unknown | 2025-02-27 | Unknown | Unknown | 2023-12-06 | 2024-02-12 | 69 | 49 | 2024-02-12 | 2024-02-12 | 1 | 1 | 91 | 65 | 71 | 51 | 162 | 116 | Steps 2,3,5,6,7 | 449 | 321 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-17 | 235 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 1382.03 | -13.06 | Unknown | Unknown | 13.55 | 1381.54 | 3981 | 1125.13 | 1382.03 | -256.9 | Yes | N/A | N/A | 2023-09-14 | 2024-01-18 | 127 | 91 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2024-04-18 | 169 | 121 | Unknown | 2024-04-17 | Unknown | Unknown | 2024-04-18 | 2024-05-09 | 22 | 16 | 2024-05-09 | 2024-05-09 | 1 | 1 | 296 | 212 | 23 | 17 | 319 | 229 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 519.08 | 307.12 | Unknown | Unknown | Unknown | 211.96 | Unknown | 197.01 | 519.08 | -322.07 | Yes | N/A | N/A | 2024-09-10 | 2024-09-25 | 16 | 12 | 2024-09-25 | 2024-09-26 | 2 | 2 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 16 | 12 | 3 | 3 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 476 | 476 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-10-16 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 20198.53 | 6353 | Unknown | Unknown | -1094.17 | 14939.7 | 3981 | 1709.51 | 20198.53 | -18489.02 | Yes | N/A | N/A | 2023-03-15 | 2023-06-20 | 98 | 70 | 2023-06-20 | 2023-11-20 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-01-09 | 51 | 37 | Unknown | 2023-12-19 | Unknown | Unknown | 2023-12-28 | 2024-01-17 | 21 | 15 | 2024-01-17 | 2024-01-16 | Unknown | Unknown | 149 | 107 | 175 | 125 | 324 | 232 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -706 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 570.52 | -11.7 | Unknown | Unknown | Unknown | 582.22 | 3981 | 1368.79 | 570.52 | 798.27 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-15 | 8 | 6 | 2024-08-15 | 2024-08-15 | 1 | 1 | 9 | 7 | 10 | 8 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 29.8 | Unknown | Unknown | Unknown | Unknown | 29.8 | 3981 | 197.01 | 29.8 | 167.21 | Yes | N/A | N/A | 2024-12-17 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2025-01-09 | 45 | 33 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-03-19 | 69 | 49 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2 | 2 | 115 | 83 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-12 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 672.68 | 244.9 | Unknown | Unknown | Unknown | 427.78 | 3981 | 1097.54 | 672.68 | 424.86 | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-05 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-09 | 5 | 3 | 2023-10-09 | 2023-10-09 | 1 | 1 | 26 | 20 | 7 | 5 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-04 | 550 | 393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-26 | 2023-08-26 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 3275.45 | 509.4 | Unknown | 250.25 | Unknown | 2515.8 | 3981 | 362.2 | 3275.45 | -2913.25 | Yes | N/A | N/A | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | 2024-03-20 | 208 | 148 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2025-01-22 | 309 | 221 | Unknown | 2024-12-20 | Unknown | Unknown | 2025-01-22 | 2025-02-04 | 14 | 10 | 2025-02-04 | 2025-02-04 | 1 | 1 | 310 | 221 | 223 | 159 | 533 | 380 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-12 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 385.99 | -8.71 | Unknown | Unknown | Unknown | 394.7 | 3941 | 1025.32 | 385.99 | 639.33 | Yes | N/A | N/A | 2024-04-12 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-04-12 | 59 | 43 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-17 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-21 | 5 | 3 | 2024-05-21 | 2024-05-20 | Unknown | Unknown | 36 | 26 | 64 | 46 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | -387 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-14 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 2485.46 | 641.12 | Unknown | Unknown | Unknown | 1844.34 | 3981 | 2215.99 | 2485.46 | -269.47 | Yes | N/A | N/A | 2025-01-06 | 2025-01-14 | 9 | 7 | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-03-19 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-03 | 16 | 12 | 2025-04-03 | 2025-04-03 | 1 | 1 | 74 | 54 | 18 | 14 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -337 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 396.64 | 126.28 | Unknown | Unknown | Unknown | 270.36 | 3981 | 1631.94 | 396.64 | 1235.3 | Yes | N/A | N/A | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-10 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-19 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-30 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 1427.35 | Unknown | Unknown | Unknown | 49.46 | 1377.89 | 3981 | 1047.04 | 1427.35 | -380.31 | Yes | N/A | N/A | 2023-10-27 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-10-27 | 50 | 36 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-09-03 | 310 | 222 | Unknown | 2024-08-13 | Unknown | Unknown | 2024-09-03 | 2024-09-16 | 14 | 10 | 2024-09-16 | 2024-09-17 | 2 | 2 | 310 | 222 | 66 | 48 | 376 | 270 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -647 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 24.13 | Unknown | Unknown | Unknown | Unknown | 24.13 | 3981 | 1718.9 | 24.13 | 1694.77 | Yes | N/A | N/A | 2024-10-22 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-10-22 | 34 | 24 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-15 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-20 | 6 | 4 | 2024-11-20 | 2024-11-20 | 1 | 1 | 25 | 19 | 41 | 29 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -716 | -512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 3092.17 | 1756.42 | Unknown | 119.63 | Unknown | 1216.12 | 3981 | 1503.35 | 3092.17 | -1588.82 | Yes | N/A | N/A | 2024-10-22 | 2024-10-21 | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-10-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-10-31 | 4 | 4 | 2024-10-31 | 2024-10-31 | 1 | 1 | 7 | 5 | 5 | 5 | 12 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -61 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 2048.62 | 380.61 | Unknown | Unknown | 47.46 | 1620.55 | 3981 | 239.97 | 2048.62 | -1808.65 | Yes | N/A | N/A | 2024-02-27 | 2024-03-27 | 30 | 22 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2025-02-11 | 322 | 230 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-18 | 8 | 6 | 2025-02-18 | 2025-02-18 | 1 | 1 | 352 | 252 | 10 | 8 | 362 | 260 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Residential | Underserved Community | Alpine | COUNTY OF SAN DIEGO-SOUTH of 56 | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2028-08-31 | -1406 | -1005 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-10 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 156017.7 | 18138.47 | Unknown | Unknown | -20357.39 | 158236.62 | 6783.46 | 65767.32 | 156017.7 | -90250.38 | Yes | N/A | N/A | 2023-08-03 | 2023-08-03 | 1 | 1 | 2023-08-03 | 2024-01-19 | 170 | 122 | 2023-09-19 | 2024-10-30 | 55 | 41 | 2023-11-17 | 2024-06-10 | 149 | 105 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-06 | 2024-10-31 | 87 | 63 | 2024-11-05 | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2024-10-25 | 1 | 1 | 56 | 42 | 407 | 291 | 463 | 333 | Steps 2,3,5,6,7 | 470 | 336 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 3113.05 | 412.09 | Unknown | 113.34 | Unknown | 2587.62 | 3981 | 1042.63 | 3113.05 | -2070.42 | Yes | N/A | N/A | 2023-04-28 | 2023-05-05 | 8 | 6 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-10-19 | 7 | 7 | 2023-05-05 | 2024-01-04 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-09 | 6 | 4 | 2024-01-09 | 2024-01-09 | 1 | 1 | 253 | 181 | 14 | 12 | 267 | 193 | Steps 2,3,5,6,7 | 167 | 119 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-21 | -83 | -60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 4383.35 | 1182.68 | Unknown | 302.16 | 307.12 | 2591.39 | 3885 | 442.06 | 4383.35 | -3941.29 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-09-29 | 193 | 139 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-11-12 | 411 | 293 | 2024-11-12 | 2023-09-29 | Unknown | Unknown | 194 | 140 | 411 | 293 | 605 | 433 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -606 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 7.4 | Unknown | Unknown | Unknown | 1.22 | 6.18 | 3981 | 1268.2 | 7.4 | 1260.8 | Yes | N/A | N/A | 2024-12-04 | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-12-11 | 23 | 17 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-02-18 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-03 | 14 | 10 | 2025-03-03 | 2025-03-03 | 1 | 1 | 70 | 50 | 38 | 28 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 1878 | 1878 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-01-16 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-08 | 2025-02-08 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | 1933.94 | Unknown | Unknown | Unknown | Unknown | 1933.94 | Unknown | 607.03 | 1933.94 | -1326.91 | Yes | N/A | N/A | 2025-02-08 | 2025-02-18 | 11 | 7 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-23 | 2025-03-10 | 16 | 11 | 2025-03-12 | 2025-06-06 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-10 | 5 | 3 | 2025-06-10 | 2025-06-10 | 1 | 1 | 98 | 70 | 22 | 15 | 120 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 27.35 | 27.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -465 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 47.48 | -0.62 | Unknown | Unknown | Unknown | 48.1 | 3941 | 935.95 | 47.48 | 888.47 | Yes | N/A | N/A | 2024-04-02 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-04-02 | 49 | 35 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-10-08 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-23 | 16 | 12 | 2024-10-23 | 2024-10-23 | 1 | 1 | 190 | 136 | 66 | 48 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-05 | 372 | 267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 4590.27 | Unknown | Unknown | Unknown | Unknown | 4590.27 | Unknown | 571.18 | 4590.27 | -4019.09 | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2023-12-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-01-12 | 10 | 8 | 2024-01-12 | 2024-01-12 | 1 | 1 | 1 | 1 | 18 | 14 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-03 | -323 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-03-02 | IOU Designed & Installed | N/A | No | N/A | -7 | -5.07 | Unknown | Unknown | Unknown | -1.93 | Unknown | 363.72 | -7 | 370.72 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-03-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-03-17 | 16 | 12 | 2023-03-17 | 2023-03-17 | 1 | 1 | 3 | 3 | 17 | 13 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | 69 | 50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-02 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 9016.41 | Unknown | Unknown | Unknown | 17.58 | 8998.83 | 3981 | 922.51 | 9016.41 | -8093.9 | Yes | N/A | N/A | 2024-02-01 | 2024-02-02 | 2 | 2 | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-25 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-04 | 11 | 9 | 2024-04-04 | 2024-12-11 | 252 | 180 | 55 | 39 | 264 | 190 | 319 | 229 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 227 | 227 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-17 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-29 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 914.77 | -5.71 | Unknown | Unknown | 11 | 909.48 | 3981 | 771.74 | 914.77 | -143.03 | Yes | N/A | N/A | 2024-04-26 | 2024-05-09 | 14 | 10 | 2024-05-09 | 2024-05-10 | 2 | 2 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-07-01 | 53 | 37 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-07-01 | 2024-07-16 | 16 | 12 | 2024-07-16 | 2024-07-15 | Unknown | Unknown | 67 | 47 | 18 | 14 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Jamul | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 20511.63 | 272.1 | Unknown | Unknown | -1606.39 | 21845.92 | 1663 | 4836.19 | 20511.63 | -15675.44 | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-08-02 | 95 | 69 | 2024-07-17 | 2024-07-26 | 10 | 8 | 2024-07-29 | 2024-07-31 | 3 | 3 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-06 | 2024-09-11 | 37 | 27 | 2024-10-01 | 2024-10-23 | 23 | 17 | 2024-10-23 | 2024-10-23 | 1 | 1 | 11 | 9 | 159 | 117 | 170 | 126 | Steps 2,3,5,6,7 | 16 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -583 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 427.17 | Unknown | Unknown | Unknown | 2.64 | 424.53 | 3981 | 1183.33 | 427.17 | 756.16 | Yes | N/A | N/A | 2024-11-01 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-11-26 | 44 | 32 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-27 | 17 | 13 | 2024-12-27 | 2024-12-27 | 1 | 1 | 16 | 12 | 62 | 46 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-09 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 20.37 | -18.07 | Unknown | Unknown | Unknown | 38.44 | Unknown | 1341 | 20.37 | 1320.63 | Yes | N/A | N/A | 2024-04-11 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-11 | 50 | 36 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-24 | 14 | 10 | 2024-04-24 | 2024-04-24 | 1 | 1 | 1 | 1 | 65 | 47 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 74 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | 5553.34 | Unknown | Unknown | Unknown | Unknown | 5553.34 | 3981 | 1077.22 | 5553.34 | -4476.12 | Yes | N/A | N/A | 2023-02-10 | 2023-02-10 | 1 | 1 | 2023-02-10 | 2023-08-02 | 174 | 124 | 2023-03-08 | 2023-07-24 | 139 | 99 | 2023-10-02 | 2023-10-05 | 4 | 4 | 2023-08-02 | 2023-09-13 | 43 | 31 | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-25 | 2023-11-20 | 27 | 19 | 2023-11-20 | 2023-11-14 | Unknown | Unknown | 183 | 131 | 205 | 147 | 388 | 278 | Steps 2,3,5,6,7 | 211 | 151 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-07 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 580.16 | 513.12 | Unknown | Unknown | -1198 | 1265.04 | 2296 | 3107.1 | 580.16 | 2526.94 | Yes | N/A | N/A | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | 2024-05-15 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-09-06 | 115 | 83 | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-06 | 2024-09-12 | 7 | 5 | 2024-09-12 | 2024-09-12 | 1 | 1 | 157 | 113 | 9 | 7 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | -604 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 7.84 | Unknown | Unknown | Unknown | Unknown | 7.84 | Unknown | 1559.12 | 7.84 | 1551.28 | Yes | N/A | N/A | 2024-11-04 | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-11-04 | 32 | 22 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-12-17 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-17 | 32 | 24 | 2025-01-17 | 2025-01-17 | 1 | 1 | 44 | 32 | 65 | 47 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-20 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | -4.39 | -18.46 | Unknown | Unknown | Unknown | 14.07 | 3981 | 1643.36 | -4.39 | 1647.75 | Yes | N/A | N/A | 2025-03-10 | 2025-03-20 | 11 | 9 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-03-26 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-03-28 | 3 | 3 | 2025-03-28 | 2025-03-28 | 1 | 1 | 18 | 14 | 5 | 5 | 23 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -697 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 90.99 | -1.25 | Unknown | Unknown | Unknown | 92.24 | 3981 | 1609.49 | 90.99 | 1518.5 | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-11 | 22 | 16 | 2024-12-11 | 2024-12-11 | 1 | 1 | 9 | 7 | 24 | 18 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2025-01-02 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 102.75 | -1.5 | Unknown | Unknown | Unknown | 104.25 | Unknown | 1183.52 | 102.75 | 1080.77 | Yes | N/A | N/A | 2024-12-17 | 2025-01-02 | 17 | 13 | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-01-27 | 5 | 3 | 2025-01-27 | 2025-01-27 | 1 | 1 | 39 | 29 | 7 | 5 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -153 | -110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1849.35 | Unknown | Unknown | Unknown | Unknown | 1849.35 | Unknown | 499.14 | 1849.35 | -1350.21 | Yes | N/A | N/A | 2024-12-04 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-12-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-30 | 1 | 1 | 0 | 0 | 36 | 26 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | -755 | -540 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 491.45 | -11.78 | Unknown | Unknown | 14.18 | 489.05 | 3981 | 641.94 | 491.45 | 150.49 | Yes | N/A | N/A | 2023-08-23 | 2023-05-30 | Unknown | Unknown | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-12-21 | 105 | 75 | Unknown | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2024-03-04 | 75 | 53 | 2024-03-04 | 2024-03-04 | 1 | 1 | 105 | 75 | 77 | 55 | 182 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -452 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 1510.83 | 280.92 | Unknown | 89.36 | 5.46 | 1135.09 | 3981 | 514.73 | 1510.83 | -996.1 | Yes | N/A | N/A | 2023-01-03 | 2023-03-14 | 71 | 51 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-06-23 | 95 | 69 | Unknown | 2023-06-16 | Unknown | Unknown | 2023-06-23 | 2023-06-26 | 4 | 2 | 2023-06-26 | 2023-06-26 | 1 | 1 | 166 | 120 | 5 | 3 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | 261 | 186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1046.98 | 1333.62 | Unknown | 239.8 | -1083 | 556.56 | 0 | 1083.36 | 1046.98 | 36.38 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | 2023-04-17 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 49 | 35 | 50 | 36 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -360 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-22 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 3442.67 | 772.19 | Unknown | 297.29 | Unknown | 2373.19 | 3981 | 601.35 | 3442.67 | -2841.32 | Yes | N/A | N/A | 2023-12-26 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2024-01-22 | 84 | 60 | 2024-01-22 | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-12 | 15 | 11 | 2024-08-06 | 2024-09-06 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-17 | 12 | 8 | 2024-09-17 | 2024-09-18 | 2 | 2 | 32 | 24 | 113 | 81 | 145 | 105 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 34.32 | Unknown | Unknown | Unknown | Unknown | 34.32 | 3941 | 1374.81 | 34.32 | 1340.49 | Yes | N/A | N/A | 2024-06-12 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-06-12 | 50 | 36 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-30 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-07 | 9 | 7 | 2024-08-07 | 2024-08-12 | 6 | 4 | 49 | 35 | 65 | 47 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-08-13 | -1052 | -753 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 1367.06 | 417.4 | Unknown | Unknown | Unknown | 949.66 | Unknown | Not available | 1367.06 | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-19 | 6 | 4 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-24 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-25 | 2 | 2 | 2024-09-25 | 2024-09-25 | 1 | 1 | 37 | 27 | 9 | 7 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 308.1 | 308.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-09-16 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 494.73 | -8.05 | Unknown | Unknown | Unknown | 502.78 | 3981 | 1402.03 | 494.73 | 907.3 | Yes | N/A | N/A | 2024-08-20 | 2024-09-06 | 18 | 14 | 2024-09-06 | 2024-09-19 | 14 | 10 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-09-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-04 | 10 | 8 | 2024-10-04 | 2024-09-30 | Unknown | Unknown | 25 | 19 | 24 | 18 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | -502 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 300.94 | 116.47 | Unknown | 10.4 | Unknown | 174.07 | 3981 | 539.65 | 300.94 | 238.71 | Yes | N/A | N/A | 2023-03-21 | 2023-03-22 | 2 | 2 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-06-23 | 94 | 68 | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-23 | 2023-06-26 | 4 | 2 | 2023-06-26 | 2023-06-26 | 1 | 1 | 96 | 70 | 5 | 3 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 830 | 594 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 7843.49 | 1926.26 | Unknown | Unknown | 51.37 | 5865.86 | 466924 | 62259.33 | 7843.49 | 54415.84 | Yes | N/A | N/A | 2023-06-21 | 2023-05-19 | Unknown | Unknown | 2023-05-19 | 2023-10-16 | 151 | 107 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2025-04-04 | 537 | 385 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-04-10 | 1 | 1 | 537 | 385 | 153 | 109 | 690 | 494 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | -10 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | 2024-05-05 | IOU Designed & Installed | N/A | No | N/A | 31670.1 | 14449.07 | Unknown | 613.49 | -4501.75 | 21109.29 | 0 | 4728.94 | 31670.1 | -26941.16 | Yes | N/A | N/A | 2023-08-02 | 2024-05-28 | 301 | 215 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-09-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-05 | 2024-05-20 | 16 | 11 | 2024-05-20 | 2024-05-20 | 1 | 1 | 301 | 215 | 19 | 14 | 320 | 229 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 7042.64 | Unknown | Unknown | Unknown | Unknown | 7042.64 | 3981 | 2056.01 | 7042.64 | -4986.63 | Yes | N/A | N/A | 2024-06-24 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-07-25 | 179 | 129 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-19 | 21 | 15 | 2024-08-19 | 2024-08-19 | 1 | 1 | 0 | 0 | 201 | 145 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | -19 | -14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-05-06 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 927.83 | 244.9 | Unknown | 143.08 | Unknown | 539.85 | 3981 | 1739.5 | 927.83 | 811.67 | Yes | N/A | N/A | 2024-04-25 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-05-06 | 40 | 28 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-31 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-12 | 13 | 9 | 2024-06-12 | 2024-06-12 | 1 | 1 | 26 | 20 | 54 | 38 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Alpine | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -303 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-07-28 | IOU Designed & Installed | N/A | No | N/A | -728.91 | 728.65 | Unknown | 609.36 | -2644 | 577.08 | Unknown | 2644.27 | -728.91 | 3373.18 | Yes | N/A | N/A | 2024-06-26 | 2024-06-28 | 3 | 3 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-28 | 2024-08-15 | 19 | 14 | 2024-08-15 | 2024-08-15 | 1 | 1 | 3 | 3 | 20 | 15 | 23 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-18 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-16 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | -13.27 | -10.74 | Unknown | Unknown | Unknown | -2.53 | Unknown | 1084.89 | -13.27 | 1098.16 | Yes | N/A | N/A | 2024-01-25 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2024-02-16 | 87 | 63 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-04 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 12 | 10 | 2024-03-15 | 2024-03-15 | 1 | 1 | 18 | 12 | 100 | 74 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 32.33 | Unknown | Unknown | Unknown | Unknown | 32.33 | 3981 | 872.51 | 32.33 | 840.18 | Yes | N/A | N/A | 2023-10-17 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-11-08 | 92 | 66 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-08-22 | 289 | 207 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-10-03 | 43 | 31 | 2024-10-03 | 2024-10-03 | 1 | 1 | 289 | 207 | 136 | 98 | 425 | 305 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-04 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | -12 | -9.72 | Unknown | Unknown | Unknown | -2.28 | Unknown | 891 | -12 | 903 | Yes | N/A | N/A | 2024-04-01 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-04 | 38 | 28 | 2024-04-04 | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-12 | 8 | 6 | 2024-04-04 | 2024-04-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-06 | 26 | 18 | 2024-05-06 | 2024-05-06 | 1 | 1 | 8 | 6 | 73 | 53 | 81 | 59 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-10-26 | IOU Designed & Installed | N/A | No | N/A | -9.31 | -7.71 | Unknown | Unknown | Unknown | -1.6 | Unknown | 158.51 | -9.31 | 167.82 | Yes | N/A | N/A | 2023-10-09 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-10-25 | 163 | 117 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-10-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-10 | 16 | 12 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2 | 2 | 180 | 130 | 182 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 151.05 | 151.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | -576 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1681.71 | Unknown | Unknown | Unknown | 4.34 | 1677.37 | 3981 | 1189.69 | 1681.71 | -492.02 | Yes | N/A | N/A | 2024-10-21 | 2024-10-24 | 4 | 4 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-01-21 | 90 | 64 | Unknown | 2024-12-23 | Unknown | Unknown | 2025-01-21 | 2025-01-23 | 3 | 3 | 2025-01-23 | 2025-01-23 | 1 | 1 | 94 | 68 | 5 | 5 | 99 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 54 | 39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 113358.37 | 4061.76 | Unknown | 421.1 | 95.8 | 108779.71 | Unknown | 29243.01 | 113358.37 | -84115.36 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-07-25 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-09-03 | 82 | 58 | 2024-09-03 | 2024-09-03 | 1 | 1 | 1 | 1 | 156 | 112 | 157 | 113 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-11-13 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 129.47 | 44.75 | Unknown | Unknown | 0.24 | 84.48 | 3981 | 652.27 | 129.47 | 522.8 | Yes | N/A | N/A | 2023-10-18 | 2023-11-01 | 15 | 11 | 2023-11-01 | 2023-11-13 | 13 | 9 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2025-03-24 | 498 | 356 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-03-19 | Unknown | Unknown | 513 | 367 | 14 | 10 | 527 | 377 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -268 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-05-15 | 2023-06-03 | IOU Designed & Installed | N/A | No | N/A | -6.61 | -4.78 | Unknown | Unknown | Unknown | -1.83 | Unknown | 495.75 | -6.61 | 502.36 | Yes | N/A | N/A | 2023-04-24 | 2023-05-15 | 22 | 16 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-06-03 | 2 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-06-03 | 2023-06-12 | 10 | 6 | 2023-06-12 | 2023-06-12 | 1 | 1 | 24 | 17 | 11 | 7 | 35 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -124 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-20 | 2025-06-14 | IOU Designed & Installed | N/A | No | N/A | 77.68 | Unknown | Unknown | Unknown | Unknown | 77.68 | 3981 | 2339.38 | 77.68 | 2261.7 | Yes | N/A | N/A | 2024-09-10 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-24 | 35 | 25 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-06-14 | 264 | 189 | Unknown | Unknown | Unknown | Unknown | 2025-06-14 | 2025-06-25 | 12 | 8 | 2025-06-25 | 2025-06-25 | 1 | 1 | 264 | 189 | 48 | 34 | 312 | 223 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-10-16 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 47.71 | Unknown | Unknown | Unknown | Unknown | 47.71 | 3981 | 1634.63 | 47.71 | 1586.92 | Yes | N/A | N/A | 2024-07-31 | 2024-10-16 | 78 | 56 | 2024-10-16 | 2024-10-17 | 2 | 2 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-02-04 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-10 | 35 | 25 | 2025-03-10 | 2025-03-10 | 1 | 1 | 189 | 135 | 38 | 28 | 227 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-17 | 18 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | -2464.88 | 1033.18 | Unknown | 1404.04 | -5677 | 774.9 | Unknown | 5676.98 | -2464.88 | 8141.86 | Yes | N/A | N/A | 2023-07-12 | 2023-07-18 | 7 | 5 | 2023-07-18 | 2023-07-26 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | 2023-08-04 | 1 | 1 | 7 | 5 | 11 | 9 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | -227 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | -5.25 | -10.26 | Unknown | Unknown | Unknown | 5.01 | 3981 | 847.58 | -5.25 | 852.83 | Yes | N/A | N/A | 2023-03-16 | 2023-07-12 | 119 | 85 | 2023-07-12 | 2023-07-14 | 3 | 3 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2023-08-30 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-14 | 16 | 12 | 2023-09-14 | 2023-09-12 | Unknown | Unknown | 287 | 205 | 19 | 15 | 306 | 220 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -100 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 16697.13 | 3764.38 | Unknown | Unknown | 36.13 | 12896.62 | Unknown | 8225.4 | 16697.13 | -8471.73 | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-03-26 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-08 | 3 | 3 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-07-23 | 44 | 32 | 2024-07-23 | 2024-07-23 | 1 | 1 | 1 | 1 | 89 | 65 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-10 | 55 | 40 | No | 2023-06-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-30 | 2023-07-10 | IOU Designed & Installed | N/A | Yes | 195 | 1544.77 | -37.05 | Unknown | Unknown | Unknown | 1581.82 | Unknown | 513.58 | 1544.77 | -1031.19 | Yes | N/A | N/A | 2023-06-27 | 2024-01-08 | 196 | 140 | 2024-01-08 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-10 | 3 | 3 | 2023-06-30 | 2023-07-10 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-28 | 19 | 15 | 2023-07-28 | 2024-06-04 | 313 | 223 | 207 | 147 | 335 | 241 | 542 | 388 | Steps 2,3,5,6,7 | 194 | 138 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.75 | 9.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -404 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-28 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 4190.83 | 536.45 | Unknown | Unknown | 103.74 | 3550.64 | 3941 | 934.62 | 4190.83 | -3256.21 | Yes | N/A | N/A | 2024-03-21 | 2024-01-08 | Unknown | Unknown | 2024-01-08 | 2024-04-16 | 100 | 72 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-10-25 | 193 | 139 | Unknown | 2024-11-15 | Unknown | Unknown | 2024-10-25 | 2024-11-18 | 25 | 17 | 2024-11-18 | 2024-11-18 | 1 | 1 | 193 | 139 | 126 | 90 | 319 | 229 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | -286 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | 2881.81 | 477.78 | Unknown | 1381.95 | Unknown | 1022.08 | 3981 | 998.32 | 2881.81 | -1883.49 | Yes | N/A | N/A | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-08-28 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-08-31 | 4 | 4 | 2023-08-31 | 2023-08-31 | 1 | 1 | 15 | 11 | 6 | 6 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-19 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-25 | 2023-04-17 | IOU Designed & Installed | N/A | No | N/A | 972.72 | -20.2 | Unknown | Unknown | Unknown | 992.92 | Unknown | 341 | 972.72 | -631.72 | Yes | N/A | N/A | 2023-02-24 | 2023-02-27 | 4 | 2 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-04-17 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2023-06-12 | 57 | 41 | 2023-06-12 | 2023-06-12 | 1 | 1 | 54 | 38 | 58 | 42 | 112 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -183 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -641.7 | -18.74 | Unknown | Unknown | -666 | 43.04 | 90751 | 3264.7 | -641.7 | 3906.4 | Yes | N/A | N/A | 2022-11-08 | 2023-12-12 | 400 | 286 | 2023-12-12 | 2024-02-14 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-25 | 11 | 9 | 400 | 286 | 76 | 56 | 476 | 342 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 41.7 | Unknown | Unknown | Unknown | Unknown | 41.7 | Unknown | 1063.08 | 41.7 | 1021.38 | Yes | N/A | N/A | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2025-03-18 | 127 | 91 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 1 | 1 | 128 | 92 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 382 | 273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-04-18 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 4455.39 | 901.65 | Unknown | 117.05 | Unknown | 3436.69 | 21691.6 | 2538.59 | 4455.39 | -1916.8 | Yes | N/A | N/A | 2024-02-14 | 2024-04-18 | 65 | 47 | 2024-04-18 | 2024-08-29 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-27 | 36 | 26 | 2024-08-29 | 2024-11-06 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-16 | 5 | 3 | 2024-12-16 | 2024-12-16 | 1 | 1 | 135 | 97 | 176 | 126 | 311 | 223 | Steps 2,3,5,6,7 | 90 | 64 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -551 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 475.33 | 257.06 | Unknown | Unknown | Unknown | 218.27 | 3981 | 900.34 | 475.33 | 425.01 | Yes | N/A | N/A | 2024-04-17 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-04-17 | 86 | 62 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-07-03 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-08 | 6 | 4 | 2024-07-08 | 2024-07-08 | 1 | 1 | 78 | 56 | 93 | 67 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | 422.45 | 232.94 | Unknown | 41.6 | Unknown | 147.91 | Unknown | 149.62 | 422.45 | -272.83 | Yes | N/A | N/A | 2023-02-28 | 2023-04-13 | 45 | 33 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-06-28 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-06-29 | 2 | 2 | 2023-06-29 | 2023-06-29 | 1 | 1 | 122 | 88 | 3 | 3 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-08 | 199 | 143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 25.44 | -9.18 | Unknown | Unknown | Unknown | 34.62 | 3981 | 308.87 | 25.44 | 283.43 | Yes | N/A | N/A | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | 2024-03-22 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-04-24 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-26 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 390.22 | 122.45 | Unknown | Unknown | Unknown | 267.77 | 3981 | 1111 | 390.22 | 720.78 | Yes | N/A | N/A | 2024-02-22 | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2024-02-26 | 71 | 51 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-04-30 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-05-01 | 1 | 1 | 65 | 47 | 74 | 54 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | -250 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1156.89 | 1608.49 | Unknown | 305.71 | -1528 | 770.69 | Unknown | 1527.66 | 1156.89 | 370.77 | Yes | N/A | N/A | 2024-04-11 | 2024-05-14 | 34 | 24 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 34 | 24 | 1 | 1 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -1101 | -788 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 313.56 | 183.68 | Unknown | Unknown | Unknown | 129.88 | 26990 | 320.3 | 313.56 | 6.74 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-12-26 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-03 | 9 | 7 | 2024-01-03 | 2024-01-03 | 1 | 1 | 182 | 130 | 11 | 9 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-15 | 500 | 357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2023-06-30 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 0.48 | -6.11 | Unknown | Unknown | Unknown | 6.59 | 3981 | 961.89 | 0.48 | 961.41 | Yes | N/A | N/A | 2022-10-21 | 2023-06-27 | 250 | 178 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-11-17 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-27 | 11 | 7 | 2023-11-27 | 2023-11-27 | 1 | 1 | 391 | 279 | 12 | 8 | 403 | 287 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 388 | 277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -984.4 | 2559.84 | Unknown | 322.95 | -5033 | 1165.81 | Unknown | 5033.09 | -984.4 | 6017.49 | Yes | N/A | N/A | 2023-08-03 | 2023-12-12 | 132 | 94 | 2023-12-12 | 2024-03-04 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 132 | 94 | 85 | 61 | 217 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 3563.05 | 905.92 | Unknown | 154.59 | Unknown | 2502.54 | 3981 | 1477.32 | 3563.05 | -2085.73 | Yes | N/A | N/A | 2024-11-14 | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-14 | 11 | 9 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-03-18 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-03-25 | 8 | 6 | 2025-03-25 | 2025-03-25 | 1 | 1 | 125 | 89 | 20 | 16 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-14 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-21 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 723.56 | 244.9 | Unknown | Unknown | Unknown | 478.66 | 3981 | 800.65 | 723.56 | 77.09 | Yes | N/A | N/A | 2023-06-05 | 2023-06-22 | 18 | 14 | 2023-06-22 | 2023-06-29 | 8 | 6 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-12-12 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-02 | 22 | 16 | 2024-01-02 | 2024-01-02 | 1 | 1 | 192 | 138 | 31 | 23 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 183 | 183 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | 20 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -39.08 | 434.09 | Unknown | Unknown | -1609 | 1135.83 | Unknown | 1339.13 | -39.08 | 1378.21 | Yes | N/A | N/A | 2024-09-25 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-10-18 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-28 | 33 | 23 | 2024-10-18 | 2025-02-14 | 120 | 86 | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-06 | Unknown | Unknown | 120 | 86 | 143 | 103 | 263 | 189 | Steps 2,3,5,6,7 | 10 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 2137.58 | -44 | Unknown | Unknown | Unknown | 2181.58 | 3981 | 1651.64 | 2137.58 | -485.94 | Yes | N/A | N/A | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-02 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-27 | 26 | 18 | 2025-01-27 | 2025-01-27 | 1 | 1 | 17 | 13 | 28 | 20 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-14 | -121 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 830 | -27.09 | Unknown | Unknown | Unknown | 857.09 | Unknown | 861.77 | 830 | 31.77 | Yes | N/A | N/A | 2023-12-12 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | 2023-12-12 | 16 | 12 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-02-21 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-15 | 24 | 18 | 2024-03-15 | 2024-03-15 | 1 | 1 | 72 | 52 | 41 | 31 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-09-23 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 2130.73 | 596.98 | Unknown | 143.13 | Unknown | 1390.62 | 3981 | 1547.9 | 2130.73 | -582.83 | Yes | N/A | N/A | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | 2024-09-23 | 76 | 54 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-11 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-17 | 7 | 5 | 2024-10-17 | 2024-10-17 | 1 | 1 | 20 | 16 | 84 | 60 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-18 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 227.65 | -10.67 | Unknown | Unknown | 3.54 | 234.78 | 3981 | 646.14 | 227.65 | 418.49 | Yes | N/A | N/A | 2023-08-08 | 2023-09-11 | 35 | 25 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-03 | 23 | 17 | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-03 | 2023-11-28 | 57 | 41 | 2023-11-28 | 2023-11-28 | 1 | 1 | 58 | 42 | 59 | 43 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-01 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 1849.42 | 253.74 | Unknown | Unknown | 2.59 | 1593.09 | 3981 | 2503.07 | 1849.42 | 653.65 | Yes | N/A | N/A | 2024-07-31 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-10-22 | 63 | 45 | Unknown | 2025-03-07 | Unknown | Unknown | 2024-10-22 | 2024-10-28 | 7 | 5 | 2024-10-28 | 2024-10-28 | 1 | 1 | 63 | 45 | 9 | 7 | 72 | 52 | Steps 2,3,5,6,7 | 136 | 98 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 329.08 | 2170.99 | Unknown | 623.86 | -3595 | 1129.23 | Unknown | 3711.56 | 329.08 | 3382.48 | Yes | N/A | N/A | 2022-06-22 | 2024-01-12 | 570 | 408 | 2024-01-12 | 2024-07-03 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-07-30 | 161 | 115 | 570 | 408 | 335 | 239 | 905 | 647 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-04 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 19.69 | Unknown | Unknown | Unknown | Unknown | 19.69 | 3981 | 1161.62 | 19.69 | 1141.93 | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-15 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-13 | 30 | 22 | 2024-11-13 | 2024-11-13 | 1 | 1 | 17 | 13 | 32 | 24 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | 509 | 509 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-26 | 659 | 472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2024-04-24 | 2025-01-04 | IOU Designed & Installed | N/A | No | N/A | 62881.92 | 20477.01 | Unknown | 2242.59 | 195.45 | 39966.87 | 126159 | 70784.34 | 62881.92 | 7902.42 | Yes | N/A | N/A | 2022-07-18 | 2024-04-25 | 648 | 464 | 2024-04-25 | 2024-07-16 | 83 | 59 | 2024-04-24 | 2024-04-25 | 2 | 2 | 2024-07-12 | 2024-12-06 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2025-01-09 | 168 | 120 | 2025-01-04 | 2025-02-13 | 41 | 29 | 2025-02-13 | 2025-02-13 | 1 | 1 | 650 | 466 | 322 | 230 | 972 | 696 | Steps 2,3,5,6,7 | 88 | 62 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 139.1 | 139.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | -114 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 297.99 | -12.41 | Unknown | Unknown | Unknown | 310.4 | 3981 | 1004.61 | 297.99 | 706.62 | Yes | N/A | N/A | 2023-06-13 | 2023-06-14 | 2 | 2 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2023-12-11 | Unknown | Unknown | 2 | 2 | 0 | 0 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | -271 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | -4.18 | -12.39 | Unknown | Unknown | Unknown | 8.21 | Unknown | 1696.32 | -4.18 | 1700.5 | Yes | N/A | N/A | 2023-06-21 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-06-22 | 52 | 38 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-10 | 13 | 9 | 2023-07-10 | 2023-07-10 | 1 | 1 | 7 | 5 | 66 | 48 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-07 | 1024 | 731 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | 2024-10-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 39500.85 | 1102.24 | Unknown | 164.91 | 1161.88 | 37071.82 | 30040 | 15548.2 | 39500.85 | -23952.65 | Yes | N/A | N/A | 2023-01-23 | 2023-06-15 | 144 | 104 | 2023-06-15 | 2023-10-04 | 112 | 80 | 2023-06-22 | 2023-10-03 | 38 | 26 | 2023-08-23 | 2024-05-13 | 230 | 164 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-09-17 | 203 | 145 | 2024-10-10 | 2025-02-24 | 138 | 98 | 2025-02-24 | 2025-02-24 | 1 | 1 | 182 | 130 | 684 | 488 | 866 | 618 | Steps 2,3,5,6,7 | 145 | 103 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-19 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-01-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -10.21 | -9.5 | Unknown | Unknown | Unknown | -0.71 | Unknown | 98.41 | -10.21 | 108.62 | Yes | N/A | N/A | 2023-01-17 | 2023-02-10 | 25 | 19 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-08-30 | 1 | 1 | 25 | 19 | 1 | 1 | 26 | 20 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -532 | -381 | No | 2024-07-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | 2024-09-23 | IOU Designed & Installed | N/A | Yes | 30 | 511.34 | Unknown | Unknown | Unknown | 23.99 | 487.35 | 3981 | 2421.38 | 511.34 | 1910.04 | Yes | N/A | N/A | 2024-07-22 | 2024-08-17 | 27 | 20 | 2024-08-17 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-23 | 39 | 27 | Unknown | 2024-09-19 | Unknown | Unknown | 2024-09-23 | 2024-12-18 | 87 | 63 | 2024-12-18 | 2024-12-18 | 1 | 1 | 66 | 47 | 88 | 64 | 154 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -452 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 311.8 | 171.27 | Unknown | 16.29 | Unknown | 124.24 | Unknown | 163.83 | 311.8 | -147.97 | Yes | N/A | N/A | 2024-01-05 | 2023-10-23 | Unknown | Unknown | 2023-10-23 | 2024-01-29 | 99 | 71 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-05-23 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-07-18 | 57 | 41 | 2024-07-18 | 2024-07-18 | 1 | 1 | 116 | 84 | 157 | 113 | 273 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | -275 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-08 | 2024-09-02 | IOU Designed & Installed | N/A | No | N/A | 2651.27 | 809.28 | Unknown | Unknown | Unknown | 1841.99 | 3985 | 634.01 | 2651.27 | -2017.26 | Yes | N/A | N/A | 2023-09-07 | 2023-09-08 | 2 | 2 | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2024-09-02 | 361 | 257 | Unknown | Unknown | Unknown | Unknown | 2024-09-02 | 2024-09-04 | 3 | 3 | 2024-09-04 | 2024-09-04 | 1 | 1 | 363 | 259 | 5 | 5 | 368 | 264 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 161 | 116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 862.1 | -27.98 | Unknown | Unknown | Unknown | 890.08 | 4472 | 532.87 | 862.1 | -329.23 | Yes | N/A | N/A | 2024-01-17 | 2024-02-07 | 22 | 16 | 2024-02-07 | 2024-02-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-13 | 8 | 6 | 2024-02-12 | 2024-05-30 | 109 | 79 | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2024-06-10 | Unknown | Unknown | 131 | 95 | 14 | 10 | 145 | 105 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SD 1190-A2 CMR PA9 PH3 (E) | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 749 | 536 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | 2025-02-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 80034.23 | 10152.86 | Unknown | 123.33 | 5769.17 | 63988.87 | 0 | 30231.75 | 80034.23 | -49802.48 | Yes | N/A | N/A | 2022-04-27 | 2023-08-07 | 468 | 334 | 2023-08-07 | 2023-09-19 | 44 | 32 | 2023-08-07 | 2024-04-08 | 246 | 176 | 2023-09-19 | 2025-01-22 | 183 | 129 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-22 | 349 | 249 | 2025-02-05 | 2025-04-07 | 62 | 44 | 2025-04-07 | 2025-04-07 | 1 | 1 | 714 | 510 | 639 | 455 | 1353 | 965 | Steps 2,3,5,6,7 | 685 | 489 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | 220 | 159 | No | 2023-04-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-07-17 | IOU Designed & Installed | N/A | Yes | 33 | 1465.26 | -14.1 | Unknown | Unknown | 210.84 | 1268.52 | 3981 | 1101.33 | 1465.26 | -363.93 | Yes | N/A | N/A | 2023-02-13 | 2023-05-31 | 108 | 78 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-07-17 | 81 | 57 | Unknown | 2023-07-07 | Unknown | Unknown | 2023-07-17 | 2024-10-02 | 444 | 318 | 2024-10-02 | 2024-09-06 | Unknown | Unknown | 189 | 135 | 444 | 318 | 633 | 453 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | -504 | -361 | No | 2024-10-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-24 | 2025-04-03 | IOU Designed & Installed | N/A | Yes | 140 | 366.05 | -7.35 | Unknown | Unknown | Unknown | 373.4 | Unknown | 1899.99 | 366.05 | 1533.94 | Yes | N/A | N/A | 2024-10-22 | 2025-03-18 | 148 | 106 | 2025-03-18 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-04-03 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-23 | 21 | 15 | 2025-04-23 | 2025-04-23 | 1 | 1 | 310 | 222 | 22 | 16 | 332 | 238 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 325 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 454.09 | -12.73 | Unknown | Unknown | 24 | 442.82 | Unknown | 1958.21 | 454.09 | 1504.12 | Yes | N/A | N/A | 2023-07-17 | 2023-08-29 | 44 | 32 | 2023-08-29 | 2023-09-08 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2024-03-20 | 106 | 76 | 2023-09-08 | 2024-04-29 | 235 | 167 | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-05-06 | Unknown | Unknown | 279 | 199 | 117 | 85 | 396 | 284 | Steps 2,3,5,6,7 | 194 | 138 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-11-06 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | 0.71 | -9.57 | Unknown | Unknown | Unknown | 10.28 | 3981 | 24631.05 | 0.71 | 24630.34 | Yes | N/A | N/A | 2023-10-18 | 2023-11-01 | 15 | 11 | 2023-11-01 | 2023-11-06 | 6 | 4 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-30 | 11 | 9 | 2023-11-30 | 2023-11-30 | 1 | 1 | 30 | 22 | 18 | 14 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | 2024-02-29 | IOU Designed & Installed | N/A | No | N/A | 719.93 | -19.92 | Unknown | Unknown | Unknown | 739.85 | 3981 | 601.1 | 719.93 | -118.83 | Yes | N/A | N/A | 2023-09-13 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-09-13 | 50 | 36 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2024-02-29 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-14 | 15 | 11 | 2024-03-14 | 2024-03-07 | Unknown | Unknown | 170 | 122 | 65 | 47 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | 787 | 562 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 15517.41 | 286.62 | Unknown | Unknown | Unknown | 15230.79 | Unknown | 2239.25 | 15517.41 | -13278.16 | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-02-21 | 29 | 21 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-02-19 | 2025-02-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-24 | 20 | 14 | 2025-03-24 | 2025-03-24 | 1 | 1 | 2 | 2 | 51 | 37 | 53 | 39 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | 78.13 | Unknown | Unknown | Unknown | Unknown | 78.13 | Unknown | 1886.03 | 78.13 | 1807.9 | Yes | N/A | N/A | 2024-09-20 | 2024-09-25 | 6 | 4 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-03-21 | 173 | 125 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-26 | 6 | 4 | 2025-03-26 | 2025-03-26 | 1 | 1 | 179 | 129 | 8 | 6 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -528 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | 1690.97 | 224.5 | Unknown | Unknown | Unknown | 1466.47 | 3981 | 1079.76 | 1690.97 | -611.21 | Yes | N/A | N/A | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-25 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-11-01 | 8 | 6 | 2023-11-01 | 2023-11-01 | 1 | 1 | 43 | 31 | 10 | 8 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 1380.47 | -14.03 | Unknown | Unknown | 13.52 | 1380.98 | 3981 | 1158.4 | 1380.47 | -222.07 | Yes | N/A | N/A | 2024-10-01 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-11-01 | 50 | 36 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-03-27 | 147 | 105 | Unknown | 2025-03-18 | Unknown | Unknown | 2025-03-27 | 2025-04-02 | 7 | 5 | 2025-04-02 | 2025-04-01 | Unknown | Unknown | 147 | 105 | 57 | 41 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | Unknown | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 1483.7 | -30.6 | Unknown | Unknown | Unknown | 1514.3 | 3981 | 2056.84 | 1483.7 | 573.14 | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-21 | 15 | 11 | 2024-11-21 | 2024-11-21 | 1 | 1 | 5 | 5 | 17 | 13 | 22 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | DULZURA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | 437 | 314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 2442.59 | 656 | Unknown | Unknown | Unknown | 1786.59 | 3381 | 865.75 | 2442.59 | -1576.84 | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | 2023-07-27 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2024-10-21 | 453 | 323 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-02-28 | 4 | 4 | 2025-02-28 | 2025-02-28 | 1 | 1 | 454 | 324 | 106 | 78 | 560 | 402 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | -328 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-03 | 2023-02-23 | IOU Designed & Installed | N/A | No | N/A | -3.78 | -11.14 | Unknown | Unknown | Unknown | 7.36 | 3981 | 777.72 | -3.78 | 781.5 | Yes | N/A | N/A | 2023-02-01 | 2023-02-07 | 7 | 5 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | 2023-02-23 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-06-13 | 111 | 79 | 2023-06-13 | 2023-03-03 | Unknown | Unknown | 24 | 18 | 111 | 79 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -558 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 693.45 | 252.46 | Unknown | Unknown | Unknown | 440.99 | 3981 | 924.47 | 693.45 | 231.02 | Yes | N/A | N/A | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-09-27 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-02 | 6 | 4 | 2023-10-02 | 2023-10-02 | 1 | 1 | 37 | 27 | 8 | 6 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 64524.2 | 64524.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-03-14 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1843.23 | -11.31 | Unknown | Unknown | -2496 | 664.08 | 3981 | 1134.98 | -1843.23 | 2978.21 | Yes | N/A | N/A | 2023-05-04 | 2023-06-06 | 34 | 24 | 2023-06-06 | 2023-06-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-08-08 | 51 | 37 | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2023-08-25 | Unknown | Unknown | 85 | 61 | 14 | 10 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -481 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 3.17 | -2.83 | Unknown | Unknown | Unknown | 6 | 3981 | 1021.24 | 3.17 | 1018.07 | Yes | N/A | N/A | 2024-04-03 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-05-12 | 154 | 110 | 2024-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-12 | 2024-05-22 | 11 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-10 | 20 | 14 | 2024-06-10 | 2024-06-10 | 1 | 1 | 11 | 8 | 175 | 125 | 186 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -162 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-03-22 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 8241.68 | 272.1 | Unknown | Unknown | -477.92 | 8447.5 | 3981 | 2736.76 | 8241.68 | -5504.92 | Yes | N/A | N/A | 2023-12-05 | 2023-12-19 | 15 | 11 | 2023-12-19 | 2024-07-02 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-31 | 30 | 22 | Unknown | 2024-07-29 | Unknown | Unknown | 2024-08-08 | 2024-09-04 | 28 | 20 | 2024-09-04 | 2024-08-23 | Unknown | Unknown | 45 | 33 | 225 | 161 | 270 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | 287 | 206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-12-12 | 2025-06-15 | IOU Designed & Installed | N/A | No | N/A | 3044.05 | Unknown | Unknown | Unknown | 102.98 | 2941.07 | 23886 | 1331.88 | 3044.05 | -1712.17 | Yes | N/A | N/A | 2023-10-17 | 2023-12-19 | 64 | 46 | 2023-12-19 | 2024-05-20 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-09 | 19 | 13 | 2024-05-20 | 2025-06-09 | 386 | 276 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-06-15 | 2025-06-16 | 2 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 450 | 322 | 176 | 125 | 626 | 447 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-30 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 507.56 | -10.2 | Unknown | Unknown | Unknown | 517.76 | Unknown | 1496.46 | 507.56 | 988.9 | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-02 | 4 | 4 | 2024-07-30 | 2025-04-18 | 263 | 189 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-22 | 5 | 3 | 2025-04-22 | 2025-04-22 | 1 | 1 | 265 | 191 | 11 | 9 | 276 | 200 | Steps 2,3,5,6,7 | 3 | 3 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 118.25 | 118.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-26 | -333 | -238 | No | 2023-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | 2023-08-08 | IOU Designed & Installed | N/A | Yes | 75 | -3.79 | -11.13 | Unknown | Unknown | Unknown | 7.34 | Unknown | 745.24 | -3.79 | 749.03 | Yes | N/A | N/A | 2023-02-16 | 2023-05-02 | 76 | 54 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2023-08-08 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-09-28 | 52 | 38 | 2023-09-28 | 2023-09-28 | 1 | 1 | 250 | 178 | 53 | 39 | 303 | 217 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-28 | -276 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.21 | -3.52 | Unknown | Unknown | Unknown | 2.31 | 3981 | 400.59 | -1.21 | 401.8 | Yes | N/A | N/A | 2023-02-24 | 2023-03-28 | 33 | 23 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-04-27 | Unknown | Unknown | 33 | 23 | 0 | 0 | 33 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 615 | 615 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-18 | -449 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | -4.85 | -3.93 | Unknown | Unknown | Unknown | -0.92 | 3981 | 881.94 | -4.85 | 886.79 | Yes | N/A | N/A | 2024-01-23 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2024-01-24 | 188 | 134 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-03-14 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-26 | 13 | 9 | 2024-03-26 | 2024-03-26 | 1 | 1 | 52 | 38 | 202 | 144 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-20 | 1211 | 866 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | -8.06 | -6.5 | Unknown | Unknown | Unknown | -1.56 | Unknown | 228.88 | -8.06 | 236.94 | Yes | N/A | N/A | 2023-12-13 | 2023-12-13 | 1 | 1 | 2023-12-13 | 2023-12-13 | 1 | 1 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-02-28 | 78 | 56 | Unknown | 2024-02-29 | Unknown | Unknown | 2024-02-28 | 2024-03-15 | 17 | 13 | 2024-03-15 | 2024-03-15 | 1 | 1 | 79 | 57 | 19 | 15 | 98 | 72 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | -72 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-01-12 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 172.41 | -16.65 | Unknown | Unknown | Unknown | 189.06 | 3981 | 835.78 | 172.41 | 663.37 | Yes | N/A | N/A | 2023-10-16 | 2024-01-10 | 87 | 63 | 2024-01-10 | 2024-01-18 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-03-15 | 58 | 42 | 2024-03-15 | 2024-03-15 | 1 | 1 | 87 | 63 | 68 | 50 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-27 | 37 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2134.36 | 572.48 | Unknown | 226.86 | 62.34 | 1272.68 | 3981 | 161.21 | 2134.36 | -1973.15 | Yes | N/A | N/A | 2024-01-25 | 2024-03-28 | 64 | 46 | 2024-03-28 | 2024-03-29 | 2 | 2 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-03 | Unknown | Unknown | 64 | 46 | 2 | 2 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 287 | 206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 20.22 | Unknown | Unknown | Unknown | Unknown | 20.22 | 3981 | 823.35 | 20.22 | 803.13 | Yes | N/A | N/A | 2024-05-01 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2024-05-01 | 146 | 104 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-25 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-08-14 | 51 | 37 | 2024-08-14 | 2024-08-15 | 2 | 2 | 55 | 39 | 199 | 143 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-09 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | 16.06 | -14.06 | Unknown | Unknown | Unknown | 30.12 | 3981 | 951.47 | 16.06 | 935.41 | Yes | N/A | N/A | 2024-01-19 | 2024-02-06 | 19 | 13 | 2024-02-06 | 2024-02-08 | 3 | 3 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-22 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-15 | 23 | 17 | 2024-03-15 | 2024-03-15 | 1 | 1 | 33 | 23 | 27 | 21 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-21 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 12.07 | -10.71 | Unknown | Unknown | Unknown | 22.78 | 3941 | 804.02 | 12.07 | 791.95 | Yes | N/A | N/A | 2024-01-11 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-01-11 | 31 | 23 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-04-19 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-05-06 | 18 | 12 | 2024-05-06 | 2024-05-20 | 15 | 11 | 100 | 72 | 64 | 46 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | 286 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 700.4 | Unknown | Unknown | Unknown | -7979 | 8679.4 | 0 | 11671.93 | 700.4 | 10971.53 | Yes | N/A | N/A | 2024-01-09 | 2024-03-12 | 64 | 46 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-21 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-12 | 50 | 36 | 2025-03-12 | 2025-03-12 | 1 | 1 | 64 | 46 | 93 | 67 | 157 | 113 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | 42 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 7670.96 | 465.4 | Unknown | 56.21 | Unknown | 7149.35 | Unknown | 2571.75 | 7670.96 | -5099.21 | Yes | N/A | N/A | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-10-16 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-12 | 20 | 14 | 2024-11-12 | 2024-11-12 | 1 | 1 | 1 | 1 | 44 | 32 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 1130.43 | 170.13 | Unknown | Unknown | Unknown | 960.3 | Unknown | 3742.27 | 1130.43 | 2611.84 | Yes | N/A | N/A | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | 2025-01-21 | 30 | 22 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-24 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 15 | 11 | 32 | 24 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 738 | 529 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2024-01-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 79508.78 | 19948.95 | Unknown | Unknown | 249.84 | 59309.99 | 143415 | 72222.67 | 79508.78 | -7286.11 | Yes | N/A | N/A | 2022-09-01 | 2023-04-04 | 216 | 154 | 2023-04-04 | 2023-04-12 | 9 | 7 | 2023-03-03 | 2023-07-21 | 35 | 23 | 2023-04-10 | 2023-06-20 | 17 | 13 | 2023-04-21 | Unknown | Unknown | Unknown | 2023-04-21 | 2023-12-21 | 245 | 175 | 2024-01-09 | 2024-02-09 | 32 | 24 | 2024-02-09 | 2024-02-09 | 1 | 1 | 251 | 177 | 304 | 220 | 555 | 397 | Steps 2,3,5,6,7 | 202 | 144 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 615.68 | -12.3 | Unknown | Unknown | 18.05 | 609.93 | 3981 | 521.42 | 615.68 | -94.26 | Yes | N/A | N/A | 2023-03-06 | 2023-03-24 | 19 | 15 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 19 | 15 | 1 | 1 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 350 | 251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2024-05-07 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 26799.88 | 5258.24 | Unknown | Unknown | 4.21 | 21537.43 | 82573 | 30921.42 | 26799.88 | 4121.54 | Yes | N/A | N/A | 2023-09-07 | 2023-10-03 | 27 | 19 | 2023-10-03 | 2024-05-30 | 241 | 173 | 2024-01-22 | 2024-05-29 | 129 | 93 | 2024-05-15 | 2025-03-14 | -1 | -3 | 2024-05-30 | 2025-02-11 | 258 | 184 | 2024-06-05 | 2025-02-11 | 252 | 180 | 2025-02-27 | 2025-03-19 | 21 | 15 | 2025-03-19 | 2025-03-17 | Unknown | Unknown | 414 | 296 | 513 | 365 | 927 | 661 | Steps 2,3,5,6,7 | 682 | 488 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 804.51 | 252.46 | Unknown | Unknown | Unknown | 552.05 | Unknown | 923.77 | 804.51 | 119.26 | Yes | N/A | N/A | 2024-02-09 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-02-09 | 156 | 112 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-13 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-18 | 37 | 27 | 2024-04-18 | 2024-04-18 | 1 | 1 | 34 | 24 | 194 | 140 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | La Mesa | LA MESA | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 310 | 223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2175.99 | Unknown | Unknown | Unknown | -9892 | 7716.01 | 0 | 10347.08 | -2175.99 | 12523.07 | Yes | N/A | N/A | 2023-04-10 | 2023-03-22 | Unknown | Unknown | 2023-03-22 | 2024-05-29 | 435 | 311 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2024-07-24 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1 | 1 | 0 | 0 | 480 | 344 | 480 | 344 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | -467 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 217.2 | 122.45 | Unknown | Unknown | Unknown | 94.75 | Unknown | 153.83 | 217.2 | -63.37 | Yes | N/A | N/A | 2023-08-16 | 2023-08-30 | 15 | 11 | 2023-08-30 | 2023-09-05 | 7 | 5 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-10-12 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2024-01-08 | 89 | 63 | 2024-01-08 | 2024-01-08 | 1 | 1 | 59 | 43 | 97 | 69 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | -305 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-27 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 1522.13 | 409.84 | Unknown | Unknown | Unknown | 1112.29 | 0 | 1886.69 | 1522.13 | 364.56 | Yes | N/A | N/A | 2024-06-14 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-27 | 25 | 19 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2025-06-03 | 342 | 244 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 342 | 244 | 27 | 21 | 369 | 265 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-20 | 101 | 74 | No | 2022-12-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | 2023-03-23 | IOU Designed & Installed | N/A | Yes | 53 | 1659.18 | -12.84 | Unknown | Unknown | 16.01 | 1656.01 | 3981 | 1233.03 | 1659.18 | -426.15 | Yes | N/A | N/A | 2022-12-12 | 2023-02-03 | 54 | 40 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-03-23 | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | 2023-03-23 | 2023-04-08 | 17 | 12 | 2023-04-08 | 2023-03-31 | Unknown | Unknown | 54 | 40 | 17 | 12 | 71 | 52 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-04-16 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 18633.44 | 1789.04 | Unknown | 563.37 | 67.74 | 16213.29 | 3981 | 786.67 | 18633.44 | -17846.77 | Yes | N/A | N/A | 2024-03-14 | 2024-04-16 | 34 | 24 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-16 | 46 | 34 | 2024-08-16 | 2024-08-16 | 1 | 1 | 34 | 24 | 47 | 35 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -598.29 | 1366.29 | Unknown | 61.86 | -2691 | 664.56 | Unknown | 2589.42 | -598.29 | 3187.71 | Yes | N/A | N/A | 2024-03-04 | 2024-03-04 | 1 | 1 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-26 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 1362.35 | Unknown | Unknown | Unknown | 11.08 | 1351.27 | 3981 | 1211.76 | 1362.35 | -150.59 | Yes | N/A | N/A | 2024-06-21 | 2024-07-16 | 26 | 18 | 2024-07-16 | 2024-07-22 | 7 | 5 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-10-09 | 80 | 58 | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-09 | 2024-10-29 | 21 | 15 | 2024-10-29 | 2024-10-29 | 1 | 1 | 106 | 76 | 29 | 21 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-23 | 769 | 550 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-28 | 2022-04-28 | 2025-06-02 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 128761.18 | 31873.67 | Unknown | Unknown | 2033.23 | 94854.28 | 329291 | 161013.11 | 128761.18 | 32251.93 | Yes | N/A | N/A | 2022-04-28 | 2023-10-06 | 527 | 377 | 2023-10-06 | 2024-02-13 | 131 | 93 | 2023-10-16 | 2024-02-08 | 62 | 46 | 2024-02-08 | 2024-03-11 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2025-07-30 | 451 | 323 | 2025-06-02 | 2025-06-30 | 29 | 21 | 2025-06-30 | 2025-06-30 | 1 | 1 | 589 | 423 | 645 | 461 | 1234 | 884 | Steps 2,3,5,6,7 | 178 | 128 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | 173 | 124 | No | 2023-03-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-04 | 2023-03-07 | 2024-06-24 | IOU Designed & Installed | N/A | Yes | 476 | 20.22 | -15.6 | Unknown | Unknown | Unknown | 35.82 | 3941 | 805.01 | 20.22 | 784.79 | Yes | N/A | N/A | 2023-03-04 | 2024-06-24 | 479 | 341 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2024-06-24 | 476 | 340 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-18 | 25 | 19 | 2024-07-18 | 2024-07-17 | Unknown | Unknown | 955 | 681 | 25 | 19 | 980 | 700 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-01 | 1039 | 742 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-16 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1386.24 | Unknown | Unknown | Unknown | Unknown | 1386.24 | 3981 | 1081.8 | 1386.24 | -304.44 | Yes | N/A | N/A | 2022-05-16 | 2023-07-13 | 424 | 304 | 2023-07-13 | 2023-07-24 | 12 | 8 | 2023-07-18 | 2023-07-21 | 4 | 4 | 2023-07-21 | 2025-04-22 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 428 | 308 | 20 | 14 | 448 | 322 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 186 | 186 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-16 | 446 | 319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 632.64 | -9.76 | Unknown | Unknown | 5.51 | 636.89 | 3885 | 376.32 | 632.64 | -256.32 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2024-05-08 | 416 | 298 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-07 | Unknown | Unknown | 417 | 299 | 1 | 1 | 418 | 300 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | 389 | 278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 2707.05 | 1630.08 | Unknown | Unknown | Unknown | 1076.97 | 0 | 153.83 | 2707.05 | -2553.22 | Yes | N/A | N/A | 2023-07-31 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2023-08-25 | 92 | 66 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2025-06-11 | 657 | 469 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | 2025-06-11 | 1 | 1 | 657 | 469 | 94 | 68 | 751 | 537 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | 265 | 190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 18953.32 | 2542.55 | Unknown | Unknown | -1026.68 | 17437.45 | 7962 | 2300.41 | 18953.32 | -16652.91 | Yes | N/A | N/A | 2024-04-18 | 2024-04-23 | 6 | 4 | 2024-04-23 | 2024-08-29 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2025-03-27 | 211 | 151 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-02-20 | 2025-05-05 | 75 | 53 | 2025-05-05 | 2025-03-27 | Unknown | Unknown | 217 | 155 | 204 | 146 | 421 | 301 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-24 | -283 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1330.79 | 1998.62 | Unknown | 450.52 | -2031 | 912.65 | Unknown | 2031.4 | 1330.79 | 700.61 | Yes | N/A | N/A | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | EN 1167-D1 (E) | N/A | 19.2 | 19.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-09-26 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 855.63 | Unknown | Unknown | Unknown | 15.04 | 840.59 | 3913.61 | 3845.63 | 855.63 | 2990 | Yes | N/A | N/A | 2024-07-10 | 2024-10-01 | 84 | 60 | 2024-10-01 | 2025-04-04 | 186 | 134 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-10 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-12 | 2025-05-21 | 10 | 8 | 2025-05-21 | 2025-05-21 | 1 | 1 | 84 | 60 | 201 | 147 | 285 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | -8.46 | -6.86 | Unknown | Unknown | Unknown | -1.6 | Unknown | 163.83 | -8.46 | 172.29 | Yes | N/A | N/A | 2024-02-05 | 2024-02-12 | 8 | 6 | 2024-02-12 | 2024-02-14 | 3 | 3 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-02-16 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-15 | 29 | 21 | 2024-03-15 | 2024-03-15 | 1 | 1 | 11 | 9 | 33 | 25 | 44 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-06 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-29 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 923.05 | Unknown | Unknown | Unknown | 5.97 | 917.08 | Unknown | 1270.28 | 923.05 | 347.23 | Yes | N/A | N/A | 2025-01-23 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-02-11 | 22 | 16 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-12 | 2025-03-05 | 22 | 16 | 2025-03-05 | 2025-03-05 | 1 | 1 | 1 | 1 | 45 | 33 | 46 | 34 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 532.49 | -10.7 | Unknown | Unknown | Unknown | 543.19 | 3981 | 1594.42 | 532.49 | 1061.93 | Yes | N/A | N/A | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-27 | 4 | 4 | 2025-03-21 | 2025-03-26 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-05-07 | 43 | 31 | 2025-05-07 | 2025-05-07 | 1 | 1 | 7 | 5 | 49 | 37 | 56 | 42 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 287.1 | 287.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | -556 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-12-20 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 1009.36 | 257.74 | Unknown | Unknown | Unknown | 751.62 | 3981 | 1985.87 | 1009.36 | 976.51 | Yes | N/A | N/A | 2024-11-26 | 2024-11-26 | 1 | 1 | 2024-11-26 | 2024-11-26 | 1 | 1 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-28 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-13 | 17 | 13 | 2025-02-13 | 2025-02-13 | 1 | 1 | 41 | 29 | 19 | 15 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 183.25 | 183.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-14 | 419 | 300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 4732.07 | -42.53 | Unknown | Unknown | 651.26 | 4123.34 | 3981 | 723.4 | 4732.07 | -4008.67 | Yes | N/A | N/A | 2023-03-06 | 2023-03-10 | 5 | 5 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2024-07-15 | 494 | 352 | Unknown | 2024-07-12 | Unknown | Unknown | 2024-07-15 | 2024-08-01 | 18 | 14 | 2024-08-01 | 2024-08-06 | 6 | 4 | 499 | 357 | 24 | 18 | 523 | 375 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 908.97 | 115.05 | Unknown | 58.96 | 0.77 | 734.19 | 3981 | 2241.84 | 908.97 | 1332.87 | Yes | N/A | N/A | 2024-01-10 | 2024-01-12 | 3 | 3 | 2024-01-12 | 2024-02-05 | 25 | 17 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 3 | 3 | 26 | 18 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | 136000 | 136000 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-05-31 | 705 | 504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2024-01-08 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 17222.22 | 748.96 | Unknown | Unknown | 120.52 | 16352.74 | 39341 | 24314.19 | 17222.22 | 7091.97 | Yes | N/A | N/A | 2022-11-22 | 2023-04-06 | 136 | 98 | 2023-04-06 | 2024-07-24 | 476 | 340 | 2024-01-24 | 2025-02-18 | 2 | 2 | 2024-07-19 | 2024-10-28 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-03-12 | 51 | 37 | 2025-03-24 | 2025-05-05 | 43 | 31 | 2025-05-05 | 2025-05-05 | 1 | 1 | 138 | 100 | 673 | 481 | 811 | 581 | Steps 2,3,5,6,7 | 396 | 282 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 97077.56 | 13241.7 | Unknown | 912.03 | 702.42 | 82221.41 | 594807.78 | 25033.28 | 97077.56 | -72044.28 | Yes | N/A | N/A | 2024-03-05 | 2024-05-21 | 78 | 56 | 2024-05-21 | 2024-08-29 | 101 | 73 | 2024-03-25 | 2024-06-18 | 1 | 1 | 2024-05-14 | 2024-09-03 | 28 | 20 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-13 | 45 | 33 | 2024-11-13 | 2024-11-13 | 1 | 1 | 79 | 57 | 175 | 127 | 254 | 184 | Steps 2,3,5,6,7 | 197 | 141 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | -694 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 4439.37 | 1082.9 | Unknown | Unknown | Unknown | 3356.47 | Unknown | 2263.16 | 4439.37 | -2176.21 | Yes | N/A | N/A | 2025-05-16 | 2025-05-16 | 1 | 1 | 2025-05-16 | 2025-05-16 | 1 | 1 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-13 | 23 | 17 | 2025-06-13 | 2025-06-13 | 1 | 1 | 8 | 6 | 25 | 19 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 13.98 | Unknown | Unknown | Unknown | Unknown | 13.98 | Unknown | 186.09 | 13.98 | 172.11 | Yes | N/A | N/A | 2024-07-02 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-07-02 | 43 | 31 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-02 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-20 | 19 | 13 | 2024-08-20 | 2024-08-20 | 1 | 1 | 32 | 24 | 63 | 45 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-10 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | Unknown | 2023-03-29 | IOU Designed & Installed | N/A | No | N/A | 485.71 | -20.56 | Unknown | Unknown | Unknown | 506.27 | 3885 | 794.05 | 485.71 | 308.34 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-03-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-04-08 | 11 | 8 | 2023-04-08 | 2023-04-08 | 1 | 0 | 44 | 32 | 12 | 8 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -443 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-12 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 1040.5 | Unknown | Unknown | Unknown | Unknown | 1040.5 | 3981 | 1323.97 | 1040.5 | 283.47 | Yes | N/A | N/A | 2024-09-11 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-09-11 | 142 | 102 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-11-08 | 58 | 42 | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-08 | 2024-12-13 | 36 | 26 | 2024-12-13 | 2024-12-13 | 1 | 1 | 58 | 42 | 179 | 129 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 7.48 | Unknown | Unknown | Unknown | Unknown | 7.48 | Unknown | 186.52 | 7.48 | 179.04 | Yes | N/A | N/A | 2024-08-27 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-27 | 29 | 21 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-08-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-11 | 15 | 11 | 2024-09-11 | 2024-09-11 | 1 | 1 | 2 | 2 | 45 | 33 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | BONITA | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-28 | 380 | 271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.5 | -7 | Unknown | Unknown | Unknown | 7.5 | Unknown | 284.51 | 0.5 | 284.01 | Yes | N/A | N/A | 2023-10-18 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-11-29 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 0 | 0 | 46 | 34 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 221.05 | 221.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-01 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | -8.69 | -6.56 | Unknown | Unknown | Unknown | -2.13 | 3981 | 810.31 | -8.69 | 819 | Yes | N/A | N/A | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-11-21 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-12-14 | 24 | 18 | 2023-12-14 | 2023-12-04 | Unknown | Unknown | 83 | 59 | 25 | 19 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 85 | 85 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2112.94 | Unknown | Unknown | Unknown | 5.57 | 2107.37 | 3981 | 1396.94 | 2112.94 | -716 | Yes | N/A | N/A | 2025-03-04 | 2025-04-04 | 32 | 24 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-09 | 1 | 1 | 32 | 24 | 2 | 2 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -135 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 58.58 | -25.01 | Unknown | Unknown | -797.22 | 880.81 | 3981 | 1404.06 | 58.58 | 1345.48 | Yes | N/A | N/A | 2023-04-20 | 2023-05-01 | 12 | 8 | 2023-05-01 | 2023-05-16 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-09-19 | 127 | 91 | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-09-19 | Unknown | Unknown | 139 | 99 | 16 | 12 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-06 | 2024-07-06 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 150.12 | Unknown | Unknown | Unknown | -637.99 | 788.11 | Unknown | 625.86 | 150.12 | 475.74 | Yes | N/A | N/A | 2024-07-06 | 2024-07-24 | 19 | 13 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | 2024-08-13 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-07 | 56 | 40 | Unknown | 2024-08-26 | Unknown | Unknown | 2024-10-07 | 2024-10-10 | 4 | 4 | 2024-10-10 | 2024-10-10 | 1 | 1 | 96 | 68 | 6 | 6 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-10-09 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 514.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-10-09 | 14 | 10 | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-24 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-06 | 14 | 10 | 2023-11-06 | 2023-11-06 | 1 | 1 | 30 | 22 | 16 | 12 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-12 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1098.04 | -9.51 | Unknown | Unknown | Unknown | 1107.55 | 3981 | 906.84 | 1098.04 | -191.2 | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | -211 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-06-20 | IOU Designed & Installed | N/A | No | N/A | 199.85 | -10.4 | Unknown | Unknown | -427 | 637.25 | Unknown | 647.76 | 199.85 | 447.91 | Yes | N/A | N/A | 2023-03-01 | 2023-04-14 | 45 | 33 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-06-20 | 44 | 32 | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-20 | 2023-06-23 | 4 | 4 | 2023-06-23 | 2023-06-23 | 1 | 1 | 89 | 65 | 5 | 5 | 94 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-30 | 468 | 335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-12 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 12562.92 | -258.83 | Unknown | Unknown | -516.76 | 13338.51 | Unknown | 672.53 | 12562.92 | -11890.39 | Yes | N/A | N/A | 2023-06-12 | 2023-10-03 | 114 | 82 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-03-19 | 2024-06-06 | 80 | 58 | Unknown | 2024-05-07 | Unknown | Unknown | 2024-06-06 | 2024-07-10 | 35 | 25 | 2024-07-10 | 2024-07-10 | 1 | 1 | 194 | 140 | 37 | 27 | 231 | 167 | Steps 2,3,5,6,7 | 56 | 40 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -453 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | -18.49 | -14.86 | Unknown | Unknown | Unknown | -3.63 | Unknown | 153.83 | -18.49 | 172.32 | Yes | N/A | N/A | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-11-10 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-27 | 18 | 12 | 2023-11-27 | 2023-11-27 | 1 | 1 | 94 | 68 | 20 | 14 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-21 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1162.65 | Unknown | Unknown | Unknown | 13.97 | 1148.68 | 3885 | 1106.45 | 1162.65 | -56.2 | Yes | N/A | N/A | 2024-02-01 | 2024-07-29 | 180 | 128 | 2024-07-29 | 2024-08-29 | 32 | 24 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2024-12-05 | 1 | 1 | 180 | 128 | 33 | 25 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-15 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | -5866.5 | 264.1 | Unknown | 14.66 | -6279 | 133.74 | Unknown | 6279.48 | -5866.5 | 12145.98 | Yes | N/A | N/A | 2024-07-12 | 2024-07-30 | 19 | 13 | 2024-07-30 | 2024-08-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-08 | 3 | 3 | 2024-08-08 | 2024-08-08 | 1 | 1 | 21 | 15 | 13 | 11 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-16 | 1770 | 1265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 3014.22 | 884.12 | Unknown | 123.95 | Unknown | 2006.15 | 0 | 983.97 | 3014.22 | -2030.25 | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2024-08-19 | 461 | 329 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-20 | 2 | 2 | 2024-08-20 | 2024-08-20 | 1 | 1 | 462 | 330 | 3 | 3 | 465 | 333 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | La Jolla | N/A | 66303 | 66303 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-19 | 136 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2024-11-29 | IOU Designed & Installed | N/A | No | N/A | 6543.86 | 2565.17 | Unknown | 524.76 | 11.85 | 3442.08 | 0 | 3424.25 | 6543.86 | -3119.61 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | 2023-03-02 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-03-02 | 2 | 2 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-29 | 2024-12-02 | 4 | 2 | 2024-12-02 | 2024-12-02 | 1 | 1 | 1 | 1 | 24 | 18 | 25 | 19 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-21 | -40 | -29 | No | 2022-12-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-01 | 2022-12-02 | Unknown | IOU Designed & Installed | N/A | Yes | 127 | 500.3 | -4.33 | Unknown | Unknown | Unknown | 504.63 | 3241 | 708.23 | 500.3 | 207.93 | Yes | N/A | N/A | 2022-12-01 | 2023-04-07 | 128 | 92 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-05-12 | Unknown | Unknown | 128 | 92 | 0 | 0 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | El Cajon | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 1397.73 | 447.3 | Unknown | Unknown | 76.14 | 874.29 | 0 | 2311.88 | 1397.73 | 914.15 | Yes | N/A | N/A | 2023-12-19 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2023-12-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2025-03-14 | 445 | 319 | 2025-03-14 | 2025-03-14 | 1 | 1 | 8 | 6 | 446 | 320 | 454 | 326 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 187.75 | 187.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -121 | -88 | No | 2024-05-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | Yes | 11 | -12.93 | -44.26 | Unknown | Unknown | -468 | 499.33 | 3981 | 1840.35 | -12.93 | 1853.28 | Yes | N/A | N/A | 2023-10-16 | 2024-05-31 | 229 | 165 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | 2024-10-02 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 354 | 254 | 2 | 2 | 356 | 256 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 190.1 | 190.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | -499 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 4472.82 | 847.22 | Unknown | 473.21 | 47.26 | 3105.13 | 3981 | 1249.11 | 4472.82 | -3223.71 | Yes | N/A | N/A | 2024-05-17 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-05-17 | 103 | 75 | 2024-05-17 | 2024-05-21 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-10-24 | 161 | 115 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-24 | 2024-11-01 | 9 | 7 | 2024-11-01 | 2024-11-01 | 1 | 1 | 166 | 118 | 113 | 83 | 279 | 201 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 31.62 | Unknown | Unknown | Unknown | Unknown | 31.62 | 3981 | 1896.63 | 31.62 | 1865.01 | Yes | N/A | N/A | 2024-08-26 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-08-27 | 35 | 25 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-31 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-11 | 12 | 8 | 2024-11-11 | 2024-11-11 | 1 | 1 | 66 | 48 | 48 | 34 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-28 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | -20.44 | -13.23 | Unknown | Unknown | Unknown | -7.21 | Unknown | 996.66 | -20.44 | 1017.1 | Yes | N/A | N/A | 2025-01-30 | 2025-02-04 | 6 | 4 | 2025-02-04 | 2025-02-28 | 25 | 19 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-04-07 | 34 | 24 | 2025-04-07 | 2025-04-07 | 1 | 1 | 12 | 8 | 60 | 44 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POTRERO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -577 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | -1042.41 | Unknown | Unknown | -197.74 | Unknown | -844.67 | Unknown | 517.33 | -1042.41 | 1559.74 | Yes | N/A | N/A | 2024-04-18 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-18 | 53 | 39 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-07-15 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-18 | 4 | 4 | 2024-07-18 | 2024-07-18 | 1 | 1 | 89 | 63 | 58 | 44 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 59 | 59 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -10 | -7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | -1544.95 | Unknown | Unknown | Unknown | -1574 | 29.05 | Unknown | 1573.97 | -1544.95 | 3118.92 | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-10-17 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-12-05 | 50 | 36 | 2024-12-05 | 2024-12-05 | 1 | 1 | 60 | 44 | 51 | 37 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 1200.15 | 1200.15 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-06-30 | 3 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2023-03-22 | 2023-06-16 | IOU Designed & Installed | N/A | No | N/A | 3798.62 | 1014.35 | Unknown | 412.48 | 7.32 | 2364.47 | 3981 | 905.38 | 3798.62 | -2893.24 | Yes | N/A | N/A | 2022-08-02 | 2023-03-27 | 238 | 170 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-07-03 | 18 | 12 | 2023-07-03 | 2023-07-03 | 1 | 1 | 238 | 170 | 19 | 13 | 257 | 183 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-29 | 439 | 314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-11-10 | 2021-11-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 495.75 | -12.8 | Unknown | Unknown | 8.98 | 499.57 | 3981 | 3145.72 | 495.75 | 2649.97 | Yes | N/A | N/A | 2021-11-10 | 2023-03-30 | 506 | 362 | 2023-03-30 | 2023-04-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-01-11 | Unknown | Unknown | 506 | 362 | 7 | 5 | 513 | 367 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 847.32 | -6.19 | Unknown | Unknown | 1.79 | 851.72 | 3981 | 566.28 | 847.32 | -281.04 | Yes | N/A | N/A | 2023-04-11 | 2023-04-11 | 1 | 1 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6534 | 6534 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-14 | 441 | 316 | No | 2023-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-03-17 | 2023-12-28 | IOU Designed & Installed | N/A | Yes | 330 | 1170.43 | 376.26 | Unknown | 58.16 | Unknown | 736.01 | 7962 | 777.55 | 1170.43 | -392.88 | Yes | N/A | N/A | 2023-02-15 | 2024-01-11 | 331 | 237 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | 2023-12-28 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-29 | 33 | 23 | 2024-01-29 | 2024-01-29 | 1 | 1 | 618 | 442 | 34 | 24 | 652 | 466 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 1371.4 | 1371.4 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-07-03 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-08-22 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | 4488.57 | 432.02 | Unknown | Unknown | -7460.07 | 11516.62 | 3981 | 11364.3 | 4488.57 | 6875.73 | Yes | N/A | N/A | 2023-07-24 | 2023-07-26 | 3 | 3 | 2023-07-26 | 2023-10-16 | 83 | 59 | 2023-08-29 | 2023-08-30 | 2 | 2 | 2023-10-16 | 2023-10-26 | 11 | 9 | 2023-10-16 | 2024-01-02 | 79 | 57 | 2023-10-26 | 2023-12-14 | 50 | 36 | 2023-12-18 | 2024-01-02 | 16 | 12 | 2024-01-02 | 2024-01-03 | 2 | 2 | 84 | 62 | 162 | 118 | 246 | 180 | Steps 2,3,5,6,7 | 126 | 90 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 67.9 | Unknown | Unknown | Unknown | Unknown | 67.9 | Unknown | 1554.46 | 67.9 | 1486.56 | Yes | N/A | N/A | 2024-09-10 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-09-18 | 66 | 48 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-24 | 15 | 11 | 2024-10-24 | 2024-10-24 | 1 | 1 | 24 | 18 | 82 | 60 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 20.05 | 20.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-23 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-03-18 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | -9.18 | -7.44 | Unknown | Unknown | Unknown | -1.74 | Unknown | 973.77 | -9.18 | 982.95 | Yes | N/A | N/A | 2024-02-05 | 2024-03-18 | 43 | 31 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-14 | 13 | 9 | 2024-05-14 | 2024-05-13 | Unknown | Unknown | 43 | 31 | 13 | 9 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | -750.79 | Unknown | Unknown | Unknown | -2986.45 | 2235.66 | Unknown | 3005.17 | -750.79 | 3755.96 | Yes | N/A | N/A | 2025-02-05 | 2025-02-25 | 21 | 15 | 2025-02-25 | 2025-02-28 | 4 | 4 | 2025-02-28 | 2025-03-17 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-07 | 22 | 16 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-04-07 | 2025-04-29 | 23 | 17 | 2025-04-29 | 2025-04-29 | 1 | 1 | 61 | 43 | 28 | 22 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 89 | 64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2024-04-24 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 58.44 | Unknown | Unknown | Unknown | Unknown | 58.44 | 3981 | 246.67 | 58.44 | 188.23 | Yes | N/A | N/A | 2023-07-28 | 2024-04-04 | 252 | 180 | 2024-04-04 | 2024-04-29 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-10-08 | 163 | 117 | Unknown | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-10-09 | 17 | 13 | 2024-10-09 | 2024-10-08 | Unknown | Unknown | 415 | 297 | 43 | 31 | 458 | 328 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 612.38 | -11.7 | Unknown | Unknown | Unknown | 624.08 | 3981 | 1490.05 | 612.38 | 877.67 | Yes | N/A | N/A | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-01-30 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2024-02-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 51816.81 | 4098.79 | Unknown | Unknown | -26575.56 | 74293.58 | Unknown | 26581.09 | 51816.81 | -25235.72 | Yes | N/A | N/A | 2023-02-02 | 2023-12-04 | 306 | 218 | 2023-12-04 | 2024-02-14 | 73 | 53 | 2023-12-18 | 2024-01-16 | 30 | 22 | 2023-09-13 | 2024-02-15 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-25 | 27 | 19 | 2024-03-25 | 2024-03-25 | 1 | 1 | 336 | 240 | 111 | 81 | 447 | 321 | Steps 2,3,5,6,7 | 183 | 131 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | -1.56 | -4.79 | Unknown | Unknown | Unknown | 3.23 | Unknown | 148.7 | -1.56 | 150.26 | Yes | N/A | N/A | 2023-08-03 | 2023-08-26 | 24 | 17 | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | 2024-01-08 | 136 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2023-10-24 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-14 | 22 | 16 | 2023-11-14 | 2023-11-14 | 1 | 1 | 220 | 155 | 24 | 17 | 244 | 172 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | PALA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 539 | 386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-08-03 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 24499.78 | 6.02 | Unknown | Unknown | 243.97 | 24249.79 | 10704 | 2389.03 | 24499.78 | -22110.75 | Yes | N/A | N/A | 2023-03-13 | 2023-04-11 | 30 | 22 | 2023-04-11 | 2024-07-11 | 458 | 328 | 2024-02-02 | 2024-02-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-10-10 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-11-22 | 117 | 85 | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 123 | 89 | 575 | 413 | 698 | 502 | Steps 2,3,5,6,7 | 160 | 114 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 2817.44 | -56.62 | Unknown | Unknown | Unknown | 2874.06 | Unknown | 2224.09 | 2817.44 | -593.35 | Yes | N/A | N/A | 2025-03-26 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-26 | 9 | 7 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-08 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-15 | 38 | 28 | 2025-05-15 | 2025-05-15 | 1 | 1 | 14 | 10 | 48 | 36 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-05 | 125 | 90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 637.42 | 1978.84 | Unknown | 678.04 | -2852 | 832.54 | Unknown | 2851.91 | 637.42 | 2214.49 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-04 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-08 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -487 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2025-01-19 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3891 | 1845.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2025-01-21 | 71 | 51 | 2025-01-21 | 2025-04-23 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-09 | 14 | 10 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-17 | 56 | 40 | 2025-06-17 | 2025-06-17 | 1 | 1 | 71 | 51 | 164 | 118 | 235 | 169 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 145 | 145 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-20 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 446.31 | -9.3 | Unknown | Unknown | Unknown | 455.61 | 17477 | 2696.47 | 446.31 | 2250.16 | Yes | N/A | N/A | 2024-08-01 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-08-29 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-12 | 32 | 24 | 2024-08-29 | 2025-05-20 | 265 | 189 | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-21 | 1 | 1 | 265 | 189 | 110 | 80 | 375 | 269 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -180 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-10 | 2024-07-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 29395.24 | 2890.68 | Unknown | 128.33 | 57.57 | 26318.66 | 6708296 | 93189.31 | 29395.24 | 63794.07 | Yes | N/A | N/A | 2023-01-10 | 2023-09-26 | 260 | 186 | 2023-09-26 | 2024-03-26 | 183 | 131 | 2023-10-13 | 2023-11-01 | 20 | 14 | 2024-03-28 | 2024-04-05 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-07-08 | 2024-08-16 | 40 | 30 | 2024-08-16 | 2024-08-16 | 1 | 1 | 280 | 200 | 234 | 170 | 514 | 370 | Steps 2,3,5,6,7 | 165 | 117 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -478 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 431.55 | -13.33 | Unknown | Unknown | 9.68 | 435.2 | 3981 | 542.25 | 431.55 | 110.7 | Yes | N/A | N/A | 2023-01-24 | 2023-01-31 | 8 | 6 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | 2023-07-19 | 169 | 121 | Unknown | 2023-06-19 | Unknown | Unknown | 2023-07-19 | 2023-07-25 | 7 | 5 | 2023-07-25 | 2023-07-25 | 1 | 1 | 177 | 127 | 8 | 6 | 185 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1128-H1 N.CITY PA6 (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 344 | 247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2025-05-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 140806.35 | 27084.95 | Unknown | Unknown | 10667.44 | 103053.96 | 359855 | 99107.92 | 140806.35 | -41698.43 | Yes | N/A | N/A | 2022-12-07 | 2024-02-14 | 435 | 311 | 2024-02-14 | 2024-08-06 | 175 | 125 | 2024-03-19 | 2025-06-04 | 60 | 42 | 2024-03-20 | 2024-10-29 | 30 | 20 | 2024-08-19 | Unknown | Unknown | Unknown | 2024-08-19 | 2025-05-13 | 268 | 192 | 2025-05-20 | 2025-06-10 | 22 | 16 | 2025-06-10 | 2025-06-10 | 1 | 1 | 495 | 353 | 496 | 354 | 991 | 707 | Steps 2,3,5,6,7 | 652 | 466 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-07 | 123 | 90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2065.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | 2023-08-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-08 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-26 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-03-02 | IOU Designed & Installed | N/A | No | N/A | 2241.9 | 499.75 | Unknown | Unknown | Unknown | 1742.15 | 3981 | 1863.53 | 2241.9 | -378.37 | Yes | N/A | N/A | 2025-01-15 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-01-15 | 14 | 10 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-03-02 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-03-02 | 2025-03-18 | 17 | 12 | 2025-03-18 | 2025-03-18 | 1 | 1 | 47 | 33 | 32 | 23 | 79 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-02 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 1067.26 | -17.08 | Unknown | Unknown | 6.35 | 1077.99 | 3981 | 761.28 | 1067.26 | -305.98 | Yes | N/A | N/A | 2024-03-26 | 2024-04-08 | 14 | 10 | 2024-04-08 | 2024-04-12 | 5 | 5 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-20 | 39 | 27 | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-06-13 | 25 | 19 | 2024-06-13 | 2024-06-13 | 1 | 1 | 53 | 37 | 31 | 25 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | -667 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-20 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | -3.85 | -15.83 | Unknown | Unknown | Unknown | 11.98 | 3981 | 3683.38 | -3.85 | 3687.23 | Yes | N/A | N/A | 2025-02-18 | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-20 | 16 | 12 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-25 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-03 | 10 | 8 | 2025-04-03 | 2025-04-03 | 1 | 1 | 34 | 24 | 27 | 21 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-20 | 361 | 258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-06-06 | IOU Designed & Installed | N/A | No | N/A | 857.22 | 4177.39 | Unknown | 603.04 | -6442 | 2518.79 | 0 | 6441.89 | 857.22 | 5584.67 | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | 2023-06-02 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2024-07-15 | 406 | 290 | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 433 | 311 | 434 | 312 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -537 | -385 | No | 2024-11-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | Yes | 114 | 887.48 | Unknown | Unknown | Unknown | Unknown | 887.48 | 3981 | 2866.76 | 887.48 | 1979.28 | Yes | N/A | N/A | 2024-11-19 | 2025-03-11 | 113 | 81 | 2025-03-11 | 2025-03-13 | 3 | 3 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 113 | 81 | 4 | 4 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-24 | 625 | 448 | No | 2021-04-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-16 | 2021-04-17 | 2023-05-04 | IOU Designed & Installed | N/A | Yes | 664 | 13093.87 | 2262.37 | Unknown | Unknown | -777.84 | 11609.34 | 3885 | 13784.72 | 13093.87 | 690.85 | Yes | N/A | N/A | 2021-04-16 | 2023-02-10 | 666 | 476 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-04-26 | 1 | 1 | 2022-04-14 | 2023-05-04 | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | 2023-05-04 | 2023-07-14 | 72 | 52 | 2023-07-14 | 2023-05-11 | Unknown | Unknown | 666 | 476 | 73 | 53 | 739 | 529 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 344 | 247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 27.02 | Unknown | Unknown | Unknown | Unknown | 27.02 | 3941 | 734.15 | 27.02 | 707.13 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2024-07-19 | 403 | 289 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-01 | 14 | 10 | 2024-08-01 | 2024-08-09 | 9 | 7 | 404 | 290 | 23 | 17 | 427 | 307 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -610 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-30 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 13.2 | -10.17 | Unknown | Unknown | Unknown | 23.37 | 3981 | 1457.03 | 13.2 | 1443.83 | Yes | N/A | N/A | 2024-05-28 | 2024-05-30 | 3 | 3 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-21 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-15 | 25 | 17 | 2024-07-15 | 2024-07-12 | Unknown | Unknown | 26 | 20 | 26 | 18 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -669 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-26 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3981 | 1923.01 | Unknown | 1923.01 | Yes | N/A | N/A | 2024-08-20 | 2024-08-21 | 2 | 2 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-12 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-09-23 | 12 | 8 | 2024-09-23 | 2024-09-23 | 1 | 1 | 2 | 2 | 31 | 23 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13580.05 | 13580.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-30 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-09-22 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 13.28 | -16.14 | Unknown | Unknown | Unknown | 29.42 | 3981 | 615.25 | 13.28 | 601.97 | Yes | N/A | N/A | 2023-06-29 | 2023-04-25 | Unknown | Unknown | 2023-04-25 | 2023-09-22 | 151 | 109 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2024-02-07 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-28 | 22 | 16 | 2024-02-28 | 2024-02-28 | 1 | 1 | 139 | 99 | 174 | 126 | 313 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 558 | 399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-30 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 757.5 | -28.92 | Unknown | Unknown | 85.95 | 700.47 | 7962 | 1115.76 | 757.5 | 358.26 | Yes | N/A | N/A | 2023-08-07 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-08-30 | 106 | 76 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-22 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2024-10-10 | 385 | 275 | 2024-10-10 | 2024-10-10 | 1 | 1 | 24 | 18 | 492 | 352 | 516 | 370 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | 854 | 611 | No | 2020-06-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-06-26 | 2020-06-26 | Unknown | IOU Designed & Installed | N/A | Yes | 965 | -9.53 | -6.91 | Unknown | Unknown | Unknown | -2.62 | 3241 | 361.38 | -9.53 | 370.91 | Yes | N/A | N/A | 2020-06-26 | 2023-02-16 | 966 | 690 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2020-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-05-04 | 1 | 1 | 966 | 690 | 1 | 1 | 967 | 691 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-26 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.27 | -5.39 | Unknown | Unknown | Unknown | -0.88 | Unknown | 98.41 | -6.27 | 104.68 | Yes | N/A | N/A | 2023-03-01 | 2023-03-15 | 15 | 11 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-14 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-09-19 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 61.32 | -13.05 | Unknown | Unknown | Unknown | 74.37 | 3981 | 944.5 | 61.32 | 883.18 | Yes | N/A | N/A | 2023-08-17 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-09-19 | 111 | 79 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-10-23 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-10-30 | 8 | 6 | 2023-10-30 | 2023-10-26 | Unknown | Unknown | 35 | 25 | 119 | 85 | 154 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 490.34 | 181.95 | Unknown | Unknown | Unknown | 308.39 | Unknown | 1476.19 | 490.34 | 985.85 | Yes | N/A | N/A | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-12-06 | 37 | 27 | 2024-12-06 | 2024-12-06 | 1 | 1 | 16 | 12 | 40 | 30 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 1031.19 | 251.36 | Unknown | 148.65 | Unknown | 631.18 | 3981 | 1488.86 | 1031.19 | 457.67 | Yes | N/A | N/A | 2024-09-06 | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-09-06 | 4 | 4 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-16 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-23 | 8 | 6 | 2024-09-23 | 2024-09-23 | 1 | 1 | 11 | 7 | 13 | 11 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-20 | -34 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 725.38 | -14.57 | Unknown | Unknown | Unknown | 739.95 | 3981 | 1675.81 | 725.38 | 950.43 | Yes | N/A | N/A | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | 2024-12-06 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-03-25 | 147 | 105 | 2024-12-06 | 2025-03-06 | 91 | 65 | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-16 | 1 | 1 | 92 | 66 | 186 | 134 | 278 | 200 | Steps 2,3,5,6,7 | 109 | 77 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -355 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | -302.54 | Unknown | Unknown | Unknown | -748.98 | 446.44 | Unknown | 1876 | -302.54 | 2178.54 | Yes | N/A | N/A | 2024-09-18 | 2025-02-25 | 161 | 115 | 2025-02-25 | 2025-02-26 | 2 | 2 | 2025-02-26 | 2025-03-11 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-28 | 49 | 35 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-04-28 | 2025-06-02 | 36 | 26 | 2025-06-02 | 2025-06-02 | 1 | 1 | 224 | 160 | 39 | 29 | 263 | 189 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-19 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 25034.52 | 3293.41 | Unknown | 3.39 | 34.03 | 21703.69 | 28177 | 18154.08 | 25034.52 | -6880.44 | Yes | N/A | N/A | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | Unknown | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-03-31 | 2024-06-24 | 72 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-08-16 | 52 | 38 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2 | 2 | 125 | 88 | 127 | 90 | Steps 2,3,5,6,7 | 52 | 37 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 186 | 133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.71 | -13.07 | Unknown | Unknown | Unknown | 27.78 | 3981 | 865.75 | 14.71 | 851.04 | Yes | N/A | N/A | 2022-12-08 | 2023-04-06 | 120 | 86 | 2023-04-06 | 2023-05-19 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2024-06-03 | 382 | 272 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-06-04 | Unknown | Unknown | 502 | 358 | 44 | 32 | 546 | 390 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-15 | 694 | 497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 32.32 | Unknown | Unknown | Unknown | Unknown | 32.32 | 20404 | 3689.08 | 32.32 | 3656.76 | Yes | N/A | N/A | 2023-09-12 | 2023-03-06 | Unknown | Unknown | 2023-03-06 | 2023-10-05 | 214 | 154 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-11 | 1 | 1 | 2023-10-05 | 2024-09-03 | 335 | 239 | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-08 | Unknown | Unknown | 335 | 239 | 215 | 155 | 550 | 394 | Steps 2,3,5,6,7 | 250 | 178 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-15 | 259 | 186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2024-01-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 15976.18 | 6845.24 | Unknown | Unknown | -32523 | 41653.94 | Unknown | 32522.69 | 15976.18 | 16546.51 | Yes | N/A | N/A | 2023-04-25 | 2023-05-19 | 25 | 19 | 2023-05-19 | 2023-11-14 | 180 | 128 | 2023-06-08 | 2023-06-22 | 15 | 11 | 2023-06-27 | 2023-11-20 | 21 | 15 | 2024-01-17 | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-29 | 43 | 31 | 2024-02-29 | 2024-02-29 | 1 | 1 | 40 | 30 | 245 | 175 | 285 | 205 | Steps 2,3,5,6,7 | 159 | 113 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -521 | -374 | No | 2024-05-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-09-23 | IOU Designed & Installed | N/A | Yes | 133 | 491.72 | Unknown | Unknown | Unknown | -795.41 | 1287.13 | Unknown | 804.7 | 491.72 | 312.98 | Yes | N/A | N/A | 2024-05-07 | 2024-09-17 | 134 | 96 | 2024-09-17 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-05-24 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-09-23 | 123 | 87 | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-23 | 2024-09-30 | 8 | 6 | 2024-09-30 | 2024-09-30 | 1 | 1 | 275 | 197 | 9 | 7 | 284 | 204 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-16 | 819 | 586 | No | 2020-03-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-03-25 | 2020-03-25 | Unknown | IOU Designed & Installed | N/A | Yes | 1099 | 844.33 | -11.35 | Unknown | Unknown | Unknown | 855.68 | Unknown | 560.44 | 844.33 | -283.89 | Yes | N/A | N/A | 2020-03-25 | 2023-03-29 | 1100 | 786 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2020-03-25 | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | 2023-06-13 | 2023-06-13 | 1 | 1 | 1100 | 786 | 1 | 1 | 1101 | 787 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | Unknown | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 76.5 | -0.94 | Unknown | Unknown | Unknown | 77.44 | 3981 | 1542.14 | 76.5 | 1465.64 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-22 | 43 | 31 | 2024-10-22 | 2024-10-22 | 1 | 1 | 15 | 11 | 45 | 33 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 7.36 | Unknown | Unknown | Unknown | Unknown | 7.36 | Unknown | 1449.37 | 7.36 | 1442.01 | Yes | N/A | N/A | 2024-06-12 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-12 | 44 | 32 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-19 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-29 | 11 | 7 | 2024-07-29 | 2024-07-29 | 1 | 1 | 38 | 28 | 56 | 40 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 24.36 | Unknown | Unknown | Unknown | Unknown | 24.36 | 3981 | 1826.14 | 24.36 | 1801.78 | Yes | N/A | N/A | 2024-12-23 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-23 | 4 | 2 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-07 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-22 | 16 | 12 | 2025-01-22 | 2025-01-22 | 1 | 1 | 16 | 12 | 21 | 15 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -180 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-10 | 2024-07-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 17676.33 | 1598.26 | Unknown | Unknown | 61.18 | 16016.89 | 6587012 | 88318.57 | 17676.33 | 70642.24 | Yes | N/A | N/A | 2023-01-10 | 2023-09-26 | 260 | 186 | 2023-09-26 | 2024-01-24 | 121 | 87 | 2023-10-13 | 2023-11-01 | 20 | 14 | 2024-01-26 | 2024-02-06 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-07-08 | 2024-08-16 | 40 | 30 | 2024-08-16 | 2024-08-16 | 1 | 1 | 280 | 200 | 175 | 127 | 455 | 327 | Steps 2,3,5,6,7 | 103 | 73 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-07-09 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 1455.04 | Unknown | Unknown | Unknown | 12.57 | 1442.47 | 3981 | 1128.23 | 1455.04 | -326.81 | Yes | N/A | N/A | 2024-06-06 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-07-09 | 71 | 51 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-09-25 | 79 | 57 | Unknown | 2024-09-24 | Unknown | Unknown | 2024-09-25 | 2024-10-09 | 15 | 11 | 2024-10-09 | 2024-10-09 | 1 | 1 | 79 | 57 | 87 | 63 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 7.67 | Unknown | Unknown | Unknown | Unknown | 7.67 | Unknown | 192.95 | 7.67 | 185.28 | Yes | N/A | N/A | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-09-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-02 | 14 | 10 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2 | 2 | 16 | 12 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | 41 | 30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 20712.09 | 1394.76 | Unknown | Unknown | 206.25 | 19111.08 | Unknown | 11865.01 | 20712.09 | -8847.08 | Yes | N/A | N/A | 2025-01-14 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-03 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-05-19 | 67 | 47 | 2025-05-19 | 2025-05-19 | 1 | 1 | 0 | 0 | 79 | 55 | 79 | 55 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | 403 | 288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2024-04-24 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 275550.54 | 11779.99 | Unknown | 61.07 | 915.16 | 262794.32 | 0 | 194682.93 | 275550.54 | -80867.61 | Yes | N/A | N/A | 2023-03-23 | 2024-04-11 | 386 | 276 | 2024-04-11 | 2025-01-06 | 271 | 193 | 2024-04-23 | 2024-09-26 | 2 | 2 | 2024-08-02 | 2025-01-03 | 44 | 32 | 2025-01-06 | 2025-03-26 | 80 | 58 | 2025-02-10 | 2025-03-10 | 29 | 21 | 2025-01-07 | 2025-04-28 | 112 | 80 | 2025-04-28 | 2025-04-28 | 1 | 1 | 468 | 336 | 457 | 327 | 925 | 663 | Steps 2,3,5,6,7 | 419 | 299 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 118.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-13 | 2 | 2 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-09 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 28 | 20 | 4 | 4 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.4 | 14.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -544 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-13 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 1642.12 | 1101.68 | Unknown | 13.17 | Unknown | 527.27 | 3961 | 192.51 | 1642.12 | -1449.61 | Yes | N/A | N/A | 2024-06-07 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-07-16 | 79 | 57 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-09-25 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-18 | 24 | 18 | 2024-10-18 | 2024-10-18 | 1 | 1 | 72 | 52 | 104 | 76 | 176 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1040.05 | 1040.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-02-21 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 683.19 | -11.26 | Unknown | Unknown | 32.42 | 662.03 | 3981 | 632.46 | 683.19 | -50.73 | Yes | N/A | N/A | 2023-03-27 | 2023-05-04 | 39 | 29 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-08-29 | 118 | 84 | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-29 | 2024-01-24 | 149 | 107 | 2024-01-24 | 2024-01-24 | 1 | 1 | 157 | 113 | 150 | 108 | 307 | 221 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 262 | 262 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -498 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-06-29 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | 389.88 | -14.96 | Unknown | Unknown | 108.05 | 296.79 | 3981 | 1213.23 | 389.88 | 823.35 | Yes | N/A | N/A | 2023-05-22 | 2023-07-13 | 53 | 39 | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-09-25 | 75 | 53 | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-25 | 2024-10-10 | 382 | 274 | 2024-10-10 | 2023-10-06 | Unknown | Unknown | 128 | 92 | 383 | 275 | 511 | 367 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | -6.67 | -12.91 | Unknown | Unknown | Unknown | 6.24 | Unknown | 768.28 | -6.67 | 774.95 | Yes | N/A | N/A | 2023-06-07 | 2023-06-07 | 1 | 1 | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-07-07 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-07-31 | 25 | 17 | 2023-07-31 | 2023-07-31 | 1 | 1 | 32 | 24 | 26 | 18 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1011.41 | 166.14 | Unknown | 156.92 | 20.82 | 667.53 | 3981 | 661.33 | 1011.41 | -350.08 | Yes | N/A | N/A | 2023-05-12 | 2023-05-19 | 8 | 6 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -272 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 811.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-17 | 2023-06-15 | 91 | 65 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-01-19 | Unknown | Unknown | 91 | 65 | 0 | 0 | 91 | 65 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | OCEANSIDE | OCEANSIDE, VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-03 | 375 | 269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | 2023-12-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 176606.09 | 35090.2 | Unknown | 27.14 | 2131.22 | 139357.53 | 733088 | 80676.45 | 176606.09 | -95929.64 | Yes | N/A | N/A | 2022-09-15 | 2023-02-02 | 141 | 101 | 2023-02-02 | 2023-06-20 | 139 | 99 | 2023-03-03 | 2023-12-26 | 77 | 53 | 2023-03-09 | 2024-01-09 | 130 | 94 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-12-06 | 120 | 86 | 2023-12-08 | 2024-01-17 | 41 | 29 | 2024-01-17 | 2024-01-13 | Unknown | Unknown | 218 | 154 | 430 | 308 | 648 | 462 | Steps 2,3,5,6,7 | 401 | 285 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -121 | -88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | 671.72 | -19.22 | Unknown | Unknown | 32 | 658.94 | 3885 | 412.4 | 671.72 | -259.32 | Yes | N/A | N/A | 2023-01-25 | 2023-02-17 | 24 | 18 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2023-08-17 | 182 | 130 | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-17 | 2023-09-06 | 21 | 15 | 2023-09-06 | 2023-09-06 | 1 | 1 | 206 | 148 | 22 | 16 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | DANA POINT | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2046.1 | -44.43 | Unknown | Unknown | Unknown | 2090.53 | Unknown | 1996.82 | 2046.1 | -49.28 | Yes | N/A | N/A | 2025-03-19 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-19 | 2 | 2 | 2025-03-19 | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-27 | 9 | 7 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 0 | 0 | 12 | 10 | 12 | 10 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DULZURA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-18 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-02-18 | IOU Designed & Installed | N/A | No | N/A | 694.98 | 389.06 | Unknown | 19.91 | Unknown | 286.01 | 3941 | 517.29 | 694.98 | -177.69 | Yes | N/A | N/A | 2024-02-12 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-02-12 | 33 | 23 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-18 | 2024-03-15 | 27 | 20 | 2024-03-15 | 2024-03-28 | 14 | 10 | 7 | 5 | 74 | 53 | 81 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -612 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-29 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 12.89 | -11.44 | Unknown | Unknown | Unknown | 24.33 | 3241 | 982.05 | 12.89 | 969.16 | Yes | N/A | N/A | 2024-04-24 | 2024-04-29 | 6 | 4 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-08 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-13 | 6 | 4 | 2024-05-13 | 2024-05-10 | Unknown | Unknown | 16 | 12 | 7 | 5 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | -147 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 1037.2 | 2209.36 | Unknown | 940.91 | -3557 | 1443.93 | Unknown | 3557.12 | 1037.2 | 2519.92 | Yes | N/A | N/A | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-12 | 32 | 24 | 2024-01-12 | 2024-01-12 | 1 | 1 | 7 | 5 | 33 | 25 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 527.05 | 527.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | -762.04 | -17.71 | Unknown | Unknown | -785 | 40.67 | 3981 | 1772.52 | -762.04 | 2534.56 | Yes | N/A | N/A | 2024-01-29 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-01-29 | 33 | 23 | 2024-01-29 | 2024-05-01 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-27 | 53 | 39 | Unknown | 2024-06-18 | Unknown | Unknown | 2024-06-27 | 2024-07-11 | 15 | 11 | 2024-07-11 | 2024-07-09 | Unknown | Unknown | 147 | 107 | 48 | 34 | 195 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | -185 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | -29.99 | -24 | Unknown | Unknown | Unknown | -5.99 | 3885 | 153.83 | -29.99 | 183.82 | Yes | N/A | N/A | 2023-06-26 | 2023-06-29 | 4 | 4 | 2023-06-29 | 2023-08-11 | 44 | 32 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-08-30 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-12 | 14 | 10 | 2023-09-12 | 2023-09-12 | 1 | 1 | 24 | 18 | 59 | 43 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -572 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-06-27 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 44.67 | Unknown | Unknown | Unknown | Unknown | 44.67 | 3981 | 1476.53 | 44.67 | 1431.86 | Yes | N/A | N/A | 2024-05-21 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-06-27 | 66 | 48 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-15 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-05 | 22 | 16 | 2024-08-05 | 2024-08-05 | 1 | 1 | 19 | 13 | 89 | 65 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | -1151.99 | -5.56 | Unknown | Unknown | -1156 | 9.57 | 3981 | 1959.72 | -1151.99 | 3111.71 | Yes | N/A | N/A | 2024-01-18 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-18 | 10 | 8 | 2024-01-18 | 2024-01-22 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-07 | 17 | 13 | Unknown | 2024-02-06 | Unknown | Unknown | 2024-02-07 | 2024-02-15 | 9 | 7 | 2024-02-15 | 2024-02-15 | 1 | 1 | 22 | 16 | 20 | 16 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 741 | 530 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2025-01-13 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 1379.34 | Unknown | Unknown | Unknown | Unknown | 1379.34 | 7962 | 3294.48 | 1379.34 | 1915.14 | Yes | N/A | N/A | 2023-08-01 | 2024-08-20 | 386 | 276 | 2024-08-20 | 2025-02-19 | 184 | 132 | 2025-01-13 | 2025-01-14 | 2 | 2 | 2025-01-14 | 2025-02-05 | 23 | 17 | 2025-02-19 | 2025-04-29 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | 2025-06-11 | 1 | 1 | 458 | 328 | 209 | 151 | 667 | 479 | Steps 2,3,5,6,7 | 37 | 27 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | -242 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-04-07 | IOU Designed & Installed | N/A | No | N/A | -7.5 | -6.29 | Unknown | Unknown | Unknown | -1.21 | Unknown | 98.41 | -7.5 | 105.91 | Yes | N/A | N/A | 2023-03-06 | 2023-03-22 | 17 | 13 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-04-07 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-06-12 | 67 | 47 | 2023-06-12 | 2023-06-12 | 1 | 1 | 34 | 26 | 68 | 48 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 577.05 | 577.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -373 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-29 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 7.88 | Unknown | Unknown | Unknown | Unknown | 7.88 | 3961 | 163.83 | 7.88 | 155.95 | Yes | N/A | N/A | 2024-02-21 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-03-25 | 60 | 42 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-08-22 | 151 | 109 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-22 | 2024-09-05 | 15 | 11 | 2024-09-05 | 2024-09-04 | Unknown | Unknown | 151 | 109 | 75 | 53 | 226 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-10 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 8733.56 | Unknown | Unknown | Unknown | Unknown | 8733.56 | Unknown | 1249.4 | 8733.56 | -7484.16 | Yes | N/A | N/A | 2024-10-09 | 2024-10-09 | 1 | 1 | 2024-10-09 | 2024-10-21 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-14 | 25 | 19 | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-25 | 2024-11-05 | 12 | 8 | 2024-11-05 | 2024-11-19 | 15 | 11 | 26 | 20 | 40 | 28 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | 240 | 171 | No | 2023-09-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2025-02-10 | IOU Designed & Installed | N/A | Yes | 505 | 315.63 | Unknown | Unknown | Unknown | 6.27 | 309.36 | 3981 | 700.33 | 315.63 | 384.7 | Yes | N/A | N/A | 2023-09-07 | 2025-01-24 | 506 | 362 | 2025-01-24 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2025-02-10 | 399 | 285 | Unknown | 2024-11-04 | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-02-24 | 5 | 3 | 905 | 647 | 16 | 12 | 921 | 659 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SB 1187-G1 SOLANA HGLD PH3 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 612 | 438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-07 | 2021-09-07 | 2025-04-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 50803.04 | 4296.24 | Unknown | Unknown | 3933.36 | 42573.44 | 373617 | 45784.44 | 50803.04 | -5018.6 | Yes | N/A | N/A | 2021-09-07 | 2024-01-29 | 875 | 625 | 2024-01-29 | 2024-08-21 | 206 | 148 | 2024-02-01 | 2025-04-16 | 380 | 272 | 2024-08-02 | 2024-09-12 | 42 | 30 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-19 | 2025-04-15 | 118 | 84 | 2025-04-25 | 2025-06-18 | 55 | 39 | 2025-06-18 | 2025-06-18 | 1 | 1 | 1255 | 897 | 422 | 302 | 1677 | 1199 | Steps 2,3,5,6,7 | 459 | 327 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-09 | -417 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 676.79 | -6.14 | Unknown | Unknown | Unknown | 682.93 | Unknown | 723.52 | 676.79 | 46.73 | Yes | N/A | N/A | 2023-02-10 | 2023-02-10 | 1 | 1 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-28 | 263 | 188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 5161.95 | Unknown | Unknown | Unknown | -759 | 5920.95 | 4252 | 4075.53 | 5161.95 | -1086.42 | Yes | N/A | N/A | 2023-05-23 | 2023-05-24 | 2 | 2 | 2023-05-24 | 2023-06-13 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-07-05 | 42 | 30 | 2023-06-13 | 2023-09-11 | 91 | 65 | Unknown | 2023-10-11 | Unknown | Unknown | 2023-10-12 | 2023-10-20 | 9 | 7 | 2023-10-20 | 2023-10-18 | Unknown | Unknown | 93 | 67 | 72 | 52 | 165 | 119 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 751.95 | -11.19 | Unknown | Unknown | -746.06 | 1509.2 | Unknown | 746.52 | 751.95 | -5.43 | Yes | N/A | N/A | 2024-01-23 | 2024-02-13 | 22 | 16 | 2024-02-13 | 2024-02-16 | 4 | 4 | 2024-02-16 | 2024-06-07 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-13 | 31 | 23 | Unknown | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-06-27 | 15 | 11 | 2024-06-27 | 2024-06-27 | 1 | 1 | 166 | 120 | 20 | 16 | 186 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -429 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.7 | Unknown | Unknown | Unknown | Unknown | 30.7 | Unknown | 1467.39 | 30.7 | 1436.69 | Yes | N/A | N/A | 2024-05-23 | 2024-04-19 | Unknown | Unknown | 2024-04-19 | 2024-06-27 | 70 | 50 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-05 | 1 | 1 | 0 | 0 | 71 | 51 | 71 | 51 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | 165 | 118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-07-18 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | -26097.08 | -16.8 | Unknown | Unknown | -33138 | 7057.72 | 19355 | 65333.08 | -26097.08 | 91430.16 | Yes | N/A | N/A | 2024-06-14 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2025-03-04 | 268 | 192 | 2024-09-05 | 2025-02-28 | 24 | 18 | 2024-12-17 | 2025-03-11 | 37 | 27 | 2025-03-04 | 2025-05-12 | 70 | 50 | 2025-03-27 | 2025-05-06 | 41 | 29 | 2025-05-20 | 2025-06-27 | 39 | 29 | 2025-06-27 | 2025-06-25 | Unknown | Unknown | 94 | 68 | 385 | 277 | 479 | 345 | Steps 2,3,5,6,7 | 306 | 218 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -456 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.16 | -15.59 | Unknown | Unknown | Unknown | 16.75 | 3981 | 797.23 | 1.16 | 796.07 | Yes | N/A | N/A | 2023-03-06 | 2023-04-08 | 34 | 25 | 2023-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | 2023-11-15 | 2023-11-15 | 1 | 1 | 34 | 25 | 1 | 1 | 35 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-12-05 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 36.18 | Unknown | Unknown | Unknown | Unknown | 36.18 | 3981 | 1478.26 | 36.18 | 1442.08 | Yes | N/A | N/A | 2024-11-06 | 2024-10-27 | Unknown | Unknown | 2024-10-27 | 2024-12-05 | 40 | 29 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-22 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-06 | 16 | 12 | 2025-02-06 | 2025-02-05 | Unknown | Unknown | 48 | 34 | 56 | 41 | 104 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 220.24 | -6.67 | Unknown | Unknown | Unknown | 226.91 | 3981 | 745.28 | 220.24 | 525.04 | Yes | N/A | N/A | 2023-03-30 | 2023-04-03 | 5 | 3 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 102 | 73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 35145.47 | 11714.57 | Unknown | 127.71 | -12546 | 35849.19 | 1803805 | 20141.97 | 35145.47 | -15003.5 | Yes | N/A | N/A | 2023-03-16 | 2023-04-19 | 35 | 25 | 2023-04-19 | 2023-04-21 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2024-05-06 | 382 | 272 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-08 | 2024-05-13 | 6 | 4 | 2024-05-13 | 2024-05-13 | 1 | 1 | 417 | 297 | 10 | 8 | 427 | 305 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-27 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | 27.32 | -6.86 | Unknown | Unknown | Unknown | 34.18 | 3981 | 717.61 | 27.32 | 690.29 | Yes | N/A | N/A | 2023-06-20 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2023-06-22 | 66 | 48 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-08-02 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-08-16 | 15 | 11 | 2023-08-16 | 2023-08-16 | 1 | 1 | 42 | 30 | 82 | 60 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-07 | 13 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 0.81 | -10.61 | Unknown | Unknown | Unknown | 11.42 | Unknown | 647.81 | 0.81 | 647 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-12-11 | 300 | 214 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-20 | 10 | 8 | 2023-12-20 | 2023-12-20 | 1 | 1 | 301 | 215 | 11 | 9 | 312 | 224 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-10 | -136 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 477.84 | 186.96 | Unknown | Unknown | Unknown | 290.88 | 3981 | 1126.27 | 477.84 | 648.43 | Yes | N/A | N/A | 2023-09-12 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-10-02 | 43 | 31 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-03-27 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18.2 | 18.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1357.73 | -33.46 | Unknown | Unknown | -1935 | 610.73 | Unknown | 1709.87 | -1357.73 | 3067.6 | Yes | N/A | N/A | 2025-01-08 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2025-01-14 | 23 | 17 | 2025-01-14 | 2025-03-26 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-04 | Unknown | Unknown | 72 | 52 | 23 | 17 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-06-24 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 9.07 | -6.99 | Unknown | Unknown | Unknown | 16.06 | 3981 | 1440.48 | 9.07 | 1431.41 | Yes | N/A | N/A | 2024-04-16 | 2024-06-24 | 70 | 50 | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-08 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-10-04 | 89 | 65 | 2024-10-04 | 2024-07-16 | Unknown | Unknown | 85 | 61 | 90 | 66 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 803.05 | 803.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-02 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-07-13 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | -2 | -3.92 | Unknown | Unknown | Unknown | 1.92 | 3981 | 791.46 | -2 | 793.46 | Yes | N/A | N/A | 2023-06-29 | 2023-07-14 | 16 | 12 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-09-14 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-19 | 6 | 4 | 2023-09-19 | 2023-09-19 | 1 | 1 | 79 | 57 | 8 | 6 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 1719.42 | 263.36 | Unknown | 89.36 | Unknown | 1366.7 | 3981 | 782.88 | 1719.42 | -936.54 | Yes | N/A | N/A | 2023-03-20 | 2023-04-26 | 38 | 28 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-05-12 | 17 | 13 | 2023-04-26 | 2023-06-23 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-26 | 4 | 2 | 2023-06-26 | 2023-06-26 | 1 | 1 | 97 | 71 | 22 | 16 | 119 | 87 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | Unknown | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 32.84 | Unknown | Unknown | Unknown | Unknown | 32.84 | Unknown | 1626.94 | 32.84 | 1594.1 | Yes | N/A | N/A | 2024-09-24 | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-10-02 | 21 | 15 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-03 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-18 | 16 | 12 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2 | 2 | 38 | 28 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-25 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-25 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 27.04 | -17.78 | Unknown | Unknown | Unknown | 44.82 | 3981 | 1803.07 | 27.04 | 1776.03 | Yes | N/A | N/A | 2025-03-14 | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-03-25 | 16 | 12 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-07 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-15 | 9 | 7 | 2025-04-15 | 2025-04-14 | Unknown | Unknown | 14 | 10 | 25 | 19 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | -210 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-18 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 40.65 | -10.09 | Unknown | Unknown | 40.35 | 10.39 | 3981 | 834.23 | 40.65 | 793.58 | Yes | N/A | N/A | 2023-08-08 | 2023-08-18 | 11 | 9 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-11-09 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-10 | 337 | 241 | 2024-10-10 | 2024-10-10 | 1 | 1 | 95 | 69 | 339 | 243 | 434 | 312 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-07 | -256 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 462.55 | -12.03 | Unknown | Unknown | Unknown | 474.58 | 3981 | 884.72 | 462.55 | 422.17 | Yes | N/A | N/A | 2024-04-03 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-04-17 | 37 | 27 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-06-24 | 1 | 1 | 0 | 0 | 38 | 28 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-19 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 833.1 | Unknown | Unknown | Unknown | Unknown | 833.1 | 3981 | 783.95 | 833.1 | -49.15 | Yes | N/A | N/A | 2024-04-10 | 2024-04-19 | 10 | 8 | 2024-04-19 | 2024-04-19 | 1 | 1 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-07-16 | 89 | 63 | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-16 | 2024-07-30 | 15 | 11 | 2024-07-30 | 2024-07-30 | 1 | 1 | 99 | 71 | 17 | 13 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -11 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 37264.47 | 323.75 | Unknown | 22.92 | 180.35 | 36737.45 | 2034074 | 12680.12 | 37264.47 | -24584.35 | Yes | N/A | N/A | 2023-12-13 | 2024-04-02 | 112 | 80 | 2024-04-02 | 2024-05-16 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-12-02 | 201 | 143 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-28 | 2025-03-11 | 43 | 31 | 2025-03-11 | 2025-02-01 | Unknown | Unknown | 313 | 223 | 88 | 64 | 401 | 287 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1371.86 | 17.51 | Unknown | Unknown | 40.55 | 1313.8 | 3981 | 2988.95 | 1371.86 | 1617.09 | Yes | N/A | N/A | 2024-09-13 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-12-10 | 105 | 75 | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-09-16 | 2024-09-18 | 3 | 3 | 2024-12-10 | 2025-03-18 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-15 | Unknown | Unknown | 100 | 72 | 108 | 78 | 208 | 150 | Steps 2,3,5,6,7 | 85 | 61 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 458.77 | -11.5 | Unknown | Unknown | Unknown | 470.27 | 3981 | 1466.13 | 458.77 | 1007.36 | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-28 | 24 | 18 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2 | 2 | 26 | 20 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 635.24 | 488.19 | Unknown | 162.84 | -1194 | 1178.21 | 3981 | 1921.36 | 635.24 | 1286.12 | Yes | N/A | N/A | 2024-05-17 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-17 | 52 | 38 | 2024-05-17 | 2024-05-28 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-08-02 | 67 | 49 | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-29 | 28 | 20 | 2024-08-29 | 2024-08-28 | Unknown | Unknown | 79 | 57 | 80 | 58 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-11 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | -24896.64 | Unknown | Unknown | Unknown | -56651.27 | 31754.63 | Unknown | 55101.71 | -24896.64 | 79998.35 | Yes | N/A | N/A | 2024-11-08 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2025-02-14 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-04-23 | 69 | 49 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-25 | 2025-06-05 | 42 | 30 | 2025-06-05 | 2025-04-24 | Unknown | Unknown | 69 | 49 | 143 | 103 | 212 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | -216 | -155 | No | 2024-03-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2025-01-06 | 2025-03-25 | IOU Designed & Installed | N/A | Yes | 308 | 1029.76 | Unknown | Unknown | Unknown | Unknown | 1029.76 | 3981 | 720.66 | 1029.76 | -309.1 | Yes | N/A | N/A | 2024-03-04 | 2024-12-18 | 290 | 208 | 2024-12-18 | 2024-03-04 | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-03-25 | 79 | 57 | Unknown | 2025-03-20 | Unknown | Unknown | 2025-03-25 | 2025-04-11 | 18 | 14 | 2025-04-11 | 2025-04-11 | 1 | 1 | 369 | 265 | 19 | 15 | 388 | 280 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -198 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | -17.93 | -14.13 | Unknown | Unknown | Unknown | -3.8 | Unknown | 496.75 | -17.93 | 514.68 | Yes | N/A | N/A | 2023-11-21 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-11-21 | 43 | 31 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-03-07 | 101 | 73 | 2024-03-07 | 2024-03-07 | 1 | 1 | 8 | 6 | 145 | 105 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -183 | -132 | No | 2023-10-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-25 | 2023-12-26 | IOU Designed & Installed | N/A | Yes | 69 | -6.5 | -5.12 | Unknown | Unknown | Unknown | -1.38 | Unknown | 532.33 | -6.5 | 538.83 | Yes | N/A | N/A | 2023-10-03 | 2023-12-11 | 70 | 50 | 2023-12-11 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-12-26 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-31 | 37 | 27 | 2024-01-31 | 2024-01-31 | 1 | 1 | 133 | 95 | 38 | 28 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -640 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 608.76 | -23.1 | Unknown | Unknown | Unknown | 631.86 | Unknown | 982.63 | 608.76 | 373.87 | Yes | N/A | N/A | 2023-04-12 | 2023-05-16 | 35 | 25 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | 2023-06-07 | 2023-06-07 | 1 | 1 | 35 | 25 | 1 | 1 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -463 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-12 | 2024-10-12 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1258.58 | -16.15 | Unknown | Unknown | 30.29 | 1244.44 | 3981 | 1739.07 | 1258.58 | 480.49 | Yes | N/A | N/A | 2024-10-12 | 2024-11-13 | 33 | 23 | 2024-11-13 | 2025-02-20 | 100 | 72 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-01 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-23 | 23 | 17 | 2025-04-23 | 2025-04-23 | 1 | 1 | 74 | 52 | 124 | 90 | 198 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -493 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-13 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | -348.64 | 122.45 | Unknown | Unknown | -697 | 225.91 | Unknown | 597.49 | -348.64 | 946.13 | Yes | N/A | N/A | 2023-08-29 | 2023-09-12 | 15 | 11 | 2023-09-12 | 2023-09-13 | 2 | 2 | 2023-09-13 | 2023-10-12 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-13 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-20 | 8 | 6 | 2023-10-20 | 2023-10-20 | 1 | 1 | 47 | 35 | 11 | 9 | 58 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2029.15 | 458.32 | Unknown | Unknown | Unknown | 1570.83 | 3981 | 1683.03 | 2029.15 | -346.12 | Yes | N/A | N/A | 2024-09-26 | 2024-10-01 | 6 | 4 | 2024-10-01 | 2024-10-14 | 14 | 10 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-13 | 1 | 1 | 6 | 4 | 15 | 11 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 24.05 | 24.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | -668 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-29 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1277.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-21 | 2 | 2 | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-26 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-06-30 | 5 | 3 | 2025-06-30 | 2025-06-30 | 1 | 1 | 31 | 23 | 15 | 11 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-16 | -101 | -74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-14 | 2023-05-23 | IOU Designed & Installed | N/A | No | N/A | 944.01 | 297.2 | Unknown | 111.71 | 13.16 | 521.94 | Unknown | 1859.78 | 944.01 | 915.77 | Yes | N/A | N/A | 2023-04-14 | 2023-04-14 | 1 | 1 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-05-23 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-08-07 | 77 | 55 | 2023-08-07 | 2023-08-07 | 1 | 1 | 41 | 29 | 78 | 56 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-29 | 328 | 235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 37865.3 | 8600.33 | Unknown | Unknown | -9372.56 | 38637.53 | Unknown | 23278.43 | 37865.3 | -14586.87 | Yes | N/A | N/A | 2023-05-31 | 2023-11-29 | 183 | 131 | 2023-11-29 | 2023-12-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-11 | 4 | 2 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-20 | 16 | 12 | 2024-02-20 | 2024-02-20 | 1 | 1 | 183 | 131 | 34 | 24 | 217 | 155 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-04-14 | -167 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -98.09 | -36.85 | Unknown | Unknown | -889.62 | 828.38 | 15540 | 1730.26 | -98.09 | 1828.35 | Yes | N/A | N/A | 2023-03-28 | 2023-02-08 | Unknown | Unknown | 2023-02-08 | 2023-05-17 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2024-02-01 | 33 | 25 | 2023-05-17 | 2023-09-13 | 120 | 86 | Unknown | 2023-10-18 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-10-30 | Unknown | Unknown | 120 | 86 | 132 | 96 | 252 | 182 | Steps 2,3,5,6,7 | 260 | 186 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 331.05 | 331.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-15 | -564 | -403 | No | 2024-12-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-04 | 2025-02-14 | IOU Designed & Installed | N/A | Yes | 9 | 16.69 | Unknown | Unknown | Unknown | Unknown | 16.69 | 3981 | 1145.26 | 16.69 | 1128.57 | Yes | N/A | N/A | 2024-12-02 | 2024-12-11 | 10 | 8 | 2024-12-11 | 2024-12-04 | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-02-14 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-10 | 25 | 17 | 2025-03-10 | 2025-02-28 | Unknown | Unknown | 83 | 61 | 25 | 17 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1206.28 | -23.61 | Unknown | Unknown | Unknown | 1229.89 | 0 | 1076.84 | 1206.28 | -129.44 | Yes | N/A | N/A | 2023-12-14 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-01-18 | 112 | 80 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-10-04 | 1 | 1 | 0 | 0 | 113 | 81 | 113 | 81 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-03 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | 18.31 | Unknown | Unknown | Unknown | Unknown | 18.31 | Unknown | 1576.73 | 18.31 | 1558.42 | Yes | N/A | N/A | 2024-05-30 | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-07-03 | 69 | 49 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-08-05 | 32 | 22 | 2024-08-05 | 2024-08-05 | 1 | 1 | 3 | 3 | 102 | 72 | 105 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-28 | -144 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | 527.7 | -15.5 | Unknown | Unknown | Unknown | 543.2 | 3981 | 1089.34 | 527.7 | 561.64 | Yes | N/A | N/A | 2023-11-10 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | 2023-11-10 | 187 | 135 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-06 | 22 | 16 | 2023-12-06 | 2023-12-06 | 1 | 1 | 6 | 4 | 210 | 152 | 216 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | 36 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 400.54 | -8.05 | Unknown | Unknown | Unknown | 408.59 | 3981 | 1362.26 | 400.54 | 961.72 | Yes | N/A | N/A | 2024-03-20 | 2024-03-22 | 3 | 3 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2024-11-08 | Unknown | Unknown | 3 | 3 | 0 | 0 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 126.05 | 126.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 1308.02 | 252.46 | Unknown | 36.6 | 8.54 | 1010.42 | 3981 | 743.44 | 1308.02 | -564.58 | Yes | N/A | N/A | 2024-01-17 | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2024-01-25 | 112 | 80 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-03-15 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-18 | 4 | 2 | 2024-03-18 | 2024-03-18 | 1 | 1 | 51 | 37 | 117 | 83 | 168 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 1577.59 | -31.16 | Unknown | Unknown | Unknown | 1608.75 | 3981 | 1683.03 | 1577.59 | 105.44 | Yes | N/A | N/A | 2024-10-16 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-16 | 2 | 2 | 2024-10-16 | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-19 | 35 | 25 | 2024-10-16 | 2024-10-23 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-12-04 | 43 | 31 | 2024-12-04 | 2024-12-04 | 1 | 1 | 8 | 6 | 81 | 59 | 89 | 65 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | Lemon Grove | LEMON GROVE | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-10-30 | 985 | 704 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 17554.05 | Unknown | Unknown | Unknown | 1771.45 | 15782.6 | Unknown | 2862.91 | 17554.05 | -14691.14 | Yes | N/A | N/A | 2023-12-13 | 2024-01-23 | 42 | 30 | 2024-01-23 | 2024-05-14 | 113 | 81 | 2024-01-22 | 2024-04-25 | 2 | 2 | 2024-04-26 | 2024-05-29 | 8 | 4 | 2024-05-23 | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-06 | 15 | 11 | 2024-06-17 | 2024-07-11 | 25 | 19 | 2024-07-11 | 2024-07-11 | 1 | 1 | 44 | 32 | 162 | 116 | 206 | 148 | Steps 2,3,5,6,7 | 119 | 85 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 178.1 | 178.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | -98 | -71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1914.79 | -8.11 | Unknown | Unknown | Unknown | 1922.9 | 3981 | 612.54 | 1914.79 | -1302.25 | Yes | N/A | N/A | 2024-01-11 | 2024-01-12 | 2 | 2 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | -683 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 426.45 | -8.57 | Unknown | Unknown | Unknown | 435.02 | Unknown | 1713.1 | 426.45 | 1286.65 | Yes | N/A | N/A | 2025-04-28 | 2025-05-02 | 5 | 5 | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 5 | 5 | 2 | 2 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -108 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2169.76 | Unknown | Unknown | Unknown | -2767 | 597.24 | 146799 | Not available | -2169.76 | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-02-27 | Unknown | Unknown | 2023-02-27 | 2023-11-22 | 269 | 193 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-07-24 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-27 | Unknown | Unknown | 246 | 176 | 269 | 193 | 515 | 369 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -563 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-10-16 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 2730.72 | 574.42 | Unknown | 747.15 | Unknown | 1409.15 | Unknown | 3528.38 | 2730.72 | 797.66 | Yes | N/A | N/A | 2024-06-17 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-18 | 42 | 30 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2024-10-16 | 1 | 1 | 1 | 1 | 44 | 32 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Fallbrook | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | 709 | 508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-03-07 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 20801.75 | 3066.22 | Unknown | Unknown | -335.18 | 18070.71 | 7294.1 | 10811.46 | 20801.75 | -9990.29 | Yes | N/A | N/A | 2023-01-10 | 2023-02-22 | 44 | 32 | 2023-02-22 | 2024-01-31 | 344 | 246 | 2023-04-17 | 2024-01-03 | 262 | 188 | 2024-01-08 | 2024-01-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-10-10 | 43 | 31 | 2024-10-10 | 2024-10-10 | 1 | 1 | 306 | 220 | 390 | 280 | 696 | 500 | Steps 2,3,5,6,7 | 289 | 207 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-11 | 22 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.67 | -13.16 | Unknown | Unknown | 8.51 | 6.32 | 3981 | 1935.77 | 1.67 | 1934.1 | Yes | N/A | N/A | 2023-03-28 | 2023-04-24 | 28 | 20 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 28 | 20 | 1 | 1 | 29 | 21 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 4790.18 | 875.49 | Unknown | 94.72 | 14.12 | 3805.85 | 3981 | 779.89 | 4790.18 | -4010.29 | Yes | N/A | N/A | 2024-04-16 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-04-30 | 55 | 39 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-09-06 | 130 | 94 | Unknown | 2024-08-07 | Unknown | Unknown | 2024-09-06 | 2024-09-12 | 7 | 5 | 2024-09-12 | 2025-01-23 | 134 | 96 | 130 | 94 | 196 | 140 | 326 | 234 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34755 | 34755 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-29 | -555 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-12 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 1362.29 | -37.42 | Unknown | Unknown | Unknown | 1399.71 | 3981 | 1103.51 | 1362.29 | -258.78 | Yes | N/A | N/A | 2024-01-12 | 2024-02-07 | 27 | 19 | 2024-02-07 | 2024-02-12 | 6 | 4 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-05-15 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-05-23 | 9 | 7 | 2024-05-23 | 2024-05-23 | 1 | 1 | 121 | 87 | 16 | 12 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-06-03 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 953.01 | Unknown | Unknown | Unknown | Unknown | 953.01 | 3981 | 1249.55 | 953.01 | 296.54 | Yes | N/A | N/A | 2024-05-23 | 2024-05-28 | 6 | 4 | 2024-05-28 | 2024-06-03 | 7 | 5 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-27 | 49 | 35 | Unknown | 2024-08-23 | Unknown | Unknown | 2024-08-27 | 2024-09-09 | 14 | 10 | 2024-09-09 | 2024-09-09 | 1 | 1 | 55 | 39 | 22 | 16 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | 128.05 | 128.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -437 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-04-23 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 1750.25 | Unknown | Unknown | Unknown | Unknown | 1750.25 | Unknown | 595.44 | 1750.25 | -1154.81 | Yes | N/A | N/A | 2024-04-19 | 2024-04-23 | 5 | 3 | 2024-04-23 | 2024-07-02 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-09-18 | 73 | 53 | 2024-09-18 | 2024-09-18 | 1 | 1 | 5 | 3 | 145 | 105 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 682 | 682 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | 68 | 49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | -4.74 | -4.79 | Unknown | Unknown | Unknown | 0.05 | Unknown | 158.14 | -4.74 | 162.88 | Yes | N/A | N/A | 2023-09-25 | 2023-10-12 | 18 | 14 | 2023-10-12 | 2023-10-26 | 15 | 11 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2024-02-21 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-14 | 23 | 17 | 2024-03-14 | 2024-03-14 | 1 | 1 | 137 | 99 | 39 | 29 | 176 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 123 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 2850.27 | 590.35 | Unknown | Unknown | Unknown | 2259.92 | 3885 | 1122.66 | 2850.27 | -1727.61 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-12-12 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-02 | 22 | 16 | 2024-01-02 | 2024-01-02 | 1 | 1 | 135 | 97 | 24 | 18 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A